## G1 - Investment
SCOTTISH WATER
2019
ANNUAL RETURN
SECTION G: INVESTMENT MONITORING
Table G1: Summary - Investment
|  |  |  | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90
Line | Description | Units | Field | Report Year | Actual Report Year | Actual Report Year | Actual Report Year | Actual Report Year | Forecast Report Year | Forecast Report Year | Forecast Post | Forecast Total Financed in
Ref. |  |  | Type
|  |  |  | Pre 2015 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021 | SR15-21
Capital Maintenance
G1.01 | Water Service Infrastructure | £m | I | 0 | 81.0428 | 115.1667 | 144.5808 | 92.0979 | 61.0999 | 63.933 | 37.8372 | 595.7584
G1.02 | Water Service Non-Infrastructure | £m | I | 0 | 71.6075 | 75.6482 | 80.2275 | 103.9058 | 95.7272 | 94.7679 | 0 | 521.8841
G1.03 | Wastewater Service Infrastructure | £m | I | 0 | 31.3638 | 38.547 | 38.2143 | 69.8467 | 57.314 | 56.6766 | 0 | 291.9625
G1.04 | Wastewater Service Non-Infrastructure | £m | I | 0 | 49.0528 | 58.4241 | 72.3091 | 64.9018 | 66.1933 | 64.8041 | 0 | 375.6851
G1.05 | Management and General | £m | I | 0 | 28.1693 | 52.8718 | 61.7075 | 53.5219 | 57.0057 | 112.0348 | 0 | 365.311
G1.06 | Total Capital Maintenance | £m | C | 0 | 261.2363 | 340.6578 | 397.0392 | 384.2741 | 337.3402 | 392.2163 | 37.8372 | 2150.6011
Growth
G1.07 | Growth in the Water Network | £m | I | 0 | 3.3998 | 7.1441 | 7.8634 | 9.2587 | 15.7338 | 37.1865 | 4.9836 | 85.5699
G1.08 | Growth in the Wastewater Network | £m | I | 0 | 8.8741 | 8.2268 | 13.1059 | 34.7001 | 39.3028 | 38.6901 | 2.312e-05 | 142.8997
G1.09 | Water Reasonable Cost Contributions | £m | I | 0 | 8.1987 | 7.2182 | 6.7422 | 10.4484 | 8.876 | 10.339 | 0 | 51.8226
G1.10 | Wastewater Reasonable Cost Contributions | £m | I | 0 | 8.6536 | 10.4298 | 9.8565 | 18.229 | 9.4171 | 11.6728 | 0 | 68.2588
G1.11 | Service Relocations Water | £m | I | 0 | 15.0386 | 12.4053 | 9.3689 | 7.816 | 10.6711 | 1.7131 | 0 | 57.0131
G1.12 | Service Relocations Wastewater | £m | I | 0 | 4.8054 | 4.9606 | 3.4735 | 1.8201 | 4.5218 | 3.4733 | 0 | 23.0548
G1.13 | Total Growth Expenditure | £m | C | 0 | 48.9703 | 50.3848 | 50.4104 | 82.2724 | 88.5226 | 103.0748 | 4.9836 | 428.6189
Q&SIV Enhancement Expenditure
G1.14 | Improving drinking water quality compliance and reliability | £m | I | 9.2909 | 18.1377 | 46.4909 | 57.2492 | 66.3757 | 121.7355 | 54.1853 | 143.7348 | 517.1998
G1.15 | Improving drinking water availability and resilience of service | £m | I | 3.3164 | 10.9888 | 14.5594 | 18.0363 | 32.3506 | 35.8153 | 15.1799 | 33.3764 | 163.6231
G1.16 | Protecting and enhancing the environment | £m | I | 8.9269 | 15.1313 | 25.5275 | 41.472 | 31.3314 | 39.4786 | 65.2991 | 95.7509 | 322.9176
G1.17 | Reducing flooding and pollution from sewers | £m | I | 21.1556 | 24.0514 | 14.8646 | 15.2367 | 16.0488 | 39.2695 | 54.0079 | 18.8166 | 203.4509
G1.18 | Improving the customer experience | £m | I | 0.9286 | 1.8363 | 6.0951 | 5.2788 | 4.7796 | 8.1588 | 12.7417 | 3.4253 | 43.2442
G1.19 | Climate Change | £m | I | 0.23491 | 0.15567 | 0.41575 | 0.34954 | 0.039189 | 0.40926 | 1.3549 | 0.14778 | 3.107
G1.20 | Reducing long term cost of service | £m | I | 2.9412 | 4.7829 | 4.445 | 2.9189 | 1.6093 | 2.3167 | 4.6481 | 1.6293 | 25.2914
G1.21 | Total Q&SIV Enhancement Expenditure | £m | C | 46.7946 | 75.084 | 112.3982 | 140.5414 | 152.5344 | 247.1836 | 207.4168 | 296.881 | 1278.8341
Q&SIV Enhancement - IR18
G1.22 | Total remaining IR18 Unallocated Investment | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Q&SIIIa & Q&SIIIb Completion Expenditure
G1.23 | Total OMG180 Completion Expenditure | £m | I | 0 | 72.4573 | 96.2252 | 34.8229 | 29.7012 | 26.1381 | 20.1693 | 7.4132 | 286.9271
G1.24 | Total Non OMG180 Completion Expenditure | £m | I | 0 | 3.9662 | 27.0445 | 23.848 | 11.151 | 0.81558 | 0.96922 | 0.054192 | 67.8487
G1.25 | Total Completion Expenditure | £m | C | 0 | 76.4235 | 123.2697 | 58.6708 | 40.8522 | 26.9536 | 21.1385 | 7.4674 | 354.7758
Q&SV Early Start
G1.26 | Total Q&SV Early Start Enhancement Expenditure | £m | I | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 0 | 30
Total Additional Operating Expenditure
G1.27 | Additional Operating Expenditure from Capital Maintenance | £m | I | 0 | 0.97566 | 0.75877 | 0.41055 | 0.43433 | 1.9311 | 0.66625 | 0.58705 | 5.7637
G1.28 | Additional Operating Expenditure from Water Growth | £m | I | 0 | 0 | 0.025756 | 0.0040854 | 0.0025373 | 0.030806 | 0.013785 | 0 | 0.07697
G1.29 | Additional Operating Expenditure from Wastewater Growth | £m | I | 0 | 0 | 0 | 0 | 0 | 0.14871 | 0.26522 | 0.059603 | 0.47354
G1.30 | Additional Operating Expenditure from Improving drinking water quality compliance and reliability | £m | I | 0 | 0 | 0 | 0.008662 | 0.07916 | -0.019303 | 0.21685 | 0.10004 | 0.3854
G1.31 | Additional Operating Expenditure from Improving drinking water availability and resilience of service | £m | I | 0 | 0 | 0 | 0 | 0 | 0.028756 | 0.018121 | 0.0021978 | 0.049075
G1.32 | Additional Operating Expenditure from Protecting and enhancing the environment | £m | I | 0 | 0 | 0 | 0 | 0.207 | 0.011306 | 0.016388 | 0.012367 | 0.24706
G1.33 | Additional Operating Expenditure from Reducing flooding and pollution from sewers | £m | I | 0 | 0.0054 | 0 | 0 | 0 | 0.0037021 | 0.010765 | 0 | 0.019867
G1.34 | Additional Operating Expenditure from Improving the customer experience | £m | I | 0 | 0 | 0 | 0 | 0 | -0.0018715 | -0.0011037 | 0 | -0.0029752
G1.35 | Additional Operating Expenditure from Climate Change | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1.36 | Additional Operating Expenditure from Reducing long term cost of service | £m | I | 0 | 0 | 0 | 0.11 | 0 | 0 | -0.080645 | -0.91935 | -0.89
G1.37 | Additional Operating Expenditure from IR18 | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1.38 | Additional Operating Expenditure from Completion | £m | I | 0 | 0.20123 | 0.63447 | 0.23556 | 0.25855 | 0.14031 | 0.23706 | 0.057404 | 1.7646
G1.39 | Additional Operating Expenditure from Q&SV Early Start | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1.40 | Total Additional Operating Expenditure | £m | C | 0 | 1.1823 | 1.419 | 0.76886 | 0.98157 | 2.2735 | 1.3627 | -0.1007 | 7.8872
Grants and Capital Contributions
G1.41 | Grants for infrastructure assets | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1.42 | Grants for non-infrastructure assets | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1.43 | Contributions to infrastructure assets | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1.44 | Contributions to non-infrastructure assets | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G1.45 | Contributions to service relocations - Water | £m | I | 0 | -10.7902 | -6.5168 | -7.3147 | -4.6331 | -6.4554 | -6.4554 | 0 | -42.1657
G1.46 | Contributions to service relocations - Wastewater | £m | I | 0 | -5.5586 | -3.3571 | -3.7682 | -1.7827 | -2.4838 | -2.4838 | 0 | -19.4343
G1.47 | “Infrastructure charge" contributions for infrastructure assets | £m | I | 0 | -1.7095 | -14.871 | -7.0921 | -20.084 | -14.7217 | -14.7217 | 0 | -73.2
G1.48 | Total Capital Contributions | £m | C | 0 | -18.0583 | -24.745 | -18.1751 | -26.4998 | -23.6609 | -23.6609 | 0 | -134.8
Expenditure Totals
G1.49 | Capital Maintenance Expenditure | £m | C | 0 | 261.2363 | 340.6578 | 397.0392 | 384.2741 | 337.3402 | 392.2163 | 37.8372 | 2150.6011
G1.50 | Growth Expenditure | £m | C | 0 | 48.9703 | 50.3848 | 50.4104 | 82.2724 | 88.5226 | 103.0748 | 4.9836 | 428.6189
G1.51 | Q&SIV Enhancement Expenditure | £m | C | 46.7946 | 75.084 | 112.3982 | 140.5414 | 152.5344 | 247.1836 | 207.4168 | 296.881 | 1278.8341
G1.52 | Q&SIIIa & Q&SIIIb Completion Expenditure | £m | C | 0 | 76.4235 | 123.2697 | 58.6708 | 40.8522 | 26.9536 | 21.1385 | 7.4674 | 354.7758
G1.53 | Q&SV Early Start Expenditure | £m | C | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 0 | 30
G1.54 | Gross Capital Investment | £m | C | 46.7946 | 461.7141 | 626.7105 | 646.6619 | 659.9331 | 710 | 743.8464 | 347.1692 | 4242.8298
G1.55 | Total Capital Contributions | £m | C | 0 | -18.0583 | -24.745 | -18.1751 | -26.4998 | -23.6609 | -23.6609 | 0 | -134.8
G1.56 | Net Capital Investment | £m | C | 46.7946 | 443.6558 | 601.9656 | 628.4868 | 633.4333 | 686.3391 | 720.1855 | 347.1692 | 4108.0298
G1.57 | Total Additional Operating Expenditure | £m | C | 0 | 1.1823 | 1.419 | 0.76886 | 0.98157 | 2.2735 | 1.3627 | -0.1007 | 7.8872
Prepared by: …………………………………………….. |  |  | Date: ……………………
Checked by: …………………………………………….. |  |  | Date: ……………………
Authorised by: |  |  | Date: 14th June 2019

## G2 - Q&SIV Outputs
SCOTTISH WATER
2019
ANNUAL RETURN
SECTION G: INVESTMENT MONITORING
Table G2: Summary - Outputs
|  |  |  | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90
Line | Description | Units | Field | Report Year | Actual Report Year | Actual Report Year | Actual Report Year | Actual Report Year | Forecast Report Year | Forecast Report Year | Forecast Post | Forecast Total Financed in
Ref. |  |  | Type
|  |  |  | Pre 2016 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021 | SR15-21
Growth
G2.1 | Strategic Capacity - Water Treatment [WG1] | Pe | I | 0 | 0 | 14509 | 0 | 0 | 388 | 0 | 0 | 14897
G2.2 | Strategic Capacity - Wastewater Treatment [SG1] | Pe | I | 0 | 1351 | 792 | 3182 | 677 | 28200 | 10699 | 0 | 44901
G2.3 | Strategic Water Network Capacity (Infrastructure Charge) [WG5 ] | Pe | I | 0 | 1920 | 12758 | 10705 | 2058 | 4050 | 1101 | 0 | 32592
G2.4 | Strategic Wastewater Network Capacity (Infrastructure Charge) [SG5 ] | Pe | I | 0 | 0 | 0 | 0 | 1 | 681 | 0 | 0 | 682
Q&SIV Enhancements - Drinking Water Quality
G2.5 | Number of water treatment works improved | No. | I | 0 | 0 | 1 | 3 | 6 | 5 | 7 | 8 | 22
G2.6 | Number of zones made compliant with iron & manganese standards | No. | I | 0 | 0 | 0 | 4 | 34 | 17 | 10 | 7 | 65
G2.7 | Number of enhancements to improve reliability of supply (catchments and treatment) | No. | I | 0 | 2 | 1 | 5 | 4 | 11 | 19 | 12 | 42
G2.8 | Number of enhancements to improve reliability of supply (networks and storage) | No. | I | 0 | 1 | 10 | 2 | 9 | 37 | 25 | 3 | 84
G2.9 | Distribution mains cleaned (km) | Km | I | 0 | 0 | 0 | 106.06 | 458.24 | 1247.536 | 3082.3947 | 1462.8968 | 4894.2307
G2.10 | Water supply resilience strategy and improvements made | No. | I | 0 | 4 | 3 | 1 | 4 | 2 | 3 | 2 | 17
G2.11 | Number of zones with improved security of supply (SOSI) | No. | I | 0 | 1 | 0 | 0 | 3 | 2 | 1 | 4 | 7
G2.12 | Number of security measures and improvements to the infrastructure of critical reservoirs | No. | I | 0 | 3 | 74 | 195 | 188 | 104 | 128 | 1 | 692
G2.13 | Number of water quality etc studies to inform future periods | No. | I | 0 | 12 | 74 | 134 | 43 | 84 | 15 | 0 | 362
G2.14 | 2010-15 outputs planned to complete in the 2015-21 period | No. | I | 0 | 2 | 4 | 2 | 5 | 4 | 4 | 1 | 21
Q&SIV Enhancements - Environment
G2.15 | Number of WWTWs improved to meet UWWTD | No. | I | 1 | 5 | 1 | 8 | 6 | 2 | 3 | 0 | 26
G2.16 | Number of waste water networks improved to meet UWWTD | No. | I | 0 | 4 | 13 | 5 | 7 | 13 | 8 | 9 | 50
G2.17 | Number of improvements required to meet UWWTD - Glasgow completion | No. | I | 0 | 24 | 12 | 15 | 10 | 8 | 16 | 0 | 85
G2.18 | Number of improvements required to meet the Water Framework Directive | No. | I | 0 | 1 | 0 | 0 | 1 | 0 | 10 | 18 | 12
G2.19 | Number of revised Bathing Waters Directive studies | No. | I | 0 | 0 | 0 | 8 | 0 | 1 | 2 | 1 | 11
G2.20 | Number of studies and catchments to meet the requirements of the Flood Risk Management Act | No. | I | 0 | 0 | 13 | 52 | 75 | 61 | 17 | 0 | 218
G2.21 | Number of environmental studies to inform future periods | No. | I | 0 | 0 | 5 | 28 | 33 | 50 | 12 | 2 | 128
G2.22 | Number of improvements required by the Compliance Assessment Scheme; odour reduction and sludge management | No. | I | 0 | 10 | 9 | 8 | 4 | 7 | 56 | 2 | 94
G2.23 | 2010-15 outputs planned to complete in the 2015-21 period | No. | I | 0 | 7 | 1 | 4 | 1 | 1 | 0 | 1 | 14
G2.24 | Number of improvements to dams to meet the requirements of the Flood Risk Management Act | No. | I | 0 | 6 | 4 | 7 | 19 | 17 | 1 | 0 | 54
Q&SIV Enhancements - Supporting Economic Development
G2.25 | Number of climate change vulnerability assessments | No. | I | 0 | 4 | 50 | 3 | 2 | 57 | 7 | 0 | 123
G2.26 | Improvements in renewable power and energy efficiency | Gwh | I | 0.52 | 1.12 | 7.65 | 3.17 | 5.04 | 0 | 0 | 0 | 17.5
Q&SIV Enhancements - Output Monitoring Group - Annual Measures
G2.27 | Number of lead communication pipes replaced | No. | I | 0 | 1343 | 1350 | 1169 | 1551 | 0 | 0 | 0 | 5413
G2.28 | Assessment of levels of pressure for all customers and number of improvements if low levels of service are found | No. | I | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
G2.29 | Improve response times to reduce average duration of short term interruptions to supply | No. | I | 0 | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC
G2.30 | Number of water efficiency advice and water saving packs provided (to 2% of customer base) | No. | I | 0 | 0 | 233 | 6684 | 18362 |  |  |  | 25279
G2.31 | Number of internal flooding improvements | No. | I | 0 | 47 | 39 | 54 | 101 |  |  |  | 241
G2.32 | Number of internal flooding improvements - completion programme | No. | I | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
G2.33 | Number of external flooding investigations and improvements | No. | I | 0 | 29 | 22 | 49 | 45 |  |  |  | 145
G2.34 | % of customers covered by flood resilience assessments | No. | I | 0 | n/a | 66.4% | 66.4% | 66.4% | TBC | TBC | TBC | TBC
G2.35 | Number of surface water management investigations | No. | I | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
G2.36 | Number of connections for new households and businesses | No. | I | 0 | 19803 | 21993 | 23914 | 24459 |  |  |  | 90169
G2.37 | New waste water capacity for 58,000 people | No. | I | 0 | 1351 | 792 | 3182 | 678 | 28881 | 10699 | 0 | 45583
G2.38 | Number of developer constructed assets (Part 2&3) adopted | No. | I | 0 | 25 | 416 | 838 | 834 |  |  |  | 2113
G2.39 | Number of first time non domestic meters installed | No. | I | 0 | 4069 | 3313 | 2586 | 2825 |  |  |  | 12793
G2.40 | Number of statutory requirements to relocate services for transport infrastructure projects | No. | I | 0 | 77 | 59 | 60 | 40 |  |  |  | 236
G2.41 | Improved contact management and proactive communication | No. | I | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
G2.42 | Number of wholesale meter accuracy improvements | No. | I | 0 | 7729 | 10441 | 13868 | 15562 | 0 | 0 | 0 | 47600
G2.43 | Number of Strategic Mains Diversions | No. | I | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2 | 3
Q&SIIIa & Q&SIIIb Delivery projects
G2.44 | Q&SIIIa projects remaining | No. | I | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
G2.45 | Q&SIIIb projects remaining | No. | I | 36 | 14 | 8 | 3 | 2 | 0 | 0 | 0
G2.46 | Q&S3b Km of Mains Rehabilitated remaining | Km | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prepared by: …………………………………………….. |  |  | Date: ……………………
Checked by: …………………………………………….. |  |  | Date: ……………………
Authorised by: |  |  | Date: 14th June 2019

## G3 -Serviceability
SCOTTISH WATER
2019
ANNUAL RETURN
SECTION G: INVESTMENT MONITORING
Table G3: Monitoring Serviceability
|  |  |  | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 110 | 120 | 130 | 140 | 150 | 160 | 170
Line | Description | Units | Field | Ministerial Target 2015-21 | Baseline Delivery Plan Target Mar 2015 | Actual March 2015 | Delivery Plan Target Mar 2016 | Actual March 2016 | Delivery Plan Target Mar 2017 | Actual March 2017 | Delivery Plan Target Mar 2018 | Actual March 2018 | Delivery Plan Target Mar 2019 | Actual March 2019 | Delivery Plan Target Mar 2020 | Forecast March 2020 | Delivery Plan Target Mar 2021 | Forecast March 2021 | Delivery Plan Target Post Mar 2021 | Forecast Post March 2021
Ref. |  |  | Type
Drinking Water Quality Indicators
G3.1 | Number of failing zones for iron | Nr | I | n/a | n/a | 16 | n/a | 21 | n/a | 18 | n/a | 25 | n/a | 29 | n/a |  | n/a
G3.2 | Number of failing zones for manganese | Nr | I | n/a | n/a | 14 | n/a | 11 | n/a | 7 | n/a | 9 | n/a | 15 | n/a |  | n/a
G3.3 | Number of microbiological failures at WTWs | Nr | I | n/a | 38 | 40 | n/a | 16 | n/a | 33 | n/a | 22 | n/a | 24 | n/a |  | n/a
G3.4 | Number of Customer Contacts relating to Taste | Nr | I | 5000 | n/a | 2671 | 5000 | 2691 | 5000 | 2526 | 5000 | 2503 | 5000 | 2224 | 5000 |  | 5000
G3.5 | Number of Customer Contacts relating to Discolouration | Nr | I | 10000 | n/a | 9211 | 10000 | 6325 | 10000 | 5973 | 10000 | 4744 | 10000 | 6101 | 10000 |  | 10000
Environment Serviceability Indicators
G3.6 | Number of failing WWTW | Nr | I | 5 | 18 | 3 | 5 | 6 | 5 | 4 | 5 | 0 | 5 | 2 | 5 |  | 5
G3.7 | Number of sludge treatment facilities improved to comply with safe sludge matrix | Nr | I | n/a | 2 | 2 | n/a | 8 | n/a | 8 | 8 | 9 | 8 | 11 | 8 |  | 8
G3.8 | Maximum number of UIDs | Nr | I | n/a | n/a | 791 | n/a | 761 | n/a | 738 | n/a | 720 | n/a | 704 | n/a |  | n/a
G3.9 | Number of pollution incidents | Nr | I | 330 | 548 | 249 | 330 | 260 | 330 | 239 | 330 | 193 | 330 | 227 | 330 |  | 330
G3.10 | Total number of Pollution incidents (sewerage) | Nr | I | n/a | n/a | 249 | 329 | 257 | 329 | 238 | 329 | 191 | 329 | 219 | 329 |  | 329
G3.11 | Serious pollution incidents (sewerage) Cat 1 & 2 | Nr | I | n/a | n/a | 8 | 13 | 10 | 13 | 12 | 13 | 5 | 13 | 9 | 13 |  | 13
G3.12 | Serious pollution incidents (water) Cat 1 | Nr | I | n/a | n/a | 1 | 1 | 3 | 1 | 1 | 1 | 0 | 1 | 0 | 1 |  | 1
G3.13 | Discharge permit compliance | % | I | n/a | n/a | 99.49% | n/a | 98.98% | n/a | 99.32% | n/a | 100% | n/a | 99.67% | n/a |  | n/a
G3.14 | Satisfactory sludge disposal | % | I | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100%
G3.15 | Greenhouse gas (GHG) emissions (ktCO2e) | ktCO2e | I | n/a | n/a | 379* | n/a | 404* | n/a | 352 | n/a | 315 | n/a | 272 | n/a |  | n/a
Customer Service Serviceability Indicators
G3.16 | Properties on the low pressure register | Nr | I | 100 | 240 | 46 | 100 | 47 | 100 | 45 | 100 | 45 | 100 | 51 | 100 |  | 100
G3.17 | Properties with unplanned interruptions to supply > 12 hrs | Nr | I | <1,000 | 684 | 563 | <1,000 | 716 | <1,000 | 648 | <1,000 | 552 | <1,000 | 357 | <1,000 |  | <1,000
G3.17a | Properties with unplanned interruptions to supply > 6 hrs | Nr | I | 13000 | n/a | n/a | 13000 | 6434 | 13000 | 6027 | 13000 | 6393 | 13000 | 4989 | 13000 |  | 13000
G3.18 | Number of hours lost due to water supply interruptions for three hours or longer | Hrs/prop | I | n/a | n/a | 0.2763 | n/a | 0.26106 | n/a | 0.2607 | n/a | 0.386 | n/a | 0.391 | n/a |  | n/a
G3.19 | Bursts per 1,000km of mains | Nr | I | n/a | 188 | 160 | n/a | 140.2219 | n/a | 137.3576 | n/a | 157 | n/a | 172 | n/a |  | n/a
G3.20 | Properties at risk of internal sewer flooding | Nr | I | 370 | 341 | 302 | 370 | 334 | 370 | 315/381 | >370 | 373 | 370 | 307 | 370 |  | 370
G3.21 | Properties internally flooded due to other causes | Nr | I | n/a | 1270 | 367 | n/a | 389 | n/a | 328 | n/a | 346 | n/a | 369 | n/a |  | n/a
G3.22 | Properties internally flooded due to overloaded sewers | Nr | I | n/a | n/a | 54 | n/a | 95 | n/a | 121 | n/a | 63 | n/a | 129 | n/a |  | n/a
G3.23 | Incidents of internal sewer flooding for properties that have flooded within the last ten years | Nr | I | n/a | n/a | 156 | n/a | 243 | n/a | 241 | n/a | 202 | n/a | 125 | n/a |  | n/a
G3.24 | Properties at risk of external sewer flooding | Nr | I | <5,000 | n/a | 3708 | <5,000 | 3693 | <5,000 | 3699 | <5,000 | 3701 | <5,000 | 3698 | <5,000 |  | <5,000
G3.25 | Incidents of external sewer flooding due to other causes | Nr | I | 13000 | n/a | 10768 | 13000 | 9981 | 13000 | 8565 | 13000 | 7498 | 13000 | 8169 | 13000 |  | 13000
G3.26 | Incidents of external sewer flooding due to overloaded sewers | Nr | I | 400 | n/a | 227 | 400 | 349 | 400 | 159 | 400 | 120 | 400 | 116 | 400 |  | 400
G3.27 | The Overall Satisfaction level (from the customer service questionnaire) | % | I | n/a | >78% | 92% | n/a | 89.51% | n/a | 90.7% | n/a | 91.5% | n/a | 92.32% | n/a |  | n/a
G3.28 | The maximum number of 'second tier' complaints referred to Scottish Public Services Ombudsman | Nr | I | n/a | <121 | 4 | n/a | 1 | n/a | 2 | n/a | 3 | n/a | 0 | n/a |  | n/a
G3.29 | The number of telephone contacts relating to drinking water quality | Nr | I | n/a | <24,168 | 14150 | n/a | 11667 | n/a | 10563 | n/a | 9309 | n/a | 10193 | n/a |  | n/a
G3.30 | The Overall Performance Assessment (OPA) Score (In Year Value) | Nr | I | 380-385 | 380 | 400 | 380 | 393 | 381 | 398.38 | 382 | 406 | 383 | 403 | 384 |  | 385
G3.31 | The Overall Performance Assessment (OPA) Score (Period Average) | Nr | I | 382.5 | n/a | 370 | 382.5 | 393 | 382.5 | 396.16 | 382.5 | 399 | 382.5 | 400 | 382.5 |  | 382.5
G3.32 | The average annual level of leakage | Ml/d | I | 575 | 600 | 543.993 | 575 | 499.63 | 575 | 494.7575 | 575 | 491.979 | 575 | 480.01 | 575 |  | 575
G3.33 | Household Customer Experience Measure (HCEM) | Nr | I | >82.60 | n/a | 82.6 | >82.60 | 84.32 | >82.60 | 85.88 | >82.60 | 86.36 | >82.60 | 87.54 | >82.60 |  | >82.60
G3.34 | Non-Household Customer Experience Measure (nHHCEM) | Nr | I | n/a | n/a | n/a | n/a | n/a | n/a | 83.92 | n/a | 77.5 | n/a | 81.74 | n/a |  | n/a
G3.35 | High Esteem Test | % | I | n/a | n/a | n/a | n/a | 78.6% | n/a | 76.4% | n/a | 76.4% | n/a | 78.1% | n/a |  | n/a
G3.36 | Wholesale Key Performance Indicator (KPI's) | % | I | 95% | 95% | 92% | 95% | 90.96% | 95% | 91.92% | 95% | 97.6% | 95% | 98.4% | 95% |  | 95%
Resilience of supply
G3.37 | Water Available for Supply Index: % of Population covered by 1:40 level of Service | % | I | n/a | n/a | 88.9% | n/a | 87.3% | n/a | 86.8% | n/a | 86.74% | n/a | 86.71% | n/a |  | n/a
G3.38 | Water Available for Supply Index: % of Population covered by 1:100 level of Service | % | I | n/a | n/a | 71.5% | n/a | 77.3% | n/a | 82.2% | n/a | 70.1% | n/a | 71.35% | n/a |  | n/a
Asset Serviceability Indicators
G3.39 | Asset Health Index: Water resources |  |  | n/a | n/a | n/a | n/a | 0.617 | n/a | 0.617 | n/a | 0.6169 | n/a | 0.62531 | n/a |  | n/a
G3.40 | Asset Health Index: Water mains |  |  | n/a | n/a | n/a | n/a | 0.411 | n/a | 0.755 | n/a | 0.60513 | n/a | 0.61209 | n/a |  | n/a
G3.41 | Asset Health Index: Water treatment works |  |  | n/a | n/a | n/a | n/a | 0.782 | n/a | 0.786 | n/a | 0.72032 | n/a | 0.72013 | n/a |  | n/a
G3.42 | Asset Health Index: Water storage |  |  | n/a | n/a | n/a | n/a | 0.754 | n/a | 0.754 | n/a | 0.71587 | n/a | 0.71554 | n/a |  | n/a
G3.43 | Asset Health Index: Water pumping stations |  |  | n/a | n/a | n/a | n/a | 0.755 | n/a | 0.755 | n/a | 0.71791 | n/a | 0.71842 | n/a |  | n/a
G3.44 | Asset Health Index: Wastewater sewers |  |  | n/a | n/a | n/a | n/a | 0.816 | n/a | 0.813 | n/a | 0.82095 | n/a | 0.81663 | n/a |  | n/a
G3.45 | Asset Health Index: Wastewater sewer structures |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a
G3.46 | Asset Health Index: Wastewater sea outfalls |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a
G3.47 | Asset Health Index: Wastewater sewage pumping stations |  |  | n/a | n/a | n/a | n/a | 0.54 | n/a | 0.541 | n/a | 0.53223 | n/a | 0.53311 | n/a |  | n/a
G3.48 | Asset Health Index: Wastewater sewage treatment works |  |  | n/a | n/a | n/a | n/a | 0.551 | n/a | 0.551 | n/a | 0.54096 | n/a | 0.54095 | n/a |  | n/a
G3.49 | Asset Health Index: Wastewater sludge treatment facilities |  |  | n/a | n/a | n/a | n/a | 0.581 | n/a | 0.586 | n/a | 0.57878 | n/a | 0.58092 | n/a |  | n/a
Prepared by: …………………………………………….. |  |  | Date: ……………………
Checked by: …………………………………………….. |  |  | Date: ……………………
Authorised by: |  |  | Date: 14th June 2019

## G4 - OMD Inputs
SCOTTISH WATER
2019
ANNUAL RETURN
SECTION G: INVESTMENT MONITORING
Table G4: OMD Inputs including Q&SIIIa&b Project Sign-Offs
Q&SIV Enhancements - Drinking Water Quality - OMD Outputs
Line Ref. | Output | Drivers | Total No Outputs | OMG Programme Group | OMD Weighting % | Milestone Stage | Units | Field Type | 2015/16 |  |  |  | 2016/17 |  |  |  | 2017/18 |  |  |  | 2018/19 |  |  |  | 2019/20 |  |  |  | 2020/21 |  |  |  | 2015-21
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
G4.1 | Number of water treatment works improved | DW2, DW3B, DW3C, DW23, DW25, DW25P, DW25T | 30 | 1 | 11.9 | 1 | No. | I | 15 | 18 | 20 | 25 | 26 | 27 | 27 | 27 | 27 | 29 | 29 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
[6 empty] | 2 | Zones | I | 1 | 1 | 2 | 10 | 10 | 14 | 14 | 16 | 17 | 17 | 18 | 22 | 22 | 22 | 23 | 26 | 27 | 28 | 28 | 29 | 29 | 30 | 30 | 30 | 30
[6 empty] | 3 | Zones | I | 0 | 0 | 1 | 8 | 8 | 13 | 13 | 16 | 16 | 17 | 18 | 22 | 22 | 22 | 22 | 24 | 27 | 27 | 28 | 28 | 29 | 29 | 30 | 30 | 30
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 5 | 5 | 8 | 12 | 13 | 16 | 16 | 16 | 17 | 17 | 18 | 20 | 21 | 24 | 26 | 28 | 28
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 5 | 6 | 10 | 11 | 14 | 15 | 15 | 15 | 16 | 17 | 22 | 22
G4.2 | Number of zones made compliant with iron & manganese standards | DW5 | 72 | 2 | 6.4 | 1 | No. | I | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 65 | 65 | 65 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72
[6 empty] | 2 | Zones | I | 0 | 0 | 0 | 23 | 28 | 39 | 39 | 51 | 51 | 56 | 56 | 57 | 62 | 64 | 64 | 67 | 67 | 71 | 72 | 72 | 72 | 72 | 72 | 72 | 72
[6 empty] | 3 | Zones | I | 0 | 0 | 0 | 1 | 20 | 27 | 36 | 50 | 51 | 56 | 56 | 57 | 62 | 64 | 64 | 67 | 67 | 70 | 71 | 72 | 72 | 72 | 72 | 72 | 72
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 12 | 14 | 20 | 30 | 42 | 45 | 49 | 55 | 56 | 61 | 62 | 62 | 64 | 64 | 67 | 72 | 72
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 4 | 10 | 10 | 17 | 38 | 43 | 46 | 51 | 55 | 58 | 61 | 63 | 65 | 65
G4.3 | Number of enhancements to improve reliability of supply (catchments and treatment) | WR1, DW25P | 54 | 3 | 5.9 | 1 | No. | I | 4 | 5 | 6 | 17 | 21 | 23 | 28 | 36 | 38 | 40 | 41 | 47 | 49 | 49 | 51 | 51 | 52 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
[6 empty] | 2 | Zones | I | 1 | 1 | 1 | 7 | 8 | 9 | 10 | 15 | 16 | 16 | 20 | 28 | 28 | 30 | 34 | 35 | 40 | 43 | 45 | 49 | 51 | 53 | 54 | 54 | 54
[6 empty] | 3 | Zones | I | 0 | 0 | 0 | 6 | 8 | 9 | 9 | 15 | 16 | 16 | 17 | 24 | 25 | 29 | 30 | 33 | 39 | 40 | 41 | 44 | 47 | 49 | 53 | 54 | 54
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 3 | 3 | 3 | 4 | 5 | 7 | 9 | 9 | 13 | 13 | 13 | 16 | 16 | 18 | 21 | 26 | 31 | 32 | 34 | 44 | 47 | 47
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 4 | 6 | 8 | 8 | 8 | 9 | 12 | 15 | 16 | 18 | 23 | 31 | 32 | 34 | 42 | 42
G4.4 | Number of enhancements to improve reliability of supply (networks and storage) | DW25D, DW25P, DW25T | 87 | 4 | 2.1 | 1 | No. | I | 1 | 4 | 14 | 28 | 29 | 41 | 42 | 61 | 61 | 61 | 61 | 85 | 85 | 86 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87
[6 empty] | 2 | Zones | I | 0 | 0 | 2 | 9 | 10 | 19 | 19 | 28 | 28 | 29 | 39 | 63 | 63 | 64 | 66 | 81 | 83 | 84 | 86 | 87 | 87 | 87 | 87 | 87 | 87
[6 empty] | 3 |  | I | 0 | 0 | 1 | 8 | 10 | 18 | 18 | 21 | 27 | 27 | 28 | 48 | 62 | 64 | 65 | 66 | 68 | 84 | 85 | 87 | 87 | 87 | 87 | 87 | 87
[6 empty] | 4 |  | I | 0 | 0 | 1 | 3 | 4 | 10 | 11 | 12 | 12 | 13 | 14 | 15 | 23 | 34 | 36 | 37 | 44 | 55 | 60 | 66 | 68 | 83 | 85 | 86 | 86
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 1 | 3 | 10 | 10 | 11 | 11 | 12 | 13 | 13 | 14 | 14 | 22 | 22 | 41 | 44 | 54 | 59 | 65 | 67 | 83 | 84 | 84
G4.5 | Distribution mains cleaned (km) | DW25D, DW25FS | 6357.1274 | 5 | 5.8 | 1 | Km | I | 114.02 | 506.98 | 1499.85 | 2111.55 | 2329.65 | 3201.39 | 3529.23 | 3529.23 | 3529.23 | 3529.23 | 3529.23 | 3529.23 | 4206.8387 | 4335.8207 | 5630.9174 | 5630.9174 | 5630.9174 | 6357.1274 | 6357.1274 | 6357.1274 | 6357.1274 | 6357.1274 | 6357.1274 | 6357.1274 | 6357.1274
[6 empty] | 2 | Zones | I | 0 | 0 | 0 | 398.65 | 398.65 | 488.26 | 488.26 | 706.33 | 744.24 | 934.31 | 1590.93 | 1891.14 | 2635.64 | 3529.23 | 3778.73 | 3778.73 | 4335.8207 | 5420.8964 | 5630.9174 | 5630.9174 | 5630.9174 | 5798.7174 | 5798.7174 | 6357.1274 | 6357.1274
[6 empty] | 3 | Zones | I | 0 | 0 | 0 | 108.02 | 309.83 | 332.69 | 359.41 | 653.07 | 713 | 842.94 | 1025.55 | 1590.93 | 1912.72 | 2258.11 | 3374.24 | 3778.73 | 3778.73 | 4335.8207 | 5420.8964 | 5630.9174 | 5630.9174 | 5630.9174 | 5798.7174 | 6357.1274 | 6357.1274
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 153.13 | 291.75 | 300.63 | 522.94 | 561.08 | 621.4 | 658.37 | 1435.02 | 1926.27 | 2508.21 | 3273.38 | 3778.73 | 3991.0813 | 4485.3991 | 5317.0884 | 6357.1274 | 6357.1274
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.76 | 106.06 | 362.48 | 362.48 | 445.24 | 564.3 | 752.14 | 831.08 | 1323.67 | 1811.836 | 2210.836 | 2744.6073 | 4011.4207 | 4894.2307 | 4894.2307
G4.6 | Water supply resilience strategy and improvements made | CS16WR | 19 | 6 | 7.5 | 1 | No. | I | 2 | 4 | 6 | 11 | 11 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
[6 empty] | 2 | Zones | I | 1 | 1 | 3 | 8 | 8 | 9 | 9 | 10 | 13 | 13 | 14 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 19 | 19 | 19 | 19 | 19
[6 empty] | 3 | Zones | I | 1 | 1 | 1 | 8 | 8 | 9 | 9 | 9 | 13 | 13 | 14 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 19 | 19 | 19 | 19
[6 empty] | 4 | Zones | I | 1 | 1 | 1 | 6 | 6 | 6 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 13 | 15 | 15 | 15 | 16 | 17 | 17 | 17 | 17 | 17
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 4 | 6 | 6 | 6 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 12 | 12 | 13 | 14 | 14 | 16 | 16 | 16 | 17 | 17
G4.7 | Number of zones with improved security of supply (SOSI) | WG4 | 11 | 7 | 2.9 | 1 | No. | I | 2 | 2 | 3 | 5 | 5 | 5 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
[6 empty] | 2 | Zones | I | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 8 | 9 | 10 | 11 | 11 | 11 | 11
[6 empty] | 3 | Zones | I | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 5 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 8 | 9 | 10 | 11 | 11 | 11
[6 empty] | 4 | Zones | I | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 4 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7
[6 empty] | 5 | Zones | I | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7
G4.8 | Number of security measures and improvements to the infrastructure of critical reservoirs | DW9A, DW9D, DW9F, DW9H | 693 | 8 | 4.6 | 1 | No. | I | 633 | 689 | 689 | 689 | 689 | 690 | 690 | 691 | 692 | 692 | 692 | 692 | 692 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693 | 693
[6 empty] | 2 | Zones | I | 30 | 86 | 86 | 292 | 292 | 292 | 292 | 323 | 324 | 447 | 447 | 575 | 575 | 576 | 692 | 692 | 692 | 692 | 692 | 692 | 693 | 693 | 693 | 693 | 693
[6 empty] | 3 | Zones | I | 30 | 86 | 86 | 292 | 292 | 292 | 292 | 321 | 323 | 324 | 447 | 575 | 575 | 576 | 691 | 692 | 692 | 692 | 692 | 692 | 692 | 693 | 693 | 693 | 693
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 3 | 3 | 5 | 41 | 139 | 139 | 156 | 240 | 345 | 351 | 368 | 451 | 542 | 561 | 564 | 565 | 574 | 576 | 692 | 692 | 692 | 692
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 3 | 3 | 5 | 41 | 77 | 139 | 145 | 176 | 272 | 279 | 339 | 355 | 460 | 552 | 561 | 562 | 564 | 576 | 576 | 692 | 692 | 692
G4.9 | Number of water quality etc studies to inform future periods | CS16S, DW2_S, DW25PS, DW25TS, DW3C_S, | 362 | 18 | 1.7 | 1 | No. | I | 232 | 341 | 342 | 342 | 342 | 342 | 342 | 342 | 353 | 353 | 353 | 358 | 361 | 361 | 361 | 361 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362
[6 empty] | 2 | Zones | I | 27 | 49 | 189 | 341 | 342 | 342 | 342 | 342 | 342 | 342 | 342 | 352 | 356 | 356 | 358 | 359 | 361 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362
[6 empty] | 3 | Zones | I | 27 | 49 | 188 | 341 | 342 | 342 | 342 | 342 | 342 | 342 | 342 | 352 | 352 | 356 | 357 | 358 | 361 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 12 | 12 | 40 | 59 | 113 | 117 | 154 | 185 | 252 | 252 | 302 | 302 | 307 | 313 | 331 | 346 | 358 | 359 | 359 | 362 | 362 | 362
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 12 | 12 | 18 | 36 | 86 | 106 | 138 | 138 | 220 | 220 | 220 | 220 | 263 | 325 | 326 | 328 | 347 | 359 | 359 | 359 | 362 | 362
G4.10 | 2010-15 outputs planned to complete in the 2015-21 period | DW5, DW13, DW23, DW25 | 22 | 19 | 4.3 | 1 | No | I | 18 | 20 | 20 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
[6 empty] | 2 | Zones | I | 13 | 14 | 16 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 20 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
[6 empty] | 3 |  | I | 13 | 14 | 14 | 17 | 17 | 17 | 17 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 20 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
[6 empty] | 4 |  | I | 1 | 3 | 3 | 4 | 4 | 4 | 6 | 8 | 8 | 8 | 9 | 11 | 11 | 13 | 13 | 15 | 16 | 16 | 17 | 17 | 20 | 20 | 21 | 22 | 22
[6 empty] | 5 | Zones | I | 0 | 0 | 1 | 2 | 2 | 3 | 3 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 9 | 13 | 15 | 15 | 16 | 17 | 17 | 19 | 19 | 21 | 21
Q&SIV Enhancements - Environment - OMD Outputs
Line Ref. | Output | Drivers | Total No Outputs | OMG Programme Group | OMD Weighting % | Milestone Stage | Units | Field Type | 2015/16 |  |  |  | 2016/17 |  |  |  | 2017/18 |  |  |  | 2018/19 |  |  |  | 2019/20 |  |  |  | 2020/21 |  |  |  | 2015-21
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
G4.11 | Number of WWTWs improved to meet UWWTD | EC01A, EC10A | 26 | 9 | 6.7 | 1 | No. | I | 21 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 24 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
[6 empty] | 2 | Zones | I | 6 | 6 | 7 | 18 | 18 | 18 | 18 | 18 | 18 | 21 | 21 | 23 | 23 | 23 | 25 | 25 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 26
[6 empty] | 3 | Zones | I | 6 | 6 | 6 | 14 | 18 | 18 | 18 | 18 | 18 | 19 | 21 | 23 | 23 | 23 | 25 | 25 | 25 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 26
[6 empty] | 4 | Zones | I | 4 | 5 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 10 | 15 | 18 | 18 | 19 | 21 | 22 | 23 | 23 | 23 | 23 | 24 | 26 | 26 | 26
[6 empty] | 5 | Zones | I | 4 | 5 | 5 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 15 | 15 | 17 | 19 | 21 | 22 | 23 | 23 | 23 | 23 | 23 | 24 | 26 | 26
G4.12 | Number of waste water networks improved to meet UWWTD | CS11, EC01B,EC01C, EC01F, EC10B | 59 | 10 | 6.9 | 1 | No. | I | 41 | 41 | 42 | 42 | 42 | 42 | 42 | 43 | 50 | 50 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59
[6 empty] | 2 | Zones | I | 1 | 8 | 14 | 28 | 28 | 28 | 30 | 31 | 32 | 34 | 35 | 35 | 40 | 40 | 44 | 45 | 46 | 51 | 58 | 59 | 59 | 59 | 59 | 59 | 59
[6 empty] | 3 | Zones | I | 1 | 6 | 10 | 19 | 28 | 28 | 28 | 31 | 31 | 33 | 34 | 35 | 35 | 40 | 42 | 44 | 44 | 45 | 45 | 52 | 52 | 55 | 56 | 59 | 59
[6 empty] | 4 | Zones | I | 0 | 2 | 4 | 7 | 7 | 13 | 17 | 17 | 18 | 20 | 21 | 23 | 23 | 25 | 25 | 29 | 29 | 38 | 42 | 43 | 43 | 46 | 50 | 52 | 52
[6 empty] | 5 | Zones | I | 0 | 0 | 4 | 4 | 7 | 7 | 7 | 17 | 17 | 17 | 19 | 22 | 23 | 23 | 25 | 29 | 29 | 29 | 38 | 42 | 43 | 43 | 46 | 50 | 50
G4.13 | Number of improvements required to meet UWWTD - Glasgow completion | EC01B, EC04B, EC10B | 85 | 20 | 15.8 | 1 | No. | I | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85
[6 empty] | 2 | Zones | I | 38 | 38 | 38 | 56 | 56 | 60 | 63 | 63 | 64 | 65 | 67 | 69 | 70 | 71 | 72 | 78 | 79 | 80 | 83 | 83 | 85 | 85 | 85 | 85 | 85
[6 empty] | 3 | Zones | I | 31 | 37 | 37 | 47 | 51 | 53 | 58 | 62 | 62 | 64 | 66 | 68 | 70 | 70 | 70 | 73 | 74 | 77 | 78 | 82 | 83 | 85 | 85 | 85 | 85
[6 empty] | 4 | Zones | I | 3 | 8 | 23 | 27 | 27 | 29 | 32 | 37 | 43 | 46 | 52 | 53 | 56 | 57 | 58 | 64 | 66 | 68 | 72 | 73 | 79 | 80 | 83 | 85 | 85
[6 empty] | 5 | Zones | I | 0 | 6 | 7 | 24 | 25 | 25 | 29 | 36 | 36 | 41 | 43 | 51 | 51 | 52 | 56 | 61 | 62 | 64 | 67 | 69 | 69 | 77 | 78 | 85 | 85
G4.14 | Number of improvements required to meet the Water Framework Directive | EC10A, WR1, WR2A | 30 | 11 | 1.6 | 1 | No. | I | 12 | 12 | 12 | 17 | 17 | 17 | 20 | 20 | 20 | 20 | 23 | 23 | 23 | 26 | 27 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
[6 empty] | 2 | Zones | I | 1 | 1 | 1 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 15 | 15 | 21 | 21 | 21 | 21 | 26 | 26 | 27 | 29 | 29 | 29
[6 empty] | 3 | Zones | I | 1 | 1 | 1 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 21 | 21 | 21 | 21 | 22 | 26 | 26 | 27 | 28 | 28
[6 empty] | 4 | Zones | I | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 5 | 6 | 17 | 17 | 17
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 6 | 12 | 12
G4.15 | Number of revised Bathing Waters Directive studies | EC16, EC16A, EC16B | 12 | 12 | 1.2 | 1 | No. | I | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12
[6 empty] | 2 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12
[6 empty] | 3 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 9 | 9 | 9 | 9 | 9 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 10 | 10 | 11 | 11 | 11 | 11
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 10 | 10 | 11 | 11 | 11
G4.16 | Number of studies and catchments to meet the requirements of the Flood Risk Management Act | CS16D | 218 | 13 | 1.3 | 1 | No. | I | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218
[6 empty] | 2 | Zones | I | 0 | 5 | 17 | 55 | 177 | 187 | 201 | 216 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218
[6 empty] | 3 | Zones | I | 0 | 0 | 6 | 47 | 166 | 187 | 193 | 210 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218 | 218
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 23 | 29 | 44 | 55 | 71 | 83 | 103 | 115 | 147 | 168 | 187 | 201 | 214 | 217 | 218 | 218 | 218 | 218
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 13 | 16 | 38 | 51 | 65 | 73 | 91 | 101 | 140 | 143 | 167 | 186 | 201 | 214 | 217 | 218 | 218 | 218
G4.17 | Number of environmental studies to inform future periods | EC01D, EC01G, EC06C, EC08C, EC10D, EC10E, EC10H, EC21, LA01_S, WR1A, WR2B | 130 | 14 | 2.8 | 1 | No. | I | 98 | 123 | 123 | 123 | 123 | 123 | 123 | 126 | 126 | 126 | 126 | 127 | 127 | 129 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130
[6 empty] | 2 | Zones | I | 9 | 10 | 11 | 31 | 56 | 93 | 109 | 122 | 125 | 125 | 126 | 126 | 126 | 126 | 126 | 128 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130
[6 empty] | 3 | Zones | I | 9 | 9 | 10 | 21 | 37 | 78 | 98 | 116 | 125 | 125 | 126 | 126 | 126 | 126 | 126 | 128 | 129 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 7 | 10 | 23 | 36 | 42 | 51 | 68 | 87 | 95 | 107 | 116 | 121 | 128 | 128 | 128 | 129 | 129
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 6 | 16 | 33 | 35 | 35 | 42 | 66 | 81 | 93 | 107 | 116 | 123 | 128 | 128 | 128 | 128
G4.18 | Number of improvements required by the Compliance Assessment Scheme; odour reduction and sludge management | EC08A, EC23A, LA01, WQ01D, WQ01E | 96 | 15 | 2.5 | 1 | No. | I | 15 | 18 | 38 | 38 | 39 | 39 | 40 | 40 | 42 | 43 | 43 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96
[6 empty] | 2 | Zones | I | 9 | 10 | 11 | 12 | 21 | 26 | 27 | 29 | 29 | 36 | 36 | 40 | 40 | 40 | 40 | 41 | 41 | 42 | 42 | 96 | 96 | 96 | 96 | 96 | 96
[6 empty] | 3 | Zones | I | 9 | 10 | 11 | 12 | 21 | 25 | 26 | 28 | 29 | 36 | 36 | 39 | 40 | 40 | 40 | 40 | 40 | 40 | 41 | 41 | 96 | 96 | 96 | 96 | 96
[6 empty] | 4 | Zones | I | 6 | 7 | 10 | 11 | 11 | 11 | 11 | 20 | 21 | 22 | 27 | 28 | 29 | 29 | 31 | 31 | 37 | 37 | 37 | 38 | 40 | 40 | 94 | 94 | 94
[6 empty] | 5 | Zones | I | 4 | 5 | 6 | 10 | 10 | 10 | 10 | 19 | 19 | 20 | 22 | 27 | 28 | 28 | 29 | 31 | 31 | 37 | 37 | 38 | 38 | 40 | 40 | 94 | 94
G4.19 | 2010-15 outputs planned to complete in the 2015-21 period | EC16, WG4, WR1 | 15 | 21 | 3.3 | 1 | No. | I | 14 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
[6 empty] | 2 | Zones | I | 8 | 9 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 15 | 15
[6 empty] | 3 | Zones | I | 5 | 7 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 15 | 15
[6 empty] | 4 | Zones | I | 0 | 0 | 1 | 7 | 7 | 8 | 8 | 10 | 10 | 10 | 10 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 7 | 7 | 7 | 8 | 8 | 10 | 10 | 10 | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G4.20 | Number of improvements to dams to meet the requirements of the Flood Risk Management Act | WR6 | 54 | 26 | 0.6 | 1 | No. | I | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
[6 empty] | 2 | Zones | I | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
[6 empty] | 3 | Zones | I | 0 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 6 | 6 | 7 | 8 | 11 | 11 | 16 | 16 | 25 | 27 | 32 | 35 | 40 | 48 | 50 | 52 | 54 | 54 | 54 | 54 | 54 | 54
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 6 | 6 | 7 | 8 | 10 | 10 | 10 | 13 | 17 | 18 | 22 | 24 | 36 | 38 | 47 | 49 | 53 | 54 | 54 | 54 | 54 | 54
Q&SIV Enhancements -Supporting Economic Development - OMD Outputs
Line Ref. | Output | Drivers | Total No Outputs | OMG Programme Group | OMD Weighting % | Milestone Stage | Units | Field Type | 2015/16 |  |  |  | 2016/17 |  |  |  | 2017/18 |  |  |  | 2018/19 |  |  |  | 2019/20 |  |  |  | 2020/21 |  |  |  | 2015-21
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
G4.21 | Number of climate change vulnerability assessments | CC3S, CC4S, CC4W, CC5S, CC7S | 123 | 17 | 1.6 | 1 | No. | I | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123
[6 empty] | 2 | Zones | I | 3 | 55 | 55 | 55 | 55 | 55 | 57 | 57 | 57 | 111 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123
[6 empty] | 3 | Zones | I | 3 | 55 | 55 | 55 | 55 | 55 | 57 | 57 | 57 | 109 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123 | 123
[6 empty] | 4 | Zones | I | 0 | 0 | 0 | 4 | 6 | 31 | 54 | 54 | 55 | 55 | 56 | 59 | 59 | 59 | 59 | 81 | 96 | 108 | 117 | 117 | 117 | 117 | 123 | 123 | 123
[6 empty] | 5 | Zones | I | 0 | 0 | 0 | 4 | 6 | 31 | 54 | 54 | 54 | 55 | 55 | 57 | 57 | 57 | 57 | 59 | 95 | 107 | 107 | 116 | 116 | 116 | 116 | 123 | 123
G4.22 | Improvements in renewable power and energy efficiency | I2S_WNI, I2S_WWNI | 17.5 | 16 | 2.4 | 1 | Gwh | I | 2.273 | 13.244 | 13.244 | 13.244 | 13.244 | 13.244 | 13.244 | 13.244 | 13.244 | 13.244 | 13.244 | 13.244 | 13.8 | 13.9 | 16.4 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5
[6 empty] | 2 | Zones | I | 1.85 | 1.85 | 2.273 | 13.244 | 13.244 | 13.244 | 13.244 | 13.244 | 13.244 | 13.244 | 13.244 | 13.244 | 13.8 | 13.9 | 16.4 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5
[6 empty] | 3 | Zones | I | 0.94 | 1.11 | 1.11 | 12.504 | 12.504 | 12.504 | 12.504 | 13.244 | 13.244 | 13.244 | 13.244 | 13.244 | 13.8 | 13.9 | 16.4 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5
[6 empty] | 4 | Zones | I | 0.94 | 0.94 | 0.94 | 1.64 | 1.64 | 5 | 7.9 | 9.29 | 9.92 | 10.04 | 11.25 | 12.46 | 13.8 | 13.9 | 16.4 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5
[6 empty] | 5 | Zones | I | 0.94 | 0.94 | 0.94 | 1.64 | 1.64 | 5 | 7.9 | 9.29 | 9.92 | 10.04 | 11.25 | 12.46 | 13.8 | 13.9 | 16.4 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5
Prepared by: …………………………………………….. |  |  | Date: ……………………
Checked by: …………………………………………….. |  |  | Date: ……………………
Authorised by: |  |  | Date: 14th June 2019

## G5 - Growth
SCOTTISH WATER
2019
ANNUAL RETURN
SECTION G: INVESTMENT MONITORING
Table G5: Growth
|  |  |  | 10 | 20 | 30 | 40 | 50 | 60 | 70
Line | Line Title | Units | Field | Report Year | Report Year | Report Year | Report Year | Forecast Year | Forecast Year | Forecast Post
No. |  |  | Type
|  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021
Growth expenditure (gross)
G5.1 | Expenditure for reasonable cost contributions - household - water | £m | I | 8.2148 | 7.2236 | 6.6699 | 10.4821 | 8.835 | 10.3002 | 0
G5.2 | Expenditure for reasonable cost contributions - non-household - water | £m | I | -0.016061 | -0.0053652 | 0.072344 | -0.03366 | 0.040946 | 0.038828 | 0
G5.3 | Total expenditure on reasonable cost contributions - water | £m | C | 8.1987 | 7.2182 | 6.7422 | 10.4484 | 8.876 | 10.339 | 0
G5.4 | Expenditure for reasonable cost contributions - household - wastewater | £m | I | 8.6536 | 10.3839 | 9.8368 | 18.2287 | 9.4001 | 11.6563 | 0
G5.5 | Expenditure for reasonable cost contributions - non-household - wastewater | £m | I | 0 | 0.045892 | 0.019743 | 0.00035978 | 0.016954 | 0.016494 | 0
G5.6 | Total expenditure on reasonable cost contributions - wastewater | £m | C | 8.6536 | 10.4298 | 9.8565 | 18.229 | 9.4171 | 11.6728 | 0
G5.7 | Total expenditure on reasonable cost Contributions - water and wastewater | £m | C | 16.8523 | 17.648 | 16.5987 | 28.6775 | 18.293 | 22.0118 | 0
G5.8 | Expenditure on Part 3 strategic capacity - water | £m | I | 1.0213 | 2.0186 | 4.8618 | 5.7545 | 8.0678 | 16.7852 | 0
G5.9 | Expenditure on Part 3 strategic capacity - wastewater | £m | I | 1.5238 | 2.1282 | 4.2969 | 12.0185 | 14.1402 | 11.7101 | 2.312e-05
G5.10 | Total expenditure on Part 3 strategic capacity - water and wastewater | £m | C | 2.5451 | 4.1468 | 9.1587 | 17.773 | 22.208 | 28.4953 | 2.312e-05
G5.11 | Expenditure on Part 4 assets - water | £m | I | 2.3785 | 5.1255 | 3.0015 | 3.5042 | 7.666 | 20.4013 | 4.9836
G5.12 | Expenditure on Part 4 assets - wastewater | £m | I | 7.3503 | 6.0986 | 8.809 | 22.6816 | 25.1626 | 26.98 | 0
G5.13 | Total expenditure on Part 4 assets - water and wastewater | £m | C | 9.7288 | 11.2241 | 11.8105 | 26.1858 | 32.8286 | 47.3813 | 4.9836
G5.14 | Total gross expenditure on growth - (RCC + Part 3 strategic capacity + Part 4) | £m | C | 29.1263 | 33.0189 | 37.568 | 72.6362 | 73.3297 | 97.8884 | 4.9836
Service Relocations
G5.15 | Service Relocations Water | £m | I | 15.0386 | 12.4053 | 9.3689 | 7.816 | 10.6711 | 1.7131 | 0
G5.16 | Service Relocations Wastewater | £m | I | 4.8054 | 4.9606 | 3.4735 | 1.8201 | 4.5218 | 3.4733 | 0
G5.17 | Service Relocations Water Contributions | £m | I | -10.7902 | -6.5168 | -7.3147 | -4.6331 | -6.4554 | -6.4554 | 0
G5.18 | Service Relocations Wastewater Contributions | £m | I | -5.5586 | -3.3571 | -3.7682 | -1.7827 | -2.4838 | -2.4838 | 0
G5.19 | Net Service Relocations | £m | C | 3.4952 | 7.4919 | 1.7595 | 3.2204 | 6.2537 | -3.7529 | 0
Growth income (Infrastructure charge)
G5.20 | Water household infrastructure charge income | £m | I | 6.5083 | 7.5061 | 8.0983 | 8.4815 | 8.774 | 8.9049 | 0
G5.21 | Water non-household infrastructure charge income | £m | I | 0.18903 | 0.21293 | 0.053823 | 0.106 | 0.10954 | 0.1113 | 0
G5.22 | Wastewater household infrastructure charge income | £m | I | 5.0938 | 6.4276 | 7.3153 | 7.8088 | 8.0721 | 8.1926 | 0
G5.23 | Wastewater non-household infrastructure charge income | £m | I | 0.077305 | 0.057785 | 0.027592 | 0.017794 | 0.018257 | 0.018608 | 0
G5.24 | Total infrastructure charge income | £m | C | 11.8684 | 14.2044 | 15.495 | 16.4142 | 16.9739 | 17.2274 | 0
Growth expenditure (net of income)
G5.25 | Total net growth expenditure | £m | C | 20.7531 | 26.3064 | 23.8325 | 59.4425 | 62.6095 | 76.9081 | 4.9836
Growth - properties and populations
G5.26 | Number of new household properties connected to the water network | Nr | I | 19244 | 22214 | 23756 | 24157.029 | 24990 | 25363 | 0
G5.27 | Number of new non-household properties connected to the water network | Nr | I | 559 | 630 | 158 | 301.8949 | 312 | 317 | 0
G5.28 | Total number of new properties connected to the water network | Nr | C | 19803 | 22844 | 23914 | 24458.9239 | 25302 | 25680 | 0
G5.29 | Number of new household properties connected to the wastewater network | Nr | I | 15061 | 19022 | 21459 | 22241.0463 | 22990.8 | 23333.96 | 0
G5.30 | Number of new non-household properties connected to the wastewater network | Nr | I | 229 | 171 | 81 | 50.6804 | 52 | 53 | 0
G5.31 | Total number of new properties connected to the wastewater network | Nr | C | 15290 | 19193 | 21540 | 22291.7268 | 23042.8 | 23386.96 | 0
G5.32 | Number of new household properties receiving reasonable cost contributions - water | Nr | I | 14393 | 15914 | 13807 | 14948.7873 | 12600 | 14571 | 0
G5.33 | Number of new non-household properties receiving reasonable cost contributions - water | Nr | I | 0 | 0 | 150 | -78.3154 | 95 | 90 | 0
G5.34 | Total number of properties receiving reasonable cost contributions - water part 2 & 3 | Nr | C | 14393 | 15914 | 13957 | 14870.4719 | 12695 | 14661 | 0
G5.35 | Number of new household properties receiving reasonable cost contributions - wastewater | Nr | I | 11211 | 12961 | 7469 | 12159.3207 | 6270 | 7978 | 0
G5.36 | Number of new non-household properties receiving reasonable cost contributions - wastewater | Nr | I | 0 | 57 | 15 | 15.1585 | 714 | 695 | 0
G5.37 | Total number of properties receiving reasonable cost contributions - wastewater part 2 & 3 | Nr | C | 11211 | 13018 | 7484 | 12174.4791 | 6984 | 8673 | 0
G5.38 | Number of household property infrastructure charge payments - water | Nr | I | 19244 | 22214 | 23756 | 24157.029 | 24990 | 25363 | 0
G5.39 | Number of non-household property infrastructure charge payments - water | Nr | I | 559 | 630 | 158 | 301.8949 | 312 | 317 | 0
G5.40 | Total number of infrastructure charge payments - water | Nr | C | 19803 | 22844 | 23914 | 24458.9239 | 25302 | 25680 | 0
G5.41 | Number of household property infrastructure charge payments - wastewater | Nr | I | 15061 | 19022 | 21459 | 22241.0463 | 22990.8 | 23333.96 | 0
G5.42 | Number of non-household property infrastructure charge payments - wastewater | Nr | I | 229 | 171 | 81 | 50.6804 | 52 | 53 | 0
G5.43 | Total number of property infrastructure charge - wastewater | Nr | C | 15290 | 19193 | 21540 | 22291.7268 | 23042.8 | 23386.96 | 0
G5.44 | Additional population equivalent served from new part 4 investment - water | Pe | I | 0 | 14509 | 0 | 0 | 388 | 0 | 0
G5.45 | Additional population equivalent served from new part 4 investment - wastewater | Pe | I | 1351 | 792 | 3182 | 677 | 28200 | 10699 | 0
Prepared by: …………………………………….……………………………….. |  |  | Date: ……………………
Checked by: …………………………….………………………………………….. |  |  | Date: ……………………
Authorised by: |  |  | Date: 14th June 2019

## G6 - Project Analysis
SCOTTISH WATER
2019 | [10 empty] | Prepared by: …………………………………….……………………………….. |  |  |  | Date: ……………………
ANNUAL RETURN
[11 empty] | Checked by: …………………………….………………………………………….. |  |  |  | Date: ……………………
SECTION G : INVESTMENT PLAN | [10 empty] | Authorised by: |  |  |  | Date: 14th June 2019
Table G6: Project Analysis - Actuals & Forecast - Water & Wastewater
[8 empty] | Include all projects with expenditure in the price control period | [5 empty] | Edition | 8
Regulatory Outputs
[54 empty] | OMG-01 | OMG-02 | OMG-03 | OMG-04 | OMG-05 | OMG-06 | OMG-07 | OMG-08 | OMG-09 | OMG-10 | OMG-11 | OMG-12 | OMG-13 | OMG-14 | OMG-15 | OMG-16 | OMG-17 | OMG-18 | OMG-19 | OMG-20 | OMG-21 | OMG-22 | OMG-23 | OMG-24 | OMG-25 | OMG-26 | OMG-27 | OMG-28 | OMG-29 | OMG-30 | OMG-31 | OMG-32 | OMG-33 | OMG-34 | OMG-35 | OMG-36 | OMG-37 | OMG-38 | OMG-39 | OMG-40 | OMG-41 | OMG-42 | OMG-43 | OMG-44 | OMG-45 | OMG-46 | OMG-47 | OMG-48 | OMG-49 | OMG-50
1 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105
Project Autocode | Q&S Period (3b,4, IR18,5) | Programme Grouping (1) | Programme Grouping (2) | Programme Grouping (3) | Programme Grouping (4) | Water or wastewater project (primary purpose) | Technical Expression - Sign-off Owner | Accountability | Programme Grouping | Current Project Status Code | Forecast MS1 Date | Forecast MS2 Date | Forecast MS3 Date | Forecast MS4 Date | Forecast MS5 Date | Project location - Local Authority | Expenditure Pre 2015-16 | Actual Expenditure 2015-16 | Actual Expenditure 2016-17 | Actual Expenditure 2017-18 | Actual Expenditure 2018-19 | Forecast Expenditure 2019-20 | Forecast Expenditure 2020-21 | Total Q&SIV period expenditure to 2020-21 | Post 2020-21 expenditure | Project Grand Total expenditure | Table K Budget allocation | Grants for infrastructure assets | Grants for non-infrastructure assets | Contributions to infrastructure assets | Contributions to non-infrastructure assets | Impact of project on OPEX - additional operating expediture | Regulatory sign off required | Driver 1 | Driver 1 % allocation | Driver 2 | Driver 2 % allocation | Driver 3 | Driver 3 % allocation | Driver 4 | Driver 4 % allocation | Driver 5 | Driver 5 % allocation | Driver 6 | Driver 6 % allocation | Driver 7 | Driver 7 % allocation | Driver 8 | Driver 8 % allocation | Driver 9 | Driver 9 % allocation | Driver 10 | Driver 10 % allocation | Number of water treatment works made compliant with water quality standards | Number of water supply zones made compliant with iron and manganese standards | Water quality completion programme | Number of raw water catchments where reliability is improved | Number of enhancements to networks and treated water storage to improve reliability of supply | Length of distribution mains refurbished | Water supply resilience strategy and the number of improvements made. | Improvements to Drought Resilience | Number of zones to improve security of supply (SOSI) | Number of improvements required to meet SEMD requirements | Number of improvements to dams to meet the obligations of the FRMA | Number of lead communication pipes replaced | Number of improvements in the infrastructure of critical – reservoirs | Number of properties where low pressure issues are addressed’ | Average duration of short term interruptions in supply | Number of water efficiency advice and water saving packs provided (to 2% of customer base) | Number of improvements delivered to meet UWWTD: above ground works | Number of improvements delivered to meet UWWTD: below ground networks | Number of improvements delivered to meet UWWTD: Glasgow scheme | Number of improvements to meet the WFD | Number of improvements to meet the rBWD | Number of catchments improved to meet the Flood Risk Management Act (FRMA) | Number of studies to prepare for future investment periods | Number of Sludge Management sites investigated and / or improved | Develop a national strategy on the Priority Substances Directive | Number of improvements to meet the Habitats Directive | Number of improvements required under the Compliance Assessment Scheme | Number of improvements required by Scot. Gov’t to protect the water environment | Number of improvements required by SEPA and LAs to reduce odour nuisance | Number of properties removed from the internal flooding register | Number of internal flooding improvements - completion programme | Number of external flooding investigations and improvements | % of customers covered by flood resilience assessments | Number of surface water management investigations | Number of reasonable cost contributions made to connect new households and businesses - water | Number of RCC made to connect new households and businesses - waste water | Delivery of new waste water capacity for 58,000 people | Number of developer constructed assets (Part 2&3) adopted | Number of first time non domestic meters installed | Number of projects completed under statutory requirements to relocate services for transport infrastructure projects | Improved contact management and proactive communication | Number of wholesale meters | Renewable power generation | Reduction in energy usage | Number of vulnerability assessments and monitoring improvements to support Climate Change mitigation and reduction | Number of Research & Innovation projects completed | Number of water quality studies to prepare for future investment periods | OMG-48 (not used) | Strategic Mains Diversions | OMG-50 (not used)
503523 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2019-04-08 | 2019-04-08 | 2019-08-30 | 2020-02-28 | 2020-03-19 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 300000.02 | 0 | 300000.02 | 0 | 300000.02 | 0 | [6 empty] | CM_WSNI | 100%
503524 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2019-04-08 | 2019-04-08 | 2019-08-30 | 2020-02-28 | 2020-03-06 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 104999.99 | 0 | 104999.99 | 0 | 104999.99 | 0 | [6 empty] | CM_WSNI | 100%
503528 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2019-07-01 | 2019-08-05 | 2019-12-05 | 2021-07-12 | 2021-10-12 | Stirling | 0 | 0 | 0 | 0 | 0 | 133285.82 | 203895.55 | 337181.37 | 126818.68 | 464000.05 | 0 | [6 empty] | CM_WSI | 100%
501018 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS5 | 2017-11-27 | 2019-07-15 | 2019-07-15 | 2019-01-16 | 2018-01-16 | Moray | 0 | 26893 | 39072.99 | 38223.01 | -104188.004 | 0 | 0 | 0.996 | 0 | 0.996 | 229318.7788 | [6 empty] | CS11 | 100%
501559 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS5 | 2016-02-22 | 2016-04-18 | 2016-04-18 | 2018-01-24 | 2018-01-24 | Scottish Water Wide | 0 | 47647.82 | 256245.64 | 6106.54 | 141.11 | 189858.9 | 0 | 500000.01 | 0 | 500000.01 | 0 | [6 empty] | CM_WWNI | 100%
502893 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-03-05 | 2021-02-22 | 2021-05-05 | 2021-12-07 | 2022-03-09 | East Renfrewshire | 0 | 0 | 0 | 43000 | 64000 | 31000.01 | 25191.49 | 163191.5 | 138808.53 | 302000.03 | 240495.8008 | [6 empty] | CS11A | 100%
500707 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2015-06-12 | 2017-12-20 | 2018-03-29 | 2019-11-22 | 2019-11-22 | Perth and Kinross | 0 | 21000 | 32778 | 223222 | 470506 | 0 | 0 | 747506 | 2414 | 749920 | 0 |  |  |  |  | 1280.0003 |  | CM_WWNI | 100%
503268 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2021-04-01 | 2021-04-01 | 2021-06-21 | 2022-01-14 | 2022-04-18 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267000 | 267000 | 0 | [6 empty] | CM_WWI | 100%
501813 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2017-04-28 | 2018-03-14 | 2018-03-26 | 2018-06-29 | 2018-06-29 | Fife | 0 | 0 | 6606.12 | 25859.88 | 52613.3172 | 0 | 0 | 85079.3172 | 0 | 85079.3172 | 0 | [6 empty] | CM_WWI | 100%
500058 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-11-30 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | East Renfrewshire | 192.99 | 34807.01 | 3000 | 4000 | 164.0981 | 0 | 0 | 41971.1081 | 0 | 42164.0981 | 144841.4737 | [6 empty] | CS15A | 100%
503367 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2020-07-03 | 2021-05-05 | 2021-07-22 | 2022-04-05 | 2022-07-06 | Scottish Borders | 0 | 0 | 0 | 0 | 46000 | 42602 | 79681.36 | 168283.36 | 131716.71 | 300000.07 | 240495.8008 | [6 empty] | CS11A | 100%
503392 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2020-07-03 | 2021-05-05 | 2021-08-19 | 2022-05-03 | 2022-08-03 | Scottish Borders | 0 | 0 | 0 | 0 | 46000 | 42166.93 | 53247.75 | 141414.68 | 158585.34 | 300000.02 | 240495.8008 | [6 empty] | CS11A | 100%
401087 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | [5 empty] | Scottish Water Wide | 13710.93 | -1703.83 | 0 | 83.18 | 1949.4 | 0 | 0 | 328.75 | 0 | 14039.68 | 0 | [6 empty] | OHDS1 | 50% | OHDW1 | 50%
500928 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS2 | 2015-10-26 | 2016-07-15 | 2019-10-30 | 2019-10-30 | 2020-03-19 | Perth and Kinross | 0 | 8367.68 | 58778.32 | 52031.104 | 111037.1045 | 26999.94 | 0 | 257214.1485 | 0 | 257214.1485 | 385337.2745 | [6 empty] | CS15A | 50% | CS11A | 50%
503467 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2019-07-01 | 2020-06-15 | 2020-09-09 | 2021-04-12 | 2021-07-13 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 269856.06 | 269856.06 | 111117.19 | 380973.25 | 0 | [6 empty] | CM_WWI | 100%
501582 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2016-05-04 | 2017-09-29 | 2018-01-22 | 2018-03-26 | 2018-03-26 | North Ayrshire | 0 | 0 | 74411 | 185822 | 14767 | 0 | 0 | 275000 | 0 | 275000 | 0 | [6 empty] | CM_WWI | 100%
501435 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-04-01 | 2016-07-25 | 2016-07-26 | 2016-09-14 | 2016-09-30 | East Dunbartonshire | 0 | 0 | 776.72 | 0 | 0 | 0 | 0 | 776.72 | 0 | 776.72 | 824836.9475 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
501440 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-03-30 | 2017-03-01 | 2017-03-02 | 2017-03-24 | 2017-03-31 | North Ayrshire | 0 | 0 | 930.57 | 268.83 | 0 | 0 | 0 | 1199.4 | 0 | 1199.4 | 439302.4088 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
501418 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2017-04-28 | 2018-12-10 | 2018-12-18 | 2020-10-07 | 2020-12-31 | Na H-Eileanan an Iar | 0 | 0 | 96266.67 | 469886.82 | 573399.9315 | 3537107.64 | 1809680.91 | 6486341.9715 | 48306.63 | 6534648.6015 | 1017925.3446 |  |  |  |  | 12500.0004 |  | DW25P | 100% | bar: Regulatory Outputs OMG-04
501360 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS6 | 2016-03-29 | 2016-10-24 | 2017-02-03 | 2018-01-30 | 2020-04-06 | Argyll and Bute-Cowal & Bute | 0 | 142 | 39477.05 | 139961.96 | 5028.4645 | 0 | 0 | 184609.4745 | 0 | 184609.4745 | 72673.918 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
501436 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2016-07-06 | 2016-07-25 | 2016-07-25 | 2021-08-27 | 2021-11-05 | West Dunbartonshire | 0 | 0 | 20408.28 | 1704.245 | 7688.77 | 0 | 0 | 29801.295 | 0 | 29801.295 | 502191.4351 | [6 empty] | CM_WSNI | 11.89% | DW25P | 88.11%
501421 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2018-03-08 | 2019-06-14 | 2019-06-19 | 2020-11-24 | 2021-03-02 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 514.255 | 140.025 | 4443.16 | 0 | 5097.44 | 0 | 5097.44 | 142207.1972 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
501419 | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWD | Flood Assessments | MS0 | 2017-03-03 | 2019-10-21 | 2020-02-27 | 2021-01-21 | 2021-04-23 | Scottish Water Wide | 0 | 0 | 135738.62 | 266210.2125 | 235051.1675 | 168742.97 | 383229.43 | 1188972.4 | 51214.58 | 1240186.98 | 986378.2441 | [6 empty] | CS15E | 100%
501439 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2017-01-10 | 2017-05-16 | Scottish Water Wide | 0 | 0 | 2197.89 | 0 | 0 | 0 | 0 | 2197.89 | 0 | 2197.89 | 1817908.3275 | [6 empty] | CS16WR | 100% | bar: Regulatory Outputs OMG-07
501791 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MSU | 2021-04-15 |  |  | 2021-04-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 2288661.99 | 2288661.98 | 4577323.97 | 0 | 4577323.97 | 0 |  |  | 42165748.96 |  |  |  | CS23W | 100%
501796 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MSU | 2021-04-15 |  |  | 2021-04-15 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 2041304.98 | 2041304.98 | 4082609.96 | 0 | 4082609.96 | 3112230.0788 |  |  | 19434251.04 |  |  |  | CS23S | 100%
501806 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2020-01-27 | 2021-07-05 | 2021-11-05 | 2023-02-02 | 2023-05-05 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 10136.9 | 73475.91 | 83612.81 | 2288886.13 | 2372498.94 | 144841.4737 | [6 empty] | CS15A | 100%
501805 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2020-01-27 | 2021-07-05 | 2021-11-05 | 2023-02-02 | 2023-05-05 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 10136.9 | 73475.91 | 83612.81 | 2288886.13 | 2372498.94 | 9244605.8896 | [6 empty] | CS11A | 100%
502046 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS6 | 2013-02-02 | 2017-01-26 | 2017-03-21 | 2017-09-28 | 2018-01-15 | North Lanarkshire | 0 | 65.42 | 9690.21 | 31906.505 | 0.005 | 0 | 1000 | 42662.14 | 0 | 42662.14 | 42692.4959 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
503339 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-12-17 | 2021-11-23 | 2022-02-07 | 2022-09-08 | 2022-12-09 | East Ayrshire | 0 | 0 | 0 | 0 | 20000 | 49751.85 | 47988.89 | 117740.74 | 182259.21 | 299999.95 | 240495.8008 | [6 empty] | CS11A | 100%
503428 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2020-09-11 | 2021-07-26 | 2021-11-25 | 2022-07-20 | 2022-10-20 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 45000 | 35995.77 | 131990.89 | 212986.66 | 987013.26 | 1199999.92 | 240495.8008 | [6 empty] | CS11A | 100%
503398 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2020-08-14 | 2021-08-09 | 2021-11-08 | 2022-07-01 | 2022-10-03 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 49000 | 34827.1 | 95200.11 | 179027.21 | 720972.79 | 900000 | 240495.8008 | [6 empty] | CS11A | 100%
502809 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2017-07-10 | 2017-07-10 | 2017-11-21 | 2017-12-04 | 2017-12-04 | Glasgow City | 0 | 0 | 0 | 239291.31 | 0 | 0 | 0 | 239291.31 | 0 | 239291.31 | 587726.5342 | [6 empty] | WG5 | 100%
503335 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS5 | 2018-08-20 | 2018-10-25 | 2018-10-25 | 2019-01-22 | 2019-01-22 | Renfrewshire | 0 | 0 | 0 | 0 | 105333 | 14667 | 0 | 120000 | 0 | 120000 | 48164.5084 | [6 empty] | CS23W | 100%
403650 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS7 | 2014-02-03 | 2014-03-24 | 2014-03-24 | 2019-02-20 | 2019-02-20 | Highland | 1400000 | 0 | -426630.55 | 1251663.32 | 5737181.62 | 0 | 0 | 6562214.39 | 0 | 7962214.39 | 0 | [6 empty] | SG5 | 100%
402736 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2012-06-11 | 2013-05-16 | 2013-10-28 | 2014-02-26 | 2014-02-26 | Perth and Kinross | 205340.87 | 3635 | 181.62 | 41.37 | 0 | 0 | 0 | 3857.99 | 0 | 209198.86 | 0 | [6 empty] | SG1 | 100%
401379 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2010-09-24 | 2012-10-29 | 2015-01-19 | 2015-03-13 | 2015-03-13 | Aberdeenshire | 50142 | -46590.69 | 0 | 0 | 0 | 0 | 0 | -46590.69 | 0 | 3551.31 | 240495.8008 | [6 empty] | CS11 | 100%
403781 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS0 | 2017-01-10 | 2019-05-13 | 2019-09-09 | 2020-07-03 | 2020-07-03 | Aberdeenshire | 11188 | 26952.58 | 6246.1 | 5733.84 | 144320.68 | 206169.92 | 81905.79 | 471328.91 | 0 | 482516.91 | 0 | [6 empty] | SG1 | 100%
403478 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2013-07-02 | 2013-10-21 | 2013-10-21 | 2014-12-18 | 2015-01-21 | Aberdeenshire | 428744 | -10603.49 | 0 | 0 | 0 | 0 | 0 | -10603.49 | 0 | 418140.51 | 0 | [6 empty] | WG5 | 100%
403788 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2014-10-21 | 2014-11-21 | 2015-01-14 | 2015-07-21 |  | Aberdeen City | 105136 | 4169 | 1430.86 | -1974.49 | 0 | 0 | 0 | 3625.37 | 0 | 108761.37 | 0 | [6 empty] | CM_WWI | 100%
402477 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-06-28 | 2013-02-20 | 2013-02-20 | 2015-03-26 | 2015-03-30 | Scottish Water Wide | 1447201 | 121043 | -25526.68 | 15675.73 | 0 | 0 | 0 | 111192.05 | 0 | 1558393.05 | 102155 | [6 empty] | CS16S | 100%
046262 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-12-03 | 2010-09-27 | 2013-01-21 | 2013-07-31 |  | Aberdeen City | 742687.29 | -30786.58 | 0 | 0 | 0 | 0 | 0 | -30786.58 | 0 | 711900.71 | 0 | [6 empty] | CM_WSNI | 100%
501094 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS4 | 2015-09-30 | 2016-07-20 | 2016-07-25 | 2019-03-19 | 2019-07-10 | Aberdeen City | 0 | 4738 | 79992.21 | 13869.79 | 21400 | 3000.01 | 0 | 123000.01 | 0 | 123000.01 | 0 | [6 empty] | EC10D | 100% | bar: Regulatory Outputs OMG-23
503203 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-10-21 | 2023-01-25 | 2023-05-24 | 2024-01-09 | 2024-04-10 | Aberdeen City | 0 | 0 | 0 | 0 | 322752.25 | 114817.52 | 200735.41 | 638305.18 | 113255.41 | 751560.59 | 148885.7057 | [6 empty] | SG1 | 100%
500814 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-08-13 | 2015-12-11 | 2015-12-11 | 2018-02-01 | 2018-02-01 | Aberdeenshire | 0 | 49031.93 | 1973.87 | -7925.985 | 0 | 0 | 0 | 43079.815 | 0 | 43079.815 | 144841.4737 | [6 empty] | CS15A | 100%
501095 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS4 | 2015-09-30 | 2016-09-26 | 2016-09-28 | 2019-03-19 | 2019-10-10 | Aberdeenshire | 0 | 3730 | 45232.36 | 20237.64 | 24800 | 6000 | 0 | 100000 | 0 | 100000 | 0 | [6 empty] | EC10D | 100% | bar: Regulatory Outputs OMG-23
402969 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-09-26 | 2015-10-05 | 2015-10-05 | 2015-10-05 |  | Stirling | 37520 | 363.29 | 0 | 0 | 0 | 0 | 0 | 363.29 | 0 | 37883.29 | 0 | [6 empty] | CM_WSI | 100%
503078 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2019-02-14 | 2019-02-14 | 2019-02-14 | 2019-01-15 | 2019-01-15 | Stirling | 0 | 0 | 0 | 8884.13 | 6769.836 | 0 | 0 | 15653.966 | 0 | 15653.966 | 0 | [6 empty] | CM_WWI | 100%
500916 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2015-09-28 | 2018-03-22 | 2018-03-27 | 2019-11-28 | 2019-06-28 | Stirling | 0 | 10485 | 67740.26 | 145567.74 | 714755.29 | 130000 | 0 | 1068548.29 | 0 | 1068548.29 | 0 | [6 empty] | CM_WSI | 100%
500112 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS4 | 2015-03-17 | 2016-12-19 | 2017-01-16 | 2019-02-26 | 2019-06-26 | Moray | 0 | 8751 | 15597 | 27193 | 22659 | 0 | 0 | 74200 | 0 | 74200 | 16923.852 | [6 empty] | EC01G | 28.08% | EC01D | 32.76% | CS16D | 39.16%
400946 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-05-31 | 2013-09-12 | 2013-09-30 | 2014-08-08 | 2014-03-31 | Moray | 1811330 | 1376.14 | -12031.84 | 7328.87 | 0 | 0 | 0 | -3326.83 | 0 | 1808003.17 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
045537 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-29 | 2011-03-23 | 2011-10-12 | 2012-08-30 | 2012-11-26 | South Lanarkshire | 764146.75 | 38434.37 | 0 | 0 | 0 | 0 | 0 | 38434.37 | 0 | 802581.12 | 0 | [6 empty] | WQ01 | 100%
400092 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-11-04 | 2011-03-29 | 2011-07-18 | 2012-06-25 | 2012-09-25 | Aberdeenshire | 1620884.6 | -1887.58 | 0 | 0 | -3702.6 | 0 | 0 | -5590.18 | 0 | 1615294.42 | 0 | [6 empty] | DW23 | 100%
502958 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS0 | 2017-11-29 | 2020-09-07 | 2021-01-11 | 2021-10-29 | 2022-01-28 | Aberdeenshire | 0 | 0 | 0 | 28353.125 | 26629.875 | 25297.8 | 199387.78 | 279668.58 | 469494.69 | 749163.27 | 0 | [6 empty] | CM_WWNI | 100%
500722 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-08-24 | 2018-08-24 | 2018-08-23 | 2018-08-23 | 2018-08-23 | Aberdeenshire | 0 | 36204 | 34571.42 | 16338.9125 | 860.1625 | 0 | 0 | 87974.495 | 0 | 87974.495 | 148885.7057 | [6 empty] | SG1 | 100%
503100 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | General |  | SWD | Flooding Demand Driven | MS2 | 2018-07-09 | 2018-07-09 | 2019-06-19 | 2021-11-26 | 2022-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 95356.204 | 176435.36 | 174319.37 | 446110.934 | 1289309.32 | 1735420.254 | 536364292.6425 | [6 empty] | SR15_CMA_MAG | 0.04046% | SR15_CMA_WSNI | 0.3295% | SR15_ENV_WFD | 0.4377% | SR15_SED_INFC | 0.514% | SR15_ENV_UWWD | 1.922% | SR15_CMP_LATE | 2.093% | SR15_SED_SCAP | 2.331% | SR15_ENV_SHEL | 3.357% | SR15_EXC_EXC | 6.778% | SR15_UID_UWWD | 7.72%
502227 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MS7 | 2016-05-12 | 2016-09-15 | 2016-10-21 | 2017-12-06 | 2017-12-06 | Scottish Water Wide | 0 | 0 | 33697.12 | 9185.86 | -829.11 | 0 | 0 | 42053.87 | 0 | 42053.87 | 0 | [6 empty] | CM_M&G | 100%
500673 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-06-03 | 2017-03-16 | 2017-03-16 | 2017-01-16 |  | Scottish Water Wide | 0 | 60205.5 | 83.72 | 0 | 0 | 0 | 0 | 60289.22 | 0 | 60289.22 | 0 | [6 empty] | CM_M&G | 100%
501059 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-10-08 | 2015-11-25 | 2015-11-25 | 2015-11-25 | 2015-11-25 | Highland | 0 | 1689.39 | 0 | 0 | 0 | 0 | 0 | 1689.39 | 0 | 1689.39 | 0 | [6 empty] | CM_WSNI | 100%
502845 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-18 | 2022-10-21 | 2023-02-20 | 2024-02-15 | 2024-05-17 | Highland | 0 | 0 | 0 | 20930.23 | 956.55 | 24670.77 | 3442.43 | 49999.98 | 0 | 49999.98 | 148885.7057 | [6 empty] | WG1 | 100%
045300 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-17 | 2011-03-01 | 2011-08-15 | 2012-07-03 | 2012-09-24 | Highland | 1496054.78 | 70 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 1496124.78 | 0 | [6 empty] | DW23 | 100%
403590 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2013-09-27 | 2014-05-23 | 2014-06-02 | 2014-12-19 | 2015-03-27 | East Lothian | 55258 | -18430.19 | 0 | 0 | 0 | 0 | 0 | -18430.19 | 0 | 36827.81 | 829 | [6 empty] | EC16 | 100%
403592 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2013-09-27 | 2014-09-30 | 2014-09-30 | 2016-09-22 | 2016-10-05 | City of Edinburgh | 231036 | 159888 | 62253.21 | 6233.45 | -6233.45 | 0 | 0 | 222141.21 | 0 | 453177.21 | 356071 | [6 empty] | EC16 | 100% | bar: Regulatory Outputs OMG-48
402688 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-11-19 | 2016-02-02 | 2015-04-14 | 2015-04-14 | 2015-04-14 | Scottish Water Wide | 149291.88 | -11135.82 | 0 | 0 | 0 | 0 | 0 | -11135.82 | 0 | 138156.06 | 0 | [6 empty] | DW9A | 100%
500791 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-10-30 | 2015-10-30 | 2016-05-06 | 2018-04-11 | 2018-04-11 | Scottish Water Wide | 0 | 8028 | 0 | 0 | -7992.86 | 0 | 0 | 35.14 | 0 | 35.14 | 0 | [6 empty] | CM_WSNI | 100%
403916 | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2014-09-03 | 2015-02-16 | 2015-02-18 | 2015-10-15 | 2015-10-15 | Scottish Water Wide | 335925 | 139459.14 | 7022.5 | 0 | 0 | 0 | 0 | 146481.64 | 0 | 482406.64 | 152726 | [6 empty] | CS20 | 100%
402506 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-02-06 | 2012-09-24 | 2013-11-25 | 2016-12-01 |  | Scottish Water Wide | 29728.86 | 4683.4 | -15513.26 | 0 | 0 | 0 | 0 | -10829.86 | 0 | 18899 | 0 | [6 empty] | CM_WSNI | 100%
404110 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-04-24 | 2015-06-10 | 2015-09-07 | 2017-01-20 | 2017-01-20 | Scottish Water Wide | 0 | 233134 | 12140 | 0 | -709.46 | 0 | 0 | 244564.54 | 0 | 244564.54 | 0 | [6 empty] | CM_WSNI | 100%
402462 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2011-12-20 | 2013-01-22 | 2013-01-22 | 2016-02-17 |  | Scottish Water Wide | 1652053 | 57744.73 | 0 | 0 | 0 | 0 | 0 | 57744.73 | 0 | 1709797.73 | 0 | [6 empty] | CM_M&G | 100%
403657 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-01-10 | 2014-01-10 | 2014-01-10 | 2015-02-09 |  | Scottish Water Wide | 256705 | 6426.06 | 0 | 0 | 0 | 0 | 0 | 6426.06 | 0 | 263131.06 | 0 | [6 empty] | CM_M&G | 100%
034813 | Q&S3A | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-12-15 | 2012-09-25 | 2012-11-01 | 2013-03-18 | 2013-03-18 | Scottish Water Wide | 484317 | 4453.16 | 361.52 | 0 | 0 | 0 | 0 | 4814.68 | 0 | 489131.68 | 706365 | [6 empty] | WR1 | 100%
501273 | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | MSU | 2022-05-02 | 2022-05-02 | 2022-05-02 | 2022-05-02 | 2022-05-02 | East Ayrshire | 0 | 0 | 12014.76 | 7849.5 | 17327.94 | 0 | 0 | 37192.2 | 0 | 37192.2 | 0 | [6 empty] | I2S_WI | 100%
046242 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-01-08 | 2010-11-22 | 2011-03-31 | 2014-03-28 | 2014-03-28 | East Ayrshire | 1191831.77 | -555.3 | 0 | 0 | 0 | 0 | 0 | -555.3 | 0 | 1191276.47 | 0 | [6 empty] | CM_WSI | 100%
501274 | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | MSU | 2019-12-05 | 2019-12-05 | 2019-12-05 | 2019-12-05 | 2019-12-05 | East Ayrshire | 0 | 0 | 19382.03 | 20968.07 | 9569.12 | 0 | 0 | 49919.22 | 0 | 49919.22 | 0 | [6 empty] | I2S_WI | 100%
501278 | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | MSU | 2019-06-13 | 2019-06-13 | 2019-06-13 | 2019-06-13 | 2019-06-13 | East Ayrshire | 0 | 0 | 120635.21 | 68964.985 | -104358.875 | 0 | 0 | 85241.32 | 0 | 85241.32 | 0 | [6 empty] | I2S_WI | 100%
402951 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-09-28 | 2013-10-22 | 2013-11-18 | 2014-10-27 |  | East Ayrshire | 263017 | 24 | 251.96 | 0 | 0 | 0 | 0 | 275.96 | 0 | 263292.96 | 0 | [6 empty] | CM_WSNI | 100%
502651 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS0 | 2018-02-21 | 2020-01-20 | 2020-04-20 | 2021-09-06 | 2021-12-07 | South Ayrshire | 0 | 0 | 0 | 8155.105 | 73764.095 | 205663.47 | 278014.55 | 565597.22 | 104402.8 | 670000.02 | 279249.212 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
500650 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-08-19 | 2016-08-29 | 2016-08-29 | 2018-06-14 | 2018-06-14 | Scottish Water Wide | 0 | 283087 | 660952.64 | 621341.5995 | -18146.9145 | 0 | 0 | 1547234.325 | 0 | 1547234.325 | 0 | [6 empty] | CM_M&G | 100%
402658 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2012-05-31 | 2014-05-19 | 2014-05-19 | 2014-03-20 |  | Scottish Water Wide | 1712711.83 | 506.26 | 0 | 0 | 0 | 0 | 0 | 506.26 | 0 | 1713218.09 | 0 | [6 empty] | CM_M&G | 100%
502710 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | Na H-Eileanan an Iar | 0 | 0 | 0 | 2607.67 | 0 | 0 | 0 | 2607.67 | 0 | 2607.67 | 0 | [6 empty] | CM_WWI | 100%
045810 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2011-03-21 | 2014-02-03 | 2014-03-31 | 2014-03-31 | Na H-Eileanan an Iar | 1262685.36 | -18435.15 | 0 | 0 | 0 | 0 | 0 | -18435.15 | 0 | 1244250.21 | 7894 | [6 empty] | WQ01C | 100%
502378 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2016-12-23 | 2022-01-31 | 2022-03-03 | 2022-08-01 | 2022-11-01 | Falkirk | 0 | 0 | 3082.93 | 8720.43 | 8319.685 | 0 | 0 | 20123.045 | 483638.78 | 503761.825 | 0 | [6 empty] | CM_WSNI | 100%
030009 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-09-08 | 2012-01-09 | 2012-03-20 | 2013-07-15 | 2013-10-09 | Falkirk | 2021289.87 | 1874.96 | 0 | 0 | 0 | 0 | 0 | 1874.96 | 0 | 2023164.83 | 4661.5316 | [6 empty] | CM_WWNI | 5% | SG1 | 15% | EC01A | 80%
502874 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS5 | 2017-12-20 | 2018-10-25 | 2018-12-12 | 2019-01-31 | 2019-01-31 | Perth and Kinross | 0 | 0 | 0 | 13775.94 | 68915.06 | 879.11 | 999.9 | 84570.01 | 0 | 84570.01 | 0 | [6 empty] | CM_WWI | 100%
500204 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2015-05-01 | 2017-04-28 | 2017-05-02 | 2018-03-06 | 2018-03-06 | City of Edinburgh | 0 | 205000 | 331514 | 1494098 | -5095.8753 | 0 | 0 | 2025516.1247 | 0 | 2025516.1247 | 0 | [6 empty] | CM_WWNI | 100%
503433 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2019-05-27 | 2019-09-30 | 2019-11-26 | 2020-01-31 | 2020-03-13 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 338592.04 | 11407.92 | 349999.96 | 0 | 349999.96 | 0 | [6 empty] | CM_WSI | 100%
501208 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2016-07-06 | 2016-07-25 | 2016-07-25 | 2018-04-17 | 2018-06-22 | West Dunbartonshire | 0 | 0 | 445.09 | 9044.16 | -9489.25 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | DW25D | 100% | bar: Regulatory Outputs OMG-05
500723 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS0 | 2017-08-28 | 2020-04-06 | 2020-08-11 | 2021-07-09 | 2021-10-07 | Aberdeenshire | 0 | 34493.38 | 59294.5 | 26842.3275 | 10146.9425 | 43799.76 | 415820.23 | 590397.14 | 232763.22 | 823160.36 | 148885.7057 | [6 empty] | SG1 | 100%
401936 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2011-09-12 | 2015-09-11 | 2015-09-14 | 2015-10-23 |  | East Dunbartonshire | 101213 | -2732.23 | 0 | 0 | 0 | 0 | 0 | -2732.23 | 0 | 98480.77 | 0 | [6 empty] | SG5 | 100%
502690 | Q&S4 | Protecting and enhancing the environment | Odour |  |  | Wastewater |  | SWD | Odour | MS7 | 2015-08-01 | 2016-03-01 | 2016-03-01 | 2016-03-01 | 2017-03-23 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CS2 | 100%
503319 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-04-01 | 2022-12-07 | 2023-04-06 | 2024-07-04 | 2024-10-04 | Highland | 0 | 0 | 0 | 0 | 70513.86 | 21816.58 | 63269.5 | 155599.94 | 4344999.96 | 4500599.9 | 0 | [6 empty] | CM_WWNI | 100%
030011 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-23 | 2012-02-21 | 2012-02-21 | 2014-06-11 | 2014-07-02 | South Lanarkshire | 4577775.74 | 32363.33 | -6590.11 | 0 | 0 | 0 | 0 | 25773.22 | 0 | 4603548.96 | 13100.6625 | [6 empty] | EC10A | 10.34% | EC01A | 25.02% | EC04A | 25.02% | CM_WWNI | 39.63%
402221 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2011-09-27 | 2011-09-27 | 2011-10-10 | 2019-07-09 |  | South Lanarkshire | 732771.85 | 296.49 | 112.5 | 667.8375 | 0.0025 | 0 | 0 | 1076.83 | 0 | 733848.68 | 0 | [6 empty] | CM_WWNI | 100%
403883 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2014-07-24 | 2014-10-02 | 2014-10-02 | 2018-09-03 | 2018-09-03 | Scottish Water Wide | 449856 | 136096 | -41186.42 | 139635.923 | -139635.92 | 0 | 0 | 94909.583 | 0 | 544765.583 | 0 | [6 empty] | CM_M&G | 100%
045302 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-24 | 2011-03-17 | 2011-07-22 | 2013-03-22 | 2013-04-10 | Highland | 232842.88 | -137.68 | 0 | 0 | 0 | 0 | 0 | -137.68 | 0 | 232705.2 | 0 | [6 empty] | DW13 | 100%
502739 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2017-05-31 | 2018-03-23 | 2018-05-11 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 459488.53 | 690864.93 | 636464.67 | 149455.36 | 1936273.49 | 63726 | 1999999.49 | 0 | [6 empty] | CM_WSI | 100%
500111 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-17 | 2017-03-17 | 2017-05-08 | 2018-06-18 | 2018-07-20 | Clackmannanshire | 0 | 10830 | 51324 | 55724.67 | 5685.0275 | 0 | 0 | 123563.6975 | 0 | 123563.6975 | 278002.7669 | [6 empty] | CS16D | 100%
402874 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-12-21 | 2016-02-15 | 2016-02-01 | 2016-02-19 |  | Clackmannanshire | 67374 | 660 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | 68034 | 0 | [6 empty] | CM_WWI | 100%
501159 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS2 | 2016-07-07 | 2018-12-31 | 2019-07-31 | 2020-10-21 | 2021-01-27 | Clackmannanshire | 0 | 0 | 54819.57 | 236259.02 | 680414.51 | 2754057.28 | 729825.92 | 4455376.3 | 31907.67 | 4487283.97 | 0 | [6 empty] | CM_WWNI | 100%
500195 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS5 | 2015-03-20 | 2016-03-14 | 2016-03-21 | 2016-11-30 | 2017-02-28 | Angus | 0 | 11755 | 29014.14 | 8298.07 | 442.47 | 0 | 0 | 49509.68 | 0 | 49509.68 | 14844.4817 | [6 empty] | EC08C | 100% | bar: Regulatory Outputs OMG-23
503234 | Q&S4 | Protecting and enhancing the environment | Habitats Directive |  |  | Wastewater |  | SWMD | Habitats Directive | MS1 | 2018-06-29 | 2019-08-12 | 2019-10-28 | 2020-12-14 | 2021-03-22 | Highland | 0 | 0 | 0 | 0 | 88200.69 | 167440.58 | 214915.62 | 470556.89 | 50899.14 | 521456.03 | 476250.6854 | [6 empty] | EC08D | 100%
400723 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-04-14 | 2013-03-18 | 2013-05-21 | 2013-11-15 | 2013-11-15 | Perth and Kinross | 251977 | -6059.86 | 0 | 0 | 0 | 0 | 0 | -6059.86 | 0 | 245917.14 | 0 | [6 empty] | SG1 | 100%
500189 | Q&S4 | Protecting and enhancing the environment | Odour |  |  | Wastewater |  | SWD | Odour | MS7 | 2015-03-16 | 2015-10-02 | 2015-10-02 | 2015-03-13 | 2015-10-02 | Highland | 0 | 0.07 | 0 | -318.33 | 0 | 0 | 0 | -318.26 | 0 | -318.26 | 2505.2077 | [6 empty] | CS2 | 100% | bar: Regulatory Outputs OMG-29
500854 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-03-31 | 2018-03-23 | 2018-06-14 | 2019-03-27 | 2019-12-20 | City of Edinburgh | 0 | 22932.61 | 23674.39 | 51034.96 | 209635.39 | 18257.55 | 0 | 325534.9 | 0 | 325534.9 | 820835.2647 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 44.46
501387 | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWMD | Energy efficiency | MS7 | 2016-09-26 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | City of Edinburgh | 0 | 0 | 309793 | 59612 | -24636.572 | 0 | 0 | 344768.428 | 0 | 344768.428 | 0 | [6 empty] | I2S_WI | 18.62% | CM_WSI | 81.38%
403410 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2013-03-01 | 2015-02-18 | 2015-02-23 | 2015-02-24 | 2015-02-24 | City of Edinburgh | 1763.37 | 0 | 0 | 275.625 | 0 | 0 | 0 | 275.625 | 0 | 2038.995 | 0 | [6 empty] | CC1W | 100%
502401 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2016-12-13 | 2016-12-13 | 2017-02-15 | 2018-07-20 | 2018-07-20 | City of Edinburgh | 0 | 0 | 556674 | 2046423.88 | 136945.93 | 3867.72 | 3885.48 | 2747797.01 | 2053.44 | 2749850.45 | 0 | [6 empty] | CM_WSI | 100%
501222 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2015-11-18 | 2021-09-20 | 2022-01-14 | 2022-08-11 | 2022-11-08 | Moray | 0 | 5969.18 | 23718.82 | 2768.29 | 0 | 0 | 0 | 32456.29 | 1830572.73 | 1863029.02 | 0 | [6 empty] | CM_WWI | 100%
402202 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-07-01 | 2013-07-24 | 2013-09-30 | 2015-03-27 | 2015-03-27 | Angus | 2016856 | 483832 | -79.17 | 1887.66 | 0 | 0 | 0 | 485640.49 | 0 | 2502496.49 | 0 | [6 empty] | SG1 | 100%
403864 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-07-31 | 2015-02-26 | 2015-02-26 | 2017-09-01 |  | Scottish Water Wide | 898925 | 1069828 | 246951 | -117775.09 | 0 | 0 | 0 | 1199003.91 | 0 | 2097928.91 | 0 | [6 empty] | CM_M&G | 100%
502258 | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | WWINF | Exceptional Capital Maintenance | MS5 | 2016-06-17 | 2016-06-17 | 2016-07-01 | 2018-09-28 | 2018-09-28 | East Renfrewshire | 0 | 0 | 20899687 | 2303097 | 1491496 | 432940 | 0 | 25127220 | 2586 | 25129806 | 0 | [6 empty] | SR15_EXC_EXC | 100%
503194 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS3 | 2018-06-28 | 2019-01-31 | 2019-01-31 | 2021-02-24 | 2021-12-28 | East Ayrshire | 0 | 0 | 0 | 0 | 821924 | 1774028.47 | 2337580.14 | 4933532.61 | 19479.32 | 4953011.93 | 0 | [6 empty] | DW5FS | 4.745% | DW5MR | 95.26%
503193 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2018-06-28 | 2018-12-21 | 2019-03-28 | 2019-12-20 | 2020-12-14 | East Ayrshire | 0 | 0 | 0 | 0 | 227645.55 | 215473.36 | 0 | 443118.91 | 0 | 443118.91 | 0 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 84.152
502607 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2018-06-28 | 2018-12-20 | 2019-03-28 | 2019-12-23 | 2020-03-30 | East Ayrshire | 0 | 0 | 46347 | 250250.905 | 135664.095 | 90340.16 | 37293 | 559895.16 | 4917.91 | 564813.07 | 522741.6786 | [6 empty] | DW5MC | 100% | [18 empty] | Regulatory Outputs OMG-06: 36.366
503069 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS3 | 2018-02-12 | 2018-02-12 | 2018-06-13 | 2019-10-25 | 2019-10-28 | North Ayrshire | 0 | 0 | 0 | 21602.312 | 93852.258 | 140063.85 | 947.63 | 256466.05 | 1533.9 | 257999.95 | 4534308.9311 | [6 empty] | DW25P | 100%
402614 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2012-03-27 | 2012-03-27 | 2012-04-02 | 2019-07-26 |  | East Ayrshire | 841384 | 31616 | 62477.35 | 66188.06 | 0 | 0 | 0 | 160281.41 | 0 | 1001665.41 | 0 | [6 empty] | CM_WSNI | 100%
403572 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-08-30 | 2013-08-30 | 2013-08-30 | 2015-07-31 |  | Scottish Water Wide | 568891.54 | 8644.95 | 0 | 0 | 0 | 0 | 0 | 8644.95 | 0 | 577536.49 | 0 | [6 empty] | CM_M&G | 100%
500919 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2016-06-30 | 2016-07-01 | 2017-09-11 | 2017-09-11 | Angus | 0 | 8951.12 | 62105.02 | -51525 | 0 | 0 | 0 | 19531.14 | 0 | 19531.14 | 144841.4737 | [6 empty] | CS15A | 100%
503385 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-02-26 | 2019-02-26 | 2019-02-26 | 2019-02-26 | 2019-02-26 | Aberdeenshire | 0 | 0 | 0 | 0 | 64479.976 | 0 | 0 | 64479.976 | 0 | 64479.976 | 148885.7057 | [6 empty] | SG1 | 100%
500114 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS4 | 2015-03-17 | 2016-02-26 | 2016-08-11 | 2019-03-21 | 2019-07-05 | Dumfries and Galloway | 0 | 30381 | 102008.99 | 55979.53 | 9737 | 462.4 | 0.1 | 198569.02 | 0 | 198569.02 | 42581.501 | [6 empty] | EC01G | 7.97% | EC01D | 39.2% | CS16D | 52.83%
500113 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS5 | 2015-03-17 | 2016-02-26 | 2016-03-21 | 2018-12-11 | 2019-03-22 | Fife | 0 | 21739 | 31819.52 | 51739.48 | 15842 | 2662.44 | 0 | 123802.44 | 0 | 123802.44 | 4782.2082 | [6 empty] | CS16D | 100%
502626 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-04 | 2027-07-19 | 2027-09-30 | 2028-09-05 | 2028-12-06 | Highland | 0 | 0 | 20930.23 | 415.9 | 1196.3 | 12217.86 | 12170.51 | 46930.8 | 7953089.15 | 8000019.95 | 148885.7057 | [6 empty] | WG1 | 100%
501922 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2019-01-15 | 2019-01-15 | 2019-01-15 | 2019-09-27 | 2019-09-27 | Scottish Water Wide | 0 | 0 | 0 | 0 | 459619.24 | 191948.66 | 0 | 651567.9 | 0 | 651567.9 | 0 | [6 empty] | CM_M&G | 100%
500587 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-01-18 | 2016-08-22 | 2016-08-22 | 2017-10-12 | 2017-04-20 | Scottish Water Wide | 0 | 196259 | 17838.39 | 27739.32 | 0 | 0 | 0 | 241836.71 | 0 | 241836.71 | 0 | [6 empty] | CM_M&G | 100%
403797 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-06-11 | 2014-06-11 | 2014-06-26 | 2015-03-12 |  | Scottish Water Wide | 2012615 | -15928.57 | 0 | 0 | 0 | 0 | 0 | -15928.57 | 0 | 1996686.43 | 0 | [6 empty] | CM_M&G | 100%
500435 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2015-04-30 | 2017-10-18 | 2018-03-06 | 2019-05-01 | 2019-05-01 | Angus | 0 | 36000 | 35530 | 336259 | 246268 | 0 | 0 | 654057 | 2400 | 656457 | 0 | [6 empty] | CM_WWNI | 28% | CM_WWI | 72%
500989 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-09-25 | 2016-05-12 | 2016-05-12 | 2016-05-12 |  | Scottish Water Wide | 0 | 62742.86 | 0 | 0 | 0 | 0 | 0 | 62742.86 | 0 | 62742.86 | 0 | [6 empty] | CM_M&G | 100%
500115 | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-17 | 2015-11-30 | 2016-01-12 | 2017-02-02 | 2017-07-01 | Highland | 0 | 49955 | 86901.95 | -3667.97 | 0 | 0 | 0 | 133188.98 | 0 | 133188.98 | 561676.3877 | [6 empty] | CS15 | 33.33% | CS16D | 33.33% | CS11 | 33.33% | bar: Regulatory Outputs OMG-22
501290 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS3 | 2015-12-24 | 2018-05-31 | 2018-06-26 | 2020-06-24 | 2020-09-16 | Highland | 0 | 33462 | 284751.32 | 487405.34 | 5031420.48 | 4991345.37 | 76891.07 | 10905275.58 | 54724.47 | 10960000.05 | 148885.7057 |  |  |  |  | 255440.0003 |  | SG1 | 100%
500649 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS3 | 2015-06-30 | 2018-11-07 | 2018-12-10 | 2019-06-01 | 2019-09-01 | Highland | 0 | 61832 | 345821.35 | 613713.65 | 2668752 | 907746.9 | 0 | 4597865.9 | 0 | 4597865.9 | 0 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-48
500012 | Q&S4 | Protecting and enhancing the environment | Habitats Directive |  |  | Wastewater |  | NONINF | Habitats Directive | MS5 | 2015-06-17 | 2016-11-30 | 2016-12-07 | 2017-11-01 | 2018-01-01 | Highland | 0 | 88006 | 841003.84 | 1509147.92 | -1647243.3 | 29456.53 | 0 | 820370.99 | 0 | 820370.99 | 267829.323 | [6 empty] | EC08A | 100% | bar: Regulatory Outputs OMG-26
045305 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-24 | 2011-03-31 | 2011-05-16 | 2011-10-24 | 2011-12-07 | Argyll and Bute-North Argyll | 41157.73 | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 41169.73 | 0 | [6 empty] | DW13 | 100%
502316 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-03 | 2027-11-22 | 2028-03-30 | 2029-03-21 | 2029-06-21 | Argyll and Bute-North Argyll | 0 | 0 | 26143.02 | 3238.09 | 1237.31 | 14221.98 | 14166.86 | 59007.26 | 4941012.97 | 5000020.23 | 148885.7057 | [6 empty] | WG1 | 100%
501183 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-03-23 | 2019-03-12 | 2018-02-01 | 2019-01-28 | 2019-01-28 | Glasgow City | 0 | 0 | 52000 | 35130.2841 | -87129.2841 | 0 | 0 | 1 | 0 | 1 | 229318.7788 | [6 empty] | CS11A | 100%
402632 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2012-06-11 | 2014-01-21 | 2014-02-03 | 2015-03-01 | 2015-05-01 | Highland | 840340 | 69475 | -5975.51 | -1387.53 | 0 | 0 | 0 | 62111.96 | 0 | 902451.96 | 3783756.1971 | [6 empty] | SG5 | 100% | [18 empty] | Regulatory Outputs OMG-17: 3
501330 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2016-05-11 | 2017-07-27 | 2017-10-30 | 2018-03-30 | 2018-03-30 | Inverclyde | 0 | 0 | 49217 | 830835 | 43922 | 0 | 0 | 923974 | 0 | 923974 | 0 | [6 empty] | CM_WWNI | 100%
500121 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2015-03-17 | 2016-06-27 | 2016-08-24 | 2019-09-27 | 2019-12-27 | West Dunbartonshire | 0 | 17396 | 68936 | 218548.35 | 150000 | 62569.21 | 32550.46 | 550000.02 | 0 | 550000.02 | 174067.5848 | [6 empty] | EC01G | 10.86% | EC01D | 40.15% | CS16D | 48.99%
501158 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-12-14 | 2018-10-15 | 2018-10-22 | 2019-12-05 | 2020-03-11 | West Dunbartonshire | 0 | 20690 | 258206.33 | 175176.19 | 506094.218 | 1318546.72 | 62951.45 | 2341664.908 | 43600.61 | 2385265.518 | 0 |  |  |  |  | 40329.9996 |  | CM_WWNI | 100%
503416 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2020-04-01 | 2021-08-20 | 2022-01-06 | 2023-03-15 | 2023-06-15 | Highland | 0 | 0 | 0 | 0 | 60503.3 | 82083.36 | 26772.89 | 169359.55 | 331227.14 | 500586.69 | 148885.7057 | [6 empty] | SG1 | 100%
501187 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-11-12 | 2016-06-28 | 2016-08-08 | 2018-02-09 | 2018-02-09 | Na H-Eileanan an Iar | 0 | 3276 | 19316.83 | 60691.04 | -781.14 | 0 | 0 | 82502.73 | 0 | 82502.73 | 0 | [6 empty] | CM_WSI | 100%
403552 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS3 | 2013-09-25 | 2018-11-29 | 2018-11-30 | 2019-05-23 | 2019-05-23 | Glasgow City | 65107.01 | 39892.99 | 27387 | 33994.1166 | 128616.3634 | 1593.7 | 0 | 231484.17 | 0.3 | 296591.48 | 1030932.5573 | [6 empty] | CS11A | 5.715% | CS11 | 94.28%
500793 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS0 | 2016-06-28 | 2020-09-14 | 2020-10-12 | 2022-03-17 | 2022-06-29 | Argyll and Bute-North Argyll | 0 | 0 | 13644.19 | 225569.48 | 65768.43 | 951352.22 | 500731.87 | 1757066.19 | 1593188.86 | 3350255.05 | 0 | [6 empty] | CM_WSNI | 100%
500906 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-27 | 2016-10-14 | 2016-10-14 | 2016-10-14 | 2016-10-14 | Argyll and Bute-Cowal & Bute | 0 | 4940.33 | 679.91 | 0 | 0 | 0 | 0 | 5620.24 | 0 | 5620.24 | 144841.4737 | [6 empty] | CS15A | 100%
500224 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS5 | 2015-03-20 | 2016-03-30 | 2016-06-28 | 2017-12-01 | 2018-06-01 | Argyll and Bute-North Argyll | 0 | 561.48 | 28073.18 | 17720.1776 | 1653.3024 | 1000 | 0 | 49008.14 | 0 | 49008.14 | 219331.0989 | [6 empty] | DW5FS | 100% | bar: Regulatory Outputs OMG-02
502315 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-14 | 2027-11-22 | 2028-03-30 | 2029-03-21 | 2029-06-21 | Argyll and Bute-North Argyll | 0 | 0 | 25265.2 | 43741.871 | 4014.309 | 11162.79 | 11119.53 | 95303.7 | 4904859.41 | 5000163.11 | 148885.7057 | [6 empty] | WG1 | 100%
500821 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-08-24 | 2015-09-22 | 2015-09-23 | 2018-03-07 | 2018-03-07 | Renfrewshire | 0 | 44095.56 | 8998.91 | -3488.7 | 0 | 0 | 0 | 49605.77 | 0 | 49605.77 | 144841.4737 | [6 empty] | CS15A | 100%
501548 | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWMD | Renewable power | MS7 | 2015-12-24 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | Falkirk | 0 | 5923 | 61503.07 | 0 | 0 | 0 | 0 | 67426.07 | 0 | 67426.07 | 764721.6298 | [6 empty] | I2S_WI | 100%
500670 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS3 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2019-05-28 | 2019-05-28 | East Lothian | 0 | 409914 | -208778.24 | 0 | 273.225 | 0 | 0 | 201408.985 | 0 | 201408.985 | 3783756.1971 | [6 empty] | SG5 | 100%
501713 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2016-07-19 | 2021-04-30 | 2021-07-26 | 2021-12-07 | 2022-03-09 | West Lothian | 0 | 0 | 15078 | 9922 | 0 | 0 | 0 | 25000 | 147153.04 | 172153.04 | 0 | [6 empty] | CM_WWI | 100%
030028 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-16 | 2010-09-20 | 2011-03-17 | 2013-03-18 | 2013-03-18 | West Lothian | 1579435.98 | 508.04 | 0 | 0 | 0 | 0 | 0 | 508.04 | 0 | 1579944.02 | 0 | [6 empty] | CM_WWNI | 50% | EC01A | 50%
403997 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-12-23 | 2016-01-29 | 2016-05-03 | 2017-02-13 | 2017-03-22 | Highland | 24239 | 95460 | 368953.18 | 2495.22 | 894.07 | 0 | 0 | 467802.47 | 0 | 492041.47 | 717180 | [6 empty] | DW23 | 100%
502370 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-05-20 | 2022-01-17 | 2022-05-19 | 2023-12-13 | 2024-03-14 | Highland | 0 | 0 | 5006.46 | 28996.65 | 2038.63 | 0 | 0 | 36041.74 | 736252.3 | 772294.04 | 0 | [6 empty] | CM_WSNI | 100%
046849 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2016-04-01 | 2014-09-17 | 2014-11-04 | 2014-11-04 | Highland | 238767.23 | -2 | 0 | 0 | 0 | 0 | 0 | -2 | 0 | 238765.23 | 0 | [6 empty] | DW23 | 100%
503470 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2021-04-01 | 2021-04-01 | 2021-04-08 | 2021-05-19 | 2021-08-19 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 61600 | 0 | 61600 | 567028.68 | 628628.68 | 0 | [6 empty] | CM_WWI | 100%
501721 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2021-07-07 | 2022-05-12 | 2022-09-15 | 2023-01-25 | 2023-04-27 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12073.03 | 12073.03 | 0 | [6 empty] | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 33.33% | CM_WSI | 42.86%
401323 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2010-09-13 | 2011-02-04 | 2011-04-01 | 2017-01-31 |  | Scottish Water Wide | 1029421 | 50407 | 6006.06 | 0 | 0 | 0 | 0 | 56413.06 | 0 | 1085834.06 | 0 | [6 empty] | CM_M&G | 100%
030030 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2010-06-28 | 2010-09-06 | 2011-12-22 | 2012-01-10 | South Lanarkshire | 1787178.82 | 189.37 | 0 | 0 | 0 | 0 | 0 | 189.37 | 0 | 1787368.19 | 0 | [6 empty] | CM_WWNI | 19.64% | EC04A | 80.36%
503405 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS0 | 2018-10-12 | 2019-08-26 | 2019-11-07 | 2020-04-07 | 2020-07-14 | South Lanarkshire | 0 | 0 | 0 | 0 | 40178 | 700168.49 | 83523.99 | 823870.48 | 6123.51 | 829993.99 | 229318.7788 | [6 empty] | CS11 | 100%
403435 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2013-04-16 | 2019-03-06 | 2019-03-06 | 2019-01-14 | 2019-01-14 | South Lanarkshire | 120677.02 | 7647.98 | 24700 | 33318.8741 | 24566.0605 | 0 | 0 | 90232.9146 | 0 | 210909.9346 | 0 | [6 empty] | CM_WWI | 28% | CS11A | 72%
501620 | Q&S4 | Improving drinking water availability and resilience of service | Pressure |  |  | Water |  | SWD | Pressure | MS7 | 2016-02-12 | 2016-07-14 | 2016-08-15 | 2018-02-01 | 2018-02-01 | Scottish Water Wide | 0 | 319.15 | 30478.26 | 104552.2825 | -1250.6 | 0 | 0 | 134099.0925 | 0 | 134099.0925 | 234830.2329 | [6 empty] | CS1B | 100%
403915 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2014-12-10 | 2015-03-09 | 2015-03-10 | 2015-05-15 | 2015-08-06 | Scottish Water Wide | 124054 | -6078.08 | 0 | 0 | 0 | 0 | 0 | -6078.08 | 0 | 117975.92 | 0 | [6 empty] | CS18W | 100%
400661 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-04-02 | 2012-05-23 | 2012-05-23 | 2014-04-11 |  | Scottish Water Wide | 7108827.57 | 0 | 0 | 145.565 | 0 | 0 | 0 | 145.565 | 0 | 7108973.135 | 0 | [6 empty] | CM_M&G | 100%
500053 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-02-13 | 2016-07-13 | 2016-07-14 | 2016-07-28 | 2016-07-28 | Dundee City | 0 | 2012.48 | 471.18 | 0 | 0 | 0 | 0 | 2483.66 | 0 | 2483.66 | 0 | [6 empty] | CM_WSI | 100%
503089 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-04-15 | 2022-09-16 | 2023-01-13 | 2024-01-04 | 2024-04-05 | Highland | 0 | 0 | 0 | 21827.479 | 25729.116 | 0 | 0 | 47556.595 | 953546.54 | 1001103.135 | 0 | [6 empty] | CM_WSNI | 100%
403558 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2013-08-27 | 2014-08-20 | 2014-08-27 | 2015-12-21 | 2015-12-21 | Highland | 155920 | 280688 | 6104.95 | -3553.68 | 0 | 0 | 0 | 283239.27 | 0 | 439159.27 | 0 | [6 empty] | WG5 | 100%
503063 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-04-06 | 2022-03-17 | 2022-06-03 | 2023-03-06 | 2023-06-06 | Highland | 0 | 0 | 0 | 21627.782 | 139841.988 | 56779.92 | 75930.06 | 294179.75 | 3505820.29 | 3800000.04 | 0 | [6 empty] | CM_WSI | 100%
403171 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-03-11 | 2013-03-11 | 2013-07-15 | 2016-03-25 |  | Highland | 734085 | 169803 | 14576.17 | 463.9765 | 0 | 0 | 0 | 184843.1465 | 0 | 918928.1465 | 0 | [6 empty] | CM_WSI | 100%
500753 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2015-08-27 | 2021-12-20 | 2022-02-10 | 2022-03-23 | 2022-06-16 | Highland | 0 | 95506 | 39579.88 | 589.87 | 446.09 | 0 | 0 | 136121.84 | 1318878.17 | 1455000.01 | 0 | [6 empty] | CM_WSNI | 100%
502833 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2018-07-17 | 2018-07-17 | 2018-07-17 | 2018-07-17 | 2018-07-17 | Highland | 0 | 0 | 0 | 20520.166 | 2247.795 | 0 | 0 | 22767.961 | 0 | 22767.961 | 0 | [6 empty] | CM_WSI | 100%
503402 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-06-07 | 2022-09-16 | 2023-01-09 | 2023-08-25 | 2023-11-27 | Highland | 0 | 0 | 0 | 0 | 24279.1 | 11434.44 | 20697.16 | 56410.7 | 717868.4 | 774279.1 | 0 | [6 empty] | CM_WSNI | 100%
500789 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | NONINF | Supply Resilience | MS3 | 2015-09-17 | 2017-12-22 | 2017-12-22 | 2019-06-01 | 2019-11-01 | Highland | 0 | 126145 | 212052.45 | 1043502.58 | 3865138.5 | 479957.13 | 33884.98 | 5760680.64 | 7515.34 | 5768195.98 | 1817908.3275 |  |  |  |  | 36710.0004 |  | CS16WR | 100% | bar: Regulatory Outputs OMG-07
032111 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2005-09-20 | 2008-03-28 | 2008-08-18 | 2010-04-30 | 2011-03-31 | Highland | 19237618.42 | 0.58 | 29 | 0 | 0 | 0 | 0 | 29.58 | 0 | 19237648 | 0 | [6 empty] | DW13 | 13.25% | DW3B | 13.25% | DW3J | 13.25% | DW4A | 13.25% | WSNI | 20% | WG1 | 27%
503258 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-28 | 2023-07-13 | 2023-11-14 | 2024-11-07 | 2025-02-07 | East Lothian | 0 | 0 | 0 | 0 | 80855.55 | 10008.73 | 15552.4 | 106416.68 | 39446.73 | 145863.41 | 148885.7057 | [6 empty] | SG1 | 100%
501551 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2021-04-14 |  |  | 2021-04-14 | 2021-04-14 | Scottish Water Wide | 0 | 91261.68 | -90741.92 | -519.76 | 0 | 5249238 | 5249237.97 | 10498475.97 | 0 | 10498475.97 | 0 | [6 empty] | CM_WWI | 100%
402178 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-06-28 | 2012-03-27 | 2012-06-18 | 2014-12-08 | 2014-12-08 | Argyll and Bute-North Argyll | 350229.84 | -2299.18 | 0 | 0 | 0 | 0 | 0 | -2299.18 | 0 | 347930.66 | 0 | [6 empty] | CM_WSI | 100%
501224 | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | General |  | SWMD | Developer Asset Adoption | MS6 | 2016-02-22 | 2016-11-21 | 2016-11-29 | 2018-03-27 | 2018-03-27 | North Ayrshire | 0 | 74252 | 100211.8 | 293385 | 177 | 2175.42 | 2124.56 | 472325.78 | 23.12 | 472348.9 | 0 | [6 empty] | SG6 | 100%
503221 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-10 | 2023-06-23 | 2023-10-20 | 2024-10-16 | 2025-01-16 | Aberdeen City | 0 | 0 | 0 | 0 | 80312.101 | 11606.87 | 31108.73 | 123027.701 | 24451.16 | 147478.861 | 148885.7057 | [6 empty] | SG1 | 100%
503162 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2018-08-27 | 2018-08-27 | 2020-01-13 | 2020-09-07 | 2020-12-08 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 37074.77 | 130003.7 | 303229.86 | 470308.33 | 4691.61 | 474999.94 | 0 | [6 empty] | CM_WSNI | 100%
404090 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS3 | 2015-07-17 | 2015-07-17 | 2015-07-17 | 2019-07-26 | 2019-07-26 | Perth and Kinross | 0 | 96394 | 4000 | 922630.13 | 0 | 0 | 0 | 1023024.13 | 0 | 1023024.13 | 0 | [6 empty] | WG5 | 100%
503282 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-17 | 2023-05-31 | 2023-10-03 | 2024-09-30 | 2024-12-31 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 74149.38 | 13808.97 | 34484.05 | 122442.4 | 21769.68 | 144212.08 | 148885.7057 | [6 empty] | SG1 | 100%
502846 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-04-02 | 2027-12-06 | 2028-04-04 | 2029-03-30 | 2029-07-02 | Highland | 0 | 0 | 0 | 20930.23 | 2496.43 | 27000.41 | 0 | 50427.07 | 7949999.99 | 8000427.06 | 148885.7057 | [6 empty] | WG1 | 100%
501188 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2015-11-12 | 2016-07-29 | 2016-11-28 | 2017-08-29 | 2017-08-29 | Highland | 0 | 8324 | 731271.07 | 189546.62 | 17719.66 | 798.06 | 0 | 947659.41 | 0 | 947659.41 | 0 | [6 empty] | CM_WSNI | 100%
502562 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-14 | 2027-11-29 | 2028-03-22 | 2029-03-12 | 2029-06-12 | Highland | 0 | 0 | 0 | 11848.306 | 1899.582 | 5355.72 | 5334.96 | 24438.568 | 9975643.37 | 10000081.938 | 148885.7057 | [6 empty] | WG1 | 100%
404069 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS3 | 2015-03-09 | 2018-01-31 | 2018-10-31 | 2020-02-28 | 2020-03-02 | Highland | 2936.05 | 146656.95 | 365789.82 | 451304.76 | 1134971.62 | 1081640.54 | 45800.84 | 3226164.53 | 15949.42 | 3245050 | 0 |  |  |  |  | 177.84 |  | SG1 | 100%
402228 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2011-07-29 | 2012-02-14 | 2012-04-10 | 2020-02-10 |  | Falkirk | 870005 | -290488 | 19584.27 | 53384.96 | 149760.77 | 83574.88 | 69358.16 | 85175.04 | 1531.52 | 956711.56 | 0 | [6 empty] | CM_WSI | 100%
501799 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2017-04-28 | 2019-01-29 | 2019-03-11 | 2019-09-18 | 2019-12-19 | City of Edinburgh | 0 | 0 | 4742.5 | 13656.5 | 52483 | 15591.98 | 0 | 86473.98 | 1167 | 87640.98 | 0 | [6 empty] | CM_WWI | 100%
401207 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-07-15 | 2011-07-06 | 2011-08-29 | 2013-03-28 |  | South Ayrshire | 1661943.78 | 35525.22 | 0.26 | 120084.4855 | 0 | 0 | 0 | 155609.9655 | 0 | 1817553.7455 | 0 | [6 empty] | CM_WSI | 100%
503507 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2019-04-01 | 2019-04-01 | 2019-04-01 | 2019-04-08 | 2019-04-12 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 130317 | 0 | 130317 | 0 | 130317 | 0 | [6 empty] | CM_WSI | 100%
400288 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-03-17 | 2011-11-21 | 2012-02-06 | 2013-02-07 |  | Inverclyde | 629609 | 0 | -34550.53 | 27.2765 | 0 | 0 | 0 | -34523.2535 | 0 | 595085.7465 | 0 | [6 empty] | CM_WSI | 100%
401500 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-15 | 2012-03-26 | 2012-04-30 | 2015-03-26 |  | All West Unitary Authorities | 396128 | 3750 | -1395.66 | 0 | 0 | 0 | 0 | 2354.34 | 0 | 398482.34 | 0 | [6 empty] | CM_WSI | 100%
503393 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2018-10-02 | 2018-10-02 | 2018-10-15 | 2019-10-04 | 2019-10-07 | South Ayrshire | 0 | 0 | 0 | 0 | 1244866.77 | 240133.22 | 0 | 1484999.99 | 0 | 1484999.99 | 0 | [6 empty] | CM_WWNI | 100%
033957 | Q&S3A | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2007-03-27 | 2008-02-12 | 2008-04-14 | 2010-03-31 |  | South Ayrshire | 8357062.73 | 48495.27 | 102708.9 | 0 | 0 | 0 | 0 | 151204.17 | 0 | 8508266.9 | 0 | [6 empty] | WWI | 3.82% | WWNI | 96.18%
500704 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2015-06-12 | 2019-07-15 | 2019-10-14 | 2020-03-25 | 2020-05-20 | Orkney Islands | 0 | 56471 | 29804 | 31758.11 | 5554.53 | 0 | 0 | 123587.64 | 0 | 123587.64 | 0 | [6 empty] | CM_WWNI | 100%
502834 | Q&S4 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWMD | Revised Bathing Waters Directive | GW1 | 2019-06-25 | 2021-07-26 | 2021-12-16 | 2023-03-20 | 2023-06-20 | East Ayrshire | 0 | 0 | 0 | 148647.655 | 278937.345 | 0 | 0 | 427585 | 0 | 427585 | 2269817.6904 | [6 empty] | EC16B | 100%
500523 | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | WINF | Exceptional Capital Maintenance | MS0 | 2016-11-02 | 2020-06-22 | 2020-08-24 | 2022-08-01 | 2022-12-01 | South Ayrshire | 0 | 331276.92 | 292053.08 | 753269 | 750440.0405 | 593999.96 | 5036145.34 | 7757184.3405 | 37245986.14 | 45003170.4805 | 0 | [6 empty] | SR15_EXC_EXC | 100% | bar: Regulatory Outputs OMG-07
502278 | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | WINF | Exceptional Capital Maintenance | MS5 | 2016-09-14 | 2017-05-30 | 2017-05-30 | 2019-03-27 | 2019-03-29 | East Ayrshire | 0 | 0 | 1776359 | 41280859 | 14894029.84 | 719244.04 | 0 | 58670491.88 | 0 | 58670491.88 | 0 | [6 empty] | SR15_EXC_EXC | 100%
403887 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2014-07-10 | 2015-01-23 | 2015-01-26 | 2016-08-12 |  | East Ayrshire | 1500715 | 2698535 | 666534 | -26022 | -157670.288 | 0 | 0 | 3181376.712 | 0 | 4682091.712 | 0 | [6 empty] | CM_WSI | 100%
403889 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS4 | 2014-07-10 | 2015-05-25 | 2015-06-25 | 2018-08-20 |  | South Ayrshire | 114943.4 | 3927523.6 | 3535670 | 2542941.82 | 244235.1 | 0 | 0 | 10250370.52 | 0 | 10365313.92 | 0 | [6 empty] | CM_WSI | 100%
403888 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS4 | 2014-07-10 | 2015-12-03 | 2015-12-07 | 2018-07-30 |  | South Ayrshire | 298158.19 | 1864758.81 | 5341320 | 4501579.626 | 135118.224 | 0 | 0 | 11842776.66 | 0 | 12140934.85 | 0 | [6 empty] | CM_WSI | 100%
403890 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS4 | 2014-07-10 | 2015-03-30 | 2015-04-16 | 2017-05-10 |  | Inverclyde | 146251 | 718528 | 79562.03 | -21334.5 | -267080.245 | 75.97 | 0 | 509751.255 | 0 | 656002.255 | 0 | [6 empty] | CM_WSI | 100%
403891 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2014-07-10 | 2015-03-30 | 2015-03-30 | 2017-05-18 |  | Renfrewshire | 615298 | 1495271 | 199767.38 | -39500.79 | -160426.72 | 0 | 0 | 1495110.87 | 0 | 2110408.87 | 0 | [6 empty] | CM_WSI | 100%
403863 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-11 | 2014-06-11 | 2014-06-11 | 2017-03-09 |  | South Ayrshire | 9350 | 40650 | -43941.21 | -1071.73 | 0 | 0 | 0 | -4362.94 | 0 | 4987.06 | 0 | [6 empty] | CM_WSI | 100%
403568 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS7 | 2013-08-30 | 2015-01-20 | 2015-01-26 | 2015-03-30 | 2015-03-30 | City of Edinburgh | 143194 | 16786.07 | -0.01 | 783.45 | 0 | 0 | 0 | 17569.51 | 0 | 160763.51 | 366789.9202 | [6 empty] | CS11 | 100%
502600 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS0 | 2016-05-18 | 2019-04-29 | 2019-05-03 | 2020-12-01 | 2021-03-01 | Na H-Eileanan an Iar | 0 | 0 | 0 | 232046 | 573417.96 | 3384526.8 | 4699063.64 | 8889054.4 | 362154.61 | 9251209.01 | 3021114.6704 | [6 empty] | DW25P | 6.879% | DW3B | 93.12% | bar: Regulatory Outputs OMG-01
500795 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS5 | 2015-10-28 | 2016-03-31 | 2016-05-30 | 2017-09-25 | 2019-02-15 | Highland | 0 | 89774 | 110985.97 | 186230.4026 | 80328.3541 | 8449.25 | 0 | 475767.9767 | 0 | 475767.9767 | 801436.2274 | [6 empty] | DW5FS | 100%
403721 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-02-12 | 2014-05-27 | 2014-06-30 | 2015-01-05 |  | Highland | 309486.23 | 811.81 | 342.64 | 0 | 0 | 0 | 0 | 1154.45 | 0 | 310640.68 | 0 | [6 empty] | CM_WSI | 100%
403383 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-03-07 | 2013-05-13 | 2013-09-18 | 2014-05-12 |  | Highland | 332839 | 0 | -159.47 | 0 | 0 | 0 | 0 | -159.47 | 0 | 332679.53 | 0 | [6 empty] | CM_WSI | 100%
403199 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2012-12-17 | 2014-02-21 | 2014-06-30 | 2017-09-26 |  | Highland | 322176 | 23702 | 35688.92 | 20303.5 | -49.17 | 0 | 0 | 79645.25 | 0 | 401821.25 | 0 | [6 empty] | CM_WSI | 100%
501259 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2016-02-19 | 2018-10-24 | 2018-10-29 | 2019-08-22 | 2019-08-23 | Highland | 0 | 1308.41 | 2087 | 69137.59 | 833023.6 | 156519.78 | 22075.64 | 1084152.02 | 0 | 1084152.02 | 0 | [6 empty] | CM_WSI | 100%
501198 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2016-04-25 | 2021-06-21 | 2021-08-30 | 2022-05-19 | 2022-08-19 | Highland | 0 | 0 | 86866.37 | 0 | 0 | 0 | 0 | 86866.37 | 749133.63 | 836000 | 0 | [6 empty] | CM_WSNI | 100%
402905 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-11 | 2013-07-17 | 2013-10-28 | 2015-02-09 |  | Highland | 782545.41 | 7794.59 | -3471.12 | 0 | 0 | 0 | 0 | 4323.47 | 0 | 786868.88 | 0 | [6 empty] | CM_WSI | 100%
402276 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-08-11 | 2013-11-25 | 2014-03-31 | 2015-01-16 |  | Highland | 540209.07 | 337.5 | 277.23 | 0 | 0 | 0 | 0 | 614.73 | 0 | 540823.8 | 0 | [6 empty] | CM_WSNI | 100%
403266 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-02-01 | 2013-07-03 | 2013-07-03 | 2016-08-01 |  | All East Unitary Authorities | 438898 | -26250.02 | 60 | 0 | 0 | 0 | 0 | -26190.02 | 0 | 412707.98 | 0 | [6 empty] | CM_WWI | 100%
500956 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-10-05 | 2016-09-29 | 2016-09-29 | 2017-11-15 |  | Scottish Water Wide | 0 | 165092 | 1079630.52 | 152559.98 | 0 | 0 | 0 | 1397282.5 | 0 | 1397282.5 | 0 | [6 empty] | CM_M&G | 100%
401361 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2010-09-10 | 2015-06-25 | 2015-06-03 | 2017-03-01 | 2017-06-09 | Angus | 296794 | 724855 | 68348.69 | 1190.99 | -1006.02 | 0 | 0 | 793388.66 | 0 | 1090182.66 | 0 | [6 empty] | CM_WSI | 100%
502844 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-18 | 2022-10-21 | 2023-02-20 | 2024-02-15 | 2024-05-17 | Highland | 0 | 0 | 0 | 21033.13 | 687.48 | 28279.39 | 0 | 50000 | 949999.96 | 999999.96 | 148885.7057 | [6 empty] | WG1 | 100%
501197 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2015-11-12 | 2016-11-30 | 2016-12-08 | 2018-09-07 | 2018-09-07 | Highland | 0 | 9849 | 60703.23 | 162325.13 | 37101.64 | 5021 | 0 | 275000 | 0 | 275000 | 0 | [6 empty] | CM_WSI | 100%
045307 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-24 | 2011-03-11 | 2011-07-22 | 2012-01-19 | 2012-03-14 | Highland | 176835.3 | -135.35 | 0 | 0 | 0 | 0 | 0 | -135.35 | 0 | 176699.95 | 0 | [6 empty] | DW13 | 100%
502843 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-18 | 2027-12-06 | 2028-04-04 | 2029-03-30 | 2029-07-02 | Highland | 0 | 0 | 0 | 20930.23 | 902.22 | 28167.56 | 0 | 50000.01 | 4949999.9 | 4999999.91 | 148885.7057 | [6 empty] | WG1 | 100%
500226 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS3 | 2015-03-27 | 2018-06-28 | 2018-06-29 | 2019-07-01 | 2020-08-01 | Moray | 0 | 1449 | 0 | 43421 | 63943.12 | 402386.39 | 86485.17 | 597684.68 | 0 | 597684.68 | 832813.2182 | [6 empty] | DW5FS | 10.4% | DW5 | 89.6% | bar: Regulatory Outputs OMG-02
500844 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2016-07-27 | 2018-06-28 | 2018-12-04 | 2019-12-18 | 2020-10-26 | Moray | 0 | 19062.39 | 9488.15 | 41920.38 | 219638.01 | 129926.46 | 0 | 420035.39 | 0 | 420035.39 | 1041128.5044 | [6 empty] | DW5FS | 100%
403197 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-01-16 | 2013-08-19 | 2013-11-01 | 2015-02-20 |  | Moray | 936364 | 44163.16 | 812.76 | 0 | 0 | 0 | 0 | 44975.92 | 0 | 981339.92 | 0 | [6 empty] | CM_WSNI | 100%
503419 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2018-10-31 | 2021-03-01 | 2021-06-15 | 2022-09-13 | 2022-12-15 | Moray | 0 | 0 | 0 | 0 | 34589.25 | 28593.72 | 429258.96 | 492441.93 | 1307813.55 | 1800255.48 | 0 | [6 empty] | CM_WSNI | 100%
501218 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2018-03-28 | 2019-09-20 | 2019-12-20 | 2020-09-01 | 2022-03-01 | Aberdeenshire | 0 | 4604.65 | 1324.77 | 6865.265 | 872.11 | 10310.94 | 34562.44 | 58540.175 | 64912.51 | 123452.685 | 319809.1218 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
046256 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-11-13 | 2010-06-28 | 2010-11-02 | 2012-02-14 |  | Scottish Borders | 280871.42 | 0.13 | 0 | 0 | 0 | 0 | 0 | 0.13 | 0 | 280871.55 | 0 | [6 empty] | CM_WSI | 100%
501526 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2016-12-22 | 2022-07-19 | 2022-08-17 | 2023-04-11 | 2023-07-12 | East Renfrewshire | 0 | 0 | 2612.08 | 52.07 | -27.84 | 0 | 0 | 2636.31 | 342387.9 | 345024.21 | 0 | [6 empty] | CM_WSNI | 100%
402853 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-08-15 | 2014-08-26 | 2014-08-26 | 2014-08-29 | 2014-09-01 | Aberdeenshire | 22777.22 | -571.18 | 0 | 0 | 0 | 0 | 0 | -571.18 | 0 | 22206.04 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
502760 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-05-31 | 2018-05-31 | 2018-05-31 | 2018-05-31 | 2018-05-31 | Perth and Kinross | 0 | 0 | 0 | 34831.63 | 14.2725 | 0 | 0 | 34845.9025 | 0 | 34845.9025 | 148885.7057 | [6 empty] | SG1 | 100%
045547 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-29 | 2011-03-24 | 2011-07-25 | 2012-03-22 | 2012-03-27 | Perth and Kinross | 491171.2 | 30.72 | 0 | 0 | 0 | 0 | 0 | 30.72 | 0 | 491201.92 | 0 | [6 empty] | WQ01 | 100%
503320 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-23 | 2023-08-15 | 2023-12-11 | 2024-12-06 | 2025-03-10 | Perth and Kinross | 0 | 0 | 0 | 0 | 79559.16 | 0 | 18141.93 | 97701.09 | 51147.1 | 148848.19 | 148885.7057 | [6 empty] | SG1 | 100%
400056 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-11-11 | 2011-02-28 | 2011-02-28 | 2011-02-28 | 2011-02-28 | Stirling | 30347.9 | 1.1 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 30349 | 0 | [6 empty] | CM_WWNI | 100%
401585 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-12-08 | 2011-05-03 | 2011-06-13 | 2014-01-17 | 2014-01-17 | East Renfrewshire | 443245 | -532.49 | 0 | 0 | 0 | 0 | 0 | -532.49 | 0 | 442712.51 | 0 | [6 empty] | CM_WSI | 100%
503401 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2019-02-07 | 2020-09-28 | 2021-01-25 | 2021-11-12 | 2022-02-14 | Angus | 0 | 0 | 0 | 0 | 37986.64 | 80044.82 | 163672.42 | 281703.88 | 308606.62 | 590310.5 | 466391.8995 | [6 empty] | DW25T | 100%
500845 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS5 | 2015-11-04 | 2016-03-25 | 2017-01-02 | 2018-03-01 | 2018-06-01 | Highland | 0 | 3166.17 | 9897.5 | 37880.89 | 0 | 140.85 | 0 | 51085.41 | 0 | 51085.41 | 15327.862 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 39.24
501064 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-10-21 | 2023-03-29 | 2023-07-25 | 2024-07-12 | 2024-10-04 | Aberdeenshire | 0 | 16952.66 | 1001.08 | 272.7 | 631.84 | 0 | 0 | 18858.28 | 981141.7 | 999999.98 | 0 | [6 empty] | CM_WSI | 100%
503270 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-31 | 2023-06-14 | 2023-10-17 | 2024-10-14 | 2025-01-14 | Aberdeenshire | 0 | 0 | 0 | 0 | 79664.11 | 0 | 34917.81 | 114581.92 | 29917.45 | 144499.37 | 148885.7057 | [6 empty] | SG1 | 100%
403586 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-09-25 | 2014-02-12 | 2014-02-12 | 2016-09-26 | 2014-08-05 | Scottish Water Wide | 836876 | 16443 | 5128.34 | 48.04 | 0 | 0 | 0 | 21619.38 | 0 | 858495.38 | 0 | [6 empty] | CM_WSI | 100%
502870 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2021-05-18 | 2027-11-29 | 2028-03-21 | 2029-03-13 | 2029-06-13 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 21237.996 | 1850.55 | 11737.8 | 11692.3 | 46518.646 | 4953501.34 | 5000019.986 | 148885.7057 | [6 empty] | WG1 | 100%
402008 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-05-27 | 2014-07-31 | 2014-09-08 | 2015-03-11 | 2015-03-23 | Stirling | 744278.86 | -1397.43 | 36.75 | 0 | 0 | 0 | 0 | -1360.68 | 0 | 742918.18 | 85083.0001 | [6 empty] | WQ01 | 100%
503108 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2019-10-07 | 2021-02-08 | 2021-06-01 | 2022-01-17 | 2022-04-19 | Stirling | 0 | 0 | 0 | 30976.74 | 52621.46 | 17520.95 | 112152.4 | 213271.55 | 537346.7 | 750618.25 | 148885.7057 | [6 empty] | SG1 | 100%
502813 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-08-12 | 2022-07-22 | 2022-11-14 | 2023-11-02 | 2024-02-02 | Aberdeenshire | 0 | 0 | 0 | 67136.2025 | 15448.8045 | 17736.09 | 17667.4 | 117988.497 | 24011.68 | 142000.177 | 148885.7057 | [6 empty] | SG1 | 100%
500002 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2015-11-23 | 2017-12-21 | 2018-03-20 | 2019-12-03 | 2020-03-11 | North Ayrshire | 0 | 44466 | 14100 | 71361 | 130509.27 | 42006.93 | 6642.9 | 309086.1 | 0 | 309086.1 | 1046104.6405 | [6 empty] | DW5FS | 100%
502094 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2021-07-28 | 2023-04-20 | 2023-08-16 | 2024-10-31 | 2025-01-31 | North Ayrshire | 0 | 16326 | 1157.27 | 0 | 833.51 | 0 | 0 | 18316.78 | 0 | 18316.78 | 0 | [6 empty] | CM_WSI | 50% | CM_WSNI | 50%
502564 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2021-05-24 | 2024-12-23 | 2024-12-24 | 2026-02-04 | 2026-05-07 | North Ayrshire | 0 | 0 | 20930.23 | 1679.04 | 6320.73 | 9847.98 | 9809.81 | 48587.79 | 951412.32 | 1000000.11 | 148885.7057 | [6 empty] | WG1 | 100%
046837 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2011-09-14 | 2011-10-17 | 2015-08-20 | 2016-12-20 | North Ayrshire | 3449705.96 | 79678.71 | 16329.86 | -2539.08 | 0 | 0 | 0 | 93469.49 | 0 | 3543175.45 | 81535 |  |  |  |  | 50776.882 |  | DW23 | 100%
501196 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2016-09-23 | 2018-02-26 | 2018-02-26 | 2018-03-06 | 2018-03-06 | Aberdeenshire | 0 | 6087.85 | 17675.82 | -1294.42 | 0 | 0 | 0 | 22469.25 | 0 | 22469.25 | 0 | [6 empty] | CM_WSNI | 100%
500846 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2016-09-20 | 2017-12-20 | 2017-12-20 | 2019-06-28 | 2020-03-02 | North Lanarkshire | 0 | 12698.42 | 12928.34 | 14062.573 | 144909.807 | 12029.59 | 5419.37 | 202048.1 | 0 | 202048.1 | 701368.749 | [6 empty] | DW5FS | 100%
500847 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-07-27 | 2018-09-28 | 2018-10-01 | 2019-01-01 | 2019-11-01 | Glasgow City | 0 | 27600 | 11361.76 | 124769.2375 | 351996.3925 | 5097.99 | 0 | 520825.38 | 0 | 520825.38 | 1137727.613 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 5.44
500227 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS4 | 2015-03-27 | 2016-03-30 | 2016-04-20 | 2017-02-07 | 2020-08-27 | West Lothian | 0 | 6098 | 30706.71 | 31617.25 | 18440.5 | 244187.55 | 16150 | 347200.01 | 0 | 347200.01 | 1092439.1508 | [6 empty] | DW5FS | 100%
500228 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS3 | 2015-03-27 | 2016-09-29 | 2016-10-31 | 2019-06-28 | 2019-11-15 | West Lothian | 0 | 104446 | 1064630 | 1792108 | 946308.69 | 2000 | 0 | 3909492.69 | 0 | 3909492.69 | 2722270.8961 | [6 empty] | DW5 | 100%
500848 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-03-31 | 2017-12-19 | 2018-03-20 | 2018-08-28 | 2019-04-30 | West Lothian | 0 | 5413.63 | 8820.37 | 760.73 | 113256.16 | 5098.16 | 0 | 133349.05 | 0 | 133349.05 | 214522.2075 | [6 empty] | DW5FS | 100%
400109 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2010-02-23 | 2010-02-22 | 2010-11-15 | 2012-09-26 |  | Falkirk | 2225356 | 197289 | 1219597.9 | 1633871.735 | 799552.745 | 0 | 0 | 3850311.38 | 0 | 6075667.38 | 0 | [6 empty] | CM_WSI | 100%
502430 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | WINF | Water Non infrastructure | MS0 | 2018-01-22 | 2021-02-01 | 2021-05-06 | 2022-03-14 | 2022-06-14 | East Dunbartonshire | 0 | 0 | 23738.26 | 20517.34 | 84319.04 | 497834.31 | 3983500.44 | 4609909.39 | 3390090.48 | 7999999.87 | 0 | [6 empty] | CM_M&G | 100%
502783 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2017-09-06 | 2018-12-20 | 2019-01-15 | 2020-04-02 | 2020-07-03 | Glasgow City | 0 | 0 | 0 | 85000 | 397484.24 | 755559.09 | 131459.01 | 1369502.34 | 3951.44 | 1373453.78 | 0 | [6 empty] | CM_WSI | 100%
501082 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2016-04-28 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | West Lothian | 0 | 14760 | -11329.46 | 1973.72 | 0 | 0 | 0 | 5404.26 | 0 | 5404.26 | 0 | [6 empty] | CM_WSI | 100%
501081 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-06 | 2022-07-18 | 2022-08-29 | 2023-03-29 | 2023-06-29 | West Lothian | 0 | 59472 | -12687 | 0 | -2719 | 0 | 0 | 44066 | 275464.8 | 319530.8 | 0 | [6 empty] | CM_WSI | 100%
500035 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2016-04-01 | 2017-03-22 | 2017-03-22 | 2019-11-01 | 2020-05-01 | East Dunbartonshire | 0 | 500406 | 654504.78 | 1503828.33 | 1530676.44 | 296419.61 | 346018.07 | 4831853.23 | 36231.11 | 4868084.34 | 934032.9828 | [6 empty] | CM_WSNI | 8.528% | DW25P | 91.47% | bar: Regulatory Outputs OMG-04
502550 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2018-04-30 | 2018-08-16 | 2018-08-16 | 2018-08-16 | 2018-08-16 | North Lanarkshire | 0 | 0 | 0 | 17909.565 | 455.875 | 0 | 0 | 18365.44 | 0 | 18365.44 | 934032.9828 | [6 empty] | DW25P | 100%
401053 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | [5 empty] | East Dunbartonshire | 0 | 0 | 0 | 0 | 206.4 | 0 | 0 | 206.4 | 0 | 206.4 | 0 | [6 empty] | CM_WSNI | 100%
502210 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-05-11 | 2016-09-13 | 2016-09-13 | 2017-05-05 | 2017-10-11 | Stirling | 0 | 0 | 44.15 | 0 | 0 | 0 | 0 | 44.15 | 0 | 44.15 | 270597.9016 | [6 empty] | DW25P | 100%
402600 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-03-27 | 2012-12-13 | 2013-01-21 | 2013-10-01 |  | All East Unitary Authorities | 87764 | -395.66 | 0 | 0 | 0 | 0 | 0 | -395.66 | 0 | 87368.34 | 0 | [6 empty] | CM_WWNI | 100%
501021 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS0 | 2018-01-09 | 2019-12-30 | 2020-02-03 | 2021-07-02 | 2021-10-01 | Aberdeenshire | 0 | 43768.74 | 76143.85 | 51038.9575 | 397233.6225 | 950309.39 | 1556562.8 | 3075057.36 | 834409.7 | 3909467.06 | 148885.7057 | [6 empty] | CM_WWNI | 4% | SG1 | 96%
402856 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-08-15 | 2014-08-28 | 2014-10-27 | 2015-01-28 | 2015-02-02 | Fife | 140163 | 17498.16 | 0 | 0 | 0 | 0 | 0 | 17498.16 | 0 | 157661.16 | 4199.4 | [6 empty] | CM_WWI | 40% | CS11A | 60%
501160 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2015-12-10 | 2017-03-28 | 2017-06-30 | 2019-05-07 | 2019-07-26 | South Ayrshire | 0 | 9030.91 | 262407.05 | 871421.04 | 793882 | 12000 | 0 | 1948741 | 2400 | 1951141 | 0 | [6 empty] | CM_WWNI | 100%
502896 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2019-04-01 | 2021-01-18 | 2021-05-10 | 2022-08-02 | 2022-11-02 | Renfrewshire | 0 | 0 | 0 | 21315.78 | 7847.15 | 110623.17 | 410123.97 | 549910.07 | 1456089.83 | 2005999.9 | 0 | [6 empty] | CM_WSI | 100%
402358 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-09-20 | 2012-03-28 | 2012-04-27 | 2013-06-26 |  | Renfrewshire | 418100 | 867.57 | 0 | 0 | 0 | 0 | 0 | 867.57 | 0 | 418967.57 | 0 | [6 empty] | CM_WSI | 100%
046244 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-12-11 | 2010-09-29 | 2010-10-28 | 2011-01-19 |  | Renfrewshire | 30696.12 | 5455.88 | 0 | 0 | 0 | 0 | 0 | 5455.88 | 0 | 36152 | 0 | [6 empty] | CM_WSI | 100%
500655 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS0 | 2018-04-27 | 2019-09-23 | 2020-01-06 | 2021-02-03 | 2021-05-06 | Argyll and Bute-North Argyll | 0 | 72873 | 95043 | 51084 | 300327 | 941568.45 | 1595211.66 | 3056107.11 | 319480.82 | 3375587.93 | 229318.7788 | [6 empty] | CS11 | 100%
403274 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-01-23 | 2014-11-27 | 2015-01-09 | 2015-03-20 | 2015-03-20 | City of Edinburgh | 474654 | -20869 | -0.02 | -1638.26 | 0 | 0 | 0 | -22507.28 | 0 | 452146.72 | 229318.7788 | [6 empty] | CS11 | 100%
402635 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-04-16 | 2013-01-03 | 2013-03-11 | 2014-12-05 |  | South Ayrshire | 1640969 | 21228 | -31370.16 | 0 | 0 | 0 | 0 | -10142.16 | 0 | 1630826.84 | 0 | [6 empty] | CM_WWI | 100%
403303 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2013-02-27 | 2014-08-25 | 2014-10-20 | 2017-11-10 | 2017-11-10 | Renfrewshire | 685659.82 | 478168.51 | 541097.8 | 132308.795 | -24695.5225 | 6995.01 | 0 | 1133874.5925 | 0 | 1819534.4125 | 0 | [6 empty] | CM_WSI | 100%
502392 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS3 | 2017-05-16 | 2017-05-16 | 2017-08-07 | 2021-02-26 | 2021-02-26 | East Renfrewshire | 0 | 0 | 0 | 196261.68 | 0 | 0 | 1203738.32 | 1400000 | 0 | 1400000 | 587726.5342 | [6 empty] | WG5 | 100%
500116 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS4 | 2015-03-26 | 2016-09-29 | 2016-09-30 | 2019-03-27 | 2019-07-12 | West Lothian | 0 | 18657 | 155319 | 122816 | 33504 | 23577.02 | 0 | 353873.02 | 0 | 353873.02 | 278002.7669 | [6 empty] | CS16D | 100%
503330 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2021-04-01 | 2022-06-15 | 2022-06-23 | 2022-08-03 | 2022-11-03 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499999.99 | 499999.99 | 32762.3472 | [6 empty] | CM_WSI | 100%
030087 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-16 | 2010-12-17 | 2011-03-28 | 2012-09-24 | 2012-10-05 | West Lothian | 1993686.17 | 3399.44 | 0 | 0 | 0 | 0 | 0 | 3399.44 | 0 | 1997085.61 | 0 | [6 empty] | CM_WWNI | 20% | EC04A | 80%
502183 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2016-11-01 | 2019-08-05 | 2019-08-05 | 2019-08-05 | 2019-08-05 | West Lothian | 0 | 20930.23 | 86269.77 | 488747.23 | 162411.49 | 9543 | 0 | 767901.72 | 0 | 767901.72 | 0 | [6 empty] | CM_WSI | 100%
502242 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2016-06-01 | 2016-08-31 | 2016-08-31 | 2017-03-28 | 2017-03-28 | West Lothian | 0 | 0 | 721017.38 | -20051 | -6188.84 | 0 | 0 | 694777.54 | 0 | 694777.54 | 0 | [6 empty] | CM_WSI | 100%
502184 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-03-22 | 2019-05-16 | 2019-05-16 | 2019-05-16 | 2019-05-16 | West Lothian | 0 | 1308.41 | 32669.13 | 355.8 | 64894.76 | 11000 | 0 | 110228.1 | 0 | 110228.1 | 0 | [6 empty] | CM_WSI | 100%
500247 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2015-03-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-30 | Scottish Water Wide | 475.02 | 4034.98 | 57396 | 33031.95 | -11809.66 | 0 | 0 | 82653.27 | 0 | 83128.29 | 0 | [6 empty] | EC16 | 100%
049391 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MSU | 2016-11-30 | 2017-08-20 | 2017-11-30 | 2019-04-30 | 2019-07-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19133207.65 | [6 empty] | EC02B | 100%
502778 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS1 | 2017-06-16 | 2019-06-03 | 2019-09-09 | 2020-01-14 | 2020-04-17 | Inverclyde | 0 | 0 | 0 | 3394.85 | 91391.325 | 791839.39 | 60898.52 | 947524.085 | 1845.65 | 949369.735 | 0 | [6 empty] | CM_WWNI | 100%
501352 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2016-08-31 | 2018-09-05 | 2018-10-10 | 2020-11-04 | 2020-11-04 | Inverclyde | 0 | 0 | 27067 | 271229 | 1618405 | 1596215.24 | 2153595.34 | 5666511.58 | 0 | 5666511.58 | 0 |  |  |  |  | -67680 |  | CM_WWNI | 100%
500849 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2016-06-01 | 2018-06-27 | 2019-02-04 | 2019-06-01 | 2020-03-01 | Na H-Eileanan an Iar | 0 | 4021.83 | 1480.39 | 30733.78 | 88301.99 | 14575.8 | 4786.69 | 143900.48 | 193.72 | 144094.2 | 175911.6256 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 65.25
500690 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS7 | 2015-08-26 | 2015-12-23 | 2016-01-22 | 2016-06-23 | 2016-06-24 | Highland | 0 | 336686 | -336686 | 4962.01 | 3000.9775 | 0 | 0 | 7962.9875 | 0 | 7962.9875 | 370429.4949 | [6 empty] | DW23 | 100%
045309 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-24 | 2011-03-31 | 2013-04-01 | 2013-04-02 | 2016-04-01 | Highland | 47621.11 | 22.5 | 0 | 0 | 0 | 0 | 0 | 22.5 | 0 | 47643.61 | 0 | [6 empty] | DW13 | 100%
502369 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2015-08-26 | 2015-12-23 | 2016-01-22 | 2019-11-01 | 2020-02-01 | Highland | 0 | 0 | 0 | 2029.375 | 1977.409 | 344783.96 | 829.61 | 349620.354 | 519.73 | 350140.084 | 0 | [6 empty] | CM_WSNI | 100% | bar: Regulatory Outputs OMG-03
402857 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS7 | 2012-08-15 | 2012-12-04 | 2013-01-18 | 2015-08-13 | 2015-08-13 | Fife | 42581.6 | -42580.6 | 662.24 | 0 | 0 | 0 | 0 | -41918.36 | 0 | 663.24 | 0 | [6 empty] | CS11 | 100%
502709 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | Midlothian | 0 | 0 | 0 | 2609.3 | 0 | 0 | 0 | 2609.3 | 0 | 2609.3 | 0 | [6 empty] | CM_WWI | 100%
500118 | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-19 | 2015-09-27 | 2017-03-08 | 2017-04-04 | 2017-04-04 | Dumfries and Galloway | 0 | 19644 | -2009 | -2696.49 | 41.28 | 0 | 0 | 14979.79 | 0 | 14979.79 | 72474.3726 | [6 empty] | CS11 | 100%
402992 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-10-01 | 2013-03-15 | 2013-06-03 | 2013-10-25 | 2013-10-25 | Glasgow City | 103140 | -7519.29 | 0 | 0 | 0 | 0 | 0 | -7519.29 | 0 | 95620.71 | 14.4 | [6 empty] | CM_WWI | 40% | CS11A | 60%
503546 | Q&S4 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWD | Revised Bathing Waters Directive | MSU | 2019-07-01 | 2020-05-18 | 2020-08-14 | 2021-05-21 | 2021-08-23 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 130328.3 | 824660.44 | 954988.74 | 428011.26 | 1383000 | 2269817.6904 | [6 empty] | EC16B | 100%
501527 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-05-28 | 2022-01-25 | 2022-05-31 | 2022-10-10 | 2023-01-10 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145956.96 | 145956.96 | 0 | [6 empty] | CM_WSNI | 100%
503141 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-04-16 | 2022-03-28 | 2022-06-06 | 2023-01-02 | 2023-04-04 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 7836.28 | 2332.72 | 4194.21 | 4177.97 | 18541.18 | 371458.87 | 390000.05 | 0 | [6 empty] | CM_WSI | 100%
501209 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2017-12-22 | 2018-11-28 | 2019-03-18 | 2020-02-01 | 2020-05-01 | Argyll and Bute-Cowal & Bute | 0 | 12558.14 | 7317.87 | 59031.48 | 201345.51 | 487242.49 | 88157.55 | 855653.04 | 4208.92 | 859861.96 | 837594.9044 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
500855 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2016-07-25 | 2018-06-27 | 2019-02-18 | 2019-09-01 | 2020-05-01 | Na H-Eileanan an Iar | 0 | 4692.29 | 1846.8 | 14611.16 | 90096.62 | 9490.56 | 3126.73 | 123864.16 | 0 | 123864.16 | 270110.509 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 75.09
403045 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-23 | 2012-11-13 | 2013-01-14 | 2013-09-04 |  | Na H-Eileanan an Iar | 183184.99 | 1634 | 0 | 0 | 0 | 0 | 0 | 1634 | 0 | 184818.99 | 0 | [6 empty] | CM_WSI | 100%
503539 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | GW0 | 2020-02-21 | 2020-11-23 | 2021-03-03 | 2021-10-12 | 2022-01-12 | Perth and Kinross | 0 | 0 | 0 | 0 | 48304.07 | 144383.4 | 0 | 192687.47 | 0 | 192687.47 | 587726.5342 | [6 empty] | WG5 | 100%
503303 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS2 | 2018-08-14 | 2018-08-14 | 2019-05-21 | 2020-06-19 | 2020-09-21 | Perth and Kinross | 0 | 0 | 0 | 0 | 3742.77 | 2861555.4 | 1935341.3 | 4800639.47 | 0 | 4800639.47 | 587726.5342 | [6 empty] | WG5 | 100%
502766 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2020-07-16 | 2022-08-09 | 2022-12-08 | 2023-11-28 | 2024-02-28 | Perth and Kinross | 0 | 0 | 0 | 83645.0025 | 46696.2395 | 14950.99 | 1314450.78 | 1459743.012 | 41543017.58 | 43002760.592 | 148885.7057 | [6 empty] | SG1 | 100%
403795 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-05-19 | 2016-03-18 | 2016-03-28 | 2016-04-08 | 2016-04-08 | Stirling | 26116.12 | 44802.16 | 0 | 0 | 0 | 0 | 0 | 44802.16 | 0 | 70918.28 | 0 | [6 empty] | CM_WSI | 100%
500951 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS4 | 2015-09-30 | 2016-05-16 | 2016-05-16 | 2018-11-22 |  | Scottish Water Wide | 0 | 119842 | 485188.83 | 759734.71 | -165162.03 | 0 | 0 | 1199603.51 | 0 | 1199603.51 | 0 | [6 empty] | CM_WSI | 24.48% | CM_M&G | 75.52%
403796 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-10-15 | 2014-10-15 | 2014-11-06 | 2015-03-12 |  | Scottish Water Wide | 1007215 | -17927.06 | 0 | 0 | 0 | 0 | 0 | -17927.06 | 0 | 989287.94 | 0 | [6 empty] | CM_M&G | 100%
500051 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS3 | 2016-09-30 | 2018-09-06 | 2018-09-24 | 2019-05-24 | 2019-07-15 | South Lanarkshire | 0 | 46503.28 | 24619.39 | 251268.59 | 856184.64 | 120111.9 | 18930.84 | 1317618.64 | 2946.43 | 1320565.07 | 148885.7057 | [6 empty] | SG1 | 100%
501654 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | Scottish Borders | 0 | 0 | 0 | 26344.16 | 1774.5 | 0 | 0 | 28118.66 | 0 | 28118.66 | 0 | [6 empty] | CM_WWNI | 100%
402498 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2012-04-18 | 2014-01-29 | 2014-03-13 | 2014-09-15 | 2014-09-15 | Scottish Borders | 519000 | 432.06 | 0 | 0 | 0 | 0 | 0 | 432.06 | 0 | 519432.06 | 0 | [6 empty] | SG1 | 100%
500239 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS4 | 2015-03-27 | 2016-09-30 | 2017-01-02 | 2018-08-27 | 2019-06-28 | Dumfries and Galloway | 0 | 4000 | 12763.62 | 144074.67 | 21594.73 | 29902.01 | 268.55 | 212603.58 | 0 | 212603.58 | 1916540.7656 | [6 empty] | DW5FS | 100%
503426 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2019-08-30 | 2020-08-17 | 2020-10-22 | 2021-07-06 | 2021-10-06 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 159268.41 | 589817.15 | 749085.56 | 350914.49 | 1100000.05 | 0 | [6 empty] | SG1 | 100%
502358 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | NONINF | Strategic Capacity | MS0 | 2018-11-21 | 2020-07-20 | 2020-07-24 | 2021-10-11 | 2022-01-11 | Dumfries and Galloway | 0 | 0 | 69147.69 | 24322.571 | 100348.339 | 359533.97 | 1906240.82 | 2459593.39 | 3205301.58 | 5664894.97 | 587726.5342 | [6 empty] | CM_WSNI | 3% | WG5 | 44.3% | WG1 | 52.7%
500797 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2015-09-30 | 2018-06-28 | 2018-09-28 | 2020-03-26 | 2021-01-15 | Dumfries and Galloway | 0 | 133210 | 8719.89 | 218976.11 | 136142.64 | 227029.49 | 0 | 724078.13 | 0 | 724078.13 | 1454818.1563 | [6 empty] | DW5FS | 100%
500799 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2015-09-30 | 2017-09-29 | 2017-10-11 | 2019-06-01 | 2020-03-01 | Dumfries and Galloway | 0 | 20929 | -1919 | 124172.576 | 163697.384 | 3736.33 | 15794.53 | 326410.82 | 0 | 326410.82 | 288109.3224 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 56.19
501140 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2016-05-27 | 2021-08-16 | 2021-09-14 | 2023-09-07 | 2023-12-08 | Dumfries and Galloway | 0 | 76680 | 41139.01 | 283992 | 188963.21 | 0 | 0 | 590774.22 | 6550111.66 | 7140885.88 | 0 | [6 empty] | CM_WSI | 100%
501136 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501134 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501135 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501131 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501142 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501130 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501143 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501132 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | Dumfries and Galloway | 0 | 0 | 0 | 49.504 | 0 | 0 | 0 | 49.504 | 0 | 49.504 | 0 | [6 empty] | CM_WSI | 100%
501133 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501141 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | Dumfries and Galloway | 0 | 81 | -81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501129 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501137 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | Dumfries and Galloway | 0 | 81 | -81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501138 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2016-04-04 | 2021-08-16 | 2021-09-10 | 2022-06-30 | 2022-06-30 | Dumfries and Galloway | 0 | 97776 | -10683 | 104803 | 100550.44 | 0 | 0 | 292446.44 | 1208668.53 | 1501114.97 | 0 | [6 empty] | CM_WSI | 100%
503047 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-05-25 | 2023-08-01 | 2023-11-22 | 2024-08-02 | 2024-11-04 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376999.96 | 376999.96 | 0 | [6 empty] | CM_WSNI | 100%
503049 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS4 | 2014-03-31 | 2016-03-23 | 2016-03-28 | 2017-11-01 | 2020-12-01 | Dumfries and Galloway | 0 | 0 | 0 | 17631.55 | 248528.11 | 87122.8 | 118573.64 | 471856.1 | 6541.95 | 478398.05 | 0 | [6 empty] | CM_WSNI | 100% | bar: Regulatory Outputs OMG-01
046196 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-08-12 | 2011-03-22 | 2011-05-02 | 2011-08-29 |  | Highland | 402081.62 | -0.69 | 0 | 0 | 0 | 0 | 0 | -0.69 | 0 | 402080.93 | 0 | [6 empty] | CM_WSNI | 100%
401008 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2014-02-27 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | Perth and Kinross | 141079 | 257403 | 212180.64 | -9871.7425 | 72.86 | 0 | 0 | 459784.7575 | 0 | 600863.7575 | 0 | [6 empty] | SG1 | 100%
030097 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-20 | 2010-06-28 | 2010-10-04 | 2012-03-16 | 2012-03-23 | West Lothian | 5265641.6 | 1720.87 | 0 | 0 | 0 | 0 | 0 | 1720.87 | 0 | 5267362.47 | 0 | [6 empty] | CM_WWNI | 8.955% | EC10A | 30.35% | EC04A | 60.7%
501709 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2016-06-29 | 2016-06-29 | 2016-06-29 | 2016-06-02 | 2016-06-29 | West Lothian | 0 | 0 | 1674.42 | 138.645 | 61.22 | 0 | 0 | 1874.285 | 0 | 1874.285 | 0 | [6 empty] | CM_WWI | 100%
401345 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-13 | 2012-12-13 | 2013-02-25 | 2014-09-04 | 2013-09-30 | Highland | 80825 | -1758.88 | 98.34 | 0 | 0 | 0 | 0 | -1660.54 | 0 | 79164.46 | 72 | [6 empty] | CS1 | 100%
500120 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2015-11-30 | 2016-01-12 | 2017-04-01 | 2017-07-01 | South Lanarkshire | 0 | 51658 | 53991 | 6357.43 | 123.84 | 0 | 0 | 112130.27 | 0 | 112130.27 | 72474.3726 | [6 empty] | CS11 | 44.65% | CS16D | 55.35% | bar: Regulatory Outputs OMG-22
502815 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-07-07 | 2022-07-22 | 2022-11-14 | 2023-11-02 | 2024-02-02 | South Lanarkshire | 0 | 0 | 0 | 80034.785 | 17145.685 | 14413.17 | 14357.27 | 125950.91 | 16049.21 | 142000.12 | 148885.7057 | [6 empty] | SG1 | 100%
503502 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MSU | 2021-04-01 | 2022-01-17 | 2022-03-25 | 2022-08-09 | 2022-11-09 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 3151.11 | 3138.91 | 6290.02 | 682755.99 | 689046.01 | 0 | [6 empty] | CM_M&G | 100%
503231 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 | 2019-01-28 | 2019-01-28 | 2019-05-31 | 2020-03-20 | 2020-06-22 | Perth and Kinross | 0 | 0 | 0 | 0 | 184249.6 | 183482.25 | 29009.64 | 396741.49 | 3258.48 | 399999.97 | 0 | [6 empty] | CM_WWNI | 100%
502818 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-08-20 | 2022-07-22 | 2022-11-14 | 2023-11-02 | 2024-02-02 | Perth and Kinross | 0 | 0 | 0 | 64892.94 | 24485.8 | 8272.09 | 14957.12 | 112607.95 | 38985.3 | 151593.25 | 148885.7057 | [6 empty] | SG1 | 100%
502931 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-10-31 | 2018-08-23 | 2019-03-11 | 2019-08-08 | 2019-08-09 | Perth and Kinross | 0 | 0 | 0 | 6800 | 286583.53 | 197961.69 | 1072.83 | 492418.05 | 1744.91 | 494162.96 | 0 | [6 empty] | CM_WWNI | 100%
400062 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-08-31 | 2012-02-21 | 2012-08-07 | 2013-02-14 | 2013-03-21 | Clackmannanshire | 933359.83 | -755.31 | 0 | 0 | 0 | 0 | 0 | -755.31 | 0 | 932604.52 | 1000.6118 | [6 empty] | CM_WWNI | 10% | WQ01 | 90%
501565 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWMD | Water infrastructure | MS7 | 2016-02-10 | 2016-08-31 | 2016-09-26 | 2019-03-18 | 2019-03-18 | West Dunbartonshire | 0 | 5514 | 563128.15 | 634631 | 1018492.0015 | 0 | 0 | 2221765.1515 | 0 | 2221765.1515 | 0 | [6 empty] | CM_M&G | 100%
503408 | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | SWD | Exceptional Capital Maintenance | GW0 | 2019-06-28 | 2020-05-11 | 2020-07-21 | 2021-03-19 | 2021-06-21 | West Dunbartonshire | 0 | 0 | 0 | 0 | 32148.84 | 325959.25 | 1010262.03 | 1368370.12 | 263778.77 | 1632148.89 | 0 | [6 empty] | SR15_EXC_EXC | 100%
501215 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-03-21 | 2016-09-08 | 2016-09-09 | 2016-09-01 | 2016-09-01 | Inverclyde | 0 | 3341.78 | 2231.83 | 0 | 341.04 | 0 | 0 | 5914.65 | 0 | 5914.65 | 466391.8995 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
502565 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2019-09-27 | 2023-05-10 | 2023-05-11 | 2024-06-21 | 2024-09-23 | Moray | 0 | 0 | 20930.23 | 2988.95 | 89869.847 | 41059.48 | 0 | 154848.507 | 886561.67 | 1041410.177 | 148885.7057 | [6 empty] | WG1 | 100%
503369 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2021-04-02 | 2022-06-02 | 2022-10-05 | 2023-07-03 | 2023-10-03 | Moray | 0 | 0 | 0 | 0 | 0 | 11337.21 | 26986.08 | 38323.29 | 311676.72 | 350000.01 | 0 | [6 empty] | CM_WSI | 100%
403139 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-12 | 2013-06-28 | 2013-09-02 | 2014-11-15 |  | Moray | 447551 | -7274 | 3744.23 | 0 | 0 | 0 | 0 | -3529.77 | 0 | 444021.23 | 0 | [6 empty] | CM_WSI | 100%
403934 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | WWINF | Strategic Capacity | MS0 | 2017-06-20 | 2020-08-24 | 2020-09-22 | 2021-09-09 | 2021-12-10 | Aberdeenshire | 2745 | 38205.19 | 21927.45 | 28903.36 | 254723.97 | 135028.91 | 826467.38 | 1305256.26 | 1002926.84 | 2310928.1 | 0 | [6 empty] | SG1 | 100%
500770 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS5 | 2015-07-24 | 2017-12-21 | 2018-02-26 | 2018-12-20 | 2018-12-20 | South Lanarkshire | 0 | 26795 | 98510 | 420695 | 505938 | 0 | 2400 | 1054338 | 0 | 1054338 | 0 | [6 empty] | CM_WWI | 100%
500694 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-08-25 | 2018-11-30 | 2018-12-18 | 2020-07-29 | 2020-07-29 | Falkirk | 0 | 38324 | 261068.37 | 130952.12 | 517779.64 | 1034486.92 | 216453.42 | 2199064.47 | 15537.48 | 2214601.95 | 0 |  |  |  |  | 21630 |  | CM_WWNI | 100%
500864 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS6 | 2015-08-10 | 2017-05-31 | 2017-08-02 | 2018-03-01 | 2019-05-01 | Orkney Islands | 0 | 1337.86 | 24414.31 | 227533.015 | 46839.455 | 2515.62 | 19.5 | 302659.76 | 0 | 302659.76 | 459211.1018 | [6 empty] | DW25P | 5% | DW3C | 95% | bar: Regulatory Outputs OMG-01
300016 | Q&S3A | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-05-23 | 2011-09-20 | 2011-10-31 | 2012-08-15 | 2013-07-25 | Orkney Islands | 3535272.03 | -430 | 0 | 0 | 0 | 0 | 0 | -430 | 0 | 3534842.03 | 5597 | [6 empty] | DW3 | 100%
502235 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS6 | 2016-11-18 | 2017-10-31 | 2017-10-31 | 2019-02-28 | 2019-02-28 | Orkney Islands | 0 | 0 | 38463.2 | 52908.8 | 196782.38 | 0 | 0 | 288154.38 | 0 | 288154.38 | 0 | [6 empty] | DW25D | 100%
501570 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS6 | 2016-03-25 | 2017-09-28 | 2017-10-23 | 2018-01-01 | 2019-06-01 | Orkney Islands | 0 | 4696.28 | 5496.43 | 52309.9525 | 11395.9375 | 473.58 | 471.75 | 74843.93 | 44.05 | 74887.98 | 466391.8995 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
502186 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2016-09-21 | 2016-09-30 | 2016-11-07 | 2019-09-19 | 2020-10-05 | Orkney Islands | 0 | 2093 | 82392.9 | 5583.4125 | 2339.54 | 83686.26 | 71783.64 | 247878.7525 | 1901.12 | 249779.8725 | 466391.8995 |  |  |  |  | 4700.0004 |  | DW25T | 100%
502388 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2022-05-24 | 2023-08-09 | 2023-12-12 | 2024-07-17 | 2024-10-17 | Orkney Islands | 0 | 0 | 10046.51 | 3142.9625 | 5111.2 | 0 | 0 | 18300.6725 | 481699.32 | 499999.9925 | 0 | [6 empty] | CM_WSNI | 100%
400258 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2010-01-25 | 2010-03-11 | 2011-10-10 | 2017-09-29 |  | Orkney Islands | 283940 | 571 | 512.74 | 0 | 0 | 600.4 | 0 | 1684.14 | 0 | 285624.14 | 0 | [6 empty] | CM_WSNI | 100%
400815 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-05-03 | 2013-11-18 | 2013-11-25 | 2015-06-10 | 2015-06-10 | Highland | 4883648.21 | 440694.64 | 12963.31 | -1080.77 | 0 | 0 | 0 | 452577.18 | 0 | 5336225.39 | 16065.6853 | [6 empty] | CS11A | 1.982% | CM_WWI | 2.972% | SG1 | 95.05%
403284 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-08 | 2013-03-19 | 2013-03-19 | 2013-09-13 |  | West Lothian | 176014 | -17.57 | 0 | 0 | 0 | 0 | 0 | -17.57 | 0 | 175996.43 | 0 | [6 empty] | CM_WSI | 100%
501528 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-07-22 | 2022-07-04 | 2022-11-07 | 2023-06-22 | 2023-09-22 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1617604.03 | 1617604.03 | 0 | [6 empty] | CM_WSNI | 100%
502427 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS6 | 2017-06-19 | 2017-09-18 | 2017-10-02 | 2017-12-01 | 2018-01-01 | Scottish Borders | 0 | 0 | 4280.32 | 26271.92 | 16632.76 | 0 | 0 | 47185 | 0 | 47185 | 30795.6344 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
045405 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-09-28 | 2012-09-10 | 2013-05-29 | 2013-08-22 | Scottish Borders | 1002209.01 | -18746.08 | 0 | 0 | 0 | 0 | 0 | -18746.08 | 0 | 983462.93 | 47047 | [6 empty] | DW23 | 100%
500798 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-07-24 | 2017-09-12 | 2018-03-26 | 2018-11-29 | 2018-11-29 | South Lanarkshire | 0 | 62345 | 94301 | 204917.34 | 215947.66 | 5489 | 0 | 583000 | 0 | 583000 | 0 | [6 empty] | CM_WWI | 100%
500800 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2016-01-12 | 2017-03-09 | 2017-03-30 | 2019-04-11 | 2019-12-13 | Scottish Borders | 0 | 15247.21 | 31202.93 | 40058.29 | 121580.63 | 17929.35 | 1417.49 | 227435.9 | 0 | 227435.9 | 201049.8957 | [6 empty] | DW5FS | 100%
500244 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2016-02-26 | 2018-03-27 | 2018-03-27 | 2020-08-01 | 2020-08-01 | Scottish Borders | 0 | 30177.5 | 322708.87 | 901046.7 | 300533.11 | 1671666.55 | 61499.93 | 3287632.66 | 9680.65 | 3297313.31 | 496627.1805 |  |  |  |  | 14160 |  | CM_WSNI | 50% | DW25P | 50% | bar: Regulatory Outputs OMG-04
502714 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-05-12 | 2017-05-12 | 2017-10-01 | 2019-07-15 | 2019-10-15 | Scottish Borders | 0 | 0 | 0 | 452474.305 | 8736.03 | 0 | 0 | 461210.335 | 0 | 461210.335 | 0 |  |  |  |  | 5000.0004 |  | CM_WSNI | 100%
502570 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2019-10-17 | 2021-11-08 | 2022-01-19 | 2022-12-29 | 2023-03-31 | Scottish Borders | 0 | 0 | 20930.23 | 80868.285 | 185035.6415 | 135872.85 | 196276.94 | 618983.9465 | 15381696.48 | 16000680.4265 | 148885.7057 | [6 empty] | WG1 | 100%
046268 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-12-17 | 2010-12-17 | 2011-01-26 | 2013-12-23 |  | Scottish Water Wide | 1507464.71 | 3356.88 | 0 | 0 | 0 | 0 | 0 | 3356.88 | 0 | 1510821.59 | 0 | [6 empty] | CM_WSNI | 100%
501394 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-06-29 | 2017-06-29 | 2017-10-16 | 2019-08-29 | 2019-08-30 | Scottish Water Wide | 0 | 0 | 42885.71 | 974265.44 | 509895.68 | 134682.92 | 3371.02 | 1665100.77 | 5745.16 | 1670845.93 | 0 | [6 empty] | CM_WSI | 100%
501462 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-04-26 | 2021-12-20 | 2022-04-14 | 2023-04-04 | 2023-06-27 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1552316.05 | 1552316.05 | 0 | [6 empty] | CM_WSI | 100%
500939 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS5 | 2015-09-02 | 2018-04-30 | 2018-09-28 | 2019-03-19 | 2019-03-19 | South Lanarkshire | 0 | 44364 | 34062 | 214724 | 927963 | 13015.06 | 24499.95 | 1258628.01 | 0 | 1258628.01 | 0 | [6 empty] | CM_WWI | 100%
503415 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2019-02-28 | 2019-02-28 | 2019-03-18 | 2019-11-22 | 2019-11-22 | South Lanarkshire | 0 | 0 | 0 | 0 | 32834.84 | 464050.11 | 1547.55 | 498432.5 | 3471.52 | 501904.02 | 0 | [6 empty] | CM_WWI | 100%
030107 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-23 | 2010-09-20 | 2010-11-29 | 2014-10-21 | 2015-01-05 | South Lanarkshire | 1948423.25 | 1623.02 | -1742.01 | 0 | 0 | 0 | 0 | -118.99 | 0 | 1948304.26 | 1307.345 | [6 empty] | CM_WWNI | 20% | EC01A | 80%
502307 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2021-04-05 | 2022-07-14 | 2022-11-03 | 2023-06-15 | 2023-09-15 | South Lanarkshire | 0 | 0 | 35014.7 | 690.59 | 5572.445 | 0 | 0 | 41277.735 | 2205950.27 | 2247228.005 | 148885.7057 | [6 empty] | SG1 | 100%
403750 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2014-04-03 | 2014-04-03 | 2014-07-30 | 2017-02-22 |  | South Lanarkshire | 352139 | 115361 | -38421.14 | 0 | 0 | 0 | 0 | 76939.86 | 0 | 429078.86 | 0 | [6 empty] | CM_WWNI | 100%
403404 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-05 | 2013-10-24 | 2013-11-18 | 2013-12-09 | 2014-03-21 | South Lanarkshire | 89207 | -618.32 | 0 | 0 | 0 | 0 | 0 | -618.32 | 0 | 88588.68 | 0 | [6 empty] | CM_WWI | 100%
500729 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2015-08-21 | 2022-01-03 | 2022-03-30 | 2022-10-24 | 2023-01-24 | Scottish Water Wide | 0 | 5306 | 95727 | 120208 | -23350 | 0 | 0 | 197891 | 840675.99 | 1038566.99 | 0 | [6 empty] | CM_WWI | 100%
501513 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2016-06-29 | 2017-12-20 | 2018-03-26 | 2019-07-11 | 2019-10-15 | Falkirk | 0 | 0 | 85352 | 205270 | 814546.02 | 19333.04 | 0.11 | 1124501.17 | 2399.84 | 1126901.01 | 0 | [6 empty] | CM_WWNI | 100%
501814 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-08-31 | 2016-09-29 | Fife | 0 | 10640.68 | 6602.48 | 0 | 0 | 0 | 0 | 17243.16 | 0 | 17243.16 | 148885.7057 | [6 empty] | SG1 | 100%
500898 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Water |  | SWMD | Flood Risk Management Act | MS6 | 2015-06-30 | 2015-06-30 | 2015-07-31 | 2017-08-01 | 2017-10-01 | West Dunbartonshire | 0 | 7000 | 330140.57 | 81493.7 | 0 | 0 | 0 | 418634.27 | 0 | 418634.27 | 985398.5607 | [6 empty] | WR6 | 100% | bar: Regulatory Outputs OMG-11
503379 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-04-25 | 2023-03-02 | 2023-07-05 | 2023-12-26 | 2024-03-27 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 66783.083 | 42190.94 | 28746.54 | 137720.563 | 10375.62 | 148096.183 | 148885.7057 | [6 empty] | SG1 | 100%
401333 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-21 | 2010-07-09 | 2010-09-21 | 2013-02-13 | 2013-12-19 | South Ayrshire | 6347735.04 | 8822.96 | 745.43 | 0 | 0 | 0 | 0 | 9568.39 | 0 | 6357303.43 | 37166.907 | [6 empty] | DW5 | 46.23% | CM_WSI | 53.77%
401334 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS4 | 2010-09-21 | 2010-07-09 | 2010-09-21 | 2018-03-01 | 2019-03-01 | South Ayrshire | 7858175 | -565446.03 | 26323.18 | 91419.67 | 548242.66 | 18949.44 | 10508.56 | 129997.48 | 0 | 7988172.48 | 64301.4708 | [6 empty] | CM_WSI | 17.82% | DW5 | 82.18% | bar: Regulatory Outputs OMG-03
401335 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS4 | 2010-09-21 | 2010-07-09 | 2010-09-21 | 2018-08-01 | 2019-03-01 | South Ayrshire | 9254841 | -292999.35 | 19123.95 | 76176.06 | 24037.1 | 0 | 0 | -173662.24 | 0 | 9081178.76 | 76678.9963 | [6 empty] | CM_WSI | 16.79% | DW5 | 83.21% | bar: Regulatory Outputs OMG-03
401336 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-21 | 2010-07-09 | 2010-09-21 | 2012-04-30 | 2013-06-25 | South Ayrshire | 2784173 | 27722 | -146080.1 | 0 | 0 | 0 | 0 | -118358.1 | 0 | 2665814.9 | 22186.9981 | [6 empty] | DW5 | 41.48% | CM_WSI | 58.52%
500005 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-04-24 | 2019-02-12 | 2019-02-25 | 2019-04-08 | 2019-04-09 | South Ayrshire | 0 | 89898 | 203683.62 | 272171.38 | 207426 | 0 | 0 | 773179 | 0 | 773179 | 0 | [6 empty] | CM_WSI | 100%
403942 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-09-25 | 2016-03-29 | 2016-04-04 | 2017-03-16 |  | South Ayrshire | 335975.53 | 464830.47 | 82986.42 | 66897.06 | 0 | 0 | 0 | 614713.95 | 0 | 950689.48 | 0 | [6 empty] | CM_WSI | 100%
500040 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS3 | 2015-04-13 | 2016-09-23 | 2016-09-26 | 2020-08-25 | 2021-01-18 | South Ayrshire | 0 | 312710 | 139433 | 627304 | 357720.08 | 78000 | 1109987.77 | 2625154.85 | 0 | 2625154.85 | 2279880.8311 | [6 empty] | DW5FS | 100%
403309 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS1 | 2013-06-06 | 2019-05-27 | 2019-06-03 | 2019-06-04 |  | South Ayrshire | 24000 | 37122.47 | 8892.53 | 142104 | 113520 | 670171.88 | 0 | 971810.88 | 0 | 995810.88 | 0 | [6 empty] | CM_WSI | 100%
500685 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-07-09 | 2022-03-14 | 2022-04-11 | 2022-07-01 | 2022-07-01 | South Ayrshire | 0 | 416098 | 92035 | -10000 | 27820 | 0 | 0 | 525953 | 830523.01 | 1356476.01 | 0 | [6 empty] | CM_WSI | 100%
501178 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-25 | 2022-02-28 | 2022-04-27 | 2022-11-08 | 2023-02-08 | East Ayrshire | 0 | 0 | 20152.97 | 0 | 14304.76 | 0 | 0 | 34457.73 | 737407.99 | 771865.72 | 0 | [6 empty] | CM_WSI | 100%
403316 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS5 | 2013-03-25 | 2013-03-25 | 2013-04-02 | 2018-12-10 | 2018-12-10 | South Ayrshire | 980000 | 116583 | 47995.52 | 34000 | -14902.4 | 0 | 0 | 183676.12 | 0 | 1163676.12 | 0 | [6 empty] | CM_WSNI | 100%
502960 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2017-11-07 | 2018-07-13 | 2018-07-13 | 2020-02-27 | 2020-05-28 | South Ayrshire | 0 | 0 | 0 | 222976.29 | 4227444.63 | 2091207.6 | 1630334.26 | 8171962.78 | 32412.21 | 8204374.99 | 0 | [6 empty] | CM_WSNI | 100%
500709 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS0 | 2017-10-30 | 2019-12-09 | 2020-01-28 | 2021-07-30 | 2021-10-27 | South Ayrshire | 0 | 35821 | -6582.56 | 57931.55 | 165906.79 | 662640.64 | 4565830.84 | 5481548.26 | 835159.74 | 6316708 | 1582934.7791 | [6 empty] | CM_WSNI | 15.27% | DW25P | 84.73%
046266 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-11-20 | 2010-11-26 | 2011-02-28 | 2014-09-16 | 2015-11-02 | South Ayrshire | 1007295.56 | 1382.64 | -362 | 0 | 0 | 0 | 0 | 1020.64 | 0 | 1008316.2 | 0 | [6 empty] | CM_WSNI | 100%
502412 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2015-07-16 | 2017-03-13 | 2017-03-27 | 2019-05-31 | 2019-09-05 | South Ayrshire | 0 | 0 | 1151164.05 | 11277843.69 | 2270210.3 | 307380.03 | 79601.86 | 15086199.93 | 13938.07 | 15100138 | 10839215.9436 |  |  |  |  | 48000 |  | DW25PS | 33.33% | DW25P | 33.33% | DW2_S | 33.33%
403407 | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWMD | Renewable power | MS6 | 2013-03-01 | 2013-03-01 | 2017-03-27 | 2018-03-01 | 2018-04-01 | Stirling | 758220.29 | 54797.71 | -4385 | 824054.745 | 325972.805 | 16277.58 | 3722.39 | 1220440.23 | 0 | 1978660.52 | 764721.6298 | [6 empty] | CC1W | 100% | [18 empty] | Regulatory Outputs OMG-43: 0.74
501185 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2016-05-31 | 2017-09-15 | 2018-02-09 | 2018-11-30 | 2018-11-30 | South Lanarkshire | 0 | 0 | 106074 | 719318 | 905838 | 0 | 2400 | 1733630 | 0 | 1733630 | 0 | [6 empty] | CM_WWNI | 100%
502557 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-05-17 | 2023-02-28 | 2023-05-24 | 2023-12-25 | 2024-03-25 | Aberdeenshire | 0 | 0 | 0 | 57911.7035 | 12332.105 | 0 | 0 | 70243.8085 | 669756.09 | 739999.8985 | 0 | [6 empty] | CM_WSNI | 100%
501210 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS4 | 2017-03-20 | 2018-03-13 | 2018-07-27 | 2018-11-01 | 2019-03-01 | Aberdeenshire | 0 | 1440 | 25259.9 | 12692.1 | 157760.52 | 3608.83 | 708 | 201469.35 | 683.22 | 202152.57 | 44129.723 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
045312 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-24 | 2011-03-23 | 2011-07-22 | 2012-01-19 | 2012-03-14 | Aberdeenshire | 202516.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202516.79 | 0 | [6 empty] | DW13 | 100%
503322 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2019-06-05 | 2019-06-05 | 2019-06-05 | 2019-06-05 | 2019-06-05 | Aberdeenshire | 0 | 0 | 0 | 0 | 64479.32 | 0 | 0 | 64479.32 | 0 | 64479.32 | 148885.7057 | [6 empty] | SG1 | 100%
500875 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS5 | 2016-08-18 | 2017-07-25 | 2018-02-28 | 2018-05-01 | 2019-12-01 | Highland | 0 | 969 | 1179.65 | 3727.09 | 9278.21 | 5000 | 0 | 20153.95 | 0 | 20153.95 | 20284.2493 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 3.05
500934 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2015-10-07 | 2016-07-21 | 2016-08-26 | 2019-05-27 | 2019-05-27 | Angus | 0 | 515113 | 781423.75 | 1282268.43 | 768277.25 | 301865.65 | 1451.69 | 3650399.77 | 3377.87 | 3653777.64 | 0 | [6 empty] | CM_WWI | 100%
500123 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS5 | 2015-03-20 | 2016-11-24 | 2016-11-25 | 2018-11-29 | 2019-03-29 | Angus | 0 | 14782 | 19950 | 5490 | 7156 | 9622.01 | 0 | 57000.01 | 0 | 57000.01 | 10362.528 | [6 empty] | EC01G | 39.74% | CS16D | 60.26%
500969 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2015-10-13 | 2020-03-09 | 2020-05-20 | 2020-12-10 | 2021-03-29 | Angus | 0 | 3478.79 | 146.15 | 45.7 | 9.11 | 96135.94 | 386531.74 | 486347.43 | 22141.62 | 508489.05 | 0 | [6 empty] | CM_WWI | 100%
045673 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-08-11 | 2010-12-21 | 2011-05-09 | 2013-03-28 |  | Angus | 451850.43 | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 451856.43 | 0 | [6 empty] | CM_WWNI | 100%
030115 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-11-12 | 2010-12-23 | 2011-03-07 | 2013-11-29 | 2013-12-12 | Angus | 2585102.49 | 234536.1 | 0 | 0 | 0 | 0 | 0 | 234536.1 | 0 | 2819638.59 | 3028.6926 | [6 empty] | EC01A | 40% | CM_WWNI | 60%
502885 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2021-04-01 | 2022-12-01 | 2023-03-29 | 2024-06-24 | 2024-09-24 | Angus | 0 | 0 | 0 | 47918.17 | 5647.33 | 20154.84 | 20076.72 | 93797.06 | 961294.94 | 1055092 | 0 | [6 empty] | CM_WWNI | 100%
502333 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2020-03-12 | 2021-06-28 | 2021-10-15 | 2022-05-27 | 2022-08-29 | Angus | 0 | 0 | 45288.41 | 16165.9825 | 45692.123 | 13213.89 | 438604.81 | 558965.2155 | 5443340.02 | 6002305.2355 | 148885.7057 | [6 empty] | SG1 | 100%
500856 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-06-01 | 2017-05-31 | 2017-08-07 | 2019-01-01 | 2019-09-01 | Shetland Islands | 0 | 1178.51 | 926.64 | 8874.98 | 18247.5 | 9878.82 | 0 | 39106.45 | 0 | 39106.45 | 49754.6461 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 17.99
502775 | Q&S4 | Supporting economic development | First Time Provision |  |  | Water |  | SWD | First Time Provision | GW0 | 2019-08-28 | 2021-04-12 | 2021-07-06 | 2023-01-18 | 2023-04-18 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 12118.635 | 117033.865 | 222577.29 | 144931.1 | 496660.89 | 4482491.57 | 4979152.46 | 1081305.7956 | [6 empty] | WG3 | 100%
403068 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-11-21 | 2014-07-15 | 2014-07-16 | 2015-03-30 | 2015-03-30 | West Lothian | 511864 | 16096 | -0.47 | -12652.83 | 0 | 0 | 0 | 3442.7 | 0 | 515306.7 | 229318.7788 | [6 empty] | CS11 | 100%
402691 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-08-31 | 2013-09-24 | 2013-11-12 | 2014-11-04 |  | Aberdeenshire | 308442 | 8312 | -1648.43 | 0 | 0 | 0 | 0 | 6663.57 | 0 | 315105.57 | 0 | [6 empty] | CM_WSI | 100%
503295 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2020-07-27 | 2021-03-15 | 2021-07-13 | 2022-07-08 | 2022-10-10 | Highland | 0 | 0 | 0 | 0 | 20233.02 | 36316.71 | 1011814.41 | 1068364.14 | 10951868.83 | 12020232.97 | 148885.7057 | [6 empty] | WG1 | 100%
030119 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-24 | 2011-03-31 | 2011-10-17 | 2013-08-08 | 2015-03-06 | Highland | 232609.57 | 1846.82 | 0 | 0 | 0 | 0 | 0 | 1846.82 | 0 | 234456.39 | 957.0001 | [6 empty] | DW13 | 100%
501834 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2021-07-15 | 2022-04-06 | 2022-07-04 | 2023-02-01 | 2023-05-04 | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439829.89 | 439829.89 | 0 | [6 empty] | CM_WSI | 100%
402822 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-09-11 | 2015-10-05 | 2015-10-05 | 2015-10-05 |  | Falkirk | 52290 | -1735.32 | 0 | 0 | 0 | 0 | 0 | -1735.32 | 0 | 50554.68 | 0 | [6 empty] | CM_WSI | 100%
401973 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-05-12 | 2016-03-31 | 2016-10-10 | 2017-10-06 |  | South Ayrshire | 34191 | 41708 | 83421 | -19430.88 | 0 | 0 | 0 | 105698.12 | 0 | 139889.12 | 0 | [6 empty] | CM_WSI | 100%
503382 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MSU | 2022-07-07 | 2023-05-16 | 2023-09-18 | 2024-03-08 | 2024-06-10 | North Ayrshire | 0 | 0 | 0 | 0 | 64237.594 | 20448.03 | 25069 | 109754.624 | 35498.27 | 145252.894 | 148885.7057 | [6 empty] | SG1 | 100%
403430 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-04-18 | 2014-11-04 | 2014-11-04 | 2015-03-27 | 2015-03-27 | Aberdeenshire | 600114 | 120977 | 0.48 | -1155.86 | 0 | 0 | 0 | 119821.62 | 0 | 719935.62 | 229318.7788 | [6 empty] | CS11A | 100%
500117 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2015-03-19 | 2016-03-30 | 2016-08-31 | 2019-07-01 | 2019-10-01 | Highland | 0 | 23507 | 3106 | 44279 | 40324 | 37243.13 | 785.86 | 149244.99 | 0 | 149244.99 | 83128.4412 | [6 empty] | EC01G | 14.83% | EC01D | 85.17% | bar: Regulatory Outputs OMG-23
300021 | Q&S3A | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2011-03-30 | 2011-08-30 | 2011-10-10 | 2012-02-20 |  | Aberdeenshire | 36835.17 | -642.63 | 0 | 0 | 0 | 0 | 0 | -642.63 | 0 | 36192.54 | 0 | [6 empty] | WWI | 100%
503511 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2019-07-01 | 2019-07-29 | 2019-11-28 | 2021-07-05 | 2021-10-05 | Fife | 0 | 0 | 0 | 0 | 0 | 195905.92 | 291027.88 | 486933.8 | 163066.19 | 649999.99 | 0 | [6 empty] | CM_WWNI | 100%
402990 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-10-01 | 2013-03-15 | 2013-11-18 | 2014-01-23 | 2014-01-23 | Glasgow City | 20060 | -316.06 | 0 | 0 | 0 | 0 | 0 | -316.06 | 0 | 19743.94 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
402644 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-06-18 | 2012-06-18 | 2012-07-30 | 2017-01-02 |  | North Ayrshire | 649024.58 | 94390.42 | 7115.59 | 0 | 0 | 0 | 0 | 101506.01 | 0 | 750530.59 | 0 | [6 empty] | CM_WWNI | 100%
502864 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-08-28 | 2018-02-23 | 2018-02-26 | 2020-01-07 | 2020-04-08 | North Ayrshire | 0 | 0 | 0 | 143775.035 | 19624.965 | 11995.16 | 705.52 | 176100.68 | 583.33 | 176684.01 | 0 | [6 empty] | CM_WWNI | 100%
046245 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-12-11 | 2010-10-04 | 2010-09-27 | 2011-02-01 | 2011-02-01 | Dumfries and Galloway | 129350.3 | 1.68 | 0 | 0 | 0 | 0 | 0 | 1.68 | 0 | 129351.98 | 0 | [6 empty] | CM_WSI | 100%
500027 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-11-22 | 2017-06-21 | 2017-06-21 | 2017-06-21 | 2017-06-21 | Argyll and Bute-North Argyll | 0 | 502.5 | 911.25 | 0 | 0 | 0 | 0 | 1413.75 | 0 | 1413.75 | 0 | [6 empty] | CM_WSI | 100%
500642 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWMD | Supply Resilience | MS7 | 2015-06-23 | 2015-10-23 | 2016-03-14 | 2016-02-01 | 2016-03-01 | Argyll and Bute-North Argyll | 0 | 709154 | 480481.06 | 4453.63 | 675.3325 | 0 | 0 | 1194764.0225 | 0 | 1194764.0225 | 1817908.3275 | [6 empty] | CS16WR | 1.674% | CM_WSI | 98.33% | bar: Regulatory Outputs OMG-07
500911 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2015-11-24 | 2016-03-25 | 2016-03-25 | 2016-03-01 | 2016-03-01 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
500786 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-08-14 | 2016-03-07 | 2016-04-25 | 2016-05-03 | 2016-05-03 | Stirling | 0 | 238924.93 | 272.45 | 0 | 0 | 0 | 0 | 239197.38 | 0 | 239197.38 | 0 | [6 empty] | CM_WSI | 100%
502556 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2017-11-21 | 2019-06-10 | 2019-08-12 | 2020-04-09 | 2020-06-24 | Stirling | 0 | 0 | 14408.37 | 23098.836 | 14095.144 | 87916.21 | 20699.22 | 160217.78 | 782.19 | 160999.97 | 0 | [6 empty] | CM_WSNI | 100%
500697 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-07-15 | 2016-06-28 | 2016-07-22 | 2016-08-30 | 2016-08-30 | Stirling | 0 | 2490 | 284341.33 | -831.33 | -102.16 | 0 | 0 | 285897.84 | 0 | 285897.84 | 0 | [6 empty] | CM_WSNI | 100%
503548 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2019-07-01 | 2019-07-08 | 2019-10-22 | 2020-06-08 | 2020-09-08 | Stirling | 0 | 0 | 0 | 0 | 0 | 172443.45 | 115518.71 | 287962.16 | 2037.81 | 289999.97 | 0 | [6 empty] | CM_WSNI | 100%
502132 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS3 | 2016-03-17 | 2019-03-29 | 2019-03-19 | 2020-12-01 | 2021-11-29 | Stirling | 0 | 19141.6 | 189820.4 | 758551.95 | 5045526.2695 | 17298167.49 | 6257799.66 | 29569007.3695 | 698453.88 | 30267461.2495 | 8083708.1066 |  |  |  |  | -143000.0004 |  | WR1 | 2.01% | DW25P | 5.05% | CM_WSNI | 43.27% | DW2 | 49.67%
402998 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-22 | 2013-09-24 | 2014-02-07 | 2014-07-04 |  | Scottish Borders | 393397.08 | 3518.12 | 0 | 0 | 0 | 0 | 0 | 3518.12 | 0 | 396915.2 | 0 | [6 empty] | CM_WSI | 100%
402848 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS7 | 2012-08-15 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-23 | Highland | 204996 | -32318 | -172677 | 0 | 0 | 0 | 0 | -204995 | 0 | 1 | 0 | [6 empty] | CS11 | 100%
503122 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS0 | 2019-02-08 | 2020-04-06 | 2020-07-06 | 2021-10-01 | 2021-12-24 | South Lanarkshire | 0 | 0 | 0 | 266.176 | 188327.824 | 216993.36 | 354816.33 | 760403.69 | 227611.19 | 988014.88 | 0 | [6 empty] | CM_WWI | 100%
502579 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-05-26 | 2017-05-26 | 2017-05-26 | 2017-03-15 | 2017-03-15 | South Lanarkshire | 0 | 0 | 2209.57 | 228.35 | 212.9 | 0 | 0 | 2650.82 | 0 | 2650.82 | 0 | [6 empty] | CM_WWI | 100%
045789 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2011-12-12 | 2012-02-13 | 2013-03-28 | 2013-03-29 | Dundee City | 730464.48 | -3196.05 | 0 | 0 | 0 | 0 | 0 | -3196.05 | 0 | 727268.43 | 3394.95 | [6 empty] | WQ01B | 5% | CM_WWNI | 25% | WQ01C | 70%
500233 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | WWINF | Strategic Capacity | MS0 | 2018-09-04 | 2020-07-27 | 2020-10-14 | 2021-07-27 | 2021-10-29 | Perth and Kinross | 0 | 51135.77 | 46906.81 | 27162.89 | 57031.53 | 179907.06 | 763509.86 | 1125653.92 | 708234.96 | 1833888.88 | 148885.7057 | [6 empty] | SG1 | 100%
500049 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS6 | 2012-12-31 | 2016-12-20 | 2017-02-06 | 2017-12-01 | 2018-01-01 | East Renfrewshire | 0 | 61000 | 239240 | 194480 | 0 | 0 | 0 | 494720 | 0 | 494720 | 19932.9779 | [6 empty] | EC01F | 20.58% | CM_WWNI | 79.42% | bar: Regulatory Outputs OMG-18
500674 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-06-05 | 2018-02-28 | 2018-02-28 | 2019-07-26 |  | Scottish Water Wide | 0 | 216302 | 531415 | 1123073.78 | 1238451.23 | 1690727 | 0 | 4799969.01 | 0 | 4799969.01 | 0 |  |  |  |  | 381999.9996 |  | CM_M&G | 100%
500588 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-09-25 | 2018-01-31 | 2018-01-31 | 2019-06-25 | 2019-06-26 | Scottish Water Wide | 0 | 297862 | 493380.36 | 394478.48 | 9868.61 | 86103.88 | 0 | 1281693.33 | 0 | 1281693.33 | 0 | [6 empty] | CM_M&G | 100%
502587 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-06-04 | 2022-03-14 | 2022-05-30 | 2022-10-12 | 2023-01-12 | Angus | 0 | 0 | 5320 | 7880.791 | 1220.12 | 0 | 0 | 14420.911 | 722212.1 | 736633.011 | 0 | [6 empty] | CM_WSI | 100%
503529 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2019-07-01 | 2019-08-05 | 2019-12-05 | 2021-07-12 | 2021-10-12 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 137881.86 | 210926.41 | 348808.27 | 131191.72 | 479999.99 | 0 | [6 empty] | CM_WSI | 100%
403893 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-07-10 | 2015-01-29 | 2015-04-06 | 2018-10-22 | 2018-10-22 | North Ayrshire | 108014.75 | 543674.25 | 34079 | 255500.42 | 13282.4639 | 0 | 0 | 846536.1339 | 0 | 954550.8839 | 0 | [6 empty] | CM_WSI | 100%
402179 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-07-14 | 2015-04-17 | 2014-08-14 | 2014-08-14 | 2014-08-14 | North Ayrshire | 735726 | 51.8 | 0 | 0 | 0 | 0 | 0 | 51.8 | 0 | 735777.8 | 0 | [6 empty] | CM_WSI | 100%
401376 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-11-08 | 2012-05-02 | 2012-08-27 | 2013-12-19 | 2013-12-19 | Scottish Borders | 1719185.32 | 1833.26 | 0 | 0 | 0 | 0 | 0 | 1833.26 | 0 | 1721018.58 | 0 | [6 empty] | SG1 | 100%
403910 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS5 | 2014-10-24 | 2015-09-21 | 2015-11-30 | 2018-09-26 | 2018-09-26 | Aberdeen City | 13417 | 33649 | 9509.63 | 3052 | 147064.9 | 18072.33 | 235.13 | 211582.99 | 0 | 224999.99 | 0 | [6 empty] | WG5 | 100%
501567 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2019-03-29 | 2020-07-20 | 2020-10-26 | 2021-06-24 | 2021-09-24 | Aberdeen City | 0 | 5023.26 | 35993.26 | 59273.5725 | 22834.8525 | 154065.84 | 852401.68 | 1129592.465 | 681362.13 | 1810954.595 | 0 | [6 empty] | CM_WSI | 100%
404096 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2015-03-18 | 2015-03-18 | 2015-03-18 | 2016-10-13 | 2017-03-02 | West Lothian | 351960.59 | 5921.41 | 64118.12 | 0 | 0 | 0 | 0 | 70039.53 | 0 | 422000.12 | 0 | [6 empty] | WG5 | 100%
402876 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2012-12-21 | 2017-06-30 | 2017-08-21 | 2018-05-30 |  | Falkirk | 26923 | 28893.64 | 114175.36 | 322796 | 42200.9234 | 0 | 0 | 508065.9234 | 0 | 534988.9234 | 0 | [6 empty] | CM_WWI | 100%
402875 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-01-11 | 2016-02-29 | 2016-02-18 | 2016-02-19 |  | Stirling | 88246 | 8283.31 | 0 | 0 | 0 | 0 | 0 | 8283.31 | 0 | 96529.31 | 0 | [6 empty] | CM_M&G | 24% | CM_WWI | 76%
503307 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-03-21 | 2023-09-08 | 2024-01-08 | 2025-01-03 | 2025-04-07 | Stirling | 0 | 0 | 0 | 0 | 28915.3 | 22722.57 | 22634.56 | 74272.43 | 72346.42 | 146618.85 | 148885.7057 | [6 empty] | SG1 | 100%
500232 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2015-09-08 | 2015-09-08 | 2015-09-08 | 2015-08-19 | 2015-09-08 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG1 | 100%
501720 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2019-03-13 | 2020-01-13 | 2020-04-13 | 2020-08-25 | 2020-11-25 | Glasgow City | 0 | 0 | 6731.42 | 0 | 11432.22 | 402050.53 | 525356.09 | 945570.26 | 5961.35 | 951531.61 | 0 | [6 empty] | CM_WWI | 100%
501161 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2016-02-11 | 2017-06-05 | 2017-11-09 | 2018-10-31 | 2018-10-31 | Glasgow City | 0 | 1126 | 114705 | 508928 | 144232 | 2500 | 0 | 771491 | 0 | 771491 | 0 | [6 empty] | CM_WWNI | 100%
501162 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS5 | 2016-02-17 | 2017-06-05 | 2017-11-09 | 2019-02-27 | 2019-02-27 | Glasgow City | 0 | 858.64 | 92229.36 | 517442 | 188650 | 0 | 2500 | 801680 | 0 | 801680 | 0 | [6 empty] | CM_WWNI | 100%
501112 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2016-08-25 | 2021-12-06 | 2022-04-14 | 2022-11-23 | 2023-02-23 | Argyll and Bute-North Argyll | 0 | 18000 | 55006.2 | 553 | 0 | 0 | 0 | 73559.2 | 925130.27 | 998689.47 | 0 | [6 empty] | CM_WSNI | 100%
403331 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-19 | 2013-02-19 | 2013-03-01 | 2013-08-09 |  | Argyll and Bute-North Argyll | 631330.27 | 5661.45 | 0 | 0 | 0 | 0 | 0 | 5661.45 | 0 | 636991.72 | 0 | [6 empty] | CM_WSI | 100%
502978 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2021-04-01 | 2022-07-01 | 2022-10-28 | 2023-06-09 | 2023-09-11 | Highland | 0 | 0 | 0 | 31695.59 | 1005.99 | 4610.01 | 36699.48 | 74011.07 | 6425999.5 | 6500010.57 | 0 | [6 empty] | CM_WWNI | 100%
046246 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-01-05 | 2011-06-23 | 2011-07-22 | 2012-01-25 | 2012-01-25 | North Ayrshire | 284478.74 | 3.55 | 0 | 0 | 0 | 0 | 0 | 3.55 | 0 | 284482.29 | 0 | [6 empty] | CM_WSI | 100%
503061 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWD | Reservoirs | GW1 | 2019-06-26 | 2021-08-09 | 2021-12-10 | 2023-11-14 | 2024-02-14 | North Ayrshire | 0 | 0 | 0 | 6402.7 | 0 | 22245.99 | 52602.76 | 81251.45 | 668722.17 | 749973.62 | 1560467.3848 | [6 empty] | CS22 | 100%
502136 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS5 | 2016-03-30 | 2017-11-10 | 2017-11-30 | 2017-07-01 | 2019-03-01 | North Ayrshire | 0 | 0 | 802.96 | 1239.675 | 85.165 | 0 | 0 | 2127.8 | 0 | 2127.8 | 37638.2409 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
402204 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-07-19 | 2011-09-21 | 2011-10-17 | 2012-02-21 |  | North Ayrshire | 141431.12 | 374.85 | 0 | 0 | 0 | 0 | 0 | 374.85 | 0 | 141805.97 | 0 | [6 empty] | CM_WSNI | 100%
500016 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS0 | 2015-05-08 | 2019-07-08 | 2019-07-16 | 2019-10-29 | 2019-10-30 | South Lanarkshire | 0 | 35428 | 52345.52 | -84612.51 | 76069.91 | 161386.79 | 945.7 | 241563.41 | 835.29 | 242398.7 | 0 | [6 empty] | CM_M&G | 100%
502785 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2019-02-28 | 2020-05-25 | 2020-09-29 | 2021-05-17 | 2021-08-17 | South Lanarkshire | 0 | 0 | 0 | 10670.11 | 19896.1205 | 24887.09 | 513039.94 | 568493.2605 | 249023.63 | 817516.8905 | 0 | [6 empty] | CM_WSI | 100%
502735 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS2 | 2017-10-20 | 2019-02-21 | 2019-04-23 | 2019-12-11 | 2020-03-26 | Fife | 0 | 0 | 0 | 22566 | 100133 | 228333.88 | 0.05 | 351032.93 | 2400 | 353432.93 | 0 | [6 empty] | CM_WWI | 100%
503195 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS0 | 2018-12-20 | 2019-09-16 | 2019-11-18 | 2020-11-01 | 2021-09-01 | South Lanarkshire | 0 | 0 | 0 | 0 | 267807 | 1089326.3 | 1033696.76 | 2390830.06 | 0 | 2390830.06 | 0 | [6 empty] | DW5FS | 50% | DW5MR | 50% | [16 empty] | Regulatory Outputs OMG-06: 278.1064
501275 | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | MSU | 2019-06-13 | 2019-06-13 | 2019-06-13 | 2019-06-13 | 2019-06-13 | South Lanarkshire | 0 | 0 | 41062.04 | -11907.62 | -19022.56 | 0 | 0 | 10131.86 | 0 | 10131.86 | 0 | [6 empty] | I2S_WI | 100%
500038 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2015-05-08 | 2021-04-12 | 2021-08-12 | 2021-09-22 | 2021-12-23 | South Lanarkshire | 0 | 61609 | 148634.01 | 7216.62 | 0 | 0 | 0 | 217459.63 | 0 | 217459.63 | 0 | [6 empty] | CM_WSNI | 100%
402123 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-05-27 | 2013-09-17 | 2013-10-21 | 2014-03-26 | 2014-03-26 | Highland | 490340 | 1445.71 | 0 | 0 | 0 | 0 | 0 | 1445.71 | 0 | 491785.71 | 0 | [6 empty] | SG1 | 100%
403465 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2013-04-15 | 2015-04-23 | 2015-02-12 | 2015-02-12 | 2015-02-12 | Dumfries and Galloway | 660977.3 | 365.46 | 0 | 0 | 0 | 0 | 0 | 365.46 | 0 | 661342.76 | 0 | [6 empty] | SG1 | 100%
403943 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS1 | 2014-12-19 | 2019-07-15 | 2019-08-26 | 2021-01-08 | 2021-01-08 | Dumfries and Galloway | 79731 | 254057 | 309429 | 502245 | 296718 | 1529684.01 | 2861273.04 | 5753406.05 | 503746.45 | 6336883.5 | 0 | [6 empty] | SG1 | 100%
500597 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 1774532.76 | 1929016.3 | 1814460.4615 | 1506491.7876 | 0 | 0 | 7024501.3091 | 0 | 7024501.3091 | 0 | [6 empty] | CM_OVH | 100%
500598 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 274139.35 | 499417.02 | 550632.43 | 1273989.1697 | 13.65 | 13.49 | 2598205.1097 | 2.87 | 2598207.9797 | 0 | [6 empty] | CM_OVH | 100%
500599 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 203924.34 | 201080.54 | -263805.04 | 0 | 44.55 | 44.39 | 141288.78 | 30.06 | 141318.84 | 0 | [6 empty] | CM_OVH | 100%
500600 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 1049362.04 | 1633223.89 | 2100086.6673 | 2488812.1167 | 0 | 0 | 7271484.714 | 0 | 7271484.714 | 0 | [6 empty] | CM_OVH | 100%
500601 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 185856.56 | 9600.99 | 34494.689 | 31329.2175 | 0 | 0 | 261281.4565 | 0 | 261281.4565 | 0 |  |  |  |  | 7362 |  | CM_OVH | 100%
500602 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 1215211.18 | 1348764.06 | 940614.8541 | 837785.7325 | 0 | 0 | 4342375.8266 | 0 | 4342375.8266 | 0 | [6 empty] | CM_OVH | 100%
500603 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 3480760.2 | 4556197.16 | 4912233.1789 | 4815935.2512 | 0 | 0 | 17765125.7901 | 0 | 17765125.7901 | 0 | [6 empty] | CM_OVH | 100%
500604 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 1194333.15 | 1340614.23 | 1597066.9307 | 1747431.2875 | 0 | 0 | 5879445.5982 | 0 | 5879445.5982 | 0 | [6 empty] | CM_OVH | 100%
500605 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 297039.97 | 1038702.22 | 1634463.4907 | 1345474.599 | 0 | 0 | 4315680.2797 | 0 | 4315680.2797 | 0 | [6 empty] | CM_OVH | 100%
500596 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 328648.62 | 274894.56 | 208045.4277 | 245244.82 | 0 | 0 | 1056833.4277 | 0 | 1056833.4277 | 0 |  |  |  |  | 0.9996 |  | CM_OVH | 100%
400736 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-21 | 2010-04-21 | 2011-04-01 | 2015-07-02 |  | Scottish Water Wide | 667304.77 | 50190.75 | 827.2 | 0 | 0 | 0 | 0 | 51017.95 | 0 | 718322.72 | 0 | [6 empty] | CM_WSI | 100%
400735 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-21 | 2010-04-21 | 2010-04-21 | 2016-10-06 |  | Scottish Water Wide | 440186 | 12505.69 | 0 | 0 | 0 | 0 | 0 | 12505.69 | 0 | 452691.69 | 0 | [6 empty] | CM_WSI | 100%
400397 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS5 | 2001-02-25 | 2005-01-21 | 2005-02-21 | 2018-10-08 | 2018-10-08 | Aberdeen City | -0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | [6 empty] | WSI | 100%
400753 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2011-04-29 | 2015-06-15 |  | Scottish Water Wide | 524000 | -15665.75 | 0 | 0 | 0 | 0 | 0 | -15665.75 | 0 | 508334.25 | 0 | [6 empty] | CM_WSI | 100%
400754 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2010-06-21 | 2015-06-15 |  | Scottish Water Wide | 176973 | -671.15 | 0 | 0 | 0 | 0 | 0 | -671.15 | 0 | 176301.85 | 0 | [6 empty] | CM_WSI | 100%
030532 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-02-19 | 2010-06-28 | 2010-10-04 | 2012-03-22 | 2012-03-26 | North Lanarkshire | 8631398.41 | 14242.54 | -14364.54 | 0 | 0 | 0 | 0 | -122 | 0 | 8631276.41 | 0 | [6 empty] | SG1 | 4.005% | EC10A | 6.014% | EC04A | 18.65% | EC01A | 23.4% | CM_WWNI | 47.93%
500806 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2016-07-19 | 2017-08-28 | 2017-06-12 | 2017-06-12 | 2017-06-12 | North Lanarkshire | 0 | 10836.78 | 91986.07 | 21321.9125 | 0 | 0 | 0 | 124144.7625 | 0 | 124144.7625 | 148885.7057 | [6 empty] | SG1 | 100%
502584 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS3 | 2017-03-07 | 2018-10-03 | 2018-10-15 | 2020-02-06 | 2020-05-08 | North Lanarkshire | 0 | 0 | 4285.05 | 146534.61 | 696721.61 | 610117.05 | 92703.69 | 1550362.01 | 3680.81 | 1554042.82 | 148885.7057 | [6 empty] | SG1 | 100%
500857 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2016-08-17 | 2017-06-25 | 2018-02-02 | 2018-04-01 | 2018-12-01 | Highland | 0 | 978.55 | 911.7 | 8342.186 | 14327.034 | 750.02 | 0 | 25309.49 | 0 | 25309.49 | 3981.6295 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 13.25
502627 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-03 | 2024-12-02 | 2025-02-04 | 2026-01-14 | 2026-04-16 | Highland | 0 | 0 | 20930.23 | 291.13 | 2187.97 | 12102.78 | 12055.87 | 47567.98 | 7953032.09 | 8000600.07 | 148885.7057 | [6 empty] | WG1 | 100%
403528 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2013-07-12 | 2014-09-30 | 2014-11-10 | 2015-03-27 | 2015-03-27 | Glasgow City | 298317 | -36304.44 | 74.61 | 0.01 | 66026.5 | 0 | 0 | 29796.68 | 0 | 328113.68 | 229318.7788 | [6 empty] | CS11 | 100%
045562 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-29 | 2011-02-07 | 2011-05-09 | 2011-11-10 | 2011-11-17 | Scottish Borders | 519365.92 | 78.34 | 0 | 0 | 0 | 0 | 0 | 78.34 | 0 | 519444.26 | 0 | [6 empty] | WQ01 | 19.75% | CM_WWNI | 80.25%
502824 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-10-25 | 2022-07-22 | 2022-11-14 | 2023-11-02 | 2024-02-02 | Scottish Borders | 0 | 0 | 0 | 74056.346 | 14864.157 | 32520.35 | 21826.5 | 143267.353 | 7787.92 | 151055.273 | 148885.7057 | [6 empty] | SG1 | 100%
502222 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MS7 | 2016-08-15 | 2016-08-15 | 2016-11-16 | 2017-07-20 | 2017-07-20 | Scottish Water Wide | 0 | 0 | 566760 | -58287.71 | 0 | 0 | 0 | 508472.29 | 0 | 508472.29 | 0 | [6 empty] | CM_M&G | 100%
501554 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-12-23 | 2015-12-23 | 2016-04-27 | 2019-11-29 | 2019-11-29 | Scottish Water Wide | 0 | 400509 | 338338 | 7093756.8 | 1278126.75 | 54578.73 | 4311.37 | 9169620.65 | 1.05 | 9169621.7 | 0 | [6 empty] | CM_WSI | 100%
501555 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-12-23 | 2015-12-23 | 2016-02-01 | 2019-05-10 | 2017-12-15 | Scottish Water Wide | 0 | 81 | 758928.19 | 173329.75 | 30761.06 | 25575.19 | 0 | 988675.19 | 0 | 988675.19 | 0 | [6 empty] | CM_WSI | 100%
502398 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MSU | 2021-04-26 | 2021-09-17 | 2021-09-20 | 2022-04-22 | 2022-04-22 | Scottish Water Wide | 0 | 0 | 99300 | 1834927.8765 | 336393.969 | 0 | 0 | 2270621.8455 | 0 | 2270621.8455 | 0 | [6 empty] | CM_M&G | 100%
501212 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-01-28 | 2016-03-04 | 2016-03-07 | 2016-03-01 | 2016-06-01 | Dumfries and Galloway | 0 | 2527 | -2092.11 | 0 | 0 | 0 | 0 | 434.89 | 0 | 434.89 | 466391.8995 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
501151 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2016-06-14 | 2018-04-30 | 2018-10-18 | 2019-08-28 | 2019-08-28 | Dumfries and Galloway | 0 | 0 | 35966 | 306274 | 928796 | 337822.04 | 193313.93 | 1802171.97 | 0.03 | 1802172 | 0 | [6 empty] | CM_WWNI | 100%
402933 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS6 | 2012-10-23 | 2013-12-23 | 2015-05-18 | 2018-04-01 | 2018-04-01 | Na H-Eileanan an Iar | 38035 | 3315 | 90811.13 | 204932.6 | -169.48 | 0 | 0 | 298889.25 | 0 | 336924.25 | 0 | [6 empty] | SG1 | 100%
403342 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-02-04 | 2013-08-20 | 2013-08-20 | 2015-10-15 | 2015-11-11 | South Lanarkshire | 1975828 | 36754 | 5977.45 | -26818.82 | 30.96 | 0 | 0 | 15943.59 | 0 | 1991771.59 | 0 | [6 empty] | CM_WWI | 100%
501163 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS5 | 2015-12-02 | 2017-06-05 | 2017-11-09 | 2019-02-27 | 2019-02-27 | Glasgow City | 0 | 1438 | 74837 | 515613 | 163895 | 0 | 2400 | 758183 | 0 | 758183 | 0 | [6 empty] | CM_WWNI | 100%
502240 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW0 | 2021-09-23 | 2022-07-22 | 2022-10-11 | 2023-05-19 | 2023-08-21 | Glasgow City | 0 | 0 | 9332.07 | 1681.32 | 0 | 3624.11 | 3609.38 | 18246.88 | 1753.12 | 20000 | 0 | [6 empty] | CM_WWI | 100%
404089 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-01-20 | 2015-03-27 | 2015-09-07 | 2016-06-16 |  | Highland | 12787.39 | 283932.61 | -35613.94 | 0 | 0 | 0 | 0 | 248318.67 | 0 | 261106.06 | 0 | [6 empty] | CM_WWNI | 100%
503079 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW0 | 2021-04-28 | 2022-02-25 | 2022-05-20 | 2022-12-15 | 2023-03-17 | Midlothian | 0 | 0 | 0 | 9700.062 | 7036.578 | 2927.82 | 2916.47 | 22580.93 | 228215.68 | 250796.61 | 0 | [6 empty] | CM_WWI | 100%
502367 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-05-03 | 2022-08-26 | 2022-12-29 | 2024-07-24 | 2024-10-24 | Argyll and Bute-North Argyll | 0 | 0 | 17507.18 | 13935.166 | 687.064 | 0 | 0 | 32129.41 | 348571.21 | 380700.62 | 0 | [6 empty] | CM_WSNI | 100%
503240 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2021-05-19 | 2022-04-08 | 2022-07-01 | 2023-04-03 | 2023-06-30 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 4790.28 | 19672.14 | 19595.89 | 44058.31 | 1460731.99 | 1504790.3 | 0 | [6 empty] | CM_WSNI | 100%
045315 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-10-03 | 2013-03-22 | 2013-09-06 | Argyll and Bute-North Argyll | 267842.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267842.49 | 0 | [6 empty] | DW13 | 100%
502598 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2017-06-30 | 2018-06-28 | 2018-07-16 | 2019-04-10 | 2019-04-11 | Falkirk | 0 | 0 | 1709.09 | 178429.55 | 1015727.85 | 13918.5 | 0 | 1209784.99 | 2623 | 1212407.99 | 0 | [6 empty] | CM_WSNI | 100%
502276 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS3 | 2017-04-04 | 2018-07-30 | 2018-08-06 | 2019-08-01 | 2019-08-01 | Stirling | 0 | 0 | 8222.26 | 17414.74 | 836163.79 | 31721.46 | 976.48 | 894498.73 | 1383.03 | 895881.76 | 618386.0588 | [6 empty] | WR6 | 100% | bar: Regulatory Outputs OMG-13
503250 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2018-06-28 | 2019-05-27 | 2019-08-06 | 2020-07-01 | 2020-10-01 | Stirling | 0 | 0 | 0 | 0 | 541245 | 852852.66 | 428990.3 | 1823087.96 | 9541.05 | 1832629.01 | 1459359.9687 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 344.7394
502605 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2018-06-28 | 2019-06-10 | 2019-08-16 | 2020-07-24 | 2020-10-26 | Stirling | 0 | 0 | 46297 | 189763.025 | 154348.975 | 524279.82 | 357533.6 | 1272222.42 | 58870.52 | 1331092.94 | 3342696.144 | [6 empty] | DW5MC | 100%
501089 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS5 | 2016-04-13 | 2018-09-06 | 2018-09-17 | 2019-02-11 | 2019-02-11 | Falkirk | 0 | 6048 | 5410.17 | 70355.83 | 335435.14 | 4612.34 | 573.82 | 422435.3 | 0 | 422435.3 | 0 | [6 empty] | CM_WSI | 100%
500013 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-02-19 | 2022-04-01 | 2022-06-03 |  | 2023-04-19 | Falkirk | 716 | 24477 | 2326 | 0 | 13742 | 0 | 0 | 40545 | 314105.99 | 355366.99 | 0 | [6 empty] | CM_WSI | 100%
501088 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-13 | 2022-03-28 | 2022-05-30 | 2023-01-31 | 2023-05-03 | Falkirk | 0 | 0 | 10138.89 | 3861.11 | 5778 | 0 | 0 | 19778 | 719146.35 | 738924.35 | 0 | [6 empty] | CM_WSI | 100%
501087 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | Falkirk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
500105 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS5 | 2015-04-13 | 2017-01-25 | 2017-01-25 | 2018-02-21 | 2018-02-21 | Falkirk | 0 | 40069 | 644286 | 351224 | 327051.01 | 0 | 0 | 1362630.01 | 0 | 1362630.01 | 0 | [6 empty] | CM_WSI | 100%
500061 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2015-05-08 | 2021-06-21 | 2021-08-13 | 2022-12-06 | 2022-12-06 | Falkirk | 0 | 45283 | 55525.4 | -5579.145 | -1545.925 | 0 | 0 | 93683.33 | 1469320.34 | 1563003.67 | 0 | [6 empty] | CM_WSNI | 100%
500478 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS3 | 2016-12-13 | 2018-03-30 | 2018-08-13 | 2020-02-01 | 2020-05-01 | Dumfries and Galloway | 0 | 11106.06 | 19425.05 | 18815.94 | 61230.85 | 82058.43 | 58266.39 | 250902.72 | 3842.85 | 254745.57 | 428689.9896 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
030136 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-09-15 | 2010-12-30 | 2011-02-14 | 2011-12-21 | 2012-03-02 | North Lanarkshire | 1317525.88 | 1380.88 | 0 | 0 | 0 | 0 | 0 | 1380.88 | 0 | 1318906.76 | 0 | [6 empty] | EC04A | 100%
500052 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS1 | 2016-07-07 | 2019-06-03 | 2019-07-02 | 2020-12-15 | 2020-12-16 | South Lanarkshire | 0 | 54006.59 | 101633.03 | 403261 | 378898.83 | 958704.44 | 3678982.68 | 5575486.57 | 24632.57 | 5600119.14 | 148885.7057 | [6 empty] | SG1 | 100%
400067 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-09-24 | 2012-01-24 | 2012-02-06 | 2013-03-01 | 2013-03-27 | South Lanarkshire | 1669686.31 | 89751.58 | -29024.87 | 0 | 0 | 0 | 0 | 60726.71 | 0 | 1730413.02 | 0 |  |  |  |  | 16632 |  | EC10A | 33.33% | EC04A | 33.33% | SG3 | 33.33%
502169 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2016-05-06 | 2017-02-03 | 2017-03-17 | 2017-06-30 | 2017-06-30 | Perth and Kinross | 0 | 0 | 79196 | 65961 | 8549.3609 | 0 | 0 | 153706.3609 | 0 | 153706.3609 | 0 | [6 empty] | CM_WWI | 100%
500119 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-01-19 | 2016-03-21 | 2017-07-25 | 2017-08-30 | Dumfries and Galloway | 0 | 24256 | 106458.72 | 7380.49 | -2383.68 | 0 | 0 | 135711.53 | 0 | 135711.53 | 52780.6923 | [6 empty] | CS16D | 50% | EC01D | 50%
503314 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS5 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-03-05 | 2019-03-05 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 29390.39 | 0 | 0 | 29390.39 | 0 | 29390.39 | 148885.7057 | [6 empty] | SG1 | 100%
404117 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-03-05 | 2015-03-05 | 2015-03-05 | 2015-07-10 | 2015-08-19 | Fife | 80000 | 5617.98 | 0 | 0 | 0 | 0 | 0 | 5617.98 | 0 | 85617.98 | 0 | [6 empty] | CM_M&G | 100%
501657 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2016-06-29 | 2017-05-25 | 2017-05-29 | 2018-03-14 | 2018-03-14 | Argyll and Bute-Cowal & Bute | 0 | 0 | 9173.02 | 139370.482 | -36968.982 | 0 | 0 | 111574.52 | 0 | 111574.52 | 0 | [6 empty] | CM_WWI | 100%
500991 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-10-21 | 2017-05-09 | 2017-06-30 | 2018-04-30 | 2018-04-30 | Highland | 0 | 10755 | 94268 | 153803 | 15554.63 | 0 | 0 | 274380.63 | 0 | 274380.63 | 0 | [6 empty] | CM_WWI | 100%
400058 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-11-11 | 2012-01-24 | 2012-04-23 | 2013-01-16 |  | West Dunbartonshire | 876403.11 | -52.2 | 0 | 0 | 0 | 0 | 0 | -52.2 | 0 | 876350.91 | 0 | [6 empty] | CM_WWNI | 100%
501529 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS5 | 2016-12-23 | 2018-03-09 | 2018-04-04 | 2019-01-01 | 2019-01-01 | Glasgow City | 0 | 0 | 3385.88 | 160839.22 | 774041.83 | 21811.29 | 13939.44 | 974017.66 | 54.24 | 974071.9 | 0 | [6 empty] | CM_WSNI | 100%
402775 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-07-16 | 2013-06-19 | 2013-10-16 | 2016-03-21 |  | Highland | 657779 | 87436 | -22476.02 | 0 | 0 | 0 | 0 | 64959.98 | 0 | 722738.98 | 0 | [6 empty] | CM_WWI | 100%
500031 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2015-02-27 | 2015-07-17 | 2015-07-27 | 2017-03-21 | 2017-07-14 | Scottish Water Wide | 153.33 | 126569.65 | 38277.02 | 8613.7 | -10136.01 | 0 | 0 | 163324.36 | 0 | 163477.69 | 302672.3337 | [6 empty] | DW25PS | 100%
502967 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 | Dumfries and Galloway | 0 | 0 | 0 | 12576.164 | 13056.58 | 0 | 0 | 25632.744 | 0 | 25632.744 | 0 | [6 empty] | CM_WWI | 100%
501588 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-09-08 | 2021-12-20 | 2022-02-07 | 2022-09-02 | 2022-12-05 | Falkirk | 0 | 0 | 3865.55 | 0 | 2000.09 | 0 | 0 | 5865.64 | 283349.32 | 289214.96 | 0 | [6 empty] | CM_WSI | 100%
501812 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-09-08 | 2021-12-20 | 2022-02-07 | 2022-09-02 | 2022-12-05 | Falkirk | 0 | 0 | 13522.28 | -8206.31 | 2000.31 | 0 | 0 | 7316.28 | 352336.65 | 359652.93 | 0 | [6 empty] | CM_WSI | 100%
030138 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS6 | 2008-06-09 | 2011-07-01 | 2011-07-25 | 2016-09-29 | 2016-03-29 | East Ayrshire | 1939092.84 | 2222069.07 | 828721 | -391.78 | -5747.2775 | 0 | 0 | 3044651.0125 | 0 | 4983743.8525 | 1055613.0935 | [6 empty] | CM_WWNI | 25% | EC04A | 75%
401912 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-03-22 | 2011-09-05 | 2011-09-05 | 2012-07-31 | 2015-06-22 | West Lothian | 112498 | 23216 | 17662.7 | -1450.13 | 0 | 0 | 0 | 39428.57 | 0 | 151926.57 | 0 | [6 empty] | DW10 | 100%
500303 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Aberdeen City | 0 | 254224.19 | 544716.15 | 692967.5425 | 1268171.263 | 0 | 0 | 2760079.1455 | 0 | 2760079.1455 | 854534.412 | [6 empty] | SG2 | 100%
500304 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Aberdeenshire | 0 | 2020013.3 | 1091246.23 | 310401.0645 | 1678995.1955 | 1373176.86 | 1335920.13 | 7809752.78 | 0 | 7809752.78 | 854534.412 | [6 empty] | SG2 | 100%
500305 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Angus | 0 | 21522.26 | 16661.26 | 479084.1605 | 162543.386 | 74050.05 | 72040.96 | 825902.0765 | 0 | 825902.0765 | 854534.412 | [6 empty] | SG2 | 100%
500306 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Argyll and Bute-North Argyll | 0 | 0 | 98082.67 | 76627.67 | 128.21 | 40392.48 | 39296.56 | 254527.59 | 0 | 254527.59 | 854534.412 | [6 empty] | SG2 | 100%
500307 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Scottish Borders | 0 | 9514.16 | 26792.35 | 30109.49 | 358603.494 | 0 | 0 | 425019.494 | 0 | 425019.494 | 854534.412 | [6 empty] | SG2 | 100%
500308 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Clackmannanshire | 0 | 54538.61 | 30267.08 | 222971.46 | 37093.9735 | 95714.43 | 93117.55 | 533703.1035 | 0 | 533703.1035 | 854534.412 | [6 empty] | SG2 | 100%
500309 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Dumfries and Galloway | 0 | 28905.21 | 150914.7 | 47019.63 | 17885.22 | 133867.53 | 130235.45 | 508827.74 | 0 | 508827.74 | 854534.412 | [6 empty] | SG2 | 100%
500310 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Dundee City | 0 | 66288.53 | 94544.33 | 58972.5385 | 302518.83 | 18955.14 | 18440.85 | 559720.2185 | 0 | 559720.2185 | 854534.412 | [6 empty] | SG2 | 100%
500311 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | East Ayrshire | 0 | 280489.15 | 321981.45 | 92805.2645 | 91502.54 | 447116.04 | 434984.98 | 1668879.4245 | 0 | 1668879.4245 | 854534.412 | [6 empty] | SG2 | 100%
500312 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | East Dunbartonshire | 0 | 56046.76 | 1040136.62 | 124499.0975 | 885950.63 | 818688.18 | 796475.71 | 3721796.9975 | 0 | 3721796.9975 | 854534.412 | [6 empty] | SG2 | 100%
500313 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | East Lothian | 0 | 481890.8 | 615184.71 | 384161.332 | 564471.02 | 790520.61 | 769072.36 | 3605300.832 | 0 | 3605300.832 | 854534.412 | [6 empty] | SG2 | 100%
500314 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | East Renfrewshire | 0 | 75241.12 | 218545.95 | 158046.773 | 2332741.98 | 2750.28 | 2675.66 | 2790001.763 | 0 | 2790001.763 | 854534.412 | [6 empty] | SG2 | 100%
500315 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | City of Edinburgh | 0 | 242058.68 | 859110.26 | 622915.1335 | 1412193.359 | 215494.86 | 209648.11 | 3561420.4025 | 0 | 3561420.4025 | 854534.412 | [6 empty] | SG2 | 100%
500316 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Falkirk | 0 | 685598.42 | 283684.21 | 183599.294 | 1658746.263 | 0 | 0 | 2811628.187 | 0 | 2811628.187 | 854534.412 | [6 empty] | SG2 | 100%
500317 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Fife | 0 | 150300.27 | 340500.72 | 358938.9085 | 800041.95 | 0 | 0 | 1649781.8485 | 0 | 1649781.8485 | 854534.412 | [6 empty] | SG2 | 100%
500318 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Glasgow City | 0 | 682112.31 | 892085.69 | 991262.391 | 904494.8825 | 998795.04 | 971695.95 | 5440446.2635 | 0 | 5440446.2635 | 854534.412 | [6 empty] | SG2 | 100%
500319 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Highland | 0 | 1030869.59 | 689020.41 | -29432.3935 | 543262.7036 | 1050427.5 | 1021927.52 | 4306075.3301 | 0 | 4306075.3301 | 854534.412 | [6 empty] | SG2 | 100%
500320 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Inverclyde | 0 | 257553.29 | 240311.07 | 16405.5465 | 74627.52 | 353731.14 | 344133.79 | 1286762.3565 | 0 | 1286762.3565 | 854534.412 | [6 empty] | SG2 | 100%
500321 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Midlothian | 0 | 384664.79 | 871358.43 | 588529.2825 | 569016.61 | 842716.2 | 819851.81 | 4076137.1225 | 0 | 4076137.1225 | 854534.412 | [6 empty] | SG2 | 100%
500322 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Moray | 0 | 807072.06 | 33976.31 | -14445.989 | 134255.0495 | 666846.87 | 648754.11 | 2276458.4105 | 0 | 2276458.4105 | 854534.412 | [6 empty] | SG2 | 100%
500323 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Na H-Eileanan an Iar | 0 | 0 | 185611.68 | 19525.2625 | 0 | 142014.03 | 138160.92 | 485311.8925 | 0 | 485311.8925 | 854534.412 | [6 empty] | SG2 | 100%
500324 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | North Ayrshire | 0 | 268608.65 | 43792.6 | 223003.5365 | 67380.08 | 174168.75 | 169443.26 | 946396.8765 | 0 | 946396.8765 | 854534.412 | [6 empty] | SG2 | 100%
500325 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | North Lanarkshire | 0 | 592093.94 | 582885.44 | 422669.2225 | 1138659.0335 | 104317.65 | 101487.31 | 2942112.596 | 0 | 2942112.596 | 854534.412 | [6 empty] | SG2 | 100%
500326 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Orkney Islands | 0 | 20133.36 | 199627.9 | 23049.1835 | 24305.76 | 166368.45 | 161854.59 | 595339.2435 | 0 | 595339.2435 | 854534.412 | [6 empty] | SG2 | 100%
500327 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Perth and Kinross | 0 | 72711.5 | 521075.4 | 177504.9965 | 101391.53 | 323853.36 | 315066.64 | 1511603.4265 | 0 | 1511603.4265 | 854534.412 | [6 empty] | SG2 | 100%
500328 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Renfrewshire | 0 | 131987.72 | 317456.35 | 73537.99 | 258213.93 | 270169.08 | 262838.91 | 1314203.98 | 0 | 1314203.98 | 854534.412 | [6 empty] | SG2 | 100%
500329 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Shetland Islands | 0 | 50395.99 | 59317.6 | 0 | 9283.71 | 84904.32 | 82600.71 | 286502.33 | 0 | 286502.33 | 854534.412 | [6 empty] | SG2 | 100%
500330 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | South Ayrshire | 0 | 53428.95 | 72710.97 | 28707.7065 | 245389.72 | 26957.22 | 26225.82 | 453420.3865 | 0 | 453420.3865 | 854534.412 | [6 empty] | SG2 | 100%
500331 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | South Lanarkshire | 0 | -103318.83 | 677623.79 | 538167.65 | 1036275.466 | 710.64 | 691.36 | 2150150.076 | 0 | 2150150.076 | 854534.412 | [6 empty] | SG2 | 100%
500332 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Stirling | 0 | 46253.97 | 285817.68 | 571397.5105 | -91748.37 | 171680.49 | 167022.48 | 1150423.7605 | 0 | 1150423.7605 | 854534.412 | [6 empty] | SG2 | 100%
500333 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | West Dunbartonshire | 0 | 123410.3 | 58898.69 | 182041.61 | 106368.8505 | 11751.42 | 11432.58 | 493903.4505 | 0 | 493903.4505 | 854534.412 | [6 empty] | SG2 | 100%
500334 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | West Lothian | 0 | 124195.87 | 1002145.24 | 782055.5595 | 853864.7205 | 0 | 0 | 2762261.39 | 0 | 2762261.39 | 854534.412 | [6 empty] | SG2 | 100%
500367 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2021-03-02 | 2021-03-02 | Aberdeen City | 0 | 375481.16 | 547820.36 | 195990.97 | 340791.9476 | 701336.25 | 682307.76 | 2843728.4476 | 0 | 2843728.4476 | 233661.7532 | [6 empty] | WG2 | 100%
500368 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Aberdeenshire | 0 | 760768.23 | 700523.79 | 458756.964 | 723835.1496 | 815387.76 | 793264.84 | 4252536.7336 | 0 | 4252536.7336 | 233661.7532 | [6 empty] | WG2 | 100%
500369 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Angus | 0 | 59694.27 | 158331 | 57680.3068 | 129778.42 | 143305.56 | 139417.42 | 688206.9768 | 0 | 688206.9768 | 233661.7532 | [6 empty] | WG2 | 100%
500370 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Argyll and Bute-North Argyll | 0 | 0 | 74804.16 | 232.19 | 59517.92 | 31844.01 | 30980.01 | 197378.29 | 0 | 197378.29 | 233661.7532 | [6 empty] | WG2 | 100%
500371 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Scottish Borders | 0 | 73618.17 | 178059.23 | 21456.88 | 148962.38 | 118264.86 | 115056.13 | 655417.65 | 0 | 655417.65 | 233661.7532 | [6 empty] | WG2 | 100%
500372 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Clackmannanshire | 0 | 10173.05 | 100112.37 | 70834.04 | 32170.29 | 70552.56 | 68638.35 | 352480.66 | 0 | 352480.66 | 233661.7532 | [6 empty] | WG2 | 100%
500373 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Dumfries and Galloway | 0 | 35570.14 | 105679.16 | 12935.6 | 65029.22 | 125315.01 | 121915 | 466444.13 | 0 | 466444.13 | 233661.7532 | [6 empty] | WG2 | 100%
500374 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Dundee City | 0 | 103943.99 | 277335.46 | -684.57 | 107572.73 | 260646.39 | 253574.58 | 1002388.58 | 0 | 1002388.58 | 233661.7532 | [6 empty] | WG2 | 100%
500375 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | East Ayrshire | 0 | 164251.4 | 191074.94 | 54880.3 | 114398.04 | 258229.11 | 251222.91 | 1034056.7 | 0 | 1034056.7 | 233661.7532 | [6 empty] | WG2 | 100%
500376 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2021-03-02 | 2021-03-02 | East Dunbartonshire | 0 | 74255.24 | 59107.84 | 170608.06 | 130369.06 | 312852.12 | 304363.89 | 1051556.21 | 0 | 1051556.21 | 233661.7532 | [6 empty] | WG2 | 100%
500377 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | East Lothian | 0 | 166882.23 | 914100.22 | 84550.17 | 353801.483 | 536366.76 | 521814.18 | 2577515.043 | 0 | 2577515.043 | 233661.7532 | [6 empty] | WG2 | 100%
500378 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | East Renfrewshire | 0 | 87873.85 | 190420.97 | -18786.08 | 97657.74 | 153207.39 | 149050.62 | 659424.49 | 0 | 659424.49 | 233661.7532 | [6 empty] | WG2 | 100%
500379 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | City of Edinburgh | 0 | 366936.26 | 949991.89 | 420888.69 | 793237.745 | 612289.26 | 595676.76 | 3739020.605 | 0 | 3739020.605 | 233661.7532 | [6 empty] | WG2 | 100%
500380 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Falkirk | 0 | 560808.56 | 131548.21 | 161399.41 | 1143452.34 | 7849.5 | 7636.52 | 2012694.54 | 0 | 2012694.54 | 233661.7532 | [6 empty] | WG2 | 100%
500381 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2021-03-02 | 2021-03-02 | Fife | 0 | 272632.63 | 512547.8 | 364422.4071 | 370969.47 | 477221.94 | 464274.06 | 2462068.3071 | 0 | 2462068.3071 | 233661.7532 | [6 empty] | WG2 | 100%
500382 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Glasgow City | 0 | 372677.09 | 613249.84 | 191630.1266 | 643297.6766 | 602114.73 | 585778.3 | 3008747.7632 | 0 | 3008747.7632 | 233661.7532 | [6 empty] | WG2 | 100%
500383 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Highland | 0 | 246372.47 | 312008.04 | 220747.7405 | 547777.2824 | 225044.94 | 218939.07 | 1770889.5429 | 0 | 1770889.5429 | 233661.7532 | [6 empty] | WG2 | 100%
500384 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Inverclyde | 0 | 17540.78 | 72535.9 | -8796.47 | 36096.22 | 64000.23 | 62263.77 | 243640.43 | 0 | 243640.43 | 233661.7532 | [6 empty] | WG2 | 100%
500385 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2021-03-02 | 2021-03-02 | Midlothian | 0 | 238339.11 | 510078.81 | 232535.0029 | 521933.89 | 347170.68 | 337751.32 | 2187808.8129 | 0 | 2187808.8129 | 233661.7532 | [6 empty] | WG2 | 100%
500386 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-03-31 | 2015-03-31 | 2021-03-02 | 2021-03-02 | Moray | 0 | 442268.06 | 166783.43 | 51252.9903 | 235777.0291 | 385602.54 | 375140.46 | 1656824.5094 | 0 | 1656824.5094 | 233661.7532 | [6 empty] | WG2 | 100%
500387 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Na H-Eileanan an Iar | 0 | 0 | 21859.87 | 3171.82 | 1132.69 | 19545.15 | 19014.84 | 64724.37 | 0 | 64724.37 | 233661.7532 | [6 empty] | WG2 | 100%
500388 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | North Ayrshire | 0 | 62489.6 | 117012.01 | 33780.9709 | 96012.94 | 99911.4 | 97200.63 | 506407.5509 | 0 | 506407.5509 | 233661.7532 | [6 empty] | WG2 | 100%
500389 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | North Lanarkshire | 0 | 150190.61 | 640013.63 | 313693.6342 | 805911.2112 | 250450.56 | 243655.4 | 2403915.0454 | 0 | 2403915.0454 | 233661.7532 | [6 empty] | WG2 | 100%
500390 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Orkney Islands | 0 | 11093.41 | 44233.26 | -2628.721 | 48179.5 | 18288.6 | 17792.39 | 136958.439 | 0 | 136958.439 | 233661.7532 | [6 empty] | WG2 | 100%
500391 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Perth and Kinross | 0 | 127705.48 | 287620.14 | 177599.3538 | 240068.85 | 140248.56 | 136443.38 | 1109685.7638 | 0 | 1109685.7638 | 233661.7532 | [6 empty] | WG2 | 100%
500392 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Renfrewshire | 0 | 137377.62 | 270137.4 | 202499.2963 | 749409.84 | 22727.34 | 22110.71 | 1404262.2063 | 0 | 1404262.2063 | 233661.7532 | [6 empty] | WG2 | 100%
500393 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Shetland Islands | 0 | 43760.67 | 43568.91 | -27414.0437 | 5070.97 | 48344.34 | 47032.67 | 160363.5163 | 0 | 160363.5163 | 233661.7532 | [6 empty] | WG2 | 100%
500394 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | South Ayrshire | 0 | 98713.77 | 163263.59 | -36603.53 | 114910.17 | 124740.18 | 121355.76 | 586379.94 | 0 | 586379.94 | 233661.7532 | [6 empty] | WG2 | 100%
500395 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | South Lanarkshire | 0 | 151888.6 | 537900.98 | 594934.3115 | 714887.5748 | 388880.49 | 378329.46 | 2766821.4163 | 0 | 2766821.4163 | 233661.7532 | [6 empty] | WG2 | 100%
500396 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Stirling | 0 | 101982.96 | 143246.93 | 151660.3757 | 143210.32 | 121120.56 | 117834.35 | 779055.4957 | 0 | 779055.4957 | 233661.7532 | [6 empty] | WG2 | 100%
500397 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | West Dunbartonshire | 0 | 105166.84 | 45809.65 | 43540.57 | 52103.31 | 120854.01 | 117575.01 | 485049.39 | 0 | 485049.39 | 233661.7532 | [6 empty] | WG2 | 100%
500398 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | West Lothian | 0 | 336950.81 | 526884.38 | 807970.2613 | 222566.64 | 742761.72 | 722609.27 | 3359743.0813 | 0 | 3359743.0813 | 0 | [6 empty] | WG2 | 100%
500335 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Aberdeen City | 0 | 0 | -102.67 | 102.67 | -23389.85 | 0 | 0 | -23389.85 | 0 | -23389.85 | 854534.412 | [6 empty] | SG2 | 100%
500336 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Aberdeenshire | 0 | 0 | 24558.86 | -12183.44 | -12323.23 | 7752.66 | 7542.31 | 15347.16 | 0 | 15347.16 | 854534.412 | [6 empty] | SG2 | 100%
500337 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Angus | 0 | 0 | 8362.42 | -4094.23 | -4181.21 | 2219.1 | 2158.89 | 4464.97 | 0 | 4464.97 | 854534.412 | [6 empty] | SG2 | 100%
500338 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
500339 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Scottish Borders | 0 | 0 | -10.82 | 10.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
500403 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Scottish Borders | 0 | 0 | 15.95 | 82.29 | 316.36 | 0 | 0 | 414.6 | 0 | 414.6 | 233661.7532 | [6 empty] | WG2 | 100%
500340 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
500341 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Dumfries and Galloway | 0 | 0 | 9546.06 | -4778.54 | -4767.52 | 2451.75 | 2385.22 | 4836.97 | 0 | 4836.97 | 854534.412 | [6 empty] | SG2 | 100%
500342 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Dundee City | 0 | 0 | 0 | 36.32 | 0 | 0 | 0 | 36.32 | 0 | 36.32 | 854534.412 | [6 empty] | SG2 | 100%
500343 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
500347 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | City of Edinburgh | 0 | 0 | -77.31 | 321.54 | 0 | 0 | 0 | 244.23 | 0 | 244.23 | 854534.412 | [6 empty] | SG2 | 100%
500348 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Falkirk | 0 | 0 | 50.1 | -50.1 | 0 | 967.62 | 941.37 | 1908.99 | 0 | 1908.99 | 854534.412 | [6 empty] | SG2 | 100%
500349 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
500350 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Glasgow City | 0 | 0 | 3575.22 | -1721.61 | -1787.61 | 967.62 | 941.37 | 1974.99 | 0 | 1974.99 | 854534.412 | [6 empty] | SG2 | 100%
500351 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
500352 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
500353 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Midlothian | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 75 | 0 | 75 | 854534.412 | [6 empty] | SG2 | 100%
500354 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Moray | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 180 | 0 | 180 | 854534.412 | [6 empty] | SG2 | 100%
500355 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Na H-Eileanan an Iar | 0 | 0 | -39 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
500356 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | North Ayrshire | 0 | 0 | -111.94 | 439.69 | 0 | 0 | 0 | 327.75 | 0 | 327.75 | 854534.412 | [6 empty] | SG2 | 100%
500357 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
500358 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 |  | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
500359 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
500360 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
500361 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
500362 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
500363 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | South Lanarkshire | 0 | 0 | 0 | 0 | 6053.6 | 2595.24 | 2524.82 | 11173.66 | 0 | 11173.66 | 854534.412 | [6 empty] | SG2 | 100%
500364 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Stirling | 0 | 0 | -25.33 | 170.12 | 0 | 0 | 0 | 144.79 | 0 | 144.79 | 854534.412 | [6 empty] | SG2 | 100%
500365 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
500366 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
500399 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Aberdeen City | 0 | 0 | 22026.88 | 2729.99 | -19118.95 | 9751.8 | 9487.22 | 24876.94 | 0 | 24876.94 | 233661.7532 | [6 empty] | WG2 | 100%
500400 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Aberdeenshire | 0 | 0 | -2166.62 | 25940.47 | -9661.61 | 4945.08 | 4810.91 | 23868.23 | 0 | 23868.23 | 233661.7532 | [6 empty] | WG2 | 100%
500401 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Angus | 0 | 0 | 0 | 0 | 1854.03 | 0 | 0 | 1854.03 | 0 | 1854.03 | 233661.7532 | [6 empty] | WG2 | 100%
500402 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Argyll and Bute-North Argyll | 0 | 0 | -142.68 | 1934.9 | -862.53 | 908.28 | 883.64 | 2721.61 | 0 | 2721.61 | 233661.7532 | [6 empty] | WG2 | 100%
500404 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2021-03-02 | 2021-03-02 | Clackmannanshire | 0 | 0 | 0 | 68.05 | 0 | 35.49 | 34.54 | 138.08 | 0 | 138.08 | 233661.7532 | [6 empty] | WG2 | 100%
500405 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Dumfries and Galloway | 0 | 0 | 4.2 | 942.78 | 1412.56 | 1223.07 | 1189.87 | 4772.48 | 0 | 4772.48 | 233661.7532 | [6 empty] | WG2 | 100%
500406 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Dundee City | 0 | 0 | -115.55 | 2906.02 | -1977.02 | 1414.2 | 1375.83 | 3603.48 | 0 | 3603.48 | 233661.7532 | [6 empty] | WG2 | 100%
500407 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | East Ayrshire | 0 | 0 | 0 | 740.59 | 499.7675 | 1809.57 | 1760.45 | 4810.3775 | 0 | 4810.3775 | 233661.7532 | [6 empty] | WG2 | 100%
500408 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | East Dunbartonshire | 0 | 0 | -85.65 | 159.32 | 0 | 0 | 0 | 73.67 | 0 | 73.67 | 233661.7532 | [6 empty] | WG2 | 100%
500409 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | East Lothian | 0 | 0 | -142.59 | 627.25 | 58 | 0 | 0 | 542.66 | 0 | 542.66 | 233661.7532 | [6 empty] | WG2 | 100%
500410 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | East Renfrewshire | 0 | 0 | 62.66 | -62.66 | 386.8 | 0 | 0 | 386.8 | 0 | 386.8 | 233661.7532 | [6 empty] | WG2 | 100%
500411 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | City of Edinburgh | 0 | 0 | -451.54 | 1053.09 | 1846.32 | 2200.86 | 2141.15 | 6789.88 | 0 | 6789.88 | 233661.7532 | [6 empty] | WG2 | 100%
500412 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Falkirk | 0 | 0 | 125.32 | -125.32 | 74.27 | 0 | 0 | 74.27 | 0 | 74.27 | 233661.7532 | [6 empty] | WG2 | 100%
500413 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Fife | 0 | 0 | -225.54 | 1415.71 | 427.9 | 895.62 | 871.33 | 3385.02 | 0 | 3385.02 | 233661.7532 | [6 empty] | WG2 | 100%
500414 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Glasgow City | 0 | 0 | -295.63 | 5478.32 | 2132.805 | 5898 | 5737.98 | 18951.475 | 0 | 18951.475 | 233661.7532 | [6 empty] | WG2 | 100%
500415 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Highland | 0 | 490 | -198.54 | 591.19 | 1412.89 | 1691.97 | 1646.08 | 5633.59 | 0 | 5633.59 | 233661.7532 | [6 empty] | WG2 | 100%
500416 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Inverclyde | 0 | 317.76 | -49.63 | 113.07 | 456.67 | 690.36 | 671.63 | 2199.86 | 0 | 2199.86 | 233661.7532 | [6 empty] | WG2 | 100%
500417 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Midlothian | 0 | 0 | -197.14 | 197.14 | 350.22 | 0 | 0 | 350.22 | 0 | 350.22 | 233661.7532 | [6 empty] | WG2 | 100%
500418 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Moray | 0 | 0 | 109.55 | 3993.17 | -2661.49 | 2079.72 | 2023.3 | 5544.25 | 0 | 5544.25 | 233661.7532 | [6 empty] | WG2 | 100%
500419 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Na H-Eileanan an Iar | 0 | 0 | -105.46 | 445.08 | 265.51 | 1035.01 | 0 | 1640.14 | 0 | 1640.14 | 233661.7532 | [6 empty] | WG2 | 100%
500420 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | North Ayrshire | 0 | 0 | -103.35 | 729.13 | 114.4 | 684.3 | 665.73 | 2090.21 | 0 | 2090.21 | 233661.7532 | [6 empty] | WG2 | 100%
500421 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | North Lanarkshire | 0 | 0 | 62.66 | 67.29 | 1123.14 | 922.5 | 897.48 | 3073.07 | 0 | 3073.07 | 233661.7532 | [6 empty] | WG2 | 100%
500422 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Orkney Islands | 0 | 0 | 0 | 0 | 45.7 | 0 | 0 | 45.7 | 0 | 45.7 | 233661.7532 | [6 empty] | WG2 | 100%
500423 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Perth and Kinross | 0 | 0 | -314.7 | 3295.43 | -2681.98 | 1510.98 | 1469.99 | 3279.72 | 0 | 3279.72 | 233661.7532 | [6 empty] | WG2 | 100%
500424 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Renfrewshire | 0 | 0 | 0 | 0 | 1877.47 | 973.2 | 946.8 | 3797.47 | 0 | 3797.47 | 233661.7532 | [6 empty] | WG2 | 100%
500425 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Shetland Islands | 0 | 0 | 0 | 0 | 77.55 | 0 | 0 | 77.55 | 0 | 77.55 | 233661.7532 | [6 empty] | WG2 | 100%
500426 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | South Ayrshire | 0 | 0 | 0 | 173.06 | 477.66 | 337.59 | 328.44 | 1316.75 | 0 | 1316.75 | 233661.7532 | [6 empty] | WG2 | 100%
500427 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | South Lanarkshire | 0 | 0 | -359.7 | 439.51 | 1006.1 | 563.13 | 547.87 | 2196.91 | 0 | 2196.91 | 233661.7532 | [6 empty] | WG2 | 100%
500428 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | Stirling | 0 | 0 | -212.17 | 997.72 | 180.16 | 775.02 | 753.99 | 2494.72 | 0 | 2494.72 | 233661.7532 | [6 empty] | WG2 | 100%
500429 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | West Dunbartonshire | 0 | 0 | 0 | 758.29 | 250.59 | 600.12 | 583.84 | 2192.84 | 0 | 2192.84 | 233661.7532 | [6 empty] | WG2 | 100%
500430 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2021-03-02 | 2021-03-02 | West Lothian | 0 | 0 | 12.7 | 395.43 | 155.66 | 0 | 0 | 563.79 | 0 | 563.79 | 233661.7532 | [6 empty] | WG2 | 100%
400226 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-25 | 2019-04-25 | Aberdeen City | 0 | 0 | 0 | 41001.33 | 40875.6 | 0 | 0 | 81876.93 | 0 | 81876.93 | 0 | [6 empty] | SG2 | 100%
400229 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | Argyll and Bute-North Argyll | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 120 | 0 | [6 empty] | SG2 | 100%
400233 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | Dundee City | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 120 | 0 | [6 empty] | SG2 | 100%
400234 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | East Ayrshire | 0 | 0 | 0 | 120 | -120 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
400238 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | City of Edinburgh | 0 | 0 | -73.96 | 73.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
400240 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | Fife | 0 | 0 | 0.74 | 0 | 0 | 0 | 0 | 0.74 | 0 | 0.74 | 0 | [6 empty] | SG2 | 100%
400241 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
400248 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG2 | 100%
400162 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | Aberdeen City | 15805.15 | -15805.15 | 51.93 | -13400.17 | 0 | 0 | 0 | -29153.39 | 0 | -13348.24 | 0 | [6 empty] | WG2 | 100%
400163 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-26 | 2019-04-26 | Aberdeenshire | 55.15 | -55.15 | -12323.23 | 15079.31 | -5512.16 | 0 | 0 | -2811.23 | 0 | -2756.08 | 0 | [6 empty] | WG2 | 100%
400164 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | Angus | 0 | 0 | -4181.21 | 4181.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400168 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | Dumfries and Galloway | 1008.78 | -1008.78 | -4713.89 | 4713.89 | 0 | 0 | 0 | -1008.78 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400169 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | Dundee City | 0 | 0 | -51.09 | 4044.39 | -7986.6 | 0 | 0 | -3993.3 | 0 | -3993.3 | 0 | [6 empty] | WG2 | 100%
400170 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400172 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | East Lothian | 0 | 0 | 51.93 | -51.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400173 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400174 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | City of Edinburgh | 0 | 0 | 53.62 | -53.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400177 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | Glasgow City | 0 | 0 | -1787.61 | 1787.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400178 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | Highland | 0 | 0 | 104.26 | 195.04 | 0 | 0 | 0 | 299.3 | 0 | 299.3 | 0 | [6 empty] | WG2 | 100%
400182 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | Na H-Eileanan an Iar | 61.34 | 0 | 62.66 | -124 | 0 | 0 | 0 | -61.34 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400184 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | North Lanarkshire | 0 | 0 | -11.65 | 11.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400186 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | Perth and Kinross | 0 | 0 | 62.66 | -62.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400190 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | South Lanarkshire | 0 | 0 | 62.96 | -62.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400192 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400193 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
400194 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Aberdeen City | 645202.78 | -120 | -198754.89 | 49424.59 | 149450.3 | 0 | 0 | -2.9104e-11 | 0 | 645202.78 | 0 | [6 empty] | SG2 | 100%
400195 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Aberdeenshire | 4439801.95 | -135 | -308500.05 | 270842.55 | 37417.5 | 0 | 0 | -375 | 0 | 4439426.95 | 0 | [6 empty] | SG2 | 100%
400196 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Angus | 811134.81 | -121.16 | -4219.1 | -142979.72 | 147319.98 | 0 | 0 | 0 | 0 | 811134.81 | 0 | [6 empty] | SG2 | 100%
400197 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Argyll and Bute-North Argyll | 385341.75 | 0 | 75.96 | 0 | -128.21 | 0 | 0 | -52.25 | 0 | 385289.5 | 0 | [6 empty] | SG2 | 100%
400198 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Scottish Borders | 904594.34 | -240 | 0 | 195 | -213.56 | 0 | 0 | -258.56 | 0 | 904335.78 | 0 | [6 empty] | SG2 | 100%
400199 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Clackmannanshire | 123262.65 | -47.95 | 0 | -75821.97 | 75869.92 | 0 | 0 | 0 | 0 | 123262.65 | 0 | [6 empty] | SG2 | 100%
400200 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Dumfries and Galloway | 1160392.46 | -120 | 0 | 0 | -18.02 | 0 | 0 | -138.02 | 0 | 1160254.44 | 0 | [6 empty] | SG2 | 100%
400201 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Dundee City | 537363.9 | 0 | 23174.69 | -23174.69 | 0 | 0 | 0 | 0 | 0 | 537363.9 | 0 | [6 empty] | SG2 | 100%
400202 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-26 | 2019-04-26 | East Ayrshire | 1320355.31 | 0 | -22374.34 | 22618.17 | -363.83 | 0 | 0 | -120 | 0 | 1320235.31 | 0 | [6 empty] | SG2 | 100%
400203 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | East Dunbartonshire | 294546.85 | 0 | -58430.09 | 58430.09 | 0 | 0 | 0 | 0 | 0 | 294546.85 | 0 | [6 empty] | SG2 | 100%
400204 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-25 | 2019-04-25 | East Lothian | 524744.49 | 0 | -55300.94 | 29371.14 | 25929.8 | 0 | 0 | -3.638e-12 | 0 | 524744.49 | 0 | [6 empty] | SG2 | 100%
400205 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | East Renfrewshire | 556219.32 | 0 | -11874.36 | 12242.36 | -368 | 0 | 0 | 0 | 0 | 556219.32 | 0 | [6 empty] | SG2 | 100%
400206 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | City of Edinburgh | 1833388.1 | 0 | -301097.78 | 350903.21 | -50128.47 | 0 | 0 | -323.04 | 0 | 1833065.06 | 0 | [6 empty] | SG2 | 100%
400207 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-25 | 2019-04-25 | Falkirk | 1665249.56 | 0 | -103404.58 | 103404.58 | 0 | 0 | 0 | 0 | 0 | 1665249.56 | 0 | [6 empty] | SG2 | 100%
400208 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Fife | 2628158.85 | 0 | -36249.94 | 36384.94 | -255 | 0 | 0 | -120 | 0 | 2628038.85 | 0 | [6 empty] | SG2 | 100%
400209 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Glasgow City | 1708218.33 | -900 | -39275.1 | -138558.92 | 178469.57 | 0 | 0 | -264.45 | 0 | 1707953.88 | 0 | [6 empty] | SG2 | 100%
400210 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Highland | 2526715.38 | 0 | -149013.25 | 121138.75 | 27874.5 | 0 | 0 | 0 | 0 | 2526715.38 | 0 | [6 empty] | SG2 | 100%
400211 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | Inverclyde | 480370.59 | 0 | -16910.01 | 16910.01 | 0 | 0 | 0 | 0 | 0 | 480370.59 | 0 | [6 empty] | SG2 | 100%
400212 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Midlothian | 1866126.33 | 0 | -84908.97 | 103443.405 | -18534.435 | 0 | 0 | -3.638e-12 | 0 | 1866126.33 | 0 | [6 empty] | SG2 | 100%
400213 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Moray | 820705.08 | -8 | 120 | 0 | -112 | 0 | 0 | 0 | 0 | 820705.08 | 0 | [6 empty] | SG2 | 100%
400215 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | East Ayrshire | 1188743.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1188743.7 | 0 | [6 empty] | SG2 | 100%
400216 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | North Lanarkshire | 4389311.79 | -453.34 | -116379.9 | 88297.386 | 28535.85 | 0 | 0 | -0.004 | 0 | 4389311.786 | 0 | [6 empty] | SG2 | 100%
400217 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-17 | 2019-04-17 | Orkney Islands | 191435.15 | 0 | -3274.15 | 3274.15 | 0 | 0 | 0 | 0 | 0 | 191435.15 | 0 | [6 empty] | SG2 | 100%
400218 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Perth and Kinross | 1119987.02 | -120 | -49460.52 | 46312.91 | 3267.61 | 0 | 0 | 6.8212e-12 | 0 | 1119987.02 | 0 | [6 empty] | SG2 | 100%
400219 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Renfrewshire | 916586.78 | 0 | -68843.18 | 69201.88 | -367.54 | 0 | 0 | -8.84 | 0 | 916577.94 | 0 | [6 empty] | SG2 | 100%
400220 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Shetland Islands | 105388.02 | 48593.2 | -48593.2 | 0 | 0 | 0 | 0 | 0 | 0 | 105388.02 | 0 | [6 empty] | SG2 | 100%
400221 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | South Ayrshire | 522741.26 | 60 | 3719.43 | -3599.43 | -188 | 0 | 0 | -8 | 0 | 522733.26 | 0 | [6 empty] | SG2 | 100%
400222 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | South Lanarkshire | 5203100.88 | -48593.2 | -190209.94 | 109802.15 | 128930.27 | 0 | 0 | -70.72 | 0 | 5203030.16 | 0 | [6 empty] | SG2 | 100%
400223 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Stirling | 876227.43 | 0 | 0 | -81607.23 | 81607.23 | 0 | 0 | 0 | 0 | 876227.43 | 0 | [6 empty] | SG2 | 100%
400224 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | West Dunbartonshire | 629488.04 | 970.48 | -15973.4 | 9647.77 | 5355.15 | 0 | 0 | 0 | 0 | 629488.04 | 0 | [6 empty] | SG2 | 100%
400225 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | West Lothian | 1781393.84 | 0 | -241683.55 | 378765.97 | -137322.42 | 0 | 0 | -240 | 0 | 1781153.84 | 0 | [6 empty] | SG2 | 100%
400130 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Aberdeen City | 602219.62 | 109098 | -177069.04 | 58754.47 | 9348.96 | 0 | 0 | 132.39 | 0 | 602352.01 | 0 | [6 empty] | WG2 | 100%
400131 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Aberdeenshire | 2579408.49 | 141116.83 | -254073.28 | 109137.58 | 3091.82 | 0 | 0 | -727.05 | 0 | 2578681.44 | 0 | [6 empty] | WG2 | 100%
400132 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Angus | 420625.65 | 39054 | -65339.95 | 31652.7 | -3581.08 | 0 | 0 | 1785.67 | 0 | 422411.32 | 0 | [6 empty] | WG2 | 100%
400134 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Scottish Borders | 468068.58 | 32618.54 | -84900.07 | 53337.35 | -1439.89 | 0 | 0 | -384.07 | 0 | 467684.51 | 0 | [6 empty] | WG2 | 100%
400135 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Clackmannanshire | 137638.4 | 9863 | -19797.51 | -4878.09 | 14812.6 | 0 | 0 | 1.819e-12 | 0 | 137638.4 | 0 | [6 empty] | WG2 | 100%
400136 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Dumfries and Galloway | 386310.47 | 37398.03 | -64344.43 | 25836.49 | 698.6 | 0 | 0 | -411.31 | 0 | 385899.16 | 0 | [6 empty] | WG2 | 100%
400133 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Argyll and Bute-North Argyll | 101248.09 | 9357.56 | -14729.49 | 5919.83 | -547.9 | 0 | 0 | -3.4106e-13 | 0 | 101248.09 | 0 | [6 empty] | WG2 | 100%
400137 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Dundee City | 138755.3 | 17014 | -79227.05 | 65140.08 | -2927.03 | 0 | 0 | -1.3642e-12 | 0 | 138755.3 | 0 | [6 empty] | WG2 | 100%
400138 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | East Ayrshire | 386826.37 | 31578 | -88779.22 | 57201.22 | 0 | 0 | 0 | 0 | 0 | 386826.37 | 0 | [6 empty] | WG2 | 100%
400139 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-03 | 2019-04-03 | East Dunbartonshire | 795837.97 | 58903.97 | -26300.03 | -51945.57 | 17552.57 | 0 | 0 | -1789.06 | 0 | 794048.91 | 0 | [6 empty] | WG2 | 100%
400141 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | East Renfrewshire | 270590.47 | 25292 | -97209.86 | 61894.97 | 9959.71 | 0 | 0 | -63.18 | 0 | 270527.29 | 0 | [6 empty] | WG2 | 100%
400142 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | City of Edinburgh | 1157931.44 | 128814 | -333612.93 | 181144.03 | 25698.17 | 0 | 0 | 2043.27 | 0 | 1159974.71 | 0 | [6 empty] | WG2 | 100%
400143 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Falkirk | 941192.69 | 57398 | -2447.5 | -58773.24 | 3614.76 | 0 | 0 | -207.98 | 0 | 940984.71 | 0 | [6 empty] | WG2 | 100%
400140 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | East Lothian | 398452.4 | 44080 | -338418.85 | 294833.4668 | -1450.88 | 0 | 0 | -956.2632 | 0 | 397496.1368 | 0 | [6 empty] | WG2 | 100%
400144 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Fife | 1005678.27 | 81652.08 | -125041.41 | 44964.39 | -3609.67 | 0 | 0 | -2034.61 | 0 | 1003643.66 | 0 | [6 empty] | WG2 | 100%
400145 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Glasgow City | 1554091.97 | 127372 | -244326.86 | 116677.62 | 145.5 | 0 | 0 | -131.74 | 0 | 1553960.23 | 0 | [6 empty] | WG2 | 100%
400147 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Inverclyde | 170845.8 | 10052 | -44621.8 | 34569.802 | 0 | 0 | 0 | 0.002 | 0 | 170845.802 | 0 | [6 empty] | WG2 | 100%
400148 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-15 | 2019-04-15 | Midlothian | 6064127.31 | 85130 | -161879.55 | 95364.1383 | -19119.9 | 0 | 0 | -505.3117 | 0 | 6063621.9983 | 0 | [6 empty] | WG2 | 100%
400146 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Highland | 1641396.02 | 91700.49 | -109838.86 | -3486.95 | 20930.56 | 0 | 0 | -694.76 | 0 | 1640701.26 | 0 | [6 empty] | WG2 | 100%
400150 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-03 | 2019-04-03 | Na H-Eileanan an Iar | 48969.15 | 1577.57 | -1440 | -104 | -33.57 | 0 | 0 | -6.3949e-14 | 0 | 48969.15 | 0 | [6 empty] | WG2 | 100%
400149 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Moray | 808713.57 | 32897.99 | -61268.74 | 36311.03 | -7288.66 | 0 | 0 | 651.62 | 0 | 809365.19 | 0 | [6 empty] | WG2 | 100%
400151 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | North Ayrshire | 509894.72 | 25990 | -43203.66 | 16590.28 | 524.4 | 0 | 0 | -98.98 | 0 | 509795.74 | 0 | [6 empty] | WG2 | 100%
400152 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | North Lanarkshire | 1108414.75 | 97132 | -168925.96 | 71422.1937 | 114.98 | 0 | 0 | -256.7863 | 0 | 1108157.9637 | 0 | [6 empty] | WG2 | 100%
400153 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-26 | 2019-04-26 | Orkney Islands | 88474.77 | 11156.85 | -16465.21 | 5961.51 | -741.6 | 0 | 0 | -88.45 | 0 | 88386.32 | 0 | [6 empty] | WG2 | 100%
400154 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Perth and Kinross | 354294.87 | 29642.4 | -97366.67 | 67742.51 | -509.86 | 0 | 0 | -491.62 | 0 | 353803.25 | 0 | [6 empty] | WG2 | 100%
400155 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Renfrewshire | 462500.09 | 59129.46 | -83199.14 | 22319.73 | 1688.33 | 0 | 0 | -61.62 | 0 | 462438.47 | 0 | [6 empty] | WG2 | 100%
400156 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-03 | 2019-04-03 | Shetland Islands | 83911.64 | 6369.59 | -25988.92 | 19933.4 | -314.07 | 0 | 0 | 3.3538e-12 | 0 | 83911.64 | 0 | [6 empty] | WG2 | 100%
400157 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | South Ayrshire | 208279.15 | 18900 | -71314.56 | 53122.83 | -1319.15 | 0 | 0 | -610.88 | 0 | 207668.27 | 0 | [6 empty] | WG2 | 100%
400158 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | South Lanarkshire | 1139178.19 | 57800.51 | -106378.26 | 3159.79 | 45328.47 | 0 | 0 | -89.49 | 0 | 1139088.7 | 0 | [6 empty] | WG2 | 100%
400159 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | Clackmannanshire | 216448.68 | 20149.14 | -51784.25 | 22568.32 | 8876.15 | 0 | 0 | -190.64 | 0 | 216258.04 | 0 | [6 empty] | WG2 | 100%
400160 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | West Dunbartonshire | 290437.66 | 22886 | -17529.43 | -38839.6 | 33483.03 | 0 | 0 | 0 | 0 | 290437.66 | 0 | [6 empty] | WG2 | 100%
400161 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2019-04-24 | 2019-04-24 | West Lothian | 951240.54 | 93318 | -165404.13 | 80364.6914 | -8157.91 | 0 | 0 | 120.6514 | 0 | 951361.1914 | 0 | [6 empty] | WG2 | 100%
502191 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-09-20 | 2018-01-17 | 2018-02-26 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 3427.06 | 191062.89 | 416163.05 | 0 | 0 | 610653 | 0 | 610653 | 0 | [6 empty] | CM_WWI | 100%
502404 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2017-04-28 | 2018-06-21 | 2018-08-31 | 2019-09-02 | 2019-11-29 | South Lanarkshire | 0 | 0 | 1807.55 | 12425.55 | 732232.9 | 7592.06 | 2665.95 | 756724.01 | 0 | 756724.01 | 0 | [6 empty] | CM_WWI | 100%
502405 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2017-04-28 | 2018-03-27 | 2018-05-31 | 2019-04-01 | 2019-04-01 | Aberdeenshire | 0 | 0 | 1674.42 | 88929.58 | 565647 | 5000.11 | 1433.89 | 662685 | 0 | 662685 | 0 | [6 empty] | CM_WWI | 100%
502641 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS2 | 2018-01-30 | 2018-12-05 | 2019-05-13 | 2019-12-12 | 2019-12-12 | West Lothian | 0 | 0 | 6630.7 | 10429.17 | 139380.13 | 326374.05 | 26597.88 | 509411.93 | 0.08 | 509412.01 | 0 | [6 empty] | CM_WWI | 100%
502642 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2018-01-30 | 2018-10-26 | 2019-01-31 | 2019-11-29 | 2019-11-29 | Highland | 0 | 0 | 4420.47 | 11454.23 | 159542.3 | 289585.99 | 2218.36 | 467221.35 | 181.65 | 467403 | 0 | [6 empty] | CM_WWI | 100%
502643 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS2 | 2018-03-29 | 2019-03-05 | 2019-05-08 | 2020-04-02 | 2020-04-03 | Highland | 0 | 0 | 4420.47 | 6005.0775 | 63639.2025 | 289207.95 | 735.16 | 364007.86 | 1664.92 | 365672.78 | 0 | [6 empty] | CM_WWI | 100%
503046 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS0 | 2018-10-26 | 2020-12-14 | 2021-07-16 | 2021-09-29 | 2022-01-13 | Stirling | 0 | 0 | 0 | 5261.772 | 4207.198 | 30210.53 | 103280.2 | 142959.7 | 117792.33 | 260752.03 | 0 | [6 empty] | CM_WWI | 100%
503201 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS0 | 2018-07-27 | 2019-07-15 | 2019-09-30 | 2020-05-01 | 2020-08-03 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 48847.9 | 152982.44 | 70968.07 | 272798.41 | 1881.76 | 274680.17 | 0 | [6 empty] | CM_WWI | 100%
503411 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2021-05-27 | 2022-04-15 | 2022-07-21 | 2023-03-15 | 2023-06-15 | Fife | 0 | 0 | 0 | 0 | 15023.15 | 7049.37 | 7022.06 | 29094.58 | 572092.97 | 601187.55 | 0 | [6 empty] | CM_WWI | 100%
403614 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-12-19 | 2014-04-30 | 2014-06-09 | 2016-03-30 | 2018-02-08 | Scottish Water Wide | 682168 | 359296.72 | 25137.03 | 0 | 0 | 0 | 0 | 384433.75 | 0 | 1066601.75 | 0 | [6 empty] | CM_WWI | 100%
402858 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-08-15 | 2013-09-18 | 2013-12-19 | 2014-06-13 | 2014-06-13 | Fife | 2279102 | -7665 | -882.94 | 0 | 0 | 0 | 0 | -8547.94 | 0 | 2270554.06 | 538.2 | [6 empty] | CM_WWI | 40% | CS11A | 60%
403344 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-25 | 2014-09-10 | 2014-10-06 | 2015-07-17 |  | Scottish Borders | 65921 | 2170.65 | 0 | 0 | 0 | 0 | 0 | 2170.65 | 0 | 68091.65 | 0 | [6 empty] | CM_WSI | 100%
502585 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | Fife | 0 | 0 | 2930.23 | 1575.13 | 0 | 0 | 0 | 4505.36 | 0 | 4505.36 | 0 | [6 empty] | CM_WWI | 100%
502394 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS3 | 2017-02-21 | 2017-02-21 | 2017-03-01 | 2019-07-29 | 2019-07-29 | Aberdeenshire | 0 | 0 | 911064 | 0 | -425507.295 | 0 | 0 | 485556.705 | 0 | 485556.705 | 0 | [6 empty] | SG5 | 100%
402076 | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2011-06-16 | 2011-06-16 | 2011-07-05 | 2015-03-31 |  | Scottish Water Wide | 11231.71 | -457.76 | 0 | 0 | 0 | 0 | 0 | -457.76 | 0 | 10773.95 | 0 | [6 empty] | CS20 | 100%
401562 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-11-02 | 2011-12-15 | 2012-03-12 | 2014-03-17 | 2013-09-30 | Fife | 74079.7 | 238.67 | 217.89 | 0 | 0 | 0 | 0 | 456.56 | 0 | 74536.26 | 94 | [6 empty] | CS1 | 100%
502084 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2022-06-14 | 2022-10-26 | 2023-01-09 | 2023-08-09 | 2023-11-09 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 490986.96 | 490986.96 | 0 | [6 empty] | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 33.33% | CM_WSI | 42.86%
502847 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2018-08-24 | 2021-04-26 | 2021-08-26 | 2022-06-07 | 2022-09-06 | Aberdeenshire | 0 | 0 | 0 | 0 | 6451.26 | 4645.89 | 4627.87 | 15725.02 | 270402.52 | 286127.54 | 0 | [6 empty] | CM_WSNI | 100%
502848 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2018-11-21 | 2020-07-20 | 2020-11-30 | 2021-08-27 | 2021-11-29 | East Lothian | 0 | 0 | 0 | 0 | 5548 | 12635.97 | 323764.3 | 341948.27 | 296061.7 | 638009.97 | 0 | [6 empty] | CM_WSNI | 100%
502849 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2018-11-13 | 2020-06-22 | 2020-10-26 | 2021-05-07 | 2021-05-07 | South Lanarkshire | 0 | 0 | 0 | 0 | 6980.42 | 4398.35 | 126303.89 | 137682.66 | 59317.23 | 196999.89 | 0 | [6 empty] | CM_WSNI | 100%
502850 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2018-08-28 | 2021-04-26 | 2021-08-26 | 2022-06-06 | 2022-09-06 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 13698 | 12506.01 | 12457.52 | 38661.53 | 912966.21 | 951627.74 | 0 | [6 empty] | CM_M&G | 33.98% | CM_WSNI | 66.02%
502851 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2017-12-22 | 2020-08-17 | 2020-11-16 | 2021-09-24 | 2021-12-20 | Aberdeenshire | 0 | 0 | 0 | 5902 | 15839.97 | 12859.8 | 124027.2 | 158628.97 | 124371.04 | 283000.01 | 0 | [6 empty] | CM_WSNI | 100%
502852 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2017-12-22 | 2020-04-13 | 2020-07-21 | 2021-04-05 | 2021-07-06 | Highland | 0 | 0 | 0 | 5994.49 | 9735.19 | 73391.21 | 454358.95 | 543479.84 | 382132.8 | 925612.64 | 0 | [6 empty] | CM_WSNI | 100%
502853 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2017-12-22 | 2019-11-25 | 2019-11-29 | 2020-12-03 | 2021-03-18 | Fife | 0 | 0 | 0 | 13267.6 | 107717.0695 | 696817.41 | 139362.14 | 957164.2195 | 99705.54 | 1056869.7595 | 0 | [6 empty] | CM_WSNI | 100%
502854 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2018-08-24 | 2021-04-26 | 2021-08-26 | 2022-06-07 | 2022-09-07 | Fife | 0 | 0 | 0 | 0 | 6591.66 | 5290.98 | 5270.47 | 17153.11 | 279974.66 | 297127.77 | 0 | [6 empty] | CM_WSNI | 100%
502855 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS1 | 2018-08-20 | 2021-04-26 | 2021-08-26 | 2021-11-23 | 2022-02-22 | Perth and Kinross | 0 | 0 | 0 | 0 | 6952.29 | 30528.47 | 32108.82 | 69589.58 | 179538.07 | 249127.65 | 0 | [6 empty] | CM_M&G | 100%
502858 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2017-11-23 | 2020-04-13 | 2020-07-08 | 2021-07-12 | 2021-10-12 | All North Unitary Authorities | 0 | 0 | 0 | 13308.69 | 5197.11 | 73790.49 | 579942.47 | 672238.76 | 694183.01 | 1366421.77 | 0 |  |  |  |  | 20119 |  | CM_M&G | 21.7% | CM_WSNI | 78.3%
502861 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2018-11-20 | 2020-09-14 | 2021-01-22 | 2021-11-05 | 2021-11-05 | Scottish Borders | 0 | 0 | 0 | 0 | 6005.89 | 4957.42 | 138721.35 | 149684.66 | 158315.31 | 307999.97 | 0 | [6 empty] | CM_WSNI | 100%
502860 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS1 | 2018-11-20 | 2020-11-16 | 2021-04-05 | 2022-02-28 | 2022-02-28 | North Lanarkshire | 0 | 0 | 0 | 0 | 8243.17 | 0 | 159085.72 | 167328.89 | 253671.11 | 421000 | 0 | [6 empty] | CM_M&G | 100%
502859 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2018-11-13 | 2020-05-11 | 2020-09-14 | 2021-03-25 | 2021-03-25 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 5369.59 | 34833.17 | 72241.43 | 112444.19 | 37055.79 | 149499.98 | 0 |  |  |  |  | 100456 |  | CM_M&G | 8.629% | CM_WSNI | 91.37%
502857 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2017-12-22 | 2020-08-17 | 2020-11-16 | 2021-09-24 | 2021-12-20 | Aberdeenshire | 0 | 0 | 0 | 9408.24 | 52011.24 | 587.15 | 224010.77 | 286017.4 | 261676.55 | 547693.95 | 0 | [6 empty] | CM_WSNI | 100%
502856 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2017-11-15 | 2020-05-25 | 2020-07-13 | 2021-02-26 | 2021-05-31 | All West Unitary Authorities | 0 | 0 | 0 | 80449.88 | -9315.36 | 18595.32 | 485857.47 | 575587.31 | 252050.24 | 827637.55 | 0 | [6 empty] | CM_M&G | 25% | CM_WSNI | 75%
402671 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-05-16 | 2013-07-31 | 2013-07-31 | 2014-09-25 |  | Scottish Water Wide | 1896620 | 4181.91 | -534.6 | 0 | 0 | 0 | 0 | 3647.31 | 0 | 1900267.31 | 0 | [6 empty] | CM_M&G | 100%
503242 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2018-09-13 | 2019-10-14 | 2020-02-03 | 2020-09-18 | 2020-09-18 | Scottish Water Wide | 0 | 0 | 0 | 0 | 351102.33 | 245668.59 | 630.11 | 597401.03 | 0 | 597401.03 | 0 | [6 empty] | CM_M&G | 100%
503227 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-11-03 | 2023-04-18 | 2023-08-11 | 2024-08-07 | 2024-11-07 | Scottish Borders | 0 | 0 | 0 | 0 | 85886 | 8341.62 | 13447.9 | 107675.52 | 36209.59 | 143885.11 | 148885.7057 | [6 empty] | SG1 | 100%
402849 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-09-04 | 2014-11-28 | 2014-12-01 | 2015-03-27 | 2015-03-27 | Moray | 875097 | 12381.68 | 178.02 | 0 | 0 | 0 | 0 | 12559.7 | 0 | 887656.7 | 229318.7788 | [6 empty] | CS11A | 100%
400088 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2009-12-18 | 2009-12-18 | 2011-10-06 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | -2985513.38 | -117957.33 | 0 | 60.28 | 0 | 0 | 0 | -117897.05 | 0 | -3103410.43 | 0 | [6 empty] | OHDS1 | 50% | OHDW1 | 50%
401028 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWD | Wastewater infrastructure | MS7 | 2010-04-21 | 2012-02-28 | 2012-03-01 | 2015-11-03 |  | Scottish Water Wide | 865439 | 2184.12 | 0 | 262.72 | 0 | 0 | 0 | 2446.84 | 0 | 867885.84 | 0 | [6 empty] | WSI | 25% | WSNI | 25% | WWI | 25% | WWNI | 25%
502299 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-09-09 | 2016-09-09 | 2016-11-02 | 2017-09-19 | 2017-09-19 | Scottish Water Wide | 0 | 0 | 164559.45 | 117899.73 | 0 | 0 | 0 | 282459.18 | 0 | 282459.18 | 0 | [6 empty] | CM_WSI | 100%
502773 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2017-09-20 | 2017-09-20 | 2017-09-29 | 2020-06-30 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 78446 | 222045.67 | 77570.94 | 5763.79 | 383826.4 | 0 | 383826.4 | 0 | [6 empty] | CM_WSI | 100%
502223 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MS3 | 2016-07-21 | 2016-07-21 | 2016-11-02 | 2020-11-20 | 2020-11-20 | Scottish Water Wide | 0 | 0 | 789224.56 | 1173962.45 | 1215484.74 | 32247.08 | 1449081.32 | 4660000.15 | 0 | 4660000.15 | 0 | [6 empty] | CM_WSI | 33.33% | CM_M&G | 66.67%
400806 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2010-05-05 | 2010-05-05 | 2010-05-05 | 2019-07-15 |  | Scottish Water Wide | 166238 | 786.98 | 0 | 0 | 0 | 0 | 0 | 786.98 | 0 | 167024.98 | 0 | [6 empty] | CM_WWI | 100%
502417 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 | 2017-06-29 | 2018-10-25 | 2019-07-09 | 2019-11-01 | 2019-11-04 | Argyll and Bute-North Argyll | 0 | 0 | 4202.33 | 12934.93 | 38586.49 | 71281.46 | 556.26 | 127561.47 | 346.32 | 127907.79 | 0 | [6 empty] | CM_WWI | 100%
500925 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | Clackmannanshire | 0 | 6000 | 793.41 | 0 | 0 | 0 | 0 | 6793.41 | 0 | 6793.41 | 144841.4737 | [6 empty] | CS15A | 100%
502932 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-08-24 | 2027-12-20 | 2028-04-18 | 2029-04-12 | 2029-07-13 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 21179.77 | 1106.24 | 10808.43 | 10766.55 | 43860.99 | 4956314.99 | 5000175.98 | 148885.7057 | [6 empty] | WG1 | 100%
402863 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2012-08-15 | 2014-09-30 | 2014-11-03 | 2016-08-12 | 2016-08-12 | North Lanarkshire | 324755 | -12655 | 5000 | 0 | 40102.8575 | 0 | 0 | 32447.8575 | 0 | 357202.8575 | 229318.7788 | [6 empty] | CS11 | 100%
402854 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS0 | 2012-08-15 | 2020-03-09 | 2020-05-11 | 2020-08-07 | 2020-10-30 | Stirling | 39648.83 | 2030.17 | 43927.91 | 30393.09 | 49747.293 | 0 | 0 | 126098.463 | 0 | 165747.293 | 240495.8008 | [6 empty] | CM_WWI | 40% | CS11A | 60%
502357 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2016-11-27 | 2016-11-27 | 2017-08-01 | 2018-06-26 | 2018-06-26 | Dundee City | 0 | 0 | 129000 | 226612.1875 | -49649.9975 | 0 | 0 | 305962.19 | 0 | 305962.19 | 0 | [6 empty] | CM_WSNI | 100%
501616 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2021-12-09 | 2022-09-06 | 2022-12-02 | 2023-04-17 | 2023-07-18 | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142049.99 | 142049.99 | 0 | [6 empty] | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 33.33% | CM_WSI | 42.86%
501711 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-05-05 | 2022-01-17 | 2022-05-17 | 2022-09-29 | 2022-12-28 | East Lothian | 0 | 0 | 10169.61 | 24820.8065 | 14989.5835 | 0 | 0 | 49980 | 1845794.02 | 1895774.02 | 0 | [6 empty] | CM_WSI | 100%
500062 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS5 | 2015-03-19 | 2016-05-26 | 2016-05-30 | 2017-09-14 | 2018-12-19 | Dundee City | 0 | 405493 | 1254291 | 114503 | 13965.24 | 0 | 0 | 1788252.24 | 0 | 1788252.24 | 367947.8663 | [6 empty] | DW5 | 100%
500802 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2015-11-23 | 2016-09-30 | 2017-01-11 | 2019-01-01 | 2019-04-01 | Dundee City | 0 | 29821 | 176000.51 | 140878.077 | 204431.313 | 5126.14 | 0 | 556257.04 | 0 | 556257.04 | 544757.6554 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 89.61
500006 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS4 | 2015-02-20 | 2016-09-30 | 2016-10-31 | 2019-03-28 | 2019-11-08 | Dundee City | 332.03 | 306152.97 | 831400 | 2530470 | 1721070.28 | 25397.72 | 0 | 5414490.97 | 0 | 5414823 | 2947850.2695 | [6 empty] | CM_WSI | 16.77% | DW5 | 83.23%
500803 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2015-11-23 | 2017-12-20 | 2018-03-26 | 2019-03-01 | 2019-12-01 | Dundee City | 0 | 55736 | 80652.12 | 178133.125 | 223430.235 | 15472.61 | 13158.71 | 566582.8 | 0 | 566582.8 | 776559.4325 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 116.11
500067 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2015-03-11 | 2017-05-24 | 2017-08-10 | 2019-09-03 | 2019-09-04 | Perth and Kinross | 0 | 73000 | 65144 | 878108 | 585257.9 | 441835.16 | 0 | 2043345.06 | 0 | 2043345.06 | 0 | [6 empty] | CM_WSI | 100%
501202 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS0 | 2016-02-11 | 2021-09-13 | 2021-09-13 | 2022-09-06 | 2022-10-18 | Dundee City | 0 | 14109 | 159419.88 | -1838.88 | -4586.03 | 0 | 0 | 167103.97 | 0 | 167103.97 | 0 | [6 empty] | CM_WSNI | 100%
502270 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-06-15 | 2022-09-23 | 2023-01-19 | 2023-08-31 | 2023-12-01 | Dundee City | 0 | 0 | 10190.5 | 454.785 | 5575.53 | 0 | 0 | 16220.815 | 235920.26 | 252141.075 | 0 | [6 empty] | CM_WSNI | 100%
045620 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-06-30 | 2011-04-01 | 2013-05-01 | 2013-12-30 | Dundee City | 604974.56 | -609.16 | 0 | 0 | 0 | 0 | 0 | -609.16 | 0 | 604365.4 | 1236 | [6 empty] | DW1A | 100%
404070 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2014-12-09 | 2014-12-09 | 2014-12-09 | 2017-07-03 |  | North Lanarkshire | 579203.01 | 25945.99 | 0 | -25945.99 | 0 | 0 | 0 | 0 | 0 | 579203.01 | 0 | [6 empty] | CM_WWI | 100%
400721 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-04-14 | 2014-05-22 | 2014-06-02 | 2015-03-19 | 2015-03-19 | South Lanarkshire | 338093.74 | 31002.26 | 2676.95 | 5077.65 | 0 | 0 | 0 | 38756.86 | 0 | 376850.6 | 0 | [6 empty] | SG1 | 100%
502928 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 | 2017-11-13 | 2018-09-05 | 2019-07-08 | 2020-02-26 | 2020-04-22 | East Ayrshire | 0 | 0 | 0 | 6921.17 | 49583.09 | 229916.29 | 8312.75 | 294733.3 | 1734.82 | 296468.12 | 0 | [6 empty] | CM_WSI | 100%
502871 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2021-05-18 | 2027-11-29 | 2028-03-21 | 2029-03-13 | 2029-06-13 | Na H-Eileanan an Iar | 0 | 0 | 0 | 21237.996 | 1111.629 | 13046.13 | 12995.55 | 48391.305 | 4951668.62 | 5000059.925 | 148885.7057 | [6 empty] | WG1 | 100%
500097 | Q&S4 | Climate Change | Climate Change |  |  | Wastewater |  | SWMD | Climate Change | MS7 | 2015-03-31 | 2016-11-29 | 2016-11-30 | 2017-12-01 | 2018-02-01 | Scottish Water Wide | 0 | 6176 | 37820.8 | 113010.85 | -133871.421 | 0 | 0 | 23136.229 | 0 | 23136.229 | 230883.6828 | [6 empty] | CC4S | 100% | bar: Regulatory Outputs OMG-45
500099 | Q&S4 | Climate Change | Climate Change |  |  | Water |  | SWMD | Climate Change | MS7 | 2015-03-31 | 2016-11-29 | 2016-11-30 | 2018-01-01 | 2018-03-01 | Scottish Water Wide | 0 | 1498 | 27962.87 | 30084.31 | 1345.985 | 0 | 0 | 60891.165 | 0 | 60891.165 | 55046.9032 | [6 empty] | CC4W | 100% | bar: Regulatory Outputs OMG-45
500190 | Q&S4 | Climate Change | Climate Change |  |  | Water |  | SWD | Climate Change | MS3 | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-12-08 | 2021-03-26 | Scottish Water Wide | 0 | 1798 | 150 | 28984.717 | 13160.623 | 153680.07 | 159354.6 | 357128.01 | 27282.5 | 384410.51 | 479655.548 | [6 empty] | CC4W | 100%
500098 | Q&S4 | Climate Change | Climate Change |  |  | General |  | SWD | Climate Change | MS7 | 2015-03-31 | 2015-09-25 | 2015-09-25 | 2016-06-14 | 2016-03-30 | Scottish Water Wide | 0 | 20843.73 | 10622.38 | 0 | 0 | 0 | 0 | 31466.11 | 0 | 31466.11 | 68448.9616 | [6 empty] | CC4S | 50% | CC4W | 50%
500093 | Q&S4 | Climate Change | Climate Change |  |  | General |  | SWD | Climate Change | MS7 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | Scottish Water Wide | 0 | 4186.05 | 71.18 | 0 | 0 | 0 | 0 | 4257.23 | 0 | 4257.23 | 82084.3408 | [6 empty] | CC4S | 50% | CC4W | 50%
500092 | Q&S4 | Climate Change | Climate Change |  |  | Wastewater |  | SWD | Climate Change | MS3 | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-08-30 | 2019-09-30 | Scottish Water Wide | 0 | 10465.12 | 871.87 | 30086.2975 | 97914.7125 | 102499.99 | 0 | 241837.99 | 0 | 241837.99 | 933102.516 | [6 empty] | CC4S | 100%
500091 | Q&S4 | Climate Change | Climate Change |  |  | Wastewater |  | SWD | Climate Change | MS4 | 2015-09-30 | 2015-12-21 | 2015-12-21 | 2018-11-30 | 2019-04-02 | Scottish Water Wide | 0 | 17558.09 | 11550 | 667.91 | 4724 | 151759 | 0 | 186259 | 0 | 186259 | 167165.1468 | [6 empty] | CC4S | 100%
500094 | Q&S4 | Climate Change | Climate Change |  |  | Water |  | SWD | Climate Change | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-24 | 2016-05-20 | Scottish Water Wide | 0 | 418.6 | 0 | 0 | 0 | 0 | 0 | 418.6 | 0 | 418.6 | 0 | [6 empty] | CC4W | 100%
500719 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2015-06-30 | 2017-04-06 | 2017-05-02 | 2018-07-11 | 2018-07-11 | Aberdeen City | 0 | 69870 | 182475.89 | 665982.11 | 16672 | 0 | 0 | 935000 | 0 | 935000 | 0 | [6 empty] | CM_WWI | 5.5% | CM_WWNI | 94.5%
402631 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-04-16 | 2012-08-01 | 2012-09-03 | 2013-08-07 |  | Aberdeen City | 396613 | -1837.82 | 0 | 0 | 0 | 0 | 0 | -1837.82 | 0 | 394775.18 | 0 | [6 empty] | CM_WSI | 100%
501304 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-12-10 | 2016-06-02 | 2016-06-02 | 2017-11-15 | 2017-11-15 | Scottish Water Wide | 0 | 69734 | 208440.13 | 104835.58 | 0 | 0 | 0 | 383009.71 | 0 | 383009.71 | 0 | [6 empty] | CM_M&G | 100%
401383 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-09-24 | 2012-07-16 | 2012-10-29 | 2013-06-24 | 2013-06-24 | Highland | 232257 | -2072.3 | 0 | 0 | 0 | 0 | 0 | -2072.3 | 0 | 230184.7 | 1229.4 | [6 empty] | CM_WWI | 40% | CS11A | 60%
500885 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-10-06 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Highland | 0 | 2518.66 | 181.34 | 11378 | -11073.865 | 0 | 0 | 3004.135 | 0 | 3004.135 | 203188.8574 | [6 empty] | DW5FS | 100%
045791 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2011-06-28 | 2011-11-14 | 2012-09-06 | 2012-11-26 | Fife | 495961.95 | 312.49 | 0 | 0 | 0 | 0 | 0 | 312.49 | 0 | 496274.44 | 0 | [6 empty] | WQ01B | 14.53% | WQ01C | 85.47%
400122 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-02-24 | 2012-09-26 | 2012-10-29 | 2015-03-25 |  | Glasgow City | 4403337 | -48209 | -73606.87 | 121.32 | 0 | 0 | 0 | -121694.55 | 0 | 4281642.45 | 0 | [6 empty] | CM_WSI | 100%
400123 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-02-24 | 2012-09-26 | 2012-10-29 | 2014-03-24 |  | Glasgow City | 1171462.37 | 710.63 | -1472.26 | 0 | 0 | 0 | 0 | -761.63 | 0 | 1170700.74 | 0 | [6 empty] | CM_WSI | 100%
501717 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-01-27 | 2017-01-27 | 2017-01-27 | 2016-12-06 | 2017-01-27 | Glasgow City | 0 | 0 | 1674.42 | 0 | 0 | 0 | 0 | 1674.42 | 0 | 1674.42 | 0 | [6 empty] | CM_WWI | 100%
500718 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS3 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2021-03-15 | 2021-03-16 | Scottish Water Wide | 0 | 149946.61 | 215079.39 | 265717.1025 | 410769.9275 | 548606.27 | 96034.46 | 1686153.76 | 0 | 1686153.76 | 0 | [6 empty] | CM_M&G | 100%
401390 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-09-20 | 2010-10-07 | 2011-05-02 | 2015-09-04 |  | Scottish Water Wide | 301994.4 | 32301.34 | 0 | 0 | 0 | 0 | 0 | 32301.34 | 0 | 334295.74 | 0 | [6 empty] | CM_WSI | 100%
402705 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-05-16 | 2015-05-07 | 2015-05-07 | 2015-04-09 |  | Scottish Water Wide | 190000 | 705.72 | 0 | 0 | 0 | 0 | 0 | 705.72 | 0 | 190705.72 | 0 | [6 empty] | CM_WWNI | 100%
402703 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-05-16 | 2013-10-11 | 2013-10-14 | 2017-03-17 |  | Scottish Water Wide | 1650000 | 50000 | -10890.65 | 0 | 0 | 0 | 0 | 39109.35 | 0 | 1689109.35 | 0 | [6 empty] | CM_WWNI | 100%
501632 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2021-03-15 |  | Scottish Water Wide | 0 | 0 | 201299.1 | 177872 | 560710 | 160000 | 163682.9 | 1263564 | 0 | 1263564 | 0 | [6 empty] | CM_M&G | 100%
402071 | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2011-03-29 | 2011-03-29 | 2011-04-01 | 2016-08-08 |  | Scottish Water Wide | 983867 | 13080.11 | 0 | 0 | 0 | 0 | 0 | 13080.11 | 0 | 996947.11 | 35117 | [6 empty] | CS20 | 100%
403350 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2013-04-29 | 2013-04-29 | 2013-05-22 | 2014-11-14 |  | Scottish Water Wide | 822926.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 822926.35 | 0 | [6 empty] | CM_WWI | 100%
403351 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2013-03-18 | 2013-03-18 | 2013-07-01 | 2015-06-25 |  | Scottish Water Wide | 1630000 | -31971.24 | 0 | 0 | 0 | 0 | 0 | -31971.24 | 0 | 1598028.76 | 0 | [6 empty] | CM_WWI | 100%
501294 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2021-04-15 |  |  | 2021-04-15 | 2021-04-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 902919.66 | 902919.66 | 0 | 902919.66 | 0 | [6 empty] | CM_WWI | 100%
403904 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2014-09-15 | 2015-01-19 | 2016-09-19 | 2017-05-29 |  | Highland | 69877 | 348919 | 160228 | 24653.643 | 15056.15 | 0 | 0 | 548856.793 | 0 | 618733.793 | 0 | [6 empty] | CM_WWNI | 100%
403748 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-02-24 | 2014-02-24 | 2014-04-09 | 2016-03-10 |  | Scottish Water Wide | 327673.97 | 34007.2 | 0 | 0 | 0 | 0 | 0 | 34007.2 | 0 | 361681.17 | 0 | [6 empty] | CM_WSI | 100%
403615 | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWMD | Non OMG180 | MS7 | 2013-12-18 | 2013-12-18 | 2014-02-03 | 2016-12-14 |  | Scottish Water Wide | 3424237 | -31727.02 | -44475 | 302.29 | 0 | 0 | 0 | -75899.73 | 0 | 3348337.27 | 2687972 | [6 empty] | ESP | 100%
402441 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2011-11-10 | 2012-10-31 | 2012-11-19 | 2017-05-29 |  | Scottish Water Wide | 1238293 | 13139.3 | 104.91 | 44.59 | 0 | 0 | 0 | 13288.8 | 0 | 1251581.8 | 0 | [6 empty] | CM_M&G | 100%
403375 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 | 2013-02-26 | 2013-02-26 | 2013-03-28 | 2019-02-14 |  | All South Unitary Authorities | 3653315 | 431465 | -30591.53 | 27723.8275 | 11685.3925 | 0 | 0 | 440282.69 | 0 | 4093597.69 | 0 | [6 empty] | CM_WWI | 100%
403378 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 | 2013-02-26 | 2013-02-26 | 2013-03-22 | 2017-03-06 |  | All West Unitary Authorities | 2988090 | 737457 | -56711.58 | -3822.02 | 63.87 | 0 | 0 | 676987.27 | 0 | 3665077.27 | 0 | [6 empty] | CM_WWI | 100%
403371 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2014-05-15 | 2014-05-16 |  | All North Unitary Authorities | 9820.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9820.49 | 0 | [6 empty] | CM_WWI | 100%
404021 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-11-26 | 2014-11-26 | 2015-01-12 | 2015-07-30 |  | All North Unitary Authorities | 99599 | 197893.81 | 0 | 0 | 0 | 0 | 0 | 197893.81 | 0 | 297492.81 | 0 | [6 empty] | CM_WSI | 100%
403627 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2013-11-13 | 2013-11-13 | 2014-05-06 | 2019-05-17 |  | Scottish Water Wide | 142968 | 3874 | 3026.98 | 4472.98 | 902.0775 | 0 | 0 | 12276.0375 | 0 | 155244.0375 | 0 | [6 empty] | CM_WSI | 100%
030148 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2010-06-28 | 2010-09-20 | 2012-02-01 | 2012-03-12 | South Lanarkshire | 3371144.21 | 1198.09 | 0 | 0 | 0 | 0 | 0 | 1198.09 | 0 | 3372342.3 | 0 | [6 empty] | CM_WWNI | 26.6% | EC04A | 33.84% | EC10A | 39.56%
400073 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-10-06 | 2011-03-30 | 2011-09-19 | 2012-09-05 |  | Angus | 678633.81 | 75.52 | 0 | 0 | 0 | 0 | 0 | 75.52 | 0 | 678709.33 | 0 | [6 empty] | CM_WWNI | 100%
503133 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2021-08-05 | 2022-10-05 | 2023-02-07 | 2023-09-19 | 2023-12-20 | West Dunbartonshire | 0 | 0 | 0 | 0 | 11932.823 | 0 | 0 | 11932.823 | 237999.94 | 249932.763 | 0 | [6 empty] | CM_WSNI | 100%
403221 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-01-16 | 2014-10-01 | 2014-10-01 | 2014-10-01 |  | Glasgow City | 138508.25 | 550.84 | 0 | 0 | 0 | 0 | 0 | 550.84 | 0 | 139059.09 | 0 | [6 empty] | CM_WSNI | 100%
500716 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2022-02-07 | 2023-09-29 | 2024-02-02 | 2025-07-30 | 2025-10-28 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5118907.11 | 5118907.11 | 0 | [6 empty] | CM_WSNI | 100%
403065 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-11-22 | 2014-10-01 | 2014-10-01 | 2014-10-21 |  | Glasgow City | 157857.02 | 16 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 157873.02 | 0 | [6 empty] | CM_WSNI | 100%
403565 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2013-08-27 | 2016-12-15 | 2016-12-15 | 2016-12-16 | 2016-12-16 | Fife | 41656 | 46642.9 | 46237.73 | 0 | 0 | 0 | 0 | 92880.63 | 0 | 134536.63 | 0 | [6 empty] | SG1 | 100%
502313 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2022-04-08 | 2023-01-10 | 2023-03-16 | 2023-07-31 | 2023-10-31 | Argyll and Bute-North Argyll | 0 | 0 | 5133.26 | 923.31 | 42.58 | 0 | 0 | 6099.15 | 5900.85 | 12000 | 0 | [6 empty] | CM_WSI | 100%
402934 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2012-10-23 | 2013-12-18 | 2017-02-02 | 2017-02-07 | 2017-02-07 | Na H-Eileanan an Iar | 39672 | 33359 | -21609.79 | 0 | 0 | 0 | 0 | 11749.21 | 0 | 51421.21 | 0 | [6 empty] | SG1 | 100%
403170 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-11-26 | 2013-05-20 | 2013-06-25 | 2013-10-23 | 2013-10-23 | City of Edinburgh | 40917 | -3265.08 | 0 | 0 | 0 | 0 | 0 | -3265.08 | 0 | 37651.92 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
300025 | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-09-05 | 2011-09-05 | 2011-10-19 | 2012-03-16 | 2011-03-14 | Dumfries and Galloway | 35891.52 | -2843.7 | 0 | 0 | 0 | 0 | 0 | -2843.7 | 0 | 33047.82 | 0 | [6 empty] | EC01D | 100%
401202 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-07-19 | 2010-12-17 | 2011-01-24 | 2014-06-20 | 2014-07-31 | All East Unitary Authorities | 1318698 | 646 | -818.25 | 0 | 0 | 0 | 0 | -172.25 | 0 | 1318525.75 | 2500 | [6 empty] | DW1A | 100%
401204 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-07-19 | 2010-12-17 | 2011-01-24 | 2014-03-28 | 2014-03-31 | All North Unitary Authorities | 496352 | 240 | -753.63 | 0 | 0 | 0 | 0 | -513.63 | 0 | 495838.37 | 898 | [6 empty] | DW1A | 100%
400069 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-10-06 | 2011-09-21 | 2011-09-23 | 2015-03-30 | 2015-03-30 | Scottish Water Wide | 3463779.75 | 4733.51 | 0 | 323.47 | 0 | 0 | 0 | 5056.98 | 0 | 3468836.73 | 42643 | [6 empty] | WQ01A | 100%
500589 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-10-01 | 2016-11-09 | 2016-11-09 | 2017-06-30 | 2017-06-30 | Scottish Water Wide | 0 | 386941.66 | 270481.57 | 38834.74 | -2789.45 | 0 | 0 | 693468.52 | 0 | 693468.52 | 0 | [6 empty] | CM_M&G | 100%
403413 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2013-05-24 | 2019-06-27 | 2019-06-28 | 2021-07-05 | 2021-08-02 | Scottish Water Wide | 50000 | 0 | 0 | 0 | -48780.49 | 11253.24 | 36585 | -942.25 | 941.77 | 49999.52 | 0 | [6 empty] | WSI | 0.25% | WSNI | 0.25% | WWNI | 0.25% | WWI | 99.25%
503325 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 | 2018-07-31 | 2019-03-19 | 2019-04-24 | 2019-10-07 | 2019-10-07 | Scottish Water Wide | 0 | 0 | 0 | 0 | 34513.0125 | 352643.74 | 0 | 387156.7525 | 0 | 387156.7525 | 0 | [6 empty] | CM_WSI | 100%
502631 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2017-06-15 | 2018-02-28 | 2018-05-18 | 2018-11-12 | 2018-11-12 | North Lanarkshire | 0 | 0 | 0 | 227319 | 78536.078 | 0 | 0 | 305855.078 | 0 | 305855.078 | 0 | [6 empty] | CM_WSI | 100%
502377 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-11-02 | 2018-11-02 | 2018-11-02 | 2018-11-02 | 2018-11-02 | Highland | 0 | 0 | 46062.91 | 16468.81 | 340.06 | 0 | 0 | 62871.78 | 0 | 62871.78 | 148885.7057 | [6 empty] | SG1 | 100%
502794 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2021-04-01 | 2022-02-09 | 2022-06-08 | 2022-10-13 | 2023-01-13 | Highland | 0 | 0 | 0 | 20817.18 | 537.73 | 722.59 | 26933.09 | 49010.59 | 450999.98 | 500010.57 | 0 | [6 empty] | CM_WWNI | 100%
502923 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWD | Reservoirs | GW1 | 2020-02-14 | 2021-05-24 | 2021-09-06 | 2022-04-25 | 2022-07-26 | Scottish Water Wide | 0 | 0 | 0 | 227947.58 | 9243.4 | 262809.03 | 0 | 500000.01 | 0 | 500000.01 | 0 | [6 empty] | WR6 | 100%
402850 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2012-08-20 | 2014-09-30 | 2015-01-13 | 2015-03-24 | 2015-03-24 | West Lothian | 295629 | 40885.66 | 204.5 | -1631.245 | 0 | 0 | 0 | 39458.915 | 0 | 335087.915 | 229318.7788 | [6 empty] | CS11 | 100%
500957 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-11-24 | 2017-03-01 | 2017-03-01 | 2018-03-28 |  | Scottish Water Wide | 0 | 416746 | 2445157.22 | 1950165.12 | -31285.66 | 0 | 0 | 4780782.68 | 0 | 4780782.68 | 0 | [6 empty] | CM_M&G | 100%
503321 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-04-05 | 2023-09-18 | 2024-01-22 | 2025-01-17 | 2025-04-21 | Fife | 0 | 0 | 0 | 0 | 78524.5 | 0 | 11105.35 | 89629.85 | 56338.75 | 145968.6 | 148885.7057 | [6 empty] | SG1 | 100%
500122 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2015-03-19 | 2016-06-21 | 2016-08-18 | 2019-06-24 | 2019-09-23 | Highland | 0 | 10844 | 16121 | 7511 | 62607 | 33087.95 | 0 | 130170.95 | 0 | 130170.95 | 27558.6127 | [6 empty] | EC01G | 23.78% | EC01D | 32.91% | CS16D | 43.31%
046334 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-03-13 | 2015-04-30 | 2015-02-12 | 2015-02-12 |  | Highland | 513456.45 | 33.08 | 0 | 0 | 0 | 0 | 0 | 33.08 | 0 | 513489.53 | 0 | [6 empty] | CM_WWNI | 100%
503326 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2021-04-01 | 2022-02-04 | 2022-05-04 | 2023-05-30 | 2023-08-30 | Highland | 0 | 0 | 0 | 0 | 21764.56 | 3088.86 | 25126.73 | 49980.15 | 1950019.96 | 2000000.11 | 0 | [6 empty] | CM_WWI | 100%
403918 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2014-10-10 | 2017-11-22 | 2018-01-29 | 2019-04-08 |  | Highland | 2005.85 | 184042.15 | 77833 | 792790 | 617312 | 0.07 | 1009.93 | 1672987.15 | 0 | 1674993 | 0 |  |  |  |  | 609.9997 |  | CM_WWNI | 100%
500621 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 927543.35 | 1113164.28 | 1235000.8 | 1253028.3 | 0 | 0 | 4528736.73 | 0 | 4528736.73 | 0 | [6 empty] | CM_OVH | 100%
403272 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-01-28 | 2014-04-29 | 2014-04-29 | 2014-05-06 |  | Scottish Water Wide | 15537.85 | 0 | 47.45 | 0 | 0 | 0 | 0 | 47.45 | 0 | 15585.3 | 0 | [6 empty] | CM_WSI | 100%
501029 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-12-23 | 2016-05-16 | 2016-05-16 | 2019-04-23 | 2019-04-23 | Scottish Water Wide | 0 | 10154 | 456629.5 | 339687.6 | 218106.4 | 18080 | 0 | 1042657.5 | 0 | 1042657.5 | 0 |  |  |  |  | -30999.9997 |  | CM_M&G | 100%
400719 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-04-14 | 2011-11-10 | 2012-09-28 | 2013-02-19 | 2013-02-19 | North Ayrshire | 279753 | 25360 | -8232.95 | 0 | 0 | 0 | 0 | 17127.05 | 0 | 296880.05 | 0 | [6 empty] | SG1 | 100%
503196 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2018-09-17 | 2018-12-20 | 2019-03-28 | 2019-12-01 | 2020-12-01 | East Ayrshire | 0 | 0 | 0 | 0 | 223050.53 | 252694.42 | 0 | 475744.95 | 0 | 475744.95 | 0 | [6 empty] | DW5MR | 6.825% | DW5FS | 93.18% | [16 empty] | Regulatory Outputs OMG-06: 128.982
030154 | Q&S3A | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS6 | 2005-11-03 | 2007-04-11 | 2007-04-11 | 2011-03-31 | 2013-12-23 | East Ayrshire | 10950532.62 | 13484.3 | 0 | 0 | 0 | 0 | 0 | 13484.3 | 0 | 10964016.92 | 0 | [6 empty] | WSNI | 6% | DW13 | 18.8% | DW2 | 18.8% | DW3C | 18.8% | DW3G | 18.8% | DW4A | 18.8%
502708 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS0 | 2017-10-23 | 2019-07-01 | 2019-09-03 | 2020-03-16 | 2020-06-22 | Scottish Borders | 0 | 0 | 0 | 30066.0775 | 194303.9225 | 553392.7 | 194789.11 | 972551.81 | 5187.96 | 977739.77 | 0 | [6 empty] | CM_WWI | 100%
501047 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-11-18 | 2016-04-11 | 2016-04-11 | 2018-01-24 |  | Scottish Water Wide | 0 | 104225 | 271529.32 | 0 | 0 | 0 | 0 | 375754.32 | 0 | 375754.32 | 0 | [6 empty] | CM_M&G | 100%
501898 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS1 | 2017-03-01 | 2019-07-29 | 2019-07-29 | 2020-04-20 |  | Scottish Water Wide | 0 | 0 | 294324.8 | 1279591.97 | -419395.69 | 2953048.04 | 720697.88 | 4828267 | 0 | 4828267 | 0 | [6 empty] | CM_M&G | 100%
502306 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-05-25 | 2022-11-16 | 2023-03-16 | 2024-03-05 | 2024-06-05 | Dumfries and Galloway | 0 | 0 | 37591.29 | 4800.23 | 18870.703 | 0 | 12696.87 | 73959.093 | 1276030.19 | 1349989.283 | 0 | [6 empty] | CM_WSNI | 100%
403357 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-03-04 | 2015-09-22 | 2015-11-09 | 2016-03-23 | 2016-09-01 | South Lanarkshire | 9239 | 255761 | 23865.75 | -2386.58 | 0 | 0 | 0 | 277240.17 | 0 | 286479.17 | 0 | [6 empty] | CM_WSI | 100%
500805 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2015-10-28 | 2017-07-21 | 2017-08-14 | 2018-03-01 | 2018-06-01 | South Lanarkshire | 0 | 31000 | 369.43 | 188786.3792 | 21571.4808 | 1854.71 | 0 | 243582 | 0 | 243582 | 524015.0356 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 84.44
503056 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-04-01 | 2022-02-28 | 2022-05-16 | 2023-02-14 | 2023-05-17 | South Lanarkshire | 0 | 0 | 0 | 23260.53 | 13691.1 | 0 | 0 | 36951.63 | 1110048.32 | 1146999.95 | 0 | [6 empty] | CM_WSI | 100%
402855 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-08-15 | 2014-07-07 | 2014-07-21 | 2014-09-23 | 2014-09-23 | Dundee City | 68615 | 150 | -249.92 | 0 | 0 | 0 | 0 | -99.92 | 0 | 68515.08 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
503232 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 | 2019-01-28 | 2019-01-28 | 2019-05-31 | 2020-03-20 | 2020-06-22 | Perth and Kinross | 0 | 0 | 0 | 0 | 140375.9 | 153927.4 | 62764.08 | 357067.38 | 2932.61 | 359999.99 | 0 | [6 empty] | CM_WWNI | 100%
030157 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-16 | 2011-12-20 | 2012-02-29 | 2015-01-26 | 2015-03-30 | North Lanarkshire | 2189671.29 | -260.38 | 1653.56 | 0 | 0 | 0 | 0 | 1393.18 | 0 | 2191064.47 | 56088.906 | [6 empty] | CM_WWNI | 25% | EC04A | 75%
503542 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWD | UWWTD - Works | MS5 | 2018-01-31 | 2018-01-31 | 2018-02-26 | 2019-03-01 | 2019-03-01 | North Lanarkshire | 0 | 0 | 0 | 0 | 27672.9 | 395327.11 | 0 | 423000.01 | 0 | 423000.01 | 606545.1764 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
502754 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Wastewater |  | SWD | DWQ Reliability | MS3 | 2017-07-12 | 2017-07-12 | 2017-10-17 | 2019-04-29 | 2019-04-30 | Aberdeen City | 0 | 0 | 0 | 109508.13 | 0 | 0 | 0 | 109508.13 | 0 | 109508.13 | 4524529.4527 | [6 empty] | DW25P | 22.92% | SG5 | 77.08%
502755 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS3 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2019-04-30 | 2019-05-01 | Aberdeen City | 0 | 0 | 0 | 5011.28 | 58814.2 | 0 | 0 | 63825.48 | 0 | 63825.48 | 587726.5342 | [6 empty] | WG5 | 100%
501947 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2016-03-29 | 2021-12-06 | 2022-01-31 | 2022-06-07 | 2022-09-07 | Scottish Borders | 0 | 785 | 10943 | -4000.44 | 0 | 0 | 0 | 7727.56 | 342538.45 | 350266.01 | 0 | [6 empty] | CM_WWI | 100%
046175 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-31 | 2010-12-23 | 2011-03-18 | 2012-10-03 |  | Fife | 3032171.08 | 190 | 0 | 0 | 0 | 0 | 0 | 190 | 0 | 3032361.08 | 0 | [6 empty] | CM_WWNI | 100%
402177 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-07-11 | 2012-09-05 | 2012-11-16 | 2014-03-26 | 2014-03-26 | South Lanarkshire | 336527.8 | 984.52 | 0 | 0 | 0 | 0 | 0 | 984.52 | 0 | 337512.32 | 0 | [6 empty] | CM_WSI | 100%
500721 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2015-12-14 | 2016-03-29 | 2016-04-02 | 2019-07-01 | 2019-07-01 | Glasgow City | 0 | 403500 | 325728.74 | 1055.7746 | 9842.7354 | 0 | 0 | 740127.25 | 0 | 740127.25 | 0 | [6 empty] | CM_WWI | 100%
500892 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS0 | 2019-02-28 | 2020-06-22 | 2020-10-22 | 2022-05-24 | 2022-08-24 | Aberdeenshire | 0 | 23824.63 | 13707.34 | 80228.177 | 9017.7925 | 398707.56 | 1011255.41 | 1536740.9095 | 1649085.8 | 3185826.7095 | 587726.5342 | [6 empty] | WG5 | 100%
030397 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-15 | 2015-03-12 | 2015-03-12 | 2015-03-12 | 2015-03-12 | South Ayrshire | 803468.51 | 12 | -5643.07 | 0 | 0 | 0 | 0 | -5631.07 | 0 | 797837.44 | 4095.9067 | [6 empty] | EC04A | 100%
503279 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-07 | 2023-06-21 | 2023-10-24 | 2024-10-21 | 2025-01-21 | South Ayrshire | 0 | 0 | 0 | 0 | 77202.87 | 9717.51 | 33924.13 | 120844.51 | 22536.92 | 143381.43 | 148885.7057 | [6 empty] | SG1 | 100%
403936 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | NONINF | Non OMG180 | MS6 | 2009-05-15 | 2016-09-28 | 2017-01-23 | 2017-10-30 | 2017-10-30 | East Ayrshire | 47684 | 152230 | 1132068.88 | 2838971.48 | 201095.15 | 13651.11 | 1387.17 | 4339403.79 | 0 | 4387087.79 | 1198319.5983 |  |  |  |  | 11000 |  | EC04A | 50% | CM_WWNI | 50%
502957 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW1 | 2021-06-02 | 2022-02-08 | 2022-04-26 | 2022-09-08 | 2022-12-09 | Perth and Kinross | 0 | 0 | 0 | 6440.2765 | 25472.162 | 0 | 0 | 31912.4385 | 490000.03 | 521912.4685 | 0 | [6 empty] | CM_WWI | 100%
502877 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW1 | 2021-06-03 | 2022-04-06 | 2022-06-22 | 2023-01-23 | 2023-04-25 | Perth and Kinross | 0 | 0 | 0 | 16501.605 | 13539.9665 | 9275.73 | 9239.77 | 48557.0715 | 351717.8 | 400274.8715 | 0 | [6 empty] | CM_WWI | 100%
403323 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-05-07 | 2014-12-17 | 2014-12-17 | 2015-08-25 | 2015-08-25 | East Ayrshire | 203413 | 203087 | 0 | -693.62 | 0 | 0 | 0 | 202393.38 | 0 | 405806.38 | 0 | [6 empty] | CM_WSI | 100%
500774 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-07-27 | 2017-12-21 | 2018-02-26 | 2018-07-18 | 2018-07-18 | East Ayrshire | 0 | 4000 | 75402.21 | 296040.79 | 250151.0254 | 0 | 0 | 625594.0254 | 0 | 625594.0254 | 0 | [6 empty] | CM_WWI | 100%
502159 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2016-06-20 | 2016-06-20 | 2016-06-20 | 2016-05-26 | 2016-06-20 | Aberdeenshire | 0 | 0 | 20930.23 | 0 | 0 | 0 | 0 | 20930.23 | 0 | 20930.23 | 0 | [6 empty] | CM_WSI | 100%
500896 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS0 | 2016-10-27 | 2020-07-06 | 2020-09-07 | 2022-03-10 | 2022-06-09 | Aberdeenshire | 0 | 64413.05 | 378292.91 | 92578.51 | 112542.02 | 311750.35 | 3736346.49 | 4695923.33 | 8227150.06 | 12923073.39 | 0 | [6 empty] | CM_WSNI | 100%
502645 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2022-04-05 | 2027-11-01 | 2028-01-13 | 2028-12-22 | 2029-03-26 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 21594.096 | 1821.562 | 8153.97 | 8122.38 | 39692.008 | 4960312.03 | 5000004.038 | 148885.7057 | [6 empty] | WG1 | 100%
404008 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2014-12-04 | 2015-08-31 | 2015-10-19 | 2016-09-07 | 2016-10-03 | City of Edinburgh | 71964 | 858071.55 | 87464.45 | 0 | -6875.7852 | 0 | 0 | 938660.2148 | 0 | 1010624.2148 | 229318.7788 | [6 empty] | CS11 | 100%
500893 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-09-24 | 2023-06-01 | 2023-10-04 | 2025-04-29 | 2025-07-30 | East Dunbartonshire | 0 | 11086.02 | 42349.12 | 692.245 | 2891.448 | 0 | 0 | 57018.833 | 1076981.21 | 1134000.043 | 0 | [6 empty] | CM_WSI | 100%
500231 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS6 | 2015-03-23 | 2016-04-25 | 2016-10-03 | 2017-02-01 | 2017-10-01 | Argyll and Bute-North Argyll | 0 | 604.07 | 9907.51 | 1531.96 | 1138.46 | 0 | 0 | 13182 | 0 | 13182 | 11848.2135 | [6 empty] | DW5FS | 100% | bar: Regulatory Outputs OMG-02
500858 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2016-03-31 | 2017-06-25 | 2017-06-30 | 2018-03-29 | 2018-12-11 | Argyll and Bute-North Argyll | 0 | 2040.25 | 1994.75 | 10024.3083 | 6946.5517 | 2500.01 | 0 | 23505.87 | 0 | 23505.87 | 11240.7328 | [6 empty] | DW5FS | 100%
500633 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWMD | Supply Resilience | MS7 | 2015-06-09 | 2015-07-20 | 2015-08-03 | 2015-11-02 | 2015-12-17 | Argyll and Bute-North Argyll | 0 | 1835327.61 | 13397.06 | 2462.4495 | 0.0005 | 0 | 0 | 1851187.12 | 0 | 1851187.12 | 639260.3798 | [6 empty] | CS16WR | 100%
403322 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-03-19 | 2013-03-19 | 2013-03-21 | 2013-07-22 |  | Argyll and Bute-North Argyll | 486648.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 486648.95 | 0 |  |  |  |  | 98064 |  | CM_WSNI | 100%
045029 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-12 | 2012-11-07 | 2013-11-20 | 2015-10-27 | 2015-10-27 | Argyll and Bute-North Argyll | 7472159.47 | 151595.78 | 2195.38 | -51425.15 | 0 | 0 | 0 | 102366.01 | 0 | 7574525.48 | 423659.5204 | [6 empty] | WG1 | 25% | DW23 | 75%
503376 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-05-16 | 2023-03-23 | 2023-07-26 | 2024-01-16 | 2024-04-17 | Fife | 0 | 0 | 0 | 0 | 77571.46 | 4490.72 | 9453.64 | 91515.82 | 54597.03 | 146112.85 | 148885.7057 | [6 empty] | SG1 | 100%
500992 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2015-10-07 | 2017-01-31 | 2017-03-21 | 2017-12-11 | 2017-12-11 | Fife | 0 | 919 | 52148.14 | 184096.85 | -1058.67 | 500.4 | 399.55 | 237005.27 | 0 | 237005.27 | 0 | [6 empty] | CM_WWNI | 100%
501251 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2016-11-10 | 2022-02-14 | 2022-06-16 | 2023-09-12 | 2023-12-13 | Aberdeenshire | 0 | 18868.52 | 92874.81 | 0 | 0.001 | 0 | 0 | 111743.331 | 2387760.68 | 2499504.011 | 0 | [6 empty] | CM_WSNI | 100%
045319 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-08-27 | 2011-03-16 | 2005-02-21 | 2011-07-12 | 2011-03-14 | Aberdeenshire | 50042.19 | 4.37 | 0 | 0 | 0 | 0 | 0 | 4.37 | 0 | 50046.56 | 0 | [6 empty] | DW13 | 100%
400093 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-12-04 | 2012-03-14 | 2012-04-16 | 2015-09-11 | 2014-10-01 | Dumfries and Galloway | 3699596 | -214980 | 2874.91 | -6871.24 | 0 | 0 | 0 | -218976.33 | 0 | 3480619.67 | 18.4553 | [6 empty] | CM_WWI | 3% | CS11A | 7% | EC01B | 90%
503337 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-05-05 | 2022-04-08 | 2022-06-27 | 2023-01-23 | 2023-04-25 | Stirling | 0 | 0 | 0 | 0 | 7233.49 | 0 | 0 | 7233.49 | 352766.48 | 359999.97 | 0 | [6 empty] | CM_WSI | 100%
502977 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS2 | 2018-03-29 | 2018-11-08 | 2019-04-08 | 2019-07-01 | 2019-10-01 | Perth and Kinross | 0 | 0 | 0 | 8520.81 | 46727.19 | 73246 | 5207.97 | 133701.97 | 0.03 | 133702 | 0 | [6 empty] | CM_WWI | 100%
401340 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-13 | 2012-03-21 | 2012-08-27 | 2015-03-27 | 2014-03-31 | Aberdeenshire | 187812 | 8626.93 | 668.23 | 0 | 0 | 0 | 0 | 9295.16 | 0 | 197107.16 | 0 | [6 empty] | CS1 | 100%
500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS3 | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-07-31 | 2020-07-31 | Scottish Water Wide | 0 | 865651.6 | 2635142.06 | 1113436.65 | 790634.2981 | 120588.27 | 36225.37 | 5561678.2481 | 0 | 5561678.2481 | 1560467.3848 | [6 empty] | CS22 | 100%
502786 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS5 | 2017-09-28 | 2017-09-28 | 2017-09-28 | 2019-03-04 | 2019-03-04 | Scottish Water Wide | 0 | 0 | 0 | 416407.83 | 718410.49 | 0 | 0 | 1134818.32 | 0 | 1134818.32 | 0 | [6 empty] | CM_M&G | 100%
402474 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-12-19 | 2014-02-24 | 2014-02-27 | 2016-04-27 | 2016-05-20 | Dumfries and Galloway | 2083096.6 | 531766.4 | 212679 | -1142.83 | 0 | 0 | 0 | 743302.57 | 0 | 2826399.17 | 0 | [6 empty] | CM_WWNI | 8.919% | SG1 | 91.08%
503042 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2021-04-01 | 2022-06-22 | 2022-10-14 | 2023-05-26 | 2023-08-28 | Highland | 0 | 0 | 0 | 31203.1 | 664.69 | 2217.23 | 39936.26 | 74021.28 | 2425999.98 | 2500021.26 | 0 | [6 empty] | CM_WWNI | 100%
500493 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWD | UWWTD - Works | MS7 | 2015-06-16 | 2015-11-16 | 2015-11-17 | 2017-02-13 | 2017-02-13 | Highland | 0 | 94.75 | 0 | 0 | 0 | 0 | 0 | 94.75 | 0 | 94.75 | 1091028.8642 | [6 empty] | EC01A | 100%
045807 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2011-07-28 | 2011-09-05 | 2012-06-20 | 2012-06-29 | South Lanarkshire | 865891.06 | 22.22 | 0 | 0 | 0 | 0 | 0 | 22.22 | 0 | 865913.28 | 0 | [6 empty] | WQ01C | 100%
502403 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2019-09-06 | 2021-03-22 | 2021-07-22 | 2022-07-12 | 2022-10-12 | South Lanarkshire | 0 | 0 | 31033.94 | 34245.79 | 30578.146 | 276745.56 | 114504.34 | 487107.776 | 0 | 487107.776 | 148885.7057 | [6 empty] | SG1 | 100%
503088 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-05-05 | 2022-04-01 | 2022-08-03 | 2023-03-01 | 2023-06-01 | Perth and Kinross | 0 | 0 | 0 | 18614.12 | 2769.876 | 0 | 0 | 21383.996 | 1069612.48 | 1090996.476 | 0 | [6 empty] | CM_WSI | 100%
501400 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-04-21 | 2022-05-18 | 2022-09-21 | 2023-05-08 | 2023-08-08 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000.02 | 250000.02 | 0 | [6 empty] | CM_WSNI | 100%
403907 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2015-03-30 | 2017-02-17 | 2017-02-17 | 2017-02-20 | 2017-02-20 | Na H-Eileanan an Iar | 365.85 | 12550.15 | 32787.12 | 486.4 | 0 | 0 | 0 | 45823.67 | 0 | 46189.52 | 148885.7057 | [6 empty] | SG1 | 100%
502817 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-04-21 | 2022-07-22 | 2022-11-14 | 2023-11-02 | 2024-02-02 | Highland | 0 | 0 | 0 | 39079.11 | 2454.6 | 1631.64 | 22615.41 | 65780.76 | 77526.25 | 143307.01 | 148885.7057 | [6 empty] | SG1 | 100%
501726 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-07-23 | 2022-06-15 | 2022-09-12 | 2023-04-12 | 2023-07-13 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 965940.02 | 965940.02 | 0 | [6 empty] | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 33.33% | CM_WSI | 42.86%
500620 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 40337 | 53069.86 | 50922.05 | 51657.748 | 0 | 0 | 195986.658 | 0 | 195986.658 | 0 | [6 empty] | CM_OVH | 100%
500632 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 345715.43 | 400937.3 | 453239.93 | 800824.855 | 0 | 0 | 2000717.515 | 0 | 2000717.515 | 0 | [6 empty] | CM_OVH | 100%
500472 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2015-03-31 | 2016-02-05 | 2016-03-28 | 2019-10-01 | 2020-01-01 | South Lanarkshire | 0 | 46326 | 40332 | 39378.09 | 43963.91 | 43658.35 | 9341.66 | 223000.01 | 0 | 223000.01 | 197884.2362 | [6 empty] | EC10E | 100% | bar: Regulatory Outputs OMG-23
046265 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-12-03 | 2010-09-27 | 2011-09-26 | 2012-09-21 |  | Aberdeen City | 738943.5 | 3901.84 | -3901.84 | 0 | 0 | 0 | 0 | 0 | 0 | 738943.5 | 0 | [6 empty] | CM_WSNI | 100%
403069 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-11-21 | 2014-06-20 | 2014-07-21 | 2015-03-31 | 2015-03-31 | North Lanarkshire | 1143423 | 56391 | 576.37 | 0 | 0 | 0 | 0 | 56967.37 | 0 | 1200390.37 | 229318.7788 | [6 empty] | CS11 | 100%
501564 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2016-04-25 | 2018-09-28 | 2018-10-29 | 2019-05-03 | 2019-05-07 | North Ayrshire | 0 | 0 | 12366.29 | 35867.71 | 536689.45 | 25401.05 | 0 | 610324.5 | 0 | 610324.5 | 0 | [6 empty] | CM_WSI | 100%
400808 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2010-05-31 | 2012-09-26 | 2012-11-13 | 2014-06-27 |  | East Ayrshire | 1054658.77 | -23446.33 | -19.68 | 0 | 0 | 0 | 0 | -23466.01 | 0 | 1031192.76 | 0 |  |  |  |  | 17000 |  | CM_WWNI | 100%
402220 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2011-07-19 | 2013-02-25 | 2013-05-13 | 2014-06-27 |  | East Ayrshire | 511013.57 | 346.95 | 0 | 0 | 0 | 0 | 0 | 346.95 | 0 | 511360.52 | 0 |  |  |  |  | 16219 |  | CM_WWNI | 100%
403380 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-03-15 | 2014-03-04 | 2014-08-06 | 2015-01-28 |  | East Ayrshire | 254257 | -3080.9 | 0 | 0 | 0 | 0 | 0 | -3080.9 | 0 | 251176.1 | 0 | [6 empty] | CM_WWNI | 100%
502599 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2017-02-21 | 2017-02-21 | 2017-07-25 | 2017-11-28 | 2017-11-28 | East Ayrshire | 0 | 0 | 17284.98 | 420615.02 | 86 | 534.72 | 379.28 | 438900 | 0 | 438900 | 0 | [6 empty] | CM_WWI | 100%
402966 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-10-01 | 2014-09-22 | 2014-10-06 | 2015-02-27 | 2015-02-27 | Aberdeenshire | 403795 | 11273.18 | 163.19 | 0 | 0 | 0 | 0 | 11436.37 | 0 | 415231.37 | 229318.7788 | [6 empty] | CS11A | 100%
501816 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | Fife | 0 | 0 | 16572.1 | 25925.36 | 0 | 0 | 0 | 42497.46 | 0 | 42497.46 | 148885.7057 | [6 empty] | SG1 | 100%
500915 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2015-10-29 | 2019-05-13 | 2019-05-13 | 2019-05-13 | 2019-05-13 | Aberdeenshire | 0 | 3493.49 | 55289.57 | -19213.4 | 15660.3 | 0 | 0 | 55229.96 | 0 | 55229.96 | 0 | [6 empty] | CM_WSNI | 100%
500645 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS4 | 2015-06-01 | 2015-12-16 | 2015-12-16 | 2019-03-04 | 2018-02-28 | Scottish Water Wide | 0 | 732572.3 | 229609.75 | 272363.53 | 1121444.11 | 0 | 0 | 2355989.69 | 0 | 2355989.69 | 0 | [6 empty] | CM_M&G | 100%
500647 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-03-02 | 2021-03-02 | Scottish Water Wide | 0 | 843078.31 | 857302.45 | 187208.9901 | 548113.9896 | 488536.92 | 475282.05 | 3399522.7097 | 0 | 3399522.7097 | 233661.7532 | [6 empty] | WG2 | 100%
402935 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-08-05 | 2013-08-05 | 2013-07-24 | 2014-06-11 |  | Scottish Water Wide | 589597.82 | 0 | 0 | 3023.37 | 0 | 0 | 0 | 3023.37 | 0 | 592621.19 | 0 | [6 empty] | CM_M&G | 100%
403482 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-10-17 | 2015-06-24 | 2015-06-24 | 2015-06-15 |  | Scottish Water Wide | 392.77 | -154.77 | 0 | 0 | 0 | 0 | 0 | -154.77 | 0 | 238 | 0 | [6 empty] | CM_M&G | 100%
401920 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2011-07-29 | 2012-01-24 | 2012-02-06 | 2016-05-18 | 2016-06-22 | Scottish Water Wide | 2607539.13 | 339301.87 | -307532.11 | 0 | 0 | 0 | 0 | 31769.76 | 0 | 2639308.89 | 0 | [6 empty] | DW1C | 100%
402588 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-21 | 2012-03-21 | 2012-04-04 | 2016-12-19 |  | All East Unitary Authorities | 434110 | 0 | -2641.95 | 97.55 | 0 | 0 | 0 | -2544.4 | 0 | 431565.6 | 0 | [6 empty] | CM_WWI | 100%
503342 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2019-03-05 | 2019-03-05 | Scottish Water Wide | 0 | 0 | 0 | 0 | 165740.98 | 0 | 0 | 165740.98 | 0 | 165740.98 | 0 | [6 empty] | CM_M&G | 100%
502354 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2016-11-03 | 2016-11-03 | 2017-01-04 | 2017-03-23 | 2017-03-23 | Scottish Water Wide | 0 | 0 | 193364 | 4500.4 | 0 | 0 | 0 | 197864.4 | 0 | 197864.4 | 0 | [6 empty] | CM_M&G | 100%
503341 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2019-04-30 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 12170.73 | 486829.27 | 0 | 499000 | 0 | 499000 | 0 | [6 empty] | CM_M&G | 100%
502215 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2017-09-27 | 2017-09-27 | Scottish Water Wide | 0 | 0 | 3748560 | -49337 | 0 | 0 | 0 | 3699223 | 0 | 3699223 | 0 | [6 empty] | CM_M&G | 100%
502686 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS5 | 2017-05-29 | 2017-05-29 | 2017-07-03 | 2018-10-10 | 2018-10-10 | Scottish Water Wide | 0 | 0 | 0 | 3496926.74 | 2384801.83 | 0 | 0 | 5881728.57 | 0 | 5881728.57 | 0 | [6 empty] | CM_M&G | 100%
503142 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2018-03-27 | 2018-03-27 | 2018-04-02 | 2019-05-22 | 2019-05-22 | Scottish Water Wide | 0 | 0 | 0 | 0 | 2111015.02 | 0 | 0 | 2111015.02 | 0 | 2111015.02 | 0 | [6 empty] | CM_M&G | 100%
502198 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2017-09-27 | 2017-09-27 | Scottish Water Wide | 0 | 0 | 6077169 | 187783.02 | -14965.85 | 0 | 0 | 6249986.17 | 0 | 6249986.17 | 0 | [6 empty] | CM_M&G | 100%
502687 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS5 | 2017-05-29 | 2017-05-29 | 2017-07-03 | 2018-11-05 | 2018-11-05 | Scottish Water Wide | 0 | 0 | 0 | 6126142.574 | 2963663.336 | 65679.46 | 0 | 9155485.37 | 0 | 9155485.37 | 0 | [6 empty] | CM_M&G | 100%
503143 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2018-03-27 | 2018-03-27 | 2018-04-02 | 2019-05-22 | 2019-05-22 | Scottish Water Wide | 0 | 0 | 0 | 0 | 5344998 | 0 | 0 | 5344998 | 0 | 5344998 | 0 | [6 empty] | CM_M&G | 100%
502214 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2017-09-27 | 2017-09-27 | Scottish Water Wide | 0 | 0 | 318679 | -24827.13 | 1484.13 | 0 | 0 | 295336 | 0 | 295336 | 0 | [6 empty] | CM_M&G | 100%
502688 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2017-05-22 | 2017-05-22 | 2017-06-01 | 2018-06-19 | 2018-06-19 | Scottish Water Wide | 0 | 0 | 0 | 399843.99 | 48147.78 | 0 | 0 | 447991.77 | 0 | 447991.77 | 0 | [6 empty] | CM_M&G | 100%
503144 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2018-03-26 | 2018-03-26 | 2018-04-02 | 2019-04-30 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 1014947.06 | 0 | 0 | 1014947.06 | 0 | 1014947.06 | 0 | [6 empty] | CM_M&G | 100%
502287 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2017-01-19 | 2017-02-15 | Scottish Water Wide | 0 | 0 | 819534 | 0 | 0 | 0 | 0 | 819534 | 0 | 819534 | 0 | [6 empty] | CM_M&G | 100%
502389 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | 2021-04-15 | 2022-03-01 | 2022-05-20 | 2021-04-15 | 2021-04-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 5548873.44 | 0 | 5548873.44 | 0 | 5548873.44 | 0 | [6 empty] | CM_M&G | 100%
502753 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS5 | 2017-05-22 | 2017-05-22 | 2017-06-01 | 2018-12-19 | 2018-12-19 | Scottish Water Wide | 0 | 0 | 0 | 276867.74 | 47802.5 | 0 | 0 | 324670.24 | 0 | 324670.24 | 0 | [6 empty] | CM_M&G | 100%
503101 | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | General |  | SWD | Exceptional Capital Maintenance | MS2 | 2018-07-09 | 2018-07-09 | 2019-06-19 | 2021-11-26 | 2022-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 2310165.4 | 526150.3 | 300853.06 | 3137168.76 | 377850.11 | 3515018.87 | 396992803.5456 | [6 empty] | SR15_CMP_LATE | 0.05487% | SR15_SED_INFC | 0.3617% | SR15_CMA_MAG | 0.414% | SR15_DWA_SOSI | 2.238% | SR15_SED_SCAP | 2.768% | SR15_DWQ_REL | 3.098% | SR15_CMP_PLAN | 3.561% | SR15_SED_NRSW | 3.925% | SR15_DWA_SRE | 7.922% | SR15_CMA_WSNI | 9.833%
402350 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-03-31 | 2012-03-27 | 2012-10-29 | 2013-11-08 | 2013-11-08 | Glasgow City | 985456 | -7545.57 | 0 | 0 | 0 | 0 | 0 | -7545.57 | 0 | 977910.43 | 25 | [6 empty] | CS15 | 100%
402349 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-03-31 | 2012-03-27 | 2013-03-28 | 2014-01-22 | 2014-01-22 | Glasgow City | 1146942 | 0 | 0 | 0 | -4653.36 | 0 | 0 | -4653.36 | 0 | 1142288.64 | 0 | [6 empty] | CS11A | 50% | CS15 | 50%
034562 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG2 | 100%
034574 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | South Ayrshire | 6.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.96 | 0 | [6 empty] | WG2 | 100%
503238 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2020-02-21 | 2021-08-02 | 2021-11-19 | 2022-11-15 | 2023-02-15 | South Lanarkshire | 0 | 0 | 0 | 0 | 62472.145 | 77735.27 | 115213.82 | 255421.235 | 1618834.16 | 1874255.395 | 0 | [6 empty] | CM_WSNI | 100%
500807 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2015-09-30 | 2017-03-23 | 2017-03-28 | 2018-03-01 | 2018-06-01 | South Lanarkshire | 0 | 20200 | 28708.15 | 112380.5863 | 49259.1037 | 1634.75 | 0 | 212182.59 | 0 | 212182.59 | 220330.7709 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 37.01
501179 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS0 | 2015-10-30 | 2018-11-01 | 2018-11-01 | 2018-11-01 | 2019-02-06 | South Lanarkshire | 0 | 19618 | 139667.88 | 67484 | -71469.17 | 0 | 0 | 155300.71 | 0 | 155300.71 | 641974.3455 | [6 empty] | DW25T | 100%
403741 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-03-19 | 2014-11-17 | 2015-02-03 | 2016-05-10 | 2016-06-08 | Scottish Water Wide | 88085 | 180591 | -36656 | -460.02 | 0 | 0 | 0 | 143474.98 | 0 | 231559.98 | 0 | [6 empty] | CM_WSI | 100%
501276 | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | MSU | 2022-06-01 | 2022-06-01 | 2022-06-01 | 2022-06-01 | 2022-06-01 | South Lanarkshire | 0 | 0 | 500.62 | 5050.75 | 284.22 | 0 | 0 | 5835.59 | 0 | 5835.59 | 0 | [6 empty] | I2S_WI | 100%
501670 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2017-10-27 | 2020-01-20 | 2020-05-05 | 2021-02-26 | 2021-05-28 | South Lanarkshire | 0 | 0 | 7135.19 | 21492.1875 | 93983.1125 | 92924.91 | 704398.62 | 919934.02 | 66919.04 | 986853.06 | 0 | [6 empty] | CM_M&G | 50% | CM_WSI | 50%
501239 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2016-06-29 | 2018-08-31 | 2018-05-29 | 2019-12-02 | 2019-12-03 | South Lanarkshire | 0 | 322649 | -230766 | 261499.239 | 2563825.061 | 776966.69 | 430089.24 | 4124263.23 | 0 | 4124263.23 | 0 | [6 empty] | CM_WSI | 100%
501124 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501121 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS5 | 2016-04-11 | 2018-02-05 | 2018-02-06 | 2018-11-29 | 2018-11-29 | South Lanarkshire | 0 | 55800 | 1291 | 496512 | 1365663.23 | 410.88 | 0 | 1919677.11 | 0 | 1919677.11 | 0 | [6 empty] | CM_WSI | 100%
501240 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501238 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501123 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501122 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-14 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501241 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
502772 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS2 | 2018-02-26 | 2019-03-07 | 2019-08-05 | 2020-08-01 | 2020-11-01 | North Lanarkshire | 0 | 0 | 0 | 28483.234 | 54576.581 | 175289.45 | 105796.52 | 364145.785 | 53710.67 | 417856.455 | 439315.3485 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
501219 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS3 | 2016-03-30 | 2018-10-31 | 2018-12-10 | 2020-03-01 | 2020-05-01 | South Lanarkshire | 0 | 24826.32 | 78122.11 | 61176.984 | 206443.926 | 696670.19 | 126730.27 | 1193969.8 | 2685.37 | 1196655.17 | 0 | [6 empty] | DW25D | 100% | bar: Regulatory Outputs OMG-05
503374 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-05-16 | 2023-03-23 | 2023-07-26 | 2024-01-16 | 2024-04-17 | Fife | 0 | 0 | 0 | 0 | 78298.42 | 1516.8 | 1510.92 | 81326.14 | 65536.22 | 146862.36 | 148885.7057 | [6 empty] | SG1 | 100%
501107 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-09-30 | 2016-12-19 | 2016-12-19 | 2017-01-24 | 2017-01-24 | Dumfries and Galloway | 0 | 600 | 14811.19 | -434 | 0 | 0 | 0 | 14977.19 | 0 | 14977.19 | 9566.9572 | [6 empty] | EC01D | 100%
046326 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-04-09 | 2012-01-17 | 2012-01-25 | 2016-03-10 |  | Dumfries and Galloway | 7453224.62 | 236247.16 | -34829.52 | -22895.13 | 0 | 0 | 0 | 178522.51 | 0 | 7631747.13 | 0 | [6 empty] | CM_WWNI | 100%
046851 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2012-06-05 | 2012-08-13 | 2013-06-14 | 2016-04-01 | Highland | 1475368.72 | -22610.64 | 0 | 0 | 0 | 0 | 0 | -22610.64 | 0 | 1452758.08 | 2603 | [6 empty] | DW23 | 100%
503306 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-05 | 2023-06-27 | 2023-10-26 | 2024-10-21 | 2025-01-21 | Falkirk | 0 | 0 | 0 | 0 | 28174.04 | 23995.32 | 23902.28 | 76071.64 | 68660.12 | 144731.76 | 148885.7057 | [6 empty] | SG1 | 100%
501579 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS1 | 2016-09-05 | 2019-08-12 | 2019-11-25 | 2021-02-26 | 2021-05-28 | Falkirk | 0 | 0 | 134375.2 | 345738.22 | 195180.5 | 3168959.77 | 4102269.73 | 7946523.42 | 270556.01 | 8217079.43 | 0 | [6 empty] | CM_WWNI | 100%
502654 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW1 | 2019-10-30 | 2022-01-07 | 2022-03-31 | 2022-12-30 | 2023-04-03 | North Lanarkshire | 0 | 0 | 0 | 202623.77 | 133376.23 | 54776 | 0 | 390776 | 0 | 390776 | 188843.6893 | [6 empty] | EC01F_ID | 100%
502661 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW1 | 2019-09-16 | 2022-01-07 | 2022-03-31 | 2022-11-01 | 2023-02-01 | North Lanarkshire | 0 | 0 | 0 | 79632.0296 | 80367.9704 | 5640.01 | 0 | 165640.01 | 55113.28 | 220753.29 | 188843.6893 | [6 empty] | EC10B_ID | 100%
502663 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW0 | 2019-09-30 | 2022-01-07 | 2022-03-31 | 2023-04-25 | 2023-07-26 | North Lanarkshire | 0 | 0 | 0 | 132239.8846 | 72760.1154 | 83975.99 | 0 | 288975.99 | 134198.79 | 423174.78 | 377687.3786 | [6 empty] | EC01F_ID | 48.39% | EC10B_ID | 51.61%
502662 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW2 | 2019-06-28 | 2022-01-07 | 2022-03-31 | 2022-12-30 | 2023-04-03 | North Lanarkshire | 0 | 0 | 0 | 105016.3946 | 76983.6054 | 41614.99 | 0 | 223614.99 | 0 | 223614.99 | 188843.6893 | [6 empty] | EC01F_ID | 100%
502363 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW2 | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-07-01 | North Lanarkshire | 0 | 0 | 59085.93 | 35914.07 | 350.5616 | 0 | 0 | 95350.5616 | 0 | 95350.5616 | 188843.6893 | [6 empty] | EC01F_ID | 100%
502664 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW2 | 2019-06-28 | 2022-01-05 | 2022-03-29 | 2022-10-28 | 2023-01-30 | North Lanarkshire | 0 | 0 | 0 | 102613.9171 | 52887.0829 | 5000 | 0 | 160501 | 12511.01 | 173012.01 | 377687.3786 | [6 empty] | EC01F_ID | 48.78% | EC10B_ID | 51.22%
502665 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW2 | 2019-06-28 | 2022-01-05 | 2022-03-29 | 2022-10-28 | 2023-01-30 | North Lanarkshire | 0 | 0 | 0 | 52101.75 | 28898.25 | 9862 | 0 | 90862 | 0 | 90862 | 377687.3786 | [6 empty] | EC01F_ID | 28.57% | EC01B_ID | 71.43%
502666 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW2 | 2019-06-28 | 2021-11-10 | 2022-01-21 | 2022-06-08 | 2022-09-08 | North Lanarkshire | 0 | 0 | 0 | 51897.82 | 35053.18 | 0 | 0 | 86951 | 3999.99 | 90950.99 | 377687.3786 | [6 empty] | EC01F_ID | 47.44% | EC01B_ID | 52.56%
502667 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW2 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-28 | North Lanarkshire | 0 | 0 | 0 | 58533.13 | 23466.87 | 31814 | 0 | 113814 | 0 | 113814 | 377687.3786 | [6 empty] | EC01F_ID | 24.73% | EC01B_ID | 75.27%
502668 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW2 | 2019-06-28 | 2022-01-07 | 2022-03-31 | 2023-08-29 | 2023-11-29 | North Lanarkshire | 0 | 0 | 0 | 136000 | 83000 | 56000 | 0 | 275000 | 0 | 275000 | 188843.6893 | [6 empty] | EC01F_ID | 100%
502655 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW2 | 2019-08-30 | 2022-01-07 | 2022-03-31 | 2023-12-12 | 2024-03-13 | North Lanarkshire | 0 | 0 | 0 | 87081 | 96919 | 12311 | 0 | 196311 | 205000 | 401311 | 377687.3786 | [6 empty] | EC01F_ID | 3.125% | EC10B_ID | 96.88%
502656 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW2 | 2019-06-28 | 2022-01-07 | 2022-03-31 | 2023-08-29 | 2023-11-29 | North Lanarkshire | 0 | 0 | 0 | 93000 | 41000 | 23334 | 0 | 157334 | 447999.97 | 605333.97 | 377687.3786 | [6 empty] | EC01F_ID | 25.68% | EC10B_ID | 74.32%
502364 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW2 | 2019-06-28 | 2022-01-28 | 2022-04-21 | 2023-01-20 | 2023-04-20 | North Lanarkshire | 0 | 0 | 50737.41 | 27262.59 | 67000 | 7999.99 | 0 | 152999.99 | 0 | 152999.99 | 188843.6893 | [6 empty] | EC01B_ID | 100%
502657 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW2 | 2019-08-30 | 2022-01-07 | 2022-03-31 | 2023-12-12 | 2024-03-13 | North Lanarkshire | 0 | 0 | 0 | 237098.765 | 149065.235 | 24640 | 0 | 410804 | 400000.01 | 810804.01 | 377687.3786 | [6 empty] | EC01F_ID | 38.57% | EC10B_ID | 61.43%
502658 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW1 | 2019-08-01 | 2022-01-07 | 2022-03-31 | 2023-12-12 | 2024-03-13 | North Lanarkshire | 0 | 0 | 0 | 75726.175 | 43273.825 | 13102 | 0 | 132102 | 355999.96 | 488101.96 | 377687.3786 | [6 empty] | EC01F_ID | 6.25% | EC10B_ID | 93.75%
502659 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW2 | 2019-06-28 | 2021-11-01 | 2022-01-12 | 2022-05-30 | 2022-08-30 | North Lanarkshire | 0 | 0 | 0 | 85996.9496 | 87003.0504 | 0 | 0 | 173000 | 0 | 173000 | 188843.6893 | [6 empty] | EC01F_ID | 100%
502660 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW1 | 2019-09-09 | 2022-01-07 | 2022-03-31 | 2023-04-26 | 2023-07-27 | South Lanarkshire | 0 | 0 | 0 | 192169.0096 | 141830.9904 | 16367.01 | 0 | 350367.01 | 0 | 350367.01 | 377687.3786 | [6 empty] | EC01F_ID | 10.98% | EC10B_ID | 89.02%
500816 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-08-27 | 2016-06-03 | 2016-06-06 | 2018-06-20 | 2018-06-20 | Glasgow City | 0 | 127000 | 82027.42 | -123027.42 | 4179.422 | 0 | 0 | 90179.422 | 0 | 90179.422 | 144841.4737 | [6 empty] | CS15A | 100%
500495 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-09-17 | 2018-08-30 | 2018-08-30 | 2018-08-30 | 2018-08-30 | South Lanarkshire | 0 | 3426.08 | 42006.07 | 31030.8715 | -76212.702 | 0 | 0 | 250.3195 | 0 | 250.3195 | 0 | [6 empty] | CM_WWNI | 100%
501829 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2021-05-21 | 2022-04-06 | 2022-06-23 | 2022-11-04 | 2023-02-06 | South Lanarkshire | 0 | 0 | 6398.15 | 0 | 0 | 0 | 0 | 6398.15 | 685833.86 | 692232.01 | 0 | [6 empty] | CM_WWI | 100%
502801 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2018-08-30 | 2018-08-31 | 2018-08-31 | 2018-09-03 | 2018-09-03 | South Lanarkshire | 0 | 0 | 0 | 68250.595 | -68249.6 | 0 | 0 | 0.995 | 0 | 0.995 | 3514936.8342 | [6 empty] | EC01B | 50% | EC10B | 50%
402926 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-09-13 | 2013-02-08 | 2013-04-12 | 2016-12-14 |  | Fife | 831253 | 19333 | -34509.55 | 385.125 | 0 | 0 | 0 | -14791.425 | 0 | 816461.575 | 0 | [6 empty] | CM_WWI | 100%
400070 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-10-06 | 2011-10-17 | 2012-02-13 | 2012-10-03 |  | Fife | 452125.42 | 475 | 0 | 0 | 0 | 0 | 0 | 475 | 0 | 452600.42 | 0 | [6 empty] | CM_WWNI | 100%
046330 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-04-29 | 2011-08-29 | 2011-08-26 | 2013-09-23 |  | Falkirk | 1217196.16 | -406.44 | 0 | 0 | 0 | 0 | 0 | -406.44 | 0 | 1216789.72 | 0 | [6 empty] | CM_WWNI | 100%
400514 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-03-31 | 2012-03-20 | 2012-04-30 | 2013-03-25 | 2013-03-25 | Midlothian | 96979 | -126.02 | 0 | 0 | 0 | 0 | 0 | -126.02 | 0 | 96852.98 | 106.8 | [6 empty] | CM_WWI | 40% | CS11A | 60%
501402 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2018-03-30 | 2019-03-12 | 2019-03-25 | 2020-04-01 | 2020-06-01 | North Lanarkshire | 0 | 0 | 0 | 7684.05 | 288020.667 | 1426606.19 | 847127.19 | 2569438.097 | 14349.73 | 2583787.827 | 1876673.0224 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
503412 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | GW0 | 2019-08-30 | 2020-07-20 | 2020-10-19 | 2021-03-01 | 2021-07-01 | North Lanarkshire | 0 | 0 | 0 | 0 | 97009.29 | 256634.9 | 1416310.2 | 1769954.39 | 1349554.85 | 3119509.24 | 536771.841 | [6 empty] | DW5 | 100% | [18 empty] | Regulatory Outputs OMG-06: 83.9
045321 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-10-03 | 2012-10-24 | 2012-12-11 | Argyll and Bute-North Argyll | 185708.62 | 170.38 | 0 | 0 | 0 | 0 | 0 | 170.38 | 0 | 185879 | 0 | [6 empty] | DW13 | 100%
502322 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-09-13 | 2017-04-24 | 2017-05-02 | 2017-05-08 | 2017-05-08 | Argyll and Bute-North Argyll | 0 | 0 | 15221.97 | 1453.01 | 0 | 0 | 0 | 16674.98 | 0 | 16674.98 | 0 | [6 empty] | CM_WSI | 100%
500817 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-08-24 | 2015-12-08 | 2015-12-09 | 2017-09-11 | 2017-09-11 | Glasgow City | 0 | 23668.9 | 30784.26 | 1367.05 | 118.75 | 0 | 0 | 55938.96 | 0 | 55938.96 | 144841.4737 | [6 empty] | CS15A | 100%
030186 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-15 | 2011-09-23 | 2011-09-23 | 2012-03-20 |  | Glasgow City | 731914.11 | 63.12 | 0 | 0 | 0 | 0 | 0 | 63.12 | 0 | 731977.23 | 0 | [6 empty] | CM_WWNI | 100%
503269 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS3 | 2012-10-30 | 2018-12-01 | 2018-12-01 | 2020-12-01 | 2021-03-01 | Glasgow City | 0 | 0 | 0 | 0 | 9452152 | 2338476.48 | 9574373.27 | 21365001.75 | 6796998.26 | 28162000.01 | 10994109.1109 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
502826 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-08-01 | 2018-08-01 | 2018-07-31 | 2018-07-31 | 2018-07-31 | City of Edinburgh | 0 | 0 | 0 | 74702.5 | -48454.2 | 0 | 0 | 26248.3 | 0 | 26248.3 | 148885.7057 | [6 empty] | SG1 | 100%
402643 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2012-07-13 | 2013-01-07 | 2013-03-15 | 2017-12-14 |  | West Dunbartonshire | 510258 | 85000 | 70001 | 310707.775 | 1033.225 | 0 | 0 | 466742 | 0 | 977000 | 0 | [6 empty] | CM_WWNI | 100%
500804 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS2 | 2015-08-27 | 2019-03-29 | 2019-07-01 | 2019-07-01 | 2019-07-29 | Glasgow City | 0 | 75100 | 155575.08 | 97355.1991 | 74943.1009 | 5000.01 | 0 | 407973.39 | 0 | 407973.39 | 144841.4737 | [6 empty] | CS15A | 100%
402620 | Q&S3B | Completion | PFI |  |  | Wastewater |  | SWD | PFI | MS3 | 2012-03-27 | 2013-10-23 | 2013-11-25 | 2019-07-18 |  | West Dunbartonshire | 17774429.59 | 3562731.52 | 1045417.97 | 1711010.83 | 65363.6275 | 286867 | 0 | 6671390.9475 | 0 | 24445820.5375 | 4181829.6853 | [6 empty] | PFI | 100%
402841 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-08-24 | 2013-08-09 | 2013-10-08 | 2015-02-24 |  | West Dunbartonshire | 390289.36 | 1339.4 | -619.9 | 100.88 | 0 | 0 | 0 | 820.38 | 0 | 391109.74 | 0 | [6 empty] | CM_M&G | 100%
503473 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2019-02-13 | 2019-02-13 | 2019-03-06 | 2020-04-08 | 2020-08-26 | Renfrewshire | 0 | 0 | 0 | 0 | 934807.88 | 2502831.5 | 34995.05 | 3472634.43 | 27365.63 | 3500000.06 | 0 | [6 empty] | CM_WWI | 100%
503530 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2019-07-01 | 2019-08-12 | 2019-12-12 | 2021-07-19 | 2021-10-19 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 140566.22 | 221628.95 | 362195.17 | 137804.96 | 500000.13 | 0 | [6 empty] | CM_WWI | 100%
503531 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2019-07-01 | 2019-07-29 | 2019-11-28 | 2021-07-05 | 2021-10-05 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 596759.57 | 886515.66 | 1483275.23 | 516724.76 | 1999999.99 | 0 | [6 empty] | CM_WWI | 100%
503229 | IR18 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-02-28 | 2019-03-25 | 2019-03-25 | 2022-03-01 | 2022-06-01 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 105966.419 | 235061.6 | 198082.19 | 539110.209 | 417707.51 | 956817.719 | 0 | [6 empty] | CM_WWI | 100% | bar: Regulatory Outputs OMG-23
501776 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2021-06-02 | 2022-04-04 | 2022-06-27 | 2023-01-25 | 2023-04-27 | West Dunbartonshire | 0 | 0 | 12538.58 | 17.8 | 0 | 0 | 0 | 12556.38 | 275719.6 | 288275.98 | 0 | [6 empty] | CM_WWI | 100%
501603 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS1 | 2016-07-19 | 2020-05-11 | 2020-07-13 | 2021-05-03 | 2021-08-03 | South Ayrshire | 0 | 0 | 39427.59 | 139582.28 | -24523.99 | 0 | 1637963.68 | 1792449.56 | 528590.92 | 2321040.48 | 0 | [6 empty] | CM_WWNI | 100%
501289 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-10-14 | 2016-10-14 | Dumfries and Galloway | 0 | 0 | 59031.7 | 114.3725 | 36.43 | 0 | 0 | 59182.5025 | 0 | 59182.5025 | 0 | [6 empty] | CM_WWNI | 100%
500124 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS4 | 2015-03-19 | 2016-04-28 | 2016-06-29 | 2019-01-31 | 2019-05-13 | Dumfries and Galloway | 0 | 11549 | 32755.28 | 49515.73 | 35034 | 0 | 0 | 128854.01 | 0 | 128854.01 | 50912.9536 | [6 empty] | EC01G | 7.61% | CS16D | 33.61% | EC01D | 58.78%
503058 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2021-04-01 | 2022-11-23 | 2023-03-16 | 2024-06-18 | 2024-09-18 | Dumfries and Galloway | 0 | 0 | 0 | 27469.326 | 60096.7435 | 3225.49 | 1034.52 | 91826.0795 | 2408999.96 | 2500826.0395 | 0 | [6 empty] | CM_WWNI | 100%
404135 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS3 | 2016-03-31 | 2019-03-28 | 2019-03-29 | 2020-12-01 | 2021-03-01 | Highland | 0 | 0 | 0 | 113265.2 | 680912.36 | 1657274.36 | 1519146.71 | 3970598.63 | 31018.33 | 4001616.96 | 0 |  |  |  |  | 50.25 |  | DW25 | 100% | bar: Regulatory Outputs OMG-03
404102 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWD | OMG180 | MS7 | 2016-03-31 | 2018-01-24 | 2017-12-12 | 2017-12-12 | 2017-12-20 | Highland | 0 | 25960.89 | 102140.32 | 5148.73 | 0 | 0 | 0 | 133249.94 | 0 | 133249.94 | 0 | [6 empty] | DW25 | 100%
402605 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-28 | 2016-02-26 | 2016-03-01 | 2015-08-04 |  | All East Unitary Authorities | 99973 | -39088.42 | 0 | 26.8 | 0 | 0 | 0 | -39061.62 | 0 | 60911.38 | 0 | [6 empty] | CM_M&G | 100%
403658 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2014-01-29 | 2014-09-30 | 2014-09-30 | 2020-01-31 |  | East Renfrewshire | 2061305 | -21500 | -62816.62 | -228033.83 | 105288.86 | 641003.38 | 4753.21 | 438695 | 0 | 2500000 | 0 | [6 empty] | CM_WSI | 100%
501078 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-10-29 | 2016-03-29 | 2016-03-29 | 2017-10-12 | 2017-10-12 | Scottish Water Wide | 0 | 1634947 | -590672.14 | 389651.61 | 0 | 0 | 0 | 1433926.47 | 0 | 1433926.47 | 0 | [6 empty] | CM_M&G | 100%
502788 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-04-16 | 2022-01-17 | 2022-04-11 | 2022-09-09 | 2022-12-12 | Moray | 0 | 0 | 0 | 5739.53 | 3860.47 | 0 | 0 | 9600 | 190400.07 | 200000.07 | 0 | [6 empty] | CM_WSI | 40% | CM_WSNI | 60%
500976 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-02-15 | 2017-01-31 | 2017-01-31 | 2018-03-28 | 2018-03-28 | Scottish Water Wide | 0 | 164128 | 1079965.71 | 82591.67 | 9532.08 | 0 | 0 | 1336217.46 | 0 | 1336217.46 | 0 | [6 empty] | CM_M&G | 100%
501822 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2017-05-30 | 2019-08-12 | 2019-11-18 | 2020-02-20 | 2020-02-21 | East Ayrshire | 0 | 0 | 6296.59 | 1860.82 | 125.79 | 32117.47 | 438.59 | 40839.26 | 0 | 40839.26 | 0 | [6 empty] | CM_WWI | 100%
502629 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-05-05 | 2022-03-28 | 2022-06-08 | 2023-01-09 | 2023-04-11 | East Lothian | 0 | 0 | 18070.09 | 7703.23 | 12626.68 | 0 | 0 | 38400 | 761600.03 | 800000.03 | 0 | [6 empty] | CM_WSI | 100%
502225 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS6 | 2016-06-13 | 2016-08-30 | 2016-09-12 | 2017-01-10 | 2017-05-05 | Scottish Borders | 0 | 0 | 942638.79 | 48186 | 0 | 0 | 0 | 990824.79 | 0 | 990824.79 | 0 | [6 empty] | CM_M&G | 100%
403406 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2013-03-01 | 2013-03-01 | 2013-03-01 | 2013-03-28 | 2013-03-28 | Stirling | 1007399.77 | 32228.23 | 52411 | 14528.786 | 0 | 0 | 0 | 99168.016 | 0 | 1106567.786 | 2947 | [6 empty] | CC1W | 100%
030196 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-02-09 | 2010-11-15 | 2010-11-16 | 2011-07-27 | 2011-09-13 | Falkirk | 503650.63 | 7.5 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 503658.13 | 0 | [6 empty] | EC01A | 26.53% | CM_WWNI | 73.47%
500699 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-06-11 | 2015-08-13 | 2015-08-25 | 2016-04-29 | 2016-04-29 | Argyll and Bute-North Argyll | 0 | 432864 | 578.74 | -892.54 | 0 | 0 | 0 | 432550.2 | 0 | 432550.2 | 0 | [6 empty] | CM_WSI | 100%
036801 | Q&S3A | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-01-30 | 2010-01-26 | 2010-02-05 | 2010-07-21 | 2010-07-21 | Falkirk | 717171.38 | 288.8 | 0 | 0 | 0 | 0 | 0 | 288.8 | 0 | 717460.18 | 0 | [6 empty] | DW9 | 100%
403070 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2012-11-07 | 2014-06-11 | 2014-06-11 | 2016-12-15 |  | Scottish Water Wide | 8318677 | 192753 | 176015.03 | -5005.04 | 0 | 0 | 0 | 363762.99 | 0 | 8682439.99 | 0 | [6 empty] | CM_M&G | 100%
501549 | Q&S4 | Reducing flooding and pollution from sewers | Surface Water |  |  | Wastewater |  | SWD | Surface Water | MS7 | 2015-12-23 | 2015-12-23 | 2015-12-31 | 2017-02-01 | 2017-02-01 | Scottish Water Wide | 0 | 14746 | 18147.06 | -2427.56 | 0 | 0 | 0 | 30465.5 | 0 | 30465.5 | 45130.9791 | [6 empty] | CS15C | 100% | bar: Regulatory Outputs OMG-34
402381 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2011-12-06 | 2012-03-13 | 2012-03-13 | 2014-12-03 |  | Scottish Water Wide | 7392794 | -2824.02 | 0 | 0 | 0 | 0 | 0 | -2824.02 | 0 | 7389969.98 | 0 | [6 empty] | CM_M&G | 100%
503071 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2018-07-12 | 2019-01-21 | 2019-01-21 | 2019-11-01 | 2019-11-04 | Scottish Water Wide | 0 | 0 | 0 | 52065.366 | 4676726.474 | 4854207.39 | 0 | 9582999.23 | 0 | 9582999.23 | 0 |  |  |  |  | 168999.9996 |  | CM_M&G | 100%
034299 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Aberdeen City | 1449470.45 | -8222.3 | 0 | 0 | 0 | 0 | 0 | -8222.3 | 0 | 1441248.15 | 0 | [6 empty] | SG2 | 100%
034283 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Dumfries and Galloway | 1483009.38 | 0 | 0 | 50 | -50 | 0 | 0 | 0 | 0 | 1483009.38 | 0 | [6 empty] | SG2 | 100%
034310 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Fife | 5101908.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5101908.73 | 0 | [6 empty] | SG2 | 100%
034302 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Highland | 3062146.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3062146.64 | 0 | [6 empty] | SG2 | 100%
034295 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | North Lanarkshire | 5552571.17 | 0 | 15245.45 | -15245.45 | 0 | 0 | 0 | 0 | 0 | 5552571.17 | 0 | [6 empty] | SG2 | 100%
034298 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | South Lanarkshire | 4101443.71 | 0 | 0 | 0 | 53.225 | 0 | 0 | 53.225 | 0 | 4101496.935 | 0 | [6 empty] | SG2 | 100%
034261 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Aberdeenshire | 2362342.39 | 0 | 0 | 15 | -15 | 0 | 0 | 0 | 0 | 2362342.39 | 0 | [6 empty] | WG2 | 100%
033782 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Argyll and Bute | 77914.14 | 0 | 723 | 0 | -723 | 0 | 0 | 0 | 0 | 77914.14 | 0 | [6 empty] | WG2 | 100%
033776 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Scottish Borders | 535758.6 | 50.87 | -50.87 | -0.005 | 0.005 | 0 | 0 | 0 | 0 | 535758.6 | 0 | [6 empty] | WG2 | 100%
033777 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Dumfries and Galloway | 532969.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 532969.39 | 0 | [6 empty] | WG2 | 100%
034270 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Falkirk | 942078.55 | 52.84 | -52.84 | 0 | 0 | 0 | 0 | 0 | 0 | 942078.55 | 0 | [6 empty] | WG2 | 100%
034271 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Fife | 1937816.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1937816.48 | 0 | [6 empty] | WG2 | 100%
033786 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Glasgow City | 1679396.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679396.48 | 0 | [6 empty] | WG2 | 100%
034263 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | Highland | 1431260.07 | -233.26 | 0 | 0 | 0 | 0 | 0 | -233.26 | 0 | 1431026.81 | 0 | [6 empty] | WG2 | 100%
033789 | Q&S4 | Supporting economic development | RCC |  |  | Water |  | SWD | RCC | MS7 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2010-04-01 |  | North Lanarkshire | 1247591.02 | 0 | 0 | 0.39 | -0.39 | 0 | 0 | 0 | 0 | 1247591.02 | 0 | [6 empty] | WG2 | 100%
402094 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2011-03-31 | 2011-08-29 | 2011-09-06 | 2016-01-30 |  | Scottish Water Wide | 3436890.58 | 519210.42 | -7982.66 | 0 | 0 | 0 | 0 | 511227.76 | 0 | 3948118.34 | 0 | [6 empty] | QS4EQS | 50% | QS4EQW | 50%
500508 | Q&S4 | Protecting and enhancing the environment | Priority Substances Directive |  |  | Wastewater |  | SWMD | Priority Substances Directive | MS3 | 2015-06-02 | 2015-09-18 | 2015-09-18 | 2020-01-01 | 2020-03-01 | Scottish Water Wide | 0 | 458869 | 681131 | 485000 | 222501.6435 | 244252 | 670748 | 2762501.6435 | 0 | 2762501.6435 | 2951232.6244 | [6 empty] | EC23A | 100% | bar: Regulatory Outputs OMG-25
500706 | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWD | Renewable power | MS5 | 2019-03-31 | 2019-03-31 | 2019-03-31 | 2019-03-01 | 2019-03-01 | Scottish Water Wide | 0 | 366968.14 | 176715.18 | 170867.1225 | 226449.5575 | 127069.75 | 131930.23 | 1199999.98 | 0 | 1199999.98 | 764721.6298 | [6 empty] | I2S_WI | 100% | [18 empty] | Regulatory Outputs OMG-43: 4.227
500666 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2019-07-15 | 2019-07-16 | 2019-07-16 | 2019-07-16 | 2019-07-16 | Dumfries and Galloway | 0 | 79001 | 6405.19 | 30848.9191 | -116254.1091 | 0 | 0 | 1 | 0 | 1 | 229318.7788 | [6 empty] | CS11 | 100%
501569 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS4 | 2016-03-30 | 2016-08-26 | 2016-08-29 | 2019-02-01 | 2019-06-01 | Argyll and Bute-Cowal & Bute | 0 | 65.42 | 1268.97 | 40.43 | 1383.85 | 0 | 0 | 2758.67 | 0 | 2758.67 | 466391.8995 | [6 empty] | DW25D | 21% | DW25T | 79% | bar: Regulatory Outputs OMG-05
502649 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS0 | 2018-02-27 | 2019-11-11 | 2020-03-09 | 2021-09-01 | 2021-12-01 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 38519.49 | 300045.5 | 854971.66 | 1900326.78 | 3093863.43 | 857872.56 | 3951735.99 | 2542948.1521 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
500070 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-02-27 | 2015-04-01 | 2015-04-01 | 2017-06-19 | 2017-06-19 | Scottish Water Wide | 0 | 69516 | 102084.13 | -4846.61 | 0 | 0 | 0 | 166753.52 | 0 | 166753.52 | 0 | [6 empty] | CM_WSI | 100%
500069 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-03-18 | 2015-04-20 | 2015-06-19 | 2021-07-05 | 2021-10-05 | Scottish Water Wide | 0 | 457723 | 416289.3 | 531464.32 | 1726519.73 | 79146.57 | 2.11 | 3211145.03 | 1500.53 | 3212645.56 | 0 | [6 empty] | CM_WSI | 100%
500071 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-02-27 | 2015-03-24 | 2015-03-24 | 2020-05-12 | 2020-05-12 | Scottish Water Wide | 0 | 133771 | 131429 | 112618.74 | 119900.18 | 133018 | 0 | 630736.92 | 0 | 630736.92 | 0 | [6 empty] | CM_WSI | 100%
400799 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-21 | 2010-04-30 | 2010-08-02 | 2015-09-30 |  | Scottish Water Wide | 1949140 | 12539.98 | 0 | 0 | 0 | 0 | 0 | 12539.98 | 0 | 1961679.98 | 0 | [6 empty] | CM_WSI | 100%
502399 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2016-11-29 | 2016-11-29 | 2017-03-15 | 2020-05-12 | 2019-02-01 | Scottish Water Wide | 0 | 0 | 15983.03 | 94168.97 | 135798.905 | 138013 | 0 | 383963.905 | 0 | 383963.905 | 0 | [6 empty] | CM_WSI | 100%
400763 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2011-04-29 | 2015-06-08 |  | Scottish Water Wide | 671126.59 | -1226 | 0 | 0 | 0 | 0 | 0 | -1226 | 0 | 669900.59 | 0 | [6 empty] | CM_WSI | 100%
502836 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-18 | 2027-12-06 | 2028-04-04 | 2029-03-30 | 2029-07-02 | Highland | 0 | 0 | 0 | 21346.13 | 0 | 28653.86 | 0 | 49999.99 | 7949999.9 | 7999999.89 | 148885.7057 | [6 empty] | WG1 | 100%
046833 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-10 | 2011-06-21 | 2011-10-24 | 2011-12-07 | Highland | 40031.2 | 30.72 | 0 | 0 | 0 | 0 | 0 | 30.72 | 0 | 40061.92 | 0 | [6 empty] | DW13 | 100%
403556 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-10-11 | 2014-01-14 | 2014-01-14 | 2015-12-01 |  | Scottish Water Wide | 1439810 | -82934.47 | 0 | 0 | 0 | 0 | 0 | -82934.47 | 0 | 1356875.53 | 0 | [6 empty] | CM_M&G | 100%
503423 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2019-02-07 | 2019-04-29 | 2019-05-08 | 2020-12-24 | 2021-02-26 | Scottish Water Wide | 0 | 0 | 0 | 0 | 43733.65 | 308222.61 | 316543.74 | 668500 | 0 | 668500 | 1567396.4546 | [6 empty] | DW25P_ID | 100%
008488 | Q&S2 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS4 |  |  |  | 2004-03-31 |  | Scottish Water Wide | -7365.25 | 0 | 0 | 0 | 983.96 | 0 | 0 | 983.96 | 0 | -6381.29 | 0 | [6 empty] | WM3 | 100%
045127 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS6 | 2009-03-24 | 2010-09-14 | 2010-10-18 | 2016-11-01 | 2017-03-01 | All West Unitary Authorities | 6251083.65 | 104516.65 | 189117.24 | 68991.88 | 40264.33 | 15000.01 | 0 | 417890.11 | 0 | 6668973.76 | 38317.7586 | [6 empty] | CM_WSI | 38.37% | DW5 | 61.63% | bar: Regulatory Outputs OMG-03
045132 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-05-30 | 2012-09-24 | 2014-10-27 | 2014-12-19 | North Ayrshire | 2638525 | 0 | 583.11 | 0 | 0 | 0 | 0 | 583.11 | 0 | 2639108.11 | 1816.9343 | [6 empty] | CM_WSI | 5.24% | DW5 | 94.76%
045145 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-08-16 | 2011-05-19 | 2011-09-08 | 2012-06-27 | West Dunbartonshire | 224125.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224125.02 | 0 | [6 empty] | DW5 | 100%
045151 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-12-24 | 2011-03-31 | 2015-12-10 | 2015-12-10 | West Dunbartonshire | 2664465.4 | -269374.4 | -1252.74 | -14592.1 | 15588.26 | 0 | 0 | -269630.98 | 0 | 2394834.42 | 94791.2 | [6 empty] | CM_WSI | 30% | DW5 | 70%
404130 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | WINF | Non OMG180 | MS5 | 2015-08-26 | 2016-12-20 | 2017-02-06 | 2018-03-01 | 2019-03-01 | West Dunbartonshire | 0 | 5209 | 117704 | 449809 | -52608.34 | 5797.15 | 0 | 525910.81 | 0 | 525910.81 | 0 | [6 empty] | CM_WSI | 44.56% | DW5 | 55.44% | bar: Regulatory Outputs OMG-03
045155 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-05-23 | 2012-10-15 | 2015-08-01 | 2016-08-01 | Falkirk | 3804649 | 176790 | 17935.94 | -1399.27 | 0 | 0 | 0 | 193326.67 | 0 | 3997975.67 | 218881.5137 | [6 empty] | CM_WSI | 15.35% | DW5 | 84.65% | bar: Regulatory Outputs OMG-03
045160 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-05-31 | 2013-05-13 | 2014-07-24 | 2015-06-23 | North Ayrshire | 1533921.62 | 4112.84 | 35.5 | 0 | 0 | 0 | 0 | 4148.34 | 0 | 1538069.96 | 1394.04 | [6 empty] | CM_WSI | 44.61% | DW5 | 55.39%
045163 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-05-23 | 2012-09-17 | 2016-03-01 | 2017-04-01 | South Lanarkshire | 4236875 | 611992 | 56682.7 | 23881 | -2673.9 | 0 | 0 | 689881.8 | 0 | 4926756.8 | 43297.5711 | [6 empty] | CM_WSI | 32.12% | DW5 | 67.88% | bar: Regulatory Outputs OMG-03
045165 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-05-23 | 2012-08-20 | 2015-03-31 | 2015-03-31 | South Lanarkshire | 1346759.31 | 24793.57 | -39.53 | 0 | 0 | 0 | 0 | 24754.04 | 0 | 1371513.35 | 10808.7555 | [6 empty] | CM_WSI | 41.77% | DW5 | 58.23%
046921 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2010-09-22 | 2010-10-25 | 2011-07-27 | 2013-02-28 | Inverclyde | 1470427 | -4096 | -208733.04 | 0 | 0 | 0 | 0 | -212829.04 | 0 | 1257597.96 | 11674.5885 | [6 empty] | CM_WSI | 20.26% | DW5 | 79.74%
045173 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-09-09 | 2010-09-20 | 2012-05-15 | 2015-03-30 | City of Edinburgh | 770298 | -1421 | 0 | 0 | 0 | 0 | 0 | -1421 | 0 | 768877 | 1245.58 | [6 empty] | CM_WSI | 16.96% | DW5 | 83.04%
045179 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS6 | 2008-05-30 | 2012-05-23 | 2012-10-15 | 2016-12-01 | 2018-03-01 | Stirling | 2271787.36 | 1222345.64 | 847483.74 | 545021.88 | 85549.4365 | 3361.38 | 0 | 2703762.0765 | 0 | 4975549.4365 | 230536.6115 | [6 empty] | DW5 | 45.59% | CM_WSI | 54.41% | bar: Regulatory Outputs OMG-03
046935 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2012-05-21 | 2012-08-06 | 2014-09-17 | 2015-02-17 | South Lanarkshire | 151575 | -550.59 | 0 | 0 | 0 | 0 | 0 | -550.59 | 0 | 151024.41 | 2266.1955 | [6 empty] | DW5 | 43% | CM_WSI | 57%
045186 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-05-30 | 2012-08-20 | 2014-12-01 | 2016-11-30 | Inverclyde | 3419495 | 0 | -32448.31 | 0 | 0 | 0 | 0 | -32448.31 | 0 | 3387046.69 | 362.9285 | [6 empty] | DW5 | 5.929% | CM_WSI | 94.07%
046937 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2010-10-11 | 2011-04-22 | 2017-01-01 | 2017-03-01 | Renfrewshire | 1561928 | 0 | 0.37 | -53466.09 | 0 | 0 | 0 | -53465.72 | 0 | 1508462.28 | 12057.3492 | [6 empty] | DW5 | 43.35% | CM_WSI | 56.65% | bar: Regulatory Outputs OMG-03
046172 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS3 | 2009-03-24 | 2012-10-31 | 2013-05-06 | 2020-05-01 | 2021-03-01 | Orkney Islands | 3792639 | 986828 | 127646.49 | 213229.99 | 10270.64 | 636939.21 | 206549.8 | 2181464.13 | 6500 | 5980603.13 | 475091.8923 | [6 empty] | CM_WSI | 47.96% | DW5 | 52.04% | bar: Regulatory Outputs OMG-03
045197 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2010-09-14 | 2011-04-14 | 2015-03-01 | 2015-12-01 | Shetland Islands | 997307 | 18158 | -57.62 | 0 | 0 | 0 | 0 | 18100.38 | 0 | 1015407.38 | 10352.43 | [6 empty] | CM_WSI | 42% | DW5 | 58% | bar: Regulatory Outputs OMG-03
045200 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2012-10-31 | 2013-02-18 | 2015-08-01 | 2016-02-01 | Aberdeen City | 5033316 | -7124 | -0.16 | -3901.49 | 0 | 0 | 0 | -11025.65 | 0 | 5022290.35 | 95759.638 | [6 empty] | CM_WSI | 26% | DW5 | 74% | bar: Regulatory Outputs OMG-03
045201 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-08-16 | 2011-08-15 | 2013-12-11 | 2014-03-28 | West Lothian | 1698138 | -283.69 | -79.06 | 0 | 0 | 0 | 0 | -362.75 | 0 | 1697775.25 | 1547.52 | [6 empty] | CM_WSI | 38% | DW5 | 62%
045211 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2011-09-30 | 2011-09-30 | 2013-03-29 | 2014-02-17 | Renfrewshire | 3709218.83 | 0.55 | 0 | 0 | 0 | 0 | 0 | 0.55 | 0 | 3709219.38 | 0 | [6 empty] | CM_WSI | 31.93% | DW5 | 68.07%
045217 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-03-24 | 2010-08-16 | 2010-09-06 | 2012-02-23 | 2014-02-17 | Dumfries and Galloway | 3349210.88 | 0 | -96098.51 | 0 | 0 | 0 | 0 | -96098.51 | 0 | 3253112.37 | 0 | [6 empty] | DW5 | 39% | CM_WSI | 61%
046923 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2010-08-16 | 2010-09-27 | 2015-03-24 | 2016-03-31 | Scottish Borders | 4779276 | 45890 | -189436.84 | 5229.5 | 0 | 0 | 0 | -138317.34 | 0 | 4640958.66 | 36476.6721 | [6 empty] | DW5 | 48.81% | CM_WSI | 51.19%
045223 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2010-08-16 | 2011-02-22 | 2013-01-08 | 2014-05-15 | Scottish Borders | 2202529.46 | 0 | 0 | 0 | 34496.31 | 0 | 0 | 34496.31 | 0 | 2237025.77 | 0 | [6 empty] | CM_WSI | 45.67% | DW5 | 54.33%
045228 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2010-10-11 | 2011-01-10 | 2012-12-19 | 2013-03-27 | Moray | 4737473 | -723.66 | 0 | 0 | 0 | 0 | 0 | -723.66 | 0 | 4736749.34 | 980 | [6 empty] | CM_WSI | 23.62% | DW5 | 76.38%
500077 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-09 | 2015-03-25 | 2015-03-25 | 2020-08-03 | 2020-08-03 | Scottish Water Wide | 0 | 280000 | 245000 | 208138 | 241224 | 265949.11 | 0 | 1240311.11 | 0 | 1240311.11 | 0 | [6 empty] | CM_WSI | 100%
500076 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-11 | 2015-03-30 | 2015-03-30 | 2020-07-28 | 2020-07-28 | Scottish Water Wide | 0 | 420000 | 417476.54 | 389816.46 | 430256.8147 | 422893 | 0 | 2080442.8147 | 0 | 2080442.8147 | 0 | [6 empty] | CM_WSI | 100%
500072 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-11 | 2015-03-30 | 2015-03-30 | 2020-08-07 | 2020-08-07 | Scottish Water Wide | 0 | 664230.74 | 835769.26 | 535148 | 912187.63 | 739836.72 | 0 | 3687172.35 | 0 | 3687172.35 | 0 | [6 empty] | CM_WSI | 100%
500073 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-11 | 2015-03-30 | 2015-03-30 | 2020-07-28 | 2020-07-28 | Scottish Water Wide | 0 | 540000 | 610000 | 445035 | 436250 | 455775 | 0 | 2487060 | 0 | 2487060 | 0 | [6 empty] | CM_WSI | 100%
500078 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-02-26 | 2015-03-26 | 2015-03-26 | 2020-07-28 | 2020-07-28 | Scottish Water Wide | 0 | 245000 | 10000 | 46823 | 14527 | 20000 | 0 | 336350 | 0 | 336350 | 0 | [6 empty] | CM_WSI | 100%
501530 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2022-10-17 | 2023-09-08 | 2024-01-12 | 2024-08-28 | 2024-11-28 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 633253 | 633253 | 0 | [6 empty] | CM_WSNI | 100%
046410 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-08-25 | 2011-12-19 | 2011-12-29 | 2011-12-19 |  | Glasgow City | 58082.24 | -517.53 | 0 | 0 | 0 | 0 | 0 | -517.53 | 0 | 57564.71 | 0 | [6 empty] | CM_WSNI | 100%
502929 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2018-05-25 | 2018-05-25 | Scottish Water Wide | 0 | 0 | 0 | 93355.75 | 36953.35 | 0 | 0 | 130309.1 | 0 | 130309.1 | 0 | [6 empty] | CM_M&G | 100%
401215 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-07-15 | 2013-02-28 | 2013-03-20 | 2013-12-03 |  | Shetland Islands | 544688 | -496.83 | 0 | 0 | 0 | 0 | 0 | -496.83 | 0 | 544191.17 | 0 | [6 empty] | CM_WSI | 100%
501049 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2015-10-05 | 2016-09-22 | 2017-03-20 | 2018-03-26 | 2018-03-26 | Aberdeen City | 0 | 22441 | 75432.21 | 205354.85 | 12275.11 | 1125.66 | 1121.3 | 317750.13 | 253.06 | 318003.19 | 0 | [6 empty] | CM_WSI | 100%
400095 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-12-04 | 2012-12-07 | 2013-01-17 | 2013-06-03 | 2013-09-18 | Highland | 295059 | -1471.84 | 0 | 0 | 0 | 0 | 0 | -1471.84 | 0 | 293587.16 | 0 | [6 empty] | EC03B | 100%
502273 | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS0 | 2018-09-17 | 2020-02-17 | 2020-06-03 | 2020-08-01 | 2020-11-01 | Inverclyde | 0 | 0 | 8916.28 | 0 | 12155.73 | 22038.83 | 57425.99 | 100536.83 | 81340.76 | 181877.59 | 0 | [6 empty] | WR1 | 100% | bar: Regulatory Outputs OMG-20
501573 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2017-01-20 | 2017-03-20 | 2017-03-20 | 2020-03-01 | 2020-05-01 | Inverclyde | 0 | 3348.84 | 522.86 | -55.04 | 833.51 | 0 | 0 | 4650.17 | 0 | 4650.17 | 182070.2262 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
045559 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-26 | 2012-06-11 | 2012-08-08 | 2013-03-22 | 2013-03-22 | Stirling | 626942.67 | -9.29 | 0 | 0 | 0 | 0 | 0 | -9.29 | 0 | 626933.38 | 998.3898 | [6 empty] | CM_WWNI | 10% | WQ01 | 90%
500250 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2015-04-20 | 2021-10-25 | 2021-11-08 | 2022-09-27 | 2023-06-19 | Stirling | 0 | 67869 | 102191 | -72633 | 117343.48 | 0 | 0 | 214770.48 | 2835499.77 | 3050270.25 | 0 | [6 empty] | CM_WSI | 100%
502822 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Falkirk | 0 | 0 | 0 | 81094.045 | 931.2 | 0 | 0 | 82025.245 | 0 | 82025.245 | 148885.7057 | [6 empty] | SG1 | 100%
500726 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-09-07 | 2016-03-25 | 2016-06-20 | 2016-09-28 | 2016-09-28 | Fife | 0 | 12476.17 | 91182.83 | 0 | 956.1118 | 0 | 0 | 104615.1118 | 0 | 104615.1118 | 0 | [6 empty] | CM_WWI | 100%
403945 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-10-03 | 2015-06-30 | 2015-06-30 | 2015-06-30 |  | Scottish Water Wide | 246316 | 11479.29 | 0 | 0 | 0 | 0 | 0 | 11479.29 | 0 | 257795.29 | 0 | [6 empty] | CM_M&G | 100%
045324 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-10-03 | 2013-03-18 | 2013-09-06 | Highland | 299550.24 | -1 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 299549.24 | 0 | [6 empty] | DW13 | 100%
401315 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-09-30 | 2012-02-21 | 2012-06-18 | 2015-01-27 | 2015-02-10 | South Ayrshire | 2911721.34 | 5831.36 | 2633.52 | 5 | 0 | 0 | 0 | 8469.88 | 0 | 2920191.22 | 218123.9998 | [6 empty] | CM_WWNI | 19.99% | EC04A | 80.01%
503543 | Q&S4 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWD | Revised Bathing Waters Directive | MSU | 2019-07-01 | 2020-05-18 | 2020-08-14 | 2021-09-14 | 2021-12-15 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 237579.25 | 1760359.02 | 1997938.27 | 1536061.69 | 3533999.96 | 2269817.6904 | [6 empty] | EC16B | 100%
500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS3 | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2020-09-14 | 2020-09-15 | Scottish Water Wide | 0 | 83503.85 | 60196.32 | 58417.5228 | 82781.5972 | 298002.79 | 167097.84 | 749999.92 | 0 | 749999.92 | 639469.8706 | [6 empty] | WR7 | 100%
500056 | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | General |  | SWMD | SOSI | MS3 | 2016-01-12 | 2016-05-18 | 2016-05-20 | 2020-12-14 | 2021-03-22 | Scottish Water Wide | 0 | 55970 | 146030 | 101000 | 104400 | 119331.37 | 147787.87 | 674519.24 | 32480.69 | 706999.93 | 532143.822 | [6 empty] | WG4A | 100%
500669 | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | General |  | SWMD | SOSI | MS7 | 2015-07-15 | 2015-08-31 | 2015-10-05 | 2017-12-06 | 2017-12-06 | Scottish Water Wide | 0 | 117700 | 253028.76 | 479202.4 | 0 | 0 | 0 | 849931.16 | 0 | 849931.16 | 532143.822 | [6 empty] | WG4A | 100%
500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | General |  | SWD | SOSI | MS3 | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2020-12-18 | 2021-03-22 | Scottish Water Wide | 0 | 29053.58 | 9978.47 | 37004.15 | 9049.985 | 90793.05 | 182665.59 | 358544.825 | 13619.1 | 372163.925 | 532143.822 | [6 empty] | WG4A | 100%
502968 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW1 | 2021-06-14 | 2022-04-01 | 2022-06-27 | 2023-01-27 | 2023-05-01 | Perth and Kinross | 0 | 0 | 0 | 8263.624 | 4696.211 | 3142.56 | 3130.38 | 19232.775 | 333833.36 | 353066.135 | 0 | [6 empty] | CM_WWI | 100%
502259 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-19 | 2016-09-29 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | SG1 | 100%
502842 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-18 | 2027-12-06 | 2028-04-04 | 2029-03-30 | 2029-07-02 | Highland | 0 | 0 | 0 | 20930.23 | 2492.6 | 26799.19 | 0 | 50222.02 | 7949999.9 | 8000221.92 | 148885.7057 | [6 empty] | WG1 | 100%
046848 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2011-02-28 | 2011-06-06 | 2013-03-22 | 2013-11-21 | Highland | 768115.59 | 669.83 | 0 | 0 | 0 | 0 | 0 | 669.83 | 0 | 768785.42 | 0 | [6 empty] | DW23 | 100%
502759 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2019-06-05 | 2019-06-05 | 2019-06-05 | 2019-06-05 | 2019-06-05 | Aberdeenshire | 0 | 0 | 0 | 53034.165 | 56265.1475 | 879.74 | 0 | 110179.0525 | 0 | 110179.0525 | 148885.7057 | [6 empty] | SG1 | 100%
502332 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2019-07-08 | 2021-02-25 | 2021-06-02 | 2022-05-12 | 2022-07-06 | Highland | 0 | 0 | 21363.18 | 6387.557 | 25217.764 | 34109.26 | 98619.94 | 185697.701 | 715979.65 | 901677.351 | 148885.7057 | [6 empty] | SG1 | 100%
400738 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-09-21 | 2012-01-23 | 2012-05-04 | 2013-02-20 | 2013-02-20 | Aberdeenshire | 502604 | -5891.95 | 0 | 0 | 0 | 0 | 0 | -5891.95 | 0 | 496712.05 | 0 | [6 empty] | CM_WWNI | 14.6% | SG1 | 85.4%
403911 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2014-10-15 | 2014-10-15 | 2014-10-15 | 2016-09-08 | 2016-09-08 | Aberdeenshire | 1165662.55 | 0 | 1601.53 | 0 | 0 | 0 | 0 | 1601.53 | 0 | 1167264.08 | 0 | [6 empty] | WG5 | 100%
500679 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS5 | 2019-07-01 | 2019-07-01 | 2019-07-08 | 2019-01-21 | 2019-01-21 | Stirling | 0 | 121951 | -28962.9 | 26026.611 | -119013.711 | 0 | 0 | 1 | 0 | 1 | 45708.959 | [6 empty] | CS11 | 100%
503526 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MSU | 2021-06-15 | 2022-11-28 | 2023-03-31 | 2024-04-25 | 2024-07-26 | Stirling | 0 | 0 | 0 | 0 | 59441.86 | 72711.57 | 57689.97 | 189843.4 | 869598.26 | 1059441.66 | 148885.7057 | [6 empty] | SG1 | 100%
503278 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-17 | 2023-05-31 | 2023-10-03 | 2024-09-30 | 2024-12-31 | Moray | 0 | 0 | 0 | 0 | 78150.66 | 0 | 36322.97 | 114473.63 | 29256.25 | 143729.88 | 148885.7057 | [6 empty] | SG1 | 100%
501355 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2016-02-22 | 2016-10-13 | 2016-10-10 | 2016-09-28 | 2016-09-28 | Moray | 0 | 378.72 | 3835.28 | -115.21 | 0 | 0 | 0 | 4098.79 | 0 | 4098.79 | 0 | [6 empty] | CM_WWI | 100%
501716 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2017-03-29 | 2018-08-28 | 2018-09-24 | 2019-06-14 | 2019-06-17 | Glasgow City | 0 | 0 | 4171 | 16019 | 147347 | 22052.86 | 1075.15 | 190665.01 | 0 | 190665.01 | 0 | [6 empty] | CM_WWI | 100%
502901 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS2 | 2018-08-23 | 2018-02-27 | 2019-06-14 | 2019-08-12 | 2019-10-29 | Dumfries and Galloway | 0 | 0 | 0 | 17156.644 | 90581.2505 | 92218.31 | 0 | 199956.2045 | 0 | 199956.2045 | 148885.7057 | [6 empty] | SG1 | 100%
500924 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-27 | 2017-08-11 | 2017-08-11 | 2017-07-18 | 2017-07-18 | Dumfries and Galloway | 0 | 7000 | 1000 | -897 | 0 | 0 | 0 | 7103 | 0 | 7103 | 144841.4737 | [6 empty] | CS15A | 100%
502218 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2016-09-29 | 2016-09-29 | 2017-03-07 | 2019-05-29 | 2019-05-30 | Dumfries and Galloway | 0 | 0 | 23282.36 | 29.76 | 0 | 330687.88 | 0 | 354000 | 0 | 354000 | 0 | [6 empty] | CM_WWNI | 100%
502962 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2018-04-20 | 2018-04-20 | 2018-08-23 | 2020-01-03 | 2020-01-03 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 179111.53 | 146789.27 | 26171.98 | 352072.78 | 1833.35 | 353906.13 | 0 | [6 empty] | CM_WWNI | 100%
402035 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2011-05-26 | 2012-12-19 | 2013-01-21 | 2014-04-30 | 2014-04-30 | East Lothian | 1655701.16 | 2080.84 | -426.2 | 0 | 0 | 0 | 0 | 1654.64 | 0 | 1657355.8 | 0 | [6 empty] | CM_WSNI | 50% | WG5 | 50%
502331 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2020-06-11 | 2021-11-29 | 2022-03-23 | 2023-03-16 | 2023-06-16 | East Lothian | 0 | 0 | 31014.87 | 6183.265 | 3814.706 | 13199.57 | 195450.64 | 249663.051 | 2750691.95 | 3000355.001 | 148885.7057 | [6 empty] | SG1 | 100%
503171 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2018-07-31 | 2018-07-31 | 2018-08-20 | 2018-09-28 | 2018-09-28 | East Lothian | 0 | 0 | 0 | 0 | 302841.12 | 0 | 0 | 302841.12 | 0 | 302841.12 | 0 | [6 empty] | CM_WWNI | 100%
502379 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2016-12-22 | 2018-03-26 | 2018-05-07 | 2020-04-07 | 2020-04-08 | Stirling | 0 | 0 | 6537.58 | 19236.197 | 85288.763 | 45169.83 | 6771.4 | 163003.77 | 12.18 | 163015.95 | 0 | [6 empty] | CM_WSNI | 100%
500237 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-09-27 | 2016-09-27 | 2016-09-27 | 2016-09-05 | 2016-09-05 | Stirling | 0 | 41093.15 | 80.7 | 0 | 0 | 0 | 0 | 41173.85 | 0 | 41173.85 | 148885.7057 | [6 empty] | SG1 | 100%
502344 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-10-31 | 2018-11-21 | 2018-11-23 | 2018-11-26 | 2018-11-26 | Dundee City | 0 | 0 | 13271.03 | 42513.89 | 6501.5315 | 0 | 0 | 62286.4515 | 0 | 62286.4515 | 0 | [6 empty] | CM_WWI | 100%
403257 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-01-18 | 2017-01-10 | 2017-01-16 | 2017-01-17 |  | Dundee City | 29690 | 12840 | 3638.04 | 0 | 0 | 0 | 0 | 16478.04 | 0 | 46168.04 | 0 | [6 empty] | CM_WWI | 100%
402478 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-06-28 | 2013-01-11 | 2013-01-11 | 2015-07-17 | 2015-08-31 | Scottish Water Wide | 1219702 | 22503 | 35819.6 | 0 | -1645.26 | 0 | 0 | 56677.34 | 0 | 1276379.34 | 116933.9999 | [6 empty] | CS16S | 100%
503403 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2021-05-28 | 2022-03-10 | 2022-05-27 | 2022-12-29 | 2023-03-31 | Dundee City | 0 | 0 | 0 | 0 | 10562.95 | 0 | 0 | 10562.95 | 146947.83 | 157510.78 | 0 | [6 empty] | CM_WWI | 100%
502429 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-05-26 | 2017-05-26 | 2017-05-26 | 2017-05-12 | 2017-05-12 | Dundee City | 0 | 0 | 4019 | 2880.01 | 35.22 | 0 | 0 | 6934.23 | 0 | 6934.23 | 0 | [6 empty] | CM_WWI | 100%
030238 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-09 | 2010-12-21 | 2011-09-19 | 2012-05-10 | 2012-05-31 | Aberdeenshire | 542444.18 | 1780.2 | 0 | 0 | 0 | 0 | 0 | 1780.2 | 0 | 544224.38 | 0 | [6 empty] | CM_WWNI | 100%
046384 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2009-08-14 | 2011-03-02 | 2011-03-11 | 2012-10-15 | 2012-12-10 | Fife | 3199346 | -7318.43 | 0 | 0 | 0 | 0 | 0 | -7318.43 | 0 | 3192027.57 | 0 | [6 empty] | WG5 | 100%
502372 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2016-11-25 | 2017-01-31 | 2017-02-27 | 2017-11-24 | 2017-11-24 | Fife | 0 | 0 | 995828.08 | 1962781.3725 | 153489.4575 | 0 | 20487.95 | 3132586.86 | 0 | 3132586.86 | 0 |  |  |  |  | 57960 |  | CM_WWNI | 100%
046746 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-01 | 2011-10-18 | 2011-10-18 | 2012-03-23 | 2012-03-31 | Fife | 759944.01 | 620.39 | 0 | 0 | 0 | 0 | 0 | 620.39 | 0 | 760564.4 | 0 | [6 empty] | EC06 | 100%
502949 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS3 | 2018-01-10 | 2018-01-10 | 2018-05-31 | 2020-06-30 | 2020-07-01 | Fife | 0 | 0 | 0 | 73140.19 | 420008.805 | 174540 | 450311 | 1117999.995 | 0 | 1117999.995 | 0 | [6 empty] | SG5 | 100%
500965 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-10-05 | 2018-08-31 | 2018-08-31 | 2020-01-28 | 2020-01-29 | Fife | 0 | 53894.37 | 177451.74 | 173730.92 | 550048.92 | 1461086.79 | 31432.64 | 2447645.38 | 12692.76 | 2460338.14 | 0 |  |  |  |  | 35000 |  | CM_WWNI | 100%
503213 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-12-20 | 2023-06-09 | 2023-10-03 | 2024-09-27 | 2024-12-30 | Fife | 0 | 0 | 0 | 0 | 15513.66 | 23111.63 | 33227.78 | 71853.07 | 71513.42 | 143366.49 | 148885.7057 | [6 empty] | SG1 | 100%
045546 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-29 | 2011-03-24 | 2011-06-27 | 2012-03-23 | 2012-03-27 | Perth and Kinross | 505350.33 | 30.72 | 0 | 0 | 0 | 0 | 0 | 30.72 | 0 | 505381.05 | 0 | [6 empty] | CM_WWNI | 21.67% | WQ01 | 78.33%
502910 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS3 | 2017-11-14 | 2017-11-14 | 2017-12-01 | 2019-07-29 | 2019-07-29 | East Ayrshire | 0 | 0 | 0 | 19364.49 | 0 | 276635.51 | 0 | 296000 | 0 | 296000 | 587726.5342 | [6 empty] | WG5 | 100%
404000 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS1 | 2015-03-03 | 2019-06-03 | 2019-07-29 | 2020-02-26 | 2020-05-28 | Highland | 509.68 | 131402.32 | 44109 | 3327 | 134638 | 3175889.55 | 123788.08 | 3613153.95 | 1336.43 | 3615000.06 | 0 | [6 empty] | CM_WWNI | 100%
500812 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2021-09-16 | 2023-05-10 | 2023-09-12 | 2025-04-07 | 2025-07-08 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79662.07 | 79662.07 | 0 | [6 empty] | CM_WSI | 100%
503375 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-05-09 | 2023-03-16 | 2023-07-19 | 2024-01-09 | 2024-04-10 | Perth and Kinross | 0 | 0 | 0 | 0 | 77822.42 | 1457.82 | 1452.17 | 80732.41 | 66836.28 | 147568.69 | 148885.7057 | [6 empty] | SG1 | 100%
501271 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS4 | 2015-03-31 | 2016-07-29 | 2016-08-18 | 2019-03-27 | 2019-08-30 | North Lanarkshire | 0 | 20938 | 185376 | 132088 | 74776 | 42486.01 | 0 | 455664.01 | 0 | 455664.01 | 288365.2949 | [6 empty] | EC01G | 0.4899% | CS16D | 99.51%
030241 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-24 | 2011-06-28 | 2011-08-23 | 2013-12-09 | 2014-01-14 | North Lanarkshire | 11639043.34 | -13327.86 | 555.62 | 0 | 0 | 0 | 0 | -12772.24 | 0 | 11626271.1 | 274451.0615 | [6 empty] | CM_WWNI | 2.952% | SG1 | 6.868% | EC10A | 23.96% | EC01A | 32.93% | EC04A | 33.29%
500128 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2015-09-27 | 2015-11-02 | 2017-06-29 | 2017-07-21 | Argyll and Bute-Cowal & Bute | 0 | 96713 | 138490.05 | 34186.35 | 123.84 | 0 | 0 | 269513.24 | 0 | 269513.24 | 72474.3726 | [6 empty] | CS11 | 42.57% | CS16D | 57.43%
503558 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2019-05-01 | 2019-06-03 | 2019-09-05 | 2020-06-30 | 2020-09-30 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 176706.73 | 121056.96 | 297763.69 | 2236.36 | 300000.05 | 0 | [6 empty] | CM_M&G | 100%
500130 | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-19 | 2015-09-27 | 2017-03-01 | 2017-04-28 | 2017-04-28 | Dumfries and Galloway | 0 | 15635 | -2752.89 | -2772.35 | 0 | 0 | 0 | 10109.76 | 0 | 10109.76 | 72474.3726 | [6 empty] | CS11 | 100%
502628 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-18 | 2024-12-17 | 2025-02-20 | 2026-01-29 | 2026-05-01 | Highland | 0 | 0 | 20930.23 | 457.49 | 2229.43 | 11724.33 | 11678.9 | 47020.38 | 7953499.7 | 8000520.08 | 148885.7057 | [6 empty] | WG1 | 100%
500745 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2019-04-29 | 2019-04-29 | 2019-04-29 | 2019-05-03 | 2019-05-03 | Perth and Kinross | 0 | 23000 | 26411.54 | 20558.2475 | 312.2625 | 0 | 0 | 70282.05 | 0 | 70282.05 | 229318.7788 | [6 empty] | CS11 | 100%
500730 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2019-11-19 | 2020-08-10 | 2020-11-02 | 2021-05-20 | 2021-08-20 | Aberdeenshire | 0 | 22957.9 | 45941.32 | 44775.9825 | 6238.4985 | 8232.4 | 17523.15 | 145669.251 | 2451.07 | 148120.321 | 148885.7057 | [6 empty] | SG1 | 100%
500578 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS5 | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2016-12-19 | 2017-07-31 | Scottish Water Wide | 0 | 702341 | 483956.81 | 514143.506 | 217874.03 | 0 | 0 | 1918315.346 | 0 | 1918315.346 | 240603.2951 | [6 empty] | DW5A | 100%
404122 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2016-09-08 | 2017-01-18 | Aberdeen City | 0 | 386989.63 | 114122.16 | 0 | 0 | 0 | 0 | 501111.79 | 0 | 501111.79 | 0 | [6 empty] | WG5 | 100%
502563 | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWMD | WFD | MS0 | 2018-10-26 | 2020-01-20 | 2020-05-11 | 2020-11-01 | 2021-02-01 | East Lothian | 0 | 0 | 15550 | 5069.87 | 8271.7 | 95398.04 | 90933.04 | 215222.65 | 15146.33 | 230368.98 | 26321.4575 | [6 empty] | WR2A | 100% | bar: Regulatory Outputs OMG-20
500474 | Q&S4 | Climate Change | Climate Change |  |  | Wastewater |  | SWD | Climate Change | MS5 | 2015-04-30 | 2015-07-22 | 2015-07-27 | 2017-01-31 | 2017-01-31 | Scottish Water Wide | 0 | 56700 | 73300 | 0 | -5639.04 | 6993 | 0 | 131353.96 | 0 | 131353.96 | 34274.2748 | [6 empty] | CC3S | 100%
404100 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | General |  | SWD | Water Non infrastructure | MS7 | 2015-01-27 | 2015-02-26 | 2015-02-26 | 2016-11-03 | 2016-11-03 | Scottish Water Wide | 769247 | 301073 | 1409.55 | 0 | 0 | 0 | 0 | 302482.55 | 0 | 1071729.55 | 0 | [6 empty] | WSNI | 50% | WWNI | 50%
403745 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2014-03-17 | 2016-02-17 | 2016-03-07 | 2016-03-01 | 2016-04-01 | East Renfrewshire | 2769.81 | 9020.77 | 8476.42 | -55.2 | -1158.8633 | 0 | 0 | 16283.1267 | 0 | 19052.9367 | 383035.5326 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
500659 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW1 | 2020-02-28 | 2020-04-08 | 2020-04-08 | 2020-04-08 | 2020-04-08 | City of Edinburgh | 0 | 27200 | 30185.26 | 44114.74 | 51500 | 71486 | 514.02 | 225000.02 | 0 | 225000.02 | 1243653.368 | [6 empty] | CS11 | 100%
500661 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW0 | 2019-09-06 | 2020-10-05 | 2020-12-10 | 2021-09-21 | 2021-12-14 | City of Edinburgh | 0 | 30125 | 36128.94 | 23746.06 | 133538.6695 | 153268.8 | 897031.1 | 1273838.5695 | 1285864.16 | 2559702.7295 | 0 | [6 empty] | CS11 | 100%
500634 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS5 | 2015-06-29 | 2017-09-27 | 2017-10-08 | 2018-08-30 | 2018-08-30 | Scottish Water Wide | 0 | 339906.11 | 13031.89 | 2677684 | 287101 | 0 | 2250 | 3319973 | 0 | 3319973 | 229318.7788 | [6 empty] | CS11A | 100%
501114 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS0 | 2017-10-17 | 2019-05-20 | 2019-05-20 | 2019-05-20 | 2019-05-06 | City of Edinburgh | 0 | 227849 | 40991.89 | -146750.84 | 707.42 | 0 | 0 | 122797.47 | 0 | 122797.47 | 229318.7788 | [6 empty] | CS11 | 100%
500299 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2019-04-01 | 2020-09-21 | 2020-12-07 | 2021-09-03 | 2021-11-30 | West Lothian | 0 | 51910 | 50307 | 29816.1491 | 39466.8509 | 4611.89 | 461620.78 | 637732.67 | 656879.17 | 1294611.84 | 374160.2525 | [6 empty] | CS11 | 34.85% | CS15A | 65.15%
500667 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-01-17 | 2019-03-28 | 2019-03-28 | 2019-01-16 | 2019-01-16 | Falkirk | 0 | 70514 | 55002.86 | 33324.1101 | -157983.8701 | 0 | 0 | 857.1 | 0 | 857.1 | 229318.7788 | [6 empty] | CS11 | 100%
500995 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-10-20 | 2018-03-27 | 2018-03-27 | 2018-02-13 | 2018-02-13 | Falkirk | 0 | 22430 | 41053.04 | 14661.866 | 293.388 | 0 | 0 | 78438.294 | 0 | 78438.294 | 229318.7788 | [6 empty] | CS11 | 100%
500665 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS0 | 2018-06-13 | 2019-10-07 | 2020-01-13 | 2021-03-04 | 2021-05-27 | Falkirk | 0 | 42857 | 31078.83 | 18077.17 | 204675 | 422434.99 | 847779.86 | 1566902.85 | 55201.06 | 1622103.91 | 457110.9522 | [6 empty] | CS11 | 100%
500680 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW2 | 2021-03-01 | 2022-01-11 | 2022-03-25 | 2022-12-29 | 2023-03-29 | Falkirk | 0 | 107555 | -6059.86 | 15504.86 | 26000 | 0 | 8466.27 | 151466.27 | 848533.69 | 999999.96 | 710679.7917 | [6 empty] | CS11 | 100%
501118 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS5 | 2019-04-08 | 2019-04-11 | 2019-04-11 | 2018-02-27 | 2018-02-27 | Falkirk | 0 | 35985 | 33299.51 | 22502.49 | -91786.01 | 0 | 0 | 0.99 | 0 | 0.99 | 229318.7788 | [6 empty] | CS11 | 100%
501541 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS5 | 2019-05-02 | 2019-05-13 | 2019-05-13 | 2019-03-28 | 2019-03-28 | Falkirk | 0 | 21930 | 4421.24 | 1506.36 | -27856.6 | 0 | 0 | 1 | 0 | 1 | 229318.7788 | [6 empty] | CS11 | 100%
503327 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2019-11-04 | 2020-11-02 | 2021-01-13 | 2021-08-24 | 2021-11-24 | Fife | 0 | 0 | 0 | 0 | 123324.23 | 117208.84 | 314773.93 | 555307 | 465596.23 | 1020903.23 | 240495.8008 | [6 empty] | CS11A | 100%
500996 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2017-09-22 | 2018-02-22 | 2018-02-23 | 2018-02-22 | 2018-02-22 | Fife | 0 | 24530 | 29007.06 | 5463.44 | -58904.42 | 0 | 0 | 96.08 | 0 | 96.08 | 229318.7788 | [6 empty] | CS11 | 100%
500059 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS7 | 2015-10-07 | 2018-03-27 | 2018-03-27 | 2018-03-28 | 2018-03-28 | Fife | 0 | 83434 | 58219.13 | 70933.87 | 89904.4623 | 0 | 0 | 302491.4623 | 0 | 302491.4623 | 696606.1204 | [6 empty] | CS11 | 100%
501117 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS0 | 2017-09-26 | 2019-12-16 | 2019-12-23 | 2019-12-23 | 2019-12-09 | Angus | 0 | 99657 | 35295.04 | 19667.17 | -154452.66 | 0 | 0 | 166.55 | 0 | 166.55 | 229318.7788 | [6 empty] | CS11 | 100%
502362 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-07-17 | 2021-06-11 | 2021-08-16 | 2021-09-28 | 2021-12-29 | Fife | 0 | 0 | 0 | 0 | 44000 | 42174.05 | 117720.49 | 203894.54 | 396105.54 | 600000.08 | 240495.8008 | [6 empty] | CS11A | 100%
501190 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-05-29 | 2019-03-19 | 2019-03-19 | 2019-01-21 | 2019-01-21 | Fife | 0 | 22430 | 24592.69 | 17977.31 | 1495.9475 | 0 | 0 | 66495.9475 | 0 | 66495.9475 | 229318.7788 | [6 empty] | CS11 | 100%
502349 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-10-12 | 2021-06-28 | 2021-07-20 | 2021-08-23 | 2021-11-23 | Fife | 0 | 0 | 0 | 0 | 44000 | 34756.38 | 105444.39 | 184200.77 | 715799.23 | 900000 | 240495.8008 | [6 empty] | CS11A | 100%
501019 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS0 | 2018-10-26 | 2020-04-06 | 2020-07-07 | 2021-04-27 | 2021-07-30 | Fife | 0 | 21930 | 61223.86 | 29097.8866 | 140478.137 | 131611.74 | 495113.92 | 879455.5436 | 77847.4 | 957302.9436 | 229318.7788 | [6 empty] | CS11 | 100%
500696 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-10-17 | 2018-04-10 | 2018-02-06 | 2018-02-06 | 2018-02-06 | City of Edinburgh | 0 | 37390 | 29380.72 | -66770.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CS11 | 100%
500300 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-10-17 | 2018-12-17 | 2018-12-17 | 2018-07-05 | 2018-07-05 | City of Edinburgh | 0 | 30000 | 66063.67 | 24936.33 | -120999 | 0 | 0 | 1 | 0 | 1 | 229318.7788 | [6 empty] | CS11 | 100%
503333 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-07-20 | 2021-05-31 | 2021-07-28 | 2022-04-19 | 2022-07-20 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 49000 | 70892.77 | 74627.24 | 194520.01 | 405480.01 | 600000.02 | 240495.8008 | [6 empty] | CS11A | 100%
500997 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS5 | 2019-05-07 | 2019-05-13 | 2019-05-13 | 2019-02-26 | 2019-02-26 | Falkirk | 0 | 21930 | 26959.06 | 58110.94 | 26468.6985 | 0 | 0 | 133468.6985 | 0 | 133468.6985 | 229318.7788 | [6 empty] | CS11 | 100%
500792 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS6 | 2015-10-01 | 2016-07-20 | 2016-10-24 | 2017-03-30 | 2017-03-30 | Aberdeenshire | 0 | 95302.39 | 474632.61 | 61373 | 11346.3694 | 0 | 0 | 642654.3694 | 0 | 642654.3694 | 229318.7788 | [6 empty] | CS11 | 100%
500658 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW2 | 2019-07-01 | 2019-07-05 | 2019-07-05 | 2019-07-05 | 2019-07-05 | City of Edinburgh | 0 | 36500 | 29973.22 | 22526.78 | -83089.49 | 0 | 0 | 5910.51 | 0 | 5910.51 | 435919.2231 | [6 empty] | CS11 | 100%
500657 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS6 | 2017-03-31 | 2017-07-21 | 2017-07-24 | 2017-11-15 | 2017-11-15 | City of Edinburgh | 0 | 33500 | 43336.73 | 101790.47 | 0 | 0 | 0 | 178627.2 | 0 | 178627.2 | 681001.6661 | [6 empty] | CS11 | 100%
500131 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2015-09-28 | 2015-11-02 | 2016-12-01 | 2017-07-01 | Dumfries and Galloway | 0 | 48451 | 48679.75 | 243.66 | 61.92 | 0 | 0 | 97436.33 | 0 | 97436.33 | 72474.3726 | [6 empty] | CS11 | 46.39% | CS16D | 53.61% | bar: Regulatory Outputs OMG-22
030247 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-06-09 | 2010-11-16 | 2011-03-31 | 2015-06-02 | 2015-06-02 | East Renfrewshire | 2191314.21 | 151832 | -27667.31 | 1973.27 | 0 | 0 | 0 | 126137.96 | 0 | 2317452.17 | 0 | [6 empty] | CM_WWNI | 100%
500859 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS5 | 2016-08-19 | 2017-07-25 | 2018-03-26 | 2018-06-01 | 2018-12-01 | Highland | 0 | 830.84 | 889.12 | 10545.98 | 31627.31 | 5000 | 0 | 48893.25 | 0 | 48893.25 | 33448.3301 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 12.6
046834 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-05-23 | 2011-10-24 | 2011-12-07 | Highland | 36466.91 | 1.25 | 0 | 0 | 0 | 0 | 0 | 1.25 | 0 | 36468.16 | 0 | [6 empty] | DW13 | 100%
502620 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-03 | 2024-12-02 | 2025-02-05 | 2026-01-14 | 2026-04-16 | Highland | 0 | 0 | 20930.23 | 291.13 | 2591.75 | 11937.66 | 11891.39 | 47642.16 | 7953018.01 | 8000660.17 | 148885.7057 | [6 empty] | WG1 | 100%
402503 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-02-02 | 2012-10-30 | 2012-11-19 | 2013-12-10 | 2013-12-10 | Stirling | 506565 | -5027.11 | 0 | 0 | 0 | 0 | 0 | -5027.11 | 0 | 501537.89 | 0 | [6 empty] | CM_WSI | 100%
402959 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-09-28 | 2015-02-10 | 2015-02-16 | 2015-05-22 | 2015-05-22 | East Dunbartonshire | 255590 | 105419.3 | 4987.11 | -4252.11 | 0 | 0 | 0 | 106154.3 | 0 | 361744.3 | 229318.7788 | [6 empty] | CS11 | 100%
501500 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS3 | 2016-04-18 | 2018-09-26 | 2018-11-26 | 2020-01-07 | 2020-04-07 | Scottish Borders | 0 | 0 | 175824.43 | 128158.76 | 244937.45 | 257367.86 | 29276.98 | 835565.48 | 20255.6 | 855821.08 | 148885.7057 |  |  |  |  | 16719.9997 |  | SG1 | 100%
501592 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-06-09 | 2018-09-27 | 2018-11-26 | 2020-09-23 | 2020-12-16 | Scottish Borders | 0 | 0 | 75107.07 | 346589.02 | 538459.69 | 938818.2 | 266470.63 | 2165444.61 | 17203.32 | 2182647.93 | 0 |  |  |  |  | 16719.9996 |  | CM_WWNI | 100%
502426 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS6 | 2017-06-19 | 2017-09-18 | 2017-09-21 | 2018-03-01 | 2018-03-01 | Scottish Borders | 0 | 0 | 3869.46 | 32462.3 | 23138.1523 | 0 | 0 | 59469.9123 | 0 | 59469.9123 | 30795.6344 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
502640 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2019-05-30 | 2020-05-18 | 2020-09-08 | 2021-01-25 | 2021-04-27 | Scottish Water Wide | 0 | 0 | 42118.71 | 120870.69 | -72368.278 | 0 | 0 | 90621.122 | 0 | 90621.122 | 148885.7057 | [6 empty] | SG1 | 100%
502930 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS0 | 2012-09-17 | 2019-11-04 | 2020-02-10 | 2020-09-01 | 2020-12-01 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 11714.065 | 100753.935 | 178062.97 | 284584.53 | 575115.5 | 4884.48 | 579999.98 | 454335.6035 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
501316 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2016-05-31 | 2018-07-20 | 2018-10-15 | 2019-12-19 | 2020-04-03 | Scottish Water Wide | 0 | 0 | 55664 | 107649 | 1636959 | 74906.99 | 2399.93 | 1877578.92 | 0.07 | 1877578.99 | 0 | [6 empty] | CM_WWNI | 100%
500923 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2017-02-15 | 2017-02-15 | 2017-02-07 | 2017-02-15 | East Ayrshire | 0 | 5000 | 1687.39 | 35.36 | 0 | 0 | 0 | 6722.75 | 0 | 6722.75 | 144841.4737 | [6 empty] | CS15A | 100%
501586 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2016-07-19 | 2022-02-09 | 2022-04-06 | 2022-07-11 | 2022-10-11 | Fife | 0 | 0 | 11799 | -8628.34 | 0 | 0 | 0 | 3170.66 | 104630.34 | 107801 | 0 | [6 empty] | CM_WWI | 100%
500132 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS5 | 2015-03-20 | 2015-12-22 | 2016-03-22 | 2018-05-01 | 2018-07-01 | West Lothian | 0 | 68167 | 328852.05 | 97035.32 | -1248 | 11971.15 | 0 | 504777.52 | 0 | 504777.52 | 72474.3726 | [6 empty] | CS11 | 17.08% | CS16D | 82.92% | bar: Regulatory Outputs OMG-22
502791 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2021-04-16 | 2022-02-28 | 2022-05-25 | 2022-12-20 | 2023-03-22 | East Lothian | 0 | 0 | 0 | 31400 | 31600 | 0 | 0 | 63000 | 475780.03 | 538780.03 | 0 | [6 empty] | CM_WSI | 100%
400076 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-10-06 | 2011-07-28 | 2011-08-22 | 2013-02-20 | 2013-09-30 | South Lanarkshire | 1714911 | -3246.93 | 0 | 0 | 0 | 0 | 0 | -3246.93 | 0 | 1711664.07 | 0 | [6 empty] | EC04D | 100%
402988 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-10-23 | 2014-07-01 | 2014-07-18 | 2015-03-18 | 2015-03-18 | Argyll and Bute-Cowal & Bute | 1347271 | 80471 | -24999.66 | -46643.91 | 0 | 0 | 0 | 8827.43 | 0 | 1356098.43 | 229318.7788 | [6 empty] | CS11 | 100%
400762 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2010-05-04 | 2015-10-26 |  | City of Edinburgh | 465000 | -41243.42 | 0 | 0 | 0 | 0 | 0 | -41243.42 | 0 | 423756.58 | 0 | [6 empty] | CM_WSI | 100%
500229 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS0 | 2018-08-03 | 2020-04-20 | 2020-10-12 | 2022-03-29 | 2022-06-21 | East Lothian | 0 | 39725.61 | 15077.35 | 42278.791 | 102800.009 | 509970.32 | 1146874.36 | 1856726.44 | 2656468.64 | 4513195.08 | 148885.7057 | [6 empty] | CM_WWNI | 4.274% | SG1 | 95.73%
500921 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2017-01-31 | 2017-01-31 | 2016-12-16 | 2017-01-31 | East Lothian | 0 | 6000 | -529.59 | 35.36 | 0 | 0 | 0 | 5505.77 | 0 | 5505.77 | 144841.4737 | [6 empty] | CS15A | 100%
402976 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-09-26 | 2013-05-27 | 2013-07-17 | 2013-12-20 |  | Fife | 123879 | -1242.71 | 0 | 0 | 0 | 0 | 0 | -1242.71 | 0 | 122636.29 | 0 | [6 empty] | CM_WWI | 100%
403036 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-05-17 | 2015-05-25 | 2015-06-22 | 2015-12-22 |  | Shetland Islands | 17398 | 111316 | 0.39 | -276.29 | 0 | 0 | 0 | 111040.1 | 0 | 128438.1 | 0 | [6 empty] | CM_WWI | 100%
403031 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-11-06 | 2016-12-11 | 2016-12-12 | 2016-12-07 |  | Fife | 722 | 0 | -355.98 | 0 | 0 | 0 | 0 | -355.98 | 0 | 366.02 | 0 | [6 empty] | CM_WWI | 100%
403035 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-11-22 | 2016-06-24 | 2016-06-24 | 2016-06-28 |  | Orkney Islands | 4544 | 8939.14 | 442.86 | 0 | 0 | 0 | 0 | 9382 | 0 | 13926 | 0 | [6 empty] | CM_WWNI | 100%
402974 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-15 | 2016-12-11 | 2016-04-01 | 2016-12-13 |  | Fife | 26237 | 108541 | 60232.09 | 0 | 0 | 0 | 0 | 168773.09 | 0 | 195010.09 | 0 | [6 empty] | CM_WWI | 100%
403003 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-30 | 2016-12-11 | 2016-12-12 | 2016-12-12 |  | Aberdeenshire | 14556 | 2933 | -2851.37 | 0 | 0 | 0 | 0 | 81.63 | 0 | 14637.63 | 0 | [6 empty] | CM_WWI | 100%
402973 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-09-26 | 2016-03-14 | 2016-03-17 | 2016-09-16 |  | Fife | 1000 | 4785.9 | 0 | 0 | 0 | 0 | 0 | 4785.9 | 0 | 5785.9 | 0 | [6 empty] | CM_WWI | 100%
400629 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-04-06 | 2012-03-02 | 2012-05-25 | 2013-03-18 |  | All East Unitary Authorities | 213408 | 7727.53 | 0 | 0 | 0 | 0 | 0 | 7727.53 | 0 | 221135.53 | 0 | [6 empty] | CM_WWI | 100%
400628 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-04-06 | 2012-03-28 | 2012-09-11 | 2013-03-18 |  | All East Unitary Authorities | 300970 | 4744.13 | 0 | 0 | 0 | 0 | 0 | 4744.13 | 0 | 305714.13 | 0 | [6 empty] | CM_WWI | 100%
500015 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS5 | 2015-05-08 | 2017-11-24 | 2018-01-30 | 2019-03-06 | 2019-03-06 | South Lanarkshire | 0 | 64060 | 144225.01 | 225743.59 | 766388.24 | 15006.3 | 608.85 | 1216031.99 | 0 | 1216031.99 | 0 | [6 empty] | CM_WSNI | 100%
503373 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2019-03-15 | 2019-03-15 | 2019-03-15 | 2019-01-16 | 2019-01-16 | Fife | 0 | 0 | 0 | 0 | 74030.635 | 0 | 0 | 74030.635 | 0 | 74030.635 | 148885.7057 | [6 empty] | SG1 | 100%
402978 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-07-20 | 2016-07-20 | 2016-07-20 |  | Angus | 3142 | 44.69 | 40.93 | 0 | 0 | 0 | 0 | 85.62 | 0 | 3227.62 | 0 | [6 empty] | CM_WWI | 100%
402982 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-02-19 | 2016-04-27 | 2016-07-07 | 2016-07-07 | Fife | 224.88 | 45069.01 | 93018.52 | 313.66 | -1455.4285 | 0 | 0 | 136945.7615 | 0 | 137170.6415 | 0 | [6 empty] | CM_WWI | 100%
402984 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-02-19 | 2016-04-27 | 2016-07-31 | 2016-07-31 | Fife | 5349.96 | 32642.04 | 77500 | 0 | 3913.6351 | 0 | 0 | 114055.6751 | 0 | 119405.6351 | 0 | [6 empty] | CM_WWI | 100%
402975 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-11-09 | 2013-08-26 | 2013-10-14 | 2014-04-08 |  | Fife | 35597 | 418.72 | -385.56 | 0 | 0 | 0 | 0 | 33.16 | 0 | 35630.16 | 0 | [6 empty] | CM_WWI | 100%
402983 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-12-11 | 2016-12-12 | 2016-12-07 |  | Fife | 1000 | 0 | -411.71 | 0 | 0 | 0 | 0 | -411.71 | 0 | 588.29 | 0 | [6 empty] | CM_WWI | 100%
402985 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-12-11 | 2016-12-12 | 2016-12-07 |  | Fife | 732 | 1000 | -620.48 | 0 | 0 | 0 | 0 | 379.52 | 0 | 1111.52 | 0 | [6 empty] | CM_WWI | 100%
402979 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-12-11 | 2016-12-12 | 2016-12-07 |  | Fife | 894 | 0 | -502.29 | 0 | 0 | 0 | 0 | -502.29 | 0 | 391.71 | 0 | [6 empty] | CM_WWI | 100%
402980 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-08-12 | 2016-08-12 | 2016-08-12 |  | Fife | 6960 | 1054.97 | 0 | 0 | 0 | 0 | 0 | 1054.97 | 0 | 8014.97 | 0 | [6 empty] | CM_WWI | 100%
402972 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-12-11 | 2016-12-12 | 2016-12-07 |  | Fife | 2514 | 0 | -491.7 | 0 | 0 | 0 | 0 | -491.7 | 0 | 2022.3 | 0 | [6 empty] | CM_WWI | 100%
402971 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-06-06 | 2016-07-15 | 2016-11-02 |  | Fife | 224.88 | 37453.12 | 133708 | -0.28 | -4015.1355 | 0 | 0 | 167145.7045 | 0 | 167370.5845 | 0 | [6 empty] | CM_WWI | 100%
402604 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-28 | 2015-01-08 | 2015-05-29 | 2016-09-26 |  | All East Unitary Authorities | 280394 | 687878 | 136053.91 | 0 | -2386.22 | 0 | 0 | 821545.69 | 0 | 1101939.69 | 0 | [6 empty] | CM_M&G | 100%
501318 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-07-07 | 2018-07-31 | 2018-09-25 | 2019-07-19 | 2019-11-04 | All East Unitary Authorities | 0 | 0 | 22116.32 | 265307.96 | 695088.78 | 106394.91 | 5569.9 | 1094477.87 | 1712.15 | 1096190.02 | 0 | [6 empty] | CM_WWNI | 100%
502762 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2020-09-01 | 2022-10-14 | 2023-02-02 | 2025-04-02 | 2025-04-03 | Stirling | 0 | 0 | 0 | 199470.48 | 71241.53 | 47352.6 | 151935.42 | 470000.03 | 0 | 470000.03 | 148885.7057 | [6 empty] | SG1 | 100%
501249 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-12-07 | 2021-05-10 | 2021-06-14 | 2021-08-27 | 2021-11-29 | Dumfries and Galloway | 0 | 21096 | 17517.2 | 1390.57 | 0 | 0 | 0 | 40003.77 | 374734.49 | 414738.26 | 0 | [6 empty] | CM_WSI | 100%
500125 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS5 | 2015-03-19 | 2016-04-27 | 2016-08-25 | 2018-11-01 | 2019-03-01 | Dumfries and Galloway | 0 | 9973 | 27292.27 | 71585.73 | 15154.66 | 0 | 0 | 124005.66 | 0 | 124005.66 | 61958.8426 | [6 empty] | EC01G | 9.54% | EC01D | 90.46% | bar: Regulatory Outputs OMG-23
501101 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS5 | 2015-09-30 | 2016-08-31 | 2016-10-03 | 2018-07-01 | 2019-03-01 | Scottish Water Wide | 0 | 1129 | 24269.31 | 29965.47 | 4513.2847 | 0 | 0 | 59877.0647 | 0 | 59877.0647 | 10362.528 | [6 empty] | EC01G | 100% | [18 empty] | Regulatory Outputs OMG-23: 6
503281 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-24 | 2023-06-07 | 2023-10-10 | 2024-10-07 | 2025-01-07 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 79101.968 | 13098.04 | 32698.27 | 124898.278 | 21309.46 | 146207.738 | 148885.7057 | [6 empty] | SG1 | 100%
402230 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-06-28 | 2013-10-24 | 2014-01-09 | 2015-03-04 | 2015-03-04 | Aberdeenshire | 1706967 | 17055 | 9149.9 | 48827.0565 | 0 | 0 | 0 | 75031.9565 | 0 | 1781998.9565 | 0 | [6 empty] | SG1 | 100%
503313 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-03-14 | 2023-09-01 | 2024-01-04 | 2024-12-27 | 2025-03-31 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 87335.13 | 27844.31 | 115179.44 | 26820.3 | 141999.74 | 148885.7057 | [6 empty] | SG1 | 100%
502612 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW1 | 2021-06-09 | 2022-03-29 | 2022-06-14 | 2023-01-11 | 2023-04-13 | Moray | 0 | 0 | 9623.72 | 812.95 | 598.05 | 5706.51 | 5684.38 | 22425.61 | 457093.74 | 479519.35 | 0 | [6 empty] | CM_WWI | 100%
501104 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-09-30 | 2017-02-27 | 2017-03-27 | 2018-09-27 | 2019-01-23 | City of Edinburgh | 0 | 591 | 12353.81 | 28250.19 | 18872.46 | 0 | 0 | 60067.46 | 0 | 60067.46 | 172809.8709 | [6 empty] | EC01D | 15.25% | EC01G | 31.12% | EC10E | 53.63%
400948 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS7 | 2010-05-31 | 2013-10-18 | 2015-10-19 | 2015-10-19 | 2015-10-19 | City of Edinburgh | 126235.14 | -126234.15 | -7832.14 | 1897.01 | 0 | 0 | 0 | -132169.28 | 0 | -5934.14 | 0 | [6 empty] | CS11A | 100%
501311 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-02-17 | 2017-01-31 | 2017-02-06 | 2019-04-01 | 2019-04-01 | City of Edinburgh | 0 | 9734 | 390061 | 525183 | 800846 | 1530.01 | 1776.99 | 1729131 | 0 | 1729131 | 0 | [6 empty] | CM_WWI | 100%
500819 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-27 | 2017-03-28 | 2017-03-28 | 2016-12-02 | 2017-03-28 | City of Edinburgh | 0 | 5092.83 | 1913.91 | 531.999 | 0 | 0 | 0 | 7538.739 | 0 | 7538.739 | 144841.4737 | [6 empty] | CS15A | 100%
402479 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-06-28 | 2013-04-30 | 2013-04-30 | 2016-08-30 | 2016-11-07 | Scottish Water Wide | 1241862 | 92738.46 | 69372.54 | 29997 | 26793.75 | 0 | 0 | 218901.75 | 0 | 1460763.75 | 106014 | [6 empty] | CS16S | 100%
502961 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2019-11-14 | 2020-11-16 | 2021-02-03 | 2021-08-31 | 2021-12-01 | City of Edinburgh | 0 | 0 | 0 | 20048.615 | 80188.071 | 42499.08 | 154472.99 | 297208.756 | 203967.86 | 501176.616 | 0 | [6 empty] | CM_WWNI | 100%
501096 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS4 | 2015-09-30 | 2016-09-26 | 2016-09-28 | 2018-10-01 | 2019-07-01 | City of Edinburgh | 0 | 3837 | 34236.82 | 39826.18 | 15100 | 6000.01 | 0 | 99000.01 | 0 | 99000.01 | 0 | [6 empty] | EC10D | 100% | bar: Regulatory Outputs OMG-23
503034 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-04-16 | 2022-02-28 | 2022-05-30 | 2022-12-30 | 2023-04-03 | Aberdeenshire | 0 | 0 | 0 | 12453.61 | 16346.39 | 0 | 0 | 28800 | 571200.03 | 600000.03 | 0 | [6 empty] | CM_WSI | 100%
502819 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-08-20 | 2022-07-22 | 2022-11-14 | 2023-11-02 | 2024-02-02 | Angus | 0 | 0 | 0 | 63338.9425 | 12729.9275 | 12407.89 | 11028.5 | 99505.26 | 45781.77 | 145287.03 | 148885.7057 | [6 empty] | SG1 | 100%
500223 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS4 | 2015-03-27 | 2016-03-30 | 2016-06-15 | 2017-06-20 | 2020-04-28 | Shetland Islands | 0 | 604.56 | 31705.62 | 47595.161 | 6062.659 | 1997.97 | 1.98 | 87967.95 | 0 | 87967.95 | 602510.0072 | [6 empty] | DW5FS | 100%
500860 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-06-03 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Shetland Islands | 0 | 16989.46 | 10147.45 | 7415.4 | 0 | 0 | 0 | 34552.31 | 0 | 34552.31 | 861135.6294 | [6 empty] | DW5FS | 100%
501256 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-04-05 | 2022-04-01 | 2022-08-03 | 2022-12-01 | 2023-03-03 | Shetland Islands | 0 | 1684.21 | 18090.52 | 11568.76 | 800.875 | 0 | 0 | 32144.365 | 2269300.38 | 2301444.745 | 0 | [6 empty] | CM_WSNI | 100%
501091 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2016-11-02 | 2018-02-28 | 2018-03-28 | 2019-10-01 | 2020-01-01 | Shetland Islands | 0 | 3448.91 | 58429.83 | 402540.72 | 1229484.01 | 406070.05 | 10981.73 | 2110955.25 | 6067.72 | 2117022.97 | 52955.6678 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
500030 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | WINF | Supply Resilience | MS3 | 2016-08-01 | 2018-06-29 | 2018-09-28 | 2020-06-01 | 2020-06-01 | Shetland Islands | 0 | 160186.88 | 55510.12 | 61639 | 2011383.72 | 4314431.69 | 98166.26 | 6701317.67 | 367727.33 | 7069045 | 1817908.3275 | [6 empty] | CS16WR | 100% | bar: Regulatory Outputs OMG-07
502912 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-04-20 | 2021-12-06 | 2022-02-24 | 2022-07-11 | 2022-10-04 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 6000 | 35971.65 | 30088.8 | 72060.45 | 2939.57 | 75000.02 | 144841.4737 | [6 empty] | CS15A | 100%
503506 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2020-11-20 | 2021-08-18 | 2021-11-09 | 2022-03-28 | 2022-06-28 | East Renfrewshire | 0 | 0 | 0 | 0 | 41860.47 | 56903.64 | 43096.38 | 141860.49 | 0 | 141860.49 | 144841.4737 | [6 empty] | CS15A | 100%
503391 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-12-29 | 2021-08-27 | 2021-12-13 | 2022-06-07 | 2022-09-07 | Midlothian | 0 | 0 | 0 | 0 | 29000 | 24336.63 | 46663.39 | 100000.02 | 0 | 100000.02 | 144841.4737 | [6 empty] | CS15A | 100%
502955 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-03-31 | 2021-03-08 | 2021-05-25 | 2022-02-23 | 2022-05-26 | Inverclyde | 0 | 0 | 0 | 6000 | 21000 | 45000 | 0 | 72000 | 0 | 72000 | 144841.4737 | [6 empty] | CS15A | 100%
502700 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-05-05 | 2021-10-28 | 2022-01-10 | 2022-05-26 | 2022-08-26 | Angus | 0 | 0 | 0 | 57000 | 16000 | 10205.33 | 6794.67 | 90000 | 0 | 90000 | 144841.4737 | [6 empty] | CS15A | 100%
503368 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-06-02 | 2022-01-27 | 2022-05-13 | 2022-11-07 | 2023-02-07 | Moray | 0 | 0 | 0 | 0 | 11000 | 20363.63 | 30427.05 | 61790.68 | 38209.29 | 99999.97 | 144841.4737 | [6 empty] | CS15A | 100%
502699 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-09-06 | 2018-09-06 | 2018-09-06 | 2018-08-16 | 2018-08-16 | Renfrewshire | 0 | 0 | 0 | 34931.2816 | 15511.352 | 0 | 0 | 50442.6336 | 0 | 50442.6336 | 144841.4737 | [6 empty] | CS15A | 100%
503552 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2020-11-18 | 2021-08-04 | 2021-10-26 | 2022-04-25 | 2022-07-26 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 51856.63 | 48143.34 | 99999.97 | 0 | 99999.97 | 144841.4737 | [6 empty] | CS15A | 100%
502913 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-01-28 | 2021-09-15 | 2021-12-06 | 2022-04-20 | 2022-07-14 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 7000 | 21869.22 | 46130.78 | 75000 | 0 | 75000 | 144841.4737 | [6 empty] | CS15A | 100%
502921 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2021-07-21 | 2022-03-08 | 2022-05-27 | 2022-10-11 | 2023-01-04 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 144841.4737 | [6 empty] | CS15A | 100%
502919 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2021-07-21 | 2022-03-08 | 2022-05-27 | 2022-10-11 | 2023-01-04 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 144841.4737 | [6 empty] | CS15A | 100%
502693 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-05-18 | 2018-05-18 | 2018-04-25 | 2018-05-18 | 2018-05-18 | Fife | 0 | 0 | 0 | 8000 | -5087.05 | 0 | 0 | 2912.95 | 0 | 2912.95 | 144841.4737 | [6 empty] | CS15A | 100%
503210 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2020-08-21 | 2021-08-09 | 2021-10-28 | 2022-05-31 | 2022-08-31 | East Ayrshire | 0 | 0 | 0 | 0 | 11000 | 55868.63 | 33131.4 | 100000.03 | 0 | 100000.03 | 144841.4737 | [6 empty] | CS15A | 100%
502920 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2021-07-21 | 2022-03-08 | 2022-05-27 | 2022-10-11 | 2023-01-04 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 144841.4737 | [6 empty] | CS15A | 100%
502761 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2019-09-13 | 2020-06-15 | 2020-09-01 | 2021-01-21 | 2021-04-23 | North Lanarkshire | 0 | 0 | 0 | 84150.776 | 46849.224 | 14000 | 22285.72 | 167285.72 | 3714.28 | 171000 | 144841.4737 | [6 empty] | CS15A | 100%
502697 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-14 | 2018-08-14 | Glasgow City | 0 | 0 | 0 | 90079.4375 | 10276.256 | 0 | 0 | 100355.6935 | 0 | 100355.6935 | 144841.4737 | [6 empty] | CS15A | 100%
502917 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2021-07-21 | 2022-03-08 | 2022-05-27 | 2022-10-11 | 2023-01-04 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 144841.4737 | [6 empty] | CS15A | 100%
503338 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-12-16 | 2021-09-27 | 2021-12-08 | 2022-04-22 | 2022-07-25 | North Ayrshire | 0 | 0 | 0 | 0 | 45000 | 32031.6 | 22968.4 | 100000 | 0 | 100000 | 144841.4737 | [6 empty] | CS15A | 100%
502918 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2021-07-21 | 2022-03-08 | 2022-05-27 | 2022-10-11 | 2023-01-04 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 144841.4737 | [6 empty] | CS15A | 100%
502916 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2021-01-28 | 2021-09-15 | 2021-12-06 | 2022-04-20 | 2022-07-14 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 8000 | 21869.22 | 45130.78 | 75000 | 0 | 75000 | 144841.4737 | [6 empty] | CS15A | 100%
503192 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2021-10-12 | 2022-08-29 | 2022-11-24 | 2023-06-28 | 2023-09-28 | Renfrewshire | 0 | 0 | 0 | 0 | 20000 | 34555.31 | 29567.85 | 84123.16 | 515876.89 | 600000.05 | 144841.4737 | [6 empty] | CS15A | 100%
503438 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2020-11-18 | 2021-07-26 | 2021-10-26 | 2022-04-25 | 2022-07-26 | Glasgow City | 0 | 0 | 0 | 0 | 42435.12 | 60561.15 | 37438.88 | 140435.15 | 0 | 140435.15 | 144841.4737 | [6 empty] | CS15A | 100%
502694 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-05-18 | 2018-05-18 | 2018-04-25 | 2018-05-18 | 2018-05-18 | Fife | 0 | 0 | 0 | 6000 | -5243.45 | 0 | 0 | 756.55 | 0 | 756.55 | 144841.4737 | [6 empty] | CS15A | 100%
502922 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-04-16 | 2021-01-11 | 2021-03-31 | 2021-08-13 | 2021-11-08 | North Lanarkshire | 0 | 0 | 0 | 84000 | 53000 | 1577.91 | 15830 | 154407.91 | 67592.12 | 222000.03 | 144841.4737 | [6 empty] | CS15A | 100%
300022 | Q&S3A | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-08-22 | 2015-08-05 | 2015-01-16 | 2015-04-14 | 2014-12-01 | Scottish Water Wide | 104313.6 | -3953.47 | 0 | 0 | 0 | 0 | 0 | -3953.47 | 0 | 100360.13 | 0 | [6 empty] | DW9 | 100%
046844 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2012-05-25 | 2012-06-28 | 2012-08-02 | 2012-09-05 | Highland | 200866.84 | 13656.76 | -6822.72 | 0 | 0 | 0 | 0 | 6834.04 | 0 | 207700.88 | 0 | [6 empty] | DW23 | 100%
503214 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-10 | 2023-06-23 | 2023-10-20 | 2024-10-16 | 2025-01-16 | Fife | 0 | 0 | 0 | 0 | 84764.25 | 9864.38 | 25207.18 | 119835.81 | 27581.5 | 147417.31 | 148885.7057 | [6 empty] | SG1 | 100%
404098 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-01-28 | 2015-02-05 | 2015-02-05 | 2015-04-24 | 2015-04-24 | Scottish Water Wide | 19822.04 | 2882.23 | 0 | 0 | 0 | 0 | 0 | 2882.23 | 0 | 22704.27 | 0 | [6 empty] | CM_WSI | 100%
402489 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-12-16 | 2013-11-27 | 2013-12-06 | 2013-12-03 |  | Scottish Water Wide | 15808.39 | 0 | 0 | 0 | -0.05 | 0 | 0 | -0.05 | 0 | 15808.34 | 0 | [6 empty] | CM_WSI | 100%
502250 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-07-08 | 2016-07-08 | 2017-03-02 | 2018-06-22 | 2018-06-22 | Scottish Water Wide | 0 | 0 | 16773 | 17840 | 6711.42 | 0 | 0 | 41324.42 | 0 | 41324.42 | 0 | [6 empty] | CM_WSNI | 50% | CM_WWNI | 50%
403902 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS1 | 2014-10-20 | 2019-07-29 | 2019-09-23 | 2021-07-29 | 2021-07-29 | Aberdeenshire | 34032 | 142378 | 431194.61 | 454746.839 | 725974.471 | 2923010.07 | 3252723.74 | 7930027.73 | 2037907.34 | 10001967.07 | 0 | [6 empty] | SG1 | 100%
045031 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-12 | 2011-06-22 | 2011-07-11 | 2012-12-11 | 2013-01-21 | Highland | 1705909 | 105.53 | 30.25 | 0 | 0 | 0 | 0 | 135.78 | 0 | 1706044.78 | 0 | [6 empty] | DW23 | 100%
503354 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2018-08-13 | 2018-08-28 | 2018-08-30 | 2019-07-12 | 2019-07-15 | East Renfrewshire | 0 | 0 | 0 | 0 | 580000 | 0 | 0 | 580000 | 0 | 580000 | 0 | [6 empty] | CM_WSI | 100%
502635 | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | MS5 | 2018-11-23 | 2018-11-23 | 2018-12-13 | 2018-12-14 | 2018-12-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 36.43 | 0 | 0 | 36.43 | 0 | 36.43 | 71457.7531 | [6 empty] | I2S_WNI | 100%
500483 | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | MS3 | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2021-02-26 | 2021-02-26 | Scottish Water Wide | 0 | 49919 | 43692.27 | 163137.85 | 43555.73 | 51695.15 | 0 | 352000 | 0 | 352000 | 71457.7531 | [6 empty] | I2S_WNI | 100%
500484 | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Wastewater |  | SWD | Energy efficiency | MS3 | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2021-03-01 | 2021-03-01 | Scottish Water Wide | 0 | 139847.22 | 1892905.78 | 855491.91 | 618236.55 | 683884.96 | 555426.26 | 4745792.68 | 38053.76 | 4783846.44 | 1709913.541 |  |  |  |  | -999999.9996 |  | I2S_WWNI | 100%
403296 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-02-04 | 2013-11-18 | 2013-11-19 | 2015-10-30 |  | Scottish Water Wide | 2179530 | -90527.29 | 0 | 0 | 0 | 0 | 0 | -90527.29 | 0 | 2089002.71 | 0 | [6 empty] | CM_M&G | 100%
500001 | Q&S4 | Improving the customer experience | Contact Management |  |  | Wastewater |  | SWD | Contact Management | MS5 | 2015-09-07 | 2016-11-01 | 2016-11-01 | 2019-03-04 | 2019-03-04 | Scottish Water Wide | 532206 | 1492056 | 4070208.94 | 3324387.47 | 163296.15 | 71026 | 0 | 9120974.56 | 0 | 9653180.56 | 5712926.823 | [6 empty] | CM_M&G | 30.72% | CS21S | 34.64% | CS21W | 34.64%
503517 | Q&S4 | Protecting and enhancing the environment | Odour |  |  | Wastewater |  | SWMD | Odour | MS3 | 2019-02-18 | 2019-02-18 | 2019-02-22 | 2020-09-30 | 2021-01-06 | Highland | 0 | 0 | 0 | 0 | 65833.73 | 161866.27 | 240.46 | 227940.46 | 2059.54 | 230000 | 25899.1086 |  |  |  |  | 15000 |  | CS2 | 100%
045046 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-27 | 2010-11-25 | 2011-03-14 | 2014-12-15 | 2015-02-17 | Scottish Water Wide | 2247100.9 | -1260.15 | 1282.33 | 0 | 0 | 0 | 0 | 22.18 | 0 | 2247123.08 | 13366 | [6 empty] | DW9B | 100%
046874 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-02-25 | 2012-08-29 | 2012-11-26 | 2015-01-20 | 2015-01-22 | Scottish Water Wide | 3245931.28 | 11260.46 | -1901.75 | 0 | 0 | 0 | 0 | 9358.71 | 0 | 3255289.99 | 11403 | [6 empty] | DW9E | 100%
500225 | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWMD | SEMD | MS6 | 2015-03-27 | 2017-06-29 | 2017-07-24 | 2018-06-01 | 2018-10-01 | Scottish Water Wide | 167.15 | 752.34 | 11455.51 | 428699.92 | 110928.61 | 326.07 | 324.79 | 552487.24 | 149.11 | 552803.5 | 274541.7759 | [6 empty] | DW9D | 100% | bar: Regulatory Outputs OMG-10
500064 | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWMD | SEMD | MS6 | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-03-27 | 2017-06-30 | Scottish Water Wide | 504.83 | 70671.17 | 335813.36 | 46072.45 | -11444.17 | 3253.62 | 630.55 | 444996.98 | 0 | 445501.81 | 46914.0093 | [6 empty] | DW9F | 100%
502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWD | SEMD | MS7 | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-03 | 2017-03-31 | Scottish Water Wide | 0 | 0 | 4814.14 | 1962.24 | 0 | 0 | 0 | 6776.38 | 0 | 6776.38 | 183369.5948 | [6 empty] | DW9F | 100%
501641 | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWMD | SEMD | MS3 | 2015-03-31 | 2018-10-31 | 2019-03-06 | 2020-02-01 | 2020-05-01 | Scottish Water Wide | 0 | 0 | 13397.32 | 150802.68 | 432865.14 | 1223943.79 | 25957.31 | 1846966.24 | 3205.34 | 1850171.58 | 274541.7759 | [6 empty] | DW9D | 100% | bar: Regulatory Outputs OMG-10
500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWMD | SEMD | MS6 | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-16 | 2017-06-30 | Scottish Water Wide | 393.93 | 89765.07 | 343522.2 | 45628.04 | -18227.96 | 2696.88 | 303.14 | 463687.37 | 0 | 464081.3 | 136455.5855 | [6 empty] | DW9F | 100%
502187 | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWMD | SEMD | MS3 | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-06-14 | 2019-09-16 | Scottish Water Wide | 0 | 0 | 0 | 3978892.39 | 6524810.52 | 200639.44 | 28734.21 | 10733076.56 | 6708.38 | 10739784.94 | 274541.7759 | [6 empty] | CM_WSNI | 50% | DW9D | 50%
045045 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2014-10-15 | 2014-11-03 | 2016-03-30 | 2016-03-30 | Scottish Water Wide | 2067970.45 | -7525.44 | -21729.24 | 0 | 0 | 0 | 0 | -29254.68 | 0 | 2038715.77 | 296598.0001 | [6 empty] | DW9A | 100%
045047 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MSU |  | 2017-02-06 | 2017-06-02 | 2018-03-19 | 2018-06-18 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197588.1466 | [6 empty] | DW9C | 100%
402490 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-02-09 | 2012-03-13 | 2012-03-13 | 2013-06-10 | 2013-10-30 | Scottish Water Wide | 380616.69 | -38224.37 | 0 | 0 | 0 | 0 | 0 | -38224.37 | 0 | 342392.32 | 5189 | [6 empty] | DW9A | 100%
500066 | Q&S4 | Protecting and enhancing the environment | Scottish Government Requirements |  |  | Wastewater |  | SWD | Scottish Government Requirements | MS7 | 2016-06-08 | 2016-06-08 | 2015-12-21 | 2016-06-08 | 2016-06-08 | Scottish Water Wide | 0 | 21139.53 | 0 | 0 | 0 | 0 | 0 | 21139.53 | 0 | 21139.53 | 0 | [6 empty] | EC21A | 100%
500953 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-11-10 | 2016-11-01 | 2016-11-01 | 2017-06-23 |  | Scottish Water Wide | 0 | 33727 | 627257.6 | 11967.07 | 0 | 0 | 0 | 672951.67 | 0 | 672951.67 | 0 | [6 empty] | CM_M&G | 100%
501303 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-12-02 | 2017-04-14 | 2017-01-27 | 2017-01-27 | 2017-05-22 | Scottish Water Wide | 0 | 87463 | 32450.58 | 0 | 0 | 0 | 0 | 119913.58 | 0 | 119913.58 | 0 | [6 empty] | CM_M&G | 100%
049013 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MS3 |  |  | 2010-04-01 | 2021-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6016549.8972 | [6 empty] | EC04B | 100%
502336 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MSU | 2021-03-31 | 2021-06-07 | 2021-06-07 | 2021-06-07 | 2021-06-07 | Scottish Water Wide | 0 | 0 | 82563.99 | 13120.326 | 0.004 | 27263.52 | 27052.18 | 150000.02 | 0 | 150000.02 | 10362.528 | [6 empty] | EC01G | 100%
402923 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2012-08-24 | 2012-08-24 | 2012-09-03 | 2013-06-07 |  | Scottish Water Wide | 11021.46 | 0 | 0 | 356.48 | 0 | 0 | 0 | 356.48 | 0 | 11377.94 | 0 | [6 empty] | CM_M&G | 100%
502206 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-08-29 | 2017-06-16 | Scottish Water Wide | 0 | 0 | 30553.57 | 0 | 0 | 0 | 0 | 30553.57 | 0 | 30553.57 | 0 | [6 empty] | CM_M&G | 100%
402440 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-02-21 | 2013-08-30 | 2013-11-25 | 2015-02-25 | 2015-03-26 | Argyll and Bute-North Argyll | 837864 | 170136 | -631.01 | 801.4075 | 0 | 0 | 0 | 170306.3975 | 0 | 1008170.3975 | 0 |  |  |  |  | 9524.8 |  | DW10 | 100%
502881 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-07-02 | 2027-09-27 | 2028-01-12 | 2028-08-30 | 2028-11-30 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 21104.908 | 934.242 | 11530.02 | 11485.33 | 45054.5 | 4954949.56 | 5000004.06 | 148885.7057 | [6 empty] | WG1 | 100%
502909 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2017-11-29 | 2018-11-29 | 2018-12-11 | 2019-10-08 | 2020-01-14 | Glasgow City | 0 | 0 | 0 | 765890 | 1036515.768 | 769363.55 | 283339.4 | 2855108.718 | 3297.36 | 2858406.078 | 0 | [6 empty] | CM_WWI | 100%
502820 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2021-09-15 | 2022-07-22 | 2022-11-14 | 2023-11-02 | 2024-02-02 | Perth and Kinross | 0 | 0 | 0 | 62548.68 | 8775.8 | 26568.52 | 39400.25 | 137293.25 | 8562.06 | 145855.31 | 148885.7057 | [6 empty] | SG1 | 100%
500126 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS3 | 2015-03-27 | 2017-03-28 | 2017-05-16 | 2019-12-02 | 2020-03-04 | Renfrewshire | 0 | 24529 | 88292.38 | 235047.62 | 153697 | 103579.46 | 157819.61 | 762965.07 | 0 | 762965.07 | 523841.7272 | [6 empty] | EC01G | 0.8999% | EC10E | 4.03% | EC01D | 19.66% | CS11 | 21.86% | CS16D | 53.55%
503255 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2021-04-01 | 2021-04-01 | 2021-06-21 | 2022-01-14 | 2022-04-18 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374999.94 | 374999.94 | 0 | [6 empty] | CM_WWI | 100%
400066 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-09-04 | 2011-10-18 | 2011-11-28 | 2015-07-15 |  | Renfrewshire | 4225236.58 | 60049.65 | -571.88 | 541.42 | 0 | 0 | 0 | 60019.19 | 0 | 4285255.77 | 0 |  |  |  |  | 32057 |  | CM_WWNI | 100%
501684 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-05-28 | 2022-03-14 | 2022-06-08 | 2022-10-21 | 2023-01-19 | Renfrewshire | 0 | 0 | 15537.96 | 6213.072 | 1437.518 | 12023.61 | 11977 | 47189.16 | 1489510.76 | 1536699.92 | 0 | [6 empty] | CM_WSI | 100%
503271 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-11 | 2023-06-27 | 2023-10-30 | 2024-10-25 | 2025-01-27 | Renfrewshire | 0 | 0 | 0 | 0 | 77147.739 | 9210.34 | 12797.89 | 99155.969 | 44495.3 | 143651.269 | 148885.7057 | [6 empty] | SG1 | 100%
502780 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS1 | 2017-06-16 | 2019-08-26 | 2019-11-26 | 2020-07-10 | 2020-10-12 | Renfrewshire | 0 | 0 | 0 | 2911.39 | 82254.07 | 315140.38 | 334953.05 | 735258.89 | 1442.95 | 736701.84 | 0 | [6 empty] | CM_WWNI | 100%
503102 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | General |  | SWD | DWQ Compliance | MS2 | 2018-07-09 | 2018-07-09 | 2019-05-06 | 2021-09-08 | 2021-12-09 | Scottish Water Wide | 0 | 0 | 0 | 0 | 327102.8 | 0 | 0 | 327102.8 | 0 | 327102.8 | 543751805.3409 | [6 empty] | SR15_ENV_ODO | 0.1218% | SR15_ENV_HABD | 0.1374% | SR15_CMA_MAG | 0.3031% | SR15_CMA_WSI | 0.6449% | SR15_DWA_SOSI | 0.653% | SR15_CMP_PLAN | 0.7935% | SR15_SED_INFC | 0.8387% | SR15_DWA_SRE | 1.243% | SR15_CMP_LATE | 4.731% | SR15_DWQ_REL | 13.82%
502277 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2018-12-18 | 2018-12-18 | 2019-01-03 | 2019-04-30 | 2019-05-01 | Scottish Water Wide | 0 | 0 | 126533.47 | 15374.53 | 25967 | 0 | 0 | 167875 | 0 | 167875 | 0 | [6 empty] | CM_WSNI | 50% | CM_WWNI | 50%
502950 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS5 | 2018-05-15 | 2018-05-15 | 2018-05-17 | 2019-02-27 | 2019-02-27 | North Lanarkshire | 0 | 0 | 0 | 0 | 473670.51 | 0 | 0 | 473670.51 | 0 | 473670.51 | 0 | [6 empty] | CM_WWI | 100%
403175 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-02-05 | 2015-02-25 | 2015-04-20 | 2015-08-28 | 2014-12-11 | Scottish Water Wide | 239428.98 | 19915.61 | -253489.92 | -5854.67 | 0 | 0 | 0 | -239428.98 | 0 | 0 | 229318.7788 | [6 empty] | CS11A | 100%
402426 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-03-31 | 2012-08-31 | 2012-08-31 | 2012-08-31 | 2012-08-31 | Glasgow City | 5859.09 | 563.01 | 0 | 0 | 0 | 0 | 0 | 563.01 | 0 | 6422.1 | 0 | [6 empty] | CS15 | 100%
502272 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-11-21 | 2016-11-21 | 2017-02-27 | 2018-01-25 | 2018-01-25 | Scottish Water Wide | 0 | 0 | 11602.65 | 17155.411 | 0 | 0 | 0 | 28758.061 | 0 | 28758.061 | 0 | [6 empty] | CM_WWI | 100%
401674 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS7 | 2011-01-28 | 2011-12-07 | 2011-12-07 | 2015-10-30 |  | Scottish Water Wide | 1255309 | 6121 | -34.28 | 0 | 0 | 0 | 0 | 6086.72 | 0 | 1261395.72 | 0 | [6 empty] | CM_M&G | 100%
502610 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2017-03-13 | 2017-08-31 | 2017-09-15 | 2018-02-01 | 2018-03-01 | Scottish Borders | 0 | 0 | 314.02 | 27710.98 | -5003.31 | 0 | 0 | 23021.69 | 0 | 23021.69 | 0 | [6 empty] | EC16 | 100% | bar: Regulatory Outputs OMG-21
500135 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS5 | 2015-03-20 | 2016-05-26 | 2016-06-20 | 2019-02-20 | 2019-03-18 | Scottish Borders | 0 | 12083 | 41790 | 91336 | 58664.11 | 53.99 | 0 | 203927.1 | 0 | 203927.1 | 10362.528 | [6 empty] | CS16D | 31.49% | EC01G | 68.51%
046214 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-15 | 2010-09-20 | 2010-10-04 | 2011-05-31 |  | Scottish Borders | 621165.62 | -1.27 | 0 | 0 | 0 | 0 | 0 | -1.27 | 0 | 621164.35 | 0 | [6 empty] | CM_WWNI | 100%
400617 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-03-31 | 2010-03-31 | 2010-06-21 | 2016-01-01 |  | Scottish Water Wide | 793438 | -878.94 | 0 | 0 | 0 | 0 | 0 | -878.94 | 0 | 792559.06 | 0 | [6 empty] | CM_M&G | 100%
400623 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-03-29 | 2010-03-29 | 2010-06-21 | 2015-08-21 |  | Scottish Water Wide | 397039.06 | 32225.34 | 0 | 0 | 0 | 0 | 0 | 32225.34 | 0 | 429264.4 | 0 | [6 empty] | CM_M&G | 100%
500521 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-05-18 | 2016-10-21 | 2016-10-21 | 2017-08-30 | 2017-08-30 | Highland | 0 | 76292 | 712181.39 | 354242.84 | 0 | 0 | 0 | 1142716.23 | 0 | 1142716.23 | 0 | [6 empty] | CM_M&G | 100%
502941 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2019-07-04 | 2019-07-22 | 2019-07-22 | 2019-07-22 | 2019-07-22 | Scottish Water Wide | 0 | 0 | 0 | 93362.48 | 21585.48 | 0 | 0 | 114947.96 | 0 | 114947.96 | 0 | [6 empty] | CM_WSNI | 100%
502940 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS2 | 2014-01-13 | 2019-03-28 | 2019-06-28 | 2020-02-01 | 2021-03-01 | Shetland Islands | 0 | 0 | 0 | 119542.3575 | 661527.3525 | 650367.74 | 1400276.6 | 2831714.05 | 715817.36 | 3547531.41 | 2751782.9086 |  |  |  |  | 23070 |  | DW23 | 50% | DW25P | 50% | bar: Regulatory Outputs OMG-01
503377 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MSU | 2022-03-14 | 2023-01-19 | 2023-05-24 | 2023-11-14 | 2024-02-14 | North Ayrshire | 0 | 0 | 0 | 0 | 74385.29 | 15824.38 | 23711.05 | 113920.72 | 31029.1 | 144949.82 | 148885.7057 | [6 empty] | SG1 | 100%
500240 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS7 | 2015-03-27 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | City of Edinburgh | 0 | 36243 | 37713 | 84227.125 | 0 | 0 | 0 | 158183.125 | 0 | 158183.125 | 201395.6584 | [6 empty] | DW5 | 100%
500823 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2015-10-28 | 2017-12-21 | 2017-12-22 | 2019-03-01 | 2019-07-31 | City of Edinburgh | 0 | 39048 | -14111.63 | 130646.3 | 60561.4 | 5126.14 | 0 | 221270.21 | 0 | 221270.21 | 1918081.5826 | [6 empty] | DW5FS | 100%
503165 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS0 | 2015-03-31 | 2019-10-14 | 2019-11-15 | 2020-03-20 | 2020-06-22 | City of Edinburgh | 0 | 0 | 0 | 0 | 14465.46 | 1999.79 | 0 | 16465.25 | 0 | 16465.25 | 1547058.34 | [6 empty] | DW5FS | 100%
500241 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS3 | 2015-03-27 | 2018-09-28 | 2018-09-28 | 2020-03-31 | 2021-01-05 | City of Edinburgh | 0 | 38636.29 | 67025.71 | 79606 | 782355.59 | 816011.65 | 145974.82 | 1929610.06 | 0 | 1929610.06 | 1588914.9788 | [6 empty] | DW5FS | 100%
500824 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-08-03 | 2018-03-23 | 2018-06-14 | 2018-11-21 | 2019-12-10 | City of Edinburgh | 0 | 8629.94 | 2508.99 | 70995.16 | 169784.48 | 11810.68 | 5939.15 | 269668.4 | 0 | 269668.4 | 345514.3911 | [6 empty] | DW5FS | 100%
503166 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS0 | 2015-03-31 | 2019-10-14 | 2019-11-15 | 2020-03-20 | 2020-06-22 | City of Edinburgh | 0 | 0 | 0 | 0 | 12610.96 | 2000 | 0 | 14610.96 | 0 | 14610.96 | 1588914.9788 | [6 empty] | DW5FS | 100%
500818 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-11-03 | 2017-03-13 | 2017-03-13 | 2016-09-12 | 2017-03-13 | Falkirk | 0 | 7066.63 | 7825.43 | 258.7975 | 0 | 0 | 0 | 15150.8575 | 0 | 15150.8575 | 144841.4737 | [6 empty] | CS15A | 100%
401378 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2011-03-03 | 2012-09-26 | 2013-02-07 | 2014-03-14 |  | West Lothian | 1289380.3 | 5624.5 | 90 | 0 | 0 | 0 | 0 | 5714.5 | 0 | 1295094.8 | 0 | [6 empty] | CM_WWNI | 100%
503284 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-14 | 2023-06-28 | 2023-10-31 | 2024-10-28 | 2025-01-28 | West Lothian | 0 | 0 | 0 | 0 | 81021.2 | 0 | 32379.24 | 113400.44 | 28599.55 | 141999.99 | 148885.7057 | [6 empty] | SG1 | 100%
503225 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-05 | 2023-06-20 | 2023-10-19 | 2024-10-15 | 2025-01-15 | South Lanarkshire | 0 | 0 | 0 | 0 | 115199.52 | 5982.31 | 14135.89 | 135317.72 | 7682.63 | 143000.35 | 148885.7057 | [6 empty] | SG1 | 100%
500801 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-08-13 | 2015-12-01 | 2015-12-01 | 2016-11-25 | 2016-11-25 | Renfrewshire | 0 | 96757 | 823743.13 | 750 | 1891.91 | 0 | 0 | 923142.04 | 0 | 923142.04 | 0 | [6 empty] | CM_WWI | 100%
401349 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-13 | 2012-09-20 | 2012-12-07 | 2014-11-21 | 2014-03-31 | Fife | 362720.13 | 1396.51 | 914.68 | 0 | 0 | 0 | 0 | 2311.19 | 0 | 365031.32 | 1577 | [6 empty] | CS1 | 100%
501083 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-05-26 | 2022-02-28 | 2022-04-27 | 2023-07-06 | 2023-10-06 | Shetland Islands | 0 | 13227.91 | 9695.09 | 0 | -274 | 0 | 0 | 22649 | 274.01 | 22923.01 | 0 | [6 empty] | CM_WSI | 100%
046859 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2012-07-31 | 2013-03-11 | 2015-07-06 | 2016-03-30 | Shetland Islands | 2851122.27 | 4707.48 | -3233.87 | 0 | 0 | 0 | 0 | 1473.61 | 0 | 2852595.88 | 17352 | [6 empty] | DW23 | 100%
503323 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-22 | 2023-08-21 | 2023-12-18 | 2024-12-13 | 2025-03-17 | Aberdeenshire | 0 | 0 | 0 | 0 | 39582.14 | 19124.55 | 19050.39 | 77757.08 | 67423.5 | 145180.58 | 148885.7057 | [6 empty] | SG1 | 100%
045548 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-29 | 2011-12-14 | 2012-02-27 | 2013-02-28 | 2013-03-29 | Aberdeenshire | 905991.77 | -66.49 | 0 | 0 | 0 | 0 | 0 | -66.49 | 0 | 905925.28 | 0 | [6 empty] | CM_WWNI | 20% | WQ01 | 80%
500922 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-27 | 2017-04-27 | 2017-04-27 | 2017-04-12 | 2017-04-27 | Fife | 0 | 5000 | 11724.57 | 161.72 | 0 | 0 | 0 | 16886.29 | 0 | 16886.29 | 144841.4737 | [6 empty] | CS15A | 100%
501097 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS5 | 2015-09-30 | 2016-08-31 | 2016-08-31 | 2018-10-01 | 2019-03-01 | Fife | 0 | 4329 | 24171.43 | 6214.46 | 4784.915 | 1000.01 | 0 | 40499.815 | 0 | 40499.815 | 0 | [6 empty] | EC10D | 100% | bar: Regulatory Outputs OMG-23
500074 | Q&S4 | Climate Change | Climate Change |  |  | Water |  | SWD | Climate Change | MS7 | 2015-03-09 | 2015-06-30 | 2015-06-30 | 2016-09-01 | 2016-06-20 | Scottish Water Wide | 671 | 19409 | 89284.35 | 0 | 0 | 0 | 0 | 108693.35 | 0 | 109364.35 | 244466.6491 | [6 empty] | CC4W | 100%
500955 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS4 | 2015-09-14 | 2017-03-30 | 2017-03-30 | 2018-09-14 |  | Scottish Water Wide | 0 | 304983 | 2895477.97 | 3969557.82 | 352790.78 | 0 | 0 | 7522809.57 | 0 | 7522809.57 | 0 | [6 empty] | CM_M&G | 100%
500631 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 273864.48 | 462835.17 | 534409.54 | 538377.4408 | 0 | 0 | 1809486.6308 | 0 | 1809486.6308 | 0 | [6 empty] | CM_OVH | 100%
500688 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-06-11 | 2015-11-04 | 2015-11-27 | 2016-09-01 | 2016-09-01 | Glasgow City | 0 | 135984 | 136053 | 155 | 32430.4707 | 0 | 0 | 304622.4707 | 0 | 304622.4707 | 0 | [6 empty] | CM_WWI | 100%
502926 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2018-06-29 | 2018-08-07 | 2018-08-10 | 2019-08-16 | 2019-08-19 | Glasgow City | 0 | 0 | 0 | 6027.91 | 311004.43 | 35498.54 | 391.18 | 352922.06 | 525.14 | 353447.2 | 0 | [6 empty] | CM_WSI | 100%
036019 | Q&S3A | Sustaining existing high service for customers | Water non infrastructure |  |  | General |  | SWMD | Water non infrastructure | MS7 | 2007-06-13 | 2007-06-13 | 2009-05-25 | 2017-03-28 |  | Scottish Water Wide | 962430 | -121.11 | 0 | 0 | 0 | 0 | 0 | -121.11 | 0 | 962308.89 | 0 | [6 empty] | WSNI | 50% | WWNI | 50%
050028 | Q&S4 | Supporting economic development | First Time Provision |  |  | General |  | SWD | First Time Provision | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1674164.106 | 1674164.106 | 0 | 1674164.106 | 1081305.7956 | [6 empty] | WG3 | 100%
402956 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS7 | 2012-09-28 | 2015-08-25 | 2015-08-31 | 2015-09-14 | 2015-09-14 | East Dunbartonshire | 183243.64 | -183243.64 | -782.71 | 80.86 | 0 | 0 | 0 | -183945.49 | 0 | -701.85 | 0 | [6 empty] | CS11 | 50% | CS15 | 50%
400764 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2011-04-29 | 2015-10-02 |  | Scottish Water Wide | 1980000 | 5564.1 | 0 | 0 | 0 | 0 | 0 | 5564.1 | 0 | 1985564.1 | 0 | [6 empty] | CM_WSI | 100%
402214 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-08-02 | 2011-08-02 | 2011-08-01 | 2015-07-02 |  | Scottish Water Wide | 914154 | -880.78 | 3720.12 | 0 | 0 | 0 | 0 | 2839.34 | 0 | 916993.34 | 0 | [6 empty] | CM_WSI | 100%
500959 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWD | Wastewater infrastructure | MS7 | 2015-09-17 | 2016-03-15 | 2016-03-15 | 2017-04-03 | 2017-04-04 | Scottish Water Wide | 0 | 521826.19 | 1971873.09 | -290.21 | 0 | 0 | 0 | 2493409.07 | 0 | 2493409.07 | 0 | [6 empty] | CM_M&G | 100%
502440 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 | 2021-05-31 | All North Unitary Authorities | 0 | 0 | 447850.38 | 1432334.56 | 1294290.06 | 1385888 | 0 | 4560363 | 0 | 4560363 | 0 | [6 empty] | CM_M&G | 100%
502442 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 | 2021-05-31 | All North Unitary Authorities | 0 | 0 | 278955.53 | 660222.47 | 1458950 | 1046956 | 0 | 3445084 | 0 | 3445084 | 0 | [6 empty] | CM_M&G | 100%
502436 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 | 2021-05-31 | All North Unitary Authorities | 0 | 0 | 390610.3 | 1246277.51 | 611041.19 | 981383 | 0 | 3229312 | 0 | 3229312 | 0 | [6 empty] | CM_M&G | 100%
502438 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 | 2021-05-31 | All North Unitary Authorities | 0 | 0 | 465388.44 | 481743.4 | 693211.16 | 716128 | 0 | 2356471 | 0 | 2356471 | 0 | [6 empty] | CM_M&G | 100%
502441 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 | 2021-05-31 | All North Unitary Authorities | 0 | 0 | 354165.6 | 583928.4 | 540293 | 645423 | 0 | 2123810 | 0 | 2123810 | 0 | [6 empty] | CM_M&G | 100%
502435 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2020-09-22 | 2020-09-22 | All North Unitary Authorities | 0 | 0 | 300991.69 | 1313771.87 | 674439.44 | 999402 | 0 | 3288605 | 0 | 3288605 | 0 | [6 empty] | CM_M&G | 100%
502437 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 | 2021-05-31 | All North Unitary Authorities | 0 | 0 | 390780.16 | 207725.84 | 326381 | 403779 | 0 | 1328666 | 0 | 1328666 | 0 | [6 empty] | CM_M&G | 100%
502439 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-02 | 2017-02-02 | 2017-03-31 | 2021-05-31 | 2021-05-31 | All North Unitary Authorities | 0 | 0 | 468265.76 | 531870.24 | 472456.61 | 635274 | 0 | 2107866.61 | 0 | 2107866.61 | 0 | [6 empty] | CM_M&G | 100%
501552 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2021-04-15 |  |  | 2021-04-15 | 2021-04-15 | Scottish Water Wide | 0 | 130841.12 | -130841.05 | 0 | 0 | 6391931.94 | 6391931.93 | 12783863.94 | 0 | 12783863.94 | 0 | [6 empty] | CM_WWI | 100%
502934 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2019-01-21 | 2020-10-19 | 2020-12-30 | 2021-10-04 | 2022-01-03 | Fife | 0 | 0 | 0 | 16215.396 | 18762.434 | 82064.39 | 663837.37 | 780879.59 | 617108.24 | 1397987.83 | 0 | [6 empty] | CM_WWI | 100%
500432 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-06-02 | 2015-06-02 | 2015-06-11 | 2016-09-19 | 2016-09-19 | Scottish Water Wide | 0 | 1021661 | 95378.34 | 2105.92 | 0 | 0 | 0 | 1119145.26 | 0 | 1119145.26 | 0 | [6 empty] | CM_WWI | 100%
503481 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2021-03-31 | 2022-01-17 | 2022-03-24 | 2022-08-10 | 2022-11-10 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 2600.07 | 2596.66 | 5196.73 | 102803.2 | 107999.93 | 0 | [6 empty] | CM_WSI | 100%
500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS3 | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-11-13 | 2021-02-19 | Scottish Water Wide | 0 | 314167 | 270363.44 | 649727.46 | 1157101.2 | 480786.22 | 212856.47 | 3085001.79 | 0 | 3085001.79 | 7530976.0407 | [6 empty] | CS16D | 100%
402021 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-03-18 | 2012-07-06 | 2012-08-27 | 2013-03-28 | 2013-03-29 | Aberdeenshire | 33020 | -991.96 | 0 | 0 | 0 | 0 | 0 | -991.96 | 0 | 32028.04 | 0 | [6 empty] | CS16W | 100%
046907 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MSU |  | 2014-06-27 | 2014-10-23 | 2015-04-25 | 2015-07-24 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 30924 |  | CS16W | 100%
401684 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-02-01 | 2014-07-24 | 2014-08-18 | 2015-03-19 | 2015-03-27 | Orkney Islands | 1243064 | 458533.6 | 10005.11 | -4595.23 | 0 | 0 | 0 | 463943.48 | 0 | 1707007.48 | 12479 | [6 empty] | CS16W | 100%
401683 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-02-03 | 2013-10-17 | 2013-11-11 | 2014-03-07 | 2014-03-24 | Perth and Kinross | 368016 | -589.55 | -2645.27 | 0 | 0 | 0 | 0 | -3234.82 | 0 | 364781.18 | 5192 | [6 empty] | CS16W | 100%
402020 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-03-16 | 2012-12-19 | 2013-02-04 | 2014-03-13 | 2014-03-31 | West Dunbartonshire | 756766.86 | 12358.9 | 5811.77 | 0 | 0 | 0 | 0 | 18170.67 | 0 | 774937.53 | 0 | [6 empty] | CS16W | 100%
502647 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2021-03-31 | 2022-03-01 | 2022-05-20 | 2022-12-21 | 2023-03-23 | Scottish Water Wide | 0 | 0 | 10171.6 | 634301.9231 | 190526.4769 | 20299.24 | 19700.73 | 874999.97 | 0 | 874999.97 | 240495.8008 | [6 empty] | CS11A | 100%
501003 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS3 | 2015-09-25 | 2016-02-29 | 2016-02-29 | 2019-04-15 | 2019-04-15 | Scottish Water Wide | 0 | 32769.87 | 55709.13 | 12690 | 37597 | 0 | 0 | 138766 | 0 | 138766 | 0 | [6 empty] | CM_WSNI | 100%
500773 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-07-24 | 2017-06-27 | 2017-07-31 | 2017-12-19 | 2017-12-19 | Glasgow City | 0 | 27000 | 35014.12 | 464774.925 | 1482.065 | 0 | 0 | 528271.11 | 0 | 528271.11 | 0 | [6 empty] | CM_WWI | 100%
502320 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2016-08-23 | 2016-08-23 | 2016-10-26 | 2017-09-25 | 2017-09-25 | Scottish Water Wide | 0 | 0 | 1020877.33 | 195948.1475 | -74690.3975 | 0 | 0 | 1142135.08 | 0 | 1142135.08 | 0 | [6 empty] | CM_WWI | 100%
502716 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS5 | 2017-05-04 | 2017-05-04 | 2017-06-01 | 2018-10-01 | 2018-10-01 | Scottish Water Wide | 0 | 0 | 0 | 831214.95 | 424000 | 0 | 0 | 1255214.95 | 0 | 1255214.95 | 0 | [6 empty] | CM_WWI | 100%
503559 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2019-05-01 | 2019-06-03 | 2019-08-08 | 2020-05-05 | 2020-08-05 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 663113.21 | 330341.35 | 993454.56 | 6545.45 | 1000000.01 | 0 | [6 empty] | CM_WWI | 100%
503131 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-08-31 | 2018-08-31 | 2018-09-17 | 2019-08-23 | 2019-08-23 | Scottish Water Wide | 0 | 0 | 0 | 0 | 657266.95 | 1042733.06 | 0 | 1700000.01 | 0 | 1700000.01 | 0 | [6 empty] | CM_WWI | 100%
501295 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2021-04-15 |  |  | 2021-04-15 | 2021-04-15 | Scottish Water Wide | 0 | 0 | 0 | 80.87 | 0 | 0 | 988006.32 | 988087.19 | 0 | 988087.19 | 0 | [6 empty] | CM_WWI | 100%
500127 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-03-14 | 2016-05-09 | 2018-03-28 | 2018-03-29 | Moray | 0 | 8629 | 13732.56 | 37136.07 | 5231.94 | 0 | 0 | 64729.57 | 0 | 64729.57 | 45187.3066 | [6 empty] | EC01G | 3.399% | EC01D | 38.39% | CS16D | 58.21%
500938 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS5 | 2015-09-02 | 2018-01-31 | 2018-03-12 | 2019-03-22 | 2019-03-22 | Moray | 0 | 8755 | 97090 | 274388 | 913105 | 1478.08 | 7322.92 | 1302139 | 0 | 1302139 | 0 | [6 empty] | CM_WWI | 100%
503216 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-12-20 | 2023-06-02 | 2023-09-29 | 2024-09-25 | 2024-12-26 | Moray | 0 | 0 | 0 | 0 | 65856.09 | 17654.14 | 38257.84 | 121768.07 | 21904.07 | 143672.14 | 148885.7057 | [6 empty] | SG1 | 100%
500968 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-10-05 | 2018-01-31 | 2018-02-26 | 2019-09-04 | 2019-10-09 | Moray | 0 | 31252 | 205759.18 | 462381.3015 | 1276842.3985 | 262161.47 | 12044.03 | 2250440.38 | 5295.64 | 2255736.02 | 0 |  |  |  |  | 3219.9997 |  | CM_WWNI | 100%
500909 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2015-09-02 | 2021-10-15 | 2022-02-10 | 2022-10-19 | 2023-01-19 | Moray | 0 | 10688 | 109660 | 9722 | 0 | 0 | 0 | 130070 | 86658.96 | 216728.96 | 0 | [6 empty] | CM_WWI | 100%
502758 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2020-02-03 | 2021-01-25 | 2021-05-19 | 2021-09-23 | 2021-12-24 | Fife | 0 | 0 | 0 | 31143.1 | 1716.52 | 42065.98 | 0 | 74925.6 | 0 | 74925.6 | 148885.7057 | [6 empty] | SG1 | 100%
403486 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2013-06-17 | 2016-12-14 | 2016-12-14 | 2016-12-15 | 2016-12-15 | Fife | 46190 | 8043 | -1340.27 | 121.29 | 0 | 0 | 0 | 6824.02 | 0 | 53014.02 | 0 | [6 empty] | SG1 | 100%
503488 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2019-03-05 | 2019-03-05 | 2019-06-27 | 2020-02-18 | 2020-05-20 | Scottish Water Wide | 0 | 0 | 0 | 0 | 217451.72 | 442443.3 | 79847.71 | 739742.73 | 2942.58 | 742685.31 | 0 | [6 empty] | CM_WSNI | 100%
501268 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2016-02-12 | 2021-05-13 | 2021-07-20 | 2021-09-23 | 2021-12-24 | Aberdeenshire | 0 | 541.27 | 36618.73 | -8056.16 | 17000 | 0 | 0 | 46103.84 | 28896.18 | 75000.02 | 0 | [6 empty] | CM_WWI | 100%
502360 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-05-19 | 2023-01-03 | 2023-05-08 | 2024-07-26 | 2024-10-28 | Aberdeenshire | 0 | 0 | 44037.75 | 8138.555 | 6234.577 | 0 | 0 | 58410.882 | 48261.78 | 106672.662 | 0 | [6 empty] | CM_WSNI | 100%
500728 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2015-07-07 | 2016-02-19 | 2016-05-31 | 2017-02-07 | 2017-02-07 | Aberdeenshire | 0 | 38679.43 | 103300.57 | 12987 | -7239.1406 | 0 | 0 | 147727.8594 | 0 | 147727.8594 | 0 | [6 empty] | CM_WWNI | 100%
403969 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | WWINF | Strategic Capacity | MS0 | 2016-08-19 | 2022-03-11 | 2022-05-20 | 2023-01-09 | 2023-04-11 | Clackmannanshire | 967.25 | 26789.19 | 16366.37 | 40698.19 | 96175 | 0.13 | 2747.8 | 182776.68 | 4313779.08 | 4497523.01 | 0 | [6 empty] | SG1 | 100%
030282 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2012-03-27 | 2012-10-15 | 2013-09-30 | 2013-10-16 | Angus | 1817236.61 | -1399.68 | 0 | 0 | 0 | 0 | 0 | -1399.68 | 0 | 1815836.93 | 2051.5631 | [6 empty] | CM_WWNI | 45% | EC04A | 55%
404115 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2015-06-01 | 2019-07-18 | 2019-07-19 | 2019-07-19 | 2019-07-19 | South Lanarkshire | 0 | 64458.99 | 0 | 0 | 0 | 0 | 0 | 64458.99 | 0 | 64458.99 | 0 | [6 empty] | CM_WWI | 100%
500129 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2015-03-31 | 2017-02-27 | 2017-03-17 | 2019-08-19 | 2019-11-14 | Moray | 0 | 24530.29 | 37738.71 | 25403 | 101905 | 8710.44 | 38807.56 | 237095 | 0 | 237095 | 321401.2989 | [6 empty] | EC01G | 3.18% | EC01D | 20.41% | CS16D | 76.41%
502811 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-03-07 | 2022-07-15 | 2022-11-07 | 2023-10-26 | 2024-01-26 | Moray | 0 | 0 | 0 | 64690.0625 | 7241.0675 | 0 | 10004.03 | 81935.16 | 65831.27 | 147766.43 | 148885.7057 | [6 empty] | SG1 | 100%
500580 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS1 | 2015-06-02 | 2019-07-15 | 2019-08-13 | 2020-08-06 | 2020-08-07 | Moray | 0 | 554787 | -170134.47 | 202978.36 | 574817.4242 | 4128086.64 | 201801.2 | 5492336.1542 | 15704.34 | 5508040.4942 | 0 | [6 empty] | CM_WWNI | 100%
502251 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2018-05-30 | 2019-12-02 | 2020-02-25 | 2020-07-21 | 2020-10-23 | Moray | 0 | 0 | 8334.97 | 3419.24 | 890.38 | 49028.63 | 39763.73 | 101436.95 | 934.63 | 102371.58 | 0 | [6 empty] | CM_WWI | 100%
045577 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-07-25 | 2012-03-26 | 2012-04-16 | Highland | 54368.07 | 156.3 | 0 | 0 | 0 | 0 | 0 | 156.3 | 0 | 54524.37 | 0 | [6 empty] | DW13 | 100%
500825 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS6 | 2015-10-28 | 2016-03-31 | 2016-05-30 | 2017-03-01 | 2017-11-01 | Highland | 0 | 7753 | 16822.39 | 6578.9308 | 2798.6792 | 0 | 0 | 33953 | 0 | 33953 | 35120.3569 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 10.7
502878 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-07-01 | 2022-11-24 | 2023-03-20 | 2024-03-08 | 2024-06-10 | Highland | 0 | 0 | 0 | 21360.6865 | 1536.1035 | 12056.22 | 12009.49 | 46962.5 | 3037.42 | 49999.92 | 148885.7057 | [6 empty] | WG1 | 100%
045796 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2011-03-21 | 2011-08-23 | 2012-03-22 | 2012-03-29 | Scottish Borders | 416246.08 | 266.75 | 0 | 0 | 0 | 0 | 0 | 266.75 | 0 | 416512.83 | 0 | [6 empty] | CM_WWNI | 10.06% | WQ01C | 89.94%
503388 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-05-30 | 2023-10-17 | 2024-02-19 | 2025-03-26 | 2025-06-26 | Perth and Kinross | 0 | 0 | 0 | 0 | 70898.48 | 7368 | 7339.45 | 85605.93 | 60162.67 | 145768.6 | 148885.7057 | [6 empty] | SG1 | 100%
500004 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2015-05-06 | 2017-05-31 | 2017-09-07 | 2018-08-27 | 2018-08-27 | Scottish Water Wide | 0 | 129500 | 265188 | 1266094 | 639603 | 2690.98 | 2848.99 | 2305924.97 | 0 | 2305924.97 | 0 | [6 empty] | CM_WWNI | 100%
400120 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-02-24 | 2012-09-24 | 2012-10-22 | 2014-06-16 |  | Clackmannanshire | 646814 | 427 | -132.04 | 0 | 0 | 0 | 0 | 294.96 | 0 | 647108.96 | 0 | [6 empty] | CM_WSI | 100%
400121 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-02-24 | 2012-09-28 | 2012-10-22 | 2014-06-25 |  | East Dunbartonshire | 808054 | 1465.32 | 0 | 311.93 | 0 | 0 | 0 | 1777.25 | 0 | 809831.25 | 0 | [6 empty] | CM_WSI | 100%
501282 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-12-01 | 2017-03-28 | 2017-05-22 | 2018-06-20 | 2018-06-20 | All East Unitary Authorities | 0 | 3722.95 | 142768.05 | 419241.86 | 53653.1962 | 0 | 0 | 619386.0562 | 0 | 619386.0562 | 0 | [6 empty] | EC01G | 100%
401501 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-20 | 2011-12-20 | 2012-01-30 | 2015-03-10 |  | All West Unitary Authorities | 2336312 | 161930 | 37790.51 | 10986.616 | 0 | 0 | 0 | 210707.126 | 0 | 2547019.126 | 0 | [6 empty] | CM_WSI | 100%
403571 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-08-05 | 2013-08-05 | 2013-08-05 | 2017-02-16 |  | North Lanarkshire | 694483 | 227890 | 9808.41 | 1351.53 | 0 | 0 | 0 | 239049.94 | 0 | 933532.94 | 0 | [6 empty] | CM_WWNI | 100%
500139 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS4 | 2015-03-19 | 2016-12-19 | 2017-01-11 | 2019-02-01 | 2019-06-01 | Highland | 0 | 11621 | 15843 | 14703 | 43795 | 0 | 0 | 85962 | 0 | 85962 | 10362.528 | [6 empty] | EC01G | 100% | bar: Regulatory Outputs OMG-23
300029 | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-11-16 | 2012-03-20 | 2012-06-06 | 2013-11-27 | 2013-09-30 | Highland | 2894000 | -2876.39 | 0 | 0 | 0 | 0 | 0 | -2876.39 | 0 | 2891123.61 | 0 | [6 empty] | EC01 | 100%
501740 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2021-06-30 | 2022-03-04 | 2022-05-18 | 2022-09-29 | 2022-12-30 | East Dunbartonshire | 0 | 0 | 3348.84 | 9389.1765 | 1967.4535 | 0 | 0 | 14705.47 | 410185.02 | 424890.49 | 0 | [6 empty] | CM_WWI | 100%
501229 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-11-17 | 2015-11-17 | 2015-12-16 | 2015-12-01 | 2016-03-01 | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | DW25D | 100% | bar: Regulatory Outputs OMG-05
046857 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2012-07-31 | 2013-06-28 | 2015-11-24 | 2015-12-22 | Shetland Islands | 3757923.44 | 20964.08 | -11369.61 | -782 | 0 | 0 | 0 | 8812.47 | 0 | 3766735.91 | 42872.4615 | [6 empty] | CM_WSI | 30.28% | DW23 | 69.72%
403687 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2014-03-18 | 2014-11-20 | 2014-11-20 | 2015-04-07 | 2015-05-28 | Perth and Kinross | 99049.85 | 787.97 | 0 | 0 | 0 | 0 | 0 | 787.97 | 0 | 99837.82 | 0 | [6 empty] | DW10 | 100%
500978 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2016-06-24 | 2017-03-30 | 2017-09-18 | 2017-11-24 | 2017-11-24 | Highland | 0 | 0 | 25442.08 | 117519.5 | 1282.86 | 1248.77 | 1002.8 | 146496.01 | 0 | 146496.01 | 0 | [6 empty] | CM_WWI | 100%
500141 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-01-20 | 2016-03-23 | 2018-03-28 | 2019-02-05 | Aberdeenshire | 0 | 82416 | 129492 | 80151 | 23194.483 | 0 | 0 | 315253.483 | 0 | 315253.483 | 10362.528 | [6 empty] | EC01G | 19.97% | CS16D | 80.03%
403253 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-02-11 | 2014-01-07 | 2014-05-19 | 2014-11-07 |  | Fife | 216779 | 0 | -242.01 | 0 | 0 | 0 | 0 | -242.01 | 0 | 216536.99 | 0 | [6 empty] | CM_WWNI | 100%
500788 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2015-08-31 | 2021-07-07 | 2021-08-19 | 2022-07-01 | 2022-10-03 | Angus | 0 | 40099 | 152180.95 | 12029.5 | -5772.9 | 0 | 0 | 198536.55 | 1549980.05 | 1748516.6 | 0 | [6 empty] | CM_WWNI | 100%
502615 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-09-28 | 2017-09-28 | 2017-09-28 | 2017-09-04 | 2017-09-28 | Angus | 0 | 0 | 2359.94 | 5926.0475 | 0 | 0 | 0 | 8285.9875 | 0 | 8285.9875 | 0 | [6 empty] | CM_WWI | 100%
501280 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-07-27 | 2016-07-27 | Angus | 0 | 9054.59 | 747.63 | 0 | 0 | 0 | 0 | 9802.22 | 0 | 9802.22 | 148885.7057 | [6 empty] | SG1 | 100%
500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Water |  | SWMD | Flood Risk Management Act | MS3 | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2021-05-12 | 2021-08-04 | Scottish Water Wide | 0 | 195637 | 533343.97 | 670435.94 | 747653.69 | 249758.87 | 29189.38 | 2426018.85 | 15221.71 | 2441240.56 | 985398.5607 | [6 empty] | WR6 | 100%
501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2018-07-23 | 2018-09-03 | Scottish Water Wide | 0 | 73764 | 126964.27 | 22205.77 | -15707.88 | 0 | 0 | 207226.16 | 0 | 207226.16 | 0 | [6 empty] | CS16D | 100%
502535 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2017-02-13 | 2017-02-13 | 2017-04-21 | 2017-09-15 | 2017-09-15 | North Ayrshire | 0 | 0 | 7365.72 | 29472.3 | 579.37 | 0 | 0 | 37417.39 | 0 | 37417.39 | 9244605.8896 | [6 empty] | CS11A | 46.55% | EC10B | 53.45%
502536 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2017-02-13 | 2017-02-13 | 2017-04-20 | 2017-09-15 | 2017-09-15 | City of Edinburgh | 0 | 0 | 10521.03 | 24906.82 | 0 | 0 | 0 | 35427.85 | 0 | 35427.85 | 9244605.8896 | [6 empty] | CS11A | 28.23% | EC10B | 71.77%
502537 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2017-02-13 | 2017-02-13 | 2017-04-20 | 2017-09-15 | 2017-09-15 | Falkirk | 0 | 0 | 7365.72 | 15240.13 | 0 | 0 | 0 | 22605.85 | 0 | 22605.85 | 9244605.8896 | [6 empty] | EC10B | 46.55% | CS11A | 53.45%
502538 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-09-15 | 2017-09-15 | Dundee City | 0 | 0 | 7365.72 | 10423.78 | 0 | 0 | 0 | 17789.5 | 0 | 17789.5 | 9244605.8896 | [6 empty] | CS11A | 43.79% | EC10B | 56.21%
502534 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS5 | 2017-02-28 | 2017-02-28 | 2017-04-21 | 2018-02-26 | 2018-02-26 | Aberdeen City | 0 | 0 | 144000 | 123789.84 | 85023.16 | 0 | 0 | 352813 | 0 | 352813 | 9244605.8896 | [6 empty] | CS11A | 50% | EC10B | 50%
403642 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-12-18 | 2013-12-18 | 2013-12-30 | 2015-09-24 |  | Scottish Water Wide | 266683 | -25510.2 | 0 | 0 | 0 | 0 | 0 | -25510.2 | 0 | 241172.8 | 0 | [6 empty] | CM_M&G | 100%
403644 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-05-20 | 2014-05-20 | 2014-05-20 | 2015-07-28 |  | Scottish Water Wide | 496725 | -7024.38 | 0 | 0 | 0 | 0 | 0 | -7024.38 | 0 | 489700.62 | 0 | [6 empty] | CM_M&G | 100%
403287 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-06 | 2013-07-12 | 2013-08-05 | 2014-12-17 |  | Scottish Water Wide | 538174.78 | -476.62 | 0 | 0 | 0 | 0 | 0 | -476.62 | 0 | 537698.16 | 0 | [6 empty] | CM_WSI | 100%
403288 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-06 | 2014-03-19 | 2014-03-03 | 2014-03-03 |  | Scottish Water Wide | 91330.89 | 1105 | 0 | 0 | 0 | 0 | 0 | 1105 | 0 | 92435.89 | 0 | [6 empty] | CM_WSI | 100%
403286 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-06 | 2014-03-19 | 2014-03-03 | 2014-03-03 |  | Scottish Water Wide | 281927.69 | 299 | 0 | 0 | 0 | 0 | 0 | 299 | 0 | 282226.69 | 0 | [6 empty] | CM_WSI | 100%
503541 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW0 | 2019-08-16 | 2020-07-13 | 2020-10-05 | 2021-05-07 | 2021-08-09 | North Ayrshire | 0 | 0 | 0 | 0 | 18083.72 | 170926.36 | 502392.39 | 691402.47 | 226681.24 | 918083.71 | 0 | [6 empty] | CM_WWI | 100%
046360 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-04-28 | 2010-09-29 | 2011-02-21 | 2012-02-16 |  | Aberdeenshire | 1367791.79 | 622.5 | 0 | 0 | 0 | 0 | 0 | 622.5 | 0 | 1368414.29 | 0 | [6 empty] | CM_WWNI | 100%
401923 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2011-01-27 | 2019-03-28 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 17229131.5662 | 0.4338 | 0 | 0 | 0 | 0 | 0 | 0.4338 | 0 | 17229132 | 0 | [6 empty] | SG1 | 100%
401922 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS7 | 2011-01-27 | 2019-03-27 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 4508509.771 | 0.229 | 0 | 0 | 0 | 0 | 0 | 0.229 | 0 | 4508510 | 0 | [6 empty] | WG1 | 100%
046159 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-31 | 2011-03-31 | 2011-07-18 | 2014-10-30 | 2014-10-30 | North Ayrshire | 10217887.65 | 335374.86 | -14136.85 | 0 | 0 | 0 | 0 | 321238.01 | 0 | 10539125.66 | 0 | [6 empty] | CM_WWNI | 100%
403894 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS3 | 2017-04-30 | 2017-08-01 | 2019-01-28 | 2020-01-01 | 2020-04-01 | Highland | 9120 | 142318 | 64871.92 | 345611.249 | 655481.171 | 1609886.85 | 357397.83 | 3175567.02 | 2388.22 | 3187075.24 | 347960.5276 |  |  |  |  | -57939.9996 |  | EC02A | 42.6% | CM_WWNI | 57.4% | bar: Regulatory Outputs OMG-21
403213 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS6 | 2013-01-21 | 2015-02-26 | 2015-02-26 | 2015-03-25 | 2015-03-25 | Scottish Borders | 849238 | 228720 | 68561 | 3495 | 2367.28 | 0 | 0 | 303143.28 | 0 | 1152381.28 | 106096.9999 | [6 empty] | CC1W | 100%
500133 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-26 | 2016-12-19 | 2017-01-13 | 2018-07-12 | 2018-08-08 | Scottish Borders | 0 | 19895 | 33649 | 57826 | -57.4025 | 0 | 0 | 111312.5975 | 0 | 111312.5975 | 337510.3613 | [6 empty] | EC01D | 26.93% | CS16D | 73.07%
501405 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2018-05-31 | 2021-11-15 | 2022-03-21 | 2022-07-29 | 2022-10-31 | Scottish Borders | 0 | 0 | 6324.78 | 595.82 | 2207.44 | 0 | 0 | 9128.04 | 218190.94 | 227318.98 | 0 | [6 empty] | CM_WSNI | 100%
503235 | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | WINF | SOSI | MS2 | 2018-05-31 | 2019-03-29 | 2019-04-29 | 2020-10-23 | 2021-01-29 | Scottish Borders | 0 | 0 | 0 | 0 | 1023930.42 | 6315614.36 | 1407389.35 | 8746934.13 | 441568.25 | 9188502.38 | 2114590.1059 | [6 empty] | DW25P | 10.73% | WR1 | 18.27% | CM_WSI | 71%
500245 | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | NONINF | SOSI | MS3 | 2016-12-23 | 2018-09-28 | 2019-03-04 | 2020-10-16 | 2021-01-22 | Scottish Borders | 0 | 67704.37 | 390007.15 | 625335.21 | 1161161.07 | 3409600.12 | 3996034.56 | 9649842.48 | 270394.48 | 9920236.96 | 2114590.1059 |  |  |  |  | 999.9997 |  | CM_WSI | 13.3% | DW25P | 14% | WR1 | 23.9% | CM_WSNI | 48.8%
400063 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-10-14 | 2011-05-03 | 2011-08-01 | 2015-08-27 |  | Scottish Borders | 2913508.47 | -179181.13 | 270 | 589.78 | 0 | 0 | 0 | -178321.35 | 0 | 2735187.12 | 0 |  |  |  |  | 27876 |  | CM_WWNI | 100%
030290 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-09-29 | 2011-05-05 | 2011-08-01 | 2015-12-11 | 2016-02-25 | Scottish Borders | 4138179.87 | 143137.41 | 11113.17 | -2910.39 | 0 | 0 | 0 | 151340.19 | 0 | 4289520.06 | 36213.3618 |  |  |  |  | 27879.5018 |  | CM_WWNI | 40.36% | EC01A | 59.64%
503259 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-21 | 2023-08-11 | 2023-12-06 | 2024-11-29 | 2025-03-03 | Scottish Borders | 0 | 0 | 0 | 0 | 68097.92 | 26016.06 | 25915.28 | 120029.26 | 23394.31 | 143423.57 | 148885.7057 | [6 empty] | SG1 | 100%
503290 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2021-04-01 | 2022-12-07 | 2023-04-07 | 2024-07-05 | 2024-10-07 | Scottish Borders | 0 | 0 | 0 | 0 | 21883.55 | 13986.69 | 14129.73 | 49999.97 | 1950000 | 1999999.97 | 0 | [6 empty] | CM_WWNI | 100%
401374 | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2010-09-07 | 2011-02-21 | 2011-04-29 | 2015-07-31 | 2011-03-14 | Scottish Water Wide | 960799 | -8957.13 | 0 | 0 | 0 | 0 | 0 | -8957.13 | 0 | 951841.87 | 0 | [6 empty] | CS20 | 100%
501576 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-01-18 | 2016-01-18 | 2016-02-01 | 2017-03-31 | 2017-03-31 | Scottish Water Wide | 0 | 2228941.22 | 1162511.88 | -685647.93 | 0 | 0 | 0 | 2705805.17 | 0 | 2705805.17 | 0 | [6 empty] | CM_WSI | 100%
502787 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS5 | 2017-06-30 | 2017-10-30 | 2017-10-31 | 2018-02-28 | 2018-02-28 | North Lanarkshire | 0 | 0 | 0 | 2329220.04 | -427932.15 | 0 | 0 | 1901287.89 | 0 | 1901287.89 | 0 | [6 empty] | CM_WSI | 100%
402213 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-08-18 | 2015-03-24 | 2015-04-29 | 2015-04-02 |  | North Lanarkshire | 70000 | -1861.64 | 0 | 0 | 0 | 0 | 0 | -1861.64 | 0 | 68138.36 | 0 | [6 empty] | CM_WSI | 100%
502396 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2017-06-21 | 2023-07-18 | 2023-08-18 | 2024-03-06 | 2024-03-07 | East Dunbartonshire | 0 | 0 | 7129.27 | 20076.73 | 82222.39 | 0 | 0 | 109428.39 | 572177.19 | 681605.58 | 0 | [6 empty] | CM_WSI | 100%
503413 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | GW0 | 2019-08-30 | 2020-07-20 | 2020-10-19 | 2021-03-01 | 2021-07-01 | Moray | 0 | 0 | 0 | 0 | 91514.56 | 180267.82 | 700790.3 | 972572.68 | 594541.9 | 1567114.58 | 536771.841 | [6 empty] | DW5 | 100% | [18 empty] | Regulatory Outputs OMG-06: 83.9
503381 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-07 | 2022-12-15 | 2023-04-19 | 2023-10-10 | 2024-01-10 | Aberdeenshire | 0 | 0 | 0 | 0 | 76307.53 | 0 | 6668.43 | 82975.96 | 64364.9 | 147340.86 | 148885.7057 | [6 empty] | SG1 | 100%
403611 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2013-11-07 | 2015-02-10 | 2015-07-27 | 2016-06-06 | 2016-06-06 | Dumfries and Galloway | 155449 | 383756 | 5623.52 | 0 | -828.22 | 0 | 0 | 388551.3 | 0 | 544000.3 | 0 | [6 empty] | SG1 | 100%
403254 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2013-01-22 | 2016-03-29 | 2016-06-13 | 2016-11-03 | 2016-11-03 | Moray | 19920.46 | 43801.33 | 204957.16 | -976.95 | -100.6112 | 0 | 0 | 247680.9288 | 0 | 267601.3888 | 0 | [6 empty] | CM_WWNI | 100%
503316 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-24 | 2023-07-14 | 2023-11-13 | 2024-11-08 | 2025-02-10 | Moray | 0 | 0 | 0 | 0 | 31602.89 | 22580.85 | 22493.33 | 76677.07 | 68706.96 | 145384.03 | 148885.7057 | [6 empty] | SG1 | 100%
502407 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2017-07-25 | 2019-09-23 | 2019-11-25 | 2019-12-20 | 2019-12-20 | Moray | 0 | 0 | 7070.44 | 2052.89 | 0 | 43366.03 | 3261.47 | 55750.83 | 249.19 | 56000.02 | 0 | [6 empty] | CM_WWI | 100%
501085 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS5 | 2016-04-18 | 2018-03-30 | 2018-03-30 | 2018-11-26 | 2018-11-26 | Stirling | 0 | 26352 | 4206 | 167697.565 | 720960.345 | 23898.78 | 0 | 943114.69 | 0 | 943114.69 | 0 | [6 empty] | CM_WSI | 100%
501084 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | Stirling | 0 | 529.62 | -529.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501086 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS5 | 2016-04-13 | 2016-12-28 | 2017-03-06 | 2018-02-15 | 2018-02-15 | Stirling | 0 | 23904 | 102270 | 568645.8 | -21728.08 | 0 | 0 | 673091.72 | 0 | 673091.72 | 0 | [6 empty] | CM_WSI | 100%
401412 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-10-13 | 2011-06-01 | 2011-06-15 | 2012-03-30 |  | Stirling | 4664274.29 | 495 | 0 | 0 | 0 | 0 | 0 | 495 | 0 | 4664769.29 | 0 | [6 empty] | CM_WSNI | 100%
045642 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-07-24 | 2011-06-30 | 2011-06-30 | 2011-03-31 |  | Stirling | 138193.93 | -378.73 | 0 | 0 | 0 | 0 | 0 | -378.73 | 0 | 137815.2 | 0 | [6 empty] | CM_WSNI | 100%
402599 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS0 | 2012-03-27 | 2021-01-11 | 2021-04-21 | 2022-07-18 |  | All East Unitary Authorities | 55600 | -476.57 | 19442.96 | 59472.445 | 45159.195 | 235.77 | 146773.98 | 270607.78 | 2225235.34 | 2551443.12 | 0 | [6 empty] | CM_WWI | 100%
403004 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-04 | 2013-03-22 | 2013-05-20 | 2013-08-01 |  | Aberdeenshire | 66053.36 | -2120.07 | 0 | 0 | 0 | 0 | 0 | -2120.07 | 0 | 63933.29 | 0 | [6 empty] | CM_WWI | 100%
502618 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-05-31 | 2022-04-08 | 2022-06-29 | 2023-01-24 | 2023-04-26 | Stirling | 0 | 0 | 7600 | 0 | -93.43 | 0 | 0 | 7506.57 | 354400.03 | 361906.6 | 0 | [6 empty] | CM_WSI | 100%
402347 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-10-20 | 2012-11-22 | 2013-01-14 | 2013-08-07 | 2013-08-07 | Clackmannanshire | 662764 | -833.9 | 0 | 0 | 0 | 0 | 0 | -833.9 | 0 | 661930.1 | 0 | [6 empty] | CM_WSI | 100%
030293 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2011-08-22 | 2011-09-30 | 2013-03-20 | 2013-03-25 | West Dunbartonshire | 458320.82 | -4747.76 | 0 | 0 | 0 | 0 | 0 | -4747.76 | 0 | 453573.06 | 0 | [6 empty] | EC04A | 20% | CM_WWNI | 80%
501531 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2022-10-17 | 2023-09-22 | 2024-01-26 | 2024-09-11 | 2024-12-12 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 904142.04 | 904142.04 | 0 | [6 empty] | CM_WSNI | 100%
500808 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS6 | 2015-10-28 | 2017-03-23 | 2017-05-19 | 2017-12-01 | 2018-06-01 | Highland | 0 | 2010 | 174.7 | 6379.57 | 4227.63 | 0 | 0 | 12791.9 | 0 | 12791.9 | 19447.3703 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 5.52
046852 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2011-03-29 | 2011-06-27 | 2014-01-06 | 2014-02-17 | Highland | 1488201.42 | -42102.16 | 774.7 | 0 | 0 | 0 | 0 | -41327.46 | 0 | 1446873.96 | 5489 | [6 empty] | DW23 | 100%
403144 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-02-04 | 2013-12-04 | 2014-02-28 | 2014-12-01 |  | East Ayrshire | 144925 | 0 | -1861.47 | 0 | 0 | 0 | 0 | -1861.47 | 0 | 143063.53 | 0 | [6 empty] | CM_WWI | 100%
500143 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2015-09-27 | 2015-10-19 | 2016-10-01 | 2016-12-01 | Dumfries and Galloway | 0 | 47971 | 33479.98 | 0 | 0 | 0 | 0 | 81450.98 | 0 | 81450.98 | 72474.3726 | [6 empty] | CS11 | 40.64% | CS16D | 59.36% | bar: Regulatory Outputs OMG-22
045631 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-18 | 2011-02-14 | 2011-03-31 | 2013-03-26 |  | Dumfries and Galloway | 1560675.11 | 17638.04 | -114.55 | 0 | 0 | 0 | 0 | 17523.49 | 0 | 1578198.6 | 0 | [6 empty] | CM_WWNI | 100%
049030 | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS3 |  |  | 2010-04-01 | 2021-03-31 |  | Scottish Water Wide | 0 | -4000000 | 0 | 0 | 0 | 0 | 0 | -4000000 | 0 | -4000000 | 10008873.2019 | [6 empty] | RISK | 100%
500134 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS4 | 2015-03-19 | 2016-05-30 | 2016-08-01 | 2019-03-01 | 2019-06-01 | East Lothian | 0 | 12005 | 15136 | 17083 | 37454 | 0 | 0 | 81678 | 0 | 81678 | 81972.4608 | [6 empty] | EC01G | 13.52% | EC01D | 86.48% | bar: Regulatory Outputs OMG-23
503311 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-28 | 2023-08-18 | 2023-12-18 | 2024-12-18 | 2025-03-20 | East Lothian | 0 | 0 | 0 | 0 | 69110.491 | 15750.77 | 19627.17 | 104488.431 | 44884.96 | 149373.391 | 148885.7057 | [6 empty] | SG1 | 100%
500146 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-03-30 | 2016-04-25 | 2018-07-26 | 2019-01-31 | South Ayrshire | 0 | 23967.68 | 109655.41 | 66195.91 | 63377.6875 | 0 | 0 | 263196.6875 | 0 | 263196.6875 | 10362.528 | [6 empty] | CS16D | 45.51% | EC01G | 54.49%
501309 | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Wastewater |  | SWD | Energy efficiency | MS3 | 2015-11-25 | 2015-11-25 | 2016-07-19 | 2019-06-14 | 2019-06-14 | South Ayrshire | 0 | 7602 | 36398 | -30.12 | 35.49 | 0 | 0 | 44005.37 | 0 | 44005.37 | 1709913.541 | [6 empty] | I2S_WWNI | 100%
500590 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-09-01 | 2016-08-18 | 2016-08-18 | 2017-10-16 | 2018-01-22 | Scottish Water Wide | 0 | 281487.9 | 262956.1 | 142592.586 | 0.154 | 0 | 0 | 687036.74 | 0 | 687036.74 | 0 | [6 empty] | CM_M&G | 100%
500904 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-09-17 | 2016-09-23 | 2016-09-23 | 2018-07-12 |  | Scottish Water Wide | 0 | 2900124 | 2616598.85 | 1826234.73 | 152793.95 | 0 | 0 | 7495751.53 | 0 | 7495751.53 | 0 | [6 empty] | CM_M&G | 100%
500192 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS5 | 2015-03-20 | 2016-09-27 | 2016-09-27 | 2017-12-01 | 2017-12-01 | Midlothian | 0 | 1928 | 8901 | 3079.57 | 41.28 | 0 | 0 | 13949.85 | 0 | 13949.85 | 19060.7221 | [6 empty] | EC08C | 100% | bar: Regulatory Outputs OMG-23
503487 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2019-08-27 | 2021-05-10 | 2021-09-09 | 2022-12-14 | 2023-03-16 | Midlothian | 0 | 0 | 0 | 0 | 0 | 228962.95 | 610290.05 | 839253 | 3160747.01 | 4000000.01 | 0 | [6 empty] | CM_WSI | 100%
501401 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2021-04-22 | 2022-05-18 | 2022-09-21 | 2023-05-08 | 2023-08-08 | Midlothian | 0 | 0 | 1687.85 | 0 | 995.51 | 0 | 0 | 2683.36 | 247316.59 | 249999.95 | 0 | [6 empty] | CM_WSNI | 100%
500234 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS0 | 2017-08-15 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-01 | Angus | 0 | 49905.57 | 27672.17 | 7625.37 | 0 | 0 | 0 | 85203.11 | 0 | 85203.11 | 148885.7057 | [6 empty] | SG1 | 100%
500701 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-06-17 | 2021-07-05 | 2021-08-30 | 2022-04-20 | 2023-04-13 | Aberdeenshire | 0 | 8759 | 111388 | 28101 | -5690 | 0 | 0 | 142558 | 317386.08 | 459944.08 | 0 | [6 empty] | CM_WSI | 100%
502086 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2016-04-08 | 2018-08-14 | 2018-09-11 | 2019-05-31 | 2019-07-16 | Renfrewshire | 0 | 0 | 92360 | 251602 | 3061857.49 | 240498.9 | 0 | 3646318.39 | 0 | 3646318.39 | 0 | [6 empty] | CM_WSI | 100%
400526 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-03-31 | 2012-05-22 | 2012-06-18 | 2013-01-30 | 2013-01-30 | Glasgow City | 26440.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26440.96 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
401880 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-08-02 | 2012-08-30 | 2012-08-29 | 2015-03-26 |  | Glasgow City | 4527120 | -173603.53 | 182.95 | 0 | 0 | 0 | 0 | -173420.58 | 0 | 4353699.42 | 0 | [6 empty] | CM_WSI | 100%
401478 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2010-11-18 | 2012-05-29 | 2012-09-18 | 2013-11-18 |  | Glasgow City | 3148288 | -7297.14 | 0 | 0 | 0 | 0 | 0 | -7297.14 | 0 | 3140990.86 | 0 |  |  |  |  | 68697 |  | CM_WWNI | 100%
403738 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2014-04-03 | 2014-04-14 | 2014-04-14 | 2019-05-20 |  | Glasgow City | 259090.26 | 49249.74 | 18500.26 | -65514.41 | 0 | 0 | 0 | 2235.59 | 0 | 261325.85 | 0 | [6 empty] | CM_WWNI | 100%
501189 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2015-10-29 | 2017-08-30 | 2017-08-31 | 2018-03-23 | 2018-03-23 | Glasgow City | 0 | 507137.65 | 268501.88 | 1429607.695 | -254722.905 | 6269.58 | 3206.08 | 1959999.98 | 0 | 1959999.98 | 0 | [6 empty] | CM_WWNI | 100%
502601 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2017-02-02 | 2018-09-17 | 2018-09-17 | 2019-05-15 | 2019-06-04 | Renfrewshire | 0 | 0 | 23505 | 225098 | 850357.2 | 0 | 0 | 1098960.2 | 0 | 1098960.2 | 0 | [6 empty] | CM_WWI | 100%
046388 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-12 | 2009-10-28 | 2009-10-28 | 2019-03-04 | 2011-03-14 | Glasgow City | 2746876.29 | 2224.16 | 275.68 | 364.08 | 531.78 | 0 | 0 | 3395.7 | 0 | 2750271.99 | 2783.9999 | [6 empty] | EC04C | 32.82% | EC10E | 32.82% | EC01D | 34.37%
046389 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-12 | 2009-08-28 | 2009-08-28 | 2018-08-23 | 2011-03-14 | Glasgow City | 695000 | 27 | 0 | 0 | -201.83 | 0 | 0 | -174.83 | 0 | 694825.17 | 1299.9999 | [6 empty] | EC01D | 33.33% | EC04C | 33.33% | EC10E | 33.33%
046387 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-12 | 2009-10-14 | 2009-10-14 | 2015-08-10 | 2011-03-14 | Glasgow City | 1923834.76 | 34045.46 | 0 | 0 | 0 | 0 | 0 | 34045.46 | 0 | 1957880.22 | 0 | [6 empty] | EC04C | 33% | EC10E | 33% | EC01D | 34%
046385 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-12 | 2009-10-14 | 2009-10-14 | 2015-08-10 | 2011-03-14 | Glasgow City | 2130095 | 61629.08 | 0 | 0 | 0 | 0 | 0 | 61629.08 | 0 | 2191724.08 | 0 | [6 empty] | EC04C | 33.33% | EC01D | 33.33% | EC10E | 33.33%
401502 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-20 | 2011-06-22 | 2011-10-31 | 2014-12-12 |  | Glasgow City | 2155205 | 2004 | 35456.61 | 52176.37 | 8054.959 | 0 | 0 | 97691.939 | 0 | 2252896.939 | 0 | [6 empty] | CM_WSI | 100%
402244 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-08-05 | 2012-04-24 | 2012-05-21 | 2015-05-25 |  | Glasgow City | 1577382 | -41130 | -8956.61 | 5461.71 | -124.78 | 0 | 0 | -44749.68 | 0 | 1532632.32 | 0 | [6 empty] | CM_WSI | 100%
046868 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-05-07 | 2011-09-28 | 2011-10-24 | 2012-04-04 | 2012-12-24 | South Lanarkshire | 1886130 | 120870 | -3999.51 | 42193.9 | 0 | 0 | 0 | 159064.39 | 0 | 2045194.39 | 0 | [6 empty] | DW3C | 100%
503474 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | GW2 | 2021-04-01 | 2022-03-14 | 2022-05-20 | 2022-12-22 | 2023-03-24 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 11953.14 | 11906.81 | 23859.95 | 943363.99 | 967223.94 | 0 | [6 empty] | CM_WSI | 4.762% | CM_M&G | 95.24%
402965 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-10-01 | 2014-04-23 | 2014-04-23 | 2014-04-23 | 2015-06-16 | North Lanarkshire | 24435.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24435.1 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
502551 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2020-01-03 | 2021-03-22 | 2021-07-22 | 2022-02-16 | 2022-05-19 | Dumfries and Galloway | 0 | 0 | 31033.94 | 50651.09 | 17753.066 | 13912.24 | 157456.77 | 270807.106 | 891079.62 | 1161886.726 | 148885.7057 | [6 empty] | SG1 | 100%
501230 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2017-01-01 | 2017-01-01 | Highland | 0 | 0 | 17.75 | 0 | 0 | 0 | 0 | 17.75 | 0 | 17.75 | 0 | [6 empty] | DW25D | 100% | bar: Regulatory Outputs OMG-05
501547 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2016-01-26 | 2016-09-26 | 2016-11-28 | 2017-08-17 | 2017-08-17 | Highland | 0 | 13716 | 65778.53 | 122665.06 | 9805.03 | 0 | 0 | 211964.62 | 0 | 211964.62 | 0 | [6 empty] | CM_WSI | 100%
502571 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW2 | 2021-04-02 | 2021-10-25 | 2022-01-05 | 2022-12-15 | 2023-03-17 | Highland | 0 | 0 | 20930.23 | 671.6785 | 1536.0915 | 13431 | 13378.94 | 49947.94 | 52.06 | 50000 | 148885.7057 | [6 empty] | WG1 | 100%
401312 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-04 | 2013-11-29 | 2014-01-24 | 2015-03-31 | 2015-03-30 | Midlothian | 948556 | 0 | -7600.43 | 0 | 0 | 0 | 0 | -7600.43 | 0 | 940955.57 | 0 | [6 empty] | CM_WSI | 100%
031851 | Q&S3A | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS6 | 2005-10-03 | 2008-07-31 | 2008-08-12 | 2012-02-10 | 2012-02-17 | Midlothian | 103900000 | 397722.57 | 1076650.43 | 1301070.7695 | 952174.722 | 24152.59 | 71709.4 | 3823480.4815 | 0 | 107723480.4815 | 0 | [6 empty] | WSNI | 3.447% | WG1 | 4.538% | DW3G | 7.932% | DW4A | 7.932% | DW3J | 13.09% | DW13 | 21.02% | DW3A | 21.02% | DW3B | 21.02%
403324 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-01 | 2014-08-20 | 2014-08-13 | 2014-08-14 |  | Midlothian | 79943.79 | 116 | 0 | 0 | 0 | 0 | 0 | 116 | 0 | 80059.79 | 0 | [6 empty] | CM_WSI | 100%
501236 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | City of Edinburgh | 0 | 0 | 0 | 41.59 | 0 | 0 | 0 | 41.59 | 0 | 41.59 | 0 | [6 empty] | CM_WSI | 100%
500025 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS5 | 2015-02-13 | 2016-09-23 | 2017-10-30 | 2018-09-18 | 2018-09-18 | City of Edinburgh | 0 | 59791 | 145842 | 590442 | 134757.78 | 0 | 0 | 930832.78 | 0 | 930832.78 | 0 | [6 empty] | CM_WSI | 100%
501139 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501235 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | 2016-06-01 | City of Edinburgh | 0 | 14734.88 | -14734.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
500024 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS5 | 2015-03-05 | 2016-10-21 | 2017-08-28 | 2019-02-28 | 2019-02-28 | City of Edinburgh | 0 | 31419 | 126405 | 848301.5475 | 341694.6425 | 1469.17 | 0 | 1349289.36 | 0 | 1349289.36 | 0 | [6 empty] | CM_WSI | 100%
501126 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-04 | 2022-04-01 | 2022-05-11 | 2023-02-09 | 2023-05-12 | City of Edinburgh | 0 | 22032 | 2800 | 1000 | 6524.5 | 0 | 0 | 32356.5 | 403516.69 | 435873.19 | 0 | [6 empty] | CM_WSI | 100%
501127 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501128 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2016-04-11 | 2021-08-02 | 2021-08-24 | 2022-10-28 | 2023-02-13 | City of Edinburgh | 0 | 0 | 31526 | 102465 | 13145.02 | 0 | 0 | 147136.02 | 1335895.9 | 1483031.92 | 0 | [6 empty] | CM_WSI | 100%
502776 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS2 | 2018-05-30 | 2019-03-13 | 2019-06-21 | 2019-09-18 | 2019-12-19 | Fife | 0 | 0 | 0 | 27998.6645 | 62276.3355 | 38288.4 | 1339.78 | 129903.18 | 667.16 | 130570.34 | 0 | [6 empty] | CM_WWI | 100%
502621 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-03 | 2024-12-02 | 2025-02-05 | 2026-01-14 | 2026-04-16 | Highland | 0 | 0 | 20930.23 | 499.08 | 2351.08 | 11934.12 | 11887.86 | 47602.37 | 7953017.71 | 8000620.08 | 148885.7057 | [6 empty] | WG1 | 100%
045328 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-23 | 2011-06-06 | 2011-12-12 | 2012-02-06 | Highland | 43143.52 | 27.72 | 0 | 0 | 0 | 0 | 0 | 27.72 | 0 | 43171.24 | 0 | [6 empty] | DW13 | 100%
502730 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-05-30 | 2019-01-31 | 2019-02-18 | 2019-07-08 | 2019-10-08 | Highland | 0 | 0 | 0 | 12917.3125 | 32651.5275 | 50219.74 | 812.83 | 96601.41 | 0 | 96601.41 | 0 | [6 empty] | CM_WWI | 100%
403018 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-10-26 | 2013-03-28 | 2013-08-26 | 2014-04-28 |  | Fife | 784363 | -3490.66 | 288.24 | 0 | 0 | 0 | 0 | -3202.42 | 0 | 781160.58 | 0 | [6 empty] | CM_WSNI | 100%
500861 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2015-11-04 | 2018-09-05 | 2018-11-29 | 2019-06-01 | 2020-06-01 | Fife | 0 | 15428 | -3169.22 | 19000 | 146248.24 | 62317.92 | 0 | 239824.94 | 0 | 239824.94 | 511174.044 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 94.58
046345 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-05-07 | 2012-09-28 | 2012-11-21 | 2014-03-28 |  | Fife | 620245 | 2526 | -2959.85 | 0 | 0 | 0 | 0 | -433.85 | 0 | 619811.15 | 0 | [6 empty] | CM_WSI | 100%
501035 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2016-04-04 | 2022-03-14 | 2022-04-11 | 2023-03-13 | 2023-05-22 | Perth and Kinross | 0 | 16995.35 | 9411.71 | 174592.94 | 9084.79 | 0 | 0 | 210084.79 | 1651576.72 | 1861661.51 | 0 | [6 empty] | CM_WSI | 100%
501036 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501034 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501031 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | Perth and Kinross | 0 | 59.3 | -59.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501032 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501033 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501030 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501024 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501025 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501026 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501065 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501023 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
503503 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MSU | 2021-04-01 | 2022-02-14 | 2022-05-16 | 2022-12-16 | 2023-03-20 | Fife | 0 | 0 | 0 | 0 | 0 | 9859.11 | 9820.91 | 19680.02 | 390319.96 | 409999.98 | 0 | [6 empty] | CM_M&G | 100%
501298 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-03-28 | 2018-06-28 | 2018-10-23 | 2020-02-04 | 2020-05-06 | Fife | 0 | 3827.64 | 16582.25 | 5034.09 | 189797.26 | 343176.18 | 12174.37 | 570591.79 | 1152 | 571743.79 | 0 | [6 empty] | CM_WSNI | 100%
501600 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2017-03-21 | 2019-09-25 | 2020-11-02 | 2020-12-01 | 2021-03-01 | Fife | 0 | 0 | 72050.45 | 5656.769 | 535.47 | 0 | 0 | 78242.689 | 0 | 78242.689 | 1226521.4273 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
501226 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2017-03-15 | 2018-03-30 | 2018-07-19 | 2019-07-01 | 2019-10-01 | Fife | 0 | 2511.63 | 16007.42 | 182563.2855 | 684566.8245 | 209675.82 | 6136.26 | 1101461.24 | 1981.75 | 1103442.99 | 466391.8995 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
402211 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-09-20 | 2013-04-12 | 2013-09-12 | 2014-03-10 |  | Fife | 423456.31 | 6.69 | -2112.11 | 0 | 0 | 0 | 0 | -2105.42 | 0 | 421350.89 | 0 | [6 empty] | CM_WSNI | 100%
500242 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS4 | 2015-03-20 | 2017-03-30 | 2017-06-27 | 2019-02-01 | 2020-03-01 | Fife | 0 | 4244 | 21380 | 151683.37 | 255944.628 | 1621.04 | 0 | 434873.038 | 0 | 434873.038 | 342095.4721 | [6 empty] | DW5 | 100% | bar: Regulatory Outputs OMG-02
500918 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2015-09-07 | 2017-09-29 | 2017-10-02 | 2020-06-23 | 2020-09-23 | Aberdeenshire | 0 | 11620 | 94891 | 438137 | 59266.65 | 1137727.02 | 157895.43 | 1899537.1 | 0 | 1899537.1 | 0 | [6 empty] | CM_WSI | 100%
500243 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS3 | 2015-03-27 | 2018-06-28 | 2018-06-29 | 2019-07-19 | 2020-06-01 | Aberdeenshire | 0 | 4285 | -1476.16 | 79399.59 | 713762.33 | 295274.31 | 53638.81 | 1144883.88 | 0 | 1144883.88 | 1603174.4995 | [6 empty] | DW5 | 100%
500886 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-06-01 | 2017-12-20 | 2018-03-20 | 2019-03-01 | 2020-02-01 | Aberdeenshire | 0 | 2426.79 | 2573.21 | 14086.915 | 17056.425 | 3058.37 | 11545.73 | 50747.44 | 0 | 50747.44 | 112711.9279 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 20.21
500037 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-04-01 | 2022-02-14 | 2022-05-10 | 2023-01-31 | 2023-01-31 | Aberdeenshire | 0 | 10650 | 0 | 267.79 | 435.032 | 0 | 0 | 11352.822 | 2428067.19 | 2439420.012 | 0 | [6 empty] | CM_WSI | 100%
046255 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-10-22 | 2010-06-28 | 2010-10-25 | 2011-07-28 | 2011-07-28 | Fife | 132219.21 | -1.8 | 0 | 0 | 0 | 0 | 0 | -1.8 | 0 | 132217.41 | 0 | [6 empty] | CM_WSI | 100%
501063 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-04 | 2021-11-08 | 2021-12-30 | 2022-06-17 | 2022-09-19 | Fife | 0 | 22464 | 16972 | 0 | -4495 | 0 | 0 | 34941 | 263827.97 | 298768.97 | 0 | [6 empty] | CM_WSI | 100%
500974 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2015-09-17 | 2015-09-17 | 2015-11-26 | 2018-02-19 | 2018-02-19 | Fife | 0 | 53357 | 851167.44 | 361386.6005 | 35853.1375 | 0 | 102.44 | 1301866.618 | 1297.56 | 1303164.178 | 0 | [6 empty] | CM_WSNI | 100%
501221 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS4 | 2015-11-17 | 2015-11-17 | 2016-02-01 | 2018-11-01 | 2019-04-01 | Fife | 0 | 615.71 | 2360.05 | 8116.15 | 13935.94 | 2622.1 | 0 | 27649.95 | 0 | 27649.95 | 0 | [6 empty] | DW25D | 100% | bar: Regulatory Outputs OMG-05
502128 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2019-10-09 | 2019-10-09 | 2020-02-04 | 2020-02-04 | 2020-02-04 | Perth and Kinross | 0 | 0 | 23851.73 | 7666.01 | 7527.14 | 4619.44 | 0 | 43664.32 | 0 | 43664.32 | 148885.7057 | [6 empty] | SG1 | 100%
030308 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-12 | 2011-03-31 | 2011-08-29 | 2013-02-07 | 2013-02-21 | Highland | 1276327.51 | -1350.11 | 0 | 0 | 0 | 0 | 0 | -1350.11 | 0 | 1274977.4 | 0 | [6 empty] | DW23 | 100%
300034 | Q&S3A | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-04-23 | 2012-12-17 | 2013-02-18 | 2014-06-25 | 2011-03-14 | Dumfries and Galloway | 157181.84 | 121.45 | 213 | 0 | 0 | 0 | 0 | 334.45 | 0 | 157516.29 | 200 | [6 empty] | DW7 | 100%
501213 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-01-28 | 2016-03-04 | 2016-03-07 | 2016-03-01 | 2016-08-01 | Dumfries and Galloway | 0 | 3079 | -2656.86 | 0 | 0 | 0 | 0 | 422.14 | 0 | 422.14 | 466391.8995 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
503427 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2019-08-30 | 2020-07-20 | 2020-10-19 | 2021-05-20 | 2021-08-20 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 102958.12 | 293678.45 | 396636.57 | 128363.48 | 525000.05 | 0 | [6 empty] | SG1 | 100%
500897 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2015-10-30 | 2023-08-25 | 2023-09-25 | 2024-02-29 | 2025-02-10 | Falkirk | 0 | 10709 | 77549.04 | 113553.01 | 77712.74 | 0 | 0 | 279523.79 | 1358939.16 | 1638462.95 | 0 | [6 empty] | CM_WSI | 100%
046254 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-10-22 | 2010-06-28 | 2010-11-09 | 2011-05-23 | 2011-05-23 | Moray | 118092.06 | 51 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 118143.06 | 0 | [6 empty] | CM_WSI | 100%
401080 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-06-21 | 2012-06-13 | 2012-07-19 | 2014-01-16 | 2014-01-31 | Moray | 106158.78 | 1579.22 | -1361.79 | 0 | 0 | 0 | 0 | 217.43 | 0 | 106376.21 | 1512 | [6 empty] | CS1 | 100%
500917 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2015-10-30 | 2016-09-23 | 2016-11-28 | 2018-04-06 | 2018-04-06 | Aberdeenshire | 0 | 59148 | 746516.61 | 657914.09 | -4990.564 | 0 | 0 | 1458588.136 | 0 | 1458588.136 | 0 | [6 empty] | CM_WSNI | 100%
501217 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS3 | 2016-03-29 | 2018-03-01 | 2018-03-27 | 2020-08-01 | 2021-09-01 | Aberdeenshire | 0 | 97779.24 | 503715.93 | 1031731.15 | 789985.27 | 5773201.62 | 1005491.8 | 9201905.01 | 60290.93 | 9262195.94 | 4821121.9332 |  |  |  |  | 79349.0004 |  | DW25P | 1.275% | DW3G | 6.225% | CM_WSNI | 25% | DW3C | 67.5% | bar: Regulatory Outputs OMG-01
045598 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-06-30 | 2011-10-03 | 2014-03-21 | 2014-03-21 | Moray | 926687.37 | 3870.13 | -1265.25 | 0 | 0 | 0 | 0 | 2604.88 | 0 | 929292.25 | 7469.8667 |  |  |  |  | 30204 |  | CM_WSNI | 30% | DW1A | 70%
403831 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2019-07-01 | 2020-09-21 | 2021-01-21 | 2021-05-26 | 2021-08-26 | Argyll and Bute-Cowal & Bute | 4283.7 | 5779.93 | 2685.27 | 247.805 | 11924.405 | 15107.61 | 379944.22 | 415689.24 | 250398.7 | 670371.64 | 148885.7057 | [6 empty] | SG1 | 100%
501668 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2017-11-01 | 2017-11-01 | 2017-11-01 | 2017-11-01 | 2017-11-01 | South Lanarkshire | 0 | 0 | 4899.67 | 1915.04 | 0 | 0 | 0 | 6814.71 | 0 | 6814.71 | 0 | [6 empty] | CM_WSI | 100%
500935 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS5 | 2015-09-07 | 2018-03-29 | 2018-05-31 | 2018-11-30 | 2018-11-30 | All West Unitary Authorities | 0 | 45520 | 55883 | 140910 | 441142 | 6017 | 3735 | 693207 | 0 | 693207 | 0 | [6 empty] | CM_WWNI | 100%
501502 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2016-10-03 | 2022-05-13 | 2022-09-09 | 2023-05-03 | 2023-08-03 | Dumfries and Galloway | 0 | 0 | 6130.29 | 41.59 | 0 | 0 | 0 | 6171.88 | 358770.1 | 364941.98 | 0 | [6 empty] | CM_WWNI | 100%
502352 | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater |  | SWMD | Sludge | MS6 | 2016-11-07 | 2018-01-29 | 2018-03-23 | 2018-12-01 | 2019-01-01 | Highland | 0 | 0 | 6342.76 | 54845.095 | 173810.645 | 0 | 0 | 234998.5 | 0 | 234998.5 | 0 | [6 empty] | LA01_S | 100% | bar: Regulatory Outputs OMG-24
503134 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2019-08-15 | 2020-11-23 | 2021-03-26 | 2021-11-05 | 2022-02-07 | East Renfrewshire | 0 | 0 | 0 | 0 | 42082.732 | 15617.69 | 88439.76 | 146140.182 | 135958.96 | 282099.142 | 0 | [6 empty] | CM_WSNI | 100%
045517 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-08-25 | 2011-12-19 | 2011-12-23 | 2011-12-19 |  | East Renfrewshire | 167067.99 | 688.99 | 0 | 0 | 0 | 0 | 0 | 688.99 | 0 | 167756.98 | 0 | [6 empty] | CM_WSNI | 100%
502712 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2019-02-28 | 2019-02-28 | 2019-02-28 | 2019-01-21 | 2019-01-21 | East Renfrewshire | 0 | 0 | 0 | 17241.43 | 979.38 | 0 | 0 | 18220.81 | 0 | 18220.81 | 0 | [6 empty] | CM_WSNI | 100%
500251 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | WWINF | Water Non infrastructure | MS3 | 2015-06-08 | 2017-03-31 | 2017-03-31 | 2019-07-22 | 2019-10-24 | East Renfrewshire | 0 | 22000 | 456411 | 740557.02 | 2687.98 | 0 | 0 | 1221656 | 0 | 1221656 | 0 | [6 empty] | CM_WSNI | 100%
502825 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-07-19 | 2022-07-22 | 2022-11-14 | 2023-11-02 | 2024-02-02 | Midlothian | 0 | 0 | 0 | 61544.658 | 9720.657 | 23641.95 | 23550.36 | 118457.625 | 26289.92 | 144747.545 | 148885.7057 | [6 empty] | SG1 | 100%
403576 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2013-09-25 | 2014-02-04 | 2014-02-10 | 2014-07-17 | 2014-03-26 | Angus | 86889 | 0 | -5939.27 | 0 | 0 | 0 | 0 | -5939.27 | 0 | 80949.73 | 3814 | [6 empty] | CS1 | 100%
045332 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2012-07-26 | 2012-08-08 | 2012-08-08 | 2011-03-14 | Na H-Eileanan an Iar | 71484.17 | 1517.95 | 0 | 0 | 0 | 0 | 0 | 1517.95 | 0 | 73002.12 | 0 | [6 empty] | DW13 | 100%
402480 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-06-28 | 2013-01-30 | 2013-01-30 | 2015-03-26 | 2015-04-01 | Scottish Water Wide | 1350922 | 396328.45 | 32046.68 | 0 | 0 | 0 | 0 | 428375.13 | 0 | 1779297.13 | 100062 | [6 empty] | CS16S | 100%
501265 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2016-02-10 | 2017-10-24 | 2018-01-08 | 2018-05-24 | 2018-05-24 | South Lanarkshire | 0 | 3595 | 76405 | 221039 | 36680 | 781 | 0 | 338500 | 0 | 338500 | 0 | [6 empty] | CM_WWI | 100%
030316 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2010-09-20 | 2011-02-01 | 2012-03-16 | 2012-03-26 | North Lanarkshire | 1400389.36 | 150.28 | 0 | 0 | 0 | 0 | 0 | 150.28 | 0 | 1400539.64 | 0 | [6 empty] | EC10A | 46.21% | CM_WWNI | 53.79%
501113 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-10-21 | 2018-07-31 | 2018-08-28 | 2018-11-29 | 2018-11-29 | East Ayrshire | 0 | 11290 | 8843 | 142631 | 430250 | 66.93 | 0.07 | 593081 | 0 | 593081 | 0 | [6 empty] | CM_WWI | 100%
503226 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-11-03 | 2023-04-18 | 2023-08-11 | 2024-08-07 | 2024-11-07 | Scottish Borders | 0 | 0 | 0 | 0 | 83505.79 | 9837.12 | 30459.25 | 123802.16 | 18251.78 | 142053.94 | 148885.7057 | [6 empty] | SG1 | 100%
501671 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Water |  | SWMD | Flood Risk Management Act | MS0 | 2018-07-12 | 2019-11-25 | 2020-01-31 | 2020-10-08 | 2020-10-08 | Inverclyde | 0 | 0 | 0 | 6782.135 | 24976.645 | 95762.74 | 244832.97 | 372354.49 | 991.49 | 373345.98 | 985398.5607 | [6 empty] | WR6 | 100%
502903 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS3 | 2017-09-27 | 2018-04-30 | 2018-04-30 | 2019-07-01 | 2020-07-01 | Inverclyde | 0 | 0 | 0 | 82141 | 461826.18 | 132141.2 | 26551.59 | 702659.97 | 0 | 702659.97 | 1086158.9861 | [6 empty] | DW5FS | 18.88% | DW5MR | 81.12% | bar: Regulatory Outputs OMG-02
502606 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS0 | 2018-06-28 | 2019-07-22 | 2019-08-06 | 2020-10-06 | 2021-07-09 | Inverclyde | 0 | 0 | 46297 | 236920.395 | 63744.905 | 861213.22 | 112975.77 | 1321151.29 | 575585.74 | 1896737.03 | 3781878.2083 | [6 empty] | DW5MR | 100%
503257 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2018-06-28 | 2019-06-24 | 2019-08-26 | 2020-04-01 | 2020-07-01 | Inverclyde | 0 | 0 | 0 | 0 | 275220 | 544694.37 | 226913.01 | 1046827.38 | 2691.65 | 1049519.03 | 251143.0878 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 212.3512
503256 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2018-06-28 | 2019-06-24 | 2019-09-03 | 2020-07-13 | 2020-10-13 | Inverclyde | 0 | 0 | 0 | 0 | 326478 | 180777.33 | 142346.16 | 649601.49 | 2737.51 | 652339 | 693251.7455 | [6 empty] | DW5MC | 100%
501574 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2017-03-31 | 2019-05-05 | 2019-06-05 | 2020-09-07 | 2020-12-08 | Inverclyde | 0 | 5847 | 10278.37 | 728.345 | 907.445 | 0 | 0 | 17761.16 | 0 | 17761.16 | 250307.4211 | [6 empty] | DW25T | 100%
500660 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS6 | 2015-10-30 | 2017-05-16 | 2017-07-12 | 2018-12-11 | 2018-12-12 | Renfrewshire | 0 | 29246 | 125279.79 | 791345.19 | 611519.92 | 22518.84 | 15448.97 | 1595358.71 | 0 | 1595358.71 | 0 | [6 empty] | CM_WSNI | 100%
503533 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2019-06-24 | 2020-10-12 | 2021-01-20 | 2021-08-31 | 2021-12-01 | Inverclyde | 0 | 0 | 0 | 0 | 10567.03 | 62350.49 | 228855.37 | 301772.89 | 208794.13 | 510567.02 | 0 | [6 empty] | CM_WSNI | 100%
502972 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2019-06-18 | 2020-09-28 | 2021-02-01 | 2021-09-13 | 2021-12-14 | Inverclyde | 0 | 0 | 0 | 16358.795 | 5717.55 | 78760.57 | 128817.41 | 229654.325 | 70345.65 | 299999.975 | 0 | [6 empty] | CM_WSNI | 100%
401346 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-13 | 2012-12-12 | 2013-01-21 | 2013-03-01 | 2013-03-15 | Orkney Islands | 15500 | -561.65 | 0 | 0 | 0 | 0 | 0 | -561.65 | 0 | 14938.35 | 0 | [6 empty] | CS1 | 100%
045798 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2013-01-23 | 2013-01-23 | 2013-01-23 | 2013-01-23 | Scottish Water Wide | 17007.91 | 3891.32 | 0 | 0 | 0 | 0 | 0 | 3891.32 | 0 | 20899.23 | 0 | [6 empty] | WQ01C | 100%
500203 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2015-03-24 | 2017-03-30 | 2017-06-07 | 2018-10-18 | 2018-10-18 | Shetland Islands | 0 | 88503 | 114368 | 774720 | 97892 | 0 | 0 | 1075483 | 0 | 1075483 | 0 | [6 empty] | CM_WWNI | 100%
500136 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS5 | 2015-03-19 | 2016-03-29 | 2016-08-01 | 2018-12-11 | 2019-03-29 | Dumfries and Galloway | 0 | 24619 | 15708.33 | 67359 | 28500 | 34996.66 | 0 | 171182.99 | 0 | 171182.99 | 92119.905 | [6 empty] | EC01G | 2.151% | CS16D | 21.6% | EC01D | 38.12% | EC10E | 38.12%
400674 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-01-21 | 2009-10-30 | 2009-10-30 | 2011-06-29 | 2013-06-26 | Dumfries and Galloway | 830627.5 | -1223.88 | 0 | 0 | 0 | 0 | 0 | -1223.88 | 0 | 829403.62 | 0 | [6 empty] | CS1 | 15.35% | WG5 | 84.65%
503455 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MSU | 2021-06-15 | 2023-02-20 | 2023-06-23 | 2024-09-26 | 2024-12-27 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 59441.86 | 37499.94 | 37354.56 | 134296.36 | 1865703.43 | 1999999.79 | 148885.7057 | [6 empty] | SG1 | 100%
502548 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-10-06 | 2017-10-06 | Scottish Water Wide | 0 | 0 | 93660 | 3752.29 | 0 | 0 | 0 | 97412.29 | 0 | 97412.29 | 0 | [6 empty] | CM_M&G | 100%
402625 | Q&S4 | Supporting economic development | RCC |  |  | General |  | SWD | RCC | MS7 | 2012-03-14 | 2013-02-06 | 2013-02-06 | 2015-10-19 | 2016-07-11 | Scottish Water Wide | 3793615.62 | 0 | 411.54 | 0 | 0 | 0 | 0 | 411.54 | 0 | 3794027.16 | 0 | [6 empty] | SG2 | 50% | WG2 | 50%
402180 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-06-28 | 2012-03-21 | 2012-06-18 | 2014-02-24 | 2014-02-24 | North Ayrshire | 124832.25 | 145.32 | 0 | 0 | 0 | 0 | 0 | 145.32 | 0 | 124977.57 | 0 | [6 empty] | CM_WSI | 100%
402181 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-06-28 | 2012-12-03 | 2013-07-15 | 2014-10-27 | 2014-10-28 | North Ayrshire | 446170.39 | -1908.8 | 796.86 | 0 | 0 | 0 | 0 | -1111.94 | 0 | 445058.45 | 0 | [6 empty] | CM_WSI | 100%
501651 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS5 | 2016-02-22 | 2018-02-23 | 2018-03-19 | 2018-11-23 | 2018-11-23 | Glasgow City | 0 | 327.1 | 12345.8 | 23355.34 | 246058.52 | 860.19 | 1221.37 | 284168.32 | 831.65 | 284999.97 | 0 | [6 empty] | CM_WWI | 100%
501705 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2016-07-19 | 2019-07-15 | 2019-09-10 | 2019-12-10 | 2020-01-28 | Glasgow City | 0 | 0 | 2366.16 | 30.82 | 147.87 | 49782.14 | 0 | 52326.99 | 0 | 52326.99 | 0 | [6 empty] | CM_WWI | 100%
501706 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2016-11-07 | 2019-07-15 | 2019-08-12 | 2019-10-11 | 2019-10-14 | Renfrewshire | 0 | 0 | 2913.38 | 442.76 | 340.64 | 48824.54 | 388.68 | 52910 | 0 | 52910 | 0 | [6 empty] | CM_WWI | 100%
403428 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MS3 | 2013-03-26 | 2013-03-26 | 2013-04-03 | 2019-07-26 | 2019-08-29 | Glasgow City | 228490.56 | 95158.44 | 95378.7 | 29821.995 | 51150.305 | 0 | 0 | 271509.44 | 0 | 500000 | 156558 | [6 empty] | EC01B | 100%
046416 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2009-07-21 | 2012-12-07 | 2012-12-24 | 2018-06-22 | 2011-03-14 | Glasgow City | 110271.89 | 16340.24 | 0 | 0 | 0 | 0 | 0 | 16340.24 | 0 | 126612.13 | 0 | [6 empty] | EC04C | 0.9763% | EC01D | 33.13% | EC10E | 65.89%
503283 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-07 | 2023-06-21 | 2023-10-24 | 2024-10-21 | 2025-01-21 | Fife | 0 | 0 | 0 | 0 | 71970.386 | 6506.9 | 13232.54 | 91709.826 | 60836.16 | 152545.986 | 148885.7057 | [6 empty] | SG1 | 100%
404091 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-12-15 | 2016-12-15 | Fife | 0 | 0 | 171778.98 | 0 | 0 | 0 | 0 | 171778.98 | 0 | 171778.98 | 0 | [6 empty] | WG5 | 100%
502711 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2017-10-20 | 2018-11-29 | 2019-03-11 | 2019-06-26 | 2019-09-30 | Na H-Eileanan an Iar | 0 | 0 | 0 | 19272 | 176055 | 93817.36 | 4800.95 | 293945.31 | 20.73 | 293966.04 | 0 | [6 empty] | CM_WWI | 100%
402143 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-05-27 | 2015-03-23 | 2015-07-13 | 2016-09-27 | 2016-09-27 | Perth and Kinross | 335118 | 1555475 | 249137.56 | 100000 | 8872.3545 | 0 | 0 | 1913484.9145 | 0 | 2248602.9145 | 0 | [6 empty] | SG1 | 100%
503064 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW1 | 2021-04-01 | 2022-06-29 | 2022-10-24 | 2023-06-12 | 2023-09-12 | Shetland Islands | 0 | 0 | 0 | 31039.125 | 3657.625 | 2949.85 | 36505.7 | 74152.3 | 528000.05 | 602152.35 | 0 | [6 empty] | CM_WWNI | 100%
502290 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | East Lothian | 0 | 0 | 36444.74 | 874.75 | 0 | 0 | 0 | 37319.49 | 0 | 37319.49 | 148885.7057 | [6 empty] | SG1 | 100%
400920 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2010-05-19 | 2013-02-26 | 2013-06-24 | 2017-02-16 |  | Orkney Islands | 388207 | 2624 | 40096.64 | 11000 | 0 | 0 | 0 | 53720.64 | 0 | 441927.64 | 0 | [6 empty] | CM_WSNI | 100%
502790 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2021-04-16 | 2022-03-14 | 2022-05-16 | 2022-12-09 | 2023-03-13 | Scottish Borders | 0 | 0 | 0 | 31363.42 | 30636.58 | 0 | 0 | 62000 | 572000 | 634000 | 0 | [6 empty] | CM_WSI | 100%
500149 | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-19 | 2015-11-30 | 2016-01-12 | 2017-08-01 | 2017-09-01 | East Lothian | 0 | 56880 | 118965 | 36303 | -20580.9765 | 0 | 0 | 191567.0235 | 0 | 191567.0235 | 72474.3726 | [6 empty] | CS11 | 50% | CS16D | 50% | bar: Regulatory Outputs OMG-22
502418 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS5 | 2017-03-30 | 2017-03-30 | 2018-09-11 | 2018-11-26 | 2018-11-26 | East Lothian | 0 | 0 | 0 | 31532.71 | 0 | 450467.28 | 0 | 481999.99 | 0 | 481999.99 | 148885.7057 | [6 empty] | SG1 | 100%
501152 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-03-02 | 2018-09-27 | 2018-11-26 | 2019-11-25 | 2020-02-28 | East Lothian | 0 | 3848.36 | 202439.78 | 172677.93 | 625447.04 | 802024.97 | 35176.87 | 1841614.95 | 10071.11 | 1851686.06 | 0 |  |  |  |  | 9690 |  | CM_WWNI | 100%
030321 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-08-08 | 2010-06-28 | 2011-03-03 | 2012-09-27 | 2012-11-23 | East Lothian | 1501900.87 | 1265.43 | 0 | 0 | 0 | 0 | 0 | 1265.43 | 0 | 1503166.3 | 0 | [6 empty] | CM_WWNI | 20% | EC01A | 80%
502956 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2017-11-20 | 2017-11-20 | 2017-12-11 | 2018-05-28 | 2018-05-28 | East Lothian | 0 | 0 | 0 | 350476.64 | 95710.36 | 862.2 | 858.86 | 447908.06 | 360.92 | 448268.98 | 0 | [6 empty] | CM_WWI | 100%
403968 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS3 | 2016-07-19 | 2018-09-26 | 2018-11-26 | 2019-11-04 | 2019-11-05 | East Lothian | 14875.16 | 14622.85 | 230898.42 | 165329.94 | 669050.65 | 1164957.33 | 3470.35 | 2248329.54 | 2106.5 | 2265311.2 | 0 |  |  |  |  | 55470 |  | SG1 | 100%
501798 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2017-06-29 | 2021-09-10 | 2021-11-15 | 2022-01-07 | 2022-01-10 | East Lothian | 0 | 0 | 1607.44 | 5297.36 | 0 | 0 | 0 | 6904.8 | 137815.99 | 144720.79 | 0 | [6 empty] | CM_WWI | 100%
501591 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2016-05-10 | 2021-07-13 | 2021-09-15 | 2022-02-07 | 2022-05-10 | Highland | 0 | 0 | 27076 | 17694 | 0 | 0 | 0 | 44770 | 40311.99 | 85081.99 | 0 | [6 empty] | CM_WWI | 100%
500137 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS4 | 2015-03-19 | 2016-06-21 | 2016-08-18 | 2019-02-26 | 2019-07-26 | Highland | 0 | 10823 | 14030 | 16982 | 52826.84 | 0 | 0 | 94661.84 | 0 | 94661.84 | 31586.7252 | [6 empty] | EC01G | 12.72% | CS16D | 31.61% | EC01D | 55.67%
032104 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-10-01 | 2010-08-23 | 2010-09-27 | 2012-02-06 | 2012-03-16 | South Lanarkshire | 3975719.73 | 5339.68 | -5339.68 | 0 | 0 | 0 | 0 | 0 | 0 | 3975719.73 | 0 | [6 empty] | EC01A | 22.39% | CM_WWNI | 77.61%
501164 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2016-02-22 | 2017-09-04 | 2017-12-04 | 2018-09-27 | 2018-09-27 | South Lanarkshire | 0 | 602.52 | 89528.48 | 540862 | 29559.6525 | 0 | 0 | 660552.6525 | 0 | 660552.6525 | 0 | [6 empty] | CM_WWNI | 100%
502232 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS3 | 2018-10-31 | 2018-10-31 | 2018-12-17 | 2019-05-17 | 2019-05-20 | South Lanarkshire | 0 | 0 | 21336.24 | 14880.39 | 73042.18 | 280923.69 | 1172.99 | 391355.49 | 0 | 391355.49 | 148885.7057 |  |  |  |  | 134000.0004 |  | SG1 | 100%
501635 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-03-30 | 2017-08-22 | 2017-08-24 | 2020-02-07 | 2020-02-07 | South Lanarkshire | 0 | 3925 | 777237.72 | 430095.63 | 3122667.37 | 2092589.23 | 316308.98 | 6742823.93 | 5727.7 | 6748551.63 | 0 | [6 empty] | CM_WSI | 100%
502275 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2018-06-29 | 2019-04-15 | 2019-05-27 | 2020-06-24 | 2020-06-24 | Fife | 0 | 0 | 8571.33 | 2496.7725 | 10046.7775 | 318439.83 | 232743.3 | 572298.01 | 2700.44 | 574998.45 | 0 | [6 empty] | CM_WSI | 100%
046156 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-31 | 2010-11-15 | 2011-01-19 | 2012-03-14 |  | North Lanarkshire | 914721.47 | 3633.3 | -3633.3 | 0 | 0 | 0 | 0 | 0 | 0 | 914721.47 | 0 | [6 empty] | CM_WWNI | 100%
500820 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-21 | 2017-01-31 | 2017-01-31 | 2016-12-16 | 2017-01-31 | Dundee City | 0 | 5211.19 | 533.7 | -92.87 | 0 | 0 | 0 | 5652.02 | 0 | 5652.02 | 144841.4737 | [6 empty] | CS15A | 100%
403005 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-10-29 | 2013-03-28 | 2013-04-24 | 2013-06-13 |  | Aberdeenshire | 40227.43 | -927.36 | 0 | 0 | 0 | 0 | 0 | -927.36 | 0 | 39300.07 | 0 | [6 empty] | CM_WWNI | 100%
500235 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS0 | 2019-03-25 | 2020-02-24 | 2020-03-16 | 2021-04-15 | 2021-04-29 | Aberdeenshire | 0 | 63480.51 | 41516.5 | 23116.5485 | 23988.7085 | 381213.19 | 1117556.17 | 1650871.627 | 119506.96 | 1770378.587 | 148885.7057 | [6 empty] | SG1 | 100%
502821 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-04-10 | 2018-04-10 | 2018-04-10 | 2018-04-10 | 2018-04-10 | Aberdeenshire | 0 | 0 | 0 | 63695.0675 | 120.3 | 0 | 0 | 63815.3675 | 0 | 63815.3675 | 148885.7057 | [6 empty] | SG1 | 100%
034798 | Q&S3A | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-12-19 | 2011-03-21 | 2011-03-21 | 2011-03-31 | 2011-03-31 | Scottish Borders | 192450 | 7550 | -1747.69 | 0 | 0 | 0 | 0 | 5802.31 | 0 | 198252.31 | 0 | [6 empty] | DW7 | 100%
501945 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2016-06-03 | 2016-08-10 | 2016-08-10 | 2017-02-09 | 2017-05-02 | Scottish Borders | 0 | 0 | 1405606.4 | 419775.19 | -16432.47 | 8000 | 0 | 1816949.12 | 0 | 1816949.12 | 0 | [6 empty] | CM_WWI | 100%
400065 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-10-14 | 2011-05-03 | 2011-08-01 | 2016-12-15 |  | Scottish Borders | 1878109.62 | 101674.99 | -9730.27 | -31.19 | 98.34 | 0 | 0 | 92011.87 | 0 | 1970121.49 | 0 | [6 empty] | CM_WWNI | 100%
030322 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-09-29 | 2011-05-05 | 2011-08-01 | 2015-11-03 | 2015-05-29 | Scottish Borders | 2352426.24 | 77936.54 | -2507.44 | -431.83 | 0 | 0 | 0 | 74997.27 | 0 | 2427423.51 | 53147.8894 | [6 empty] | CM_WWNI | 50% | EC01A | 50%
500950 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-09-10 | 2015-09-10 | 2015-09-10 | 2018-10-04 | 2018-10-04 | Scottish Water Wide | 0 | 73616.97 | 6781.74 | 62.39 | 0 | 0 | 0 | 80461.1 | 0 | 80461.1 | 0 | [6 empty] | CM_M&G | 100%
403718 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-02-27 | 2014-05-29 | 2014-06-03 | 2016-03-23 | 2016-06-21 | Scottish Water Wide | 2127956 | 82000 | -8500.44 | 1484.97 | 0 | 0 | 0 | 74984.53 | 0 | 2202940.53 | 0 | [6 empty] | CM_WSI | 100%
400999 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-04-21 | 2012-06-07 | 2013-01-08 | 2013-12-10 |  | Orkney Islands | 331691 | -373.11 | -88.68 | 0 | 0 | 0 | 0 | -461.79 | 0 | 331229.21 | 0 | [6 empty] | CM_WSNI | 100%
403787 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-05-19 | 2015-06-12 | 2015-06-15 | 2015-06-15 | 2015-06-15 | Argyll and Bute-Cowal & Bute | 6220 | -1593.3 | 0 | 0 | 0 | 0 | 0 | -1593.3 | 0 | 4626.7 | 0 | [6 empty] | CM_WSI | 100%
501167 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS1 | 2016-07-20 | 2021-04-26 | 2021-04-26 | 2022-09-26 | 2022-09-26 | Argyll and Bute-Cowal & Bute | 0 | 0 | 53942.64 | 312644.74 | -19067.38 | 0 | 0 | 347520 | 2582028.02 | 2929548.02 | 0 | [6 empty] | CM_WWNI | 100%
045039 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-17 | 2011-09-28 | 2012-07-09 | 2013-03-28 | 2013-11-21 | Scottish Borders | 933948.27 | -496.53 | 0 | 0 | 0 | 0 | 0 | -496.53 | 0 | 933451.74 | 0 | [6 empty] | DW23 | 100%
502361 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS4 | 2021-04-01 | 2021-04-12 | 2021-04-12 | 2016-12-20 | 2021-04-12 | Aberdeenshire | 0 | 0 | 40186.05 | 0 | 0 | 0 | 0 | 40186.05 | 0 | 40186.05 | 0 | [6 empty] | CM_WSI | 12.5% | CM_WSNI | 87.5%
501110 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-04-02 | 2022-11-24 | 2023-03-29 | 2024-06-19 | 2024-09-11 | Aberdeenshire | 0 | 23339.61 | 120920.78 | 11583.01 | 41175.22 | 0 | 0 | 197018.62 | 3013221.88 | 3210240.5 | 0 | [6 empty] | CM_WSNI | 100%
503422 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2018-10-31 | 2019-10-14 | 2019-11-25 | 2020-10-30 | 2021-02-05 | Moray | 0 | 0 | 0 | 0 | 39230.01 | 681348.31 | 962990.8 | 1683569.12 | 16814.15 | 1700383.27 | 0 | [6 empty] | CM_WSNI | 100%
501233 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS0 | 2018-03-22 | 2019-10-28 | 2020-03-16 | 2020-12-07 | 2021-04-16 | Aberdeenshire | 0 | 2424.81 | 31934.21 | 66689.69 | 71488.29 | 284610.1 | 504806.4 | 961953.5 | 5801.4 | 967754.9 | 3537.353 | [6 empty] | DW25D | 33% | DW25P | 67%
402993 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-10-02 | 2013-03-15 | 2013-06-03 | 2013-10-25 | 2013-10-25 | Glasgow City | 52853 | -957.31 | 0 | 0 | 0 | 0 | 0 | -957.31 | 0 | 51895.69 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
403436 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2013-04-16 | 2014-08-21 | 2014-08-28 | 2014-10-28 | 2014-10-28 | Aberdeenshire | 74956 | -1393.93 | 599.83 | -276.31 | 0 | 0 | 0 | -1070.41 | 0 | 73885.59 | 1863 | [6 empty] | CM_WWI | 40% | CS11A | 60%
402529 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-05-14 | 2012-12-20 | 2013-04-25 | 2014-07-31 |  | All South Unitary Authorities | 549729 | 0 | -25780.55 | 0 | 0 | 0 | 0 | -25780.55 | 0 | 523948.45 | 0 | [6 empty] | CM_WWNI | 100%
500920 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-27 | 2018-02-23 | 2018-02-01 | 2018-02-01 | 2018-02-01 | Highland | 0 | 4904.29 | 1471.49 | -4483.58 | 0 | 0 | 0 | 1892.2 | 0 | 1892.2 | 144841.4737 | [6 empty] | CS15A | 100%
503292 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2018-08-23 | 2021-02-22 | 2021-03-02 | 2022-03-22 | 2022-06-22 | Highland | 0 | 0 | 0 | 0 | 10713.005 | 31262.43 | 34045.99 | 76021.425 | 73978.48 | 149999.905 | 0 | [6 empty] | CM_WWI | 20% | CM_WWNI | 80%
500865 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2016-09-06 | 2018-09-04 | 2018-11-29 | 2019-09-01 | 2020-06-01 | City of Edinburgh | 0 | 5818.45 | 8144.52 | 36650.36 | 95442.32 | 20414.96 | 14080.21 | 180550.82 | 0 | 180550.82 | 396207.2002 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 54.3
501733 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2022-08-01 | 2023-05-17 | 2023-09-20 | 2024-01-30 | 2024-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000.02 | 100000.02 | 0 | [6 empty] | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 33.33% | CM_WSI | 42.86%
500937 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-09-02 | 2017-01-19 | 2017-02-27 | 2017-05-31 | 2017-05-31 | East Dunbartonshire | 0 | 12500 | 104277.85 | 38168.15 | 0 | 0 | 0 | 154946 | 0 | 154946 | 0 | [6 empty] | CM_WWI | 100%
045797 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2011-06-13 | 2011-09-19 | 2014-06-09 | 2014-08-06 | East Dunbartonshire | 645407.49 | 248.91 | 0 | 0 | 0 | 0 | 0 | 248.91 | 0 | 645656.4 | 0 | [6 empty] | WQ01C | 100%
503149 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-03-31 | 2021-04-26 | 2021-04-28 | 2021-04-29 | 2021-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0.42 | 208.72 | 82668.65 | 445052.15 | 527929.94 | 0 | 527929.94 | 0 | [6 empty] | CM_WSI | 100%
503145 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWD | Wastewater infrastructure | MSU | 2021-04-02 | 2021-04-05 | 2021-06-25 | 2021-06-25 | 2021-06-25 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 959999.66 | 1919999.54 | 2879999.2 | 0 | 2879999.2 | 0 | [6 empty] | CM_M&G | 100%
503086 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | GW0 | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-04-18 | Scottish Water Wide | 0 | 0 | 0 | 2255.0098 | -2255.0098 | 0 | 0 | 0 | 2600000.03 | 2600000.03 | 0 | [6 empty] | CM_M&G | 100%
503151 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW2 | 2021-04-01 | 2021-04-05 | 2021-04-05 | 2021-04-05 | 2021-04-05 | Scottish Water Wide | 0 | 0 | 0 | 0 | 3.643 | 0 | 0 | 3.643 | 0 | 3.643 | 0 | [6 empty] | CM_WWNI | 100%
403505 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2013-07-16 | 2013-07-16 | 2013-07-18 | 2019-10-09 | 2019-10-09 | Scottish Water Wide | 674967 | 510718 | -21985.32 | 19900.3 | 0 | 0 | 0 | 508632.98 | 0 | 1183599.98 | 0 |  |  |  |  | 5000.0003 |  | CM_WSI | 100%
403535 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-07-16 | 2013-07-16 | 2013-08-30 | 2016-02-05 |  | All East Unitary Authorities | 133628 | 10515.11 | 0 | 0 | 0 | 0 | 0 | 10515.11 | 0 | 144143.11 | 0 | [6 empty] | CM_WSI | 100%
403536 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-07-16 | 2013-07-16 | 2013-07-16 | 2018-11-05 |  | All East Unitary Authorities | 292688 | 196191 | 0.06 | 79.857 | 111.495 | 0 | 0 | 196382.412 | 0 | 489070.412 | 0 | [6 empty] | CM_WSNI | 100%
502806 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWD | UWWTD - Works | MSU | [5 empty] | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 9600000 | 9600000 | 0 | 9600000 | 10994109.1109 | [6 empty] | EC01A | 100%
502304 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2017-04-25 | 2018-04-30 | 2018-06-25 | 2019-10-11 | 2019-10-11 | Fife | 0 | 0 | 15537.25 | 29859.75 | 369319.45 | 285459 | 36970.3 | 737145.75 | 16229.45 | 753375.2 | 0 | [6 empty] | CM_WSI | 100%
402501 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-01-27 | 2012-12-21 | 2013-03-22 | 2014-04-02 |  | Falkirk | 208639.33 | 171.3 | 0 | 0 | 0 | 0 | 0 | 171.3 | 0 | 208810.63 | 0 | [6 empty] | CM_WWI | 100%
402897 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-08-20 | 2013-10-30 | 2014-02-11 | 2015-04-14 | 2015-04-14 | Scottish Borders | 188319.19 | 77887.28 | 0 | 0 | 0 | 0 | 0 | 77887.28 | 0 | 266206.47 | 0 | [6 empty] | CM_WSI | 100%
500476 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2017-04-24 | 2017-04-24 | 2017-06-07 | 2017-06-01 | 2017-08-01 | East Lothian | 0 | 9164.03 | 14348.14 | 2249.87 | 0 | 0 | 0 | 25762.04 | 0 | 25762.04 | 299207.3025 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
403485 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2013-05-07 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | Scottish Water Wide | 52616 | 59901 | -112517 | 2507.14 | 15448.509 | 0 | 0 | -34660.351 | 0 | 17955.649 | 0 | [6 empty] | CC1W | 100%
502970 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-04-01 | 2022-12-02 | 2023-03-20 | 2024-06-17 | 2024-09-17 | Scottish Borders | 0 | 0 | 0 | 60911.015 | 11046.7145 | 22733.34 | 58961.22 | 153652.2895 | 1846345.96 | 1999998.2495 | 0 | [6 empty] | CM_WSNI | 100%
503266 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS3 | 2017-08-29 | 2018-12-20 | 2019-03-20 | 2021-02-01 | 2021-05-01 | Scottish Borders | 0 | 0 | 0 | 0 | 441754.02 | 956158.31 | 43575.15 | 1441487.48 | 6792.52 | 1448280 | 945320.3697 | [6 empty] | DW2 | 100% | bar: Regulatory Outputs OMG-01
400832 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-05-18 | 2012-04-24 | 2012-06-11 | 2016-03-03 |  | Scottish Borders | 1461421.17 | 98345.59 | 6305.52 | 5432.155 | 0 | 0 | 0 | 110083.265 | 0 | 1571504.435 | 0 | [6 empty] | CM_WSNI | 100%
500815 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS3 | 2015-08-24 | 2015-09-22 | 2015-09-23 | 2019-08-01 | 2019-09-06 | South Lanarkshire | 0 | 34000 | 37000.44 | 4083.71 | 7147.61 | 0 | 0 | 82231.76 | 0 | 82231.76 | 904764.0232 | [6 empty] | CS15 | 100%
500217 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS7 | 2015-03-27 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | Highland | 0 | 12402 | -8517.05 | 47460.76 | 3651.45 | 0 | 0 | 54997.16 | 0 | 54997.16 | 1796650.7376 | [6 empty] | DW5 | 100%
500862 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-07-21 | 2018-06-27 | 2018-10-03 | 2019-01-01 | 2020-02-01 | Highland | 0 | 39033.81 | 12866.89 | 6598.03 | 126457.75 | 3826.32 | 6052.5 | 194835.3 | 0 | 194835.3 | 2640734.4339 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 116.04
501830 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2017-02-17 | 2019-03-04 | 2019-03-04 | 2019-07-19 | 2019-07-19 | Scottish Water Wide | 0 | 0 | 69831.63 | 286057.4 | 3303572.17 | 2040538.8 | 0 | 5700000 | 0 | 5700000 | 0 |  |  |  |  | 731000.0004 |  | CM_M&G | 100%
402594 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-27 | 2012-03-27 | 2012-04-02 | 2017-07-03 |  | All East Unitary Authorities | 1112873 | -52496 | 2089.17 | 7109.5265 | 0 | 0 | 0 | -43297.3035 | 0 | 1069575.6965 | 0 | [6 empty] | CM_M&G | 100%
401233 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-10-07 | 2011-08-09 | 2011-08-16 | 2015-07-24 |  | Scottish Water Wide | 4919789 | -14799.73 | 0 | 0 | 0 | 0 | 0 | -14799.73 | 0 | 4904989.27 | 0 | [6 empty] | CM_M&G | 100%
501356 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-04-02 | 2022-07-14 | 2022-11-17 | 2023-11-10 | 2024-02-12 | West Lothian | 0 | 0 | 0 | 22846.86 | 3012.8075 | 0 | 0 | 25859.6675 | 574076.04 | 599935.7075 | 0 | [6 empty] | CM_WSNI | 100%
501666 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2016-04-25 | 2018-09-06 | 2018-09-28 | 2020-01-14 | 2020-01-14 | Scottish Borders | 0 | 0 | 145156.39 | 297675.17 | 1095145.57 | 1073028.02 | 130031.28 | 2741036.43 | 9553.57 | 2750590 | 0 | [6 empty] | CM_WSNI | 100%
500138 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS4 | 2015-03-19 | 2016-02-26 | 2016-04-20 | 2019-03-25 | 2019-06-28 | Aberdeenshire | 0 | 28827 | 5635 | 38771.25 | 44456 | 2434.75 | 0 | 120124 | 0 | 120124 | 148084.8492 | [6 empty] | EC01G | 0.298% | CS16D | 31.84% | EC01D | 67.86%
046581 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2009-04-28 | 2012-07-10 | 2012-11-26 | 2014-05-06 | 2014-05-06 | Aberdeenshire | 3593953.37 | 105577.13 | -7565.74 | 0 | 0 | 0 | 0 | 98011.39 | 0 | 3691964.76 | 0 | [6 empty] | CM_WWNI | 40% | SG1 | 60%
402777 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-08-06 | 2013-07-24 | 2013-09-02 | 2014-12-01 |  | East Ayrshire | 1507080 | 0 | -24812.7 | 0 | 0 | 0 | 0 | -24812.7 | 0 | 1482267.3 | 0 | [6 empty] | CM_WWI | 100%
045334 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2012-07-26 | 2012-08-08 | 2012-08-08 | 2011-03-14 | Na H-Eileanan an Iar | 81297.87 | 1482.91 | 0 | 0 | 0 | 0 | 0 | 1482.91 | 0 | 82780.78 | 0 | [6 empty] | DW13 | 100%
502262 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2017-04-28 | 2018-09-13 | 2018-09-14 | 2019-05-30 | 2019-09-03 | City of Edinburgh | 0 | 0 | 2141.96 | 72841.04 | 369885 | 27844.24 | 0 | 472712.24 | 1463.96 | 474176.2 | 0 | [6 empty] | CM_WWNI | 100%
502263 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW1 | 2021-04-01 | 2022-09-14 | 2023-01-19 | 2024-01-09 | 2024-04-10 | Falkirk | 0 | 0 | 20465 | 50987.7465 | 28420.4535 | 2402.87 | 28169.54 | 130445.61 | 1369554.3 | 1499999.91 | 0 | [6 empty] | CM_WWNI | 100%
502265 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2017-04-28 | 2019-03-07 | 2019-03-08 | 2019-11-29 | 2019-11-29 | North Ayrshire | 0 | 0 | 6300 | 102632 | 196031 | 744144.76 | 28927.08 | 1078034.84 | 1869.07 | 1079903.91 | 0 | [6 empty] | CM_WWNI | 100%
502266 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-02-28 | 2017-06-19 | 2017-06-19 | 2017-06-19 | 2017-06-19 | South Lanarkshire | 0 | 0 | 243.09 | 8.9 | 0 | 0 | 0 | 251.99 | 0 | 251.99 | 0 | [6 empty] | CM_WWNI | 100%
502267 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS1 | 2017-04-06 | 2019-04-08 | 2019-05-13 | 2020-07-17 | 2020-07-17 | Renfrewshire | 0 | 0 | 28500 | 115138 | 259816 | 1604039.92 | 529730.65 | 2537224.57 | 3899.08 | 2541123.65 | 0 | [6 empty] | CM_WWNI | 100%
502268 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2017-04-24 | 2019-03-07 | 2019-03-15 | 2020-05-14 | 2020-08-14 | Glasgow City | 0 | 0 | 38873.16 | 227005.74 | 495632.21 | 1226093.14 | 504964.49 | 2492568.74 | 13085.28 | 2505654.02 | 0 | [6 empty] | CM_WWNI | 100%
502269 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2017-04-05 | 2019-03-26 | 2019-03-28 | 2020-04-02 | 2020-04-02 | North Ayrshire | 0 | 0 | 11816 | 87054 | 403331 | 1730053.72 | 85370.06 | 2317624.78 | 14020.3 | 2331645.08 | 0 | [6 empty] | CM_WWNI | 100%
501147 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2015-10-08 | 2015-10-08 | 2016-02-01 | 2019-12-11 | 2019-12-11 | Scottish Water Wide | 0 | 25784 | 16033.35 | 94000 | 0 | 14182.65 | 0 | 150000 | 0 | 150000 | 0 | [6 empty] | CM_WSNI | 38.67% | CM_WWNI | 61.33%
503044 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Wastewater |  | SWMD | DWQ - Preparing for Future Investment | MS3 | 2018-05-17 | 2018-11-27 | 2018-12-10 | 2020-04-03 | 2020-07-06 | Scottish Water Wide | 0 | 0 | 0 | 0 | 168393.29 | 144722.97 | 908325.83 | 1221442.09 | 0.91 | 1221443 | 1555414.659 | [6 empty] | CS16S | 100%
402453 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS5 | 2011-08-30 | 2012-09-28 | 2013-01-29 | 2015-03-24 | 2015-03-24 | Scottish Water Wide | 9067418 | 172663.15 | 61754.85 | 160835 | 155859 | 125942.93 | 12955.09 | 690010.02 | 0 | 9757428.02 | 16826 | [6 empty] | CC1W | 100%
402999 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-09-28 | 2012-10-31 | 2012-11-30 | 2015-03-30 | 2015-03-30 | Scottish Water Wide | 4434154 | -17058.99 | 15064.99 | 88578 | 7499.13 | 0 | 0 | 94083.13 | 0 | 4528237.13 | 43467 | [6 empty] | CC1W | 100%
402454 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-08-30 | 2012-09-28 | 2012-10-25 | 2015-10-08 | 2015-10-08 | Scottish Water Wide | 1280300 | -83872.78 | 1763.15 | 0 | 0 | 0 | 0 | -82109.63 | 0 | 1198190.37 | 0 | [6 empty] | CC1W | 100%
402455 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-08-30 | 2012-09-28 | 2012-10-25 | 2014-12-18 | 2015-01-30 | Scottish Water Wide | 6749999 | 2493.21 | 81281.79 | 44226 | 25394.107 | 0 | 0 | 153395.107 | 0 | 6903394.107 | 54089 | [6 empty] | CC1W | 100%
402893 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | General |  | SWD | Wastewater non infrastructure | MS7 | 2012-08-31 | 2013-01-09 | 2013-02-05 | 2015-02-09 |  | Scottish Water Wide | 375097.32 | -11258.8 | 0 | 0 | 0 | 0 | 0 | -11258.8 | 0 | 363838.52 | 0 | [6 empty] | CM_WSNI | 50% | CM_WWNI | 50%
503450 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MSU | 2019-07-01 | 2019-07-29 | 2019-09-16 | 2020-04-23 | 2020-07-24 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 223673.51 | 124109.3 | 347782.81 | 2217.21 | 350000.02 | 3783756.1971 | [6 empty] | SG5 | 100%
503439 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MSU | 2019-04-01 | 2019-04-29 | 2019-08-29 | 2021-04-05 | 2021-07-06 | Glasgow City | 0 | 0 | 0 | 0 | 1253928.81 | 508678.75 | 549287.58 | 2311895.14 | 192033.67 | 2503928.81 | 3783756.1971 | [6 empty] | SG5 | 100%
503449 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS2 | 2019-02-25 | 2019-02-25 | 2019-05-13 | 2020-01-27 | 2020-04-28 | East Renfrewshire | 0 | 0 | 0 | 0 | 1225233.64 | 0 | 0 | 1225233.64 | 0 | 1225233.64 | 3783756.1971 | [6 empty] | SG5 | 100%
503522 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MSU | 2019-12-16 | 2020-10-05 | 2021-01-22 | 2022-08-18 | 2022-11-18 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 162683.8 | 1039624.28 | 1202308.08 | 1797691.88 | 2999999.96 | 3783756.1971 | [6 empty] | SG5 | 100%
503448 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MSU | 2019-07-01 | 2019-07-29 | 2019-09-09 | 2020-04-16 | 2020-07-17 | Dundee City | 0 | 0 | 0 | 0 | 0 | 523497.61 | 290506.49 | 814004.1 | 5154.9 | 819159 | 3783756.1971 | [6 empty] | SG5 | 100%
503456 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MSU | 2019-07-01 | 2020-05-25 | 2020-08-21 | 2021-04-01 | 2021-07-02 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 46518.87 | 325392.01 | 371910.88 | 128089.11 | 499999.99 | 587726.5342 | [6 empty] | WG5 | 100%
503549 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MSU | 2019-07-01 | 2019-07-01 | 2019-07-19 | 2021-03-25 | 2021-03-25 | West Lothian | 0 | 0 | 0 | 0 | 0 | 316341.61 | 411255.4 | 727597.01 | 22403.02 | 750000.03 | 587726.5342 | [6 empty] | WG5 | 100%
503451 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MSU | 2019-07-01 | 2019-07-29 | 2019-08-05 | 2019-09-13 | 2019-12-16 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 5467999.99 | 0 | 5467999.99 | 0 | 5467999.99 | 3783756.1971 | [6 empty] | SG5 | 100%
500675 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-06-05 | 2017-01-31 | 2017-01-31 | 2018-04-15 |  | Scottish Water Wide | 0 | 237418 | 1113994.05 | 145800.67 | 11566.97 | 0 | 0 | 1508779.69 | 0 | 1508779.69 | 0 | [6 empty] | CM_M&G | 100%
500262 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2017-05-26 | 2017-05-26 | All East Unitary Authorities | 0 | 6404.59 | -6404.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WWI | 100%
500293 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2016-01-31 | 2016-02-01 | Scottish Water Wide | 0 | 37812.79 | -37812.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
403845 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2015-11-13 |  | Scottish Water Wide | 135796.78 | 41182.86 | 0 | 0 | 0 | 0 | 0 | 41182.86 | 0 | 176979.64 | 0 | [6 empty] | CM_WSI | 100%
500295 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 0 | 197423 | 10906.72 | 0 | 0 | 0 | 0 | 208329.72 | 0 | 208329.72 | 0 | [6 empty] | CM_WSI | 100%
500294 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2017-05-18 | 2017-05-18 | Scottish Water Wide | 0 | 90122 | 5062.93 | 32003.15 | 0 | 0 | 0 | 127188.08 | 0 | 127188.08 | 0 | [6 empty] | CM_WSI | 100%
404120 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-03-05 | 2015-03-05 | 2015-03-05 | 2015-08-04 | 2015-09-04 | Scottish Water Wide | 320000 | -7745.71 | 0 | 0 | 0 | 0 | 0 | -7745.71 | 0 | 312254.29 | 0 | [6 empty] | CM_M&G | 100%
500296 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Water |  | SWD | Flood Risk Management Act | MS7 | 2015-04-16 | 2015-04-16 | 2016-01-06 | 2016-01-06 | 2016-01-06 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WR6 | 100%
500297 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-01-05 | 2016-01-05 | 2016-01-06 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
403861 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2017-01-31 |  | Scottish Water Wide | 50000 | 78348.08 | 51311.29 | 98.34 | 0 | 0 | 0 | 129757.71 | 0 | 179757.71 | 0 | [6 empty] | CM_WSI | 100%
403846 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2017-01-31 |  | Scottish Water Wide | 60000 | 178885.68 | 85973.17 | 0 | 0 | 0 | 0 | 264858.85 | 0 | 324858.85 | 0 | [6 empty] | CM_WSI | 100%
500292 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2016-11-15 | 2016-11-15 | Scottish Water Wide | 0 | 182491 | 21721.4 | 0 | 0 | 0 | 0 | 204212.4 | 0 | 204212.4 | 0 | [6 empty] | CM_WWI | 100%
502176 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-18 | 2017-05-18 | Scottish Water Wide | 0 | 0 | 703722.47 | 11871.62 | 23.759 | 0 | 0 | 715617.849 | 0 | 715617.849 | 0 | [6 empty] | CM_WWI | 100%
502177 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-08-22 | 2017-08-22 | 2017-08-22 | 2017-07-21 | 2017-07-21 | Scottish Water Wide | 0 | 0 | 675131.21 | 3758.1 | 0 | 0 | 0 | 678889.31 | 0 | 678889.31 | 0 | [6 empty] | CM_WWNI | 100%
502677 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-03-31 | 2021-04-09 | 2021-04-14 | 2021-04-15 | 2021-04-16 | Scottish Water Wide | 0 | 0 | 0 | 96515.6755 | 32885.42 | 4671.42 | 4635.21 | 138707.7255 | 0 | 138707.7255 | 0 | [6 empty] | CM_WWNI | 100%
502678 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-07-03 | Scottish Water Wide | 0 | 0 | 0 | 123080.3205 | 12519.14 | 2437.73 | 0 | 138037.1905 | 0 | 138037.1905 | 0 | [6 empty] | CM_WWNI | 100%
502178 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2019-07-10 | 2019-07-10 | 2019-07-17 | 2019-11-19 | 2020-02-25 | All East Unitary Authorities | 0 | 0 | 485612.9 | 23701.33 | 13396.42 | 0 | 0 | 522710.65 | 0 | 522710.65 | 0 | [6 empty] | CM_WWNI | 100%
502679 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2019-06-27 | 2019-07-08 | 2019-07-11 | 2019-07-12 | 2019-07-15 | All East Unitary Authorities | 0 | 0 | 0 | 103428.1475 | 21824.17 | 41741.82 | 0 | 166994.1375 | 0 | 166994.1375 | 0 | [6 empty] | CM_WWNI | 100%
500268 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2016-02-02 | 2017-01-06 | 2017-03-01 | All West Unitary Authorities | 0 | 41770 | -40282.65 | 813.24 | 0 | 0 | 0 | 2300.59 | 0 | 2300.59 | 0 | [6 empty] | CM_WWI | 100%
502180 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2019-07-10 | 2020-01-20 | 2020-05-21 | 2020-09-23 | 2020-12-24 | All South Unitary Authorities | 0 | 0 | 174480.13 | 10821.61 | 95.925 | 0 | 0 | 185397.665 | 0 | 185397.665 | 0 | [6 empty] | CM_WWNI | 100%
502680 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2019-06-28 | 2019-07-09 | 2019-07-12 | 2019-07-15 | 2019-07-16 | All South Unitary Authorities | 0 | 0 | 0 | 107697.83 | 0 | 57422.17 | 0 | 165120 | 0 | 165120 | 0 | [6 empty] | CM_WWNI | 100%
502181 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2019-07-01 | 2020-01-20 | 2020-05-21 | 2020-09-23 | 2020-12-24 | All West Unitary Authorities | 0 | 0 | 234149.86 | 7726.48 | 967.86 | 0 | 0 | 242844.2 | 0 | 242844.2 | 0 | [6 empty] | CM_WWNI | 100%
502681 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2019-06-28 | 2019-07-09 | 2019-07-12 | 2019-07-15 | 2019-07-16 | All West Unitary Authorities | 0 | 0 | 623.08 | 76847.22 | 147.51 | 87502.19 | 0 | 165120 | 0 | 165120 | 0 | [6 empty] | CM_WWNI | 100%
500298 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2017-05-18 | 2017-05-18 | Scottish Water Wide | 0 | 300976 | 39504.94 | 96617.565 | 0 | 0 | 0 | 437098.505 | 0 | 437098.505 | 0 | [6 empty] | CM_WSI | 100%
502170 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-07-20 | 2017-07-20 | 2017-07-20 | 2017-04-03 | 2017-07-01 | Scottish Water Wide | 0 | 0 | 1094408.92 | -152099.26 | 0 | 0 | 0 | 942309.66 | 0 | 942309.66 | 0 | [6 empty] | CM_WSNI | 100%
502682 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2019-06-27 | 2019-07-08 | 2019-07-11 | 2019-07-12 | 2019-07-15 | Scottish Water Wide | 0 | 0 | 108000 | 98593.7945 | 17086.712 | 0 | 0 | 223680.5065 | 0 | 223680.5065 | 0 | [6 empty] | CM_WSNI | 100%
502171 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-07-01 | All East Unitary Authorities | 0 | 0 | 428530.5 | 114845.23 | 0 | 0 | 0 | 543375.73 | 0 | 543375.73 | 0 | [6 empty] | CM_WSNI | 100%
502683 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2019-06-21 | 2019-06-21 | 2019-06-21 | 2019-06-21 | 2019-06-21 | Scottish Water Wide | 0 | 0 | 177120 | 177433.326 | 230400.004 | 0 | 0 | 584953.33 | 0 | 584953.33 | 0 | [6 empty] | CM_WSNI | 100%
500287 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2016-12-08 | 2016-12-21 | Scottish Water Wide | 0 | 416621.26 | 52520.63 | 0 | 0 | 0 | 0 | 469141.89 | 0 | 469141.89 | 0 | [6 empty] | CM_WSI | 100%
500274 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2015-11-03 | 2016-06-06 | 2016-09-28 | All East Unitary Authorities | 0 | 12025.09 | 3102.25 | 94.5 | 8.264 | 0 | 0 | 15230.104 | 0 | 15230.104 | 0 | [6 empty] | CM_WSI | 100%
500278 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2016-09-26 | 2017-06-29 | All North Unitary Authorities | 0 | 60060.58 | 53030.86 | -19320.57 | 0 | 0 | 0 | 93770.87 | 0 | 93770.87 | 0 | [6 empty] | CM_WSI | 100%
500282 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2017-02-01 | 2017-03-16 | All West Unitary Authorities | 0 | 63235 | 33163.69 | 1913.14 | 0 | 0 | 0 | 98311.83 | 0 | 98311.83 | 0 | [6 empty] | CM_WSI | 100%
502172 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-07-21 | 2017-07-21 | All North Unitary Authorities | 0 | 0 | 422624.76 | 17903.775 | 0 | 0 | 0 | 440528.535 | 0 | 440528.535 | 0 | [6 empty] | CM_WSNI | 100%
502684 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2019-06-27 | 2019-07-08 | 2019-07-11 | 2019-07-12 | 2019-07-15 | All North Unitary Authorities | 0 | 0 | 177120 | 115277.124 | 114346.616 | 40256.26 | 0 | 447000 | 0 | 447000 | 0 | [6 empty] | CM_WSNI | 100%
502173 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-06-20 | 2017-06-20 | All South Unitary Authorities | 0 | 0 | 471509.52 | 62195.865 | 0 | 0 | 0 | 533705.385 | 0 | 533705.385 | 0 | [6 empty] | CM_WSNI | 100%
502685 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2019-07-02 | 2019-07-11 | 2019-07-16 | 2019-07-17 | 2019-07-18 | All South Unitary Authorities | 0 | 0 | 177120 | 253315.8805 | 180044.266 | 0 | 0 | 610480.1465 | 0 | 610480.1465 | 0 | [6 empty] | CM_WSNI | 100%
502174 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-03-31 | 2017-03-31 | All West Unitary Authorities | 0 | 0 | 534693.1 | 108739.39 | 0 | 0 | 0 | 643432.49 | 0 | 643432.49 | 0 | [6 empty] | CM_WSNI | 100%
502676 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2019-07-01 | 2019-07-10 | 2019-07-15 | 2019-07-16 | 2019-07-17 | All West Unitary Authorities | 0 | 0 | 177120 | 275319.895 | 260981.8975 | 0 | 0 | 713421.7925 | 0 | 713421.7925 | 0 | [6 empty] | CM_WSNI | 100%
500275 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2015-11-03 | 2016-06-06 | 2016-08-08 | All East Unitary Authorities | 0 | 157872.26 | 19120.14 | 0 | 0 | 0 | 0 | 176992.4 | 0 | 176992.4 | 0 | [6 empty] | CM_WSNI | 100%
500279 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2016-08-18 | 2016-09-14 | All North Unitary Authorities | 0 | 43980 | -2389.4 | 0 | 0 | 0 | 0 | 41590.6 | 0 | 41590.6 | 0 | [6 empty] | CM_WSNI | 100%
500291 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2016-09-14 | 2016-09-14 | All South Unitary Authorities | 0 | 95111.44 | 56350.95 | 0 | 0 | 0 | 0 | 151462.39 | 0 | 151462.39 | 0 | [6 empty] | CM_WSNI | 100%
500283 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2017-02-01 | 2017-03-16 | All West Unitary Authorities | 0 | 147862 | -29745.92 | 0 | 0 | 0 | 0 | 118116.08 | 0 | 118116.08 | 0 | [6 empty] | CM_WSNI | 100%
500276 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2015-11-03 | 2016-06-06 | 2016-07-21 | All East Unitary Authorities | 0 | 32673 | -554.38 | 0 | 0 | 0 | 0 | 32118.62 | 0 | 32118.62 | 0 | [6 empty] | CM_WSNI | 100%
500280 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2016-08-18 | 2016-09-14 | All North Unitary Authorities | 0 | 33996 | 701.08 | 0 | 0 | 0 | 0 | 34697.08 | 0 | 34697.08 | 0 | [6 empty] | CM_WSNI | 100%
500289 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2016-11-03 | 2016-11-03 | All South Unitary Authorities | 0 | 83070.02 | 11610.56 | 0 | 0 | 0 | 0 | 94680.58 | 0 | 94680.58 | 0 | [6 empty] | CM_WSNI | 100%
500284 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2016-12-13 | 2017-02-02 | All West Unitary Authorities | 0 | 239540 | 63337.64 | 268.31 | 0 | 0 | 0 | 303145.95 | 0 | 303145.95 | 0 | [6 empty] | CM_WSNI | 100%
500286 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2016-01-06 | 2016-12-08 | 2017-03-30 | Scottish Water Wide | 0 | 1081651.52 | 247985.14 | -530.4 | 0 | 0 | 0 | 1329106.26 | 0 | 1329106.26 | 0 | [6 empty] | CM_WSNI | 100%
500277 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2016-06-06 | 2016-07-21 | All East Unitary Authorities | 0 | 593688.69 | 23897.7 | 4920.54 | 7602.6 | 0 | 0 | 630109.53 | 0 | 630109.53 | 0 | [6 empty] | CM_WSNI | 100%
500281 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-09-18 | 2016-08-18 | 2016-09-16 | All North Unitary Authorities | 0 | 365517.58 | 29930.32 | 0 | 0 | 0 | 0 | 395447.9 | 0 | 395447.9 | 0 | [6 empty] | CM_WSNI | 100%
500288 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2016-02-02 | 2016-11-03 | 2016-11-03 | All South Unitary Authorities | 0 | 511637.9 | 585542.53 | 106.31 | 0 | 0 | 0 | 1097286.74 | 0 | 1097286.74 | 0 | [6 empty] | CM_WSNI | 100%
500285 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2016-12-19 | 2017-01-19 | All West Unitary Authorities | 0 | 453258 | -200263.09 | 0 | 0 | 0 | 0 | 252994.91 | 0 | 252994.91 | 0 | [6 empty] | CM_WSNI | 100%
500271 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2017-05-12 | 2017-05-18 | 2017-05-18 | Scottish Water Wide | 0 | 1033259.2 | -24561.78 | 6945.255 | 385.75 | 0 | 0 | 1016028.425 | 0 | 1016028.425 | 0 | [6 empty] | CM_WWI | 100%
500265 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2016-02-02 | 2017-01-06 | 2017-06-29 | All South Unitary Authorities | 0 | 8909.96 | 2720.06 | 0 | 0 | 0 | 0 | 11630.02 | 0 | 11630.02 | 0 | [6 empty] | CM_WWI | 100%
500272 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-11-01 | 2016-11-01 | 2017-05-18 | Scottish Water Wide | 0 | 268531.28 | 114268.44 | 6398.26 | 0 | 0 | 0 | 389197.98 | 0 | 389197.98 | 0 | [6 empty] | CM_WWNI | 100%
500263 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2017-01-30 | 2017-01-30 | 2017-01-30 | All East Unitary Authorities | 0 | 100985 | -62109.66 | 0 | 0 | 0 | 0 | 38875.34 | 0 | 38875.34 | 0 | [6 empty] | CM_WWNI | 100%
500266 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS5 | 2015-04-20 | 2015-04-20 | 2016-02-02 | 2017-01-06 | 2017-01-06 | All South Unitary Authorities | 0 | 158609.82 | 69747.56 | 228.745 | 0 | 0 | 0 | 228586.125 | 0 | 228586.125 | 0 | [6 empty] | CM_WWNI | 100%
500269 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2016-02-02 | 2017-01-06 | 2017-01-06 | All West Unitary Authorities | 0 | 255942.21 | 60646.06 | 234.58 | 637.525 | 0 | 0 | 317460.375 | 0 | 317460.375 | 0 | [6 empty] | CM_WWNI | 100%
500273 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2016-07-20 | 2016-11-01 | 2016-11-01 | Scottish Water Wide | 0 | 399834.33 | 53662.25 | -106283.44 | 0 | 0 | 0 | 347213.14 | 0 | 347213.14 | 0 | [6 empty] | CM_WWNI | 100%
500264 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2016-02-02 | 2017-01-31 | 2017-01-31 | All East Unitary Authorities | 0 | 330052 | -203269.31 | -2930.31 | 0 | 0 | 0 | 123852.38 | 0 | 123852.38 | 0 | [6 empty] | CM_WWNI | 100%
500267 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-21 | 2015-04-21 | 2015-04-21 | 2017-01-06 | 2017-04-26 | All South Unitary Authorities | 0 | 456568.9 | 279224.69 | 722.2325 | 5699.56 | 0 | 0 | 742215.3825 | 0 | 742215.3825 | 0 | [6 empty] | CM_WWNI | 100%
500270 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-01 | 2015-07-13 | 2015-07-13 | 2017-01-06 | 2017-03-06 | All West Unitary Authorities | 0 | 289496.83 | 35341.45 | 1778.92 | 0 | 0 | 0 | 326617.2 | 0 | 326617.2 | 0 | [6 empty] | CM_WWNI | 100%
501292 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2021-04-15 |  |  | 2021-04-15 | 2021-04-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 1333333.5 | 1333333.51 | 2666667.01 | 0 | 2666667.01 | 0 | [6 empty] | CM_WWI | 100%
501293 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2021-04-15 |  |  | 2021-04-15 | 2021-04-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 1666666.5 | 1666666.5 | 3333333 | 0 | 3333333 | 0 | [6 empty] | CM_WSNI | 100%
403836 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-17 | 2014-06-17 | 2014-06-17 | 2016-12-07 |  | Scottish Water Wide | 403503 | 30983 | -2011.25 | 0 | 0 | 0 | 0 | 28971.75 | 0 | 432474.75 | 0 | [6 empty] | CM_WSI | 100%
403837 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-06-23 |  | All East Unitary Authorities | 12629 | 12371 | -15475.14 | 0 | 0 | 0 | 0 | -3104.14 | 0 | 9524.86 | 0 | [6 empty] | CM_WSI | 100%
403838 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-08 |  | All North Unitary Authorities | 24128.76 | 81354.24 | -64981.05 | 0 | 0 | 0 | 0 | 16373.19 | 0 | 40501.95 | 0 | [6 empty] | CM_WSI | 100%
403840 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-05-09 |  | All West Unitary Authorities | 20521.67 | 3716.03 | 116.15 | 0 | 0 | 0 | 0 | 3832.18 | 0 | 24353.85 | 0 | [6 empty] | CM_WSI | 100%
501783 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2020-04-03 | 2020-05-29 | 2020-05-29 | 2020-05-29 | 2020-05-29 | Scottish Water Wide | 0 | 0 | 499613 | 172485 | 113926 | 241976.02 | 0 | 1028000.02 | 0 | 1028000.02 | 0 | [6 empty] | CM_WSI | 100%
403841 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-06 |  | All East Unitary Authorities | 54389.62 | 78615.37 | 12334.62 | 0 | 0 | 0 | 0 | 90949.99 | 0 | 145339.61 | 0 | [6 empty] | CM_WWNI | 100%
403842 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2015-11-05 |  | All North Unitary Authorities | 34982.7 | -1120.29 | 0 | 0 | 0 | 0 | 0 | -1120.29 | 0 | 33862.41 | 0 | [6 empty] | CM_WSNI | 43.87% | CM_WWNI | 56.13%
500290 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-07 | 2015-04-07 | 2016-02-02 | 2016-11-03 | 2016-11-03 | All South Unitary Authorities | 0 | 41385.94 | 129720.26 | 0 | 0 | 0 | 0 | 171106.2 | 0 | 171106.2 | 0 | [6 empty] | CM_WSI | 100%
403833 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-06-07 |  | All East Unitary Authorities | 36435.57 | -2408.57 | -1012.73 | 0 | 0 | 0 | 0 | -3421.3 | 0 | 33014.27 | 0 | [6 empty] | CM_WSNI | 100%
403834 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-08 |  | All North Unitary Authorities | 29931.93 | 56849.28 | 604.44 | 0 | 0 | 0 | 0 | 57453.72 | 0 | 87385.65 | 0 | [6 empty] | CM_WSNI | 100%
403835 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-19 |  | All South Unitary Authorities | 21760.52 | 36663.48 | -5894.4 | 226.51 | 0 | 0 | 0 | 30995.59 | 0 | 52756.11 | 0 | [6 empty] | CM_WSNI | 100%
403832 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-05-10 |  | All West Unitary Authorities | 45329.9 | 5112.04 | 1250.85 | 0 | 0 | 0 | 0 | 6362.89 | 0 | 51692.79 | 0 | [6 empty] | CM_WSNI | 100%
403847 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-06-07 |  | All East Unitary Authorities | 21309.06 | 50111.4 | 10.09 | 0 | 0 | 0 | 0 | 50121.49 | 0 | 71430.55 | 0 | [6 empty] | CM_WSNI | 100%
403848 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-08-15 |  | All North Unitary Authorities | 47409.54 | 35152.46 | 2359.99 | 0 | 0 | 0 | 0 | 37512.45 | 0 | 84921.99 | 0 | [6 empty] | CM_WSNI | 100%
403849 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-19 |  | All South Unitary Authorities | 46766.9 | 22472.46 | 342.38 | 264.7 | 0 | 0 | 0 | 23079.54 | 0 | 69846.44 | 0 | [6 empty] | CM_WSNI | 100%
403850 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-05-09 |  | All West Unitary Authorities | 58090.12 | 6425.27 | 0 | 0 | 0 | 0 | 0 | 6425.27 | 0 | 64515.39 | 0 | [6 empty] | CM_WSNI | 100%
403851 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-06 |  | All East Unitary Authorities | 9479.95 | 10795.12 | 7173.08 | 0 | 0 | 0 | 0 | 17968.2 | 0 | 27448.15 | 0 | [6 empty] | CM_WWNI | 100%
403852 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-01-13 |  | All North Unitary Authorities | 624 | 423.12 | 0 | 0 | 0 | 0 | 0 | 423.12 | 0 | 1047.12 | 0 | [6 empty] | CM_WWNI | 100%
403853 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-09-01 |  | Scottish Water Wide | 371310.51 | 415764.61 | 15702.21 | 0 | 0 | 0 | 0 | 431466.82 | 0 | 802777.33 | 0 | [6 empty] | CM_WWI | 100%
403854 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-15 |  | All South Unitary Authorities | 341.73 | 415.07 | -106.07 | 0 | 0 | 0 | 0 | 309 | 0 | 650.73 | 0 | [6 empty] | CM_WWNI | 100%
403839 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-19 |  | All South Unitary Authorities | 8847.03 | 626.04 | -388.18 | 0 | 0 | 0 | 0 | 237.86 | 0 | 9084.89 | 0 | [6 empty] | CM_WWNI | 100%
403855 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-15 |  | All West Unitary Authorities | 10539.69 | 7391.5 | 422.22 | 0 | 0 | 0 | 0 | 7813.72 | 0 | 18353.41 | 0 | [6 empty] | CM_WWNI | 100%
403856 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-06 |  | All East Unitary Authorities | 135598.35 | 125725.88 | 15559.85 | 202.15 | 0 | 0 | 0 | 141487.88 | 0 | 277086.23 | 0 | [6 empty] | CM_WWNI | 100%
403858 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-09-15 |  | Scottish Water Wide | 4544.36 | 1070.55 | 0 | 0 | 0 | 0 | 0 | 1070.55 | 0 | 5614.91 | 0 | [6 empty] | CM_WWNI | 100%
403859 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-15 |  | All South Unitary Authorities | 41151.62 | 80070.25 | 1621.81 | 0 | 0 | 0 | 0 | 81692.06 | 0 | 122843.68 | 0 | [6 empty] | CM_WWNI | 100%
403860 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-06-12 | 2014-06-12 | 2014-06-12 | 2016-12-15 |  | All West Unitary Authorities | 57501.5 | 91866.5 | 416.42 | 315 | 0 | 0 | 0 | 92597.92 | 0 | 150099.42 | 0 | [6 empty] | CM_WWNI | 100%
402080 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2011-04-20 | 2011-06-14 | 2011-06-14 | 2012-05-25 |  | Scottish Water Wide | 1683555.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1683555.13 | 0 | [6 empty] | CM_WWI | 100%
402522 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-26 | 2012-04-24 | 2012-04-24 | 2013-08-14 |  | Scottish Water Wide | 1737334 | 23.63 | 0 | 0 | 0 | 0 | 0 | 23.63 | 0 | 1737357.63 | 0 | [6 empty] | CM_WWI | 100%
403354 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-18 | 2013-05-29 | 2013-05-29 | 2014-05-08 |  | Scottish Water Wide | 1686883 | 0 | -1126.16 | 0 | 0 | 0 | 0 | -1126.16 | 0 | 1685756.84 | 0 | [6 empty] | CM_WWI | 100%
403355 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-09-09 | 2014-03-25 | 2014-03-26 | 2015-09-21 |  | Scottish Water Wide | 1683000 | 53393.07 | 2197.4 | 102.59 | 0 | 0 | 0 | 55693.06 | 0 | 1738693.06 | 0 | [6 empty] | CM_WWI | 100%
503540 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-11-16 | 2022-04-07 | 2022-06-15 | 2023-01-24 | 2023-04-26 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 35403.06 | 34613.59 | 70016.65 | 403983.35 | 474000 | 240495.8008 | [6 empty] | CS11A | 100%
501148 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2016-02-17 | 2016-02-17 | 2016-04-21 | 2016-11-29 | 2016-11-29 | Scottish Water Wide | 0 | 0 | 166282.93 | 370 | -5493.28 | 0 | 0 | 161159.65 | 0 | 161159.65 | 240495.8008 | [6 empty] | CS11A | 100%
502936 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS3 | 2017-10-18 | 2017-10-18 | 2017-11-30 | 2019-04-25 | 2019-04-25 | Scottish Water Wide | 0 | 0 | 0 | 17155.14 | 195610.95 | 2500 | 0 | 215266.09 | 0 | 215266.09 | 240495.8008 | [6 empty] | CS11A | 100%
503098 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2019-07-01 | 2019-07-01 | 2019-09-11 | 2020-04-13 | 2020-07-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 165859.4 | 82573.84 | 248433.24 | 1566.84 | 250000.08 | 240495.8008 | [6 empty] | CS11A | 100%
502423 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2017-01-25 | 2017-01-25 | 2017-03-20 | 2018-03-02 | 2018-03-02 | Scottish Water Wide | 0 | 0 | 34559.14 | 178775 | -20286.725 | 0 | 0 | 193047.415 | 0 | 193047.415 | 240495.8008 | [6 empty] | CS11A | 100%
403352 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-15 | 2013-04-15 | 2013-04-15 | 2014-09-01 |  | Scottish Water Wide | 250000 | 0 | -3483.66 | 0 | 0 | 0 | 0 | -3483.66 | 0 | 246516.34 | 0 | [6 empty] | CM_WWI | 100%
403353 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-22 | 2014-03-25 | 2014-03-26 | 2015-12-04 |  | Scottish Water Wide | 244939 | 23210 | 0 | 0 | 0 | 0 | 0 | 23210 | 0 | 268149 | 0 | [6 empty] | CM_WWI | 100%
403618 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-11-11 | 2013-11-22 | 2013-11-22 | 2015-12-15 |  | Scottish Water Wide | 250039.62 | 5034.26 | 3015.57 | -214 | 0 | 0 | 0 | 7835.83 | 0 | 257875.45 | 0 | [6 empty] | CM_WWI | 100%
400107 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-09-28 | 2013-07-29 | 2014-03-19 | 2014-03-26 | Argyll and Bute-North Argyll | 927418 | 171.28 | 45 | 9237.5 | 0 | 0 | 0 | 9453.78 | 0 | 936871.78 | 799 | [6 empty] | WG4 | 100%
045389 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-07-20 | 2012-08-20 | 2014-08-29 | 2014-09-29 | Dumfries and Galloway | 8257963 | 5322 | -3611.08 | 285.995 | 0 | 0 | 0 | 1996.915 | 0 | 8259959.915 | 47035 | [6 empty] | WG4 | 100%
045390 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-09-26 | 2013-01-16 | 2014-06-20 | 2014-06-30 | Dumfries and Galloway | 8875802 | 95146.27 | 10288.93 | 3.71 | 0 | 0 | 0 | 105438.91 | 0 | 8981240.91 | 88153 |  |  |  |  | 42445.6258 |  | WG4 | 100%
045395 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS6 | 2008-07-16 | 2015-03-11 | 2015-03-23 | 2017-03-01 | 2017-03-01 | Highland | 1433616.26 | 127784.74 | 766588.79 | 183701.49 | 41076.06 | 0 | 0 | 1119151.08 | 0 | 2552767.34 | 94074 | [6 empty] | WG4 | 100% | bar: Regulatory Outputs OMG-03
045385 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-06-20 | 2013-09-02 | 2014-12-05 | 2015-02-09 | Highland | 2636329 | 131721 | 15956.57 | 0 | 0 | 0 | 0 | 147677.57 | 0 | 2784006.57 | 29723 | [6 empty] | WG4 | 100%
400103 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-06-18 | 2012-10-29 | 2013-03-25 | 2013-03-28 | Highland | 654891.77 | -2720.25 | 0 | 0 | 0 | 0 | 0 | -2720.25 | 0 | 652171.52 | 0 | [6 empty] | CM_WSNI | 21.83% | WG4 | 78.17%
045388 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2011-08-08 | 2011-08-16 | 2014-02-06 | 2014-03-19 | Fife | 3913359 | 19324.46 | 0 | 0 | 0 | 0 | 0 | 19324.46 | 0 | 3932683.46 | 6115 | [6 empty] | WG4 | 100%
045384 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-03-27 | 2012-06-04 | 2014-02-03 | 2014-03-19 | Highland | 4463646 | -9351.44 | 0 | 0 | 0 | 0 | 0 | -9351.44 | 0 | 4454294.56 | 0 | [6 empty] | WG4 | 100%
400106 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-09-11 | 2013-07-29 | 2014-03-28 | 2014-03-31 | Argyll and Bute-North Argyll | 3027762 | -9896 | -18000.01 | 16146.885 | 2026.1085 | 0 | 0 | -9723.0165 | 0 | 3018038.9835 | 32034 | [6 empty] | WG4 | 100%
045383 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2017-09-27 | 2017-07-03 | 2017-06-01 | 2017-07-03 | Highland | 1207584 | 443800 | 1204130.21 | 129429.8165 | 0 | 0 | 0 | 1777360.0265 | 0 | 2984944.0265 | 11719825.0001 | [6 empty] | WG4 | 100%
045392 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-08-31 | 2012-12-03 | 2014-03-28 | 2014-03-31 | Stirling | 1613978 | -7128 | 790.7 | 0 | 0 | 0 | 0 | -6337.3 | 0 | 1607640.7 | 4041.0001 | [6 empty] | WG4 | 100%
400105 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-07-16 | 2012-03-13 | 2012-07-23 | 2012-12-14 | 2013-03-28 | Na H-Eileanan an Iar | 891281.46 | 11422.65 | 0 | 0 | 0 | 0 | 0 | 11422.65 | 0 | 902704.11 | 0 | [6 empty] | WG4 | 100%
500043 | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | NONINF | SOSI | MS3 | 2016-03-29 | 2017-12-22 | 2017-12-22 | 2019-04-01 | 2019-04-01 | Na H-Eileanan an Iar | 302.76 | 43756.68 | 237292.44 | 526588.9 | 513198.19 | 197155.62 | 8295.18 | 1526287.01 | 258.22 | 1526847.99 | 753247.7316 | [6 empty] | WG4 | 100% | bar: Regulatory Outputs OMG-08
500041 | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS6 | 2016-10-10 | 2017-09-29 | 2018-02-26 | 2018-09-01 | 2019-01-01 | Highland | 127.3 | 15472.7 | 19109.32 | 214411.51 | 490774.52 | 782.52 | 1036.65 | 741587.22 | 580.85 | 742295.37 | 1066853.3767 | [6 empty] | WG4 | 100% | bar: Regulatory Outputs OMG-08
500048 | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWD | SOSI | MS7 | 2015-02-23 | 2015-03-18 | 2015-03-18 | 2015-04-01 | 2015-12-01 | Highland | 0 | 1150 | -895.75 | 0 | 0 | 0 | 0 | 254.25 | 0 | 254.25 | 378123.666 | [6 empty] | WG4 | 100% | bar: Regulatory Outputs OMG-08
500032 | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS5 | 2017-03-31 | 2017-12-22 | 2018-03-26 | 2018-12-19 | 2019-03-27 | Orkney Islands | 24.93 | 47754.46 | 131072.47 | 1567095.98 | 206236.325 | 105615.04 | 7119.14 | 2064893.415 | 8975.1 | 2073893.445 | 4540257.3461 | [6 empty] | WG4 | 100%
500033 | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWD | SOSI | GW1 | 2019-05-03 | 2019-05-13 | 2019-05-13 | 2019-05-13 | 2019-05-13 | Shetland Islands | 686.11 | 42999.07 | -43685.18 | 394.84 | 0 | 0 | 0 | -291.27 | 0 | 394.84 | 3243356.8919 | [6 empty] | WG4 | 100%
500042 | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWD | SOSI | MS7 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-25 | 2016-08-26 | Na H-Eileanan an Iar | 0 | 27596 | -27596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG4 | 100%
500046 | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | WINF | SOSI | MS0 | 2018-09-28 | 2020-05-25 | 2020-08-20 | 2021-11-01 | 2022-02-01 | Na H-Eileanan an Iar | 0 | 53505.94 | 61798.03 | 40362.5185 | 72120.8115 | 159369.7 | 1106974.17 | 1494131.17 | 2013178.9 | 3507310.07 | 972867.3086 | [6 empty] | WG4 | 100% | bar: Regulatory Outputs OMG-08
500034 | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS4 | 2016-10-31 | 2018-03-21 | 2018-06-26 | 2019-03-01 | 2019-05-01 | Argyll and Bute-North Argyll | 105.42 | 11237.68 | 31714.6 | 23573.82 | 201544.43 | 22787.48 | 1011.8 | 291869.81 | 314.96 | 292290.19 | 697661.2723 | [6 empty] | WG4 | 100% | bar: Regulatory Outputs OMG-08
500044 | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWD | SOSI | MS5 | 2018-09-28 | 2018-12-17 | 2018-12-17 | 2018-12-01 | 2019-03-01 | Highland | 148.01 | 10265.99 | 0 | 963.747 | 7934.543 | 6308.71 | 0 | 25472.99 | 0 | 25621 | 557627.114 | [6 empty] | WG4 | 100% | bar: Regulatory Outputs OMG-08
500045 | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWD | SOSI | MS1 | 2016-03-29 | 2019-05-13 | 2019-06-19 | 2020-07-20 | 2020-10-14 | Na H-Eileanan an Iar | 471.4 | 54181.41 | 395305.6 | 226128.06 | 11180.7 | 0 | 0 | 686795.77 | 0 | 687267.17 | 255781.031 | [6 empty] | WG4 | 100%
402842 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-09-14 | 2015-05-11 | 2015-01-12 | 2015-09-18 |  | Scottish Water Wide | 370193.69 | 317710.15 | 91.88 | 529.69 | 0 | 0 | 0 | 318331.72 | 0 | 688525.41 | 0 | [6 empty] | CM_WWNI | 100%
500475 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS3 | 2015-10-15 | 2017-03-28 | 2017-06-20 | 2019-08-06 | 2019-10-29 | Scottish Water Wide | 0 | 3426.41 | 258352.68 | 1699284.75 | 803926.7 | 106088.32 | 7834.98 | 2878913.84 | 5030.24 | 2883944.08 | 769991.1235 |  |  |  |  | 67269.9996 |  | CM_WSNI | 37.71% | DW25T | 62.29%
501039 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS4 | 2016-07-19 | 2017-12-11 | 2018-02-02 | 2018-06-27 | 2019-05-16 | Scottish Water Wide | 0 | 0 | 0 | 24418 | 4917 | 479.8 | 162.99 | 29977.79 | 22.2 | 29999.99 | 769991.1235 | [6 empty] | DW25T | 100%
501144 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS3 | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2020-04-13 | 2020-07-06 | Scottish Water Wide | 0 | 15069.77 | 24435.68 | 345517.01 | 1121617.78 | 1169564.43 | 21329.63 | 2697534.3 | 5232.71 | 2702767.01 | 769991.1235 | [6 empty] | CM_WSNI | 35% | DW25T | 65%
501145 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS5 | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-27 | 2018-12-14 | Scottish Water Wide | 0 | 15069.77 | 23441.86 | -2511.63 | 0 | 9000 | 0 | 45000 | 0 | 45000 | 769991.1235 | [6 empty] | DW25T | 100%
501146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS2 | 2018-03-26 | 2019-03-27 | 2019-07-24 | 2020-07-21 | 2020-10-21 | Scottish Water Wide | 0 | 0 | 32167.33 | 43960.24 | 0 | 0 | 0 | 76127.57 | 0 | 76127.57 | 769991.1235 | [6 empty] | DW25T | 100%
050012 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 2374088.3997 | 2374088.3997 | 0 | 2374088.3997 | 769991.1235 | [6 empty] | DW25T | 100%
501116 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-01 | 2016-05-01 | Highland | 0 | 7116.28 | 0 | 0 | 0 | 0 | 0 | 7116.28 | 0 | 7116.28 | 1817908.3275 | [6 empty] | CS16WR | 100% | bar: Regulatory Outputs OMG-07
501115 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | WINF | Supply Resilience | MS3 | 2016-09-20 | 2018-03-29 | 2018-03-29 | 2019-06-01 | 2019-08-01 | Scottish Borders | 0 | 21600 | 133675 | 569454 | 2709796.42 | 409510.79 | 0 | 3844036.21 | 0 | 3844036.21 | 2405634.8617 | [6 empty] | CS16WR | 50% | WG5 | 50% | bar: Regulatory Outputs OMG-07
501041 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2016-02-29 | 2016-03-11 | 2016-03-11 | 2016-03-01 | 2016-05-01 | Orkney Islands | 0 | 7027.31 | 0 | 0 | 0 | 0 | 0 | 7027.31 | 0 | 7027.31 | 1817908.3275 | [6 empty] | CS16WR | 100% | bar: Regulatory Outputs OMG-07
500973 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | NONINF | Supply Resilience | MS4 | 2016-03-17 | 2017-03-31 | 2017-06-30 | 2018-12-01 | 2019-03-01 | Orkney Islands | 0 | 13249.92 | 595494.23 | 314930.7 | 699443.05 | 13642.72 | 11794.71 | 1648555.33 | 0 | 1648555.33 | 1817908.3275 | [6 empty] | CS16WR | 100% | bar: Regulatory Outputs OMG-07
500733 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2015-08-25 | 2016-03-22 | 2016-03-22 | 2016-12-01 | 2017-03-01 | All North Unitary Authorities | 0 | 35000 | -8280.32 | -3471.55 | 0 | 0 | 0 | 23248.13 | 0 | 23248.13 | 1817908.3275 | [6 empty] | CS16WR | 100% | bar: Regulatory Outputs OMG-07
401262 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2010-09-15 | 2015-03-11 | 2015-03-11 | 2015-07-13 | 2015-07-13 | Scottish Water Wide | 958741 | 7703.71 | 0 | 0 | 0 | 0 | 0 | 7703.71 | 0 | 966444.71 | 469148.9999 | [6 empty] | CS18W | 100%
501257 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2016-08-15 | 2018-05-31 | 2018-06-05 | 2020-04-02 | 2020-07-02 | Aberdeenshire | 0 | 22853.75 | 23497.75 | 601684.13 | 923785.01 | 768600.33 | 66401.13 | 2406822.1 | 11925.85 | 2418747.95 | 0 |  |  |  |  | 11829.9996 |  | CM_WSNI | 100%
046198 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-07-31 | 2010-09-27 | 2011-05-30 | 2011-12-23 |  | Aberdeenshire | 1059999.17 | 72.76 | 0 | 0 | 0 | 0 | 0 | 72.76 | 0 | 1060071.93 | 0 | [6 empty] | CM_WSI | 100%
502630 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2017-03-14 | 2017-07-28 | 2017-09-11 | 2018-05-03 | 2018-05-03 | Aberdeen City | 0 | 0 | 5981.31 | 1792983.869 | 48637.641 | 1254.45 | 1249.6 | 1850106.87 | 495.95 | 1850602.82 | 0 | [6 empty] | CM_WSNI | 100%
503370 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | GW0 | 2021-04-01 | 2022-06-01 | 2022-10-04 | 2023-06-30 | 2023-10-02 | Renfrewshire | 0 | 0 | 0 | 0 | 12383.48 | 6232.38 | 5384.07 | 23999.93 | 475999.98 | 499999.91 | 0 | [6 empty] | CM_M&G | 100%
045335 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-11-18 | 2012-03-09 | 2012-03-30 | Highland | 41220.72 | 21 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 41241.72 | 0 | [6 empty] | DW13 | 100%
503275 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-08-02 | 2022-12-14 | 2023-04-18 | 2024-04-15 | 2024-07-16 | Aberdeenshire | 0 | 0 | 0 | 0 | 83449.24 | 14624.68 | 36371.55 | 134445.47 | 16385.36 | 150830.83 | 148885.7057 | [6 empty] | SG1 | 100%
500591 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-11-18 | 2016-06-30 | 2016-06-30 | 2019-06-11 | 2019-06-12 | Scottish Water Wide | 0 | 185131 | 339196.8 | 194102.15 | 166354.73 | 12579 | 0 | 897363.68 | 0 | 897363.68 | 0 | [6 empty] | CM_M&G | 100%
500593 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-09-17 | 2016-12-22 | 2016-12-22 | 2019-05-29 | 2019-05-30 | Scottish Water Wide | 0 | 496728 | 121999.92 | 330491.881 | 105818.779 | 89497.49 | 0 | 1144536.07 | 0 | 1144536.07 | 0 | [6 empty] | CM_M&G | 100%
500676 | Q&S4 | Improving the customer experience | Meter Accuracy |  |  | General |  | SWD | Meter Accuracy | MS3 | 2015-06-05 | 2017-09-01 | 2017-09-01 | 2019-08-14 |  | Scottish Water Wide | 0 | 382234.46 | 1059259.67 | 1270328.94 | 730971.26 | 181042.95 | 0 | 3623837.28 | 0 | 3623837.28 | 4007137.1184 |  |  |  |  | -148956 |  | CS4 | 1.997% | CM_M&G | 98%
503357 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS2 | 2019-03-11 | 2019-03-11 | 2022-05-09 | 2022-12-02 | 2023-03-06 | Aberdeenshire | 0 | 0 | 0 | 0 | 29439.25 | 104633.22 | 104227.67 | 238300.14 | 211699.76 | 449999.9 | 587726.5342 | [6 empty] | WG5 | 100%
503435 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MSU | 2019-07-01 | 2019-07-29 | 2019-10-03 | 2021-05-10 | 2021-08-10 | Falkirk | 0 | 0 | 0 | 0 | 0 | 170947.98 | 375730.8 | 546678.78 | 174321.18 | 720999.96 | 3783756.1971 | [6 empty] | SG5 | 100%
503436 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MSU | 2019-07-01 | 2020-06-29 | 2020-09-01 | 2021-10-01 | 2022-01-03 | Moray | 0 | 0 | 0 | 0 | 0 | 121363.65 | 898783.42 | 1020147.07 | 979852.95 | 2000000.02 | 3783756.1971 | [6 empty] | SG5 | 100%
503360 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MSU | 2019-07-01 | 2019-07-08 | 2019-09-26 | 2020-10-20 | 2021-01-26 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 441966.76 | 1539231.36 | 1981198.12 | 18801.8 | 1999999.92 | 587726.5342 | [6 empty] | WG5 | 100%
503359 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MSU | 2019-07-01 | 2019-07-08 | 2019-09-26 | 2020-04-28 | 2020-07-29 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 148096.99 | 240365.76 | 388462.75 | 2537.26 | 391000.01 | 587726.5342 | [6 empty] | WG5 | 100%
503518 | Q&S4 | Supporting economic development | Infra Charge |  |  | General |  | SWD | Infra Charge | MSU | 2019-07-01 | 2019-08-05 | 2019-12-05 | 2021-09-06 | 2021-12-07 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 3820384.83 | 3016407.08 | 6836791.91 | 2663208.11 | 9500000.02 | 4371482.7313 | [6 empty] | SG5 | 50% | WG5 | 50%
503362 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MSU | 2019-04-25 | 2019-04-25 | 2019-07-09 | 2019-08-02 | 2019-11-04 | Fife | 0 | 0 | 0 | 0 | 60797 | 2000000 | 0 | 2060797 | 0 | 2060797 | 0 | [6 empty] | SG5 | 100%
503358 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MSU | 2019-07-01 | 2019-07-08 | 2019-09-26 | 2020-04-28 | 2020-07-29 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 121201.56 | 196716.61 | 317918.17 | 2081.85 | 320000.02 | 587726.5342 | [6 empty] | WG5 | 100%
500954 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-10-23 | 2015-12-14 | 2015-12-14 | 2017-06-23 |  | Scottish Water Wide | 0 | 286124 | 52979.45 | 0 | 0 | 0 | 0 | 339103.45 | 0 | 339103.45 | 0 | [6 empty] | CM_M&G | 100%
403909 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-09-05 | 2014-09-05 | 2014-09-05 | 2015-06-30 |  | Scottish Water Wide | 261711 | 4072.61 | 0 | 0 | 0 | 0 | 0 | 4072.61 | 0 | 265783.61 | 0 | [6 empty] | CM_M&G | 100%
501532 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2022-10-17 | 2023-06-08 | 2023-10-12 | 2024-02-21 | 2024-05-23 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237340.04 | 237340.04 | 0 | [6 empty] | CM_WSNI | 100%
502572 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2019-10-17 | 2020-07-06 | 2020-09-04 | 2021-08-18 | 2021-11-18 | Scottish Borders | 0 | 0 | 20930.23 | 2091.45 | 45128.41 | 64982.73 | 648088.81 | 781221.63 | 530778.33 | 1311999.96 | 148885.7057 | [6 empty] | WG1 | 100%
045409 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-03-16 | 2011-10-03 | 2015-03-27 | 2015-12-17 | Scottish Borders | 4230414.8 | 217150.56 | 33919.75 | -32156.47 | -9436.0253 | 0 | 0 | 209477.8147 | 0 | 4439892.6147 | 45802 |  |  |  |  | 21395 |  | CS16W | 1.577% | DW23 | 98.42%
501512 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW1 | 2021-04-01 | 2021-10-25 | 2022-01-10 | 2022-05-24 | 2022-08-24 | Highland | 0 | 0 | 0 | 25324.23 | 28245.633 | 22455.41 | 36207.79 | 112233.063 | 560499.98 | 672733.043 | 0 | [6 empty] | CM_WWNI | 100%
403960 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2014-11-10 | 2015-04-20 | 2015-05-11 | 2017-03-08 | 2017-04-13 | Scottish Water Wide | 85123 | 2573932 | 291248 | 38056 | -4671.365 | 0 | 0 | 2898564.635 | 0 | 2983687.635 | 1888493.0001 | [6 empty] | EC01A | 100%
500481 | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWD | Renewable power | MS7 | 2015-05-19 | 2015-12-23 | 2016-01-07 | 2018-05-11 | 2018-05-11 | Scottish Water Wide | 0 | 791122.51 | 793.12 | 0 | 0 | 0 | 0 | 791915.63 | 0 | 791915.63 | 764721.6298 | [6 empty] | I2S_WI | 100%
401676 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2011-02-04 | 2012-09-05 | 2012-09-18 | 2016-08-08 |  | Scottish Water Wide | 15017167 | 207275 | -1133.9 | 35.59 | 0 | 0 | 0 | 206176.69 | 0 | 15223343.69 | 0 | [6 empty] | CM_M&G | 100%
503395 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2018-09-06 | 2020-10-26 | 2021-03-01 | 2022-09-19 | 2022-12-16 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSNI | 100%
503394 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2018-08-24 | 2018-09-04 | 2018-09-04 | 2019-09-12 | 2019-10-24 | Scottish Water Wide | 0 | 0 | 0 | 0 | 233115.61 | 605952.46 | 0 | 839068.07 | 0 | 839068.07 | 0 | [6 empty] | CM_WSNI | 100%
402351 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-09-20 | 2012-06-27 | 2012-08-27 | 2013-02-27 | 2013-02-27 | Aberdeen City | 92563.76 | 85.66 | 0 | 0 | 0 | 0 | 0 | 85.66 | 0 | 92649.42 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
402390 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-03-31 | 2014-07-22 | 2014-07-30 | 2014-09-22 | 2014-09-22 | Glasgow City | 322018 | 0 | 0 | 0 | -921.74 | 0 | 0 | -921.74 | 0 | 321096.26 | 573.6 | [6 empty] | CM_WWI | 40% | CS11A | 60%
402448 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-12-05 | 2012-09-14 | 2012-11-21 | 2013-12-10 | 2013-12-10 | South Ayrshire | 20111 | -215.05 | 0 | 0 | 0 | 0 | 0 | -215.05 | 0 | 19895.95 | 280.8 | [6 empty] | CM_WWI | 40% | CS11A | 60%
402449 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-12-05 | 2012-06-27 | 2012-08-27 | 2012-12-20 | 2012-12-20 | Dundee City | 27349.74 | 46.35 | 0 | 0 | 0 | 0 | 0 | 46.35 | 0 | 27396.09 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
402442 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2011-12-07 | 2015-01-09 | 2015-01-26 | 2015-03-13 | 2015-03-13 | Angus | 191645 | -16175.5 | 0 | 48.04 | 0 | 0 | 0 | -16127.46 | 0 | 175517.54 | 229318.7788 | [6 empty] | CS11A | 100%
402445 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-12-02 | 2013-07-22 | 2013-10-14 | 2014-06-30 | 2014-06-30 | West Lothian | 522906.49 | 1516.7 | 0 | 0 | 0 | 0 | 0 | 1516.7 | 0 | 524423.19 | 1154.4 | [6 empty] | CM_WWI | 40% | CS11A | 60%
402657 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-05-18 | 2013-07-12 | 2013-07-29 | 2016-11-25 | 2016-11-25 | Dundee City | 106546 | 5170 | -1282.98 | -16369.3 | 0 | 0 | 0 | -12482.28 | 0 | 94063.72 | 405511.2 | [6 empty] | CM_WWI | 40% | CS11A | 60%
402655 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS1 | 2012-04-23 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | Glasgow City | 57171 | 0 | 3829 | 2000 | 2000 | 10000 | 0 | 17829 | 0 | 75000 | 0 | [6 empty] | CS11A | 100%
402447 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-12-05 | 2013-06-20 | 2014-01-27 | 2014-03-28 | 2014-03-28 | East Ayrshire | 207982 | -2322.39 | 0 | 53.04 | 0 | 0 | 0 | -2269.35 | 0 | 205712.65 | 768.6 | [6 empty] | CM_WWI | 40% | CS11A | 60%
403292 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2013-02-20 | 2013-03-20 | 2013-04-25 | 2015-11-02 | 2016-01-05 | Scottish Water Wide | 1956539 | 29488 | 45029.29 | -625.1 | 0 | 0 | 0 | 73892.19 | 0 | 2030431.19 | 21267.0001 | [6 empty] | CM_WWI | 40% | CS11A | 60%
500715 | Q&S4 | Improving drinking water availability and resilience of service | Interruptions to Supply |  |  | Water |  | SWD | Interruptions to Supply | MS7 | 2015-06-30 | 2015-06-30 | 2016-02-01 | 2018-10-31 | 2018-10-31 | Scottish Water Wide | 0 | 365730 | 194009.85 | 138748.36 | 0 | 0 | 0 | 698488.21 | 0 | 698488.21 | 945925.7722 | [6 empty] | CS12 | 100%
403515 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2013-06-26 | 2015-02-16 | 2015-06-02 | 2015-10-07 | 2015-10-07 | Argyll and Bute-North Argyll | 40890 | 150152 | 812.93 | -346 | 0 | 0 | 0 | 150618.93 | 0 | 191508.93 | 0 | [6 empty] | SG1 | 100%
502882 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-07-02 | 2027-09-27 | 2028-01-12 | 2028-08-30 | 2028-11-30 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 21237.996 | 1824.514 | 11100.42 | 11057.39 | 45220.32 | 9954839.66 | 10000059.98 | 148885.7057 | [6 empty] | WG1 | 100%
500826 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS5 | 2015-11-17 | 2016-03-25 | 2016-10-03 | 2017-06-01 | 2018-03-01 | Highland | 0 | 5471.98 | 15794.66 | 25561.6403 | 4438.093 | 1000.01 | 0 | 52266.3833 | 0 | 52266.3833 | 55786.1496 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 26.72
034831 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-12-15 | 2010-11-05 | 2011-01-06 | 2012-03-23 | 2012-03-23 | Aberdeenshire | 4773284 | 448.31 | 0 | 0 | 0 | 0 | 0 | 448.31 | 0 | 4773732.31 | 29376.5263 | [6 empty] | WSNI | 20.96% | WR1 | 79.04%
501619 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS6 | 2016-03-25 | 2016-06-01 | 2016-06-01 | 2016-12-12 | 2020-10-14 | Aberdeenshire | 0 | 2323.88 | 63676.12 | 0 | 2520 | 0 | 0 | 68520 | 0 | 68520 | 403717.0829 | [6 empty] | DW25P | 100%
503479 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2021-04-01 | 2022-01-17 | 2022-03-24 | 2022-08-10 | 2022-11-10 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 1202.28 | 1197.62 | 2399.9 | 47599.97 | 49999.87 | 0 | [6 empty] | CM_WSI | 100%
403952 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-10-06 | 2014-10-06 | 2014-11-03 | 2015-02-05 |  | Aberdeenshire | 145523 | 9620 | 0.04 | -599.35 | 0 | 0 | 0 | 9020.69 | 0 | 154543.69 | 0 | [6 empty] | CM_WSI | 100%
503123 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | GW1 | 2019-06-28 | 2019-07-22 | 2019-07-29 | 2019-07-29 | 2019-07-29 | Aberdeenshire | 0 | 0 | 0 | 2989.195 | 58205.725 | 0 | 0 | 61194.92 | 0 | 61194.92 | 0 | [6 empty] | WG5 | 100%
502330 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2016-09-29 | 2016-09-29 | 2017-08-01 | 2019-06-07 | 2019-06-10 | Aberdeen City | 0 | 0 | 0 | 0 | 74.165 | 0 | 0 | 74.165 | 0 | 74.165 | 127997.3498 | [6 empty] | DW25P | 100%
502166 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS6 | 2016-11-16 | 2017-09-29 | 2017-10-16 | 2018-09-21 | 2018-09-21 | Aberdeenshire | 0 | 0 | 40126.31 | 1077618.96 | 149677.34 | 2951.94 | 2048.06 | 1272422.61 | 0 | 1272422.61 | 127997.3498 | [6 empty] | DW25P | 100%
502756 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS0 | 2019-01-22 | 2020-03-30 | 2020-07-22 | 2021-04-23 | 2021-07-26 | Aberdeenshire | 0 | 0 | 0 | 177570.905 | 489468.175 | 2804692.6 | 16485258.98 | 19956990.66 | 904081.83 | 20861072.49 | 8672729.8187 | [6 empty] | DW25P | 100%
502480 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS5 | 2017-02-23 | 2017-02-23 | 2017-04-12 | 2019-02-19 | 2019-02-19 | Aberdeenshire | 0 | 0 | 300779.3 | 1217634.86 | 565517.41 | 8156.62 | 776.44 | 2092864.63 | 646.55 | 2093511.18 | 0 | [6 empty] | CM_WSNI | 100%
401872 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-12-23 | 2012-09-27 | 2012-10-17 | 2014-08-29 |  | Aberdeenshire | 77235 | 3848 | -214.01 | 0 | 0 | 0 | 0 | 3633.99 | 0 | 80868.99 | 0 | [6 empty] | CM_WSI | 100%
501243 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS0 | 2019-02-08 | 2020-03-30 | 2020-07-30 | 2021-04-23 | 2021-07-26 | Aberdeenshire | 0 | 158593.32 | 27727.57 | 268382.763 | 444017.607 | 3381275.68 | 6722689.0786 | 11002686.0186 | 14192513.6814 | 25195199.7 | 6766288.1787 | [6 empty] | DW23 | 100%
500140 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS3 | 2015-03-27 | 2016-07-21 | 2016-08-11 | 2019-09-19 | 2019-12-05 | Inverclyde | 0 | 49028 | 451618 | 215673.38 | 215043.9 | 189430.93 | 18342.23 | 1139136.44 | 0 | 1139136.44 | 482084.4375 | [6 empty] | EC01G | 2.1% | EC01D | 19.34% | CS11 | 21.15% | CS16D | 57.41%
500827 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS5 | 2015-10-28 | 2017-03-23 | 2017-06-02 | 2017-12-01 | 2018-06-01 | Highland | 0 | 3000 | -689.01 | 10352.03 | 11494.28 | 1562.93 | 466.76 | 26186.99 | 0 | 26186.99 | 21049.5599 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 3.36
045811 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2011-12-05 | 2012-02-13 | 2012-08-01 | 2012-08-21 | Perth and Kinross | 171036.3 | 14.5 | 0 | 0 | 0 | 0 | 0 | 14.5 | 0 | 171050.8 | 0 | [6 empty] | WQ01C | 100%
502314 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-10-31 | 2017-05-31 | 2017-07-27 | 2018-06-29 | 2018-06-29 | All East Unitary Authorities | 0 | 0 | 4602.93 | 96498 | 36524.583 | 0 | 0 | 137625.513 | 0 | 137625.513 | 0 | [6 empty] | CM_WWI | 100%
400720 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-04-14 | 2012-01-23 | 2012-06-04 | 2014-12-04 | 2014-12-04 | Angus | 734267 | -15237.57 | 5654.79 | 8071.206 | 1342.72 | 0 | 0 | -168.854 | 0 | 734098.146 | 0 | [6 empty] | SG1 | 100%
402607 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-28 | 2013-01-22 | 2013-04-08 | 2013-09-05 |  | All East Unitary Authorities | 110195.31 | -1083.36 | 0 | 0 | 0 | 0 | 0 | -1083.36 | 0 | 109111.95 | 0 | [6 empty] | CM_M&G | 100%
400060 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-11-11 | 2012-02-06 | 2012-04-24 | 2013-03-28 |  | Fife | 651072.18 | 46529.52 | -3.81 | 0 | 0 | 0 | 0 | 46525.71 | 0 | 697597.89 | 0 | [6 empty] | CM_WWNI | 100%
502879 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-07-01 | 2022-11-24 | 2023-03-20 | 2024-03-08 | 2024-06-10 | Highland | 0 | 0 | 0 | 21341.971 | 1526.479 | 12068.88 | 12022.1 | 46959.43 | 3040.61 | 50000.04 | 148885.7057 | [6 empty] | WG1 | 100%
500218 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS0 | 2015-03-23 | 2019-09-30 | 2019-11-20 | 2021-03-01 | 2022-03-01 | Highland | 0 | 10902 | -2352.37 | 47394.09 | 53357.84 | 1149297.36 | 827356.42 | 2085955.34 | 1036789.23 | 3122744.57 | 1792093.3336 | [6 empty] | CM_WSI | 3% | DW5MR | 17% | DW5FS | 21% | DW5 | 59% | bar: Regulatory Outputs OMG-02
402060 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2011-06-07 | 2011-12-23 | 2011-12-23 | 2013-10-01 |  | Highland | 86314 | -20403.72 | 0 | 0 | 0 | 0 | 0 | -20403.72 | 0 | 65910.28 | 0 | [6 empty] | WG5 | 100%
500150 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS3 | 2015-03-27 | 2017-02-28 | 2017-03-21 | 2019-06-07 | 2019-09-06 | Highland | 0 | 36582 | 113398 | 350757.87 | 185040.98 | 64218.15 | 0 | 749997 | 0 | 749997 | 278002.7669 | [6 empty] | CS16D | 100%
501623 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-08-23 | 2021-07-05 | 2021-09-27 | 2022-03-22 | 2022-06-22 | Highland | 0 | 0 | 5868.58 | 7634.71 | 8.8375 | 0 | 0 | 13512.1275 | 0 | 13512.1275 | 0 | [6 empty] | CM_WSI | 100%
500828 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-07-25 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Highland | 0 | 5225.07 | 2774.93 | 0 | -147.16 | 0 | 0 | 7852.84 | 0 | 7852.84 | 239968.2576 | [6 empty] | DW5FS | 100%
503167 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS0 | 2015-03-31 | 2019-10-14 | 2019-11-15 | 2020-06-18 | 2020-09-18 | Highland | 0 | 0 | 0 | 0 | 20031.71 | 0 | 0 | 20031.71 | 0 | 20031.71 | 572734.7057 | [6 empty] | DW5FS | 100%
403559 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2013-08-27 | 2014-09-18 | 2014-10-07 | 2015-09-09 | 2015-09-09 | Highland | 216238 | 18838.91 | 0 | 0 | 0 | 0 | 0 | 18838.91 | 0 | 235076.91 | 0 | [6 empty] | WG5 | 100%
503247 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-04-06 | 2022-03-14 | 2022-05-16 | 2023-02-17 | 2023-05-22 | Highland | 0 | 0 | 0 | 0 | 54669.365 | 2311.14 | 2302.18 | 59282.685 | 952026.85 | 1011309.535 | 0 | [6 empty] | CM_WSI | 100%
500735 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2015-08-26 | 2018-03-01 | 2018-03-19 | 2019-08-01 | 2019-10-01 | Highland | 0 | 125135 | 127146.1 | 852359.4645 | 2195642.0655 | 252784.89 | 19257.67 | 3572325.19 | 6893.8 | 3579218.99 | 466391.8995 |  |  |  |  | 35919.9996 |  | DW25T | 100% | bar: Regulatory Outputs OMG-05
502784 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-05-28 | 2022-10-28 | 2023-02-15 | 2024-02-06 | 2024-05-08 | Highland | 0 | 0 | 0 | 30753.5185 | 18434.534 | 0 | 0 | 49188.0525 | 1150811.94 | 1199999.9925 | 0 | [6 empty] | CM_WSNI | 100%
502632 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2019-10-31 | 2021-01-18 | 2021-05-10 | 2022-02-22 | 2022-05-25 | Highland | 0 | 0 | 0 | 19096.2 | 46860.766 | 167071.82 | 520884.58 | 753913.366 | 1252043.61 | 2005956.976 | 0 | [6 empty] | CM_WSNI | 100%
401919 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2011-05-11 | 2013-06-26 | 2013-06-26 | 2014-06-24 |  | Stirling | 259474.94 | 97.06 | 0 | 0 | 0 | 0 | 0 | 97.06 | 0 | 259572 | 0 | [6 empty] | CM_WWNI | 100%
045010 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-11-24 | 2015-08-21 | 2015-02-06 | 2015-02-06 | 2015-02-06 | Aberdeenshire | 841736.06 | 472.83 | 0 | 0 | 0 | 0 | 0 | 472.83 | 0 | 842208.89 | 0 | [6 empty] | EC01A | 100%
545010 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS1 | 2008-11-24 | 2016-09-28 | 2016-11-04 | 2017-11-20 | 2018-02-16 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310409.7001 | [6 empty] | EC01A | 5% | CM_WWNI | 95%
501174 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-06-23 | 2018-03-20 | 2018-03-20 | 2017-05-25 | 2017-05-25 | Aberdeenshire | 0 | 0 | 29755.88 | -7554.89 | 0 | 0 | 0 | 22200.99 | 0 | 22200.99 | 0 | [6 empty] | CM_WWNI | 100%
030394 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-05 | 2015-08-21 | 2015-02-06 | 2015-02-06 | 2015-02-06 | Aberdeenshire | 2014773.91 | -8704.1 | 0 | 0 | 0 | 0 | 0 | -8704.1 | 0 | 2006069.81 | 0 | [6 empty] | EC01A | 100%
403935 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | NONINF | Non OMG180 | MS3 | 2009-06-05 | 2017-02-23 | 2017-04-03 | 2019-09-25 | 2019-12-10 | Aberdeenshire | 147386 | 746158 | 1651782.48 | 8299679.17 | 9718823.12 | 1247811.87 | 32963.41 | 21697218.05 | 25395.93 | 21869999.98 | 2191117.25 | [6 empty] | SG1 | 19% | CM_WWNI | 35% | EC01A | 46%
530394 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS1 | 2009-06-05 | 2016-09-28 | 2016-11-04 | 2017-11-20 | 2018-02-16 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5663.96 | [6 empty] | EC01A | 3% | EC04A | 34% | CM_WWNI | 63%
502424 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | GW1 | 2019-08-02 | 2021-04-12 | 2021-08-16 | 2022-11-02 | 2023-02-01 | Aberdeenshire | 0 | 0 | 39204.71 | 6913.687 | 11423.736 | 35788.54 | 0 | 93330.673 | 0 | 93330.673 | 587726.5342 | [6 empty] | WG5 | 100%
502323 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MSU | 2019-07-10 | 2019-07-11 | 2019-07-11 | 2019-07-11 | 2019-07-11 | Aberdeenshire | 0 | 0 | 85448.37 | -31.5 | 2314.58 | 0 | 0 | 87731.45 | 0 | 87731.45 | 587726.5342 | [6 empty] | WG5 | 100%
503504 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MSU | 2021-04-01 | 2022-01-17 | 2022-03-25 | 2022-08-09 | 2022-11-09 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 4809.36 | 4790.71 | 9600.07 | 190399.99 | 200000.06 | 0 | [6 empty] | CM_M&G | 100%
402648 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | General |  | SWD | Water Non infrastructure | MS7 | 2012-03-29 | 2012-03-29 | 2012-04-02 | 2016-10-26 |  | Scottish Water Wide | 230600.53 | 100000.47 | -46213.31 | 0 | 0 | 0 | 0 | 53787.16 | 0 | 284387.69 | 0 | [6 empty] | WSI | 4.826% | WWNI | 4.826% | WWI | 45.17% | WSNI | 45.17%
503076 | Q&S4 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWD | Revised Bathing Waters Directive | MSU | 2020-08-18 | 2021-03-08 | 2021-03-25 | 2022-05-01 | 2022-08-01 | Highland | 0 | 0 | 0 | 0 | 0 | 10662.9 | 134266.17 | 144929.07 | 249070.8 | 393999.87 | 77778.7837 | [6 empty] | EC16 | 100% | bar: Regulatory Outputs OMG-21
503084 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MSU | 2020-06-29 | 2021-12-27 | 2022-04-19 | 2023-04-14 | 2023-07-17 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 158222.57 | 158222.57 | 1115777.4 | 1273999.97 | 648914.6661 | [6 empty] | EC10E | 100%
503094 | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater |  | SWD | Sludge | MS0 | 2018-10-30 | 2019-05-13 | 2019-05-13 | 2020-04-01 | 2020-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 8431.2 | 271610.45 | 91644.67 | 371686.32 | 0 | 371686.32 | 424596.6775 | [6 empty] | LA01_S | 100% | bar: Regulatory Outputs OMG-23
503136 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MSU | 2021-06-15 | 2022-10-24 | 2023-02-15 | 2023-10-03 | 2024-01-03 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 41186.49 | 54561.48 | 95747.97 | 262251.92 | 357999.89 | 101384.4204 | [6 empty] | EC23B_ID | 100%
503137 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MSU | 2021-05-14 | 2022-10-20 | 2023-02-15 | 2023-10-03 | 2024-01-03 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 99012.45 | 131165.99 | 230178.44 | 533821.53 | 763999.97 | 216286.7634 | [6 empty] | EC10A_ID | 100%
503140 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | GW0 | 2022-08-25 | 2022-09-22 | 2022-09-22 | 2023-09-27 | 2023-09-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 86500 | 29607.89 | 33107.63 | 149215.52 | 2478784.51 | 2628000.03 | 226165.695 | [6 empty] | CS29_ID | 100%
503124 | Q&S4 | Improving the customer experience | Customer Experience Studies |  |  | Wastewater |  | SWMD | Customer Experience Studies | MS3 | 2018-09-28 | 2019-03-25 | 2019-03-27 | 2019-05-01 | 2019-06-01 | Glasgow City | 0 | 0 | 0 | 0 | 134124.04 | 41949.36 | 0 | 176073.4 | 0 | 176073.4 | 218925.155 | [6 empty] | CS16SR | 100% | bar: Regulatory Outputs OMG-23
503077 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS0 | 2018-10-31 | 2019-09-30 | 2019-11-04 | 2021-04-15 | 2021-07-16 | Scottish Water Wide | 0 | 0 | 0 | 0 | 15583 | 382312 | 560856.29 | 958751.29 | 62248.7 | 1020999.99 | 1167664.6555 | [6 empty] | WQ01_S | 100%
503083 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS0 | 2018-07-13 | 2019-06-17 | 2019-07-08 | 2021-02-01 | 2021-05-01 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 72831.78 | 401517.29 | 537843.13 | 1012192.2 | 86807.77 | 1098999.97 | 1261174.7576 | [6 empty] | EC01D | 50% | EC10E | 50% | bar: Regulatory Outputs OMG-23
503400 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2019-03-27 | 2019-08-05 | 2019-10-01 | 2020-05-01 | 2020-05-15 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 9600 | 157594.48 | 31846.96 | 199041.44 | 918.87 | 199960.31 | 229602.606 | [6 empty] | DW5FS | 100%
503126 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2018-12-20 | 2020-01-20 | 2020-04-30 | 2021-02-01 | 2021-05-01 | Orkney Islands | 0 | 0 | 0 | 0 | 55998.21 | 202453.13 | 214869.69 | 473321.03 | 50205.71 | 523526.74 | 690449.0167 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
503139 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS0 | 2018-11-21 | 2020-11-30 | 2021-03-23 | 2022-06-14 | 2022-09-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 5050.47 | 116676.41 | 320791.8 | 442518.68 | 560481.28 | 1002999.96 | 1138090.3987 | [6 empty] | CS29 | 100%
503178 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2019-07-01 | 2020-06-01 | 2020-08-25 | 2021-03-29 | 2021-06-29 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 48554.01 | 256660.1 | 305214.11 | 102785.88 | 407999.99 | 471692.0681 | [6 empty] | CS15 | 100%
503177 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS0 | 2019-03-05 | 2020-04-06 | 2020-06-19 | 2020-12-09 | 2021-03-25 | Glasgow City | 0 | 0 | 0 | 0 | 12571.94 | 137906.01 | 758681 | 909158.95 | 43812.99 | 952971.94 | 723084.3172 | [6 empty] | CS15 | 100%
503334 | Q&S4 | Improving drinking water availability and resilience of service | Pressure |  |  | Water |  | SWD | Pressure | MSU | 2021-01-05 | 2021-09-13 | 2022-01-04 | 2023-11-27 | 2024-02-26 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 45076.04 | 139764.8 | 184840.84 | 3261159.23 | 3446000.07 | 130909.1547 | [6 empty] | CS1 | 100%
503176 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2021-04-07 | 2021-05-31 | 2021-06-09 | 2021-07-21 | 2021-07-22 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 2184000.01 | 2184000 | 4368000.01 | 0 | 4368000.01 | 4374420.2613 | [6 empty] | CS11A | 100%
503179 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MSU | 2021-07-07 | 2023-01-03 | 2023-03-01 | 2023-05-23 | 2024-05-21 | Aberdeen City | 0 | 0 | 0 | 0 | 7000 | 0 | 0 | 7000 | 968999.94 | 975999.94 | 982409.8021 | [6 empty] | CS16D_ID | 100%
503184 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MSU | 2021-07-07 | 2023-01-03 | 2023-03-01 | 2023-05-23 | 2024-05-21 | City of Edinburgh | 0 | 0 | 0 | 0 | 7000 | 0 | 0 | 7000 | 555000.07 | 562000.07 | 556787.4794 | [6 empty] | CS16D_ID | 100%
503182 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MSU | 2021-07-07 | 2023-01-03 | 2023-03-02 | 2023-05-24 | 2024-05-22 | Falkirk | 0 | 0 | 0 | 0 | 7000 | 0 | 0 | 7000 | 555000.01 | 562000.01 | 556787.4794 | [6 empty] | CS16D_ID | 100%
503181 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MSU | 2020-09-04 | 2021-03-22 | 2021-05-17 | 2021-08-12 | 2021-11-12 | North Ayrshire | 0 | 0 | 0 | 0 | 7076.05 | 20918.88 | 50339.88 | 78334.81 | 483741.15 | 562075.96 | 556787.4794 | [6 empty] | CS16D_ID | 100%
503183 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MSU | 2021-07-07 | 2023-01-03 | 2023-03-01 | 2023-05-23 | 2024-05-21 | Scottish Water Wide | 0 | 0 | 0 | 0 | 26168.22 | 0 | 0 | 26168.22 | 1861999.98 | 1888168.2 | 423455.1712 | [6 empty] | CS16D_ID | 100%
503180 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MSU | 2020-09-04 | 2022-03-09 | 2022-05-05 | 2022-07-27 | 2023-07-26 | Dundee City | 0 | 0 | 0 | 0 | 7076.05 | 0 | 16693.37 | 23769.42 | 538306.67 | 562076.09 | 556787.4794 | [6 empty] | CS16D_ID | 100%
503249 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2018-06-05 | 2019-07-22 | 2019-08-08 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 4396.71 | 91684.31 | 39117.34 | 135198.36 | 1801.68 | 137000.04 | 157718.0651 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-47
503332 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | GW0 | 2020-01-08 | 2021-05-10 | 2021-10-07 | 2022-09-21 | 2022-12-22 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 69454.64 | 300520.33 | 369974.97 | 930025.06 | 1300000.03 | 2580742.7412 | [6 empty] | DW23 | 100%
503185 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS0 | 2019-02-21 | 2019-07-15 | 2019-07-16 | 2020-07-09 | 2020-09-28 | Aberdeen City | 0 | 0 | 0 | 0 | 1478.77 | 72380.61 | 35619.37 | 109478.75 | 0 | 109478.75 | 109331.8966 | [6 empty] | CS27 | 100%
503187 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS0 | 2019-02-21 | 2019-07-15 | 2019-07-16 | 2020-07-09 | 2020-09-28 | City of Edinburgh | 0 | 0 | 0 | 0 | 1478.77 | 72380.61 | 35619.37 | 109478.75 | 0 | 109478.75 | 109331.8966 | [6 empty] | CS27 | 100%
503188 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS0 | 2019-02-21 | 2019-07-15 | 2019-07-16 | 2020-07-09 | 2020-09-28 | Falkirk | 0 | 0 | 0 | 0 | 1478.77 | 69893.3 | 38106.69 | 109478.76 | 0 | 109478.76 | 109331.8966 | [6 empty] | CS27 | 100%
503189 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS0 | 2019-02-21 | 2019-07-15 | 2019-07-16 | 2020-07-09 | 2020-09-28 | North Ayrshire | 0 | 0 | 0 | 0 | 1478.77 | 72380.61 | 35619.37 | 109478.75 | 0 | 109478.75 | 109331.8966 | [6 empty] | CS27 | 100%
503190 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS0 | 2019-02-21 | 2019-07-15 | 2019-07-16 | 2020-07-09 | 2020-09-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 2721.5 | 138066.98 | 67933.03 | 208721.51 | 0 | 208721.51 | 86768.2065 | [6 empty] | CS27 | 100%
503186 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS0 | 2019-02-21 | 2019-07-15 | 2019-07-16 | 2020-07-09 | 2020-09-28 | Dundee City | 0 | 0 | 0 | 0 | 2744.29 | 72380.61 | 35619.37 | 110744.27 | 0 | 110744.27 | 109331.8966 | [6 empty] | CS27 | 100%
503191 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWD | Flood Risk Management Act | MSU | 2019-07-01 | 2020-06-15 | 2020-08-27 | 2021-09-27 | 2021-12-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 136570.35 | 980096.65 | 1116667 | 1024332.98 | 2140999.98 | 2177893.8057 | [6 empty] | CS16D_ID | 100%
503246 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS0 | 2018-07-30 | 2020-08-10 | 2020-10-26 | 2021-11-24 | 2022-02-24 | Scottish Water Wide | 0 | 0 | 0 | 0 | 58372.9 | 226463.74 | 1804616.18 | 2089452.82 | 163547.14 | 2252999.96 | 824786.8734 | [6 empty] | EC01M | 100%
503237 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2018-06-21 | 2019-05-13 | 2019-08-27 | 2020-10-01 | 2021-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 16302.93 | 412009.75 | 357467.23 | 785779.91 | 0 | 785779.91 | 499666.5948 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
503248 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS2 | 2018-06-05 | 2019-01-08 | 2019-04-30 | 2020-09-04 | 2020-11-09 | Scottish Water Wide | 0 | 0 | 0 | 0 | 24347.35 | 89960.16 | 61856.13 | 176163.64 | 3836.35 | 179999.99 | 205816.0775 | [6 empty] | DW25PS | 100%
503129 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MSU | 2020-04-28 | 2021-08-06 | 2021-11-29 | 2022-07-18 | 2022-10-18 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 39627.7 | 39627.7 | 318372.32 | 358000.02 | 188201.9131 | [6 empty] | EC23A | 100%
502648 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS0 | 2018-03-30 | 2020-01-20 | 2020-04-27 | 2021-09-01 | 2022-12-01 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 45494.62 | 116467.18 | 862391.87 | 806940.05 | 1831293.72 | 2851375.89 | 4682669.61 | 3238148.7543 | [6 empty] | DW2 | 100% | bar: Regulatory Outputs OMG-01
502652 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2018-06-30 | 2020-06-01 | 2020-07-27 | 2020-12-01 | 2021-03-01 | Na H-Eileanan an Iar | 0 | 0 | 0 | 7268.99 | 4177.09 | 403.11 | 301199.32 | 313048.51 | 101156.07 | 414204.58 | 482108.5251 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
502386 | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWD | WFD | GW2 | 2019-05-01 | 2019-05-13 | 2019-05-13 | 2019-05-13 | 2019-05-13 | Dumfries and Galloway | 0 | 0 | 17700 | 20300 | -8718.2 | 0 | 0 | 29281.8 | 0 | 29281.8 | 26321.4575 | [6 empty] | WR2A | 100%
502411 | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Wastewater |  | SWMD | WFD | MS0 | 2018-07-25 | 2020-01-20 | 2020-03-19 | 2020-11-25 | 2021-03-01 | Scottish Borders | 0 | 0 | 20900 | 24841.9 | 27530.2 | 127470.42 | 203297.04 | 404039.56 | 42738.93 | 446778.49 | 452635.7077 | [6 empty] | WR2A_ID | 100%
502381 | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWD | WFD | GW2 | 2019-05-01 | 2019-05-01 | 2019-05-01 | 2019-05-01 | 2019-05-14 | South Ayrshire | 0 | 0 | 7900 | 3721.81 | 0 | 0 | 0 | 11621.81 | 0 | 11621.81 | 131455.2678 | [6 empty] | WR1 | 100%
502382 | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWD | WFD | MS0 | 2019-01-31 | 2020-02-03 | 2020-06-04 | 2020-10-01 | 2021-01-01 | Scottish Borders | 0 | 0 | 7900 | 1888.82 | 7025.81 | 42510.14 | 149975.7 | 209300.47 | 2514.1 | 211814.57 | 384178.8011 | [6 empty] | WR1 | 100% | bar: Regulatory Outputs OMG-20
502220 | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Wastewater |  | WWINF | WFD | MS0 | 2017-11-30 | 2020-11-02 | 2021-03-22 | 2021-12-01 | 2022-03-01 | Midlothian | 0 | 0 | 82593.19 | 46293.4 | 222374.46 | 124508.55 | 417722.09 | 893491.69 | 729244.1 | 1622735.79 | 595187.4249 | [6 empty] | EC10A | 100% | bar: Regulatory Outputs OMG-20
502383 | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWD | WFD | MS0 | 2019-03-11 | 2020-07-06 | 2020-11-05 | 2021-06-01 | 2021-09-01 | Fife | 0 | 0 | 10779 | 2862.6 | 11358.4 | 28239.41 | 86990.15 | 140229.56 | 66770.53 | 207000.09 | 722884.0757 | [6 empty] | WR1 | 100% | bar: Regulatory Outputs OMG-20
502380 | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWD | WFD | MS3 | 2019-02-26 | 2019-03-25 | 2019-03-25 | 2020-05-01 | 2020-08-01 | Perth and Kinross | 0 | 0 | 4000 | 2450.25 | 4436.13 | 35596.19 | 14225.77 | 60708.34 | 0 | 60708.34 | 212763.5692 | [6 empty] | WR1 | 100% | bar: Regulatory Outputs OMG-20
502384 | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWD | WFD | GW2 | 2019-05-01 | 2019-05-01 | 2019-05-01 | 2019-05-01 | 2019-05-01 | Dumfries and Galloway | 0 | 0 | 2274 | 17726 | 0 | 0 | 0 | 20000 | 0 | 20000 | 26321.4575 | [6 empty] | WR2A | 100%
502385 | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWMD | WFD | MS0 | 2018-09-28 | 2020-01-06 | 2020-03-10 | 2020-06-01 | 2020-09-01 | Stirling | 0 | 0 | 7950 | 1143.4 | 5673.589 | 36869.77 | 84343.2 | 135979.959 | 1191.45 | 137171.409 | 156513.2474 | [6 empty] | WR2A | 100% | bar: Regulatory Outputs OMG-20
502213 | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Wastewater |  | SWD | WFD | MS5 | 2017-11-14 | 2019-05-08 | 2019-05-08 | 2019-03-05 | 2019-03-05 | North Lanarkshire | 0 | 0 | 128544.83 | 56371.51 | 14822.4335 | 0 | 0 | 199738.7735 | 0 | 199738.7735 | 213091.9432 | [6 empty] | EC10A | 100%
503491 | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Wastewater |  | SWD | WFD | MS0 | 2017-11-14 | 2022-04-01 | 2022-08-04 | 2023-11-01 | 2024-03-01 | North Lanarkshire | 0 | 0 | 0 | 0 | 45048.56 | 55364.08 | 159485.02 | 259897.66 | 2027150.89 | 2287048.55 | 213091.9432 | [6 empty] | EC10A | 100% | bar: Regulatory Outputs OMG-20
502212 | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Wastewater |  | SWD | WFD | MS0 | 2017-11-30 | 2020-12-14 | 2021-06-04 | 2022-01-01 | 2022-04-01 | City of Edinburgh | 0 | 0 | 65632.35 | 33482.65 | 78708.52 | 73235.58 | 554151.7 | 805210.8 | 2021566.93 | 2826777.73 | 1044866.0795 | [6 empty] | EC10A | 100% | bar: Regulatory Outputs OMG-20
502650 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS1 | 2017-09-15 | 2019-09-02 | 2019-10-14 | 2021-03-01 | 2022-06-01 | Argyll and Bute-North Argyll | 0 | 0 | 27062.79 | 136518.6 | 507784.07 | 626070.6 | 3427232.89 | 4724668.95 | 603763.08 | 5328432.03 | 3439749.1261 | [6 empty] | DW2 | 100% | bar: Regulatory Outputs OMG-01
502326 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater |  | SWD | Compliance Assessment Scheme | GW2 | 2019-05-08 | 2019-05-08 | 2019-05-08 | 2019-05-08 | 2019-05-08 | Scottish Water Wide | 0 | 0 | 140980.02 | 63551.84 | -56151.8438 | 0 | 0 | 148380.0162 | 0 | 148380.0162 | 710679.5962 | [6 empty] | WQ01D | 35% | WQ01E | 65%
502944 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater |  | SWMD | Compliance Assessment Scheme | MS0 | 2018-03-27 | 2020-02-24 | 2020-05-26 | 2020-11-30 | 2021-02-26 | Scottish Water Wide | 0 | 0 | 0 | 2604.35 | 72751.05 | 119190.32 | 316889.61 | 511435.33 | 57526.07 | 568961.4 | 401877.9581 | [6 empty] | WQ01E | 100%
502945 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater |  | SWMD | Compliance Assessment Scheme | MS0 | 2018-03-27 | 2020-02-24 | 2020-05-29 | 2020-11-30 | 2021-02-26 | Scottish Water Wide | 0 | 0 | 0 | 3596.88 | 76342.3 | 227084.59 | 378270.89 | 685294.66 | 100146.79 | 785441.45 | 401877.9581 | [6 empty] | WQ01E | 100%
502946 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater |  | SWMD | Compliance Assessment Scheme | MS0 | 2018-03-27 | 2020-02-24 | 2020-06-30 | 2020-12-24 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 3781.74 | 75752.48 | 194603.19 | 438996.24 | 713133.65 | 115971.43 | 829105.08 | 308801.6381 | [6 empty] | WQ01D | 100%
502947 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater |  | SWMD | Compliance Assessment Scheme | MS0 | 2018-03-22 | 2020-02-24 | 2020-06-30 | 2020-12-21 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 1330.51 | 37838.4 | 64155.44 | 152294.1 | 255618.45 | 34922.54 | 290540.99 | 308801.6381 | [6 empty] | WQ01D | 100%
502943 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater |  | SWMD | Compliance Assessment Scheme | MS0 | 2018-02-23 | 2020-02-24 | 2020-06-30 | 2020-12-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 764.42 | 71108.7 | 104709.18 | 3079.45 | 179661.75 | 773.64 | 180435.39 | 710679.5962 | [6 empty] | WQ01D | 15% | WQ01E | 85%
503118 | Q&S4 | Improving the customer experience | IT Security and Communications |  |  | General |  | SWD | IT Security and Communications | MS3 | 2018-08-23 | 2019-02-27 | 2019-02-27 | 2021-01-29 | 2021-02-05 | Scottish Water Wide | 0 | 0 | 0 | 0 | 154907.52 | 236441.25 | 208475.54 | 599824.31 | 0 | 599824.31 | 2066733.5196 | [6 empty] | CS24S | 50% | CS24W | 50%
503434 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS0 | 2015-10-30 | 2019-08-19 | 2019-08-30 | 2020-10-01 | 2021-01-01 | South Lanarkshire | 0 | 0 | 0 | 0 | 17126 | 140951.16 | 927452.94 | 1085530.1 | 10028.04 | 1095558.14 | 641974.3455 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
503243 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS3 | 2018-06-05 | 2019-03-12 | 2019-03-18 | 2020-04-01 | 2020-04-01 | South Lanarkshire | 0 | 0 | 0 | 0 | 25836.58 | 138075.03 | 6062.79 | 169974.4 | 0 | 169974.4 | 212743.2589 | [6 empty] | DW25PS | 100% | bar: Regulatory Outputs OMG-47
503430 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MSU | 2019-07-09 | 2019-08-05 | 2019-08-05 | 2022-04-29 | 2022-07-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 21286.05 | 536158.24 | 616382.73 | 1173827.02 | 860172.95 | 2033999.97 | 1144895.8677 | [6 empty] | DW25P | 100%
503437 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MSU | 2020-05-08 | 2022-07-29 | 2022-12-01 | 2023-09-01 | 2023-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 22596.28 | 28406.04 | 104394.85 | 155397.17 | 2003602.96 | 2159000.13 | 38372.3358 | [6 empty] | DW25PS | 47% | DW25TS | 53%
503175 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2021-04-07 | 2021-05-31 | 2021-06-09 | 2021-07-21 | 2021-07-22 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 555000 | 555000 | 1110000 | 0 | 1110000 | 1135197.7992 | [6 empty] | CS15E | 100%
503252 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS0 | 2018-06-15 | 2019-04-29 | 2019-05-13 | 2023-06-30 | 2023-09-29 | Scottish Water Wide | 0 | 0 | 0 | 0 | 15709.22 | 217984.78 | 195667.91 | 429361.91 | 327458.59 | 756820.5 | 176799.1374 | [6 empty] | DW25PS | 100%
503103 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | WINF | Supply Resilience | MS0 | 2018-06-26 | 2019-12-16 | 2020-03-02 | 2021-08-10 | 2022-08-10 | Highland | 0 | 0 | 0 | 0 | 470529.39 | 6217471.69 | 16995864.3 | 23683865.38 | 835134.6 | 24518999.98 | 5368103.1432 | [6 empty] | CS16WR | 20% | WG4 | 20% | WG1 | 60%
502905 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWD | UWWTD - Works | GW0 | 2020-06-05 | 2021-11-15 | 2022-03-08 | 2023-02-24 | 2023-05-29 | Scottish Borders | 0 | 0 | 0 | 29815.2285 | 12454.6215 | 15956.19 | 149342.41 | 207568.45 | 1988206.45 | 2195774.9 | 46369.8879 | [6 empty] | EC01A | 100%
503505 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | GW0 | 2019-07-15 | 2020-07-06 | 2020-10-08 | 2021-04-27 | 2021-07-28 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 11252.09 | 111266.9 | 322079.2 | 444598.19 | 126653.92 | 571252.11 | 360479.438 | [6 empty] | DW1A | 100%
503121 | Q&S4 | Improving the customer experience | IT Security and Communications |  |  | General |  | SWD | IT Security and Communications | MS0 | 2018-11-21 | 2019-08-05 | 2019-08-05 | 2020-01-27 | 2020-01-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 551169.33 | 4941059.01 | 0 | 5492228.34 | 0 | 5492228.34 | 2066733.5196 | [6 empty] | CS24S | 50% | CS24W | 50%
503128 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MSU | 2019-07-30 | 2019-05-31 | 2019-05-20 | 2019-10-21 | 2020-01-24 | Scottish Water Wide | 0 | 0 | 0 | 0 | 387264.1135 | 1508872.76 | 0 | 1896136.8735 | 0 | 1896136.8735 | 1913548.416 | [6 empty] | LA01_ID | 100%
503120 | Q&S4 | Improving the customer experience | IT Security and Communications |  |  | General |  | SWD | IT Security and Communications | MS0 | 2018-11-12 | 2019-08-12 | 2019-08-12 | 2020-01-24 | 2020-01-27 | Scottish Water Wide | 0 | 0 | 0 | 0 | 50434.58 | 1149565.42 | 0 | 1200000 | 0 | 1200000 | 2066733.5196 | [6 empty] | CS24S | 50% | CS24W | 50%
503119 | Q&S4 | Improving the customer experience | IT Security and Communications |  |  | General |  | SWD | IT Security and Communications | MS0 | 2018-11-12 | 2020-02-03 | 2020-02-03 | 2021-01-15 | 2021-01-18 | Scottish Water Wide | 0 | 0 | 0 | 0 | 42897.58 | 424408 | 3292683.44 | 3759989.02 | 0 | 3759989.02 | 2066733.5196 | [6 empty] | CS24S | 50% | CS24W | 50%
503204 | Q&S4 | Improving the customer experience | IT Security and Communications |  |  | General |  | SWD | IT Security and Communications | MS3 | 2018-12-12 | 2018-12-12 | 2018-12-12 | 2020-01-15 | 2020-01-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 263401.77 | 736577 | 0 | 999978.77 | 0 | 999978.77 | 2066733.5196 | [6 empty] | CS24S | 50% | CS24W | 50%
503052 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2018-02-02 | 2018-06-26 | 2018-08-01 | 2019-09-24 | 2019-12-27 | Scottish Water Wide | 0 | 0 | 0 | 1643.285 | 20667.1028 | 122410.46 | 845.07 | 145565.9178 | 434.04 | 145999.9578 | 166361.0382 | [6 empty] | DW25PS | 100%
503113 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | GW0 | 2019-09-27 | 2021-08-30 | 2021-11-15 | 2022-06-17 | 2022-09-19 | Scottish Water Wide | 0 | 0 | 0 | 0 | 206449.82 | 86736.71 | 49225.87 | 342412.4 | 349587.55 | 691999.95 | 798892.753 | [6 empty] | CS16WRID | 100%
503114 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | GW0 | 2020-03-31 | 2021-03-29 | 2021-06-15 | 2022-03-22 | 2022-06-22 | Scottish Water Wide | 0 | 0 | 0 | 0 | 214376.96 | 288872.93 | 359214 | 862463.89 | 379536.09 | 1241999.98 | 90190.4753 | [6 empty] | CS16WRID | 100%
503115 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MSU | 2021-03-31 | 2022-03-28 | 2022-06-15 | 2023-07-14 | 2023-10-16 | Scottish Water Wide | 0 | 0 | 0 | 0 | 375169.32 | 260424.72 | 265709.37 | 901303.41 | 1333696.54 | 2234999.95 | 91130.0148 | [6 empty] | CS16WRID | 100%
503116 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MSU | 2021-03-31 | 2022-03-14 | 2022-06-15 | 2023-03-22 | 2023-06-22 | Scottish Water Wide | 0 | 0 | 0 | 0 | 215768.985 | 141162.63 | 146318.24 | 503249.855 | 738750.04 | 1241999.895 | 90190.4753 | [6 empty] | CS16WRID | 100%
503117 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MSU | 2019-08-29 | 2020-07-20 | 2020-10-08 | 2021-05-11 | 2021-08-11 | Scottish Water Wide | 0 | 0 | 0 | 0 | 85195.925 | 178784.59 | 161477.58 | 425458.095 | 52541.92 | 478000.015 | 547617.9136 | [6 empty] | CS16WRID | 100%
503051 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2018-02-27 | 2018-06-05 | 2018-08-06 | 2019-10-01 | 2020-01-01 | Scottish Water Wide | 0 | 0 | 0 | 1476.925 | 64523.075 | 78656.97 | 858.62 | 145515.59 | 484.43 | 146000.02 | 166361.0382 | [6 empty] | DW25PS | 100% | bar: Regulatory Outputs OMG-47
503291 | Q&S4 | Improving the customer experience | IT Security and Communications |  |  | General |  | SWD | IT Security and Communications | MS0 | 2019-02-06 | 2019-07-01 | 2019-07-01 | 2019-10-31 | 2019-11-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 67237.33 | 1682003.64 | 0 | 1749240.97 | 0 | 1749240.97 | 2066733.5196 | [6 empty] | CS24S | 50% | CS24W | 50%
503241 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS2 | 2018-06-21 | 2018-10-31 | 2019-05-17 | 2020-07-20 | 2020-09-22 | Scottish Water Wide | 0 | 0 | 0 | 0 | 134215.511 | 947342.4 | 573442.08 | 1654999.991 | 0 | 1654999.991 | 1892428.6318 | [6 empty] | DW25PS | 100%
503048 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS3 | 2018-02-20 | 2018-09-03 | 2019-02-20 | 2020-03-17 | 2020-06-17 | Scottish Water Wide | 0 | 0 | 0 | 5926.675 | 78568.9525 | 89481.42 | 26012.04 | 199989.0875 | 0 | 199989.0875 | 228894.9036 | [6 empty] | DW25PS | 100%
502767 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS3 | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-01-29 | 2020-04-30 | All West Unitary Authorities | 0 | 0 | 0 | 21508.7765 | 23672.3875 | 217774.44 | 29543.04 | 292498.644 | 0 | 292498.644 | 334349.8466 | [6 empty] | DW25PS | 100%
502768 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS3 | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-01-29 | 2020-04-30 | All North Unitary Authorities | 0 | 0 | 0 | 33370.797 | 28521.2433 | 331619.82 | 44987.19 | 438499.0503 | 0 | 438499.0503 | 334349.8466 | [6 empty] | DW25PS | 100%
502769 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS3 | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-01-29 | 2020-04-30 | All South Unitary Authorities | 0 | 0 | 0 | 31187.4245 | 61469.4123 | 304939.59 | 41367.77 | 438964.1968 | 0 | 438964.1968 | 501524.7699 | [6 empty] | DW25PS | 100%
502770 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS3 | 2017-06-21 | 2018-01-08 | 2018-01-08 | 2020-01-08 | 2020-04-09 | All East Unitary Authorities | 0 | 0 | 0 | 30984.252 | 39677.7928 | 347409.3 | 20198.22 | 438269.5648 | 0 | 438269.5648 | 667312.3291 | [6 empty] | DW25PS | 100%
503110 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2018-03-26 | 2018-10-16 | 2018-10-25 | 2020-12-01 | 2021-02-01 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 30000 | 115443 | 93557 | 239000 | 0 | 239000 | 273597.7725 | [6 empty] | DW25DS | 100% | bar: Regulatory Outputs OMG-47
503236 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS2 | 2018-06-14 | 2018-10-24 | 2019-05-08 | 2019-10-01 | 2020-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 126203.84 | 109979.77 | 1477.02 | 237660.63 | 787.37 | 238448 | 312219.5296 | [6 empty] | DW25PS | 100% | bar: Regulatory Outputs OMG-47
503109 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS3 | 2018-03-26 | 2018-06-26 | 2018-08-09 | 2019-05-01 | 2019-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 29227.36 | 114816.9 | 841.21 | 144885.47 | 114.56 | 145000.03 | 166966.1061 | [6 empty] | DW25PS | 100% | bar: Regulatory Outputs OMG-47
502898 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWD | UWWTD - UID | MSU | 2020-11-27 | 2021-09-01 | 2022-01-18 | 2022-05-20 | 2022-08-22 | Falkirk | 0 | 0 | 0 | 0 | 0 | 90354.08 | 35645.98 | 126000.06 | 0 | 126000.06 | 222066.9736 | [6 empty] | EC01F | 100%
500142 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2015-03-27 | 2016-06-29 | 2016-07-07 | 2019-08-07 | 2019-11-06 | Fife | 0 | 59488.58 | 471786.42 | 188739 | 179929 | 199914.46 | 10827.57 | 1110685.03 | 0 | 1110685.03 | 635959.741 | [6 empty] | EC01G | 0.89% | CS11 | 17.02% | CS16D | 39.26% | EC01D | 42.83%
503215 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-05 | 2023-06-20 | 2023-10-19 | 2024-10-15 | 2025-01-15 | Fife | 0 | 0 | 0 | 0 | 72338.92 | 16782.37 | 34047.32 | 123168.61 | 21321.31 | 144489.92 | 148885.7057 | [6 empty] | SG1 | 100%
402601 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-03-29 | 2012-12-13 | 2013-01-30 | 2015-03-20 |  | All East Unitary Authorities | 841219 | 6572 | -94.89 | 1203.64 | 0 | 0 | 0 | 7680.75 | 0 | 848899.75 | 0 | [6 empty] | CM_WWNI | 100%
501010 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2015-10-07 | 2021-10-01 | 2021-12-01 | 2022-02-01 | 2022-03-31 | Fife | 0 | 28951 | 81470.98 | 616.8 | -5504.25 | 0 | 0 | 105534.53 | 0 | 105534.53 | 0 | [6 empty] | CM_WWNI | 100%
500485 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-28 | 2015-04-28 | 2015-04-28 | 2016-09-27 | 2016-10-31 | Scottish Water Wide | 0 | 9894141.74 | -73613.6 | 0 | 0 | 0 | 0 | 9820528.14 | 0 | 9820528.14 | 0 | [6 empty] | CM_WSI | 100%
502197 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2017-07-29 | 2017-07-31 | Scottish Water Wide | 0 | 0 | 8700000 | 187192.13 | 12509.91 | 0 | 0 | 8899702.04 | 0 | 8899702.04 | 0 | [6 empty] | CM_WSI | 100%
502637 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2017-03-23 | 2017-03-23 | 2017-04-03 | 2018-04-30 | 2018-04-30 | Scottish Water Wide | 0 | 0 | 653551.4 | 8246524.6 | 125925.58 | 0 | 0 | 9026001.58 | 0 | 9026001.58 | 0 | [6 empty] | CM_WSI | 100%
503085 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2018-03-26 | 2018-03-26 | 2018-04-02 | 2019-04-30 | 2019-04-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 9200000 | 790000 | 0 | 9990000 | 0 | 9990000 | 0 | [6 empty] | CM_WSI | 100%
503557 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2019-04-01 | 2019-04-01 | 2019-04-02 | 2020-04-30 | 2020-12-17 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 5340771.6 | 3995228.37 | 9335999.97 | 0 | 9335999.97 | 0 | [6 empty] | CM_WSI | 100%
402101 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWMD | Water infrastructure | MS7 | 2011-12-06 | 2012-07-20 | 2012-07-30 | 2014-05-27 |  | Scottish Water Wide | 2136640 | 26732 | 6332.38 | 0 | 0 | 0 | 0 | 33064.38 | 0 | 2169704.38 | 0 | [6 empty] | CM_WSI | 50% | CM_WWI | 50%
402574 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-03-12 | 2014-03-11 | 2014-03-11 | 2016-05-19 |  | Scottish Water Wide | 9933487 | 178688 | -228000.92 | 0 | 0 | 0 | 0 | -49312.92 | 0 | 9884174.08 | 0 | [6 empty] | CM_WSI | 100%
502390 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2021-04-15 | 2022-03-01 | 2022-05-20 | 2021-04-15 | 2021-04-15 | Scottish Water Wide | 0 | 0 | 0 | 13.455 | -13.455 | 0 | 9337768.25 | 9337768.25 | 0 | 9337768.25 | 0 | [6 empty] | CM_WSI | 100%
403545 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS5 | 2013-09-23 | 2017-06-05 | 2018-01-22 | 2019-02-28 | 2019-02-28 | North Ayrshire | 13361 | -2413 | 109777 | 650766 | 78599 | 10908 | 2500 | 850137 | 0 | 863498 | 80660 | [6 empty] | EC16A | 100%
400071 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-09-29 | 2011-10-27 | 2011-10-31 | 2011-12-14 |  | North Ayrshire | 123162.48 | 98.96 | 0 | 0 | 0 | 0 | 0 | 98.96 | 0 | 123261.44 | 0 | [6 empty] | CM_WWNI | 100%
402476 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-06-28 | 2013-02-06 | 2013-02-06 | 2015-03-26 | 2015-03-31 | Scottish Water Wide | 1630748 | 629 | 2694.83 | 1272.35 | 0 | 0 | 0 | 4596.18 | 0 | 1635344.18 | 139001 | [6 empty] | CS16S | 100%
501012 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-09-30 | 2016-06-29 | 2016-06-29 | 2017-04-24 | 2017-04-24 | East Ayrshire | 0 | 2000 | 43000 | 1477.4 | 0 | 0 | 0 | 46477.4 | 0 | 46477.4 | 0 | [6 empty] | CM_WWI | 100%
403752 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-03-17 | 2014-03-17 | 2014-04-04 | 2016-02-08 |  | Scottish Water Wide | 464158 | 114216.75 | 0 | 0 | 0 | 0 | 0 | 114216.75 | 0 | 578374.75 | 0 | [6 empty] | CM_M&G | 100%
500644 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2021-03-05 | 2021-03-05 | Scottish Water Wide | 0 | 371744 | 662846.94 | 681827.3 | 710142.67 | 63835.53 | 62103.58 | 2552500.02 | 0 | 2552500.02 | 0 | [6 empty] | CM_M&G | 100%
050023 | Q&S4 | Improving the customer experience | IT Security and Communications |  |  | General |  | SWD | IT Security and Communications | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | -5000515.1868 | 5000515.1868 | 0 | 0 | 0 | 0 | [6 empty] | CS24S | 25% | CS24W | 25% | CS28S | 25% | CS28W | 25%
401603 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-12-10 | 2011-01-18 | 2011-04-29 | 2015-07-07 |  | Scottish Water Wide | 1503807 | -148.84 | 0 | 0 | 0 | 0 | 0 | -148.84 | 0 | 1503658.16 | 0 | [6 empty] | CM_WSI | 100%
500713 | Q&S4 | Improving drinking water availability and resilience of service | Interruptions to Supply |  |  | Water |  | SWD | Interruptions to Supply | MS3 | 2015-06-29 | 2015-06-29 | 2016-02-26 | 2020-02-19 | 2020-04-29 | Scottish Water Wide | 0 | 535584.07 | 138920.93 | 78824.77 | 124333.41 | 1336.83 | 0 | 879000.01 | 0 | 879000.01 | 945925.7722 | [6 empty] | CS12 | 100%
401604 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-12-10 | 2011-03-16 | 2011-04-07 | 2016-05-05 |  | Scottish Water Wide | 1843779 | -39957.47 | 0 | 0 | 0 | 0 | 0 | -39957.47 | 0 | 1803821.53 | 0 | [6 empty] | CM_WSI | 100%
401605 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-12-10 | 2013-03-20 | 2013-04-23 | 2016-05-05 |  | Scottish Water Wide | 1740486.5 | 781163.5 | -524533.68 | 0 | 0 | 0 | 0 | 256629.82 | 0 | 1997116.32 | 0 | [6 empty] | CM_WSI | 100%
500714 | Q&S4 | Improving drinking water availability and resilience of service | Interruptions to Supply |  |  | Water |  | SWD | Interruptions to Supply | MS7 | 2015-06-30 | 2015-06-30 | 2016-02-04 | 2019-01-25 | 2019-01-25 | Scottish Water Wide | 0 | 489674 | 467544.3 | 141668.28 | 0 | 0 | 0 | 1098886.58 | 0 | 1098886.58 | 945925.7722 | [6 empty] | CS12 | 100%
401602 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-12-02 | 2011-01-17 | 2011-04-29 | 2015-08-12 |  | Scottish Water Wide | 300470.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300470.18 | 0 | [6 empty] | CM_WSI | 100%
501267 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2015-12-03 | 2019-07-01 | 2019-08-27 | 2020-04-09 | 2020-07-16 | South Ayrshire | 0 | 8024.88 | 59471.12 | 104498 | 143 | 9307.19 | 0 | 181444.19 | 0 | 181444.19 | 0 | [6 empty] | CM_WWI | 100%
501562 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2016-08-29 | 2022-02-09 | 2022-04-06 | 2022-09-08 | 2022-12-09 | Angus | 0 | 0 | 12650 | -8861.81 | 0 | 0 | 0 | 3788.19 | 375340.79 | 379128.98 | 0 | [6 empty] | CM_WWI | 100%
502638 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-05-05 | 2022-04-01 | 2022-06-07 | 2023-01-09 | 2023-04-11 | West Dunbartonshire | 0 | 0 | 17120.93 | 279.07 | 2060.01 | 0 | 0 | 19460.01 | 832539.99 | 852000 | 0 | [6 empty] | CM_WSI | 100%
502718 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2017-04-10 | 2017-04-10 | 2017-04-24 | 2018-04-29 | 2018-04-29 | Scottish Borders | 0 | 0 | 0 | 277200 | -1400 | 0 | 0 | 275800 | 0 | 275800 | 0 | [6 empty] | CM_WWNI | 100%
502578 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS0 | 2017-08-28 | 2020-01-27 | 2020-04-03 | 2021-04-21 | 2021-07-26 | Renfrewshire | 0 | 0 | 4601.65 | 11604.19 | 65346.16 | 173577.24 | 468990.72 | 724119.96 | 191795.05 | 915915.01 | 0 | [6 empty] | CM_WWI | 100%
402674 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-05-16 | 2013-02-27 | 2013-03-25 | 2014-03-31 |  | City of Edinburgh | 315892 | 1369 | -2335.97 | 0 | 0 | 0 | 0 | -966.97 | 0 | 314925.03 | 0 | [6 empty] | CM_WWI | 100%
045606 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-06-30 | 2011-08-29 | 2015-03-25 | 2015-06-02 | Renfrewshire | 574766.94 | 26978.6 | 16.55 | 0 | 0 | 0 | 0 | 26995.15 | 0 | 601762.09 | 7198 | [6 empty] | DW1A | 100%
502365 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2016-10-18 | 2016-10-18 | 2017-03-10 | 2018-08-29 | 2018-08-29 | Stirling | 0 | 0 | 348411.21 | 1587519.12 | 1074872.11 | 3866.44 | 4089.89 | 3018758.77 | 1543.66 | 3020302.43 | 0 | [6 empty] | CM_WSI | 100%
045652 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-07-31 | 2012-06-20 | 2012-09-03 | 2014-03-24 |  | East Dunbartonshire | 6852331.91 | 1214.09 | -266.95 | 0 | 0 | 0 | 0 | 947.14 | 0 | 6853279.05 | 0 | [6 empty] | CM_WSNI | 100%
500775 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2015-07-24 | 2017-01-30 | 2017-04-28 | 2017-08-17 | 2017-08-17 | Aberdeenshire | 0 | 8332.08 | 235336.92 | 66148 | 0 | 0 | 0 | 309817 | 0 | 309817 | 0 | [6 empty] | CM_WWNI | 100%
403006 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2012-10-30 | 2015-12-15 | 2015-12-16 | 2015-12-18 |  | Moray | 864.49 | 15341.72 | 521.21 | 0 | 0 | 0 | 0 | 15862.93 | 0 | 16727.42 | 0 | [6 empty] | CM_WWI | 100%
501561 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS2 | 2017-05-30 | 2019-01-17 | 2019-06-17 | 2019-09-02 | 2019-12-03 | Moray | 0 | 0 | 9769.62 | 11224.38 | 93353 | 134441.87 | 0.12 | 248788.99 | 2250.01 | 251039 | 0 | [6 empty] | CM_WWI | 100%
503217 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-05 | 2023-06-20 | 2023-10-13 | 2024-10-09 | 2025-01-09 | Moray | 0 | 0 | 0 | 0 | 43006.42 | 9094.38 | 18611.33 | 70712.13 | 81273.22 | 151985.35 | 148885.7057 | [6 empty] | SG1 | 100%
036072 | Q&S3A | Sustaining existing high service for customers | Water non infrastructure |  |  | Water |  | SWMD | Water non infrastructure | MS7 | 2007-07-02 | 2007-07-02 | 2008-02-07 | 2015-04-21 |  | East Lothian | 86265 | -16375 | -2391.79 | 0 | 0 | 0 | 0 | -18766.79 | 0 | 67498.21 | 0 | [6 empty] | WSNI | 100%
500198 | Q&S4 | Protecting and enhancing the environment | Odour |  |  | Wastewater |  | SWMD | Odour | MS5 | 2015-08-26 | 2017-03-23 | 2017-03-27 | 2018-03-01 | 2018-12-01 | Scottish Borders | 0 | 18160 | 85902.15 | 483157.03 | 82853.1 | 931.72 | 1083.29 | 672087.29 | 1041.13 | 673128.42 | 350414.3728 | [6 empty] | CS2 | 100% | bar: Regulatory Outputs OMG-29
500498 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2015-06-02 | 2018-03-29 | 2018-06-29 | 2019-09-05 | 2019-09-05 | Fife | 0 | 77186 | 17914 | 223857 | 940527 | 193794 | 0 | 1453278 | 2400 | 1455678 | 0 |  |  |  |  | 14900.0003 |  | CM_WWI | 100%
045410 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2013-02-18 | 2013-02-26 | 2013-11-28 | 2015-12-22 | Perth and Kinross | 657833.69 | 20733.15 | 0 | 0 | 0 | 0 | 0 | 20733.15 | 0 | 678566.84 | 29100 | [6 empty] | DW23 | 100%
503312 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS5 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-03-05 | 2019-03-05 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 30670.13 | 0 | 0 | 30670.13 | 0 | 30670.13 | 148885.7057 | [6 empty] | SG1 | 100%
403782 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS0 | 2017-02-17 | 2020-05-25 | 2020-09-21 | 2021-08-25 | 2021-11-17 | Aberdeenshire | 9738 | 4161.52 | 7031.98 | 12806.558 | 7265.992 | 98100.03 | 404699.6 | 534065.68 | 211652.73 | 755456.41 | 0 | [6 empty] | SG1 | 100%
501731 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS0 | 2018-09-27 | 2020-01-06 | 2020-01-07 | 2021-04-01 | 2021-07-01 | East Ayrshire | 0 | 0 | 0 | 0 | 29674.86 | 263720.78 | 1791493.71 | 2084889.35 | 529898.49 | 2614787.84 | 1772846.4163 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
502305 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-05-25 | 2022-11-16 | 2023-03-16 | 2024-03-05 | 2024-06-05 | Dumfries and Galloway | 0 | 0 | 36995.83 | 79190.13 | 52002.0425 | 0 | 7766.8 | 175954.8025 | 3144087.75 | 3320042.5525 | 0 | [6 empty] | CM_WSNI | 100%
503480 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2021-04-01 | 2022-01-17 | 2022-04-18 | 2022-11-25 | 2023-02-27 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 9328.08 | 9291.92 | 18620 | 369379.91 | 387999.91 | 0 | [6 empty] | CM_WSI | 100%
400730 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2010-04-16 | 2011-11-15 | 2011-11-15 | 2016-12-19 | 2016-12-19 | North Ayrshire | 146717 | 1272922 | 202361 | 0 | -11617.565 | 0 | 0 | 1463665.435 | 0 | 1610382.435 | 229318.7788 | [6 empty] | CS11 | 100%
045338 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-17 | 2011-03-29 | 2011-11-02 | 2013-07-12 | 2013-08-16 | Highland | 3068040.71 | -16125.02 | 0 | 1308 | 0 | 0 | 0 | -14817.02 | 0 | 3053223.69 | 0 | [6 empty] | DW3F | 3.277% | DW13 | 9.83% | DW23 | 86.89%
501735 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2022-07-25 | 2023-05-10 | 2023-09-13 | 2024-01-23 | 2024-04-24 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000.01 | 100000.01 | 0 | [6 empty] | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 33.33% | CM_WSI | 42.86%
030406 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-14 | 2011-08-22 | 2011-09-30 | 2012-03-22 | 2013-03-25 | Stirling | 605665.56 | -5248.87 | 0 | 0 | 0 | 0 | 0 | -5248.87 | 0 | 600416.69 | 0 | [6 empty] | EC04A | 8% | EC10A | 8% | CM_WWNI | 84%
500219 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS5 | 2015-03-20 | 2016-03-31 | 2016-03-31 | 2017-02-01 | 2017-10-01 | Perth and Kinross | 0 | 5176 | 4657.15 | 4146.38 | 1208.12 | 4220.48 | 0 | 19408.13 | 0 | 19408.13 | 162662.0209 | [6 empty] | DW5FS | 100% | bar: Regulatory Outputs OMG-02
500829 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS5 | 2016-03-24 | 2017-04-13 | 2017-05-31 | 2017-09-01 | 2018-06-01 | Stirling | 0 | 1730 | 852 | 20034.12 | 3339.88 | 2000.02 | 0 | 27956.02 | 0 | 27956.02 | 52965.5411 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 6.67
502577 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS5 | 2019-04-09 | 2019-04-15 | 2019-04-15 | 2019-01-23 | 2019-01-23 | Stirling | 0 | 0 | 20930.23 | 238.73 | 118.3 | 0 | 0 | 21287.26 | 0 | 21287.26 | 148885.7057 | [6 empty] | WG1 | 100%
401043 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS6 | 2010-09-13 | 2012-09-27 | 2012-09-27 | 2016-05-27 | 2016-06-21 | Dumfries and Galloway | 11920420 | 785534 | 469991 | 99306 | 10015 | 0 | 0 | 1364846 | 0 | 13285266 | 349590.0672 |  |  |  |  | 272088.5088 |  | DW1A | 1.7% | WG1 | 11.9% | DW3B | 12.9% | DW13 | 13% | DW3G | 13% | DW4 | 13% | CM_WSNI | 34.5%
500750 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS5 | 2015-08-26 | 2017-05-15 | 2017-09-11 | 2018-08-30 | 2018-08-30 | Highland | 0 | 111237 | 219645.37 | 793610.73 | 215877.68 | 5886.22 | 0 | 1346257 | 0 | 1346257 | 0 | [6 empty] | CM_WSNI | 100%
046841 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2012-03-27 | 2012-04-30 | 2012-11-14 | 2012-11-14 | Highland | 232517.46 | -736.3 | -5361.73 | 0 | 0 | 0 | 0 | -6098.03 | 0 | 226419.43 | 0 | [6 empty] | DW23 | 100%
500220 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS6 | 2015-03-20 | 2016-05-25 | 2016-06-25 | 2017-01-01 | 2017-07-01 | Highland | 0 | 269.54 | 3190.9 | 0 | 1243.34 | 0 | 0 | 4703.78 | 0 | 4703.78 | 5043.8193 | [6 empty] | DW5FS | 100% | bar: Regulatory Outputs OMG-02
500689 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS3 | 2015-07-28 | 2017-03-15 | 2018-09-03 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 3554 | 28491.06 | 19007.58 | 228201.94 | 75704.42 | 0 | 354959 | 0 | 354959 | 0 |  |  |  |  | 4500 |  | CM_M&G | 100%
502366 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2017-01-20 | 2022-02-28 | 2022-06-30 | 2024-01-24 | 2024-04-25 | Highland | 0 | 0 | 0 | 3087.85 | 0 | 0 | 0 | 3087.85 | 459912.13 | 462999.98 | 0 | [6 empty] | CM_WSI | 100%
045341 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-17 | 2011-09-28 | 2011-11-14 | 2016-09-26 | 2016-09-30 | Highland | 4167788.17 | 1636969.05 | 1492748.69 | 75875.6 | -16663.596 | 0 | 0 | 3188929.744 | 0 | 7356717.914 | 713823 | [6 empty] | DW23 | 100%
403974 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS3 | 2015-03-10 | 2016-03-23 | 2016-04-01 | 2019-07-01 | 2019-07-01 | Argyll and Bute-Cowal & Bute | 4700.32 | 23949.68 | 185284 | 281842 | 14004 | 40334 | 0 | 545413.68 | 0 | 550114 | 432097.299 |  |  |  |  | 1500 |  | EC01A | 100% | bar: Regulatory Outputs OMG-17
403975 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS6 | 2015-03-10 | 2016-03-23 | 2016-04-01 | 2018-07-06 | 2018-03-29 | Argyll and Bute-Cowal & Bute | 294.85 | 73301.15 | 378245 | 719971 | -365685 | 120.02 | 1752.97 | 807705.14 | 0 | 807999.99 | 432097.299 | [6 empty] | EC01A | 100%
402958 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2012-10-02 | 2014-09-30 | 2014-11-17 | 2015-04-01 | 2015-04-01 | Renfrewshire | 324721 | 15279 | 245.36 | 0 | 4009.0168 | 0 | 0 | 19533.3768 | 0 | 344254.3768 | 229318.7788 | [6 empty] | CS11 | 100%
502402 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2019-08-19 | 2020-11-30 | 2021-03-29 | 2021-11-08 | 2022-02-08 | Highland | 0 | 0 | 21430.58 | 5013.335 | 18811.5455 | 47335.45 | 124280.79 | 216871.7005 | 233671.23 | 450542.9305 | 148885.7057 | [6 empty] | SG1 | 100%
403976 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS7 | 2015-03-10 | 2016-03-23 | 2016-03-29 | 2018-03-28 | 2018-03-29 | Argyll and Bute-Cowal & Bute | 4729.75 | 1061.04 | 2209.21 | -2000 | -3298.44 | 0 | 0 | -2028.19 | 0 | 2701.56 | 432097.299 | [6 empty] | EC01A | 100%
400524 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2010-03-31 | 2014-11-28 | 2015-01-05 | 2015-12-23 | 2015-12-23 | Fife | 350297 | 982705 | 56000.34 | 13679.71 | 0 | 0 | 0 | 1052385.05 | 0 | 1402682.05 | 229318.7788 | [6 empty] | CS11A | 100%
502260 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2019-06-05 | 2019-06-05 | 2019-06-05 | 2019-06-05 | 2019-06-05 | Aberdeenshire | 0 | 0 | 35402.3 | 3385.67 | 138.98 | 0 | 0 | 38926.95 | 0 | 38926.95 | 148885.7057 | [6 empty] | SG1 | 100%
501312 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-12-03 | 2018-12-03 | 2018-12-03 | 2018-12-03 | 2018-12-03 | Fife | 0 | 13086.25 | 60700.75 | 1458.44 | 3365.37 | 0 | 0 | 78610.81 | 0 | 78610.81 | 148885.7057 | [6 empty] | SG1 | 100%
500497 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-06-02 | 2018-09-27 | 2019-01-28 | 2020-01-29 | 2020-01-29 | Fife | 0 | 181182 | 192042.71 | 75555.2875 | 383995.1925 | 1052705.44 | 21158.87 | 1906639.5 | 8772.56 | 1915412.06 | 0 |  |  |  |  | 9999.9996 |  | CM_WWNI | 100%
503500 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MSU | 2021-04-01 | 2022-01-17 | 2022-03-25 | 2022-08-09 | 2022-11-09 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 4208.13 | 4191.81 | 8399.94 | 426545 | 434944.94 | 0 | [6 empty] | CM_M&G | 100%
502338 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS5 | 2016-11-15 | 2018-03-20 | 2018-03-20 | 2018-09-01 | 2018-11-01 | Fife | 0 | 0 | 34171 | 186306 | 759431 | 22505.95 | 2586.05 | 1005000 | 0 | 1005000 | 0 | [6 empty] | EC16 | 100% | bar: Regulatory Outputs OMG-48
403506 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2013-06-26 | 2015-04-20 | 2015-05-18 | 2016-03-15 | 2016-03-15 | Fife | 108648 | 463086 | 1080.82 | 0 | -12432.8 | 0 | 0 | 451734.02 | 0 | 560382.02 | 0 | [6 empty] | SG1 | 100%
400724 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-04-01 | 2012-02-07 | 2012-07-09 | 2014-07-10 | 2014-07-10 | Highland | 4770864.63 | 38309.75 | -24810.42 | 0 | 0 | 0 | 0 | 13499.33 | 0 | 4784363.96 | 0 | [6 empty] | SG1 | 100%
502841 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-18 | 2027-12-06 | 2028-04-04 | 2029-03-30 | 2029-07-02 | Highland | 0 | 0 | 0 | 20930.23 | 1500.85 | 27790.95 | 0 | 50222.03 | 5949999.9 | 6000221.93 | 148885.7057 | [6 empty] | WG1 | 100%
045033 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-12 | 2011-03-29 | 2011-06-24 | 2013-02-28 | 2013-03-27 | Highland | 3134690.02 | -3396 | 0 | 0 | 0 | 0 | 0 | -3396 | 0 | 3131294.02 | 0 | [6 empty] | DW23 | 100%
046835 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-18 | 2011-05-02 | 2011-09-13 | 2011-12-07 | Highland | 38613.63 | 89.47 | 0 | 0 | 0 | 0 | 0 | 89.47 | 0 | 38703.1 | 0 | [6 empty] | DW13 | 100%
502880 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-07-01 | 2027-12-06 | 2028-03-29 | 2029-03-20 | 2029-06-20 | Highland | 0 | 0 | 0 | 21034.205 | 1135.292 | 12379.77 | 12331.8 | 46881.067 | 7953118.98 | 8000000.047 | 148885.7057 | [6 empty] | WG1 | 100%
045549 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-29 | 2010-12-21 | 2011-09-19 | 2013-02-26 | 2013-03-25 | Aberdeenshire | 807699.15 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 807701.15 | 0 | [6 empty] | WQ01 | 40% | CM_WWNI | 60%
501106 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-09-30 | 2016-08-31 | 2017-01-27 | 2018-06-01 | 2018-11-01 | Falkirk | 0 | 579 | 7903.25 | 10878.75 | 3321.59 | 0 | 0 | 22682.59 | 0 | 22682.59 | 54795.0904 | [6 empty] | EC10E | 46.28% | EC01G | 53.72% | bar: Regulatory Outputs OMG-23
502886 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-04-01 | 2022-06-15 | 2022-10-05 | 2023-05-24 | 2023-08-24 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374999.97 | 374999.97 | 0 | [6 empty] | CM_WWNI | 100%
500579 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-08-25 | 2018-11-30 | 2018-12-18 | 2020-04-27 | 2020-04-27 | Falkirk | 0 | 45317 | 217943.27 | 124637.36 | 1440188.87 | 2800189.75 | 857561.31 | 5485837.56 | 30335.4 | 5516172.96 | 0 |  |  |  |  | 36840 |  | CM_WWNI | 100%
501207 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2016-12-20 | 2019-05-05 | 2019-06-05 | 2019-06-01 | 2019-06-01 | Fife | 0 | 18500.42 | 118321.96 | 35276.82 | 9497.95 | 37851.39 | 27669.81 | 247118.35 | 1485.63 | 248603.98 | 1269641.4686 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
501269 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-09-29 | 2016-09-29 | Glasgow City | 0 | 41860 | 2867.69 | 147.51 | 0 | 0 | 0 | 44875.2 | 0 | 44875.2 | 0 | [6 empty] | CM_WWNI | 100%
502902 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2021-04-01 | 2022-11-23 | 2023-03-13 | 2024-09-03 | 2024-12-04 | Glasgow City | 0 | 0 | 0 | 144835.69 | 3605.9 | 0 | 181558.41 | 330000 | 6670000.02 | 7000000.02 | 0 | [6 empty] | CM_WWNI | 100%
500151 | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-19 | 2015-11-30 | 2016-01-12 | 2016-10-01 | 2016-12-01 | Perth and Kinross | 0 | 27843 | 61747.18 | 0 | 20.64 | 0 | 0 | 89610.82 | 0 | 89610.82 | 72474.3726 | [6 empty] | CS16D | 44.91% | CS11 | 55.09% | bar: Regulatory Outputs OMG-22
045795 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2011-09-01 | 2012-01-20 | 2013-03-28 | 2013-09-12 | Perth and Kinross | 1805160.73 | 21863.32 | 51855.71 | 0 | 0 | 0 | 0 | 73719.03 | 0 | 1878879.76 | 7322 | [6 empty] | WQ01C | 100%
046363 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2009-07-29 | 2012-01-24 | 2012-05-28 | 2015-01-06 | 2015-01-06 | Perth and Kinross | 3112638 | 8077.19 | 29299.51 | 30.81 | 0 | 0 | 0 | 37407.51 | 0 | 3150045.51 | 0 | [6 empty] | SG1 | 100%
500794 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2016-02-22 | 2020-06-29 | 2020-07-28 | 2020-08-07 | 2020-11-10 | Aberdeenshire | 0 | 3271.03 | 1566.9 | 0 | 0 | 43401.36 | 942884.98 | 991124.27 | 8875.74 | 1000000.01 | 0 | [6 empty] | CM_WWNI | 100%
501157 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2016-04-25 | 2021-06-09 | 2021-10-21 | 2022-05-16 | 2022-08-16 | Stirling | 0 | 0 | 42868.62 | -5664.12 | 0.0025 | 0 | 0 | 37204.5025 | 517795.51 | 555000.0125 | 0 | [6 empty] | CM_WWNI | 100%
045560 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-26 | 2011-06-01 | 2011-07-28 | 2012-03-28 | 2012-03-31 | Stirling | 1049400.59 | 401.94 | 0 | 0 | 0 | 0 | 0 | 401.94 | 0 | 1049802.53 | 0 | [6 empty] | CM_WWNI | 8.612% | WQ01 | 91.39%
503285 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2022-02-07 | 2023-06-21 | 2023-10-24 | 2024-10-21 | 2025-01-21 | Stirling | 0 | 0 | 0 | 0 | 78314.46 | 0 | 0 | 78314.46 | 0 | 78314.46 | 148885.7057 | [6 empty] | SG1 | 100%
503310 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-03-07 | 2023-08-25 | 2023-12-25 | 2024-12-20 | 2025-03-24 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 30495.35 | 10661.7 | 32932.68 | 74089.73 | 76081.61 | 150171.34 | 148885.7057 | [6 empty] | SG1 | 100%
501252 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-07-27 | 2022-06-29 | 2022-11-01 | 2023-03-16 | 2023-06-16 | Orkney Islands | 0 | 3837.43 | 3043.46 | 778.19 | 2071.33 | 0 | 0 | 9730.41 | 165119.12 | 174849.53 | 0 | [6 empty] | CM_WSNI | 100%
503244 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2019-06-28 | 2020-09-28 | 2021-02-10 | 2021-09-22 | 2021-12-23 | Orkney Islands | 0 | 0 | 0 | 0 | 24246.42 | 84498.27 | 316628.97 | 425373.66 | 468875.99 | 894249.65 | 0 | [6 empty] | CM_WSNI | 100%
501228 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2017-03-21 | 2019-06-10 | 2019-06-10 | 2019-06-01 | 2019-04-01 | Orkney Islands | 0 | 6117.97 | 58678.96 | -1342.57 | 1244.365 | 0 | 0 | 64698.725 | 0 | 64698.725 | 185113.4411 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
502566 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2019-09-27 | 2020-08-03 | 2020-10-05 | 2021-09-17 | 2021-12-20 | Orkney Islands | 0 | 0 | 20930.23 | 5186.775 | 117888.195 | 48292.56 | 393865.29 | 586163.05 | 462129.36 | 1048292.41 | 148885.7057 | [6 empty] | WG1 | 100%
402579 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-05-10 | 2014-07-29 | 2014-09-01 | 2015-05-25 |  | Orkney Islands | 164189 | 40176 | 82.08 | -490.17 | 0 | 0 | 0 | 39767.91 | 0 | 203956.91 | 0 | [6 empty] | CM_WSNI | 100%
500767 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-07-24 | 2016-04-29 | 2016-05-25 | 2017-05-24 | 2017-05-24 | Aberdeenshire | 0 | 12000 | 81006 | 24295 | 5388.1531 | 0 | 0 | 122689.1531 | 0 | 122689.1531 | 0 | [6 empty] | CM_WWI | 100%
500196 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWD | UWWTD - Works | MS7 | 2015-09-18 | 2018-03-22 | 2018-03-22 | 2018-02-05 | 2018-03-22 | Scottish Borders | 0 | 18094 | -3623.38 | 4166.19 | 0 | 0 | 0 | 18636.81 | 0 | 18636.81 | 46369.8879 | [6 empty] | EC01A | 100%
046158 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-08-11 | 2010-11-29 | 2011-06-27 | 2012-01-26 |  | Fife | 533572.99 | 43.68 | 0 | 0 | 0 | 0 | 0 | 43.68 | 0 | 533616.67 | 0 | [6 empty] | CM_WWNI | 100%
403749 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2014-03-27 | 2014-10-29 | 2014-11-03 | 2016-03-01 | 2016-03-01 | Fife | 232937 | 119503 | 11180.6 | 0 | 0 | 0 | 0 | 130683.6 | 0 | 363620.6 | 173896 | [6 empty] | EC16 | 100% | bar: Regulatory Outputs OMG-48
501102 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2013-09-09 | 2014-05-30 | 2014-06-23 | 2017-01-01 | 2017-03-01 | Fife | 0 | 3144 | 27070 | 2019.86 | 0 | 0 | 0 | 32233.86 | 0 | 32233.86 | 91275.9028 | [6 empty] | EC01G | 15% | EC01D | 85% | bar: Regulatory Outputs OMG-23
046155 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-31 | 2011-09-09 | 2011-03-30 | 2011-03-31 |  | Fife | 132499.81 | -52.52 | 0 | 0 | 0 | 0 | 0 | -52.52 | 0 | 132447.29 | 0 | [6 empty] | CM_WWNI | 100%
046219 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-08-11 | 2011-03-30 | 2011-09-23 | 2012-08-14 |  | Fife | 322993.93 | 18.19 | 0 | 0 | 0 | 0 | 0 | 18.19 | 0 | 323012.12 | 0 | [6 empty] | CM_WWNI | 100%
045635 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-31 | 2011-03-31 | 2011-09-20 | 2013-10-31 |  | Fife | 2149017.14 | 32458.08 | -652.43 | 0 | 0 | 0 | 0 | 31805.65 | 0 | 2180822.79 | 0 | [6 empty] | CM_WWNI | 100%
501746 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2021-04-09 | 2021-08-12 | 2021-08-20 | 2021-12-20 | 2021-12-21 | Fife | 0 | 0 | 3632.58 | 0 | 0 | 0 | 0 | 3632.58 | 144023.46 | 147656.04 | 0 | [6 empty] | CM_WWI | 100%
501153 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-12-10 | 2018-12-12 | 2019-01-07 | 2020-06-15 | 2020-09-15 | Dumfries and Galloway | 0 | 20632 | 211214.27 | 110259.44 | 480178.54 | 1233336.69 | 143645.81 | 2199266.75 | 3594.52 | 2202861.27 | 0 | [6 empty] | CM_WWNI | 100%
046335 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-03-25 | 2010-12-23 | 2011-02-28 | 2015-06-23 | 2015-06-23 | Dumfries and Galloway | 1409351.23 | 67676.99 | 3305.3 | 1372.055 | 0 | 0 | 0 | 72354.345 | 0 | 1481705.575 | 0 | [6 empty] | CM_WWNI | 100%
503218 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-12-06 | 2023-05-19 | 2023-09-15 | 2024-09-11 | 2024-12-12 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 67002.51 | 15555.66 | 40372.48 | 122930.65 | 20581.21 | 143511.86 | 148885.7057 | [6 empty] | SG1 | 100%
501287 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-07-07 | 2018-02-26 | 2018-02-27 | 2019-04-15 | 2019-07-22 | Fife | 0 | 0 | 104370 | 833616 | 3189428 | 55937 | 0 | 4183351 | 2500 | 4185851 | 0 | [6 empty] | CM_WWI | 100%
501070 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | GW1 | 2019-07-26 | 2020-08-17 | 2020-10-14 | 2022-05-01 | 2022-08-01 | Perth and Kinross | 0 | 13344.84 | 122988.01 | 13783.985 | 21959.5045 | 145647.29 | 1055761.7 | 1373485.3295 | 2353207.39 | 3726692.7195 | 450740.5153 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
501353 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS1 | 2016-07-11 | 2020-05-11 | 2020-08-03 | 2021-06-24 | 2021-09-24 | South Ayrshire | 0 | 0 | 42579.77 | 81481.19 | -12008.25 | 0 | 1056566.73 | 1168619.44 | 390925.57 | 1559545.01 | 0 | [6 empty] | CM_WWNI | 100%
046177 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-21 | 2011-06-27 | 2011-09-19 | 2012-06-27 | 2012-09-07 | South Ayrshire | 692270.12 | 1127.98 | 0 | 0 | 0 | 0 | 0 | 1127.98 | 0 | 693398.1 | 0 | [6 empty] | WQ01C | 100%
045538 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-29 | 2011-03-21 | 2011-10-12 | 2012-08-30 | 2013-01-21 | Dumfries and Galloway | 821788.19 | 2090.06 | 0 | 0 | 0 | 0 | 0 | 2090.06 | 0 | 823878.25 | 0 | [6 empty] | SG1 | 16.45% | WQ01 | 83.55%
500144 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS5 | 2015-03-20 | 2016-02-26 | 2016-04-19 | 2018-12-18 | 2019-03-28 | Orkney Islands | 0 | 36113 | 4093 | 40463 | 15400 | 12305.99 | 0 | 108374.99 | 0 | 108374.99 | 9568.822 | [6 empty] | EC01D | 25.5% | CS16D | 74.5%
500777 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2015-08-20 | 2021-04-22 | 2021-06-22 | 2021-11-26 | 2022-02-28 | Orkney Islands | 0 | 22822 | 70421.98 | -4847.98 | 0 | 0 | 0 | 88396 | 11643 | 100039 | 0 | [6 empty] | CM_WWNI | 100%
030425 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-07-24 | 2011-09-21 | 2011-11-08 | 2014-07-31 | 2014-08-26 | Angus | 3697297.02 | 21146.29 | -31175.6 | 7050.5775 | 0 | 0 | 0 | -2978.7325 | 0 | 3694318.2875 | 61201.88 | [6 empty] | CM_WWNI | 10% | EC04A | 90%
045800 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2011-07-28 | 2011-09-05 | 2013-03-01 | 2013-03-26 | Dumfries and Galloway | 3294058.06 | -1356.44 | 0 | 0 | 0 | 0 | 0 | -1356.44 | 0 | 3292701.62 | 4611.9157 | [6 empty] | CM_WWNI | 5% | WQ01C | 95%
501728 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-04-01 | 2022-01-17 | 2022-04-08 | 2022-08-23 | 2022-11-21 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198870.2 | 198870.2 | 0 | [6 empty] | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 33.33% | CM_WSI | 42.86%
402182 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-06-28 | 2012-03-27 | 2012-06-11 | 2013-03-08 | 2013-03-08 | North Ayrshire | 404614.81 | 118.17 | 0 | 0 | 0 | 0 | 0 | 118.17 | 0 | 404732.98 | 0 | [6 empty] | CM_WSI | 100%
503432 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWD | Reservoirs | GW0 | 2019-05-27 | 2019-08-05 | 2019-08-26 | 2020-05-25 | 2020-07-09 | North Ayrshire | 0 | 0 | 0 | 0 | 10046.51 | 385668.33 | 114331.65 | 510046.49 | 0 | 510046.49 | 1560467.3848 | [6 empty] | CS22 | 100%
501237 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2016-04-06 | 2020-04-13 | 2020-05-12 | 2020-12-17 | 2020-12-17 | Dumfries and Galloway | 0 | 0 | 33190.8 | 49740.8275 | 109998.3325 | 170328.07 | 1817344.45 | 2180602.48 | 16221.17 | 2196823.65 | 0 | [6 empty] | CM_WSI | 100%
401013 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-05-31 | 2010-12-20 | 2011-02-07 | 2015-07-20 |  | South Ayrshire | 1318123 | 32000 | 11797.93 | -52550.98 | 0 | 0 | 0 | -8753.05 | 0 | 1309369.95 | 0 | [6 empty] | CM_WSI | 100%
402183 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-06-28 | 2011-11-10 | 2011-11-14 | 2012-03-01 | 2012-03-21 | Inverclyde | 335439.09 | 43.68 | 0 | 0 | 0 | 0 | 0 | 43.68 | 0 | 335482.77 | 0 | [6 empty] | CM_WSI | 100%
402896 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-08-23 | 2013-12-17 | 2014-02-11 | 2014-10-21 | 2015-02-02 | Scottish Borders | 154029.62 | 205.43 | 0 | 0 | 0 | 0 | 0 | 205.43 | 0 | 154235.05 | 0 | [6 empty] | CM_WSI | 100%
500831 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS5 | 2016-01-20 | 2016-03-30 | 2016-06-22 | 2017-01-01 | 2017-11-01 | Highland | 0 | 4445.71 | 8896.29 | 3042.01 | 1205.05 | 0 | 0 | 17589.06 | 0 | 17589.06 | 56861.3388 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 19.22
503364 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-07-30 | 2027-12-20 | 2028-04-17 | 2029-04-12 | 2029-07-13 | Highland | 0 | 0 | 0 | 0 | 20093.02 | 14218.14 | 24980.14 | 59291.3 | 9960801.73 | 10020093.03 | 148885.7057 | [6 empty] | WG1 | 100%
502908 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-06-01 | 2022-08-26 | 2022-12-26 | 2023-08-07 | 2023-11-07 | Highland | 0 | 0 | 0 | 21935.36 | 123.03 | 0 | 0 | 22058.39 | 0 | 22058.39 | 0 | [6 empty] | CM_WSNI | 100%
500830 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS6 | 2015-10-28 | 2017-03-23 | 2017-04-18 | 2017-06-01 | 2018-03-01 | Highland | 0 | 3140 | 6229.9 | 7656.63 | 500.65 | 914.43 | 0 | 18441.61 | 0 | 18441.61 | 11869.0072 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 3.34
502840 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-18 | 2027-12-06 | 2028-04-04 | 2029-03-30 | 2029-07-02 | Highland | 0 | 0 | 0 | 20930.23 | 1545.39 | 27524.37 | 0 | 49999.99 | 7949999.9 | 7999999.89 | 148885.7057 | [6 empty] | WG1 | 100%
501533 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2022-10-17 | 2023-08-24 | 2023-12-28 | 2024-08-13 | 2024-11-13 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 488914.97 | 488914.97 | 0 | [6 empty] | CM_WSNI | 100%
503075 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2021-05-27 | 2022-03-21 | 2022-06-14 | 2023-01-10 | 2023-04-12 | Stirling | 0 | 0 | 0 | 12898.1725 | 11257.1175 | 0 | 0 | 24155.29 | 648833.69 | 672988.98 | 0 | [6 empty] | CM_WWI | 100%
404133 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS3 | 2017-04-28 | 2018-08-28 | 2018-10-11 | 2019-09-23 | 2019-10-28 | Highland | 0 | 0 | 0 | 48029.2 | 481961.44 | 146962.07 | 745.42 | 677698.13 | 1078.97 | 678777.1 | 0 |  |  |  |  | 25689.9997 |  | DW23 | 100%
502573 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-18 | 2027-07-22 | 2027-10-05 | 2028-09-13 | 2028-12-14 | Argyll and Bute-North Argyll | 0 | 0 | 20930.23 | 671.6785 | 1194.7015 | 12807.45 | 12757.82 | 48361.88 | 4951637.98 | 4999999.86 | 148885.7057 | [6 empty] | WG1 | 100%
502839 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW2 | 2021-05-20 | 2023-05-17 | 2023-09-14 | 2024-09-10 | 2024-12-11 | Highland | 0 | 0 | 0 | 21346.13 | 1290.63 | 0 | 0 | 22636.76 | 27615.28 | 50252.04 | 148885.7057 | [6 empty] | WG1 | 100%
046193 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-31 | 2011-09-23 | 2011-09-23 | 2013-12-20 |  | Renfrewshire | 5855436.22 | -68728.56 | 0 | 0 | 0 | 0 | 0 | -68728.56 | 0 | 5786707.66 | 0 |  |  |  |  | 20230 |  | CM_WWNI | 100%
501719 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-10-31 | 2018-08-14 | 2018-11-05 | 2020-01-16 | 2020-04-17 | Renfrewshire | 0 | 0 | 15850.44 | 195135.33 | 1076591.23 | 257310.77 | 0.24 | 1544888.01 | 0 | 1544888.01 | 0 | [6 empty] | CM_WWI | 100%
502733 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2017-04-25 | 2017-07-12 | 2017-08-07 | 2018-02-07 | 2018-02-07 | Glasgow City | 0 | 0 | 0 | 2250180.95 | -43342.27 | 2261.4 | 1919.57 | 2211019.65 | 0 | 2211019.65 | 0 | [6 empty] | CM_WWNI | 100%
402641 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-06-18 | 2012-06-18 | 2012-07-30 | 2016-06-30 |  | East Renfrewshire | 38932.3 | -0.3 | -6367.51 | 0 | 0 | 0 | 0 | -6367.81 | 0 | 32564.49 | 0 | [6 empty] | CM_WWNI | 100%
501399 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-06-30 | 2016-07-28 | Aberdeenshire | 0 | 2121.87 | 79.8 | 0 | 0 | 0 | 0 | 2201.67 | 0 | 2201.67 | 0 | [6 empty] | CM_WSNI | 100%
402946 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-09-28 | 2012-12-04 | 2013-02-18 | 2013-03-25 | 2013-03-25 | Fife | 30195 | -472.46 | 0 | 0 | 0 | 0 | 0 | -472.46 | 0 | 29722.54 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
503501 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MSU | 2021-04-01 | 2022-02-14 | 2022-05-16 | 2023-02-14 | 2023-05-17 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 24432.36 | 24337.66 | 48770.02 | 1971543.99 | 2020314.01 | 0 | [6 empty] | CM_M&G | 100%
503378 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MSU | 2022-03-14 | 2023-01-19 | 2023-05-24 | 2023-11-14 | 2024-02-14 | Renfrewshire | 0 | 0 | 0 | 0 | 65637.27 | 22839.42 | 28991.93 | 117468.62 | 29631.55 | 147100.17 | 148885.7057 | [6 empty] | SG1 | 100%
501693 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-07-05 | 2018-12-05 | 2019-02-25 | 2019-07-08 | 2019-10-10 | South Lanarkshire | 0 | 0 | 18862.98 | 90485.02 | 314047 | 114342.45 | 0 | 537737.45 | 1419.01 | 539156.46 | 0 | [6 empty] | CM_WWI | 100%
030434 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-20 | 2010-12-30 | 2011-01-18 | 2012-01-01 | 2012-03-21 | South Lanarkshire | 2177233.5 | 1197.87 | 0 | 0 | 0 | 0 | 0 | 1197.87 | 0 | 2178431.37 | 0 | [6 empty] | EC01A | 30.82% | CM_WWNI | 69.18%
503070 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-04-01 | 2021-04-01 | 2021-07-21 | 2022-03-03 | 2022-06-03 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316000.04 | 316000.04 | 0 | [6 empty] | CM_WWNI | 100%
501194 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-11-27 | 2015-11-27 | 2016-02-12 | 2021-01-22 | 2021-04-19 | Scottish Water Wide | 0 | 298491.68 | 894180.67 | 603924.65 | 1122274.71 | 430637 | 629491.29 | 3979000 | 0 | 3979000 | 0 | [6 empty] | CM_M&G | 100%
500145 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS4 | 2015-03-19 | 2016-05-26 | 2016-06-20 | 2019-02-28 | 2019-06-28 | Dumfries and Galloway | 0 | 12754 | 15157.18 | 97773.82 | 8161 | 0 | 0 | 133846 | 0 | 133846 | 68276.886 | [6 empty] | EC01G | 5.63% | CS16D | 34.4% | EC01D | 59.97%
500147 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2015-03-19 | 2016-05-30 | 2016-08-19 | 2019-06-01 | 2019-09-01 | Fife | 0 | 13245 | 11894 | 11838 | 40966.835 | 626 | 0 | 78569.835 | 0 | 78569.835 | 106299.7074 | [6 empty] | EC01G | 0.6% | EC10E | 31.81% | EC01D | 67.59% | bar: Regulatory Outputs OMG-23
402837 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MS0 | 2012-08-31 | 2019-07-17 | 2019-07-17 | 2019-08-12 | 2019-09-13 | Argyll and Bute-Cowal & Bute | 32664.39 | 4584.61 | 0.25 | -4302 | 334.77 | 0 | 0 | 617.63 | 0 | 33282.02 | 23244 | [6 empty] | EC02B | 100%
500152 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-01-19 | 2016-03-28 | 2018-03-29 | 2018-06-25 | North Ayrshire | 0 | 36102 | 130135 | 61859.285 | -16.85 | 0 | 0 | 228079.435 | 0 | 228079.435 | 10362.528 | [6 empty] | CS16D | 32.24% | EC01G | 67.76%
403548 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS3 | 2013-11-29 | 2018-09-25 | 2018-12-19 | 2019-08-23 | 2019-11-26 | North Ayrshire | 88297.88 | 73202.12 | 137298 | 102940.3 | 1414236.7 | 355101.51 | 1400.91 | 2084179.54 | 697.6 | 2173175.02 | 1391238 |  |  |  |  | 7950 |  | EC16 | 100%
503272 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-11 | 2023-06-27 | 2023-10-30 | 2024-10-25 | 2025-01-27 | North Ayrshire | 0 | 0 | 0 | 0 | 77263.27 | 27742.37 | 30145.09 | 135150.73 | 8145.85 | 143296.58 | 148885.7057 | [6 empty] | SG1 | 100%
502091 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-04-01 | 2022-04-12 | 2022-08-01 | 2023-03-17 | 2023-06-19 | Dumfries and Galloway | 0 | 0 | 20306.83 | 14658.54 | 0 | 0 | 0 | 34965.37 | 229124.67 | 264090.04 | 0 | [6 empty] | CM_WSNI | 100%
500248 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-06-02 | 2021-06-21 | 2021-07-19 | 2022-01-20 | 2022-10-14 | West Lothian | 0 | 1109 | 50133 | 4862 | -332 | 0 | 0 | 55772 | 209260.96 | 265032.96 | 0 | [6 empty] | CM_WSI | 100%
503107 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2021-04-06 | 2022-11-17 | 2023-03-16 | 2024-06-07 | 2024-09-09 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 41441.42 | 57882.86 | 99324.28 | 3900675.74 | 4000000.02 | 587726.5342 | [6 empty] | CM_WSNI | 50% | WG5 | 50%
402428 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-10-17 | 2013-07-24 | 2013-11-04 | 2014-08-07 | 2014-08-07 | Angus | 951313 | 98025.22 | 0 | 0 | 0 | 0 | 0 | 98025.22 | 0 | 1049338.22 | 0 | [6 empty] | SG1 | 100%
403412 | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2013-12-24 | 2013-12-24 | 2016-02-02 | 2016-04-04 | 2016-04-28 | Scottish Water Wide | 358873.93 | 0.07 | 0 | 0 | 0 | 0 | 0 | 0.07 | 0 | 358874 | 0 | [6 empty] | CS20 | 100%
503486 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2019-02-21 | 2019-04-29 | 2019-05-06 | 2020-12-24 | 2021-03-17 | Scottish Water Wide | 0 | 0 | 0 | 0 | 2851.61 | 327373.93 | 345455.73 | 675681.27 | 0 | 675681.27 | 19186.1679 | [6 empty] | DW25TS | 100%
400562 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2015-09-07 | 2015-09-24 | All East Unitary Authorities | 79483.85 | -1122.37 | 0 | 0 | 0 | 0 | 0 | -1122.37 | 0 | 78361.48 | 0 | [6 empty] | DW1B | 100%
400564 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2015-09-07 | 2015-09-17 | All North Unitary Authorities | 200377 | -8680.28 | 0 | 0 | 0 | 0 | 0 | -8680.28 | 0 | 191696.72 | 0 | [6 empty] | DW1B | 100%
400569 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2015-09-07 | 2015-09-11 | All West Unitary Authorities | 15057.35 | -1228.24 | 0 | 0 | 0 | 0 | 0 | -1228.24 | 0 | 13829.11 | 0 | [6 empty] | DW1B | 100%
030439 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-09 | 2012-01-23 | 2013-05-14 | 2013-05-22 | 2013-05-22 | South Lanarkshire | 262701.69 | 366.87 | 0 | 0 | 0 | 0 | 0 | 366.87 | 0 | 263068.56 | 0 | [6 empty] | EC04A | 23.19% | EC10A | 76.81%
500148 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS4 | 2015-03-20 | 2016-05-30 | 2016-07-29 | 2019-03-01 | 2019-11-01 | South Lanarkshire | 0 | 4037 | 12977 | 20750 | 41962.83 | 1271.76 | 1.41 | 81000 | 0 | 81000 | 24177.3085 | [6 empty] | EC01D | 100% | bar: Regulatory Outputs OMG-23
402500 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-01-16 | 2012-12-07 | 2012-12-07 | 2015-08-07 |  | Scottish Water Wide | 337450 | -378.42 | 526.68 | 0 | 0 | 0 | 0 | 148.26 | 0 | 337598.26 | 0 | [6 empty] | CM_WSI | 100%
400800 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-01 | 2010-05-04 | 2016-10-20 |  | City of Edinburgh | 1760000 | 54388.64 | -36079.88 | 0 | 0 | 0 | 0 | 18308.76 | 0 | 1778308.76 | 0 | [6 empty] | CM_WSI | 100%
400759 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2010-05-04 | 2015-10-26 |  | City of Edinburgh | 1405375.69 | 2955.12 | 0 | 0 | 0 | 0 | 0 | 2955.12 | 0 | 1408330.81 | 0 | [6 empty] | CM_WSI | 100%
400757 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2010-05-04 | 2015-12-14 |  | City of Edinburgh | 1310000 | 3898.13 | 0 | 0 | 0 | 0 | 0 | 3898.13 | 0 | 1313898.13 | 0 | [6 empty] | CM_WSI | 100%
402046 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-05-27 | 2014-10-20 | 2014-10-20 | 2015-09-18 |  | Scottish Water Wide | 26380 | -3221.85 | 0 | 0 | 0 | 0 | 0 | -3221.85 | 0 | 23158.15 | 0 | [6 empty] | CM_WSI | 100%
502720 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2021-04-15 | 2021-04-15 | 2021-04-15 | 2021-04-15 | 2021-04-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 800000 | 6630000 | 7430000 | 0 | 7430000 | 0 | [6 empty] | CM_WSI | 100%
400572 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2015-10-19 |  | Scottish Water Wide | 1733264.37 | -204424 | 0 | 0 | 0 | 0 | 0 | -204424 | 0 | 1528840.37 | 0 | [6 empty] | DW1B | 100%
400760 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2010-05-04 | 2015-10-26 |  | Glasgow City | 1400000 | 68044.17 | 0 | 0 | 0 | 0 | 0 | 68044.17 | 0 | 1468044.17 | 0 | [6 empty] | CM_WSI | 100%
400758 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2010-05-04 | 2015-10-26 |  | Glasgow City | 530000 | -16882.91 | 0 | 0 | 0 | 0 | 0 | -16882.91 | 0 | 513117.09 | 0 | [6 empty] | CM_WSI | 100%
400756 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-21 | 2010-05-04 | 2010-05-04 | 2015-10-26 |  | Glasgow City | 817000 | -78770.04 | 0 | 0 | 0 | 0 | 0 | -78770.04 | 0 | 738229.96 | 0 | [6 empty] | CM_WSI | 100%
502792 | Q&S4 | Improving the customer experience | IT Security and Communications |  |  | General |  | SWD | IT Security and Communications | MS0 | 2018-01-31 | 2019-06-17 | 2019-09-11 | 2020-08-03 | 2020-09-28 | Scottish Water Wide | 0 | 0 | 0 | 173511.8085 | 418509.0515 | 1801665.34 | 1310313.8 | 3704000 | 0 | 3704000 | 4223868.7476 | [6 empty] | CS28S | 50% | CS28W | 50%
503208 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | General |  | SWD | Water Non infrastructure | MS3 | 2018-07-26 | 2018-07-26 | 2018-11-01 | 2019-06-11 | 2019-09-11 | Scottish Water Wide | 0 | 0 | 0 | 0 | 304417.39 | 194561.86 | 2880 | 501859.25 | 638.76 | 502498.01 | 0 | [6 empty] | CM_WSNI | 50% | CM_WWNI | 50%
402864 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-08-15 | 2013-05-21 | 2013-09-10 | 2014-02-10 | 2014-02-10 | Glasgow City | 49175 | -188.54 | 0 | 0 | 0 | 0 | 0 | -188.54 | 0 | 48986.46 | 130.8 | [6 empty] | CM_WWI | 40% | CS11A | 60%
501272 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-11-16 | 2015-11-16 | 2016-03-01 | 2016-12-15 | 2017-02-15 | Scottish Water Wide | 0 | 135992.95 | 76990.95 | 0 | 0 | 0 | 0 | 212983.9 | 0 | 212983.9 | 0 | [6 empty] | CM_WWNI | 20% | CM_WSNI | 80%
500946 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2015-10-21 | 2016-11-18 | 2017-07-24 | 2019-10-18 | 2019-10-21 | Scottish Water Wide | 0 | 7736.3 | 165355.7 | 315479.4755 | 82069.5245 | 110968.43 | 2798.11 | 684407.54 | 2373.51 | 686781.05 | 0 | [6 empty] | CM_WSNI | 100%
038008 | Q&S4 | Supporting economic development | RCC |  |  | Wastewater |  | SWMD | RCC | MS7 | 2009-06-01 | 2009-06-16 | 2009-06-15 | 2013-11-19 | 2011-03-14 | Scottish Water Wide | 467667.65 | -305746.56 | 0 | 0 | 0 | 0 | 0 | -305746.56 | 0 | 161921.09 | 0 | [6 empty] | SG2 | 100%
400743 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2007-03-08 | 2010-03-31 | 2010-04-06 | 2018-08-16 | 2015-09-24 | Scottish Water Wide | 5438129 | 663990.98 | 359368.9 | 303888.05 | 65684.47 | 0 | 0 | 1392932.4 | 0 | 6831061.4 | 0 | [6 empty] | SG5 | 100%
403162 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-11-26 | 2013-12-19 | 2014-01-31 | 2015-03-04 |  | Scottish Water Wide | 700142 | 19858 | 0 | 107545.76 | 0 | 0 | 0 | 127403.76 | 0 | 827545.76 | 0 | [6 empty] | WSI | 0.3021% | WSNI | 0.3021% | WWNI | 0.3021% | WWI | 99.09%
503092 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2019-06-28 | 2020-09-28 | 2021-01-26 | 2021-09-07 | 2021-12-08 | North Lanarkshire | 0 | 0 | 0 | 15869.3 | 11599.4325 | 73831.09 | 392056.14 | 493355.9625 | 296878.17 | 790234.1325 | 0 | [6 empty] | CM_WSNI | 100%
500155 | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-19 | 2015-10-29 | 2015-12-14 | 2017-03-01 | 2017-05-01 | South Lanarkshire | 0 | 59345 | 52490.81 | -539.46 | 123.84 | 0 | 0 | 111420.19 | 0 | 111420.19 | 561676.3877 | [6 empty] | CS15 | 27.34% | CS11 | 27.88% | CS16D | 44.78% | bar: Regulatory Outputs OMG-22
502812 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-07-08 | 2022-07-22 | 2022-11-14 | 2023-11-02 | 2024-02-02 | South Lanarkshire | 0 | 0 | 0 | 77870.095 | 19160.025 | 7168.8 | 9217.15 | 113416.07 | 28584.03 | 142000.1 | 148885.7057 | [6 empty] | SG1 | 100%
045554 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-26 | 2010-09-20 | 2011-03-14 | 2012-03-23 | 2012-03-26 | Fife | 528482.63 | 187.98 | 0 | 0 | 0 | 0 | 0 | 187.98 | 0 | 528670.61 | 0 | [6 empty] | CM_WWNI | 10.08% | WQ01 | 89.92%
502883 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2020-06-18 | 2021-04-22 | 2021-07-15 | 2022-02-15 | 2022-05-18 | Falkirk | 0 | 0 | 0 | 0 | 0 | 13803.81 | 93674.18 | 107477.99 | 242522.02 | 350000.01 | 0 | [6 empty] | CM_WWI | 100%
503329 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-22 | 2023-08-07 | 2023-12-08 | 2024-11-21 | 2025-02-21 | Angus | 0 | 0 | 0 | 0 | 75284.35 | 0 | 18398.43 | 93682.78 | 51648.6 | 145331.38 | 148885.7057 | [6 empty] | SG1 | 100%
501181 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS0 | 2016-02-17 | 2021-04-01 | 2021-07-19 | 2022-07-14 | 2022-10-14 | Angus | 0 | 5311.04 | 107085.66 | 47777.96 | 4932.51 | 0 | 0 | 165107.17 | 879507.8 | 1044614.97 | 0 | [6 empty] | CM_WWNI | 100%
401338 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-13 | 2012-02-29 | 2012-08-27 | 2013-04-18 | 2013-04-18 | Highland | 123010 | -664.47 | 0 | 0 | 0 | 0 | 0 | -664.47 | 0 | 122345.53 | 0 | [6 empty] | CS1A | 30% | CS1 | 70%
500154 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS3 | 2015-03-27 | 2017-03-28 | 2017-05-30 | 2020-05-22 | 2020-08-21 | Fife | 0 | 13243 | 108441.15 | 371383.85 | 395785 | 164003.79 | 108040.19 | 1160896.98 | 0 | 1160896.98 | 327787.6478 | [6 empty] | EC01G | 0.65% | EC01D | 2.43% | EC10E | 9.73% | CS16D | 87.19%
501745 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2021-04-09 | 2021-08-09 | 2021-08-12 | 2021-12-13 | 2021-12-14 | Fife | 0 | 0 | 5499.61 | 0 | 0 | 0 | 0 | 5499.61 | 236393.4 | 241893.01 | 0 | [6 empty] | CM_WWI | 100%
503127 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2021-05-18 | 2022-04-08 | 2022-06-24 | 2024-03-06 | 2024-06-06 | City of Edinburgh | 0 | 0 | 0 | 278048.316 | 150745.6125 | 47351.81 | 81177.36 | 557323.0985 | 14516676.93 | 15074000.0285 | 0 | [6 empty] | CM_WSI | 100%
502224 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS0 | 2017-03-29 | 2019-04-29 | 2019-06-05 | 2019-09-23 | 2020-01-07 | Fife | 0 | 0 | 4983.09 | 9369.91 | 65944 | 363904.44 | 530.2 | 444731.64 | 268.35 | 444999.99 | 0 | [6 empty] | CM_WWI | 100%
402492 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2011-12-19 | 2013-04-22 | 2013-04-15 | 2015-05-13 |  | Scottish Water Wide | 2341014 | 853.12 | 0 | 0 | 0 | 0 | 0 | 853.12 | 0 | 2341867.12 | 0 | [6 empty] | CM_M&G | 100%
501818 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2017-08-21 | 2018-03-27 | 2018-03-27 | 2019-07-10 | 2019-07-10 | Scottish Water Wide | 0 | 0 | 0 | 332879.82 | 558676.08 | 106198.58 | 0 | 997754.48 | 0 | 997754.48 | 0 |  |  |  |  | 14000.0004 |  | CM_M&G | 100%
500156 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-01-19 | 2016-03-22 | 2017-11-28 | 2018-03-29 | Dumfries and Galloway | 0 | 27658 | 67082.92 | 19917.08 | -1518.1225 | 0 | 0 | 113139.8775 | 0 | 113139.8775 | 57472.577 | [6 empty] | CS16D | 5.303% | EC01D | 94.7%
500159 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS4 | 2015-03-26 | 2016-07-29 | 2016-07-29 | 2019-01-28 | 2019-07-01 | West Lothian | 0 | 21427 | 174286 | 88043 | 67069 | 39848 | 0 | 390673 | 0 | 390673 | 351896.4869 | [6 empty] | EC01D | 26.88% | CS16D | 73.12%
030446 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-23 | 2010-09-20 | 2011-03-28 | 2016-02-04 | 2016-02-04 | West Lothian | 2701382.5 | 30316.5 | -50865.97 | 0 | 0 | 0 | 0 | -20549.47 | 0 | 2680833.03 | 23388.3144 | [6 empty] | EC01A | 15% | CM_WWNI | 30% | EC04A | 55%
403066 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-20 | 2014-04-22 | 2014-04-22 | 2014-04-22 |  | Perth and Kinross | 3308.04 | -46.5 | 0 | 0 | 0 | 0 | 0 | -46.5 | 0 | 3261.54 | 0 | [6 empty] | CM_WSI | 100%
500479 | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWMD | Renewable power | MS7 | 2015-05-18 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | Angus | 0 | 32623 | -6612.25 | 0 | 0 | 0 | 0 | 26010.75 | 0 | 26010.75 | 764721.6298 | [6 empty] | I2S_WI | 100%
503263 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2021-05-05 | 2022-03-28 | 2022-06-03 | 2023-01-02 | 2023-04-04 | Angus | 0 | 0 | 0 | 0 | 17859.81 | 0 | 0 | 17859.81 | 582140.26 | 600000.07 | 0 | [6 empty] | CM_WSI | 100%
501055 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2016-05-31 | 2021-08-02 | 2021-09-23 | 2022-10-17 | 2023-01-17 | Perth and Kinross | 0 | 6823.26 | 37854.91 | 93871.83 | 57517.17 | 0 | 0 | 196067.17 | 1767457.82 | 1963524.99 | 0 | [6 empty] | CM_WSI | 100%
501056 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501057 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501054 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501051 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501052 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501053 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501050 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
500020 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2015-02-10 | 2015-11-27 | 2015-11-30 | 2016-04-01 | 2016-11-23 | Perth and Kinross | 4636 | 96788.19 | 14215.15 | 8043.41 | 7093.44 | 10000 | 0 | 136140.19 | 0 | 140776.19 | 0 | [6 empty] | CM_WSI | 100%
500021 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2015-02-09 | 2016-01-29 | 2016-03-02 | 2017-03-23 | 2017-03-27 | Aberdeenshire | 1455 | 178066 | 304091.41 | 41387.59 | 3833.46 | 0 | 0 | 527378.46 | 0 | 528833.46 | 0 | [6 empty] | CM_WSI | 100%
501044 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501045 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501046 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501043 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501216 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2018-11-23 | 2020-02-03 | 2020-05-28 | 2021-01-01 | 2021-04-01 | Angus | 0 | 5023.26 | 1774.08 | 3840.385 | 8019.185 | 96362.24 | 227746.39 | 342765.54 | 58668.15 | 401433.69 | 449856.7505 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
501227 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2015-11-18 | 2016-01-07 | 2016-04-01 | 2020-01-01 | 2020-08-01 | Angus | 0 | 0 | 71 | 1905.945 | 4565.245 | 0 | 0 | 6542.19 | 0 | 6542.19 | 466391.8995 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
045619 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-06-30 | 2011-04-01 | 2012-12-06 | 2013-01-18 | Angus | 470857.25 | -288 | 0 | 0 | 0 | 0 | 0 | -288 | 0 | 470569.25 | 0 | [6 empty] | DW1A | 100%
503424 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS0 | 2018-12-20 | 2020-04-06 | 2020-08-06 | 2021-03-23 | 2021-06-23 | Renfrewshire | 0 | 0 | 0 | 0 | 280465 | 257415.6 | 107229.02 | 645109.62 | 41573.37 | 686682.99 | 0 | [6 empty] | CM_WWNI | 100%
503383 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MSU | 2022-07-18 | 2023-05-25 | 2023-09-27 | 2024-03-19 | 2024-06-19 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 83748.31 | 0 | 4001.16 | 87749.47 | 58626.13 | 146375.6 | 148885.7057 | [6 empty] | SG1 | 100%
402885 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-11-12 | 2014-06-20 | 2014-06-30 | 2015-08-05 | 2015-08-05 | Stirling | 4921681.17 | 635551.3 | 18088.46 | 18407.5 | -44348.8 | 0 | 0 | 627698.46 | 0 | 5549379.63 | 0 | [6 empty] | CM_WSI | 100%
401352 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-26 | 2013-05-20 | 2013-06-28 | 2014-12-01 | 2014-05-26 | Argyll and Bute-North Argyll | 844436.38 | 1424 | 33.75 | 0 | 0 | 0 | 0 | 1457.75 | 0 | 845894.13 | 0 | [6 empty] | CM_WSI | 100%
501572 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2018-03-15 | 2019-03-08 | 2019-03-25 | 2019-12-01 | 2020-03-01 | Argyll and Bute-Cowal & Bute | 0 | 2930.23 | 2694.42 | 4567.631 | 141103.228 | 779957.27 | 24762.06 | 956014.839 | 2839.65 | 958854.489 | 145915.8112 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
403276 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-01-31 | 2014-10-01 | 2014-10-01 | 2014-10-01 |  | Argyll and Bute-Cowal & Bute | 67921.36 | 614.97 | 0 | 0 | 0 | 0 | 0 | 614.97 | 0 | 68536.33 | 0 | [6 empty] | CM_WSNI | 100%
402059 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-04-06 | 2014-04-30 | 2014-06-30 | 2015-03-09 |  | Highland | 538209 | 7936.47 | 82.19 | 0 | 0 | 0 | 0 | 8018.66 | 0 | 546227.66 | 0 |  |  |  |  | 20056 |  | CM_M&G | 100%
501061 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-04 | 2022-03-14 | 2022-06-22 | 2023-02-08 | 2023-05-11 | Highland | 0 | 15488.37 | 22693.63 | 250 | 4487.22 | 0 | 0 | 42919.22 | 687075.65 | 729994.87 | 0 | [6 empty] | CM_WSI | 100%
501062 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | Highland | 0 | 669.77 | -669.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
500019 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-02-17 | 2021-05-10 | 2022-06-03 | 2023-03-02 | 2023-06-02 | Highland | 1377 | 46260 | 3557 | 16501 | 20429.47 | 0 | 0 | 86747.47 | 1586249.05 | 1674373.52 | 0 | [6 empty] | CM_WSI | 100%
501060 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
500756 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-08-10 | 2021-05-10 | 2021-06-28 | 2021-12-03 | 2022-02-17 | Highland | 0 | 12336 | 4650 | 3359.56 | 832.44 | 0 | 0 | 21178 | 514445 | 535623 | 0 | [6 empty] | CM_WSI | 100%
501260 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS0 | 2015-11-09 | 2022-01-17 | 2022-03-01 | 2022-07-04 | 2022-10-04 | Highland | 0 | 19624 | 77616.49 | -0.49 | -5743.46 | 0 | 0 | 91496.54 | 0 | 91496.54 | 0 | [6 empty] | CM_WSNI | 100%
501261 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS1 | 2015-11-09 | 2021-11-08 | 2021-12-21 | 2022-10-25 | 2023-01-18 | Highland | 0 | 20908 | 120422.68 | 6352.32 | -6152.14 | 0 | 0 | 141530.86 | 0 | 141530.86 | 0 | [6 empty] | CM_WSNI | 100%
500785 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS2 | 2015-07-30 | 2016-12-15 | 2019-09-16 | 2020-01-31 | 2019-08-20 | Highland | 0 | 29700 | 11971 | 15859 | 1267.37 | 146970.29 | 0 | 205767.66 | 0 | 205767.66 | 0 | [6 empty] | CM_WSI | 100%
500742 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2015-08-25 | 2018-11-29 | 2018-12-10 | 2019-10-08 | 2020-01-14 | Highland | 0 | 33184 | 90616.72 | 165287.6 | 683823.37 | 271681.11 | 6869.37 | 1251462.17 | 3661.88 | 1255124.05 | 0 | [6 empty] | CM_WSNI | 100%
500754 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS6 | 2015-08-24 | 2016-09-08 | 2016-11-22 | 2017-07-31 | 2017-08-18 | Highland | 0 | 29132 | 242773.04 | 12877.36 | 13192.1 | 825.28 | 0 | 298799.78 | 0 | 298799.78 | 0 | [6 empty] | CM_WSNI | 100%
502588 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-05-03 | 2022-07-22 | 2022-11-04 | 2023-06-29 | 2023-09-29 | Highland | 0 | 0 | 12682.18 | 35274.87 | 574.41 | 0 | 0 | 48531.46 | 175993.01 | 224524.47 | 0 | [6 empty] | CM_WSNI | 100%
500894 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS6 | 2016-08-30 | 2017-03-27 | 2017-06-12 | 2017-09-01 | 2020-01-01 | Stirling | 0 | 12882.16 | 11217.33 | 129321.2 | 9.11 | 0 | 0 | 153429.8 | 0 | 153429.8 | 163939.7391 | [6 empty] | WR6 | 100% | bar: Regulatory Outputs OMG-13
402174 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-07-11 | 2012-08-29 | 2012-11-16 | 2014-10-28 | 2014-10-28 | Scottish Water Wide | 354500.37 | -4497.15 | -483.48 | 0 | 0 | 0 | 0 | -4980.63 | 0 | 349519.74 | 0 | [6 empty] | CM_WSI | 100%
501642 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS2 | 2017-03-29 | 2018-12-21 | 2019-05-15 | 2019-08-20 | 2019-11-20 | Argyll and Bute-Cowal & Bute | 0 | 2511.63 | 10076.66 | 14013.35 | 5020.971 | 0 | 0 | 31622.611 | 0 | 31622.611 | 132650.7376 | [6 empty] | DW25P | 100%
404082 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2015-01-27 | 2019-01-28 | 2019-02-28 | 2020-10-30 | 2021-02-05 | Argyll and Bute-Cowal & Bute | 6104 | 213592 | 272674.27 | 239157.51 | 980714.14 | 1213508.42 | 1033410.72 | 3953057.06 | 150052.23 | 4109213.29 | 0 |  |  |  |  | 28400.0004 |  | CM_WSNI | 100%
501305 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-12-23 | 2015-12-23 | 2016-02-01 | 2016-06-13 | 2016-06-13 | Argyll and Bute-Cowal & Bute | 0 | 814140.26 | 62332.93 | 124.77 | 0 | 0 | 0 | 876597.96 | 0 | 876597.96 | 0 | [6 empty] | CM_WSNI | 100%
501306 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2015-12-23 | 2015-12-23 | 2016-04-28 | 2019-07-25 | 2019-10-25 | Argyll and Bute-Cowal & Bute | 0 | 257453.52 | 75521.46 | 0 | 5428.27 | 0 | 0 | 338403.25 | 0 | 338403.25 | 0 | [6 empty] | CM_WSNI | 100%
501307 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWMD | Supply Resilience | MS7 | 2015-12-23 | 2015-12-23 | 2016-02-01 | 2016-03-01 | 2016-03-01 | Argyll and Bute-Cowal & Bute | 0 | 275834 | -22546.83 | 0 | 0 | 0 | 0 | 253287.17 | 0 | 253287.17 | 639260.3798 | [6 empty] | CM_WSNI | 30% | CS16WR | 70% | bar: Regulatory Outputs OMG-07
500039 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-04-09 | 2015-11-17 | 2015-11-17 | 2015-11-17 | 2016-10-03 | Argyll and Bute-Cowal & Bute | 0 | 627.97 | 0 | 0 | 0 | 0 | 0 | 627.97 | 0 | 627.97 | 0 | [6 empty] | CM_WSI | 100%
046312 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2008-11-07 | 2010-08-16 | 2010-09-14 | 2013-01-14 | 2013-03-28 | Argyll and Bute-Cowal & Bute | 6902178.02 | 58596.47 | 26155.33 | 0 | 0 | 0 | 0 | 84751.8 | 0 | 6986929.82 | 74877 | [6 empty] | DW3C | 100%
403679 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-02-03 | 2015-06-22 | 2015-07-20 | 2015-11-10 | 2015-11-10 | East Ayrshire | 39781 | 268451 | 39844.62 | -282.78 | 0 | 0 | 0 | 308012.84 | 0 | 347793.84 | 0 | [6 empty] | CM_WSI | 100%
403717 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-02-27 | 2015-01-29 | 2015-04-20 | 2016-03-11 | 2016-03-11 | Argyll and Bute-North Argyll | 93778 | 774209 | 0 | 0 | -4605.68 | 0 | 0 | 769603.32 | 0 | 863381.32 | 0 | [6 empty] | CM_WSI | 100%
001286 | Q&S2 | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2001-12-14 | 2004-04-28 | 2004-03-22 | 2007-10-12 | 2008-04-22 | East Dunbartonshire | 120381045.78 | 4873.68 | 266.25 | 0 | 0 | 0 | 0 | 5139.93 | 0 | 120386185.71 | 0 | [6 empty] | DW4 | 33.33% | DW1 | 33.33% | DW3 | 33.34%
403164 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-01-07 | 2014-06-25 | 2014-06-25 | 2014-11-17 | 2014-11-17 | Angus | 766237.65 | 71820.14 | -892.53 | 0 | 0 | 0 | 0 | 70927.61 | 0 | 837165.26 | 0 | [6 empty] | CM_WSI | 100%
500107 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS4 | 2015-03-20 | 2016-12-20 | 2017-01-23 | 2018-12-19 | 2019-04-25 | Scottish Water Wide | 0 | 8923 | 84596.82 | 252787.18 | 172653 | 11667 | 0 | 530627 | 0 | 530627 | 117516.8622 | [6 empty] | CS16D | 26.38% | EC10H | 73.62%
404131 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS6 | 2016-06-23 | 2016-10-10 | 2016-10-31 | 2018-03-01 | 2018-03-30 | Highland | 0 | 0 | 3283025.81 | 2547613.51 | 109665.25 | 9929.45 | 9548.99 | 5959783.01 | 0 | 5959783.01 | 0 |  |  |  |  | 43200 |  | DW23 | 50% | DW3A | 50%
045396 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-07-16 | 2009-11-02 | 2011-03-28 | 2016-07-07 | 2016-07-07 | Highland | 8254375.06 | 2493608.96 | 475527.38 | 184077.335 | 21.29 | 0 | 0 | 3153234.965 | 0 | 11407610.025 | 1972445.76 | [6 empty] | WG4 | 50% | WG1 | 50%
045505 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS6 | 2008-11-20 | 2010-06-14 | 2011-01-18 | 2015-03-01 | 2016-03-01 | Dumfries and Galloway | 47476169 | 669547.98 | 589133.02 | 152614 | 297435.41 | 60940 | 0 | 1769670.41 | 0 | 49245839.41 | -1670236.1752 |  |  |  |  | 363542 |  | CM_WSI | 0.1844% | EC01A | 49.91% | EC03A | 49.91% | bar: Regulatory Outputs OMG-07
503251 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2021-11-30 | 2022-10-24 | 2023-01-19 | 2024-10-11 | 2025-01-13 | Perth and Kinross | 0 | 0 | 0 | 0 | 32629.24 | 6514.02 | 6488.78 | 45632.04 | 9954367.93 | 9999999.97 | 0 | [6 empty] | CM_WSNI | 100%
502329 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWD | Reservoirs | MS0 | 2018-07-31 | 2020-05-25 | 2020-09-16 | 2021-12-01 | 2022-03-01 | Inverclyde | 0 | 0 | 38455.43 | 5660.8 | 230589.15 | 216162.97 | 1995510.08 | 2486378.43 | 2339621.53 | 4825999.96 | 876707.951 | [6 empty] | WR6 | 100% | bar: Regulatory Outputs OMG-13
501568 | IR18 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2016-05-20 | 2018-01-23 | 2018-02-08 | 2018-08-10 | 2018-08-10 | Perth and Kinross | 0 | 10754.35 | 14061.07 | 102799 | 59719.46 | 0 | 0 | 187333.88 | 0 | 187333.88 | 0 | [6 empty] | CM_WSI | 100%
502558 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2018-01-26 | 2018-01-26 | 2018-03-07 | 2018-04-04 | 2018-04-04 | Perth and Kinross | 0 | 0 | 0 | 39626.17 | 319000.9629 | 1018.27 | 746.24 | 360391.6429 | 75.49 | 360467.1329 | 0 | [6 empty] | CM_WSI | 100%
500191 | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWD | WFD | MS5 | 2015-03-20 | 2018-09-26 | 2018-10-01 | 2019-03-01 | 2019-03-01 | Stirling | 0 | 2325 | 458 | 4286 | 141 | 9198.5 | 486.93 | 16895.43 | 314.51 | 17209.94 | 98491.1522 | [6 empty] | WR2A | 100% | bar: Regulatory Outputs OMG-20
501634 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS5 | 2016-03-31 | 2016-09-29 | 2016-09-30 | 2017-10-01 | 2019-03-01 | Highland | 0 | 20607 | 3751345.93 | 823117.045 | 538228.245 | 3303.01 | 3398.79 | 5140000.02 | 0 | 5140000.02 | 1858328.8226 | [6 empty] | DW23 | 100% | bar: Regulatory Outputs OMG-01
046176 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-29 | 2014-05-28 | 2014-08-01 | 2014-09-12 |  | Dumfries and Galloway | 610873.75 | 473.75 | 0 | 0 | 0 | 0 | 0 | 473.75 | 0 | 611347.5 | 0 | [6 empty] | CM_WWNI | 100%
503309 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-03-18 | 2023-09-07 | 2024-01-05 | 2025-01-02 | 2025-04-04 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 30748.661 | 9991.25 | 31199.89 | 71939.801 | 76118.8 | 148058.601 | 148885.7057 | [6 empty] | SG1 | 100%
046850 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2011-03-16 | 2011-07-12 | 2013-05-20 | 2013-09-30 | Highland | 3736788.25 | 6078.23 | 0 | 0 | 0 | 0 | 0 | 6078.23 | 0 | 3742866.48 | 7727 | [6 empty] | DW23 | 100%
046869 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-05-07 | 2013-07-17 | 2013-07-17 | 2016-03-17 | 2016-05-27 | Dumfries and Galloway | 3757654 | 8135 | 21576 | 18827.623 | 21276.11 | 0 | 0 | 69814.733 | 0 | 3827468.733 | 21665.0003 | [6 empty] | DW9A | 0.2652% | DW3G | 33.23% | DW3F | 33.25% | DW3A | 33.25%
402838 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2012-08-21 | 2016-05-30 | 2016-09-08 | 2017-02-24 | 2017-02-24 | Argyll and Bute-North Argyll | 48500 | 27048.37 | 382722.89 | 33529.82 | -14659.036 | 0 | 0 | 428642.044 | 0 | 477142.044 | 0 | [6 empty] | SG1 | 100%
500813 | Q&S4 | Improving drinking water availability and resilience of service | Pressure |  |  | Water |  | SWMD | Pressure | MS6 | 2015-08-07 | 2017-08-18 | 2017-10-02 | 2017-11-07 | 2017-11-07 | Fife | 0 | 4525.56 | 22464.67 | 33779.77 | -2158.18 | 2081.38 | 1818.63 | 62511.83 | 0 | 62511.83 | 365739.3876 | [6 empty] | CS1B | 14.49% | CS1 | 85.51%
503099 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS0 | 2018-12-21 | 2020-08-17 | 2020-11-09 | 2021-09-29 | 2022-01-12 | Fife | 0 | 0 | 0 | 0 | 20324.39 | 16423.28 | 168637.79 | 205385.46 | 195079.57 | 400465.03 | 587726.5342 | [6 empty] | WG5 | 100%
501662 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-09-20 | 2018-02-27 | 2018-03-21 | 2019-09-02 | 2019-09-02 | Argyll and Bute-North Argyll | 0 | 0 | 7020.53 | 191786.47 | 456186 | 10000.04 | 2399.89 | 667392.93 | 0.06 | 667392.99 | 0 | [6 empty] | CM_WWI | 100%
501571 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2016-07-14 | 2019-04-15 | 2019-05-20 | 2019-08-09 | 2019-11-11 | Argyll and Bute-Cowal & Bute | 0 | 2511.63 | 17.09 | 454.02 | 833.51 | 0 | 0 | 3816.25 | 0 | 3816.25 | 72673.918 | [6 empty] | DW25P | 100%
502574 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2021-06-04 | 2022-01-17 | 2022-03-28 | 2023-03-09 | 2023-06-09 | Argyll and Bute-Cowal & Bute | 0 | 0 | 20930.23 | 0 | 5171.835 | 10977.54 | 10934.99 | 48014.595 | 951957.18 | 999971.775 | 148885.7057 | [6 empty] | WG1 | 100%
503132 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2021-04-01 | 2022-09-14 | 2023-01-09 | 2024-01-04 | 2024-04-05 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 28088.625 | 5894.64 | 19136.02 | 53119.285 | 1047199.97 | 1100319.255 | 0 | [6 empty] | CM_WWNI | 100%
402184 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-06-28 | 2012-09-07 | 2013-03-04 | 2014-02-27 | 2014-02-27 | North Ayrshire | 395929.97 | 167.23 | 0 | 0 | 0 | 0 | 0 | 167.23 | 0 | 396097.2 | 0 | [6 empty] | CM_WSI | 100%
502395 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-05-03 | 2022-03-28 | 2022-06-01 | 2023-01-03 | 2023-01-03 | Falkirk | 0 | 0 | 7000 | 13292.48 | 5801.86 | 0 | 0 | 26094.34 | 595905.67 | 622000.01 | 0 | [6 empty] | CM_WSI | 100%
403046 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-23 | 2012-11-22 | 2013-01-14 | 2013-09-02 |  | Na H-Eileanan an Iar | 303015 | 11921.76 | 0 | 0 | 0 | 0 | 0 | 11921.76 | 0 | 314936.76 | 0 | [6 empty] | CM_WSI | 100%
500832 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2015-10-28 | 2017-12-21 | 2018-02-13 | 2019-03-01 | 2019-11-01 | Dumfries and Galloway | 0 | 145996 | -4380.77 | 38810.28 | 155408.67 | 17256.72 | 0 | 353090.9 | 0 | 353090.9 | 592374.1303 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 97.72
502837 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-18 | 2027-12-06 | 2028-04-04 | 2029-03-30 | 2029-07-02 | Highland | 0 | 0 | 0 | 21346.13 | 1340.34 | 27313.51 | 0 | 49999.98 | 7949999.9 | 7999999.88 | 148885.7057 | [6 empty] | WG1 | 100%
402627 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-04-16 | 2013-01-08 | 2013-06-03 | 2014-02-04 |  | Dumfries and Galloway | 329482 | 435.53 | 0 | 0 | 0 | 0 | 0 | 435.53 | 0 | 329917.53 | 0 | [6 empty] | CM_WWNI | 100%
403903 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS3 | 2011-03-29 | 2016-02-29 | 2017-07-21 | 2019-05-01 | 2019-06-01 | Na H-Eileanan an Iar | 124155 | 789610 | 533484.34 | 6194438.82 | 4250210.23 | 167295.71 | 13625.06 | 11948664.16 | 15586.65 | 12088405.81 | 5043338.9997 |  |  |  |  | 230210.0004 |  | DW25 | 8.1% | DW13 | 14% | DW23 | 14% | DW3G | 14% | CM_WSNI | 49.9% | bar: Regulatory Outputs OMG-03
046870 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-05-28 | 2015-03-27 | 2014-11-28 | 2014-11-28 | 2014-11-28 | Na H-Eileanan an Iar | 877949.16 | 3032.46 | -1594.22 | 0 | 0 | 0 | 0 | 1438.24 | 0 | 879387.4 | 0 | [6 empty] | DW3G | 100%
501248 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2015-12-07 | 2016-07-19 | 2016-08-22 | 2017-05-23 | 2017-05-23 | Dumfries and Galloway | 0 | 7799 | 315643.03 | 74820.3 | 385 | 729.21 | 279.81 | 399656.35 | 0 | 399656.35 | 0 | [6 empty] | CM_WSI | 100%
500161 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS4 | 2015-03-19 | 2016-05-30 | 2016-08-05 | 2019-02-05 | 2019-06-28 | Dumfries and Galloway | 0 | 11300 | 21721 | 19810.63 | 76500 | 465.37 | 0 | 129797 | 0 | 129797 | 71378.7735 | [6 empty] | EC01G | 2.08% | CS16D | 21.64% | EC10E | 27.46% | EC01D | 48.82%
500496 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-07-21 | 2018-10-30 | 2018-10-30 | 2019-06-26 | 2019-06-27 | Dumfries and Galloway | 0 | 44415 | 307872.31 | 162492.04 | 858332.62 | 1031878.3 | 39156.16 | 2444146.43 | 10055.67 | 2454202.1 | 0 |  |  |  |  | 30840 |  | CM_WWNI | 100%
503387 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-04-25 | 2023-03-02 | 2023-07-05 | 2023-12-26 | 2024-03-27 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 76108.55 | 20049.21 | 23753.59 | 119911.35 | 38695.31 | 158606.66 | 148885.7057 | [6 empty] | SG1 | 100%
502127 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2016-04-08 | 2016-04-08 | 2016-04-08 | 2017-03-30 | 2017-03-30 | Scottish Water Wide | 0 | 0 | 1046258 | -15856 | 0 | 0 | 0 | 1030402 | 0 | 1030402 | 0 | [6 empty] | CM_M&G | 100%
401016 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-04-21 | 2010-06-14 | 2010-06-21 | 2016-06-23 |  | Scottish Water Wide | 1153954.54 | -23570 | -11683.9 | 0 | 0 | 0 | 0 | -35253.9 | 0 | 1118700.64 | 0 | [6 empty] | CM_M&G | 100%
402042 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2011-03-10 | 2011-03-31 | 2011-05-03 | 2016-06-23 |  | Scottish Water Wide | 8844315.74 | -53785.54 | 0 | 0 | 0 | 0 | 0 | -53785.54 | 0 | 8790530.2 | 0 | [6 empty] | CM_M&G | 100%
403467 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2013-04-30 | 2013-04-30 | 2013-05-07 | 2016-06-23 |  | Scottish Water Wide | 5935188 | -785393.05 | -23064.31 | 0 | 0 | 0 | 0 | -808457.36 | 0 | 5126730.64 | 0 | [6 empty] | CM_M&G | 100%
401017 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-04-21 | 2010-06-14 | 2010-06-21 | 2016-06-23 |  | Scottish Water Wide | 5615967.07 | 666546.32 | -26464.71 | 0 | 0 | 0 | 0 | 640081.61 | 0 | 6256048.68 | 0 | [6 empty] | CM_M&G | 100%
401069 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-06-28 | 2015-03-17 | 2015-03-17 | 2016-06-23 |  | Scottish Water Wide | 96405 | -49689.01 | 373.95 | 0 | 0 | 0 | 0 | -49315.06 | 0 | 47089.94 | 0 | [6 empty] | CM_M&G | 100%
501203 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2016-08-26 | 2018-08-01 | 2018-08-31 | 2020-06-05 | 2020-06-08 | Fife | 0 | 5978.09 | 84186.42 | 292354.42 | 555670.51 | 842544.11 | 23110.3 | 1803843.85 | 11241.22 | 1815085.07 | 0 |  |  |  |  | 41250 |  | CM_WSNI | 100%
503105 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2018-05-28 | 2018-05-29 | 2018-06-18 | 2018-06-18 | 2018-06-18 | Fife | 0 | 0 | 0 | 0 | 339627.811 | 0 | 0 | 339627.811 | 0 | 339627.811 | 0 | [6 empty] | CM_WSNI | 100%
500972 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS5 | 2015-11-03 | 2015-11-06 | 2015-12-14 | 2016-06-01 | 2016-09-01 | Fife | 0 | 32100.94 | 41913.47 | 63 | 321.9 | 0 | 0 | 74399.31 | 0 | 74399.31 | 795054.281 | [6 empty] | DW3C | 100% | bar: Regulatory Outputs OMG-01
500494 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2015-05-28 | 2018-03-30 | 2018-06-28 | 2019-11-18 | 2019-11-18 | All West Unitary Authorities | 0 | 90181 | 102346.02 | 167120.91 | 922759.62 | 211288.15 | 6961.42 | 1500657.12 | 4469.39 | 1505126.51 | 0 | [6 empty] | CM_WSNI | 100%
502324 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2016-09-02 | 2016-09-14 | 2016-09-28 | 2017-05-05 | 2017-05-05 | Glasgow City | 0 | 0 | 1392865.62 | -19722.01 | 680.42 | 0 | 0 | 1373824.03 | 0 | 1373824.03 | 0 | [6 empty] | CM_WWI | 100%
403941 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2014-10-06 | 2014-10-06 | 2014-10-06 | 2019-07-15 |  | Glasgow City | 11754.35 | 829.65 | 6199.85 | 22874.835 | 2226.895 | 0 | 0 | 32131.23 | 0 | 43885.58 | 0 | [6 empty] | CM_WWNI | 100%
403122 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-22 | 2013-02-20 | 2013-02-20 | 2014-03-14 |  | Glasgow City | 2031916.02 | 0 | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 2032066.02 | 0 | [6 empty] | CM_WWI | 100%
502280 | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater |  | SWMD | Sludge | MS1 | 2017-08-18 | 2019-09-09 | 2019-11-25 | 2020-10-01 | 2021-03-01 | Highland | 0 | 0 | 23204.84 | 97916.77 | 112919.88 | 346153.1 | 456984.84 | 1037179.43 | 3065.5 | 1040244.93 | 311328.5233 | [6 empty] | LA01 | 100% | bar: Regulatory Outputs OMG-24
502669 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2017-04-27 | 2017-04-27 | 2017-04-27 | 2019-04-19 | 2019-04-23 | Scottish Water Wide | 0 | 0 | 0 | 145865.69 | 40634.55 | 2250 | 0 | 188750.24 | 0 | 188750.24 | 0 | [6 empty] | CM_M&G | 100%
404105 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-03-06 | 2015-05-19 | 2015-05-27 | 2015-05-28 | 2015-06-24 | East Renfrewshire | 19.98 | 338622.1 | 0 | 0 | 0 | 0 | 0 | 338622.1 | 0 | 338642.08 | 0 | [6 empty] | CM_WSI | 100%
501410 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW0 | 2021-04-01 | 2021-11-26 | 2022-02-23 | 2022-07-07 | 2022-10-07 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67316.01 | 67316.01 | 0 | [6 empty] | CM_WWI | 100%
402606 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-28 | 2012-11-20 | 2013-01-07 | 2015-04-01 |  | All East Unitary Authorities | 125354 | 2143.35 | 299.59 | 14.84 | 0 | 0 | 0 | 2457.78 | 0 | 127811.78 | 0 | [6 empty] | CM_M&G | 100%
501749 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW1 | 2021-06-09 | 2022-02-24 | 2022-05-13 | 2022-09-26 | 2022-12-27 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80940.04 | 80940.04 | 0 | [6 empty] | CM_WSNI | 5.882% | CM_M&G | 17.65% | CM_WWNI | 35.29% | CM_WWI | 41.18%
500236 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-07-27 | 2016-07-27 | Aberdeenshire | 0 | 43391.93 | 0 | 0 | 0 | 0 | 0 | 43391.93 | 0 | 43391.93 | 148885.7057 | [6 empty] | SG1 | 100%
503443 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW0 | 2019-11-22 | 2020-10-19 | 2021-01-12 | 2021-08-02 | 2021-11-02 | Midlothian | 0 | 0 | 0 | 0 | 12365.91 | 70546.62 | 285901.94 | 368814.47 | 243551.5 | 612365.97 | 0 | [6 empty] | CM_WWI | 100%
503173 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-04-05 | 2022-03-14 | 2022-06-02 | 2022-12-28 | 2023-03-30 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791139.85 | 1791139.85 | 0 | [6 empty] | CM_WSI | 100%
502205 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-09-22 | 2019-04-29 | 2019-04-29 | 2019-04-29 | 2019-04-29 | Aberdeenshire | 0 | 0 | 16896.43 | 5114.745 | 6398.485 | 0 | 0 | 28409.66 | 0 | 28409.66 | 0 | [6 empty] | CM_WSI | 100%
503032 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2019-05-31 | 2021-01-18 | 2021-05-20 | 2022-08-12 | 2022-11-14 | Moray | 0 | 0 | 0 | 0 | 66861.7705 | 139720.15 | 408191.61 | 614773.5305 | 1646665.48 | 2261439.0105 | 0 | [6 empty] | CM_WSNI | 100%
402802 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-07-23 | 2013-01-24 | 2013-02-11 | 2013-03-31 | 2013-03-31 | Moray | 333936.25 | 585.56 | 0 | 0 | 0 | 0 | 0 | 585.56 | 0 | 334521.81 | 0 | [6 empty] | CS1 | 100%
403409 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2013-03-01 | 2015-06-10 | 2015-06-10 | 2015-06-10 | 2015-06-10 | City of Edinburgh | 560826.99 | -380973.56 | 0 | 0 | 0 | 0 | 0 | -380973.56 | 0 | 179853.43 | 0 | [6 empty] | CC1W | 100%
502616 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-05-06 | 2022-01-31 | 2022-04-15 | 2022-08-29 | 2022-11-29 | Argyll and Bute-North Argyll | 0 | 0 | 5144 | 0 | -4.69 | 3184.86 | 3172.51 | 11496.68 | 234498.62 | 245995.3 | 0 | [6 empty] | CM_WSI | 100%
500480 | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWMD | Renewable power | MS7 | 2015-05-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | Fife | 0 | 40100.85 | 54.86 | 0 | 0 | 0 | 0 | 40155.71 | 0 | 40155.71 | 764721.6298 | [6 empty] | I2S_WI | 100%
502190 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2016-08-29 | 2018-01-29 | 2018-03-26 | 2018-07-27 | 2018-07-27 | Fife | 0 | 0 | 12095 | 222361 | 419062.9284 | 0 | 0 | 653518.9284 | 0 | 653518.9284 | 0 | [6 empty] | CM_WWI | 100%
501313 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-07-27 | 2016-08-30 | Fife | 0 | 10465.12 | 3234.3 | 0 | 0 | 0 | 0 | 13699.42 | 0 | 13699.42 | 148885.7057 | [6 empty] | SG1 | 100%
502800 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2017-07-27 | 2018-08-31 | 2018-08-31 | 2018-09-03 | 2018-09-03 | Glasgow City | 0 | 0 | 0 | 447693.5175 | -447248.3975 | 0 | 0 | 445.12 | 0 | 445.12 | 10994109.1109 | [6 empty] | EC01A | 100%
502963 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS0 | 2017-11-09 | 2019-06-24 | 2019-08-26 | 2020-08-12 | 2020-08-13 | Scottish Water Wide | 0 | 0 | 0 | 4754.029 | 36211.751 | 86341.84 | 75352.41 | 202660.03 | 1939.16 | 204599.19 | 0 | [6 empty] | CM_M&G | 100%
502964 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS0 | 2017-11-09 | 2020-01-20 | 2020-03-23 | 2021-02-05 | 2021-05-10 | Scottish Water Wide | 0 | 0 | 0 | 8432.497 | 55304.823 | 14666.25 | 72485.18 | 150888.75 | 19757.22 | 170645.97 | 0 | [6 empty] | CM_M&G | 100%
502965 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS0 | 2017-11-09 | 2020-09-28 | 2021-03-22 | 2021-09-17 | 2021-09-17 | Scottish Water Wide | 0 | 0 | 0 | 17056.54 | 11932.59 | 0 | 108397.69 | 137386.82 | 56843.16 | 194229.98 | 0 | [6 empty] | CM_M&G | 100%
502966 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS0 | 2017-11-10 | 2020-01-23 | 2020-03-23 | 2020-11-13 | 2021-02-19 | Scottish Water Wide | 0 | 0 | 0 | 16124.79 | 23852.91 | 122148.64 | 369060.48 | 531186.82 | 25674.32 | 556861.14 | 0 | [6 empty] | CM_M&G | 100%
502897 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2017-10-09 | 2017-10-09 | 2018-04-02 | 2021-03-31 | 2021-07-07 | Scottish Water Wide | 0 | 0 | 0 | 17970 | 12530 | 40000 | 154500 | 225000 | 0 | 225000 | 0 | [6 empty] | CM_M&G | 100%
501593 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2016-07-19 | 2018-12-05 | 2019-02-11 | 2020-02-25 | 2020-06-02 | East Ayrshire | 0 | 0 | 88307 | 125426 | 729553 | 776416.83 | 0 | 1719702.83 | 12910 | 1732612.83 | 0 |  |  |  |  | 16059.9996 |  | CM_WWNI | 100%
401331 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-09-24 | 2014-01-29 | 2014-04-25 | 2015-01-26 | 2015-01-26 | Highland | 463211 | 25154 | -1054.84 | 0 | 0 | 0 | 0 | 24099.16 | 0 | 487310.16 | 1367.4 | [6 empty] | CM_WWI | 40% | CS11A | 60%
500157 | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-19 | 2015-09-27 | 2017-03-01 | 2017-04-24 | 2017-04-24 | Highland | 0 | 13260 | 743.08 | -4250.7 | 0 | 0 | 0 | 9752.38 | 0 | 9752.38 | 72474.3726 | [6 empty] | CS11 | 100%
045545 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-29 | 2011-08-22 | 2011-11-28 | 2012-09-30 | 2013-01-24 | Aberdeenshire | 571660.02 | 1298.08 | 0 | 0 | 0 | 0 | 0 | 1298.08 | 0 | 572958.1 | 0 | [6 empty] | WQ01 | 100%
500221 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS6 | 2015-03-20 | 2016-03-30 | 2016-06-23 | 2017-01-01 | 2018-02-01 | Highland | 0 | 193.5 | 2448.07 | 302.75 | 1272.85 | 0 | 0 | 4217.17 | 0 | 4217.17 | 5519.4182 | [6 empty] | DW5FS | 100% | bar: Regulatory Outputs OMG-02
045353 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-09-14 | 2011-10-03 | 2013-01-07 | 2013-01-31 | Na H-Eileanan an Iar | 945001.43 | 2556.53 | 0 | 0 | 0 | 0 | 0 | 2556.53 | 0 | 947557.96 | 0 | [6 empty] | DW23 | 100%
501277 | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Water |  | SWD | Energy efficiency | MS7 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2018-09-03 | 2018-09-03 | Angus | 0 | 14278.04 | -12614.89 | 2538.92 | 0 | 0 | 0 | 4202.07 | 0 | 4202.07 | 0 | [6 empty] | I2S_WI | 100%
501225 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS5 | 2016-02-22 | 2018-04-30 | 2018-06-11 | 2018-12-21 | 2018-12-21 | North Lanarkshire | 0 | 5630.61 | 134369.39 | 169757 | 781213.97 | 13704.04 | 2249.96 | 1106924.97 | 0 | 1106924.97 | 0 | [6 empty] | CM_WWI | 100%
503230 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW1 | 2021-05-27 | 2022-03-18 | 2022-06-06 | 2023-01-09 | 2023-04-11 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 11847.825 | 7135.14 | 7107.49 | 26090.455 | 474706.28 | 500796.735 | 0 | [6 empty] | CM_WWI | 100%
046225 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-10-01 | 2012-06-30 | 2012-06-30 | 2014-03-05 |  | Scottish Water Wide | 523461.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 523461.15 | 0 | [6 empty] | CM_WSI | 100%
046226 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-10-01 | 2012-07-18 | 2012-07-23 | 2015-06-30 | 2015-10-28 | Scottish Water Wide | 2052507 | 126185.54 | -112266.66 | 0 | 0 | 0 | 0 | 13918.88 | 0 | 2066425.88 | 0 | [6 empty] | CM_WSI | 100%
046677 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-19 | 2012-03-26 | 2012-05-28 | 2013-09-13 |  | City of Edinburgh | 300370 | -509.56 | 0 | 0 | 0 | 0 | 0 | -509.56 | 0 | 299860.44 | 0 | [6 empty] | CM_WSI | 100%
046076 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-06-10 | 2013-03-25 | 2013-04-25 | 2014-11-03 |  | Na H-Eileanan an Iar | 384000 | 0 | -492.87 | 0 | 0 | 0 | 0 | -492.87 | 0 | 383507.13 | 0 | [6 empty] | CM_WSI | 100%
046141 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2010-10-28 | 2011-11-21 | 2013-01-28 |  | Aberdeenshire | 455036 | -1144.49 | 0 | 0 | 0 | 0 | 0 | -1144.49 | 0 | 453891.51 | 0 | [6 empty] | CM_WSI | 100%
046679 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-12 | 2012-09-26 | 2012-11-19 | 2014-02-26 |  | Dumfries and Galloway | 2386023.73 | 1542.16 | 0 | 0 | 0 | 0 | 0 | 1542.16 | 0 | 2387565.89 | 0 | [6 empty] | CM_WSI | 100%
046655 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-19 | 2012-10-26 | 2012-11-12 | 2013-07-11 |  | Angus | 355920 | 34.33 | 0 | 0 | 0 | 0 | 0 | 34.33 | 0 | 355954.33 | 0 | [6 empty] | CM_WSI | 100%
046171 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-08-08 | 2012-08-29 | 2012-09-24 | 2013-05-17 |  | Shetland Islands | 420000 | -11611.7 | 0 | 0 | 0 | 0 | 0 | -11611.7 | 0 | 408388.3 | 0 | [6 empty] | CM_WSI | 100%
046136 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2012-09-21 | 2012-11-19 | 2013-07-15 |  | Dumfries and Galloway | 563338 | -921.46 | 0 | 0 | 0 | 0 | 0 | -921.46 | 0 | 562416.54 | 0 | [6 empty] | CM_WSI | 100%
046072 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-06-10 | 2012-09-26 | 2013-02-25 | 2014-01-21 | 2014-02-03 | Dumfries and Galloway | 1013817 | 4420.37 | 0 | 0 | 0 | 0 | 0 | 4420.37 | 0 | 1018237.37 | 0 | [6 empty] | CM_WSI | 100%
046145 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2008-07-31 | 2013-06-19 | 2013-06-28 | 2017-09-28 |  | Moray | 1407177 | 0 | 128759.04 | 204063.96 | 5237 | 4763 | 0 | 342823 | 0 | 1750000 | 0 | [6 empty] | CM_WSI | 100%
046071 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2008-06-26 | 2010-11-15 | 2011-03-07 | 2020-04-24 |  | Aberdeen City | 874096 | -71791 | 5545 | 69038.02 | 198616.78 | 293759.85 | 30735.29 | 525903.94 | 0 | 1399999.94 | 0 | [6 empty] | CM_WSI | 100%
046135 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2010-10-28 | 2011-03-07 | 2013-04-25 |  | Aberdeenshire | 425106 | -1635.83 | 0 | 0 | 0 | 0 | 0 | -1635.83 | 0 | 423470.17 | 0 | [6 empty] | CM_WSI | 100%
045657 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2009-03-12 | 2012-09-26 | 2013-01-28 | 2019-03-12 | 2019-03-12 | Dumfries and Galloway | 3230378 | 42743.65 | 1567.53 | 30689 | 7615.96 | 0 | 0 | 82616.14 | 42260.28 | 3355254.42 | 0 | [6 empty] | CM_WSI | 100%
046139 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2010-10-25 | 2011-03-21 | 2012-11-20 |  | Perth and Kinross | 206000 | -3660.02 | 0 | 0 | 0 | 0 | 0 | -3660.02 | 0 | 202339.98 | 0 | [6 empty] | CM_WSI | 100%
046689 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-19 | 2012-09-26 | 2013-01-25 | 2014-07-07 | 2014-10-01 | Dumfries and Galloway | 662664 | -2926.11 | 71 | 0 | 0 | 0 | 0 | -2855.11 | 0 | 659808.89 | 0 | [6 empty] | CM_WSI | 100%
046690 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-30 | 2013-03-06 | 2013-06-18 | 2014-05-23 | 2014-08-14 | Dumfries and Galloway | 453109 | -570.16 | 71 | 0 | 0 | 0 | 0 | -499.16 | 0 | 452609.84 | 0 | [6 empty] | CM_WSI | 100%
046672 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-08-08 | 2012-10-17 | 2012-11-05 | 2015-08-24 |  | Orkney Islands | 1098985 | -12669 | 2474.6 | 12012.8875 | 0 | 0 | 0 | 1818.4875 | 0 | 1100803.4875 | 0 | [6 empty] | CM_WSI | 100%
046070 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2008-06-26 | 2012-09-26 | 2012-11-19 | 2017-03-03 |  | Dumfries and Galloway | 4168789 | 10234 | 157961.7 | 24486.04 | 124757.63 | 13636.1 | 0 | 331075.47 | 0 | 4499864.47 | 0 | [6 empty] | CM_WSI | 100%
046169 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2012-10-24 | 2012-10-30 | 2013-09-16 |  | Na H-Eileanan an Iar | 319626.61 | 65.62 | 0 | 0 | 0 | 0 | 0 | 65.62 | 0 | 319692.23 | 0 | [6 empty] | CM_WSI | 100%
046146 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2010-11-05 | 2011-03-21 | 2012-08-23 |  | Perth and Kinross | 947796 | -3555.72 | 0 | 0 | 0 | 0 | 0 | -3555.72 | 0 | 944240.28 | 0 | [6 empty] | CM_WSI | 100%
046147 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2008-07-31 | 2012-02-29 | 2012-04-16 | 2013-02-28 |  | Shetland Islands | 382746 | -2634.13 | 0 | 0 | 0 | 0 | 0 | -2634.13 | 0 | 380111.87 | 0 | [6 empty] | CM_WSI | 100%
046663 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-27 | 2012-08-29 | 2012-09-24 | 2013-10-22 |  | Perth and Kinross | 1239159 | 2415.68 | 0 | 0 | 0 | 0 | 0 | 2415.68 | 0 | 1241574.68 | 0 | [6 empty] | CM_WSI | 100%
045654 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-12 | 2012-08-29 | 2012-09-03 | 2013-06-24 |  | Aberdeenshire | 803271 | -1755.22 | 0 | 0 | 0 | 0 | 0 | -1755.22 | 0 | 801515.78 | 0 | [6 empty] | CM_WSI | 100%
046702 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-30 | 2013-07-31 | 2013-09-16 | 2014-07-15 |  | South Lanarkshire | 2047099 | 4617 | 1560.21 | 0 | 0 | 0 | 0 | 6177.21 | 0 | 2053276.21 | 0 | [6 empty] | CM_WSI | 100%
502672 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2017-06-28 | 2017-06-28 | 2017-09-29 | 2018-08-24 | 2018-08-24 | West Lothian | 0 | 0 | 0 | 361334.472 | 14574.078 | 380.01 | 378.52 | 376667.08 | 241.42 | 376908.5 | 0 | [6 empty] | CM_WSI | 100%
503035 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2018-02-20 | 2018-07-11 | 2018-07-12 | 2018-10-01 | 2018-10-01 | West Lothian | 0 | 0 | 0 | 2204.74 | 343195.65 | 4803.15 | 5688.5 | 355892.04 | 4382.56 | 360274.6 | 0 | [6 empty] | CM_M&G | 100%
500163 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS4 | 2015-03-19 | 2016-05-30 | 2016-08-19 | 2019-02-01 | 2019-06-01 | Highland | 0 | 11027 | 19421 | 42019 | 77480 | 1000 | 0 | 150947 | 0 | 150947 | 83133.1188 | [6 empty] | EC01G | 14.83% | EC01D | 85.17% | bar: Regulatory Outputs OMG-23
502674 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | Highland | 0 | 0 | 0 | 61811.81 | 0 | 0 | 0 | 61811.81 | 0 | 61811.81 | 0 | [6 empty] | CM_WSNI | 100%
500075 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-03-09 | 2015-03-20 | 2015-03-20 | 2016-02-26 | 2016-02-26 | Aberdeen City | 11002 | 2561.5 | 0 | 0 | 0 | 0 | 0 | 2561.5 | 0 | 13563.5 | 56353.7572 | [6 empty] | DW3C_S | 100%
500209 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS7 | 2015-03-27 | 2017-12-22 | 2017-12-27 | 2018-03-23 | 2018-03-28 | Aberdeen City | 0 | 1490 | 1413 | 68175.68 | 0 | 0 | 0 | 71078.68 | 0 | 71078.68 | 487361.8668 | [6 empty] | DW5FS | 34% | DW5 | 66%
500833 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2016-03-07 | 2017-12-21 | 2018-03-23 | 2019-12-01 | 2020-08-01 | Aberdeen City | 0 | 26277.48 | 28355.52 | 230298.718 | 212543.662 | 174353.17 | 11788.45 | 683617 | 0 | 683617 | 1108892.2641 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 174.54
500834 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2016-09-20 | 2018-09-18 | 2018-11-30 | 2019-09-01 | 2020-10-01 | Aberdeen City | 0 | 25559.07 | 15355.22 | 39111.93 | 105280.83 | 16233.41 | 23900.36 | 225440.82 | 0 | 225440.82 | 1175986.0804 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 72.17
500205 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS4 | 2015-03-27 | 2018-03-30 | 2018-03-30 | 2018-10-01 | 2019-12-01 | Aberdeen City | 0 | 3854 | 2406 | 149054 | 77028.66 | 752.31 | 0 | 233094.97 | 0 | 233094.97 | 1891283.8591 | [6 empty] | DW5FS | 100% | bar: Regulatory Outputs OMG-02
500835 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2016-03-07 | 2018-03-28 | 2018-06-19 | 2020-03-31 | 2020-10-28 | Aberdeen City | 0 | 24086.41 | 15578.59 | 267817.87 | 163863.62 | 266178.47 | 0 | 737524.96 | 0 | 737524.96 | 1128913.4445 | [6 empty] | DW5FS | 100%
502555 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS5 | 2016-03-31 | 2017-12-12 | 2017-12-12 | 2018-09-01 | 2019-03-01 | Aberdeen City | 0 | 0 | 6740.69 | 69935.22 | 225792.53 | 3653.85 | 760.36 | 306882.65 | 585.81 | 307468.46 | 403717.0829 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-01
502211 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS5 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-06-21 | 2017-08-15 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | DW25P | 100%
502373 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS0 | 2019-03-06 | 2020-03-16 | 2020-07-06 | 2020-11-11 | 2021-02-12 | Aberdeen City | 0 | 0 | 51929.3 | 62957.185 | 6238.5125 | 11878.95 | 76091.79 | 209095.7375 | 1506.18 | 210601.9175 | 403717.0829 | [6 empty] | DW25P | 100%
501297 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS0 | 2016-03-31 | 2020-02-17 | 2020-05-18 | 2020-11-16 | 2020-11-17 | Aberdeen City | 0 | 8707.77 | 2807.07 | 3217.705 | 5366.365 | 5821.93 | 85754.2 | 111675.04 | 0 | 111675.04 | 403717.0829 | [6 empty] | DW25P | 100%
502653 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2017-04-10 | 2017-08-24 | 2017-10-03 | 2018-03-16 | 2018-03-16 | Aberdeen City | 0 | 0 | 0 | 320759.47 | 2956.943 | 0 | 0 | 323716.413 | 0 | 323716.413 | 0 | [6 empty] | CM_WSNI | 100%
502312 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2017-03-23 | 2020-06-22 | 2020-10-05 | 2021-05-20 | 2021-07-29 | Aberdeen City | 0 | 0 | 4850.33 | 5970.72 | 30182.8035 | 6071.48 | 152447.72 | 199523.0535 | 674064.22 | 873587.2735 | 0 | [6 empty] | DW25T | 100%
502236 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS3 | 2016-05-30 | 2016-05-30 | 2016-09-05 | 2019-06-21 | 2019-08-16 | Aberdeen City | 0 | 0 | 35209.46 | 3323.5525 | 438.7775 | 11028.19 | 0 | 49999.98 | 0 | 49999.98 | 403717.0829 | [6 empty] | DW25P | 100%
502243 | IR18 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS0 | 2017-03-31 | 2019-09-16 | 2019-10-14 | 2020-05-14 | 2020-11-11 | Aberdeen City | 0 | 0 | 115578.93 | 137340.58 | 14528.352 | 930494.61 | 1573890.55 | 2771833.022 | 22209.38 | 2794042.402 | 0 | [6 empty] | CM_WSNI | 100%
501250 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2015-11-23 | 2015-11-23 | 2015-12-01 | 2017-06-01 | 2017-06-01 | Aberdeen City | 0 | 731045 | 762009.44 | 25517.02 | 2334.22 | 329.29 | 0 | 1521234.97 | 0 | 1521234.97 | 0 | [6 empty] | CM_WSNI | 100%
500836 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-10-31 | 2018-11-21 | 2018-11-21 | 2018-11-30 | 2018-11-30 | Aberdeen City | 0 | 12297.55 | 9157.79 | 9640.3 | 2336.14 | 0 | 0 | 33431.78 | 0 | 33431.78 | 469677.579 | [6 empty] | DW5FS | 100%
402964 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS0 | 2012-10-01 | 2020-01-27 | 2020-01-27 | 2020-01-27 | 2020-01-27 | City of Edinburgh | 41239 | 11000 | 49253.12 | 24707.88 | 29074 | 63726 | 0 | 177761 | 0 | 219000 | 229318.7788 | [6 empty] | CS11 | 100%
030509 | Q&S3A | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2005-12-01 | 2007-09-26 | 2008-01-25 | 2008-01-25 | 2008-06-12 | Scottish Borders | 185895.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185895.93 | 0 | [6 empty] | DW13 | 33.33% | DW3B | 33.33% | DW4A | 33.33%
045643 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-07-31 | 2012-01-30 | 2012-02-07 | 2012-01-31 |  | Scottish Borders | 281569.05 | 639.79 | 0 | 0 | 0 | 0 | 0 | 639.79 | 0 | 282208.84 | 0 | [6 empty] | CM_WSNI | 100%
500837 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-01-12 | 2017-03-23 | 2017-05-01 | 2018-10-01 | 2019-04-01 | Scottish Borders | 0 | 7616.67 | 33053.22 | 49167.6041 | 59880.6859 | 5016.35 | 0 | 154734.53 | 0 | 154734.53 | 238049.8446 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 34.53
500206 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS3 | 2015-03-27 | 2017-09-29 | 2017-09-29 | 2020-06-26 | 2021-03-30 | City of Edinburgh | 0 | 50989 | 124821.68 | 313228.22 | 666744.54 | 536795.3 | 588517.45 | 2281096.19 | 715544.71 | 2996640.9 | 3017945.1651 | [6 empty] | DW5 | 100%
500838 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS5 | 2016-08-03 | 2017-09-29 | 2017-10-02 | 2018-08-01 | 2019-03-01 | Midlothian | 0 | 1739.39 | 851.34 | 51301.9 | 108361.95 | 5000 | 0 | 167254.58 | 0 | 167254.58 | 39688.2714 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 6.28
501080 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-28 | 2022-01-17 | 2022-03-09 | 2022-08-05 | 2022-11-07 | West Lothian | 0 | 24192 | -7710 | 0 | 481 | 0 | 0 | 16963 | 0 | 16963 | 0 | [6 empty] | CM_WSI | 100%
501079 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2016-04-01 | 2023-07-18 | 2023-08-16 | 2024-03-21 | 2024-03-22 | City of Edinburgh | 0 | 23832 | 57340 | 47222 | -27721.18 | 0 | 0 | 100672.82 | 525848.77 | 626521.59 | 0 | [6 empty] | CM_WSI | 100%
402851 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-08-15 | 2012-11-27 | 2012-12-17 | 2013-03-28 | 2013-03-28 | City of Edinburgh | 89562.86 | 274.14 | 0 | 0 | 0 | 0 | 0 | 274.14 | 0 | 89837 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
403527 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS1 | 2013-07-18 | 2020-03-23 | 2020-06-24 | 2021-03-10 | 2021-03-10 | City of Edinburgh | 318833 | 39461 | 200122.78 | -76968.78 | 47293 | 144692.08 | 5106457.1 | 5461057.18 | 44247.01 | 5824137.19 | 229318.7788 | [6 empty] | CS11 | 100%
400814 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2010-05-07 | 2011-10-11 | 2013-10-23 | 2014-09-26 | 2014-09-26 | Highland | 468782 | 43218 | -3838.46 | 0 | 0 | 0 | 0 | 39379.54 | 0 | 508161.54 | 0 | [6 empty] | SG1 | 100%
502828 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-08-20 | 2022-07-22 | 2022-11-14 | 2023-11-02 | 2024-02-02 | Aberdeenshire | 0 | 0 | 0 | 62575.945 | 7446.406 | 23730.9 | 23638.88 | 117392.131 | 29289.96 | 146682.091 | 148885.7057 | [6 empty] | SG1 | 100%
500158 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2016-04-29 | 2016-06-29 | 2018-02-01 | 2018-03-01 | East Ayrshire | 0 | 1669 | 15230 | 13078.58 | 0 | 0 | 0 | 29977.58 | 0 | 29977.58 | 10362.528 | [6 empty] | EC01G | 100% | bar: Regulatory Outputs OMG-23
045539 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-01 | 2012-09-18 | 2014-01-09 | 2015-03-23 | 2015-03-31 | East Ayrshire | 3452973.92 | 147377.27 | 2954.47 | -650.8 | 0 | 0 | 0 | 149680.94 | 0 | 3602654.86 | 50762.9909 | [6 empty] | CM_WWNI | 40.02% | WQ01 | 59.98%
503545 | Q&S4 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWD | Revised Bathing Waters Directive | MSU | 2019-07-01 | 2020-05-18 | 2020-08-14 | 2021-09-14 | 2021-12-15 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 178159.45 | 1320001.34 | 1498160.79 | 1151839.18 | 2649999.97 | 2269817.6904 | [6 empty] | EC16B | 100%
030512 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-20 | 2010-08-23 | 2010-09-27 | 2012-02-01 | 2012-03-05 | South Lanarkshire | 2322396.25 | 36488.35 | 0 | 0 | 0 | 0 | 0 | 36488.35 | 0 | 2358884.6 | 0 | [6 empty] | EC01A | 40% | CM_WWNI | 60%
502317 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2018-07-31 | 2018-07-31 | 2018-07-31 | 2018-07-31 | 2018-07-31 | South Lanarkshire | 0 | 0 | 0 | 52325.58 | 0 | 0 | 0 | 52325.58 | 0 | 52325.58 | 0 | [6 empty] | CM_WWNI | 100%
503418 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2019-07-29 | 2020-12-14 | 2021-04-21 | 2022-03-08 | 2022-06-08 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 77921.05 | 189184.5 | 267105.55 | 732894.49 | 1000000.04 | 0 | [6 empty] | CM_WWI | 100%
402603 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-28 | 2013-07-03 | 2013-09-17 | 2016-11-25 |  | All East Unitary Authorities | 180124 | 53914.8 | 5943.55 | 341.85 | 0 | 0 | 0 | 60200.2 | 0 | 240324.2 | 0 | [6 empty] | CM_M&G | 100%
502339 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-05-05 | 2022-09-22 | 2023-01-25 | 2024-01-16 | 2024-04-17 | All East Unitary Authorities | 0 | 0 | 38620.47 | 190.889 | 43.716 | 0 | 31625.54 | 70480.615 | 1851842.37 | 1922322.985 | 0 | [6 empty] | CM_WWNI | 100%
502350 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-05-05 | 2022-02-28 | 2022-05-25 | 2023-02-07 | 2023-05-10 | All East Unitary Authorities | 0 | 0 | 34200 | 184.599 | 89.2535 | 0 | 29074.49 | 63548.3425 | 1638167.82 | 1701716.1625 | 0 | [6 empty] | CM_WWNI | 100%
502342 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW2 | 2021-04-01 | 2022-09-06 | 2023-01-04 | 2023-12-21 | 2024-03-22 | South Lanarkshire | 0 | 0 | 24773.02 | 50153.65 | -3348.2916 | 0 | 0 | 71578.3784 | 1012518.62 | 1084096.9984 | 0 | [6 empty] | CM_WWNI | 100%
502355 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW2 | 2021-04-01 | 2022-09-14 | 2023-01-17 | 2024-01-01 | 2024-04-02 | Glasgow City | 0 | 0 | 29521.37 | 157120.27 | 13813.5136 | 0 | 0 | 200455.1536 | 4567553.3 | 4768008.4536 | 0 | [6 empty] | CM_WWNI | 100%
502356 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW2 | 2021-04-01 | 2022-10-12 | 2023-02-14 | 2024-02-12 | 2024-05-14 | Glasgow City | 0 | 0 | 38700 | 1857.999 | 242409.446 | 16369.71 | 6465.28 | 305802.435 | 7301589.07 | 7607391.505 | 0 | [6 empty] | CM_WWNI | 100%
502343 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-05-05 | 2022-03-18 | 2022-06-06 | 2022-12-29 | 2023-03-31 | All South Unitary Authorities | 0 | 0 | 23860.47 | 190.889 | 43.716 | 0 | 20919.74 | 45014.815 | 635671.27 | 680686.085 | 0 | [6 empty] | CM_WWNI | 100%
502340 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-05-05 | 2022-09-23 | 2023-01-24 | 2024-01-15 | 2024-04-29 | All South Unitary Authorities | 0 | 0 | 38620.47 | 307.869 | 1089.896 | 0 | 30936.73 | 70954.965 | 1851368.13 | 1922323.095 | 0 | [6 empty] | CM_WWNI | 100%
502341 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-05-05 | 2022-10-17 | 2023-02-13 | 2024-01-03 | 2024-05-01 | All West Unitary Authorities | 0 | 0 | 38842.4 | 454.099 | 43.716 | 0 | 31338.24 | 70678.455 | 1851644.63 | 1922323.085 | 0 | [6 empty] | CM_WWNI | 100%
500436 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-05-14 | 2015-05-14 | 2015-05-14 | 2018-06-21 | 2018-06-21 | All East Unitary Authorities | 0 | 134279 | 638692.24 | 479937.18 | -49306.658 | 0 | 0 | 1203601.762 | 0 | 1203601.762 | 0 | [6 empty] | CM_WWI | 100%
500796 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2015-08-13 | 2016-04-29 | 2016-05-25 | 2016-08-01 | 2016-08-01 | Fife | 0 | 3180.17 | 24605.83 | 0 | 3600.0701 | 0 | 0 | 31386.0701 | 0 | 31386.0701 | 0 | [6 empty] | CM_WWNI | 100%
403169 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS7 | 2012-11-26 | 2015-08-31 | 2015-08-31 | 2015-09-02 | 2015-09-02 | City of Edinburgh | 168947 | -168800.88 | -0.21 | 0 | 0 | 0 | 0 | -168801.09 | 0 | 145.91 | 0 | [6 empty] | CS11 | 100%
501103 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS5 | 2015-09-30 | 2017-03-28 | 2017-03-28 | 2018-06-01 | 2018-12-01 | East Ayrshire | 0 | 715 | 56584 | 220843.51 | 130823.36 | 0 | 0 | 408965.87 | 0 | 408965.87 | 147356.5551 | [6 empty] | EC10E | 4.628% | EC01G | 6.654% | EC01D | 88.72% | bar: Regulatory Outputs OMG-23
500822 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS5 | 2015-10-27 | 2015-12-16 | 2015-12-16 | 2019-03-06 | 2019-03-06 | North Ayrshire | 0 | 138784.81 | 41429.7 | 13260.1 | -87399.7 | 0 | 0 | 106074.91 | 0 | 106074.91 | 144841.4737 | [6 empty] | CS15A | 100%
403755 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2014-03-05 | 2014-05-28 | 2014-05-20 | 2016-06-24 |  | North Ayrshire | 1968942 | 734102 | -16083.83 | -3177.12 | 0 | 0 | 0 | 714841.05 | 0 | 2683783.05 | 0 |  |  |  |  | 10865 |  | CM_WWNI | 100%
503353 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-04-01 | 2021-04-01 | 2021-07-16 | 2022-03-04 | 2022-06-06 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000.01 | 500000.01 | 0 | [6 empty] | CM_WWI | 100%
501169 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-07-19 | 2018-08-31 | 2019-01-29 | 2020-05-22 | 2020-08-21 | North Ayrshire | 0 | 0 | 75934.72 | 264799.96 | 644526.29 | 1483835.14 | 479576.29 | 2948672.4 | 17345.47 | 2966017.87 | 0 |  |  |  |  | 519.9996 |  | CM_WWNI | 100%
501739 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-11-22 | 2018-03-23 | 2018-03-26 | 2019-08-16 | 2019-11-15 | North Ayrshire | 0 | 0 | 8150.38 | 281060.11 | 779583.51 | 102187.04 | 2399.92 | 1173380.96 | 0.04 | 1173381 | 0 | [6 empty] | CM_WWI | 100%
502873 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2021-05-18 | 2027-11-29 | 2028-03-21 | 2029-03-13 | 2029-06-13 | Na H-Eileanan an Iar | 0 | 0 | 0 | 21237.996 | 1387.354 | 12916.29 | 12866.24 | 48407.88 | 4951652.02 | 5000059.9 | 148885.7057 | [6 empty] | WG1 | 100%
046836 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2012-07-26 | 2012-08-08 | 2012-08-08 | 2011-03-14 | Na H-Eileanan an Iar | 62811.62 | 1099.5 | 0 | 0 | 0 | 0 | 0 | 1099.5 | 0 | 63911.12 | 0 | [6 empty] | DW13 | 100%
400104 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2010-03-26 | 2014-10-27 | 2014-10-21 | 2014-10-21 | 2014-10-21 | North Ayrshire | 740196.96 | 12589.77 | -12667.92 | 0 | 0 | 0 | 0 | -78.15 | 0 | 740118.81 | 0 | [6 empty] | CM_WWNI | 100%
501869 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | GW1 | 2019-05-23 | 2020-05-11 | 2020-08-05 | 2022-01-12 | 2022-04-14 | Midlothian | 0 | 0 | 0 | 14403.052 | 1121.708 | 87783.21 | 181925 | 285232.97 | 222766.96 | 507999.93 | 5970783.1595 | [6 empty] | CS16WR | 100%
502789 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2021-04-16 | 2022-01-17 | 2022-03-21 | 2022-08-12 | 2022-11-14 | Scottish Borders | 0 | 0 | 0 | 12252.49 | 12747.51 | 0 | 0 | 25000 | 190340.04 | 215340.04 | 0 | [6 empty] | CM_WSI | 100%
403141 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-01-07 | 2013-09-27 | 2013-10-03 | 2014-02-18 | 2014-02-18 | Scottish Borders | 263670.43 | 879.93 | 0 | 0 | 0 | 0 | 0 | 879.93 | 0 | 264550.36 | 0 | [6 empty] | CM_WSI | 100%
403678 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-02-03 | 2014-08-22 | 2014-09-30 | 2014-12-12 | 2014-12-19 | Scottish Borders | 218316 | -16806.22 | 0 | 0 | 0 | 0 | 0 | -16806.22 | 0 | 201509.78 | 0 | [6 empty] | CM_WSI | 100%
500684 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS2 | 2015-06-08 | 2018-11-30 | 2021-05-17 | 2021-06-25 | 2021-06-28 | Aberdeenshire | 0 | 40054 | 143098 | 77582.72 | 105972.42 | 0 | 0 | 366707.14 | 625721.98 | 992429.12 | 0 | [6 empty] | CM_WSI | 100%
503317 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-03-07 | 2023-08-25 | 2023-12-25 | 2024-12-20 | 2025-03-24 | Angus | 0 | 0 | 0 | 0 | 36358.8 | 20240.76 | 20162.31 | 76761.87 | 69137.71 | 145899.58 | 148885.7057 | [6 empty] | SG1 | 100%
500790 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2015-09-07 | 2021-07-14 | 2021-09-23 | 2022-08-10 | 2022-11-02 | Perth and Kinross | 0 | 38927 | 290174.81 | 1405.99 | 0 | 0 | 0 | 330507.8 | 2326149.57 | 2656657.37 | 0 | [6 empty] | CM_WWNI | 100%
502969 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-04-16 | 2022-03-14 | 2022-06-10 | 2023-01-13 | 2023-04-17 | Angus | 0 | 0 | 0 | 7178.938 | 7221.062 | 0 | 0 | 14400 | 285600.03 | 300000.03 | 0 | [6 empty] | CM_WSI | 100%
401600 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-05-12 | 2013-12-11 | 2014-02-24 | 2018-04-11 | 2018-04-11 | Aberdeenshire | 1047156.05 | 30092.95 | 11999.63 | 36768.6 | 0 | 0 | 0 | 78861.18 | 0 | 1126017.23 | 0 | [6 empty] | SG1 | 100%
500165 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS5 | 2015-03-19 | 2016-11-28 | 2017-01-23 | 2018-12-11 | 2019-03-22 | Scottish Borders | 0 | 13273 | 41433 | 69908 | 39500 | 0 | 0 | 164114 | 0 | 164114 | 55878.6732 | [6 empty] | EC01G | 6.89% | CS16D | 33.83% | EC01D | 59.28%
503308 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-28 | 2023-08-18 | 2023-12-18 | 2024-12-12 | 2025-03-14 | Scottish Borders | 0 | 0 | 0 | 0 | 27021.53 | 8787.39 | 12824.78 | 48633.7 | 99552.18 | 148185.88 | 148885.7057 | [6 empty] | SG1 | 100%
502539 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-01-27 | 2017-06-27 | 2017-06-28 | 2017-08-15 | 2017-08-15 | East Lothian | 0 | 0 | 36636 | 1220212.63 | 0 | 0 | 0 | 1256848.63 | 0 | 1256848.63 | 0 | [6 empty] | CM_WWNI | 100%
401029 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-06-21 | 2010-06-21 | 2010-07-19 | 2012-01-31 |  | Scottish Water Wide | 1180786.8 | -351.8 | 0 | 0 | 0 | 0 | 0 | -351.8 | 0 | 1180435 | 0 | [6 empty] | CM_WSNI | 100%
400551 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-21 | 2010-06-07 | 2010-06-14 | 2015-09-01 |  | Scottish Water Wide | 10235403.83 | -141732.59 | -79630.81 | -31414.75 | 6000 | 0 | 0 | -246778.15 | 0 | 9988625.68 | 0 | [6 empty] | CM_WSI | 100%
402257 | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2011-08-01 | 2013-05-29 | 2013-05-30 | 2016-08-08 | 2016-10-03 | Scottish Water Wide | 4125000 | 0 | -52307.22 | 0 | 0 | 0 | 0 | -52307.22 | 0 | 4072692.78 | 0 | [6 empty] | CS20 | 100%
503220 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-05 | 2023-06-20 | 2023-10-19 | 2024-10-15 | 2025-01-15 | Aberdeenshire | 0 | 0 | 0 | 0 | 86256.55 | 8957.2 | 27734.92 | 122948.67 | 21475.66 | 144424.33 | 148885.7057 | [6 empty] | SG1 | 100%
403680 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2014-02-18 | 2014-02-18 | 2014-02-18 | 2015-10-12 | 2017-03-29 | Scottish Water Wide | 456837 | -333227.7 | -70000 | 62.385 | 0 | 0 | 0 | -403165.315 | 0 | 53671.685 | 0 | [6 empty] | WG5 | 100%
400090 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-11-16 | 2013-01-07 | 2013-05-28 | 2014-03-31 | 2014-03-31 | Na H-Eileanan an Iar | 773340.05 | 10677.32 | 0 | 0 | 0 | 0 | 0 | 10677.32 | 0 | 784017.37 | 8882 | [6 empty] | EC10A | 50% | WQ01 | 50%
402701 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2012-10-09 | 2014-06-27 | 2014-08-29 | 2019-10-11 |  | Shetland Islands | 240764 | 141575 | 15760.72 | 10112.57 | 0 | 0 | 0 | 167448.29 | 0 | 408212.29 | 0 | [6 empty] | CM_WSI | 100%
045561 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-26 | 2011-09-06 | 2013-01-14 | 2013-10-31 | 2013-11-08 | Fife | 1584207.38 | 12081.18 | 20272.95 | 29614.25 | -25750 | 0 | 0 | 36218.38 | 0 | 1620425.76 | 34909.918 | [6 empty] | CM_WWNI | 12.22% | WQ01 | 87.78%
501556 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2016-05-04 | 2021-07-08 | 2021-08-27 | 2021-12-24 | 2022-03-28 | Highland | 0 | 0 | 73700 | 26272.09 | 9177.385 | 0 | 0 | 109149.475 | 158301.88 | 267451.355 | 0 | [6 empty] | CM_WWI | 100%
500971 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-10-12 | 2016-08-30 | 2016-09-26 | 2016-11-21 | 2016-11-21 | Fife | 0 | 4172.5 | 73266.5 | 1799 | -1865.774 | 0 | 0 | 77372.226 | 0 | 77372.226 | 0 | [6 empty] | CM_WWI | 100%
503112 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWD | Reservoirs | GW1 | 2019-08-16 | 2020-12-21 | 2021-04-28 | 2021-12-08 | 2022-03-10 | North Ayrshire | 0 | 0 | 0 | 6697.67 | 278.85 | 29187.32 | 199835.1 | 235998.94 | 563979.62 | 799978.56 | 1560467.3848 | [6 empty] | CS22 | 100%
500160 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-02-26 | 2016-07-01 | 2017-09-01 | 2018-01-01 | North Ayrshire | 0 | 14828 | 88779 | 27851 | -3555.335 | 0 | 0 | 127902.665 | 0 | 127902.665 | 10362.528 | [6 empty] | EC01G | 100% | bar: Regulatory Outputs OMG-23
503280 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-21 | 2023-07-05 | 2023-11-07 | 2024-11-04 | 2025-02-04 | North Ayrshire | 0 | 0 | 0 | 0 | 77728.06 | 1337.61 | 3470.14 | 82535.81 | 61651.54 | 144187.35 | 148885.7057 | [6 empty] | SG1 | 100%
500007 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS4 | 2015-02-25 | 2016-03-31 | 2016-07-31 | 2018-06-29 | 2019-04-01 | Glasgow City | 332.03 | 128254.97 | 7761 | 199420 | 336716.28 | 0 | 0 | 672152.25 | 0 | 672484.28 | 731964.0903 | [6 empty] | CM_WSI | 36% | DW5 | 64%
500839 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2015-10-28 | 2017-03-23 | 2017-03-31 | 2018-03-01 | 2019-06-01 | Glasgow City | 0 | 18193 | 40657.62 | 152632.6896 | 44644.0904 | 5000.02 | 0 | 261127.42 | 0 | 261127.42 | 186756.7013 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 28.28
500008 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS4 | 2015-02-26 | 2016-03-31 | 2016-08-22 | 2018-05-09 | 2019-05-13 | Glasgow City | 332.03 | 136786.97 | 234253 | 574625 | 360420.7575 | 0 | 0 | 1306085.7275 | 0 | 1306417.7575 | 1738663.5248 | [6 empty] | DW5 | 46.08% | DW5FS | 53.92%
503168 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS3 | 2015-02-28 | 2016-03-31 | 2016-08-22 | 2021-03-01 | 2021-06-01 | East Dunbartonshire | 0 | 0 | 0 | 0 | 54152.005 | 2000 | 0 | 56152.005 | 0 | 56152.005 | 869331.7624 | [6 empty] | DW5FS | 100%
500009 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS5 | 2015-02-23 | 2016-03-30 | 2016-05-02 | 2017-09-25 | 2018-12-19 | Glasgow City | 332.03 | 60038.97 | 214299 | 172131 | 320158.41 | 4185.36 | 0 | 770812.74 | 0 | 771144.77 | 536771.841 | [6 empty] | DW5 | 100%
500840 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2015-12-10 | 2017-03-23 | 2017-03-24 | 2019-01-01 | 2019-10-01 | Glasgow City | 0 | 5268 | 29890.62 | 80702.3714 | 53231.0886 | 0 | 5126.12 | 174218.2 | 0 | 174218.2 | 33346.4484 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 6.91
503169 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS3 | 2015-02-28 | 2016-03-30 | 2016-03-30 | 2021-03-01 | 2021-06-01 | East Dunbartonshire | 0 | 0 | 0 | 0 | 62977 | 2000 | 0 | 64977 | 0 | 64977 | 536771.841 | [6 empty] | DW5FS | 100%
500010 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS4 | 2015-02-25 | 2016-03-31 | 2016-06-20 | 2019-03-22 | 2019-09-30 | Glasgow City | 332.03 | 187144.97 | 591927.09 | 275470.71 | 96295.7 | 0 | 0 | 1150838.47 | 0 | 1151170.5 | 1609846.2919 | [6 empty] | CM_WSI | 34.57% | DW5 | 65.43%
503170 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS3 | 2015-02-28 | 2016-03-31 | 2016-03-31 | 2019-07-01 | 2019-10-01 | East Dunbartonshire | 0 | 0 | 0 | 0 | 49085.77 | 57721.13 | 3884.4 | 110691.3 | 1118.47 | 111809.77 | 1418214.6197 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 42.03
500863 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-09-20 | 2018-06-27 | 2018-09-12 | 2019-03-01 | 2019-10-01 | Glasgow City | 0 | 18259.61 | 28121.72 | 58974.12 | 134780.58 | 7864.83 | 0 | 248000.86 | 0 | 248000.86 | 1055497.6629 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 45.63
500887 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2016-10-13 | 2018-09-21 | 2018-10-25 | 2019-09-01 | 2020-09-01 | East Renfrewshire | 0 | 6404.84 | 2646.27 | 6920.97 | 93249.68 | 8903.82 | 6039.41 | 124164.99 | 0 | 124164.99 | 497808.1805 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 42.45
503475 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MSU | 2021-04-01 | 2022-02-14 | 2022-05-13 | 2023-12-08 | 2024-03-11 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 6878.28 | 6851.62 | 13729.9 | 629825.99 | 643555.89 | 0 | [6 empty] | CM_WSI | 4.762% | CM_M&G | 95.24%
501074 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-27 | 2022-04-15 | 2022-05-30 | 2023-08-07 | 2024-05-07 | Glasgow City | 0 | 61056 | 14211.95 | 4143 | 12425.59 | 0 | 0 | 91836.54 | 2046180.95 | 2138017.49 | 0 | [6 empty] | CM_WSI | 100%
501073 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
501072 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2016-04-13 | 2023-10-03 | 2023-11-15 | 2024-04-22 | 2024-07-01 | Glasgow City | 0 | 9720 | 17227.58 | 26577.42 | 54627.77 | 0 | 0 | 108152.77 | 271575.51 | 379728.28 | 0 | [6 empty] | CM_WSI | 100%
501071 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-04-27 | 2022-04-01 | 2022-05-18 | 2023-03-28 | 2024-01-04 | Glasgow City | 0 | 37440 | 42780 | 6000 | 106606 | 0 | 0 | 192826 | 1339003.01 | 1531829.01 | 0 | [6 empty] | CM_WSI | 100%
501075 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
403966 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2014-10-16 | 2015-06-25 | 2015-06-25 | 2016-07-21 |  | East Renfrewshire | 594719 | 1276918 | 223864.73 | 79588 | -2685.72 | 0 | 0 | 1577685.01 | 0 | 2172404.01 | 0 | [6 empty] | CM_WSNI | 100%
502793 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS0 | 2018-02-26 | 2020-06-15 | 2021-01-26 | 2021-09-14 | 2021-12-15 | North Lanarkshire | 0 | 0 | 0 | 16244.04 | 25656.96 | 86829.58 | 248460.65 | 377191.23 | 247098.82 | 624290.05 | 0 | [6 empty] | CM_WWI | 100%
502974 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MSU | 2019-07-01 | 2020-10-05 | 2021-02-05 | 2021-09-01 | 2021-12-01 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 44923.29 | 199439.29 | 244362.58 | 310596.52 | 554959.1 | 148885.7057 | [6 empty] | SG1 | 100%
501109 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-10-13 | 2015-10-13 | 2015-10-13 | 2016-06-30 | 2017-05-15 | Scottish Water Wide | 0 | 987186.22 | 506 | 0 | 0 | 0 | 0 | 987692.22 | 0 | 987692.22 | 0 | [6 empty] | CM_M&G | 100%
500230 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS0 | 2018-04-27 | 2020-09-21 | 2021-01-21 | 2022-01-13 | 2022-04-15 | Aberdeenshire | 0 | 64339.51 | 20868.31 | 39931.0725 | 27352.6475 | 249203.92 | 711521.24 | 1113216.7 | 1700421.36 | 2813638.06 | 148885.7057 | [6 empty] | CM_WWNI | 14% | SG1 | 86%
500501 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2015-06-08 | 2015-06-08 | 2015-06-08 | 2016-09-08 | 2016-09-08 | Scottish Water Wide | 0 | 329499 | 249835.18 | 0 | 196.08 | 0 | 0 | 579530.26 | 0 | 579530.26 | 639260.3798 | [6 empty] | CS16WR | 100%
403898 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | WWINF | Management and General | MS3 | 2014-07-25 | 2014-10-08 | 2014-10-08 | 2021-06-30 |  | Scottish Water Wide | 1544206.72 | 1101002.28 | -1476785.52 | -1018423.48 | 0.0039 | 0 | 0 | -1394206.7161 | 0 | 150000.0039 | 0 | [6 empty] | CM_M&G | 100%
403884 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Water |  | WINF | Management and General | MS3 | 2014-07-25 | 2014-10-08 | 2014-10-08 | 2021-06-30 | 2021-06-30 | Scottish Water Wide | 2200000 | 0 | 2526911.48 | 376948.12 | -3341838.6 | 182550.24 | 181842.68 | -73586.08 | 73586.14 | 2200000.06 | 0 | [6 empty] | CM_M&G | 100%
500942 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | NONINF | Management and General | MS3 | 2015-09-30 | 2015-10-21 | 2015-12-01 | 2021-04-30 | 2021-04-30 | Scottish Water Wide | 0 | 0 | 1538913.88 | 2184600.95 | -2174084.69 | 0 | 0 | 1549430.14 | 0 | 1549430.14 | 0 |  |  |  |  | 18000 |  | QS4EQS | 50% | QS4EQW | 50%
501800 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2019-08-16 | 2021-01-04 | 2021-05-10 | 2022-05-03 | 2022-08-03 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 31719 | 191245.88 | 222964.88 | 963281.12 | 1186246 | 9244605.8896 | [6 empty] | CS11A | 100%
502609 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2017-03-15 | 2017-06-16 | 2017-06-16 | 2017-11-01 | 2018-03-01 | Angus | 0 | 0 | 314.02 | 30565.42 | -1456.41 | 0 | 0 | 29423.03 | 0 | 29423.03 | 0 | [6 empty] | EC16 | 100% | bar: Regulatory Outputs OMG-21
502646 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS6 | 2017-04-11 | 2017-04-11 | 2017-06-26 | 2018-08-17 | 2018-08-17 | Scottish Water Wide | 0 | 0 | 0 | 357386.81 | 7656.34 | 0 | 0 | 365043.15 | 0 | 365043.15 | 0 | [6 empty] | EC16 | 100%
403546 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-09-30 | 2016-01-18 | 2016-02-29 | 2016-12-01 | 2017-02-01 | Scottish Water Wide | 69955 | 80379 | 142500.64 | 12766 | 66.948 | 0 | 0 | 235712.588 | 0 | 305667.588 | 540219.9999 | [6 empty] | EC16 | 100%
502221 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS1 | 2017-11-27 | 2019-11-04 | 2020-03-05 | 2021-02-26 | 2021-03-01 | Aberdeenshire | 0 | 0 | 36096.34 | 27842.56 | 76651.2775 | 135267.3 | 273959.51 | 549816.9875 | 147960.28 | 697777.2675 | 148885.7057 | [6 empty] | SG1 | 100%
502954 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2017-11-27 | 2018-03-14 | 2018-03-26 | 2018-06-29 | 2018-06-29 | Angus | 0 | 0 | 0 | 179401.67 | 820806.03 | 1662.39 | 837.63 | 1002707.72 | 0 | 1002707.72 | 0 | [6 empty] | CM_WWNI | 100%
500499 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS1 | 2015-05-21 | 2019-07-29 | 2019-10-07 | 2020-10-08 | 2020-10-08 | Angus | 0 | 143901 | 122582.39 | 88815.87 | 243720.59 | 1127109.24 | 29349.27 | 1755478.36 | 12868.71 | 1768347.07 | 0 | [6 empty] | CM_WWNI | 100%
502334 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2019-06-05 | 2019-06-05 | 2019-06-05 | 2019-06-05 | 2019-06-05 | Aberdeenshire | 0 | 0 | 38549.52 | 2466.9 | 0 | 0 | 0 | 41016.42 | 0 | 41016.42 | 148885.7057 | [6 empty] | SG1 | 100%
500926 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2018-11-30 | 2018-11-30 | 2018-11-30 | 2018-11-30 | Moray | 0 | 6000 | 4712.79 | -2979.67 | -701.67 | 0 | 0 | 7031.45 | 0 | 7031.45 | 144841.4737 | [6 empty] | CS15A | 100%
501022 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS0 | 2015-12-14 | 2020-04-06 | 2020-08-06 | 2022-01-28 | 2022-04-22 | Scottish Borders | 0 | 20575 | 269789.31 | 96827.67 | 59950.61 | 322556.64 | 833685.29 | 1603384.52 | 1169531.44 | 2772915.96 | 0 | [6 empty] | CM_WWNI | 100%
402712 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-07-03 | 2014-12-05 | 2014-12-16 | 2015-06-25 | 2015-03-23 | Aberdeenshire | 61387 | 2983 | -0.11 | -342.47 | 0 | 0 | 0 | 2640.42 | 0 | 64027.42 | 4258 | [6 empty] | CS1 | 100%
403434 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-04-16 | 2014-09-03 | 2014-10-10 | 2015-05-22 | 2015-05-22 | Moray | 804635 | 139977.66 | 29.67 | 658.56 | 0 | 0 | 0 | 140665.89 | 0 | 945300.89 | 229318.7788 | [6 empty] | CS11A | 100%
045806 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2011-05-27 | 2011-02-21 | 2012-01-11 | 2012-03-23 | Scottish Water Wide | 3983.13 | 365.87 | 0 | 0 | 0 | 0 | 0 | 365.87 | 0 | 4349 | 0 | [6 empty] | WQ01C | 100%
403602 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2013-10-23 | 2015-02-27 | 2015-03-31 | 2015-07-23 | 2015-07-23 | Fife | 98510 | 264270.66 | 5919.34 | 0 | 69265.885 | 0 | 0 | 339455.885 | 0 | 437965.885 | 229318.7788 | [6 empty] | CS11 | 100%
501714 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2016-07-29 | 2021-08-19 | 2021-10-14 | 2021-12-24 | 2022-03-28 | Inverclyde | 0 | 0 | 33248 | -8828 | 0 | 0 | 0 | 24420 | 403357.03 | 427777.03 | 0 | [6 empty] | CM_WWI | 100%
403047 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-11-06 | 2013-06-27 | 2013-07-29 | 2014-04-08 |  | Aberdeenshire | 83300.92 | 0.08 | -718.3 | 0 | 0 | 0 | 0 | -718.22 | 0 | 82582.7 | 0 | [6 empty] | CM_WWI | 100%
045555 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-26 | 2011-06-01 | 2011-07-28 | 2012-04-07 | 2013-02-06 | Clackmannanshire | 786725.35 | 2001.54 | 0 | 0 | 0 | 0 | 0 | 2001.54 | 0 | 788726.89 | 0 | [6 empty] | CM_WWNI | 6.398% | WQ01 | 93.6%
502421 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW2 | 2021-04-07 | 2021-04-07 | 2021-04-07 | 2021-04-07 | 2021-04-07 | Angus | 0 | 0 | 15069.77 | 628.53 | 4087.27 | 0 | 0 | 19785.57 | 0 | 19785.57 | 0 | [6 empty] | CM_WWNI | 100%
500207 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS3 | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2020-05-07 | 2021-05-20 | Renfrewshire | 0 | 44645 | 187355 | 305651.58 | 559147.36 | 3385.18 | 1614.83 | 1101798.95 | 0 | 1101798.95 | 7257350.1747 | [6 empty] | DW5FS | 100%
501535 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2022-10-18 | 2023-09-25 | 2024-01-29 | 2024-09-12 | 2024-12-13 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 860519.02 | 860519.02 | 0 | [6 empty] | CM_WSNI | 100%
501536 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2022-10-17 | 2023-09-22 | 2024-01-26 | 2024-09-11 | 2024-12-12 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417965.98 | 417965.98 | 0 | [6 empty] | CM_WSNI | 100%
501069 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-06-01 | 2022-05-17 | 2022-07-08 | 2023-08-04 | 2023-11-06 | East Renfrewshire | 0 | 88272 | 12853 | 7283 | 1719.56 | 0 | 0 | 110127.56 | 2292440.02 | 2402567.58 | 0 | [6 empty] | CM_WSI | 100%
501068 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-12 | 2016-04-12 | 2016-04-12 | 2016-04-12 | 2016-04-12 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
403955 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWD | OMG180 | MS5 | 2015-01-28 | 2015-07-31 | 2015-08-24 | 2017-12-01 | 2018-12-01 | Renfrewshire | 13000 | 4236033.98 | 10772967 | 1092460.44 | 109.29 | 585539.02 | 0 | 16687109.73 | 0 | 16700109.73 | 12121303.0001 |  |  |  |  | 179670 |  | DW3C | 0.14% | DW3H | 0.31% | DW23 | 99.55% | bar: Regulatory Outputs OMG-03
500575 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS1 | 2016-06-01 | 2019-07-22 | 2019-11-21 | 2020-07-21 | 2020-10-07 | Renfrewshire | 0 | 22338.8 | 119869.52 | 111428.68 | -127103.62 | 0 | 0 | 126533.38 | 0 | 126533.38 | 0 | [6 empty] | CM_WSNI | 100%
500914 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2015-11-06 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | Aberdeenshire | 0 | 5904.44 | 44390.19 | -4838.16 | 9042.77 | 0 | 0 | 54499.24 | 0 | 54499.24 | 0 | [6 empty] | CM_WSNI | 100%
045793 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2010-12-21 | 2011-03-25 | 2011-12-19 | 2012-01-31 | Angus | 565017.8 | 175.52 | 0 | 0 | 0 | 0 | 0 | 175.52 | 0 | 565193.32 | 0 | [6 empty] | CM_WWNI | 5.014% | WQ01B | 5.014% | WQ01C | 89.97%
503207 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS1 | 2018-09-05 | 2019-07-29 | 2020-04-27 | 2020-11-11 | 2021-03-09 | Moray | 0 | 0 | 0 | 0 | 26314.1 | 55723.82 | 101662.1 | 183700.02 | 3300.06 | 187000.08 | 0 | [6 empty] | CM_WWNI | 100%
501120 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | General |  | SWMD | Water Non infrastructure | MS7 | 2015-11-05 | 2018-12-10 | 2018-12-11 | 2018-12-12 | 2018-12-12 | Scottish Water Wide | 0 | 30896 | 62243.94 | 75423.228 | 11889.092 | 0 | 0 | 180452.26 | 0 | 180452.26 | 0 | [6 empty] | CM_M&G | 49.14% | CM_WSNI | 50.86%
500028 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-02-27 | 2015-04-28 | 2015-06-23 | 2017-10-09 | 2017-12-01 | Scottish Water Wide | 0 | 1550664 | 1276315.48 | 312182.12 | -1158.509 | 0 | 0 | 3138003.091 | 0 | 3138003.091 | 0 | [6 empty] | CM_WSNI | 100%
501772 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2016-12-08 | 2017-03-22 | 2017-07-27 | 2019-10-14 | 2020-01-20 | Scottish Water Wide | 0 | 0 | 254977.55 | 1114203.37 | 1380331.58 | 403594.13 | 0 | 3153106.63 | 0 | 3153106.63 | 0 | [6 empty] | CM_WSNI | 100%
502245 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2019-04-15 | 2019-04-15 | 2019-04-16 | 2021-06-30 | 2021-09-30 | Scottish Water Wide | 0 | 0 | 3284.15 | -17.83 | 4114.806 | 126174.48 | 3340343.66 | 3473899.266 | 113658.18 | 3587557.446 | 0 | [6 empty] | CM_WSNI | 100%
502175 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS0 | 2016-04-25 | 2021-04-15 | 2021-04-15 | 2021-04-15 | 2021-04-15 | Scottish Water Wide | 0 | 0 | 159385.81 | 313796.99 | 14013.06 | 5000 | 144952.03 | 637147.89 | 7362852.12 | 8000000.01 | 0 | [6 empty] | CM_WSNI | 100%
501675 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2016-10-14 | 2016-10-14 | 2017-05-29 | 2022-11-22 | 2023-02-22 | Aberdeen City | 0 | 0 | 0 | 3582.97 | 3192.16 | 10712.4 | 10670.87 | 28158.4 | 21841.75 | 50000.15 | 0 |  |  |  |  | 50000.0004 |  | CM_WSNI | 100%
500029 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2015-02-27 | 2015-04-28 | 2015-07-07 | 2018-06-18 | 2018-06-18 | Scottish Water Wide | 135.86 | 4177771.14 | 1928293.73 | 1073446.9 | 7997.69 | 793.12 | 98.55 | 7188401.13 | 0 | 7188536.99 | 0 | [6 empty] | CM_WSNI | 100%
501771 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2016-12-28 | 2017-05-31 | 2017-06-26 | 2019-05-10 | 2019-08-12 | Scottish Water Wide | 0 | 0 | 67764.79 | 4358385.76 | 4387706.85 | 632305.79 | 12205.87 | 9458369.06 | 0 | 9458369.06 | 0 | [6 empty] | CM_WSNI | 100%
502244 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2019-04-09 | 2019-04-09 | 2019-04-16 | 2021-06-30 | 2021-11-24 | Scottish Water Wide | 0 | 0 | 8992.45 | 972.015 | 5090.885 | 3994319.95 | 3140031.23 | 7149406.53 | 280678.62 | 7430085.15 | 0 | [6 empty] | CM_WSNI | 100%
501752 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2016-03-21 | 2020-11-09 | 2020-12-04 | 2022-05-09 | 2022-06-13 | Scottish Water Wide | 0 | 15426.5 | 6578.3 | 3226 | 146024.06 | 12151.89 | 407981.18 | 591387.93 | 2515682.45 | 3107070.38 | 0 | [6 empty] | CM_M&G | 16.67% | CM_WSNI | 83.33%
501753 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2019-08-09 | 2020-01-20 | 2020-02-28 | 2020-12-11 | 2021-01-21 | Scottish Water Wide | 0 | 0 | 28856.57 | 4496.19 | 161677.0695 | 1028045.17 | 3962360.87 | 5185435.8695 | 37926.98 | 5223362.8495 | 0 | [6 empty] | CM_M&G | 9.677% | CM_WSNI | 90.32%
501754 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2020-02-05 | 2020-07-20 | 2020-08-31 | 2021-07-16 | 2021-09-03 | Scottish Water Wide | 0 | 0 | 62288.37 | 349.36 | 2895.31 | 103757.73 | 2886394.46 | 3055685.23 | 1688669.88 | 4744355.11 | 0 | [6 empty] | CM_M&G | 6.452% | CM_WSNI | 93.55%
501755 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2020-02-18 | 2020-08-03 | 2020-08-31 | 2021-07-23 | 2021-08-26 | Scottish Water Wide | 0 | 0 | 50857.53 | 438.506 | 1523.264 | 76362.09 | 1258166.67 | 1387348.06 | 751867.95 | 2139216.01 | 0 | [6 empty] | CM_WWI | 32.99% | CM_WSNI | 67.01%
503091 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2022-02-08 | 2023-04-13 | 2023-08-08 | 2024-03-19 | 2024-06-19 | North Lanarkshire | 0 | 0 | 0 | 16137.21 | 897.38 | 0 | 0 | 17034.59 | 785965.4 | 802999.99 | 0 | [6 empty] | CM_WSNI | 100%
502614 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 | Perth and Kinross | 0 | 0 | 3696.28 | 27494.71 | 10969.451 | 0 | 0 | 42160.441 | 0 | 42160.441 | 0 | [6 empty] | CM_WWI | 100%
500249 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS2 | 2015-06-09 | 2019-03-20 | 2019-04-29 | 2020-01-16 | 2020-07-03 | East Lothian | 0 | 65357 | 55269.08 | 97403.4495 | 258941.7705 | 1287598.81 | 105723.89 | 1870294 | 0 | 1870294 | 0 | [6 empty] | CM_WSI | 100%
501665 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 | 2016-08-31 | 2017-03-27 | 2021-07-29 | 2022-03-08 | 2022-06-08 | Na H-Eileanan an Iar | 0 | 0 | 17170.11 | 3623.98 | 0 | 0 | 0 | 20794.09 | 119117.98 | 139912.07 | 0 | [6 empty] | CM_WWI | 100%
501175 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2016-10-17 | 2018-08-13 | 2018-08-20 | 2018-08-22 | 2018-08-22 | Aberdeen City | 0 | 26930 | 454433.2 | -118577.2 | -354921.4575 | 0 | 0 | 7864.5425 | 0 | 7864.5425 | 240495.8008 | [6 empty] | CS11A | 100%
500162 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-01-19 | 2016-03-23 | 2017-12-21 | 2018-03-29 | Highland | 0 | 45798 | 145814 | 67183 | -2328.0525 | 0 | 0 | 256466.9475 | 0 | 256466.9475 | 10362.528 | [6 empty] | EC01G | 41.75% | CS16D | 58.25%
503264 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2018-06-26 | 2018-08-27 | 2018-09-24 | 2019-07-08 | 2019-10-08 | Highland | 0 | 0 | 0 | 0 | 475300.84 | 24928.76 | 1075.04 | 501304.64 | 338.83 | 501643.47 | 0 | [6 empty] | CM_WSI | 100%
500188 | Q&S4 | Protecting and enhancing the environment | Odour |  |  | Wastewater |  | SWD | Odour | MS7 | 2015-03-16 | 2015-06-26 | 2015-06-29 | 2015-06-01 | 2015-06-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CS2 | 100% | bar: Regulatory Outputs OMG-29
046359 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-04-28 | 2012-01-17 | 2011-10-10 | 2013-05-08 |  | Highland | 1214920.55 | -364.04 | 0 | 0 | 0 | 0 | 0 | -364.04 | 0 | 1214556.51 | 0 | [6 empty] | CM_WWNI | 100%
500586 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-06-19 | 2015-07-24 | 2015-08-31 | 2015-12-10 | 2015-12-11 | Highland | 0 | 254887.96 | 0 | 0 | 0 | 0 | 0 | 254887.96 | 0 | 254887.96 | 0 | [6 empty] | CM_WWNI | 100%
403425 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-04-30 | 2013-04-30 | 2013-05-02 | 2015-07-27 |  | Scottish Water Wide | 5296295.2 | -2547.01 | 0 | 5433 | 0 | 0 | 0 | 2885.99 | 0 | 5299181.19 | 0 | [6 empty] | CM_M&G | 100%
501015 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS2 | 2018-01-29 | 2019-02-12 | 2019-04-08 | 2019-07-30 | 2019-11-01 | Aberdeen City | 0 | 38030 | 24065.42 | 33343.7766 | 138118.8034 | 240403.84 | 2250.16 | 476212 | 0.04 | 476212.04 | 229318.7788 | [6 empty] | CS11 | 100%
503289 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2019-10-22 | 2020-10-19 | 2021-01-26 | 2022-01-11 | 2022-04-13 | Aberdeen City | 0 | 0 | 0 | 0 | 543000 | 240522.89 | 736665 | 1520187.89 | 2448937.12 | 3969125.01 | 240495.8008 | [6 empty] | CS11A | 100%
501636 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-10-16 | 2021-09-15 | 2021-12-07 | 2022-07-08 | 2022-10-06 | Perth and Kinross | 0 | 21530 | 794.22 | 1675.78 | 9000 | 7845.75 | 111067.24 | 151912.99 | 448086.96 | 599999.95 | 240495.8008 | [6 empty] | CS11A | 100%
500747 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2019-07-01 | 2019-07-15 | 2019-07-15 | 2019-07-15 | 2019-06-17 | Angus | 0 | 22000 | 37647.26 | 16790.4475 | 26562.2925 | 7000 | 0 | 110000 | 0 | 110000 | 229318.7788 | [6 empty] | CS11 | 100%
502348 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-03-19 | 2021-02-08 | 2021-04-28 | 2021-11-24 | 2022-02-23 | Aberdeen City | 0 | 0 | 0 | 0 | 105000 | 26861.02 | 142867.2 | 274728.22 | 625271.81 | 900000.03 | 240495.8008 | [6 empty] | CS11A | 100%
500746 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-10-16 | 2021-09-06 | 2021-11-30 | 2022-07-01 | 2022-09-23 | Perth and Kinross | 0 | 23000 | 31382.88 | 16580.8 | 48606.61 | 14712.66 | 109977.08 | 244260.03 | 445310.27 | 689570.3 | 229318.7788 | [6 empty] | CS11 | 100%
502347 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-03-22 | 2019-03-22 | 2019-03-22 | 2019-01-16 | 2019-01-16 | Fife | 0 | 0 | 0 | 22000 | -16737.42 | 0 | 0 | 5262.58 | 0 | 5262.58 | 229318.7788 | [6 empty] | CS11 | 100%
502889 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-10-16 | 2021-09-16 | 2021-11-30 | 2022-07-04 | 2022-10-04 | Perth and Kinross | 0 | 0 | 0 | 0 | 52000 | 4608.93 | 29723.37 | 86332.3 | 213667.72 | 300000.02 | 240495.8008 | [6 empty] | CS11A | 100%
500500 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW2 | 2019-07-02 | 2019-07-15 | 2019-07-15 | 2019-07-15 | 2019-07-15 | Fife | 0 | 20500 | 4681.78 | 29818.22 | 11000 | 108999.99 | 0 | 174999.99 | 0 | 174999.99 | 411866.5694 | [6 empty] | CS11 | 100%
500677 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-03-23 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | Dundee City | 0 | 42930 | 12119.4 | -55049.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CS11 | 100%
500089 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS5 | 2019-07-01 | 2019-07-15 | 2019-07-15 | 2019-01-21 | 2019-01-21 | Fife | 0 | 10025 | 13092.19 | 17132.81 | -40249 | 0 | 0 | 1 | 0 | 1 | 1825070.7312 | [6 empty] | CS11 | 100%
502890 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-06-26 | 2021-06-11 | 2021-08-25 | 2022-03-29 | 2022-06-29 | Dundee City | 0 | 0 | 0 | 0 | 81000 | 14600.45 | 56973.07 | 152573.52 | 147426.49 | 300000.01 | 240495.8008 | [6 empty] | CS11A | 100%
500998 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2019-05-15 | 2020-04-06 | 2020-06-08 | 2020-08-14 | 2020-08-28 | Perth and Kinross | 0 | 22430 | 32002.89 | 45567.11 | 43000 | 62730.56 | 553627.43 | 759357.99 | 0 | 759357.99 | 229318.7788 | [6 empty] | CS11 | 100%
501254 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS7 | 2017-08-07 | 2018-01-29 | 2018-01-30 | 2018-02-08 | 2018-02-08 | Perth and Kinross | 0 | 29930 | 24915.34 | 10650.49 | -65375.98 | 0 | 0 | 119.85 | 0 | 119.85 | 41679.0579 | [6 empty] | CS11 | 100%
500656 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2016-11-21 | 2016-11-21 | 2016-11-18 | 2016-06-28 | 2016-11-18 | Angus | 0 | 60770 | -60770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CS11 | 100%
502888 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2019-10-11 | 2019-11-04 | 2019-11-04 | 2019-12-13 | 2019-12-16 | Perth and Kinross | 0 | 0 | 0 | 0 | 61000 | 36817.01 | 0 | 97817.01 | 0 | 97817.01 | 240495.8008 | [6 empty] | CS11A | 100%
501333 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-07-23 | 2022-07-13 | 2022-11-16 | 2023-07-03 | 2023-10-03 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000.03 | 100000.03 | 0 | [6 empty] | CM_WSNI | 100%
502971 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-07-08 | 2022-06-03 | 2022-09-05 | 2023-09-29 | 2024-01-01 | Glasgow City | 0 | 0 | 0 | 24867.8475 | 7699.072 | 0 | 0 | 32566.9195 | 2167433.12 | 2200000.0395 | 0 | [6 empty] | CM_WSI | 100%
030535 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-15 | 2015-03-12 | 2015-03-12 | 2015-03-12 | 2015-03-12 | East Renfrewshire | 962475.53 | 1008 | 0 | 0 | 0 | 0 | 0 | 1008 | 0 | 963483.53 | 0 | [6 empty] | EC04A | 100%
500026 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2015-02-23 | 2016-08-01 | 2016-09-12 | 2017-05-17 | 2017-05-31 | Glasgow City | 332.03 | 75903.97 | 470076 | 51298 | 19882.82 | 0 | 0 | 617160.79 | 0 | 617492.82 | 0 | [6 empty] | CM_WSI | 100%
502137 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-03-24 | 2016-07-06 | 2016-07-07 | 2016-09-01 | 2016-09-01 | East Renfrewshire | 0 | 0 | 3069.53 | 245.28 | 0 | 0 | 0 | 3314.81 | 0 | 3314.81 | 4421.6913 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
503135 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-05-26 | 2022-08-12 | 2022-12-14 | 2023-07-26 | 2023-10-26 | East Renfrewshire | 0 | 0 | 0 | 0 | 8447.4675 | 0 | 0 | 8447.4675 | 241552.56 | 250000.0275 | 0 | [6 empty] | CM_WSNI | 100%
401917 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-02-04 | 2011-12-20 | 2012-02-20 | 2014-11-05 | 2014-11-05 | East Renfrewshire | 4082651.78 | 130122.58 | 122432.28 | -111378.87 | -68996.14 | 0 | 0 | 72179.85 | 0 | 4154831.63 | 0 | [6 empty] | CM_WSNI | 100%
045641 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-07-24 | 2011-06-30 | 2011-06-30 | 2011-03-31 |  | East Renfrewshire | 232473.21 | 6341.81 | 0 | 0 | 0 | 0 | 0 | 6341.81 | 0 | 238815.02 | 0 | [6 empty] | CM_WSNI | 100%
403937 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | NONINF | Non OMG180 | MS5 | 2009-05-15 | 2016-08-31 | 2017-02-27 | 2018-11-29 | 2019-03-13 | East Renfrewshire | 144852 | 312945 | 836831.9 | 3770911.194 | 1156812.636 | -686588.72 | 7964.34 | 5398876.35 | 0 | 5543728.35 | 2782022.8384 | [6 empty] | EC04A | 24.92% | EC10A | 24.92% | CM_WWNI | 50.16%
503315 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-25 | 2023-08-17 | 2023-12-15 | 2024-12-12 | 2025-03-14 | East Renfrewshire | 0 | 0 | 0 | 0 | 18173.47 | 0 | 19169.22 | 37342.69 | 104657.57 | 142000.26 | 148885.7057 | [6 empty] | SG1 | 100%
502603 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS5 | 2017-10-19 | 2017-10-19 | 2018-04-02 | 2018-10-25 | 2018-10-25 | Highland | 0 | 0 | 0 | 284154.57 | -13639.18 | 0 | 0 | 270515.39 | 0 | 270515.39 | 587726.5342 | [6 empty] | WG5 | 100%
400115 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-02-23 | 2012-09-21 | 2012-10-22 | 2013-06-10 |  | Na H-Eileanan an Iar | 465006 | -1896.05 | 0 | 0 | 0 | 0 | 0 | -1896.05 | 0 | 463109.95 | 0 | [6 empty] | CM_WSI | 100%
400117 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-02-23 | 2012-09-14 | 2012-10-31 | 2013-08-05 |  | Na H-Eileanan an Iar | 928392 | -1214.42 | 0 | 0 | 0 | 0 | 0 | -1214.42 | 0 | 927177.58 | 0 | [6 empty] | CM_WSI | 100%
400118 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-02-23 | 2011-12-23 | 2012-01-18 | 2017-02-01 |  | Na H-Eileanan an Iar | 213643 | -8751 | 52905.9 | 6642.99 | -778.4 | 0 | 0 | 50019.49 | 0 | 263662.49 | 0 | [6 empty] | CM_WSI | 100%
403649 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS7 | 2014-01-13 | 2014-02-06 | 2014-02-06 | 2017-11-16 | 2017-11-16 | Highland | 495024 | 0 | -456353.52 | -11251.95 | -281.28 | 0 | 0 | -467886.75 | 0 | 27137.25 | 0 | [6 empty] | SG5 | 100%
502134 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-03-24 | 2016-03-29 | 2016-03-29 | 2016-07-01 | 2016-09-01 | Na H-Eileanan an Iar | 0 | 65.42 | 104.82 | 196.68 | 0 | 0 | 0 | 366.92 | 0 | 366.92 | 1017925.3446 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-05
502040 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-03-30 | 2016-03-30 | 2016-03-30 | 2018-03-28 |  | Scottish Water Wide | 0 | 508698 | 511912.53 | 353424.25 | -1809.01 | 0 | 0 | 1372225.77 | 0 | 1372225.77 | 0 | [6 empty] | CM_M&G | 100%
502540 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2017-02-02 | 2017-11-17 | 2018-05-29 | 2019-12-23 | 2019-12-23 | Angus | 0 | 0 | 440.51 | 5525.79 | 16314.4 | 5889.28 | 856 | 29025.98 | 0 | 29025.98 | 0 | [6 empty] | CM_WWI | 100%
500050 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-07-27 | 2016-07-27 | Aberdeenshire | 0 | 32482.18 | 24117.86 | 7.41 | 0 | 0 | 0 | 56607.45 | 0 | 56607.45 | 148885.7057 | [6 empty] | SG1 | 100%
030537 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS6 | 2008-07-15 | 2012-09-05 | 2012-10-29 | 2018-04-30 | 2016-02-24 | South Lanarkshire | 2223247.7 | 90421.38 | 127647.15 | 1368310.2759 | -277272.2854 | 241269.36 | 27313.64 | 1577689.5205 | 0 | 3800937.2205 | 650779 | [6 empty] | EC04A | 100%
500811 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS3 | 2015-09-28 | 2015-12-21 | 2015-12-21 | 2021-01-21 | 2021-04-19 | Scottish Water Wide | 0 | 193828 | 338947.83 | 197548.17 | 201000 | 75872.18 | 359574.1 | 1366770.28 | 38229.72 | 1405000 | 3783756.1971 | [6 empty] | SG5 | 100%
500895 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS3 | 2015-09-24 | 2015-12-23 | 2015-12-24 | 2021-03-30 | 2021-03-30 | Scottish Water Wide | 0 | 32570 | 18868 | 220224.54 | 506228.26 | 904401.18 | 1061306.54 | 2743598.52 | 731776.48 | 3475375 | 587726.5342 | [6 empty] | WG5 | 100%
401391 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWMD | Infra Charge | MS7 | 2010-09-15 | 2011-03-18 | 2011-03-18 | 2015-08-20 | 2015-10-28 | Scottish Water Wide | 287479 | 12986 | 1412.92 | 0 | 0 | 0 | 0 | 14398.92 | 0 | 301877.92 | 0 | [6 empty] | SG5 | 100%
401392 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS7 | 2010-09-24 | 2011-03-17 | 2011-03-17 | 2015-08-24 | 2015-10-28 | Scottish Water Wide | 178070 | 11940.06 | 713.91 | 0 | 0 | 0 | 0 | 12653.97 | 0 | 190723.97 | 0 | [6 empty] | WG5 | 100%
401951 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2011-03-21 | 2018-01-29 | 2018-01-29 | 2018-01-29 |  | Scottish Water Wide | 36.59 | 3463.41 | 0 | -100.31 | 0 | 0 | 0 | 3363.1 | 0 | 3399.69 | 0 | [6 empty] | CM_WWI | 100%
402000 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2011-03-21 | 2019-07-10 | 2019-07-11 | 2019-09-10 |  | Scottish Water Wide | 42269.05 | 17730.95 | 0 | -17730.95 | 0 | 0 | 0 | 0 | 0 | 42269.05 | 0 | [6 empty] | CM_WWI | 100%
045564 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-01 | 2011-09-21 | 2011-09-23 | 2015-03-31 | 2015-05-29 | Scottish Water Wide | 4569041.04 | 7238.54 | -6011.41 | 372.15 | 0 | 0 | 0 | 1599.28 | 0 | 4570640.32 | 206942 | [6 empty] | WQ01B | 100%
500592 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-12-14 | 2016-06-30 | 2016-06-30 | 2018-03-28 | 2018-03-28 | Scottish Water Wide | 0 | 213349 | 380145.06 | 290162.9 | 0 | 0 | 0 | 883656.96 | 0 | 883656.96 | 0 | [6 empty] | CM_M&G | 100%
500993 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2015-10-07 | 2016-10-27 | 2017-03-17 | 2017-11-24 | 2017-11-24 | Aberdeenshire | 0 | 2127 | 14132 | 56241 | 0.001 | 0 | 0 | 72500.001 | 0 | 72500.001 | 0 | [6 empty] | CM_WWNI | 100%
500164 | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-20 | 2016-01-19 | 2016-03-09 | 2018-03-12 | 2018-03-12 | East Ayrshire | 0 | 41549 | 82887 | 17760 | 12584.155 | 0 | 0 | 154780.155 | 0 | 154780.155 | 72474.3726 | [6 empty] | CS11 | 100%
500167 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2015-03-20 | 2016-06-21 | 2016-09-07 | 2019-06-01 | 2019-09-01 | Dumfries and Galloway | 0 | 10409 | 12925 | 12502 | 52000 | 2163.81 | 0.17 | 89999.98 | 0 | 89999.98 | 77134.3584 | [6 empty] | EC01G | 7.63% | EC01D | 92.37% | bar: Regulatory Outputs OMG-23
502816 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-07-05 | 2022-07-22 | 2022-11-14 | 2023-11-02 | 2024-02-02 | Dumfries and Galloway | 0 | 0 | 0 | 77047.466 | 27924.527 | 11156.63 | 13167.03 | 129295.653 | 21884.87 | 151180.523 | 148885.7057 | [6 empty] | SG1 | 100%
403330 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS7 | 2013-02-18 | 2016-02-15 | 2016-02-16 | 2016-07-18 | 2016-07-18 | Perth and Kinross | 196881 | 1267417 | 58388.33 | -1686.33 | -15926.9426 | 0 | 0 | 1308192.0574 | 0 | 1505073.0574 | 469952.155 | [6 empty] | CS15 | 28% | CS11 | 72%
501664 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-02-22 | 2017-03-22 | 2017-06-12 | 2017-09-11 | 2017-09-11 | Na H-Eileanan an Iar | 0 | 1267 | 20969.46 | 69556.016 | 0.004 | 0 | 0 | 91792.48 | 0 | 91792.48 | 0 | [6 empty] | CM_WWI | 100%
500166 | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-20 | 2015-09-27 | 2017-03-01 | 2017-04-14 | 2017-04-14 | Dumfries and Galloway | 0 | 15244 | -4313.77 | -2077.22 | 0 | 0 | 0 | 8853.01 | 0 | 8853.01 | 561676.3877 | [6 empty] | CS15 | 49.17% | CS11 | 50.83%
502408 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2021-04-01 | 2022-06-22 | 2022-10-14 | 2023-06-02 | 2023-08-28 | Fife | 0 | 0 | 13934.19 | 13400.57 | 28252.3 | 2746.58 | 939.5 | 59273.14 | 531514.35 | 590787.49 | 0 | [6 empty] | CM_WWNI | 100%
503372 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-05-16 | 2023-03-23 | 2023-07-26 | 2024-01-16 | 2024-04-17 | Fife | 0 | 0 | 0 | 0 | 76428.31 | 17699.31 | 23108.34 | 117235.96 | 28677.55 | 145913.51 | 148885.7057 | [6 empty] | SG1 | 100%
045718 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-19 | 2011-07-28 | 2011-10-17 | 2016-03-17 | 2016-03-30 | Scottish Borders | 3066864.75 | 435815.96 | 108168.08 | -9281.89 | -6038.3235 | 0 | 0 | 528663.8265 | 0 | 3595528.5765 | 508166 |  |  |  |  | 29173.6326 |  | DW23 | 100%
503106 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS1 | 2018-05-17 | 2019-10-14 | 2019-12-13 | 2021-03-23 | 2021-06-23 | Aberdeenshire | 0 | 0 | 0 | 0 | 95443.065 | 429246.99 | 230602.03 | 755292.085 | 183360.34 | 938652.425 | 587726.5342 | [6 empty] | WG5 | 100%
500731 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS1 | 2017-08-18 | 2019-10-07 | 2019-11-11 | 2021-08-12 | 2021-11-11 | Aberdeenshire | 0 | 21155.09 | 89337.45 | 211089.811 | 389838.849 | 1023400.91 | 3755984.16 | 5490806.27 | 484556.49 | 5975362.76 | 148885.7057 | [6 empty] | SG1 | 100%
501694 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS1 | 2017-03-29 | 2019-10-07 | 2020-01-16 | 2020-09-28 | 2021-01-12 | North Lanarkshire | 0 | 0 | 46991.03 | 65450.97 | 195173 | 961670.25 | 1752211.64 | 3021496.89 | 30925.56 | 3052422.45 | 0 | [6 empty] | CM_WWI | 100%
500208 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS4 | 2015-03-27 | 2018-06-27 | 2018-06-29 | 2019-02-01 | 2020-02-01 | Highland | 0 | 6891 | -5257.45 | 36980.45 | 116586.55 | 2475.61 | 49.42 | 157725.58 | 0 | 157725.58 | 953108.9925 | [6 empty] | DW5 | 100% | bar: Regulatory Outputs OMG-02
500705 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWMD | Water infrastructure | MS7 | 2015-07-10 | 2015-07-30 | 2015-08-11 | 2016-01-01 | 2016-01-04 | Highland | 0 | 705064.64 | 0 | 0 | 0 | 0 | 0 | 705064.64 | 0 | 705064.64 | 0 | [6 empty] | CM_M&G | 100%
500866 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-09-08 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Highland | 0 | 6715.98 | 4512.65 | 934.8 | -805.05 | 0 | 0 | 11358.38 | 0 | 11358.38 | 508639.1312 | [6 empty] | DW5FS | 100%
501370 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS0 | 2016-05-11 | 2021-10-11 | 2022-02-22 | 2023-10-10 | 2024-01-10 | Highland | 0 | 0 | 81345.57 | 3191.68 | 0 | 0 | 0 | 84537.25 | 518569.28 | 603106.53 | 0 | [6 empty] | CM_WSNI | 100%
502757 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-05-23 | 2017-08-29 | 2017-09-18 | 2019-10-11 | 2020-01-09 | Highland | 0 | 0 | 0 | 1045148.6 | 476227.71 | 83915.67 | 2707.29 | 1607999.27 | 1527.45 | 1609526.72 | 0 |  |  |  |  | 11750.0003 |  | CM_WSNI | 100%
503206 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-05-03 | 2022-07-01 | 2022-10-31 | 2023-06-15 | 2023-09-15 | Highland | 0 | 0 | 0 | 0 | 21094.27 | 13887.66 | 13833.84 | 48815.77 | 901184.23 | 950000 | 0 | [6 empty] | CM_WSNI | 100%
402067 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-05-04 | 2011-12-21 | 2012-01-30 | 2013-12-03 |  | Highland | 142274 | -185.6 | 0 | 0 | 0 | 0 | 0 | -185.6 | 0 | 142088.4 | 0 | [6 empty] | CM_WSNI | 100%
401343 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-13 | 2012-02-22 | 2012-08-27 | 2013-11-19 | 2013-03-31 | Fife | 138307.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138307.6 | 530 | [6 empty] | CS1 | 100%
401234 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS6 | 2010-09-01 | 2015-10-26 | 2016-01-11 | 2018-04-24 | 2018-04-24 | Scottish Borders | 256722 | 175202 | 623854.82 | 107979.665 | 1600.115 | 0 | 0 | 908636.6 | 0 | 1165358.6 | 0 | [6 empty] | SG1 | 100%
502796 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS5 | 2017-07-26 | 2017-07-26 | 2018-01-30 | 2018-10-25 | 2018-10-25 | South Lanarkshire | 0 | 0 | 0 | 236825.81 | 531527.2605 | 1570.44 | 1826.26 | 771749.7705 | 1023.26 | 772773.0305 | 0 | [6 empty] | CM_WWI | 100%
300032 | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-05-11 | 2014-04-25 | 2014-11-24 | 2016-06-01 | 2016-06-01 | Dumfries and Galloway | 499376 | 767727 | 47798.05 | 374.24 | -113.78 | 0 | 0 | 815785.51 | 0 | 1315161.51 | 698452.9999 | [6 empty] | WQ1/1 | 100%
501727 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-07-23 | 2022-06-15 | 2022-09-12 | 2023-04-12 | 2023-07-13 | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 435821.99 | 435821.99 | 0 | [6 empty] | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 33.33% | CM_WSI | 42.86%
500068 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS0 | 2017-11-09 | 2020-08-10 | 2020-09-10 | 2021-07-06 | 2021-10-06 | Scottish Borders | 0 | 46006.3 | 20969.55 | 52573.93 | 14567.8 | 4893 | 492106.75 | 631117.33 | 370911.79 | 1002029.12 | 148885.7057 | [6 empty] | SG1 | 100%
501779 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2021-05-25 | 2022-03-16 | 2022-06-06 | 2022-10-18 | 2023-01-18 | Aberdeenshire | 0 | 0 | 4186.05 | 80.86 | 0 | 0 | 0 | 4266.91 | 315813.97 | 320080.88 | 0 | [6 empty] | CM_WWI | 100%
400284 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-03-17 | 2012-02-28 | 2012-04-02 | 2013-03-06 |  | South Lanarkshire | 640273 | 1722 | -1163.97 | 0 | 0 | 0 | 0 | 558.03 | 0 | 640831.03 | 0 | [6 empty] | CM_WSI | 100%
400285 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-03-17 | 2012-09-21 | 2013-05-28 | 2014-07-07 |  | South Lanarkshire | 428665 | 13428 | -5899.02 | 0 | 0 | 0 | 0 | 7528.98 | 0 | 436193.98 | 0 | [6 empty] | CM_WSI | 100%
401499 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2010-10-20 | 2012-06-14 | 2012-08-27 | 2020-01-29 | 2020-01-29 | All South Unitary Authorities | 138815 | 13098 | 12003.59 | 40027.41 | 131792.51 | 14974.04 | 5369.34 | 217264.89 | 6575.01 | 362654.9 | 0 | [6 empty] | CM_WSI | 100%
401459 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-10-06 | 2011-01-11 | 2011-04-29 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 909744.8 | 0.2 | -118931.62 | 0 | 0 | 0 | 0 | -118931.42 | 0 | 790813.38 | 0 | [6 empty] | CM_WSI | 100%
300011 | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2010-10-28 | 2019-03-28 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 347516.84 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0.16 | 0 | 347517 | 11 | [6 empty] | EC01 | 100%
401461 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2010-10-06 | 2019-03-28 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 37133 | 0 | -3556.16 | 0 | 0 | 0 | 0 | -3556.16 | 0 | 33576.84 | 0 | [6 empty] | SG1 | 100%
401460 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-10-01 | 2019-03-28 | 2019-03-28 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 308210.28 | -0.28 | 0 | 0 | 0 | 0 | 0 | -0.28 | 0 | 308210 | 0 | [6 empty] | CM_WSI | 100%
401462 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2010-10-01 | 2019-03-28 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 130463 | 0 | 38949.5 | 0 | 0 | 0 | 0 | 38949.5 | 0 | 169412.5 | 0 | [6 empty] | SG1 | 100%
402638 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-04-16 | 2012-04-16 | 2012-05-01 | 2015-11-10 |  | All North Unitary Authorities | 42000 | -41999 | 0 | 0 | 0 | 0 | 0 | -41999 | 0 | 1 | 0 | [6 empty] | CM_WWI | 100%
501108 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS5 | 2015-09-30 | 2017-02-27 | 2017-06-22 | 2018-07-01 | 2019-01-01 | East Lothian | 0 | 600 | 9728.23 | 31652.77 | 19464 | 114 | 0 | 61559 | 0 | 61559 | 9676.0339 | [6 empty] | EC01D | 100% | bar: Regulatory Outputs OMG-23
403531 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2015-03-02 | 2015-03-03 | 2015-03-04 | 2015-03-04 | 2015-03-04 | East Lothian | 75343.95 | 0 | 124.25 | 0 | 82.56 | 0 | 0 | 206.81 | 0 | 75550.76 | 0 | [6 empty] | SG1 | 100%
500963 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-08-22 | 2018-08-22 | 2018-08-22 | 2018-08-22 | 2018-08-22 | East Lothian | 0 | 87789.66 | 141648.39 | 16435.888 | 1608.737 | 0 | 0 | 247482.675 | 0 | 247482.675 | 148885.7057 | [6 empty] | SG1 | 100%
503060 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | GW0 | 2021-03-31 | 2022-09-27 | 2023-01-19 | 2024-01-15 | 2024-04-16 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 1010526.9735 | 406396.44 | 523003.59 | 1939927.0035 | 0 | 1939927.0035 | 2182257.8406 | [6 empty] | EC01A_ID | 100%
403598 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-09-25 | 2013-09-25 | 2014-01-15 | 2015-01-23 |  | Highland | 14404.92 | 0 | 0 | 8.84 | 0 | 0 | 0 | 8.84 | 0 | 14413.76 | 0 | [6 empty] | CM_WSI | 100%
500755 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS0 | 2016-06-28 | 2019-12-09 | 2020-03-30 | 2021-03-23 | 2021-06-23 | Highland | 0 | 0 | 22086.21 | 67342.95 | 26493.68 | 287665.21 | 345996.52 | 749584.57 | 24415.48 | 774000.05 | 0 | [6 empty] | CM_WSNI | 100%
404137 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS3 | 2015-02-06 | 2019-03-20 | 2019-03-20 | 2020-06-01 | 2020-09-01 | Na H-Eileanan an Iar | 0 | 0 | 0 | 83414.63 | 2567597.37 | 1334814.11 | 889055.35 | 4874881.46 | 45662.62 | 4920544.08 | 0 |  |  |  |  | 22230 |  | DW13 | 100% | bar: Regulatory Outputs OMG-03
404097 | Q&S3B | Completion | OMG180 |  |  | Water |  | WINF | OMG180 | MS7 | 2015-02-06 | 2019-01-30 | 2019-01-30 | 2019-01-30 | 2019-01-30 | Na H-Eileanan an Iar | 12804.88 | 155131.12 | -213593.29 | 45755.63 | 27369.829 | 0 | 0 | 14663.289 | 0 | 27468.169 | 0 | [6 empty] | DW13 | 100%
500927 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2017-03-13 | 2017-03-13 | 2016-12-08 | 2017-03-13 | All West Unitary Authorities | 0 | 6000 | -452.9 | 0 | 0 | 0 | 0 | 5547.1 | 0 | 5547.1 | 144841.4737 | [6 empty] | CS15A | 100%
501098 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS3 | 2015-09-30 | 2016-09-27 | 2016-09-29 | 2019-08-01 | 2019-11-01 | North Lanarkshire | 0 | 3934 | 43642.05 | 7223.95 | 26700 | 10500.01 | 0 | 92000.01 | 0 | 92000.01 | 0 | [6 empty] | EC10D | 100% | [18 empty] | Regulatory Outputs OMG-23: 2
500867 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS2 | 2016-09-06 | 2018-09-20 | 2018-12-10 | 2019-12-12 | 2020-12-15 | Na H-Eileanan an Iar | 0 | 4388.67 | 16878.57 | 16737.51 | 166645.22 | 128931.08 | 0 | 333581.05 | 0 | 333581.05 | 248719.4753 | [6 empty] | DW5FS | 100%
502552 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-08-01 | 2018-08-01 | 2018-07-31 | 2018-07-31 | 2018-07-31 | Midlothian | 0 | 0 | 38756.46 | 20101.521 | -10884.64 | 0 | 0 | 47973.341 | 0 | 47973.341 | 148885.7057 | [6 empty] | SG1 | 100%
501409 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2021-12-03 | 2022-09-20 | 2023-01-24 | 2023-06-05 | 2023-09-05 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1499999.97 | 1499999.97 | 0 | [6 empty] | CM_WSI | 100%
501040 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS0 | 2018-03-30 | 2019-05-27 | 2019-09-23 | 2020-07-01 | 2020-10-01 | Orkney Islands | 0 | 4293.78 | 11.86 | 8280.651 | 51690.124 | 275634.59 | 248711.86 | 588622.865 | 5195.7 | 593818.565 | 292238.8135 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
045035 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-17 | 2012-09-11 | 2013-01-21 | 2013-07-11 | 2015-12-15 | Orkney Islands | 229994.37 | -1068.33 | 0 | 0 | 0 | 0 | 0 | -1068.33 | 0 | 228926.04 | 604 | [6 empty] | DW23 | 100%
402166 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2011-09-12 | 2013-06-26 | 2013-08-29 | 2014-06-25 |  | Shetland Islands | 315974 | 0 | -1845.69 | 0 | 0 | 0 | 0 | -1845.69 | 0 | 314128.31 | 0 | [6 empty] | CM_WWNI | 100%
402175 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-07-11 | 2012-08-29 | 2012-11-16 | 2014-09-16 | 2014-09-16 | Scottish Water Wide | 520747.18 | 6611.33 | -11908.06 | 0 | 0 | 0 | 0 | -5296.73 | 0 | 515450.45 | 0 | [6 empty] | CM_WSI | 100%
500482 | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWMD | Renewable power | MS6 | 2015-05-18 | 2015-06-30 | 2015-08-24 | 2017-03-01 | 2017-03-01 | Stirling | 0 | 1711983.15 | 165771.85 | 79808.113 | 8120.827 | 1000.01 | 0 | 1966683.95 | 0 | 1966683.95 | 764721.6298 | [6 empty] | I2S_WI | 100% | [18 empty] | Regulatory Outputs OMG-43: 0.59
402698 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-07-23 | 2013-07-29 | 2013-09-09 | 2014-04-03 |  | Shetland Islands | 311693 | 11988.21 | -101.07 | 0 | 0 | 0 | 0 | 11887.14 | 0 | 323580.14 | 0 | [6 empty] | CM_WSI | 100%
033155 | Q&S4 | Supporting economic development | NRSWA |  |  | General |  | SWMD | NRSWA | MS7 | 2006-01-20 | 2008-07-08 | 2010-04-27 | 2010-05-03 |  | City of Edinburgh | 7867844 | -250000 | 0 | 0 | 0 | 0 | 0 | -250000 | 0 | 7617844 | 0 | [6 empty] | CM_WSI | 50% | CM_WWI | 50%
401081 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2010-06-24 | 2010-06-24 | 2005-02-21 | 2015-08-28 |  | Scottish Water Wide | 78400 | -12074.6 | 0 | 0 | 0 | 0 | 0 | -12074.6 | 0 | 66325.4 | 0 | [6 empty] | CM_WWI | 100%
401082 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2010-06-24 | 2010-06-24 | 2005-02-21 | 2015-08-28 |  | Scottish Water Wide | 316229 | 26947.1 | 0 | 0 | 0 | 0 | 0 | 26947.1 | 0 | 343176.1 | 0 | [6 empty] | CM_WSI | 100%
400324 | Q&S4 | Supporting economic development | NRSWA |  |  | General |  | SWMD | NRSWA | MS3 | 2006-01-20 | 2008-06-18 | 2010-12-01 | 2023-04-14 |  | City of Edinburgh | 3635779 | -73716.56 | 102647.56 | 21628.233 | 45367.767 | 14912.18 | 16047.78 | 126886.96 | 947399 | 4710064.96 | 0 | [6 empty] | TIE | 100%
402232 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-06-23 |  |  | 2011-12-07 |  | Angus | 2527.26 | 0 | 0 | 0 | 35.22 | 0 | 0 | 35.22 | 0 | 2562.48 | 0 | [6 empty] | CM_WSI | 100%
402102 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2011-04-26 |  |  | 2013-07-10 |  | Moray | 249611.31 | 83637.89 | 18136.03 | 271.03 | 183.66 | 0 | 0 | 102228.61 | 0 | 351839.92 | 0 | [6 empty] | CM_WWI | 100%
502832 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2017-07-25 | 2018-03-29 | 2018-08-23 | 2022-10-31 | 2022-10-31 | Scottish Borders | 0 | 0 | 0 | 45177.25 | 36436.75 | 38851.48 | 171522.81 | 291988.29 | 326146.7 | 618134.99 | 48164.5084 | [6 empty] | CS23W | 100%
403062 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-10-23 |  |  | 2015-08-28 |  | Scottish Water Wide | 64356 | -11793.29 | 0 | 0 | 0 | 0 | 0 | -11793.29 | 0 | 52562.71 | 0 | [6 empty] | CM_WWI | 100%
500783 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MS5 | 2015-08-24 | 2021-04-29 | 2021-04-29 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 0 | 57103 | 46133.64 | 36345.503 | 4505.707 | 0 | 0 | 144087.85 | 0 | 144087.85 | 3112230.0788 | [6 empty] | CS23S | 100%
503299 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MS0 | 2018-07-26 | 2021-06-01 | 2021-06-02 | 2021-06-02 | 2021-08-03 | Scottish Water Wide | 0 | 0 | 0 | 0 | 57992.84 | 19479.96 | 19234.18 | 96706.98 | 3293.01 | 99999.99 | 948832.8374 | [6 empty] | CS23S | 100%
400744 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2009-04-21 | 2012-08-15 | 2012-12-17 | 2014-10-23 |  | North Lanarkshire | 149438.69 | 0 | 0 | 0 | 85.16 | 0 | 0 | 85.16 | 0 | 149523.85 | 0 | [6 empty] | CM_WWI | 100%
402917 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-08-27 |  |  | 2013-04-10 |  | Highland | 1182.25 | 0 | 0 | 0 | 26.415 | 0 | 0 | 26.415 | 0 | 1208.665 | 0 | [6 empty] | CM_WSI | 100%
503453 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS2 | 2019-02-22 | 2019-03-25 | 2019-06-10 | 2019-09-27 | 2019-10-25 | Aberdeen City | 0 | 0 | 0 | 0 | 11876.7 | 168406.21 | 0 | 180282.91 | 0 | 180282.91 | 48164.5084 | [6 empty] | CS23W | 100%
403063 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-10-23 | 2012-11-05 | 2013-01-11 | 2015-08-28 |  | Scottish Water Wide | 264292.42 | 106363.72 | 272.19 | 361.833 | 1984.136 | 0 | 0 | 108981.879 | 0 | 373274.299 | 0 | [6 empty] | CM_WSI | 100%
500782 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS5 | 2015-09-04 | 2021-04-29 | 2021-04-29 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 0 | 73930 | 328156.79 | 216767.269 | 446.461 | 0 | 0 | 619300.52 | 0 | 619300.52 | 48164.5084 | [6 empty] | CS23W | 100%
503298 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS0 | 2018-07-26 | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2021-06-18 | Scottish Water Wide | 0 | 0 | 0 | 0 | 152703.0893 | 123947.74 | 108207.16 | 384857.9893 | 15578.46 | 400436.4493 | 2249750.5038 | [6 empty] | CS23W | 100%
402196 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2011-06-15 | 2011-10-31 | 2012-01-09 | 2015-06-30 |  | North Lanarkshire | 131668 | 44945.24 | 0 | 0 | 0 | 0 | 0 | 44945.24 | 0 | 176613.24 | 0 | [6 empty] | CM_WWI | 100%
402608 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-03-30 | 2012-08-29 | 2012-12-03 | 2014-10-20 |  | Stirling | 61810.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61810.68 | 0 | [6 empty] | CM_WSI | 100%
403557 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-08-20 | 2014-04-17 | 2014-04-25 | 2014-12-09 |  | North Lanarkshire | 50870 | -336.17 | 0 | 0 | 0 | 0 | 0 | -336.17 | 0 | 50533.83 | 0 | [6 empty] | CM_WSI | 100%
403584 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-09-03 | 2014-04-02 | 2014-04-04 | 2015-01-27 |  | Falkirk | 196421 | 959.14 | 0 | 0 | 0 | 0 | 0 | 959.14 | 0 | 197380.14 | 0 | [6 empty] | CM_WSI | 100%
402702 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-06-05 | 2014-01-21 | 2014-06-16 | 2015-08-03 |  | City of Edinburgh | 2514139 | 39063 | -0.04 | -43418.63 | 0 | 0 | 0 | -4355.67 | 0 | 2509783.33 | 0 | [6 empty] | CM_WWI | 100%
402651 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-04-30 | 2012-11-30 | 2012-12-10 | 2014-04-01 |  | City of Edinburgh | 248616.33 | 6862.93 | 0 | 0 | 0 | 0 | 0 | 6862.93 | 0 | 255479.26 | 0 | [6 empty] | CM_WWI | 100%
402267 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-07-21 | 2012-11-16 | 2012-11-30 | 2015-02-02 |  | Fife | 181333 | -3078.09 | 0 | 0 | 0 | 0 | 0 | -3078.09 | 0 | 178254.91 | 0 | [6 empty] | CM_WSI | 100%
402494 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-01-26 | 2012-02-19 | 2012-03-12 | 2014-12-01 |  | Falkirk | 62272 | 881.95 | 4.45 | 0 | 0 | 0 | 0 | 886.4 | 0 | 63158.4 | 0 | [6 empty] | CM_WSI | 100%
403203 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-12-17 | 2013-08-20 | 2013-08-28 | 2016-01-20 |  | Scottish Borders | 1620673 | 156998.7 | -52485.44 | 0 | 0 | 0 | 0 | 104513.26 | 0 | 1725186.26 | 0 | [6 empty] | CM_WWI | 100%
403574 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2013-08-21 | 2014-02-28 | 2014-03-06 | 2014-10-07 |  | Scottish Borders | 4994.24 | 1143 | 0 | 0 | 0 | 0 | 0 | 1143 | 0 | 6137.24 | 0 | [6 empty] | CM_WWI | 100%
403421 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2013-03-15 | 2013-12-16 | 2014-02-20 | 2015-03-19 |  | Scottish Borders | 632218.27 | 226594.31 | 0 | 0 | 0 | 0 | 0 | 226594.31 | 0 | 858812.58 | 0 | [6 empty] | CM_WWI | 100%
403612 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2013-10-22 | 2014-10-08 | 2014-10-13 | 2016-02-01 |  | City of Edinburgh | 133491 | 534515 | 134264.43 | 22481.88 | -28405.8 | 0 | 0 | 662855.51 | 0 | 796346.51 | 0 | [6 empty] | CM_WWI | 100%
402820 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2013-05-13 | 2013-05-20 | 2014-12-10 |  | North Lanarkshire | 818395 | -508.38 | 0 | 0 | 0 | 0 | 0 | -508.38 | 0 | 817886.62 | 0 | [6 empty] | CM_WWI | 100%
403711 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2014-03-07 | 2014-04-25 | 2014-06-03 | 2014-12-10 |  | North Lanarkshire | 1243427.56 | 0 | -37131.72 | 0 | 0 | 0 | 0 | -37131.72 | 0 | 1206295.84 | 0 | [6 empty] | CM_WWI | 100%
402819 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2013-09-25 | 2013-10-07 | 2016-08-22 |  | North Lanarkshire | 395352 | 1011323 | -81952.5 | 0 | 0 | 0 | 0 | 929370.5 | 0 | 1324722.5 | 0 | [6 empty] | CM_WWI | 100%
402818 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2014-01-21 | 2014-08-18 | 2015-02-16 |  | North Lanarkshire | 450526 | -78961.1 | 0 | 0 | 0 | 0 | 0 | -78961.1 | 0 | 371564.9 | 0 | [6 empty] | CM_WWI | 100%
402817 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2013-03-27 | 2013-04-29 | 2015-02-16 |  | North Lanarkshire | 848731.31 | 1488.73 | 0 | 0 | 0 | 0 | 0 | 1488.73 | 0 | 850220.04 | 0 | [6 empty] | CM_WWI | 100%
402805 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2014-09-15 | 2015-01-26 | 2015-10-07 |  | North Lanarkshire | 696853 | 707751.96 | 166.08 | 0 | 0 | 0 | 0 | 707918.04 | 0 | 1404771.04 | 0 | [6 empty] | CM_WWI | 100%
402804 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2015-09-30 | 2015-09-30 | 2017-12-08 |  | North Lanarkshire | 279209 | 50217 | 203062 | 1435178.3 | 1717.2825 | 0 | 0 | 1690174.5825 | 0 | 1969383.5825 | 0 | [6 empty] | CM_WWI | 100%
402803 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2014-09-18 | 2015-01-23 | 2015-09-08 |  | North Lanarkshire | 482544 | 549610.81 | 0 | 0 | 0 | 0 | 0 | 549610.81 | 0 | 1032154.81 | 0 | [6 empty] | CM_WWI | 100%
402812 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-08-07 | 2014-09-15 | 2014-11-20 |  | North Lanarkshire | 52660 | -13887.54 | 0 | 0 | 0 | 0 | 0 | -13887.54 | 0 | 38772.46 | 0 | [6 empty] | CM_WWI | 100%
402809 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-11-06 | 2015-05-18 | 2015-07-01 |  | North Lanarkshire | 51923 | 4461.95 | 0 | 0 | 0 | 0 | 0 | 4461.95 | 0 | 56384.95 | 0 | [6 empty] | CM_WWI | 100%
402808 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2015-03-17 | 2015-07-31 | 2017-03-01 |  | North Lanarkshire | 86749.38 | 308022.62 | 1393267 | -53896.84 | 1043.801 | 0 | 0 | 1648436.581 | 0 | 1735185.961 | 0 | [6 empty] | CM_WWI | 100%
402806 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-03-24 | 2014-09-22 | 2016-08-22 |  | North Lanarkshire | 342.94 | 74.98 | 291.2 | 0 | 0 | 0 | 0 | 366.18 | 0 | 709.12 | 0 | [6 empty] | CM_WWI | 100%
403489 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2013-05-08 | 2014-05-20 | 2014-06-18 | 2015-03-13 |  | Fife | 19159 | 911.46 | 0 | 0 | 0 | 0 | 0 | 911.46 | 0 | 20070.46 | 0 | [6 empty] | CM_WWI | 100%
403518 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2013-07-11 | 2014-09-08 | 2014-11-24 | 2016-06-24 |  | Aberdeen City | 171725 | 31045 | -275.95 | 0 | 0 | 0 | 0 | 30769.05 | 0 | 202494.05 | 0 | [6 empty] | CM_WWI | 100%
403620 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2013-12-10 | 2014-07-22 | 2014-08-05 | 2014-08-08 |  | Scottish Borders | 308.66 | 0 | 0 | 0 | -278.85 | 0 | 0 | -278.85 | 0 | 29.81 | 0 | [6 empty] | CM_WWI | 100%
403621 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2013-12-10 | 2014-05-30 | 2014-06-09 | 2014-12-03 |  | Scottish Borders | 210336 | -26756.92 | 0 | 0 | 0 | 0 | 0 | -26756.92 | 0 | 183579.08 | 0 | [6 empty] | CM_WWI | 100%
500691 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2015-06-09 | 2015-08-26 | 2015-09-22 | 2016-06-29 | 2016-07-22 | Scottish Borders | 0 | 115651.89 | 3136.1 | 0 | 0 | 0 | 0 | 118787.99 | 0 | 118787.99 | 0 | [6 empty] | CM_WWI | 100%
403651 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | WINF | NRSWA | MS3 | 2014-01-20 | 2015-04-30 | 2015-08-31 | 2019-09-13 |  | Aberdeen City | 236758.42 | 598351.58 | 67232.39 | 293124.16 | 750540.64 | 95931.81 | 0 | 1805180.58 | 0 | 2041939 | 0 | [6 empty] | CM_WWI | 100%
402534 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-02-07 | 2012-04-18 | 2012-04-23 | 2013-06-28 |  | Angus | 64087.6 | 575.88 | 0 | 0 | 0 | 0 | 0 | 575.88 | 0 | 64663.48 | 0 | [6 empty] | CM_WSI | 100%
403521 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-06-27 | 2014-03-17 | 2014-06-16 | 2016-04-07 |  | Aberdeen City | 53008 | 276818 | -15058.63 | 0 | 0 | 0 | 0 | 261759.37 | 0 | 314767.37 | 0 | [6 empty] | CM_WSI | 100%
403319 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-02-04 | 2013-05-15 | 2013-05-28 | 2016-09-28 |  | Dundee City | 12008 | 461 | 727.74 | 9880.16 | 0 | 0 | 0 | 11068.9 | 0 | 23076.9 | 0 | [6 empty] | CM_WSI | 100%
401714 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2010-12-14 | 2011-08-01 | 2012-05-25 | 2014-11-18 |  | Scottish Borders | 1012352 | -16339.3 | 0 | 0 | 0 | 0 | 0 | -16339.3 | 0 | 996012.7 | 0 | [6 empty] | CM_WSI | 100%
403708 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-02-04 | 2014-03-25 | 2014-03-31 | 2014-11-18 |  | Scottish Borders | 582388.63 | -12482.62 | 0 | 0 | 0 | 0 | 0 | -12482.62 | 0 | 569906.01 | 0 | [6 empty] | CM_WSI | 100%
403211 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-12-17 | 2013-11-12 | 2013-12-12 | 2015-08-05 |  | Scottish Borders | 388894 | 4819.8 | 128 | 0 | 0 | 0 | 0 | 4947.8 | 0 | 393841.8 | 0 | [6 empty] | CM_WSI | 100%
403818 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-05-27 | 2014-10-09 | 2014-10-20 | 2015-06-01 |  | Perth and Kinross | 35380 | 759.77 | 0 | 0 | 0 | 0 | 0 | 759.77 | 0 | 36139.77 | 0 | [6 empty] | CM_WSI | 100%
403524 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-06-27 | 2014-03-27 | 2014-04-28 | 2015-03-13 |  | City of Edinburgh | 43470.95 | 20.44 | 0 | 0 | 0 | 0 | 0 | 20.44 | 0 | 43491.39 | 0 | [6 empty] | CM_WSI | 100%
403381 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-02-21 | 2013-04-25 | 2013-04-29 | 2013-09-25 |  | Aberdeenshire | 24064 | 0 | 0 | 0 | 10.33 | 0 | 0 | 10.33 | 0 | 24074.33 | 0 | [6 empty] | CM_WSI | 100%
403871 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-06-30 | 2014-08-29 | 2014-09-26 | 2015-04-24 |  | South Ayrshire | 27667 | -127.92 | 0 | 0 | 0 | 0 | 0 | -127.92 | 0 | 27539.08 | 0 | [6 empty] | CM_WSI | 100%
403872 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-06-30 | 2014-08-29 | 2015-01-23 | 2015-03-17 |  | Dumfries and Galloway | 23689 | 13945.83 | 0 | 0 | 0 | 0 | 0 | 13945.83 | 0 | 37634.83 | 0 | [6 empty] | CM_WSI | 100%
403484 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-05-10 | 2014-06-27 | 2014-08-13 | 2015-09-10 |  | North Lanarkshire | 70808 | 103213 | 0 | 0 | 0 | 0 | 0 | 103213 | 0 | 174021 | 0 | [6 empty] | CM_WSI | 100%
402790 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-02-19 | 2014-05-12 | 2015-12-01 |  | North Lanarkshire | 66555 | 80910.56 | 0 | 0 | 0 | 0 | 0 | 80910.56 | 0 | 147465.56 | 0 | [6 empty] | CM_WSI | 100%
402794 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-04-11 | 2014-07-07 | 2015-12-21 |  | North Lanarkshire | 117997 | 69638.01 | 468.13 | 0 | 0 | 0 | 0 | 70106.14 | 0 | 188103.14 | 0 | [6 empty] | CM_WSI | 100%
403483 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-05-10 | 2014-07-17 | 2014-07-18 | 2016-07-28 |  | North Lanarkshire | 307941 | 252602.73 | 561747.93 | 0 | 0 | 0 | 0 | 814350.66 | 0 | 1122291.66 | 0 | [6 empty] | CM_WSI | 100%
402795 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-03-05 | 2014-05-12 | 2015-12-01 |  | North Lanarkshire | 378919 | 402354.96 | -128.87 | 0 | 0 | 0 | 0 | 402226.09 | 0 | 781145.09 | 0 | [6 empty] | CM_WSI | 100%
402793 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-03-05 | 2014-05-05 | 2015-12-14 |  | North Lanarkshire | 168811 | -7932 | 5898.38 | 0 | 0 | 0 | 0 | -2033.62 | 0 | 166777.38 | 0 | [6 empty] | CM_WSI | 100%
402797 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-03-05 | 2014-06-02 | 2015-04-21 |  | North Lanarkshire | 109102 | 9916.27 | 0 | 0 | 0 | 0 | 0 | 9916.27 | 0 | 119018.27 | 0 | [6 empty] | CM_WSI | 100%
402798 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2014-07-01 | 2015-06-22 | 2016-09-19 |  | North Lanarkshire | 203092.27 | 1234625.92 | 158723.06 | 0 | 0 | 0 | 0 | 1393348.98 | 0 | 1596441.25 | 0 | [6 empty] | CM_WSI | 100%
402786 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-10 | 2014-11-25 | 2015-01-12 | 2016-09-19 |  | North Lanarkshire | 61016.23 | 105306.77 | 175746.35 | 0 | 0 | 0 | 0 | 281053.12 | 0 | 342069.35 | 0 | [6 empty] | CM_WSI | 100%
402800 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-10-28 | 2014-10-30 | 2015-09-16 |  | North Lanarkshire | 146485 | 139068.3 | 36380.86 | 45.165 | 0 | 0 | 0 | 175494.325 | 0 | 321979.325 | 0 | [6 empty] | CM_WSI | 100%
402801 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-06-30 | 2014-07-21 | 2015-02-23 |  | North Lanarkshire | 13798.59 | 5709.83 | 0 | 0 | 0 | 0 | 0 | 5709.83 | 0 | 19508.42 | 0 | [6 empty] | CM_WSI | 100%
402799 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2015-03-16 | 2015-08-12 | 2016-02-10 |  | North Lanarkshire | 31079.34 | 93575.66 | 1977.86 | 0 | 0 | 0 | 0 | 95553.52 | 0 | 126632.86 | 0 | [6 empty] | CM_WSI | 100%
403634 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-12-16 | 2015-02-23 | 2016-02-22 | 2016-11-11 |  | North Lanarkshire | 35529 | 2893 | 35457.24 | 20515.6 | 0 | 0 | 0 | 58865.84 | 0 | 94394.84 | 0 | [6 empty] | CM_WSI | 100%
403635 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-12-16 | 2014-12-05 | 2015-02-27 | 2015-10-10 |  | North Lanarkshire | 40821 | 170535.88 | 0 | 0 | 0 | 0 | 0 | 170535.88 | 0 | 211356.88 | 0 | [6 empty] | CM_WSI | 100%
402787 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-19 | 2013-08-21 | 2013-09-19 | 2015-04-21 |  | North Lanarkshire | 149199.15 | -7119.32 | 0 | 0 | 0 | 0 | 0 | -7119.32 | 0 | 142079.83 | 0 | [6 empty] | CM_WSI | 100%
403784 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-05-13 | 2015-01-27 | 2015-07-30 | 2016-05-31 |  | North Lanarkshire | 10919 | 137193 | 162253.08 | 0 | 0 | 0 | 0 | 299446.08 | 0 | 310365.08 | 0 | [6 empty] | CM_WSI | 100%
403633 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-12-16 | 2015-01-29 | 2015-01-28 | 2015-12-21 |  | North Lanarkshire | 493356 | 834996.97 | 0 | 0 | 0 | 0 | 0 | 834996.97 | 0 | 1328352.97 | 0 | [6 empty] | CM_WSI | 100%
403869 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-06-30 | 2015-02-27 | 2015-03-16 | 2015-09-16 |  | North Lanarkshire | 155535.02 | 195444.44 | 0 | 422.45 | 0 | 0 | 0 | 195866.89 | 0 | 351401.91 | 0 | [6 empty] | CM_WSI | 100%
402785 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-06-29 | 2014-08-05 | 2014-11-03 | 2015-10-10 |  | North Lanarkshire | 87941 | 8281.46 | 0 | 0 | 0 | 0 | 0 | 8281.46 | 0 | 96222.46 | 0 | [6 empty] | CM_WSI | 100%
402788 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-02-13 | 2014-06-23 | 2015-07-08 |  | North Lanarkshire | 353562 | 199010.19 | 0 | 0 | 0 | 0 | 0 | 199010.19 | 0 | 552572.19 | 0 | [6 empty] | CM_WSI | 100%
402789 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-02-27 | 2014-06-30 | 2016-02-18 |  | North Lanarkshire | 266427 | 345968.31 | 24522.29 | 0 | 0 | 0 | 0 | 370490.6 | 0 | 636917.6 | 0 | [6 empty] | CM_WSI | 100%
402791 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-16 | 2013-09-24 | 2013-10-07 | 2015-01-15 |  | North Lanarkshire | 1293564 | -242038.84 | 0 | 0 | 0 | 0 | 0 | -242038.84 | 0 | 1051525.16 | 0 | [6 empty] | CM_WSI | 100%
403742 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-03-07 | 2014-04-29 | 2014-05-22 | 2015-01-26 |  | North Lanarkshire | 660774 | 595.74 | 0 | 0 | 0 | 0 | 0 | 595.74 | 0 | 661369.74 | 0 | [6 empty] | CM_WSI | 100%
402792 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-07-02 | 2014-03-05 | 2014-05-12 | 2017-03-08 |  | North Lanarkshire | 275547 | 57936 | -18696 | 62051.85 | 0 | 0 | 0 | 101291.85 | 0 | 376838.85 | 0 | [6 empty] | CM_WSI | 100%
403488 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-05-08 | 2014-05-20 | 2014-06-09 | 2015-07-06 |  | Fife | 36261 | 673.01 | 0 | 0 | 0 | 0 | 0 | 673.01 | 0 | 36934.01 | 0 | [6 empty] | CM_WSI | 100%
403525 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-06-27 | 2014-03-27 | 2014-06-09 | 2015-11-02 |  | City of Edinburgh | 130465 | 61267.1 | 0 | 0 | 0 | 0 | 0 | 61267.1 | 0 | 191732.1 | 0 | [6 empty] | CM_WSI | 100%
403534 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-07-11 | 2014-03-03 | 2014-03-13 | 2015-02-02 |  | Perth and Kinross | 23185.95 | 445.95 | 0 | 0 | 0 | 0 | 0 | 445.95 | 0 | 23631.9 | 0 | [6 empty] | CM_WSI | 100%
403519 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-06-27 | 2014-09-11 | 2014-11-24 | 2016-06-29 |  | Aberdeen City | 246797 | 87388 | 48234.58 | 273.45 | 0 | 0 | 0 | 135896.03 | 0 | 382693.03 | 0 | [6 empty] | CM_WSI | 100%
403905 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-08-20 | 2014-09-19 | 2014-12-05 | 2015-03-12 |  | South Lanarkshire | 8327 | -1396.18 | 0 | 0 | 0 | 0 | 0 | -1396.18 | 0 | 6930.82 | 0 | [6 empty] | CM_WSI | 100%
403652 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | WINF | NRSWA | MS3 | 2014-01-16 | 2015-04-28 | 2015-06-29 | 2019-12-20 |  | Aberdeen City | 800753 | 3456914.85 | 2568606.87 | 2709028.28 | 1572245.43 | 669183.92 | 2181.62 | 10978160.97 | 0 | 11778913.97 | 0 | [6 empty] | CM_WSI | 100%
403622 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-12-10 | 2014-07-22 | 2014-08-15 | 2015-06-25 |  | Scottish Borders | 18526 | -7844.14 | 0 | 0 | 0 | 0 | 0 | -7844.14 | 0 | 10681.86 | 0 | [6 empty] | CM_WSI | 100%
403260 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-01-15 | 2014-02-13 | 2014-02-26 | 2015-09-01 |  | Fife | 89591 | -3016.5 | 0 | 0 | 0 | 0 | 0 | -3016.5 | 0 | 86574.5 | 0 | [6 empty] | CM_WSI | 100%
402739 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-09-04 | 2012-12-12 | 2013-01-07 | 2013-09-24 |  | East Ayrshire | 68672 | -2327.66 | 0 | 0 | 0 | 0 | 0 | -2327.66 | 0 | 66344.34 | 0 | [6 empty] | CM_WSI | 100%
403932 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-10-10 | 2015-01-22 | 2015-02-12 | 2016-02-01 |  | South Lanarkshire | 47986.53 | 217.45 | 0 | 0 | 0 | 0 | 0 | 217.45 | 0 | 48203.98 | 0 | [6 empty] | CM_WSI | 100%
500692 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-06-09 | 2015-09-30 | 2016-08-18 | 2017-05-04 | 2017-05-04 | Fife | 0 | 21180 | -11838.08 | -4107.04 | 0 | 0 | 0 | 5234.88 | 0 | 5234.88 | 0 | [6 empty] | CM_WSI | 100%
403806 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-05-19 | 2014-11-20 | 2014-12-24 | 2015-10-22 |  | Aberdeenshire | 17336 | 13787.42 | 0 | 0 | 0 | 0 | 0 | 13787.42 | 0 | 31123.42 | 0 | [6 empty] | CM_WSI | 100%
404011 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-12-08 | 2015-05-11 | 2015-05-19 | 2016-12-23 |  | Falkirk | 23973 | 117540 | 26725.8 | 17444.39 | 0 | 0 | 0 | 161710.19 | 0 | 185683.19 | 0 | [6 empty] | CM_WSI | 100%
403933 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-10-29 | 2015-03-31 | 2015-06-01 | 2015-10-27 |  | Highland | 15150 | 21737.34 | 0 | 0 | 0 | 0 | 0 | 21737.34 | 0 | 36887.34 | 0 | [6 empty] | CM_WSI | 100%
404012 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2014-12-10 | 2015-05-11 | 2015-05-12 | 2017-10-11 |  | North Lanarkshire | 1850 | 244422 | 438877 | 205311.01 | 52.47 | 0 | 0 | 888662.48 | 0 | 890512.48 | 0 | [6 empty] | CM_WSI | 100%
501176 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-10-28 | 2016-09-26 | 2016-09-27 | 2017-03-27 | 2017-03-27 | Argyll and Bute-North Argyll | 0 | 14000 | 31250.88 | -359.6 | 0 | 0 | 0 | 44891.28 | 0 | 44891.28 | 48164.5084 | [6 empty] | CS23W | 100%
403438 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-03-29 | 2013-11-21 | 2013-11-21 | 2016-03-24 |  | Dumfries and Galloway | 255314 | 174943 | 752.25 | 0 | 0 | 0 | 0 | 175695.25 | 0 | 431009.25 | 0 | [6 empty] | CM_WSI | 100%
403326 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2013-01-28 | 2013-09-18 | 2013-10-28 | 2015-04-22 |  | South Ayrshire | 317957 | -22017.24 | 0 | 0 | 0 | 0 | 0 | -22017.24 | 0 | 295939.76 | 0 | [6 empty] | CM_WSI | 100%
403075 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-10-25 | 2014-02-27 | 2014-06-17 | 2014-12-17 |  | Falkirk | 44926 | 220.1 | 0 | 0 | 0 | 0 | 0 | 220.1 | 0 | 45146.1 | 0 | [6 empty] | CM_WSI | 100%
401453 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2010-09-24 | 2011-11-01 | 2011-10-31 | 2012-06-19 |  | West Lothian | 21041.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21041.64 | 0 | [6 empty] | CM_WSI | 100%
404113 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2015-03-03 | 2015-09-14 | 2015-09-14 | 2015-09-09 |  | Angus | 47.16 | 326.18 | 0 | 0 | 0 | 0 | 0 | 326.18 | 0 | 373.34 | 0 | [6 empty] | CM_WWI | 100%
404016 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | WINF | NRSWA | MS4 | 2014-12-05 | 2015-05-29 | 2016-08-22 | 2017-08-31 |  | Aberdeen City | 29431 | 31033 | 357429.52 | 141873.83 | -54910.91 | 0 | 0 | 475425.44 | 0 | 504856.44 | 0 | [6 empty] | CM_WWI | 100%
500693 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-06-05 | 2015-09-24 | 2015-11-30 | 2017-11-15 | 2017-11-15 | Midlothian | 0 | 618815 | 1448319.37 | 1894699.53 | 29375.277 | 0 | 0 | 3991209.177 | 0 | 3991209.177 | 48164.5084 | [6 empty] | CS23W | 100%
404129 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-06-02 | 2015-07-07 | 2015-07-27 | 2015-11-23 |  | Stirling | 0 | 92121.18 | 0 | 0 | 0 | 0 | 0 | 92121.18 | 0 | 92121.18 | 0 | [6 empty] | CM_WSI | 100%
404128 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-06-02 | 2015-09-28 | 2015-10-26 | 2019-02-28 |  | Moray | 0 | 68865 | -46982 | 0 | 77868.876 | 0 | 0 | 99751.876 | 0 | 99751.876 | 0 | [6 empty] | CM_WSI | 100%
404111 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-03-03 | 2015-07-23 | 2015-08-17 | 2015-08-14 |  | Glasgow City | 86.46 | 584.73 | 0 | 0 | 0 | 0 | 0 | 584.73 | 0 | 671.19 | 0 | [6 empty] | CM_WSI | 100%
404014 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | WINF | NRSWA | MS4 | 2014-12-09 | 2015-12-16 | 2016-01-05 | 2018-11-16 |  | Aberdeen City | 215249 | 1053507.57 | 171917.24 | 479055.19 | -137767.34 | 61253.28 | 0 | 1627965.94 | 0 | 1843214.94 | 0 | [6 empty] | CM_WSI | 100%
404015 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | WINF | NRSWA | MS4 | 2014-12-08 | 2015-05-19 | 2016-01-15 | 2018-01-10 |  | Aberdeen City | 29699 | 31102 | 851577.02 | 118239.3225 | 53489.1575 | 0 | 0 | 1054407.5 | 0 | 1084106.5 | 0 | [6 empty] | CM_WSI | 100%
404114 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-05-18 | 2015-08-18 | 2015-10-12 | 2016-04-25 |  | Angus | 0 | 37204 | -2482.88 | 546.9 | 0 | 0 | 0 | 35268.02 | 0 | 35268.02 | 0 | [6 empty] | CM_WSI | 100%
404127 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-06-02 | 2015-09-30 | 2015-09-30 | 2016-11-22 |  | City of Edinburgh | 0 | 182820 | 82020.58 | 621.28 | 0 | 0 | 0 | 265461.86 | 0 | 265461.86 | 0 | [6 empty] | CM_WSI | 100%
404126 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-06-02 | 2015-07-30 | 2015-07-31 | 2015-10-06 |  | Highland | 0 | 57508.66 | 0 | 0 | 0 | 0 | 0 | 57508.66 | 0 | 57508.66 | 0 | [6 empty] | CM_WSI | 100%
404119 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-03-30 | 2015-09-30 | 2015-10-01 | 2016-08-09 | 2016-09-21 | Highland | 0 | 785867.13 | 29265.61 | 282.88 | 0 | 0 | 0 | 815415.62 | 0 | 815415.62 | 0 | [6 empty] | CM_WSI | 100%
404088 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-01-27 | 2015-08-31 | 2015-09-01 | 2016-07-07 |  | Highland | 5000 | 793732.11 | 123403.86 | -6719.045 | 27949.947 | 0 | 0 | 938366.872 | 0 | 943366.872 | 0 | [6 empty] | CM_WSI | 100%
404013 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | WINF | NRSWA | MS4 | 2014-12-02 | 2015-08-10 | 2015-08-10 | 2018-02-23 |  | Aberdeen City | 404227 | 870325.07 | 2315805.62 | -538575.69 | -317925.2274 | 0 | 0 | 2329629.7726 | 0 | 2733856.7726 | 0 | [6 empty] | CM_WSI | 100%
404107 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-03-03 | 2015-06-24 | 2015-06-24 | 2016-10-10 |  | City of Edinburgh | 70.74 | 43872.26 | 10654.21 | 273.45 | 0 | 0 | 0 | 54799.92 | 0 | 54870.66 | 0 | [6 empty] | CM_WSI | 100%
404087 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-01-27 | 2015-04-29 | 2015-05-15 | 2015-10-14 |  | Falkirk | 1503.56 | 42243.79 | 0 | 0 | 0 | 0 | 0 | 42243.79 | 0 | 43747.35 | 0 | [6 empty] | CM_WSI | 100%
502413 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-12-09 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | Fife | 0 | 0 | 1693 | -275.79 | 0 | 0 | 0 | 1417.21 | 0 | 1417.21 | 48164.5084 | [6 empty] | CS23W | 100%
503444 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MSU | 2019-07-01 | 2020-04-06 | 2020-06-11 | 2021-11-09 | 2022-02-09 | Highland | 0 | 0 | 0 | 0 | 0 | 6802.64 | 16332.64 | 23135.28 | 16864.78 | 40000.06 | 948832.8374 | [6 empty] | CS23S | 100%
501320 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2015-12-16 | 2016-11-30 | 2017-01-06 | 2018-03-23 | 2018-03-23 | Perth and Kinross | 0 | 974.97 | 413509.03 | 788194 | -470860.6825 | 0 | 0 | 731817.3175 | 0 | 731817.3175 | 3112230.0788 | [6 empty] | CS23S | 100%
501319 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | WINF | NRSWA | MS3 | 2016-02-26 | 2016-08-15 | 2016-08-29 | 2019-05-31 | 2019-08-07 | Aberdeen City | 0 | 20998.05 | 597152.6 | 84515.41 | 170034.61 | 0 | 0 | 872700.67 | 0 | 872700.67 | 3112230.0788 | [6 empty] | CS23S | 100%
501631 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2016-02-05 | 2016-07-29 | 2016-08-31 | 2017-03-15 | 2017-03-15 | Moray | 0 | 13506 | -5898.77 | -922.7 | 0 | 0 | 0 | 6684.53 | 0 | 6684.53 | 3112230.0788 | [6 empty] | CS23S | 100%
501630 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2016-02-08 | 2016-07-29 | 2016-09-05 | 2017-03-15 | 2017-03-15 | Moray | 0 | 2879 | 22357.96 | 66951.8065 | 0 | 0 | 0 | 92188.7665 | 0 | 92188.7665 | 3112230.0788 | [6 empty] | CS23S | 100%
502126 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2016-03-02 | 2016-11-30 | 2017-02-20 | 2017-12-08 | 2017-12-08 | Perth and Kinross | 0 | 1000 | 56512.89 | 226563.586 | 27419.849 | 0 | 0 | 311496.325 | 0 | 311496.325 | 3112230.0788 | [6 empty] | CS23S | 100%
502253 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS3 | 2016-06-29 | 2017-12-18 | 2018-06-25 | 2019-09-27 | 2019-09-27 | East Ayrshire | 0 | 0 | 723.75 | 50110.25 | -17834 | 92935.29 | 0 | 125935.29 | 0 | 125935.29 | 3112230.0788 | [6 empty] | CS23S | 100%
501624 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2016-02-05 | 2016-07-27 | 2016-07-27 | 2017-03-01 | 2017-03-01 | South Lanarkshire | 0 | 6655 | 982933.2 | 17098.703 | 169.325 | 0 | 0 | 1006856.228 | 0 | 1006856.228 | 3112230.0788 | [6 empty] | CS23S | 100%
500988 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2015-11-06 | 2016-11-29 | 2016-11-30 | 2018-12-18 | 2018-12-18 | North Lanarkshire | 0 | 2763.28 | 307308.52 | 92176.62 | 68797.73 | 0 | 0 | 471046.15 | 0 | 471046.15 | 3112230.0788 | [6 empty] | CS23S | 100%
502561 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2017-02-06 | 2017-09-14 | 2017-09-21 | 2018-03-16 | 2018-03-16 | Falkirk | 0 | 0 | 686.51 | 12376.385 | -1505.375 | 0 | 0 | 11557.52 | 0 | 11557.52 | 3112230.0788 | [6 empty] | CS23S | 100%
502547 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2017-01-31 | 2017-09-26 | 2017-09-29 | 2018-05-04 | 2018-05-04 | Glasgow City | 0 | 0 | 397.56 | 54893.44 | -44441.8215 | 0 | 0 | 10849.1785 | 0 | 10849.1785 | 3112230.0788 | [6 empty] | CS23S | 100%
502807 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS3 | 2017-07-25 | 2018-03-29 | 2018-03-30 | 2019-12-11 | 2019-12-11 | Perth and Kinross | 0 | 0 | 0 | 68338 | 85958.23 | 299769.63 | 25343.17 | 479409.03 | 0 | 479409.03 | 3112230.0788 | [6 empty] | CS23S | 100%
503147 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS3 | 2018-03-29 | 2018-07-23 | 2018-08-17 | 2020-12-30 | 2021-04-05 | Aberdeen City | 0 | 0 | 0 | 0 | 74469.45 | 218563.98 | 248580.11 | 541613.54 | 87521.7 | 629135.24 | 3112230.0788 | [6 empty] | CS23S | 100%
502863 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2018-04-11 | 2018-05-23 | 2018-06-04 | 2018-11-30 | 2018-11-30 | Highland | 0 | 0 | 0 | 0 | 5116.33 | 0 | 0 | 5116.33 | 0 | 5116.33 | 3112230.0788 | [6 empty] | CS23S | 100%
502866 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS3 | 2018-01-31 | 2018-04-11 | 2018-06-26 | 2020-01-28 | 2020-04-29 | South Lanarkshire | 0 | 0 | 0 | 37720.03 | 453779.97 | 989087.98 | 207645.01 | 1688232.99 | 0 | 1688232.99 | 3112230.0788 | [6 empty] | CS23S | 100%
502797 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2017-07-25 | 2018-03-29 | 2018-03-30 | 2018-10-26 | 2018-10-26 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 29862.9125 | 163071.9985 | 0 | 0 | 192934.911 | 0 | 192934.911 | 3112230.0788 | [6 empty] | CS23S | 100%
502906 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2017-10-25 | 2018-03-27 | 2018-03-29 | 2018-09-27 | 2018-09-27 | Aberdeen City | 0 | 0 | 0 | 26800 | 143084.1075 | 0 | 0 | 169884.1075 | 0 | 169884.1075 | 3112230.0788 | [6 empty] | CS23S | 100%
402335 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2011-09-12 | 2012-05-16 | 2012-08-13 | 2015-05-04 |  | Fife | 3657684 | 7000 | 13133.6 | 0 | 0 | 0 | 0 | 20133.6 | 0 | 3677817.6 | 0 | [6 empty] | CM_WWI | 100%
402336 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2011-09-12 | 2012-08-29 | 2012-11-19 | 2013-11-14 |  | City of Edinburgh | 409918 | -10778.56 | 0 | 0 | 0 | 0 | 0 | -10778.56 | 0 | 399139.44 | 0 | [6 empty] | CM_WWI | 100%
501625 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2016-01-25 | 2016-06-29 | 2016-06-30 | 2019-10-14 | 2019-10-14 | East Ayrshire | 0 | 23053 | 259685.44 | 99482.56 | 104298.53 | 46742.46 | 0 | 533261.99 | 0 | 533261.99 | 48164.5084 | [6 empty] | CS23W | 100%
501944 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-02-19 | 2016-05-30 | 2016-06-28 | 2017-01-09 | 2017-01-09 | East Ayrshire | 0 | 2000 | 103028.74 | 0 | 0 | 0 | 0 | 105028.74 | 0 | 105028.74 | 48164.5084 | [6 empty] | CS23W | 100%
503346 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS5 | 2018-09-17 | 2018-11-26 | 2018-11-29 | 2019-03-11 | 2019-03-11 | East Ayrshire | 0 | 0 | 0 | 0 | 41499.35 | 0 | 0 | 41499.35 | 0 | 41499.35 | 48164.5084 | [6 empty] | CS23W | 100%
502875 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-12-13 | 2018-01-31 | 2018-02-12 | 2018-05-17 | 2018-05-17 | Perth and Kinross | 0 | 0 | 0 | 26699.055 | 7720.635 | 0 | 0 | 34419.69 | 0 | 34419.69 | 48164.5084 | [6 empty] | CS23W | 100%
502634 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-02-17 | 2017-05-31 | 2017-05-31 | 2018-10-22 | 2018-10-22 | Highland | 0 | 0 | 201.9 | 78112.3 | 115467.1775 | 0 | 0 | 193781.3775 | 0 | 193781.3775 | 48164.5084 | [6 empty] | CS23W | 100%
503351 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-08-24 | 2018-12-21 | 2018-12-21 | 2020-06-08 | 2020-06-08 | Highland | 0 | 0 | 0 | 0 | 29852.23 | 41663.93 | 161399.59 | 232915.75 | 0 | 232915.75 | 48164.5084 | [6 empty] | CS23W | 100%
502289 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-07-26 | 2017-02-28 | 2017-02-28 | 2017-08-14 | 2017-08-14 | Fife | 0 | 0 | 25576 | 25313.18 | 0 | 0 | 0 | 50889.18 | 0 | 50889.18 | 48164.5084 | [6 empty] | CS23W | 100%
502636 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-02-17 | 2017-07-25 | 2017-07-28 | 2017-08-30 | 2017-08-30 | Aberdeenshire | 0 | 0 | 468.32 | 5753.75 | 0 | 0 | 0 | 6222.07 | 0 | 6222.07 | 48164.5084 | [6 empty] | CS23W | 100%
501263 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-02-15 | 2016-11-30 | 2016-12-20 | 2018-02-07 | 2018-02-07 | Perth and Kinross | 0 | 11764 | 92967.83 | 240763.7225 | 385338.816 | 0 | 0 | 730834.3685 | 0 | 730834.3685 | 48164.5084 | [6 empty] | CS23W | 100%
502125 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-03-02 | 2016-08-24 | 2016-09-26 | 2018-10-10 | 2018-10-10 | Perth and Kinross | 0 | 1000 | 341808 | 418205 | 32809.305 | 0 | 0 | 793822.305 | 0 | 793822.305 | 48164.5084 | [6 empty] | CS23W | 100%
502045 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-02-19 | 2016-10-31 | 2017-07-10 | 2017-07-26 | 2017-07-26 | North Ayrshire | 0 | 1000 | 34540.19 | 6190.18 | 0 | 0 | 0 | 41730.37 | 0 | 41730.37 | 48164.5084 | [6 empty] | CS23W | 100%
502728 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-07-25 | 2017-09-04 | 2017-09-12 | 2017-09-14 | 2017-09-14 | West Lothian | 0 | 0 | 0 | 5430.52 | 0 | 0 | 0 | 5430.52 | 0 | 5430.52 | 48164.5084 | [6 empty] | CS23W | 100%
503399 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-09-18 | 2018-10-17 | 2018-11-05 | 2019-01-03 | 2019-01-03 | Fife | 0 | 0 | 0 | 0 | 14310.4775 | 0 | 0 | 14310.4775 | 0 | 14310.4775 | 48164.5084 | [6 empty] | CS23W | 100%
503348 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-08-24 | 2019-02-26 | 2019-03-28 | 2019-08-16 | 2019-08-16 | Aberdeenshire | 0 | 0 | 0 | 0 | 32194.4875 | 203629.3 | 0 | 235823.7875 | 0 | 235823.7875 | 48164.5084 | [6 empty] | CS23W | 100%
503345 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-08-24 | 2018-12-20 | 2018-12-21 | 2019-08-26 | 2019-08-26 | Dundee City | 0 | 0 | 0 | 0 | 24491.655 | 100891.67 | 0 | 125383.325 | 0 | 125383.325 | 48164.5084 | [6 empty] | CS23W | 100%
502884 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-11-23 | 2018-01-08 | 2018-01-29 | 2018-09-27 | 2018-09-27 | Aberdeen City | 0 | 0 | 0 | 25685.52 | 91802.024 | 0 | 0 | 117487.544 | 0 | 117487.544 | 48164.5084 | [6 empty] | CS23W | 100%
501627 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-02-05 | 2016-06-30 | 2016-06-30 | 2017-01-30 | 2017-01-30 | East Dunbartonshire | 0 | 2438 | 182099.91 | -1240.72 | 0 | 0 | 0 | 183297.19 | 0 | 183297.19 | 48164.5084 | [6 empty] | CS23W | 100%
501626 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-02-05 | 2016-05-30 | 2016-06-27 | 2017-01-26 | 2017-01-26 | Moray | 0 | 1219 | 43251.73 | -34848.99 | 0 | 0 | 0 | 9621.74 | 0 | 9621.74 | 48164.5084 | [6 empty] | CS23W | 100%
501629 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-01-25 | 2016-06-30 | 2016-06-30 | 2017-03-29 | 2017-03-29 | South Lanarkshire | 0 | 22134 | 249939.19 | 51010.24 | 0 | 0 | 0 | 323083.43 | 0 | 323083.43 | 48164.5084 | [6 empty] | CS23W | 100%
501751 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-02-19 | 2016-03-30 | 2016-04-22 | 2017-02-08 | 2017-02-08 | City of Edinburgh | 0 | 355.68 | 24952.64 | 2648.27 | 0 | 0 | 0 | 27956.59 | 0 | 27956.59 | 48164.5084 | [6 empty] | CS23W | 100%
503352 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-08-24 | 2018-11-26 | 2018-11-29 | 2019-05-03 | 2019-05-03 | Inverclyde | 0 | 0 | 0 | 0 | 40000 | 8000 | 0 | 48000 | 0 | 48000 | 48164.5084 | [6 empty] | CS23W | 100%
503446 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS0 | 2019-02-26 | 2019-09-02 | 2019-09-13 | 2019-12-05 | 2020-03-04 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 457.94 | 69542.06 | 0 | 70000 | 0 | 70000 | 48164.5084 | [6 empty] | CS23W | 100%
500986 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-11-06 | 2016-05-23 | 2016-06-22 | 2019-01-10 | 2019-01-10 | Glasgow City | 0 | 3770.87 | 273611.53 | -40396 | 33756.7125 | 0 | 0 | 270743.1125 | 0 | 270743.1125 | 48164.5084 | [6 empty] | CS23W | 100%
503396 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-11-28 | 2019-02-26 | 2019-02-26 | 2019-09-13 | 2019-09-13 | South Lanarkshire | 0 | 0 | 0 | 0 | 22500.08 | 106122.64 | 0 | 128622.72 | 0 | 128622.72 | 48164.5084 | [6 empty] | CS23W | 100%
502544 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-01-19 | 2017-05-29 | 2017-06-09 | 2017-08-23 | 2017-08-23 | Argyll and Bute-North Argyll | 0 | 0 | 410 | 27284.18 | 0 | 0 | 0 | 27694.18 | 0 | 27694.18 | 48164.5084 | [6 empty] | CS23W | 100%
502000 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-02-19 | 2016-06-30 | 2016-07-28 | 2017-01-19 | 2017-01-19 | North Lanarkshire | 0 | 1000 | 97445 | -1390.99 | 0 | 0 | 0 | 97054.01 | 0 | 97054.01 | 48164.5084 | [6 empty] | CS23W | 100%
502545 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-02-08 | 2017-09-14 | 2017-09-21 | 2019-01-07 | 2019-01-07 | Stirling | 0 | 0 | 2274.83 | 233841.31 | 140172.898 | 0 | 0 | 376289.038 | 0 | 376289.038 | 48164.5084 | [6 empty] | CS23W | 100%
502560 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-02-06 | 2017-08-28 | 2017-09-18 | 2018-04-19 | 2018-04-19 | Highland | 0 | 0 | 569.85 | 35547.15 | -14686.175 | 0 | 0 | 21430.825 | 0 | 21430.825 | 48164.5084 | [6 empty] | CS23W | 100%
503547 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS0 | 2019-03-18 | 2019-08-19 | 2019-09-30 | 2020-02-19 | 2020-05-21 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 115140.85 | 34859.15 | 150000 | 0 | 150000 | 48164.5084 | [6 empty] | CS23W | 100%
500961 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-11-06 | 2016-08-29 | 2016-08-31 | 2016-11-25 | 2016-11-25 | Aberdeen City | 0 | 6312 | 109442.57 | 1196.61 | 0 | 0 | 0 | 116951.18 | 0 | 116951.18 | 48164.5084 | [6 empty] | CS23W | 100%
503350 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-08-24 | 2018-12-21 | 2018-12-21 | 2019-10-22 | 2019-10-22 | Highland | 0 | 0 | 0 | 0 | 16000 | 178833.48 | 0 | 194833.48 | 0 | 194833.48 | 48164.5084 | [6 empty] | CS23W | 100%
502189 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-03-30 | 2016-08-24 | 2016-08-24 | 2016-08-25 | 2016-08-25 | Dumfries and Galloway | 0 | 0 | 338.87 | 0 | 0 | 0 | 0 | 338.87 | 0 | 338.87 | 48164.5084 | [6 empty] | CS23W | 100%
500905 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS7 | 2015-12-11 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | Dumfries and Galloway | 0 | 2159 | 100771.11 | 0 | 0 | 0 | 0 | 102930.11 | 0 | 102930.11 | 48164.5084 | [6 empty] | CS23W | 100%
502092 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-03-17 | 2016-08-16 | 2016-09-22 | 2017-02-10 | 2017-02-10 | South Lanarkshire | 0 | 459.38 | 3901.87 | 17490.78 | 0 | 0 | 0 | 21852.03 | 0 | 21852.03 | 48164.5084 | [6 empty] | CS23W | 100%
502252 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2016-06-29 | 2017-12-18 | 2018-06-25 | 2019-09-27 | 2019-09-27 | East Ayrshire | 0 | 0 | 1126.58 | 52223.42 | -8349.71 | 9859 | 0 | 54859.29 | 0 | 54859.29 | 48164.5084 | [6 empty] | CS23W | 100%
501628 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-01-25 | 2016-06-14 | 2016-06-29 | 2017-01-30 | 2017-01-30 | Renfrewshire | 0 | 3311 | 132544 | 10325.555 | 0 | 0 | 0 | 146180.555 | 0 | 146180.555 | 48164.5084 | [6 empty] | CS23W | 100%
502559 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-02-09 | 2017-12-21 | 2017-12-22 | 2018-03-16 | 2018-03-16 | Falkirk | 0 | 0 | 509.66 | 214613.319 | -83506.385 | 0 | 0 | 131616.594 | 0 | 131616.594 | 48164.5084 | [6 empty] | CS23W | 100%
503361 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS0 | 2018-08-28 | 2019-08-19 | 2019-10-25 | 2020-07-03 | 2020-10-05 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 83146.98 | 66853.05 | 150000.03 | 0 | 150000.03 | 48164.5084 | [6 empty] | CS23W | 100%
500960 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-11-06 | 2016-02-16 | 2016-02-25 | 2016-06-27 | 2016-07-12 | West Lothian | 0 | 33673 | 21845.08 | 546.9 | 0 | 0 | 0 | 56064.98 | 0 | 56064.98 | 48164.5084 | [6 empty] | CS23W | 100%
502546 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-01-31 | 2017-07-31 | 2017-08-14 | 2018-07-09 | 2018-07-09 | Glasgow City | 0 | 0 | 574.41 | 169362.59 | -7381.659 | 0 | 0 | 162555.341 | 0 | 162555.341 | 48164.5084 | [6 empty] | CS23W | 100%
501321 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2015-12-15 | 2016-03-16 | 2016-04-28 | 2016-09-29 | 2016-10-14 | Moray | 0 | 3733 | 38364.63 | 334.04 | 0 | 0 | 0 | 42431.67 | 0 | 42431.67 | 48164.5084 | [6 empty] | CS23W | 100%
503349 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-08-24 | 2018-12-18 | 2019-02-08 | 2019-12-13 | 2019-12-13 | West Lothian | 0 | 0 | 0 | 0 | 6500 | 23983.75 | 25905.25 | 56389 | 0 | 56389 | 48164.5084 | [6 empty] | CS23W | 100%
502093 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-03-11 | 2016-08-29 | 2016-10-27 | 2017-03-28 | 2017-03-28 | Argyll and Bute-North Argyll | 0 | 499.11 | 20762.39 | 12801.7 | 0 | 0 | 0 | 34063.2 | 0 | 34063.2 | 48164.5084 | [6 empty] | CS23W | 100%
503406 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS0 | 2018-12-21 | 2019-04-29 | 2019-05-06 | 2019-11-29 | 2020-03-06 | South Lanarkshire | 0 | 0 | 0 | 0 | 19284.11 | 177345.9 | 3369.97 | 199999.98 | 0 | 199999.98 | 48164.5084 | [6 empty] | CS23W | 100%
502808 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2017-07-26 | 2018-03-30 | 2018-03-30 | 2019-12-11 | 2019-12-11 | Perth and Kinross | 0 | 0 | 0 | 219766.028 | 593166.142 | 1763359.25 | 592574.29 | 3168865.71 | 0 | 3168865.71 | 48164.5084 | [6 empty] | CS23W | 100%
503146 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-03-29 | 2018-07-23 | 2018-08-17 | 2020-12-30 | 2021-04-05 | Aberdeen City | 0 | 0 | 0 | 0 | 84114.71 | 245064.39 | 308061.26 | 637240.36 | 130671.77 | 767912.13 | 48164.5084 | [6 empty] | CS23W | 100%
502862 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-03-28 | 2018-06-28 | 2018-07-03 | 2019-02-26 | 2019-02-26 | Highland | 0 | 0 | 0 | 0 | 308101.0405 | 0 | 0 | 308101.0405 | 0 | 308101.0405 | 48164.5084 | [6 empty] | CS23W | 100%
502831 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS5 | 2017-07-25 | 2018-01-30 | 2018-02-08 | 2019-03-11 | 2019-03-11 | Inverclyde | 0 | 0 | 0 | 34855.86 | 153944.14 | 0 | 0 | 188800 | 0 | 188800 | 48164.5084 | [6 empty] | CS23W | 100%
503254 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-05-23 | 2019-03-25 | 2019-03-25 | 2021-05-18 | 2021-05-18 | Renfrewshire | 0 | 0 | 0 | 0 | 62296.74 | 3566.8 | 171658.35 | 237521.89 | 229672.42 | 467194.31 | 48164.5084 | [6 empty] | CS23W | 100%
503265 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-05-29 | 2018-06-27 | 2018-06-27 | 2018-08-01 | 2018-08-01 | Renfrewshire | 0 | 0 | 0 | 0 | 19592.0625 | 0 | 0 | 19592.0625 | 0 | 19592.0625 | 48164.5084 | [6 empty] | CS23W | 100%
402329 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-09-07 | 2012-08-29 | 2012-10-15 | 2015-04-01 |  | City of Edinburgh | 469402 | 30084.6 | 0 | 0 | 0 | 0 | 0 | 30084.6 | 0 | 499486.6 | 0 | [6 empty] | CM_WSI | 100%
402330 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-09-07 | 2012-07-23 | 2012-09-24 | 2016-07-21 |  | City of Edinburgh | 246338 | 2346 | 62267.85 | 0 | 0 | 0 | 0 | 64613.85 | 0 | 310951.85 | 0 | [6 empty] | CM_WSI | 100%
402331 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-09-07 | 2013-06-24 | 2013-11-18 | 2015-11-26 |  | Fife | 50172 | 28502.85 | 0 | 0 | 0 | 0 | 0 | 28502.85 | 0 | 78674.85 | 0 | [6 empty] | CM_WSI | 100%
402332 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-09-07 | 2012-07-26 | 2012-09-17 | 2015-12-10 |  | Fife | 223077 | 166796 | 25732.56 | 1043.79 | 6414.86 | 0 | 0 | 199987.21 | 0 | 423064.21 | 0 | [6 empty] | CM_WSI | 100%
402333 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-09-08 | 2012-07-26 | 2013-05-13 | 2014-03-06 |  | City of Edinburgh | 45067.05 | 168.92 | 0 | 133.92 | 0 | 0 | 0 | 302.84 | 0 | 45369.89 | 0 | [6 empty] | CM_WSI | 100%
402326 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-09-06 | 2012-07-20 | 2012-09-17 | 2015-11-26 |  | City of Edinburgh | 104893 | 42733.59 | 163.19 | 0 | 0 | 0 | 0 | 42896.78 | 0 | 147789.78 | 0 | [6 empty] | CM_WSI | 100%
402327 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2011-09-06 | 2012-07-26 | 2012-09-17 | 2015-11-26 |  | City of Edinburgh | 457227 | 290048 | 6160.58 | 273.45 | 0 | 0 | 0 | 296482.03 | 0 | 753709.03 | 0 | [6 empty] | CM_WSI | 100%
502867 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-01-31 | 2018-04-11 | 2018-06-26 | 2020-01-27 | 2020-01-27 | South Lanarkshire | 0 | 0 | 0 | 44162.03 | 370888.04 | 547428.05 | 193452.92 | 1155931.04 | 0 | 1155931.04 | 48164.5084 | [6 empty] | CS23W | 100%
502798 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-07-25 | 2018-03-26 | 2018-03-30 | 2018-10-19 | 2018-10-19 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 89717 | 420719.425 | 0 | 0 | 510436.425 | 0 | 510436.425 | 48164.5084 | [6 empty] | CS23W | 100%
502737 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-07-25 | 2017-11-29 | 2017-11-30 | 2019-02-04 | 2019-02-04 | Glasgow City | 0 | 0 | 0 | 172469.569 | 85750.066 | 0 | 0 | 258219.635 | 0 | 258219.635 | 48164.5084 | [6 empty] | CS23W | 100%
502799 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2017-07-25 | 2017-09-29 | 2017-09-29 | 2018-01-24 | 2018-03-22 | City of Edinburgh | 0 | 0 | 0 | 485000.23 | -399.955 | 0 | 0 | 484600.275 | 0 | 484600.275 | 48164.5084 | [6 empty] | CS23W | 100%
502345 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-10-07 | 2017-03-07 | 2017-03-10 | 2017-08-07 | 2017-08-07 | Perth and Kinross | 0 | 0 | 98646 | 424520.42 | 550 | 0 | 0 | 523716.42 | 0 | 523716.42 | 48164.5084 | [6 empty] | CS23W | 100%
502414 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2016-12-12 | 2017-09-29 | 2017-09-29 | 2019-10-22 | 2019-10-22 | North Ayrshire | 0 | 0 | 2350 | 1032257.8085 | 1472653.9615 | 227449.45 | 0 | 2734711.22 | 0 | 2734711.22 | 48164.5084 | [6 empty] | CS23W | 100%
503038 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-01-19 | 2018-06-29 | 2018-06-29 | 2020-10-12 | 2020-10-12 | North Ayrshire | 0 | 0 | 0 | 2927.685 | 204424.395 | 342772.95 | 135324.35 | 685449.38 | 0 | 685449.38 | 48164.5084 | [6 empty] | CS23W | 100%
503037 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-01-23 | 2018-08-20 | 2018-08-31 | 2020-03-06 | 2020-06-08 | South Ayrshire | 0 | 0 | 0 | 3469.613 | 56789.297 | 362697.68 | 165011.45 | 587968.04 | 0 | 587968.04 | 48164.5084 | [6 empty] | CS23W | 100%
503138 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-03-28 | 2018-11-26 | 2018-12-03 | 2020-03-06 | 2020-03-06 | Highland | 0 | 0 | 0 | 0 | 66086 | 212879.26 | 155210.72 | 434175.98 | 0 | 434175.98 | 48164.5084 | [6 empty] | CS23W | 100%
503055 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-01-30 | 2018-06-28 | 2018-07-02 | 2019-10-31 | 2019-10-31 | Highland | 0 | 0 | 0 | 3191.405 | 38248.605 | 32224.62 | 0 | 73664.63 | 0 | 73664.63 | 48164.5084 | [6 empty] | CS23W | 100%
503288 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS0 | 2018-11-07 | 2019-10-28 | 2019-11-04 | 2021-01-26 | 2021-04-06 | Perth and Kinross | 0 | 0 | 0 | 0 | 15000.06 | 518650.05 | 802869.34 | 1336519.45 | 236480.52 | 1572999.97 | 48164.5084 | [6 empty] | CS23W | 100%
502309 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-08-02 | 2017-01-06 | 2017-01-06 | 2017-01-26 | 2017-01-26 | Highland | 0 | 0 | 2071.79 | 546.9 | 0 | 0 | 0 | 2618.69 | 0 | 2618.69 | 48164.5084 | [6 empty] | CS23W | 100%
503081 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-03-28 | 2018-06-28 | 2018-06-28 | 2018-08-17 | 2018-08-17 | Highland | 0 | 0 | 0 | 0 | 75514.683 | 0 | 0 | 75514.683 | 0 | 75514.683 | 48164.5084 | [6 empty] | CS23W | 100%
503097 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS3 | 2018-04-11 | 2018-09-17 | 2018-10-08 | 2019-10-01 | 2019-10-01 | Stirling | 0 | 0 | 0 | 0 | 100084 | 32660.97 | 0 | 132744.97 | 0 | 132744.97 | 48164.5084 | [6 empty] | CS23W | 100%
502321 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-10-07 | 2016-11-30 | 2017-02-10 | 2017-06-29 | 2017-07-03 | Perth and Kinross | 0 | 0 | 70604.97 | 111905.595 | 0 | 0 | 0 | 182510.565 | 0 | 182510.565 | 48164.5084 | [6 empty] | CS23W | 100%
503057 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-01-23 | 2018-02-27 | 2018-03-15 | 2018-04-03 | 2018-04-03 | Scottish Borders | 0 | 0 | 0 | 0 | 8.805 | 0 | 0 | 8.805 | 0 | 8.805 | 48164.5084 | [6 empty] | CS23W | 100%
502415 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2016-12-09 | 2017-06-26 | 2017-06-30 | 2018-03-28 | 2018-03-28 | Orkney Islands | 0 | 0 | 309.57 | 58498.43 | -174.1875 | 0 | 0 | 58633.8125 | 0 | 58633.8125 | 48164.5084 | [6 empty] | CS23W | 100%
503043 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-01-30 | 2018-02-20 | 2018-02-21 | 2018-09-20 | 2018-09-20 | Glasgow City | 0 | 0 | 0 | 4738 | 37054.6875 | 0 | 0 | 41792.6875 | 0 | 41792.6875 | 48164.5084 | [6 empty] | CS23W | 100%
503095 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2018-04-11 | 2018-06-15 | 2018-06-26 | 2018-11-12 | 2018-11-12 | Glasgow City | 0 | 0 | 0 | 0 | 5273.498 | 0 | 0 | 5273.498 | 0 | 5273.498 | 48164.5084 | [6 empty] | CS23W | 100%
402624 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-03-22 | 2012-03-22 | 2012-07-10 | 2015-08-28 |  | Scottish Water Wide | 608000 | 103499.77 | 569.4 | 88.64 | 0 | 0 | 0 | 104157.81 | 0 | 712157.81 | 0 | [6 empty] | CM_WWI | 100%
500779 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MS5 | 2015-09-04 | 2021-04-28 | 2021-04-29 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 0 | 340509.42 | 443609.58 | 44094.325 | 0.005 | 0 | 0 | 828213.33 | 0 | 828213.33 | 3112230.0788 | [6 empty] | CS23S | 100%
402623 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-03-22 | 2012-03-22 | 2012-07-03 | 2015-08-28 |  | Scottish Water Wide | 917216.93 | 410399.61 | 584.4 | 0 | 5.544 | 0 | 0 | 410989.554 | 0 | 1328206.484 | 0 | [6 empty] | CM_WSI | 100%
500778 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS5 | 2015-09-04 | 2021-04-28 | 2021-04-29 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 0 | 462256 | 697623 | 25553.95 | -25181.93 | 0 | 0 | 1160251.02 | 0 | 1160251.02 | 48164.5084 | [6 empty] | CS23W | 100%
503301 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MS0 | 2018-07-27 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-08-06 | Scottish Water Wide | 0 | 0 | 0 | 0 | 382454 | 735223.41 | 797267.59 | 1914945 | 253001.04 | 2167946.04 | 948832.8374 | [6 empty] | CS23S | 100%
503300 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS0 | 2018-07-27 | 2021-06-07 | 2021-06-07 | 2021-06-07 | 2021-07-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 96715.44 | 1304615.16 | 1233339.06 | 2634669.66 | 369941.21 | 3004610.87 | 2249750.5038 | [6 empty] | CS23W | 100%
500781 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MS5 | 2015-09-04 | 2021-04-29 | 2021-04-29 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 0 | 24229.99 | 74820.55 | 42974.828 | 0 | 0 | 0 | 142025.368 | 0 | 142025.368 | 3112230.0788 | [6 empty] | CS23S | 100%
503297 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWD | NRSWA | MS0 | 2018-07-26 | 2021-06-02 | 2021-06-02 | 2021-06-02 | 2021-08-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 47909.0134 | 22714.63 | 9005.73 | 79629.3734 | 0 | 79629.3734 | 948832.8374 | [6 empty] | CS23S | 100%
500780 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS5 | 2015-09-04 | 2021-04-29 | 2021-04-29 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 0 | 182121.86 | 13898.26 | 115590.001 | 2619.419 | 0 | 0 | 314229.54 | 0 | 314229.54 | 48164.5084 | [6 empty] | CS23W | 100%
503296 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWD | NRSWA | MS0 | 2018-07-26 | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2021-08-13 | Scottish Water Wide | 0 | 0 | 0 | 0 | 796620.51 | 82072.02 | 81392.75 | 960085.28 | 11901.37 | 971986.65 | 2249750.5038 | [6 empty] | CS23W | 100%
502416 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2016-12-09 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | Fife | 0 | 0 | 1549 | -248.76 | 0 | 0 | 0 | 1300.24 | 0 | 1300.24 | 3112230.0788 | [6 empty] | CS23S | 100%
402997 | Q&S4 | Supporting economic development | NRSWA |  |  | Wastewater |  | SWMD | NRSWA | MS7 | 2012-09-27 |  |  | 2015-09-01 |  | Scottish Water Wide | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [6 empty] | CM_WWI | 100%
402996 | Q&S4 | Supporting economic development | NRSWA |  |  | Water |  | SWMD | NRSWA | MS7 | 2012-09-27 |  |  | 2015-10-09 |  | Scottish Water Wide | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [6 empty] | CM_WSI | 100%
501013 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2019-12-02 | 2019-12-10 | 2019-12-11 | 2019-12-12 | 2019-12-12 | Highland | 0 | 27500 | 34114.62 | 36956.0041 | -98569.6241 | 0 | 0 | 1 | 0 | 1 | 229318.7788 | [6 empty] | CS11 | 100%
500744 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS0 | 2018-01-29 | 2019-07-18 | 2019-07-19 | 2019-07-19 | 2019-07-19 | Highland | 0 | 88100 | 237348.61 | 73169.7041 | 89227.9675 | 0 | 0 | 487846.2816 | 0 | 487846.2816 | 229318.7788 | [6 empty] | CS11 | 100%
500088 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW0 | 2019-06-24 | 2020-06-01 | 2020-08-19 | 2021-03-29 | 2021-06-21 | Highland | 0 | 23600 | 54205.05 | 37172.8941 | 36022.0559 | 39445.26 | 374665.41 | 565110.67 | 128889.43 | 694000.1 | 380840.2264 | [6 empty] | CS11 | 50% | CS15 | 50%
500510 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-08-10 | 2021-08-10 | Scottish Water Wide | 0 | 17473 | 8371.65 | 20352.35 | 69487.24 | 44650 | 44665.76 | 205000 | 0 | 205000 | 0 | [6 empty] | CM_M&G | 100%
500511 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2021-06-03 | 2021-06-03 | Scottish Water Wide | 0 | 282199 | 144609 | 228401 | 256587.9 | 233528.31 | 213325.2 | 1358650.41 | 0 | 1358650.41 | 0 | [6 empty] | CM_M&G | 100%
500947 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS1 | 2015-09-17 | 2019-05-23 | 2019-05-23 | 2020-05-21 | 2020-05-21 | Dumfries and Galloway | 0 | 56607 | -5101.98 | 2200 | 97028.21 | 1840562.28 | 0 | 1991295.51 | 0 | 1991295.51 | 0 | [6 empty] | CM_M&G | 100%
500513 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2021-06-03 | 2021-06-03 | Scottish Water Wide | 0 | 90241 | 72836.42 | 69669.96 | 105744.31 | 145000 | 141508.31 | 625000 | 0 | 625000 | 0 | [6 empty] | CM_M&G | 100%
500520 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS5 | 2015-05-18 | 2016-10-24 | 2016-10-24 | 2019-03-07 | 2019-03-07 | Scottish Water Wide | 0 | 301700 | 849674.93 | 1783224.55 | 1715213.35 | 0 | 0 | 4649812.83 | 0 | 4649812.83 | 0 | [6 empty] | CM_M&G | 100%
500514 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-03-12 | 2021-03-12 | Scottish Water Wide | 0 | 108706.24 | 151257.76 | 75373 | 93638 | 81300 | 81325 | 591600 | 0 | 591600 | 0 | [6 empty] | CM_M&G | 100%
500515 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-08-10 | 2021-08-10 | Scottish Water Wide | 0 | 88605 | 54097 | 62762.82 | 100947.52 | 140000 | 195587.66 | 642000 | 0 | 642000 | 0 | [6 empty] | CM_M&G | 100%
500516 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2020-03-31 | 2020-03-31 | Scottish Water Wide | 0 | 188619 | 364067 | 412601 | 329583.49 | 405000 | 310060.46 | 2009930.95 | 0 | 2009930.95 | 0 | [6 empty] | CM_M&G | 100%
500517 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-08-10 | 2021-08-10 | Scottish Water Wide | 0 | 71001.35 | 61042.65 | 143646.295 | 141375.37 | 127477 | 54878.34 | 599421.005 | 0 | 599421.005 | 0 | [6 empty] | CM_M&G | 100%
500518 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2021-06-03 | 2021-06-03 | Scottish Water Wide | 0 | 143114 | 456482 | 329441.008 | 959030.992 | 805000 | 795739 | 3488807 | 0 | 3488807 | 0 | [6 empty] | CM_M&G | 100%
500512 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-03-12 | 2021-03-12 | Scottish Water Wide | 0 | 95097 | 49190.54 | 201343.46 | 142836.14 | 139465 | 162067.86 | 790000 | 0 | 790000 | 0 | [6 empty] | CM_M&G | 100%
500519 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2021-06-03 | 2021-06-03 | Scottish Water Wide | 0 | 106171.37 | 164061.63 | 265458.89 | 259111.2 | 156500 | 180696.91 | 1132000 | 0 | 1132000 | 0 | [6 empty] | CM_M&G | 100%
500169 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-03-16 | 2016-05-23 | 2017-07-27 | 2018-03-01 | Na H-Eileanan an Iar | 0 | 9361.17 | 31552.83 | 22638.4325 | 382.39 | 0 | 0 | 63934.8225 | 0 | 63934.8225 | 9100.8743 | [6 empty] | EC01D | 34.08% | CS16D | 65.92%
046195 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-03-27 | 2014-10-23 | 2014-10-23 | 2014-10-21 | 2014-10-23 | Argyll and Bute-North Argyll | 728722.47 | 1689.83 | 0 | 0 | 0 | 0 | 0 | 1689.83 | 0 | 730412.3 | 0 | [6 empty] | CM_WSNI | 100%
403830 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-06 | 2014-08-08 | 2014-08-08 | 2015-06-15 |  | Argyll and Bute-North Argyll | 162529.62 | 30105.21 | 0 | 0 | 0 | 0 | 0 | 30105.21 | 0 | 192634.83 | 0 | [6 empty] | CM_WSNI | 100%
046222 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-08-11 | 2011-03-07 | 2011-03-07 | 2011-03-07 | 2011-03-07 | Argyll and Bute-North Argyll | 185037.31 | -0.31 | 0 | 0 | 0 | 0 | 0 | -0.31 | 0 | 185037 | 0 | [6 empty] | CM_WWNI | 100%
046201 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-08-11 | 2011-02-28 | 2011-02-28 | 2011-02-28 | 2011-02-28 | Argyll and Bute-North Argyll | 125419.25 | -0.25 | 0 | 0 | 0 | 0 | 0 | -0.25 | 0 | 125419 | 0 | [6 empty] | CM_WWNI | 100%
501168 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS1 | 2016-04-12 | 2020-05-04 | 2020-08-04 | 2021-04-15 | 2021-07-16 | East Ayrshire | 0 | 0 | 42142.34 | 74429.76 | -5483.99 | 10585.35 | 1006228.49 | 1127901.95 | 322313.61 | 1450215.56 | 0 | [6 empty] | CM_WWNI | 100%
403798 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS7 | 2014-05-14 | 2015-12-10 | 2016-01-06 | 2016-03-01 | 2016-04-01 | Dundee City | 25562 | 429532.94 | 73005.92 | 0 | -16758.3078 | 0 | 0 | 485780.5522 | 0 | 511342.5522 | 30795.6344 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
501381 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2018-04-30 | 2023-02-02 | 2023-06-08 | 2024-01-23 | 2024-04-24 | Scottish Borders | 0 | 0 | 7779.77 | 245.79 | 424.6 | 0 | 0 | 8450.16 | 217255.88 | 225706.04 | 0 | [6 empty] | CM_WSNI | 100%
503417 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MSU | 2021-06-15 | 2022-09-19 | 2023-01-06 | 2023-08-31 | 2023-12-01 | East Lothian | 0 | 0 | 0 | 0 | 64441.86 | 35228.82 | 35092.25 | 134762.93 | 365236.88 | 499999.81 | 148885.7057 | [6 empty] | SG1 | 100%
501537 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2022-10-17 | 2023-09-22 | 2024-01-26 | 2024-09-11 | 2024-12-12 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 729210.02 | 729210.02 | 0 | [6 empty] | CM_WSNI | 100%
500772 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS5 | 2015-08-10 | 2018-04-30 | 2018-05-22 | 2018-12-24 | 2018-12-24 | Renfrewshire | 0 | 23500 | 50735 | 128377.14 | 930613.86 | 58623 | 0 | 1191849 | 0 | 1191849 | 0 | [6 empty] | CM_WWI | 100%
502736 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2019-09-12 | 2021-03-08 | 2021-07-01 | 2022-06-21 | 2022-09-21 | Aberdeenshire | 0 | 0 | 0 | 68854.8805 | 90485.3715 | 165576.14 | 918167.25 | 1243083.642 | 4815414.34 | 6058497.982 | 148885.7057 | [6 empty] | SG1 | 100%
503441 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MSU | 2019-07-01 | 2020-10-05 | 2021-01-13 | 2021-09-21 | 2021-12-22 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 44799.45 | 210253.92 | 255053.37 | 327649.63 | 582703 | 148885.7057 | [6 empty] | SG1 | 100%
050016 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | General |  | SWD | Strategic Capacity | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000000 | [6 empty] | SR15_RSK_OMG | 100%
502248 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MSU | 2019-07-10 | 2019-07-10 | 2019-07-10 | 2019-08-08 | 2019-08-08 | Scottish Water Wide | 0 | 0 | 135242.6 | -242.6 | 61663.62 | 53336.38 | 0 | 250000 | 0 | 250000 | 0 | [6 empty] | CM_M&G | 100%
503454 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS0 | 2019-01-30 | 2019-04-15 | 2019-04-22 | 2021-01-14 | 2021-01-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 37800 | 146457.68 | 120742.31 | 304999.99 | 0 | 304999.99 | 294750.8556 | [6 empty] | CS25 | 100%
500850 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS6 | 2015-11-04 | 2016-03-25 | 2016-03-28 | 2017-01-01 | 2017-11-01 | Highland | 0 | 7050 | 22977.97 | 0 | 1000.03 | 0 | 0 | 31028 | 0 | 31028 | 60983.8924 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 19.15
402589 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-20 | 2012-03-20 | 2012-04-02 | 2015-02-02 |  | All East Unitary Authorities | 269263.54 | 736.46 | 83.46 | 0 | 0 | 0 | 0 | 819.92 | 0 | 270083.46 | 0 | [6 empty] | CM_WWI | 100%
402590 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-03-27 | 2012-03-27 | 2012-04-02 | 2017-02-16 |  | All East Unitary Authorities | 1360489 | 54625.98 | 844.67 | 0 | -1566.87 | 0 | 0 | 53903.78 | 0 | 1414392.78 | 0 | [6 empty] | CM_WWNI | 100%
401680 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-01-20 | 2011-06-23 | 2011-06-27 | 2014-03-31 | 2014-03-31 | All East Unitary Authorities | 106189 | 0 | -355.62 | 0 | 0 | 0 | 0 | -355.62 | 0 | 105833.38 | 2131.0001 | [6 empty] | DW1B | 100%
401681 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-01-20 | 2012-03-15 | 2012-03-26 | 2015-03-13 | 2015-03-31 | All North Unitary Authorities | 58575.56 | 23.18 | 0 | 0 | 0 | 0 | 0 | 23.18 | 0 | 58598.74 | 216 | [6 empty] | DW1B | 100%
401679 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-01-20 | 2012-02-10 | 2012-02-10 | 2015-03-25 | 2015-03-31 | All South Unitary Authorities | 74082 | 848 | -0.41 | -602.15 | 0 | 0 | 0 | 245.44 | 0 | 74327.44 | 2270 | [6 empty] | DW1B | 100%
401678 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-01-20 | 2011-10-27 | 2011-11-14 | 2014-12-15 | 2015-03-31 | All West Unitary Authorities | 125043 | 275 | -941.04 | 0 | 0 | 0 | 0 | -666.04 | 0 | 124376.96 | 1000 | [6 empty] | DW1B | 100%
500437 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2015-11-27 | 2015-11-27 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WWI | 100%
400732 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-22 | 2010-04-22 | 2010-05-03 | 2015-07-02 |  | Scottish Water Wide | 2739142 | 39075.76 | 6442.58 | 0 | 0 | 0 | 0 | 45518.34 | 0 | 2784660.34 | 0 | [6 empty] | CM_WSI | 100%
400733 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-22 | 2010-04-22 | 2010-05-03 | 2015-07-02 |  | Scottish Water Wide | 3534103 | -20614 | -25906.68 | 0 | 0 | 0 | 0 | -46520.68 | 0 | 3487582.32 | 0 | [6 empty] | CM_WSI | 100%
404106 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-03-23 | 2015-03-23 | 2015-03-23 | 2016-06-23 |  | Scottish Water Wide | 434759 | 198424.15 | -21989.66 | 0 | 0 | 0 | 0 | 176434.49 | 0 | 611193.49 | 0 | [6 empty] | CM_M&G | 100%
502241 | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater |  | SWMD | Sludge | MS7 | 2016-06-30 | 2017-03-28 | 2017-05-11 | 2017-08-01 | 2017-11-01 | North Lanarkshire | 0 | 0 | 10327.1 | 41039.61 | 0 | 0 | 0 | 51366.71 | 0 | 51366.71 | 0 | [6 empty] | LA01_S | 100% | bar: Regulatory Outputs OMG-24
501544 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2019-05-30 | 2019-11-11 | 2020-03-18 | 2021-07-02 | 2021-10-04 | Orkney Islands | 0 | 23360.73 | 16088.43 | 18965.78 | 201636.684 | 2761130.73 | 2484226.91 | 5505409.264 | 1460940.38 | 6966349.644 | 0 | [6 empty] | CM_WSNI | 100%
502553 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | East Lothian | 0 | 0 | 31033.94 | 28867.835 | 0 | 0 | 0 | 59901.775 | 0 | 59901.775 | 148885.7057 | [6 empty] | SG1 | 100%
500576 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2021-04-01 | 2022-08-03 | 2022-10-25 | 2023-04-24 | 2024-10-01 | Orkney Islands | 0 | 25559.02 | 8671.97 | 33315.61 | 32356.9 | 4975.09 | 12524.2 | 117402.79 | 4383000.02 | 4500402.81 | 148885.7057 | [6 empty] | SG1 | 100%
403606 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-11-11 | 2013-11-21 | 2014-04-01 | 2016-12-19 |  | All East Unitary Authorities | 303821 | -54625 | -25540.49 | 256.8 | 0 | 0 | 0 | -79908.69 | 0 | 223912.31 | 0 | [6 empty] | CM_WWNI | 100%
403669 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWMD | Infra Charge | MS6 | 2014-08-18 | 2015-06-30 | 2015-10-26 | 2017-08-28 | 2017-08-28 | Aberdeen City | 7020 | 162390 | 163864.24 | 141725.76 | -8572.72 | 0 | 0 | 459407.28 | 0 | 466427.28 | 0 | [6 empty] | CM_WSNI | 7.368% | WG5 | 92.63%
502282 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | GW2 | 2019-07-31 | 2020-08-31 | 2021-01-08 | 2020-12-01 | 2021-03-01 | Highland | 0 | 0 | 24636.03 | 9100.5 | 13363.47 | 0 | 198861.66 | 245961.66 | 379038.33 | 624999.99 | 522658.1799 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
045358 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2012-02-13 | 2012-05-14 | 2014-09-16 | 2014-11-21 | Highland | 334827.49 | -238.97 | 0 | 0 | 0 | 0 | 0 | -238.97 | 0 | 334588.52 | 2774 | [6 empty] | DW13 | 100%
403271 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-01-14 | 2013-06-14 | 2013-06-14 | 2016-05-31 |  | Scottish Water Wide | 2799601.53 | 68081.42 | -112.98 | 0 | 0 | 0 | 0 | 67968.44 | 0 | 2867569.97 | 0 | [6 empty] | CM_WWNI | 100%
402687 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-05-28 | 2012-09-26 | 2013-01-31 | 2014-12-18 | 2014-12-24 | Scottish Water Wide | 2806579.54 | -36028.04 | -15610.49 | 0 | 0 | 0 | 0 | -51638.53 | 0 | 2754941.01 | 9187 | [6 empty] | DW9A | 100%
402888 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 2055446.39 | 1942792.55 | 292518.37 | -4886.64 | 0 | 0 | 0 | 2230424.28 | 0 | 4285870.67 | 761868.9351 | [6 empty] | CM_WSNI | 48% | DW9A | 52%
402889 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2016-03-25 | 2016-03-25 | Scottish Water Wide | 4210597.59 | 4551823.44 | 1395787.56 | 473.15 | -220 | 0 | 0 | 5947864.15 | 0 | 10158461.74 | 3314681.2239 | [6 empty] | CM_WSNI | 45.1% | DW9A | 54.9%
402890 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-09-14 | 2014-05-29 | 2014-07-16 | 2016-03-31 | 2016-03-31 | Scottish Water Wide | 3308494.47 | 3544477.05 | 1443347.04 | 1747.15 | 0 | 0 | 0 | 4989571.24 | 0 | 8298065.71 | 2227468.8191 | [6 empty] | DW9E | 0.1% | CM_WSNI | 48% | DW9A | 51.9%
402891 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-09-10 | 2013-02-12 | 2013-02-13 | 2013-05-29 | 2013-06-24 | Scottish Water Wide | 197486.97 | -6975 | 0 | 0 | 0 | 0 | 0 | -6975 | 0 | 190511.97 | 1282 | [6 empty] | DW9A | 100%
402892 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2016-03-30 | 2016-03-31 | Scottish Water Wide | 1740881.26 | 1731310.81 | 1010501.84 | 77188.59 | -45975.02 | 0 | 0 | 2773026.22 | 0 | 4513907.48 | 1446743 | [6 empty] | DW9E | 2.9% | CM_WSNI | 48% | DW9A | 49.1%
501742 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-06-19 | 2017-06-19 | 2017-06-19 | 2017-05-29 | 2017-05-29 | Renfrewshire | 0 | 0 | 2347.55 | 3213.47 | 125.79 | 0 | 0 | 5686.81 | 0 | 5686.81 | 0 | [6 empty] | CM_WWI | 100%
046333 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-03-25 | 2010-07-26 | 2013-03-25 | 2014-09-09 | 2014-09-09 | Dumfries and Galloway | 1159027.88 | 14945.96 | -1006.43 | 4 | 0 | 0 | 0 | 13943.53 | 0 | 1172971.41 | 0 | [6 empty] | SG1 | 24.98% | CM_WWNI | 75.02%
501155 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS5 | 2015-12-14 | 2017-03-28 | 2017-06-23 | 2019-01-31 | 2019-01-31 | South Ayrshire | 0 | 8800.42 | 221686.58 | 744670 | 374928 | 19208 | 2500 | 1371793 | 0 | 1371793 | 0 | [6 empty] | CM_WWNI | 100%
502953 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS2 | 2016-09-28 | 2019-03-27 | 2019-06-28 | 2019-12-01 | 2021-03-01 | Shetland Islands | 0 | 0 | 0 | 20542.9575 | 143986.0125 | 51065.79 | 79896.88 | 295491.64 | 3589.5 | 299081.14 | 604186.9752 |  |  |  |  | 1089.9997 |  | DW2 | 2.22% | DW23 | 48.89% | DW25P | 48.89% | bar: Regulatory Outputs OMG-01
403567 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS7 | 2013-08-30 | 2014-12-11 | 2015-02-04 | 2015-07-16 | 2016-03-10 | East Dunbartonshire | 323184 | 120116 | 5000 | 0 | 159424.788 | 0 | 0 | 284540.788 | 0 | 607724.788 | 338633.3104 | [6 empty] | CS11 | 100%
046194 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-17 | 2011-06-14 | 2011-08-22 | 2013-12-30 | 2014-02-25 | Glasgow City | 2957266.32 | 50697.84 | 0 | 0 | 0 | 0 | 0 | 50697.84 | 0 | 3007964.16 | 0 | [6 empty] | CM_WWNI | 100%
501545 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2016-01-27 | 2021-11-08 | 2022-03-10 | 2022-10-17 | 2023-01-17 | West Lothian | 0 | 3689 | 18453.17 | 0 | 0 | 0 | 0 | 22142.17 | 327857.84 | 350000.01 | 0 | [6 empty] | CM_WSNI | 100%
503197 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2018-12-10 | 2019-11-11 | 2020-01-27 | 2020-11-01 | 2021-11-01 | West Lothian | 0 | 0 | 0 | 0 | 194699.64 | 549207.31 | 385027.7 | 1128934.65 | 257734.38 | 1386669.03 | 0 | [6 empty] | DW5MR | 39% | DW5FS | 61% | [16 empty] | Regulatory Outputs OMG-06: 210.021
501750 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-01-29 | 2016-03-07 | 2016-03-07 | 2016-03-01 | 2016-03-01 | West Lothian | 0 | 2462 | 7684.64 | 228.745 | 0 | 0 | 0 | 10375.385 | 0 | 10375.385 | 1777.3932 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
501389 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-04-20 | 2022-05-18 | 2022-09-21 | 2023-05-08 | 2023-08-08 | West Lothian | 0 | 0 | 10046.51 | 0 | 638.698 | 0 | 0 | 10685.208 | 489314.76 | 499999.968 | 0 | [6 empty] | CM_WSNI | 100%
501397 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2021-05-28 | 2022-04-06 | 2022-07-04 | 2023-08-01 | 2023-11-01 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1059116.99 | 1059116.99 | 0 | [6 empty] | CM_WSI | 100%
046822 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-05-07 | 2012-02-28 | 2012-08-20 | 2014-09-29 | 2015-11-02 | West Lothian | 3031467.15 | -20087.4 | -3417.05 | 0 | 0 | 0 | 0 | -23504.45 | 0 | 3007962.7 | 0 | [6 empty] | CM_WSNI | 100%
503440 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MSU | 2021-06-15 | 2022-09-05 | 2023-01-06 | 2023-08-03 | 2023-11-03 | Midlothian | 0 | 0 | 0 | 0 | 59441.86 | 16071.26 | 48557.54 | 124070.66 | 625929.28 | 749999.94 | 148885.7057 | [6 empty] | SG1 | 100%
503544 | Q&S4 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWD | Revised Bathing Waters Directive | MSU | 2019-07-01 | 2020-05-18 | 2020-08-14 | 2021-09-14 | 2021-12-15 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 293972.64 | 2178264.68 | 2472237.32 | 1900762.7 | 4373000.02 | 2269817.6904 | [6 empty] | EC16B | 100%
501499 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS1 | 2016-07-11 | 2020-04-20 | 2020-08-21 | 2021-08-05 | 2021-11-04 | East Ayrshire | 0 | 0 | 43306.86 | 205553.08 | 24944.82 | 10008.97 | 1473783.76 | 1757597.49 | 1458639.61 | 3216237.1 | 0 | [6 empty] | CM_WWNI | 100%
502865 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS5 | 2017-09-29 | 2017-09-29 | 2017-09-29 | 2019-02-18 | 2019-02-18 | Scottish Water Wide | 0 | 0 | 0 | 393561.79 | 513769.58 | 22555.56 | 0 | 929886.93 | 0 | 929886.93 | 0 | [6 empty] | CM_M&G | 100%
403698 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-02-27 | 2016-07-29 | 2016-02-16 | 2015-10-30 |  | Scottish Water Wide | 74499 | 10759.1 | 175.36 | 0 | 0 | 0 | 0 | 10934.46 | 0 | 85433.46 | 0 | [6 empty] | CM_WSI | 100%
502434 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2021-06-30 | 2022-05-06 | 2022-08-11 | 2023-03-08 | 2023-03-08 | Fife | 0 | 0 | 4764.74 | 365.02 | 21.29 | 0 | 0 | 5151.05 | 369848.96 | 375000.01 | 0 | [6 empty] | CM_WSI | 100%
403973 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS3 | 2016-07-11 | 2018-11-05 | 2018-11-27 | 2020-03-11 | 2020-03-12 | Scottish Borders | 2866.55 | 29088.45 | 75422.73 | 271147.21 | 1451750.32 | 1704911.94 | 102559.62 | 3634880.27 | 3559.23 | 3641306.05 | 0 | [6 empty] | SG1 | 100%
502613 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS2 | 2017-08-28 | 2019-02-26 | 2019-06-07 | 2019-09-26 | 2020-01-10 | Stirling | 0 | 0 | 1551.36 | 34662.64 | 73751 | 71198 | 273.95 | 181436.95 | 135.05 | 181572 | 0 | [6 empty] | CM_WWI | 100%
502554 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2019-06-03 | 2020-11-02 | 2021-03-10 | 2022-03-08 | 2022-06-08 | East Lothian | 0 | 0 | 34581.06 | 9386.07 | 5741.56 | 29272.46 | 17674.8 | 96655.95 | 38344.12 | 135000.07 | 148885.7057 | [6 empty] | SG1 | 100%
500171 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-04-29 | 2016-06-30 | 2017-06-29 | 2018-01-30 | Midlothian | 0 | 5000 | 33648 | 18769 | -3380.38 | 0 | 0 | 54036.62 | 0 | 54036.62 | 87407.9517 | [6 empty] | EC01D | 7.47% | CS16D | 18.51% | EC01G | 37.01% | EC10E | 37.01%
030573 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-17 | 2010-09-20 | 2011-03-15 | 2012-01-27 | 2012-02-10 | Midlothian | 568855.38 | -13342.3 | 0 | 0 | 0 | 0 | 0 | -13342.3 | 0 | 555513.08 | 0 | [6 empty] | CM_WWNI | 20% | EC01A | 80%
502810 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-08-01 | 2017-08-01 | 2018-03-30 | 2020-03-06 | 2020-03-06 | Midlothian | 0 | 0 | 0 | 43591.23 | 236038.7 | 100321.69 | 23000.38 | 402952 | 3048.02 | 406000.02 | 0 | [6 empty] | CM_WWNI | 100%
503223 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-12-20 | 2023-05-26 | 2023-09-27 | 2024-09-23 | 2024-12-24 | Midlothian | 0 | 0 | 0 | 0 | 83888.742 | 15819.06 | 18508.32 | 118216.122 | 30042.43 | 148258.552 | 148885.7057 | [6 empty] | SG1 | 100%
045570 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-19 | 2011-09-28 | 2012-07-18 | 2013-09-10 | 2014-01-27 | Argyll and Bute-North Argyll | 1105298.15 | -6287.87 | 0 | 0 | 0 | 0 | 0 | -6287.87 | 0 | 1099010.28 | 2725 | [6 empty] | DW23 | 100%
501501 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-02-22 | 2017-12-18 | 2018-02-09 | 2019-08-26 | 2019-08-26 | Inverclyde | 0 | 3342.34 | 7037.66 | 181877.63 | 608155.24 | 162044.17 | 1717.89 | 964174.93 | 0.06 | 964174.99 | 0 | [6 empty] | CM_WWI | 100%
403359 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-04-29 | 2014-07-31 | 2014-07-31 | 2015-03-30 | 2015-04-29 | South Ayrshire | 2427033.35 | 113007.6 | 3211.91 | 12834.76 | 0 | 0 | 0 | 129054.27 | 0 | 2556087.62 | 0 | [6 empty] | CM_WSI | 100%
501575 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-01-12 | 2017-03-06 | 2017-03-06 | 2017-08-01 | 2017-10-01 | South Ayrshire | 0 | 0.07 | 1073.31 | 676.035 | 0.005 | 0 | 0 | 1749.42 | 0 | 1749.42 | 105089.0046 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
503356 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2019-03-12 | 2020-11-09 | 2021-02-26 | 2021-12-17 | 2022-03-18 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 1962.62 | 27094.94 | 153911.29 | 182968.85 | 202031.16 | 385000.01 | 0 | [6 empty] | CM_WSNI | 100%
501099 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2015-09-30 | 2016-01-22 | 2016-03-01 | 2016-03-04 | 2016-03-04 | Perth and Kinross | 0 | 2071.38 | 306.66 | 0 | 0 | 0 | 0 | 2378.04 | 0 | 2378.04 | 0 | [6 empty] | EC10D | 100%
500168 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS3 | 2015-03-26 | 2016-09-30 | 2016-09-30 | 2019-05-24 | 2019-08-21 | Perth and Kinross | 0 | 33270 | 284033 | 473530 | 193883.24 | 63350.97 | 0 | 1048067.21 | 0 | 1048067.21 | 350477.1395 | [6 empty] | CS11 | 19.85% | CS16D | 80.15%
045633 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-31 | 2011-06-28 | 2011-09-30 | 2013-03-28 |  | Perth and Kinross | 1974705.5 | -6148.15 | -1044.45 | 0 | 0 | 0 | 0 | -7192.6 | 0 | 1967512.9 | 0 | [6 empty] | CM_WWNI | 100%
500635 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2015-05-20 | 2016-11-21 | 2016-11-21 | 2017-05-29 | 2017-05-29 | Perth and Kinross | 0 | 101145 | 389458.35 | 151578.6 | 29848.55 | 39.51 | 24.36 | 672094.37 | 0 | 672094.37 | 0 | [6 empty] | CM_WWNI | 100%
502067 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2021-05-31 | 2022-04-29 | 2022-07-20 | 2023-02-17 | 2023-05-22 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538359.99 | 538359.99 | 0 | [6 empty] | CM_WWI | 100%
500210 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS4 | 2015-03-20 | 2017-09-29 | 2017-09-29 | 2019-03-15 | 2020-03-09 | Perth and Kinross | 0 | 1000 | 29934 | 206004 | 403391.82 | 5327.48 | 35761.2 | 681418.5 | 0 | 681418.5 | 325288.302 | [6 empty] | DW5 | 100%
045801 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-09 | 2011-07-29 | 2011-08-09 | 2011-07-01 | 2011-07-01 | Perth and Kinross | 43397.64 | 4105.34 | 0 | 0 | 0 | 0 | 0 | 4105.34 | 0 | 47502.98 | 0 | [6 empty] | CM_WWNI | 8.488% | WQ01C | 91.51%
500868 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2016-03-09 | 2018-09-18 | 2018-10-24 | 2019-09-01 | 2020-10-01 | Perth and Kinross | 0 | 19786.85 | 7325.15 | 24264.45 | 87513.77 | 11675.4 | 40010.41 | 190576.03 | 36727.43 | 227303.46 | 586263.6194 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 52.71
502933 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-10-31 | 2018-07-04 | 2018-11-26 | 2019-06-10 | 2019-06-11 | Perth and Kinross | 0 | 0 | 0 | 4549.71 | 285639.79 | 219290.64 | 1123.91 | 510604.05 | 1565.6 | 512169.65 | 0 | [6 empty] | CM_WWNI | 100%
046745 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-06-16 | 2011-06-28 | 2011-09-30 | 2013-11-28 | 2014-01-27 | Perth and Kinross | 7874424.69 | -54121.36 | 20288.55 | 0 | 0 | 0 | 0 | -33832.81 | 0 | 7840591.88 | 81872 | [6 empty] | EC06 | 100%
402012 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-04-11 | 2014-07-02 | 2014-07-02 | 2015-03-18 | 2015-03-19 | Perth and Kinross | 2527497.73 | 113186.6 | 26203.18 | 0 | 0 | 0 | 0 | 139389.78 | 0 | 2666887.51 | 279674 | [6 empty] | WQ01C | 100%
500172 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS5 | 2015-03-20 | 2016-03-31 | 2016-08-08 | 2018-09-01 | 2018-11-01 | Aberdeenshire | 0 | 32752 | 18476.81 | 61423.19 | 56589 | 10758.99 | 0 | 179999.99 | 0 | 179999.99 | 10362.528 | [6 empty] | EC01G | 10.35% | CS16D | 89.65% | bar: Regulatory Outputs OMG-22
046258 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-03-30 | 2009-02-17 | 2011-09-05 | 2012-03-29 |  | Aberdeenshire | 448551.62 | 620 | 0 | 0 | 0 | 0 | 0 | 620 | 0 | 449171.62 | 0 | [6 empty] | CM_WSNI | 100%
403277 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-05-21 | 2015-03-26 | 2015-07-08 | 2015-12-04 |  | Fife | 283861.46 | 753282.18 | 2455.31 | 809.46 | 0 | 0 | 0 | 756546.95 | 0 | 1040408.41 | 0 | [6 empty] | CM_WWNI | 100%
403278 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-02-08 | 2014-08-13 | 2014-08-13 | 2014-08-14 |  | Moray | 126036.93 | -33.92 | 0 | 0 | 0 | 0 | 0 | -33.92 | 0 | 126003.01 | 0 | [6 empty] | CM_WWNI | 100%
403280 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-01-10 | 2015-09-22 | 2015-09-16 | 2015-04-21 | 2015-04-21 | Moray | 191256 | 5254.57 | 0 | 0 | 0 | 0 | 0 | 5254.57 | 0 | 196510.57 | 0 | [6 empty] | CM_WWNI | 100%
403279 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-02-01 | 2014-06-30 | 2014-04-16 | 2014-04-16 |  | Orkney Islands | 83247.73 | 3183.73 | 0 | 0 | 0 | 0 | 0 | 3183.73 | 0 | 86431.46 | 0 | [6 empty] | CM_WWNI | 100%
500170 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS3 | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2019-05-24 | 2019-08-26 | South Lanarkshire | 0 | 73937.35 | 308628.65 | 234930 | 117125 | 80953.97 | 0 | 815574.97 | 0 | 815574.97 | 350477.1395 | [6 empty] | CS11 | 18.97% | CS16D | 81.03%
402987 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-11-30 | 2013-03-05 | 2013-03-18 | 2015-09-21 |  | South Lanarkshire | 258787 | 5450 | 0.31 | -3186.45 | 0 | 0 | 0 | 2263.86 | 0 | 261050.86 | 0 | [6 empty] | CM_WWI | 100%
046355 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-06-01 | 2011-09-21 | 2011-10-31 | 2016-02-16 |  | South Lanarkshire | 2838709.32 | 13753.03 | -16535.04 | 600.6 | 0 | 0 | 0 | -2181.41 | 0 | 2836527.91 | 0 | [6 empty] | CM_WWNI | 100%
503224 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-05 | 2023-06-20 | 2023-10-13 | 2024-10-09 | 2025-01-09 | South Lanarkshire | 0 | 0 | 0 | 0 | 65219.251 | 11823.47 | 36609.8 | 113652.521 | 28347.73 | 142000.251 | 148885.7057 | [6 empty] | SG1 | 100%
502691 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-04-01 | 2022-05-27 | 2022-09-19 | 2023-05-01 | 2023-08-01 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250250.04 | 250250.04 | 0 | [6 empty] | CM_WWNI | 100%
501807 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2021-06-30 | 2022-05-09 | 2022-08-10 | 2022-12-22 | 2023-03-24 | South Lanarkshire | 0 | 0 | 6082.77 | 204.16 | 0 | 0 | 0 | 6286.93 | 215257.17 | 221544.1 | 0 | [6 empty] | CM_WWI | 100%
500211 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS4 | 2015-03-27 | 2016-03-31 | 2016-05-30 | 2018-06-27 | 2019-10-01 | East Renfrewshire | 0 | 38753 | 47802.42 | 79902.248 | 81330.832 | 9455.4 | 625.67 | 257869.57 | 0 | 257869.57 | 2120057.4647 | [6 empty] | DW5FS | 100%
500869 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2016-04-12 | 2017-03-30 | 2017-03-31 | 2018-08-01 | 2018-12-01 | East Renfrewshire | 0 | 2671.71 | 7621.29 | 98587 | 54146.78 | 2499.97 | 0 | 165526.75 | 0 | 165526.75 | 239838.1416 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 54.04
501214 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-03-21 | 2016-09-06 | 2016-09-07 | 2016-09-01 | 2016-09-01 | South Lanarkshire | 0 | 761.13 | 1179.66 | 207.95 | 0 | 0 | 0 | 2148.74 | 0 | 2148.74 | 466391.8995 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
404132 | Q&S3B | Completion | OMG180 |  |  | Water |  | WINF | OMG180 | MS3 | 2013-06-30 | 2016-01-31 | 2016-02-29 | 2021-03-01 | 2021-10-01 | East Renfrewshire | 0 | 0 | 11661.8 | 76869.1 | 243010.9 | 2334231.55 | 8958809.9 | 11624583.25 | 31515.91 | 11656099.16 | 0 | [6 empty] | DW25 | 100% | bar: Regulatory Outputs OMG-03
503550 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2019-05-01 | 2020-08-17 | 2020-12-17 | 2022-02-01 | 2022-05-04 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 26676 | 85943.62 | 112619.62 | 147380.44 | 260000.06 | 0 | [6 empty] | CM_WSNI | 100%
500671 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-06-11 | 2017-01-30 | 2017-02-20 | 2017-10-27 | 2017-10-27 | West Dunbartonshire | 0 | 22800 | 185033 | 51130 | -5687 | 0 | 0 | 253276 | 0 | 253276 | 0 | [6 empty] | CM_WWI | 100%
501658 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2021-07-01 | 2022-04-22 | 2022-07-20 | 2023-02-17 | 2023-05-22 | Argyll and Bute-Cowal & Bute | 0 | 0 | 3834.94 | 526.76 | 12186.845 | 0 | 0 | 16548.545 | 124596.74 | 141145.285 | 0 | [6 empty] | CM_WWI | 100%
502209 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWMD | Wastewater infrastructure | MS3 | 2016-05-09 | 2016-08-01 | 2016-09-30 | 2020-03-13 | 2020-03-16 | Scottish Water Wide | 0 | 0 | 439137.02 | 938796.76 | 543444.37 | 371889.99 | 3520.71 | 2296788.85 | 3211.11 | 2299999.96 | 0 | [6 empty] | CM_M&G | 100%
502201 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWMD | Wastewater infrastructure | MS3 | 2016-04-18 | 2016-11-21 | 2017-07-04 | 2019-09-16 | 2019-12-16 | Scottish Water Wide | 0 | 0 | 69618.94 | 74409.97 | 84999.06 | 212420.3 | 29969.81 | 471418.08 | 8581.94 | 480000.02 | 0 | [6 empty] | CM_M&G | 100%
502202 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWMD | Wastewater infrastructure | MS3 | 2016-05-04 | 2016-08-30 | 2016-10-25 | 2020-03-13 | 2020-03-13 | Scottish Water Wide | 0 | 0 | 83884.46 | 568627.74 | 683256 | 585183 | 813359.5 | 2734310.7 | 3790.91 | 2738101.61 | 0 | [6 empty] | CM_M&G | 100%
502203 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWMD | Wastewater infrastructure | MS3 | 2016-04-18 | 2016-08-30 | 2016-11-28 | 2020-07-24 | 2020-10-26 | Scottish Water Wide | 0 | 0 | 127858.7 | 544404.81 | 517974.26 | 626624.64 | 247780.51 | 2064642.92 | 120356.93 | 2184999.85 | 0 | [6 empty] | CM_M&G | 100%
500967 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2015-10-21 | 2018-03-14 | 2018-05-23 | 2019-05-30 | 2019-05-30 | Fife | 0 | 7151.89 | 17447.11 | 184000 | 514970.7616 | 13780.07 | 3491.9 | 740841.7316 | 0.03 | 740841.7616 | 0 | [6 empty] | CM_WWNI | 100%
403625 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-12-17 | 2014-04-23 | 2014-04-29 | 2015-01-23 |  | Fife | 116099 | 6614.1 | 0 | 0 | 0 | 0 | 0 | 6614.1 | 0 | 122713.1 | 0 | [6 empty] | CM_WWI | 100%
501611 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW1 | 2022-02-21 | 2022-12-21 | 2023-04-26 | 2023-09-05 | 2023-12-06 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141671.02 | 141671.02 | 0 | [6 empty] | CM_WWNI | 100%
030585 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-15 | 2012-05-29 | 2012-08-20 | 2014-08-14 | 2014-09-29 | North Lanarkshire | 8537337.19 | 32812.02 | 55334.5 | 0 | 0 | 0 | 0 | 88146.52 | 0 | 8625483.71 | 85753.3561 | [6 empty] | CM_WWNI | 5% | SG1 | 5% | EC10A | 40% | EC04A | 50%
502543 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2017-02-23 | 2017-02-23 | 2017-03-01 | 2017-03-31 | 2017-03-31 | North Lanarkshire | 0 | 0 | 42523.36 | 820908.49 | -690.74 | 0 | 0 | 862741.11 | 0 | 862741.11 | 0 | [6 empty] | CM_WWI | 100%
404010 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2017-03-29 | 2017-04-03 | 2017-04-03 | 2017-04-03 |  | Scottish Water Wide | 173465.68 | 56598.32 | -939.21 | 0 | 0 | 0 | 0 | 55659.11 | 0 | 229124.79 | 0 | [6 empty] | CM_M&G | 100%
501223 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2015-12-22 | 2016-05-18 | 2017-06-26 | 2021-03-10 | 2021-03-10 | Scottish Water Wide | 0 | 33776.17 | 143894.46 | 18189.12 | 287613.25 | 433008 | 560368.82 | 1476849.82 | 0 | 1476849.82 | 0 | [6 empty] | CM_WWI | 100%
500708 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2017-01-11 | 2017-01-27 | Scottish Water Wide | 0 | 2662000 | 226225.11 | 17415.43 | 0 | 0 | 0 | 2905640.54 | 0 | 2905640.54 | 0 | [6 empty] | CM_WSI | 100%
502675 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2017-08-30 | 2017-09-26 | 2017-09-26 | 2019-05-28 | 2019-05-29 | Scottish Water Wide | 0 | 0 | 0 | 2626405.2556 | 2300251.7844 | 0 | 0 | 4926657.04 | 0 | 4926657.04 | 0 | [6 empty] | CM_WSI | 100%
503059 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2018-03-12 | 2019-03-28 | 2019-03-28 | 2020-01-21 | 2020-06-10 | Scottish Water Wide | 0 | 0 | 0 | 3753.5 | 109964.69 | 1360415.48 | 330764.34 | 1804898.01 | 0 | 1804898.01 | 0 | [6 empty] | CM_WSI | 100%
502261 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2016-07-13 | 2016-07-13 | 2016-08-01 | 2019-04-03 | 2019-04-03 | Scottish Water Wide | 0 | 0 | 1342187.81 | 922812.19 | 0 | 0 | 0 | 2265000 | 0 | 2265000 | 0 | [6 empty] | CM_WSI | 100%
501718 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-10-21 | 2016-11-17 | East Ayrshire | 0 | 0 | 3313.17 | 0 | 0 | 0 | 0 | 3313.17 | 0 | 3313.17 | 0 | [6 empty] | CM_WWI | 100%
502319 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2016-08-23 | 2016-08-23 | 2016-10-26 | 2017-09-25 | 2017-09-25 | Scottish Water Wide | 0 | 0 | 886608.99 | 277965.098 | 391.692 | 0 | 0 | 1164965.78 | 0 | 1164965.78 | 0 | [6 empty] | CM_WWI | 100%
502715 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS5 | 2017-05-04 | 2017-05-04 | 2017-06-01 | 2018-10-01 | 2018-10-01 | Scottish Water Wide | 0 | 0 | 0 | 887640.95 | 245976.988 | 0 | 0 | 1133617.938 | 0 | 1133617.938 | 0 | [6 empty] | CM_WWI | 100%
503130 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-08-31 | 2018-08-31 | 2018-09-17 | 2019-08-23 | 2019-08-23 | Scottish Water Wide | 0 | 0 | 0 | 0 | 575695.62 | 524304.38 | 0 | 1100000 | 0 | 1100000 | 0 | [6 empty] | CM_WWI | 100%
503560 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2019-05-01 | 2019-06-03 | 2019-08-08 | 2020-05-05 | 2020-08-05 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 464179.26 | 231238.94 | 695418.2 | 4581.81 | 700000.01 | 0 | [6 empty] | CM_WWI | 100%
501296 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2021-04-15 |  |  | 2021-04-15 | 2021-04-15 | Scottish Water Wide | 0 | 0 | 0 | 20.22 | 0 | 0 | 685434.77 | 685454.99 | 0 | 685454.99 | 0 | [6 empty] | CM_WWI | 100%
046411 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-08-25 | 2011-12-20 | 2011-12-29 | 2011-12-19 |  | East Renfrewshire | 40766.39 | 3291.78 | 0 | 0 | 0 | 0 | 0 | 3291.78 | 0 | 44058.17 | 0 | [6 empty] | CM_WSNI | 100%
500433 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-06-02 | 2015-06-02 | 2015-06-11 | 2016-09-22 | 2016-09-22 | Scottish Water Wide | 0 | 984391 | -25695.61 | 431.52 | 0 | 0 | 0 | 959126.91 | 0 | 959126.91 | 0 | [6 empty] | CM_WWI | 100%
500908 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS6 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-06-01 | 2016-06-01 | Argyll and Bute-North Argyll | 0 | 3010 | -149.81 | 0 | 0 | 0 | 0 | 2860.19 | 0 | 2860.19 | 466391.8995 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
502838 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-18 | 2022-10-21 | 2023-02-20 | 2024-02-15 | 2024-05-17 | Highland | 0 | 0 | 0 | 21346.13 | 1340.34 | 27313.51 | 0 | 49999.98 | 949999.96 | 999999.94 | 148885.7057 | [6 empty] | WG1 | 100%
403415 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-12-05 | 2015-01-12 |  | Argyll and Bute-North Argyll | 286000 | 0 | -2765.58 | 0 | 0 | 0 | 0 | -2765.58 | 0 | 283234.42 | 0 | [6 empty] | CM_WWI | 40.15% | CM_WWNI | 59.85%
502368 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-05-03 | 2022-11-04 | 2023-03-09 | 2024-10-02 | 2025-01-02 | Argyll and Bute-North Argyll | 0 | 0 | 35762.48 | 33128.44 | 1957.092 | 0 | 0 | 70848.012 | 1401408.9 | 1472256.912 | 0 | [6 empty] | CM_WSNI | 100%
502131 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | Argyll and Bute-North Argyll | 0 | 0 | 18464.01 | 0 | 0 | 0.01 | 0 | 18464.02 | 0 | 18464.02 | 0 | [6 empty] | CM_WWI | 100%
500776 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS0 | 2015-08-24 | 2022-01-17 | 2022-02-08 | 2022-08-01 | 2022-10-24 | Argyll and Bute-North Argyll | 0 | 28311 | 68658.02 | 10961.58 | -38615.8 | 0 | 0 | 69314.8 | 0 | 69314.8 | 0 | [6 empty] | CM_WSNI | 100%
403020 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-10-30 | 2012-10-30 | 2012-12-03 | 2013-11-22 |  | Argyll and Bute-Cowal & Bute | 414439 | 214.68 | 0 | 0 | 0 | 0 | 0 | 214.68 | 0 | 414653.68 | 0 | [6 empty] | CM_WSNI | 100%
502869 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2021-04-06 | 2022-09-02 | 2022-12-26 | 2023-12-18 | 2024-03-19 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 21237.996 | 3195.346 | 12178.98 | 13989.42 | 50601.742 | 283.97 | 50885.712 | 148885.7057 | [6 empty] | WG1 | 100%
501378 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2016-04-12 | 2017-06-20 | 2017-06-26 | 2018-03-07 | 2018-03-07 | Argyll and Bute-North Argyll | 0 | 0 | 93085 | 721499 | -4316.5113 | 0 | 0 | 810267.4887 | 0 | 810267.4887 | 0 | [6 empty] | CM_WWI | 100%
403431 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS2 | 2013-04-16 | 2019-03-26 | 2019-05-13 | 2020-02-06 | 2020-05-13 | Renfrewshire | 44912.9 | 47506.97 | 43854.13 | 67779 | 441132 | 2283814.87 | 103929.33 | 2988016.3 | 15712.6 | 3048641.8 | 229318.7788 |  |  |  |  | 8180.0004 |  | CS11 | 100%
404095 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-12-24 | 2015-02-19 | 2015-02-19 | 2016-06-14 |  | Scottish Water Wide | 199676 | 877400.01 | -20923.38 | 0 | 0 | 0 | 0 | 856476.63 | 0 | 1056152.63 | 0 | [6 empty] | CM_M&G | 100%
501577 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2017-02-28 | 2018-04-30 | 2018-04-30 | 2019-12-02 |  | Scottish Water Wide | 0 | 92596 | 1068720.1 | 4018802.1675 | 5267213.7325 | 1376785.99 | 0 | 11824117.99 | 0 | 11824117.99 | 0 |  |  |  |  | 326995.5997 |  | CM_M&G | 100%
300024 | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2011-09-29 | 2019-01-23 | 2019-01-03 | 2019-01-16 | 2019-01-16 | City of Edinburgh | 243.9 | 46251.1 | -46251.1 | 0 | 0 | 0 | 0 | 0 | 0 | 243.9 | 142822 | [6 empty] | EC01C | 100%
300033 | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-03-21 | 2012-06-15 | 2012-06-15 | 2015-01-09 | 2015-01-09 | City of Edinburgh | 83839 | -5842.4 | 0 | 0 | 0 | 0 | 0 | -5842.4 | 0 | 77996.6 | 10264 | [6 empty] | EC02B | 100%
403757 | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | SWMD | Ring Fenced Environmental | MS3 | 2014-03-31 | 2019-03-21 | 2019-03-21 | 2020-07-01 | 2020-10-01 | City of Edinburgh | 82211 | 1921 | 90735.57 | 334550.43 | 1566752 | 782664.69 | 355974.94 | 3132598.63 | 36778.41 | 3251588.04 | 0 |  |  |  |  | 2469.9996 |  | EC16 | 100% | bar: Regulatory Outputs OMG-21
403677 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-12-20 | 2013-01-30 | 2014-04-09 | 2016-12-22 | 2017-06-30 | Highland | 1137229 | 1531475 | 448847.37 | 97927.88 | -81292.3185 | 0 | 0 | 1996957.9315 | 0 | 3134186.9315 | 1528439 |  |  |  |  | 91884 |  | DW23 | 100%
502622 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-03 | 2021-12-06 | 2022-02-17 | 2023-01-24 | 2023-04-26 | Highland | 0 | 0 | 20930.23 | 415.9 | 2390.44 | 11964.78 | 11918.41 | 47619.76 | 7953020.21 | 8000639.97 | 148885.7057 | [6 empty] | WG1 | 100%
402137 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS3 | 2011-07-15 | 2011-09-26 | 2011-09-26 | 2020-10-23 |  | Scottish Water Wide | 580324.41 | 27902.59 | 48273 | 25000 | 0 | 7834.02 | 7166 | 116175.61 | 0 | 696500.02 | 84954 | [6 empty] | DW5A | 100%
400064 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-11-11 | 2011-10-27 | 2011-10-31 | 2011-12-14 |  | South Ayrshire | 185587.15 | -251.23 | 0 | 0 | 0 | 0 | 0 | -251.23 | 0 | 185335.92 | 0 | [6 empty] | CM_WWNI | 100%
503324 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-04-05 | 2023-09-18 | 2024-01-08 | 2025-01-03 | 2025-04-07 | Perth and Kinross | 0 | 0 | 0 | 0 | 68716.44 | 0 | 19938.76 | 88655.2 | 53344.86 | 142000.06 | 148885.7057 | [6 empty] | SG1 | 100%
401004 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MS7 | 2010-04-21 | 2012-05-16 | 2012-06-04 | 2015-11-03 |  | Scottish Water Wide | 2795547 | -70396.2 | 142 | 0 | 0 | 0 | 0 | -70254.2 | 0 | 2725292.8 | 0 | [6 empty] | WSI | 25% | WSNI | 25% | WWI | 25% | WWNI | 25%
500080 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-11 | 2015-03-30 | 2015-03-30 | 2020-12-04 | 2020-12-04 | Scottish Water Wide | 0 | 804674 | 917811 | 637273 | 482630 | 431344 | 17276.69 | 3291008.69 | 0 | 3291008.69 | 0 | [6 empty] | CM_WSI | 100%
500081 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-11 | 2015-03-30 | 2015-03-30 | 2020-05-08 | 2020-05-08 | Scottish Water Wide | 293.4 | 1861412.45 | -881760.44 | 2438280.17 | 2051476.42 | 2009274.89 | 0 | 7478683.49 | 0 | 7478976.89 | 0 | [6 empty] | CM_WSI | 100%
500082 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-02-27 | 2015-03-25 | 2015-03-25 | 2020-05-08 | 2020-05-08 | Scottish Water Wide | 0 | 288095 | 265604 | 292195 | 352649 | 361400 | 24221.97 | 1584164.97 | 0 | 1584164.97 | 0 | [6 empty] | CM_WSI | 100%
500057 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-02-27 | 2016-05-18 | 2016-05-18 | 2017-04-21 | 2017-04-21 | East Lothian | 102.09 | 77263.91 | 1299998 | 57077 | -20858.9172 | 0 | 0 | 1413479.9928 | 0 | 1413582.0828 | 0 | [6 empty] | CM_WWI | 100%
403956 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | Scottish Water Wide | 40000 | 102058 | -2057.89 | 0 | 0 | 0 | 0 | 100000.11 | 0 | 140000.11 | 0 | [6 empty] | CM_WSI | 100%
503410 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW2 | 2019-05-02 | 2020-03-02 | 2020-04-27 | 2020-09-07 | 2020-09-14 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 289203.16 | 913705.16 | 1202908.32 | 2732.73 | 1205641.05 | 0 | [6 empty] | CM_WSNI | 19.8% | CM_WWNI | 80.2%
503409 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW2 | 2019-05-02 | 2020-03-02 | 2020-04-27 | 2020-09-07 | 2020-09-14 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 325735.54 | 1147905.89 | 1473641.43 | 3420.58 | 1477062.01 | 0 | [6 empty] | CM_WSNI | 40.21% | CM_WWNI | 59.79%
503397 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW2 | 2019-05-02 | 2020-03-02 | 2020-04-27 | 2020-06-05 | 2020-06-12 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 192850.72 | 591568.21 | 784418.93 | 1821.11 | 786240.04 | 0 | [6 empty] | CM_WSNI | 16.68% | CM_WWNI | 83.32%
502713 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2019-05-09 | 2020-03-02 | 2020-04-27 | 2020-06-05 | 2020-06-08 | Scottish Water Wide | 0 | 0 | 0 | 83683.2075 | 38138.4515 | 641707.24 | 2278409.51 | 3041938.409 | 7072.18 | 3049010.589 | 0 | [6 empty] | CM_WWNI | 25.71% | CM_WSNI | 74.29%
400513 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2010-04-07 | 2012-10-31 | 2012-11-26 | 2015-03-27 |  | South Ayrshire | 1450053 | 238767 | 121572.86 | -254.45 | 0 | 0 | 0 | 360085.41 | 0 | 1810138.41 | 0 | [6 empty] | CM_WWI | 15.08% | CM_WWNI | 84.92%
500985 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-11-23 | 2017-10-09 | 2017-10-09 | 2018-06-13 | 2018-06-13 | Scottish Water Wide | 0 | 72904 | 107252.98 | 229242.06 | 34261.5985 | 0 | 0 | 443660.6385 | 0 | 443660.6385 | 0 | [6 empty] | CM_M&G | 100%
503062 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWD | Reservoirs | GW1 | 2019-05-30 | 2020-09-07 | 2021-01-12 | 2021-08-24 | 2021-11-24 | Inverclyde | 0 | 0 | 0 | 26399.625 | 31074.585 | 84900.67 | 632068.2 | 774443.08 | 574240.87 | 1348683.95 | 1560467.3848 | [6 empty] | CS22 | 100%
501028 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-06-09 | 2016-06-09 | 2016-06-09 | 2016-04-25 | 2016-06-09 | Scottish Water Wide | 0 | 1182834.01 | 0 | 0 | 0 | 0 | 0 | 1182834.01 | 0 | 1182834.01 | 0 | [6 empty] | CM_WSI | 100%
502196 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-09-29 | 2016-09-29 | 2016-09-14 | 2016-09-12 | 2016-09-21 | Scottish Water Wide | 0 | 0 | 233973 | 0 | 0 | 0 | 0 | 233973 | 0 | 233973 | 0 | [6 empty] | CM_WWNI | 100%
403215 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-12-10 | 2013-04-17 | 2013-04-17 | 2015-04-15 |  | Scottish Water Wide | 385060.48 | -36294.85 | 0 | 0 | 0 | 0 | 0 | -36294.85 | 0 | 348765.63 | 0 | [6 empty] | CM_WSNI | 25% | CM_WWI | 25% | CM_WWNI | 50%
502734 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-06-28 | 2017-06-28 | 2017-11-16 | 2021-03-24 | 2021-03-24 | Scottish Water Wide | 0 | 0 | 0 | 81290.48 | 206419.52 | 107393.76 | 104896.23 | 499999.99 | 0 | 499999.99 | 0 | [6 empty] | CM_WSNI | 100%
500758 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2021-05-31 | 2021-05-31 | All East Unitary Authorities | 0 | 382061 | 951443.95 | 622113.05 | -248455.06 | 885718 | 0 | 2592880.94 | 0 | 2592880.94 | 0 | [6 empty] | CM_WWNI | 100%
500759 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2021-05-31 | 2021-05-31 | All North Unitary Authorities | 0 | 603435.72 | 620516.77 | 288612.51 | -340668.15 | 574318 | 0 | 1746214.85 | 0 | 1746214.85 | 0 | [6 empty] | CM_WWNI | 100%
500760 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2021-05-31 | 2021-05-31 | All South Unitary Authorities | 0 | 385748 | 571222.62 | 429903.38 | -228125.82 | 578863 | 0 | 1737611.18 | 0 | 1737611.18 | 0 | [6 empty] | CM_WWNI | 100%
500761 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2021-05-31 | 2021-05-31 | All West Unitary Authorities | 0 | 432958 | 584047 | 236119 | -255032.01 | 485817 | 0 | 1483908.99 | 0 | 1483908.99 | 0 | [6 empty] | CM_WWNI | 100%
500762 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2021-05-31 | 2021-05-31 | All East Unitary Authorities | 0 | 328566 | 401738 | 68496 | -107950.39 | 351241 | 0 | 1042090.61 | 0 | 1042090.61 | 0 | [6 empty] | CM_WSNI | 100%
500763 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2021-05-31 | 2021-05-31 | All North Unitary Authorities | 0 | 530551.94 | 493016.06 | 785582 | -298407.9 | 756751 | 0 | 2267493.1 | 0 | 2267493.1 | 0 | [6 empty] | CM_WSNI | 100%
500764 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2021-05-31 | 2021-05-31 | All South Unitary Authorities | 0 | 313597 | 163344 | 142547 | -29560.95 | 319207 | 0 | 909134.05 | 0 | 909134.05 | 0 | [6 empty] | CM_WSNI | 100%
500765 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2021-05-31 | 2021-05-31 | All West Unitary Authorities | 0 | 326421 | 405457 | 80643 | -104966.98 | 352990 | 0 | 1060544.02 | 0 | 1060544.02 | 0 | [6 empty] | CM_WSNI | 100%
500712 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | General |  | SWD | Wastewater non infrastructure | MS3 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2021-05-31 | 2021-05-31 | Scottish Water Wide | 0 | 1110530.45 | 184219.51 | -104912.96 | -327113.28 | 36000.02 | 0 | 898723.74 | 0 | 898723.74 | 0 | [6 empty] | CM_WSI | 50% | CM_WWNI | 50%
502393 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS6 | 2017-01-16 | 2017-08-31 | 2017-08-31 | 2018-02-15 | 2018-02-15 | All West Unitary Authorities | 0 | 0 | 14000 | 646525.92 | -28075.92 | 2617.08 | 2322.92 | 637390 | 0 | 637390 | 0 | [6 empty] | CM_M&G | 100%
503087 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS3 | 2018-07-13 | 2018-07-13 | 2018-07-16 | 2020-03-20 | 2020-03-23 | Scottish Water Wide | 0 | 0 | 0 | 0 | 1127831 | 1976213 | 423192 | 3527236 | 0 | 3527236 | 0 | [6 empty] | CM_M&G | 100%
400826 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-21 | 2011-05-13 | 2011-05-13 | 2015-03-06 |  | Scottish Water Wide | 383198.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383198.72 | 0 | [6 empty] | CM_WSI | 100%
400798 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-01 | 2010-08-02 | 2015-09-16 |  | Scottish Water Wide | 1662000 | -161083.01 | 0 | 0 | 0 | 0 | 0 | -161083.01 | 0 | 1500916.99 | 0 | [6 empty] | CM_WSI | 100%
404001 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | WINF | Supply Resilience | MS4 | 2015-12-08 | 2016-03-30 | 2016-03-30 | 2019-03-01 | 2020-06-01 | North Lanarkshire | 586 | 3238759 | 5164682 | 2114871.6275 | 278644.8425 | 53531 | 0 | 10850488.47 | 0 | 10851074.47 | 1817908.3275 | [6 empty] | SR15_EXC_EXC | 7% | CS16WR | 93% | bar: Regulatory Outputs OMG-07
400991 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2010-06-07 | 2015-05-19 | 2015-06-15 | 2017-10-03 | 2017-10-03 | North Ayrshire | 136802 | 800575.52 | 792545.33 | 138555.41 | 0 | 0 | 0 | 1731676.26 | 0 | 1868478.26 | 0 | [6 empty] | CM_WSI | 100%
503499 | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS2 | 2019-02-28 | 2019-02-28 | 2019-06-03 | 2021-07-27 | 2021-10-27 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 159546.09 | 322123.05 | 287866.78 | 769535.92 | 217300.2 | 986836.12 | 804969.5194 | [6 empty] | SG7 | 100%
503496 | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS2 | 2019-02-28 | 2019-02-28 | 2019-04-08 | 2021-04-20 | 2021-07-21 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 177220.45 | 459937.01 | 489626.72 | 1126784.18 | 179085.25 | 1305869.43 | 804969.5194 | [6 empty] | SG7 | 100%
503492 | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS2 | 2019-02-28 | 2019-02-28 | 2019-04-08 | 2021-06-01 | 2021-09-01 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 91876.246 | 74121.96 | 274777.43 | 440775.636 | 164652.61 | 605428.246 | 804969.5194 | [6 empty] | SG7 | 100%
503493 | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS2 | 2019-02-28 | 2019-02-28 | 2019-04-08 | 2021-04-20 | 2021-07-21 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 338918.62 | 673377.73 | 457770.5 | 1470066.85 | 203057.73 | 1673124.58 | 804969.5194 | [6 empty] | SG7 | 100%
502096 | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Water |  | SWMD | Developer Asset Adoption | MS7 | 2016-03-07 | 2016-03-07 | 2016-07-22 | 2017-02-01 | 2017-02-03 | Scottish Water Wide | 0 | 15766.36 | -15766.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG7 | 100%
502095 | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Water |  | SWMD | Developer Asset Adoption | MS7 | 2016-03-07 | 2016-03-07 | 2016-07-21 | 2017-02-01 | 2017-02-03 | Scottish Water Wide | 0 | 15766.36 | -15766.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG7 | 100%
502097 | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Water |  | SWMD | Developer Asset Adoption | MS7 | 2016-03-07 | 2016-03-07 | 2016-07-21 | 2017-02-01 | 2017-02-03 | Scottish Water Wide | 0 | 15766.36 | -15766.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | WG7 | 100%
503498 | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS2 | 2019-02-28 | 2019-02-28 | 2019-06-14 | 2021-08-09 | 2021-11-09 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 92198.78 | 407142.32 | 433115.64 | 932456.74 | 343796.08 | 1276252.82 | 804969.5194 | [6 empty] | SG7 | 100%
503497 | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS2 | 2019-02-27 | 2019-02-27 | 2019-04-08 | 2021-04-20 | 2021-07-21 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 21377.65 | 77032.44 | 96177.95 | 194588.04 | 35109.6 | 229697.64 | 804969.5194 | [6 empty] | SG7 | 100%
503495 | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS2 | 2019-02-28 | 2019-02-28 | 2019-04-08 | 2021-04-20 | 2021-07-21 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 268250.39 | 514007.04 | 313962.44 | 1096219.87 | 114834.51 | 1211054.38 | 804969.5194 | [6 empty] | SG7 | 100%
503494 | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Wastewater |  | SWMD | Developer Asset Adoption | MS2 | 2019-02-28 | 2019-02-28 | 2019-04-08 | 2021-06-01 | 2021-09-01 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 69000.22 | 110680.02 | 161198.85 | 340879.09 | 69120.97 | 410000.06 | 804969.5194 | [6 empty] | SG7 | 100%
502099 | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | General |  | SWMD | Developer Asset Adoption | MS3 | 2016-03-07 | 2016-03-07 | 2016-07-21 | 2020-04-17 | 2020-07-20 | Scottish Water Wide | 0 | 15766.36 | 224233.94 | 592013.7 | 1014722.81 | -493710.67 | -248.36 | 1352777.78 | 0 | 1352777.78 | 1203123.2602 | [6 empty] | SG7 | 49.19% | WG7 | 50.81%
502100 | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | Water |  | SWMD | Developer Asset Adoption | MS3 | 2016-03-07 | 2016-03-07 | 2016-07-21 | 2020-05-21 | 2020-08-21 | Scottish Water Wide | 0 | 15766.36 | 9999 | 348366.011 | 332527.629 | -224267.44 | -22.43 | 482369.13 | 0 | 482369.13 | 1203123.2602 | [6 empty] | SG7 | 8.423% | WG7 | 91.58%
502098 | Q&S4 | Supporting economic development | Infra Charge |  |  | General |  | SWD | Infra Charge | MS3 | 2016-03-07 | 2016-03-07 | 2016-07-21 | 2021-04-30 | 2021-05-03 | Scottish Water Wide | 0 | 15766.36 | 2575110.63 | 3188186.01 | 2766522 | 2880000 | 1074415 | 12500000 | 0 | 12500000 | 0 | [6 empty] | SG5 | 50% | WG5 | 50%
502226 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MS7 | 2016-05-16 | 2016-09-15 | 2016-10-21 | 2017-12-06 | 2017-12-06 | Scottish Water Wide | 0 | 0 | 17390.82 | 18132.4175 | -668.68 | 0 | 0 | 34854.5575 | 0 | 34854.5575 | 0 | [6 empty] | CM_M&G | 100%
404061 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2014-12-15 | 2014-12-15 | 2015-11-17 | 2017-10-26 |  | Scottish Water Wide | 45000 | 918973 | 1114535.87 | 369383.4 | 581.845 | 0 | 0 | 2403474.115 | 0 | 2448474.115 | 0 | [6 empty] | CM_WSNI | 100%
502738 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2019-02-28 | 2019-02-28 | 2019-02-28 | 2019-02-28 | 2019-02-28 | Scottish Water Wide | 0 | 0 | 0 | 1248066.07 | -22924.72 | 0 | 0 | 1225141.35 | 0 | 1225141.35 | 0 | [6 empty] | CM_WSI | 100%
012059 | Q&S2 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2008-04-01 | 2005-01-21 | 2005-02-21 | 2009-03-31 | 2019-01-03 | Scottish Water Wide | 566461.56 | 0 | -566461.56 | 0 | 0 | 0 | 0 | -566461.56 | 0 | 0 | 0 | [6 empty] | Wa6 | 50% | Ww3 | 50%
040020 | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383772.8133 | [6 empty] | RISK | 100%
403416 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-02-28 | 2015-03-06 | 2015-03-18 | 2015-03-18 | 2015-03-18 | Highland | 82209 | -48.77 | 0 | 0 | 0 | 0 | 0 | -48.77 | 0 | 82160.23 | 0 | [6 empty] | CM_WWI | 100%
403879 | Q&S3B | Completion | OMG180 |  |  | Water |  | WINF | OMG180 | MS4 | 2014-07-31 | 2015-03-30 | 2015-03-30 | 2018-09-01 | 2019-06-01 | Glasgow City | 260097 | 1893215 | 145530.24 | 233049.396 | 224862.744 | 0 | 0 | 2496657.38 | 0 | 2756754.38 | 1951306 | [6 empty] | DW5 | 100% | bar: Regulatory Outputs OMG-03
403091 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2013-02-28 | 2014-10-02 | 2014-10-02 | 2014-10-21 | 2014-10-02 | East Renfrewshire | 212280.37 | 171 | 0 | 0 | 0 | 0 | 0 | 171 | 0 | 212451.37 | 0 | [6 empty] | DW25 | 100%
402928 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-10-29 | 2015-09-22 | 2015-10-26 | 2016-03-01 | 2016-03-01 | Highland | 58578 | 910251 | 7935.72 | -1416.752 | 36.43 | 0 | 0 | 916806.398 | 0 | 975384.398 | 633026 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-48
402950 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2012-09-17 | 2013-06-12 | 2013-08-23 | 2014-03-13 | 2014-03-25 | Aberdeenshire | 128320 | 728.29 | 0 | 0 | 0 | 0 | 0 | 728.29 | 0 | 129048.29 | 500 | [6 empty] | WR2A | 100%
403504 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2013-09-03 | 2015-03-11 | 2015-07-20 | 2016-01-01 | 2016-03-01 | West Dunbartonshire | 22655.28 | 142541.09 | 24.85 | -157.78 | 1964.7872 | 0 | 0 | 144372.9472 | 0 | 167028.2272 | 62419 | [6 empty] | WR1 | 100% | bar: Regulatory Outputs OMG-48
402986 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS7 | 2012-09-28 | 2015-04-03 | 2015-04-07 | 2017-03-01 | 2017-06-01 | Glasgow City | 1958936 | 9030877 | 648905 | 830491.25 | -1026608.6299 | 0 | 0 | 9483664.6201 | 0 | 11442600.6201 | 8344790 | [6 empty] | CS11A | 30% | CS15 | 70% | bar: Regulatory Outputs OMG-48
403880 | Q&S3B | Completion | OMG180 |  |  | Water |  | WINF | OMG180 | MS4 | 2014-07-31 | 2015-06-15 | 2015-06-29 | 2019-03-01 | 2019-12-01 | Aberdeenshire | 124114 | 1230084 | 553928 | 638871 | 1880718 | 35900.88 | 0 | 4339501.88 | 0 | 4463615.88 | 2690241 | [6 empty] | DW5 | 100% | bar: Regulatory Outputs OMG-03
403881 | Q&S3B | Completion | OMG180 |  |  | Water |  | WINF | OMG180 | MS7 | 2014-07-31 | 2016-03-17 | 2016-03-17 | 2016-03-11 | 2016-03-17 | Fife | 57331.99 | -48197.19 | 896.71 | 0 | 0 | 0 | 0 | -47300.48 | 0 | 10031.51 | 0 | [6 empty] | DW5 | 100%
402388 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2011-03-31 | 2014-01-22 | 2014-01-22 | 2014-09-09 | 2014-09-09 | Glasgow City | 1843311 | 0 | 0 | 0 | -5200.16 | 0 | 0 | -5200.16 | 0 | 1838110.84 | 822 | [6 empty] | CS11A | 50% | CS15 | 50%
403090 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS3 | 2013-01-17 | 2016-09-26 | 2016-09-27 | 2020-05-06 | 2020-07-31 | East Renfrewshire | 122472.97 | 356178.93 | 5686690.1 | 4554416.429 | 2930634.671 | 0 | 0 | 13527920.13 | 0 | 13650393.1 | 5848412.9756 | [6 empty] | DW25D | 10.45% | DW25P | 10.45% | DW2 | 39.55% | DW3C | 39.55%
403503 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2013-09-03 | 2015-03-11 | 2015-07-20 | 2016-01-01 | 2016-03-01 | Dumfries and Galloway | 19652.02 | 38798.8 | 469.46 | 1107.63 | 621.1852 | 0 | 0 | 40997.0752 | 0 | 60649.0952 | 63545 | [6 empty] | WR1 | 100% | bar: Regulatory Outputs OMG-48
403502 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2013-09-03 | 2015-03-11 | 2015-10-30 | 2016-03-01 | 2016-03-01 | Argyll and Bute-Cowal & Bute | 18230.54 | 34967.09 | 322.03 | -299.95 | 1420.748 | 0 | 0 | 36409.918 | 0 | 54640.458 | 71246 | [6 empty] | WR1 | 100% | bar: Regulatory Outputs OMG-48
402738 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2012-11-05 | 2016-03-09 | 2016-01-06 | 2016-01-06 | 2016-01-06 | Renfrewshire | 1651786.2 | -17126.19 | 0 | 0 | 0 | 0 | 0 | -17126.19 | 0 | 1634660.01 | 0 |  |  |  |  | 115944 |  | DW3C | 0.16% | DW3H | 0.29% | DW23 | 99.55%
403087 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2013-01-17 | 2015-03-06 | 2014-12-12 | 2014-12-12 | 2014-12-12 | Na H-Eileanan an Iar | 226427.35 | -1 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 226426.35 | 0 | [6 empty] | DW25 | 100%
403093 | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | SWMD | Ring Fenced Environmental | MS7 | 2012-11-22 | 2018-03-30 | 2018-03-15 | 2018-03-30 | 2018-03-30 | Glasgow City | 19000 | 0 | 0 | -104.02 | 0 | 0 | 0 | -104.02 | 0 | 18895.98 | 0 | [6 empty] | EC01B | 100%
403094 | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | SWMD | Ring Fenced Environmental | MS7 | 2012-11-22 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | Glasgow City | 274379.16 | 1228415.84 | 1012257 | 361968.07 | 76256.0425 | 0 | 0 | 2678896.9525 | 0 | 2953276.1125 | 0 | [6 empty] | EC01B | 100%
403095 | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | SWMD | Ring Fenced Environmental | MS7 | 2012-11-22 | 2018-03-30 | 2018-03-15 | 2018-03-30 | 2018-03-30 | Glasgow City | 20000 | 0 | 0 | -472.63 | 0 | 0 | 0 | -472.63 | 0 | 19527.37 | 0 | [6 empty] | EC01B | 100%
403096 | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | SWMD | Ring Fenced Environmental | MS7 | 2012-11-22 | 2018-03-30 | 2018-03-15 | 2018-03-30 | 2018-03-30 | Glasgow City | 21191.36 | 284.64 | 286.64 | 3.57 | 0 | 0 | 0 | 574.85 | 0 | 21766.21 | 0 | [6 empty] | EC01B | 100%
403097 | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | WWINF | Ring Fenced Environmental | MS3 | 2012-11-22 | 2019-03-26 | 2019-03-25 | 2020-02-01 | 2020-09-01 | Glasgow City | 30800 | 2500 | 3100 | 1362 | 201766 | 1044516.92 | 30458.17 | 1283703.09 | 2857.18 | 1317360.27 | 0 |  |  |  |  | 6050.0003 |  | EC10B | 100% | bar: Regulatory Outputs OMG-19
403098 | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | WWINF | Ring Fenced Environmental | MS0 | 2012-11-22 | 2019-10-07 | 2020-01-13 | 2020-06-01 | 2020-09-01 | Glasgow City | 64143 | 12608 | 2689 | 3000 | 146091 | 1433246.54 | 723621.88 | 2321256.42 | 14600.62 | 2400000.04 | 0 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
403099 | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | WWINF | Ring Fenced Environmental | MS2 | 2012-11-22 | 2019-03-26 | 2019-07-15 | 2019-12-01 | 2020-09-01 | Glasgow City | 57230 | 11500 | 5660.49 | 6039.51 | 223967 | 861375.68 | 7941.31 | 1116483.99 | 1009.52 | 1174723.51 | 0 |  |  |  |  | 8289.9996 |  | EC10B | 100% | bar: Regulatory Outputs OMG-19
403100 | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | WWINF | Ring Fenced Environmental | MS2 | 2012-11-22 | 2019-03-13 | 2020-04-20 | 2020-05-01 | 2020-09-01 | Glasgow City | 24700 | 100 | 0 | 0 | 3677.97 | 12039.41 | 3726.8 | 19544.18 | 0 | 44244.18 | 0 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
403101 | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | WWINF | Ring Fenced Environmental | MS2 | 2012-11-21 | 2019-03-26 | 2019-08-01 | 2020-05-01 | 2020-09-01 | Glasgow City | 27110.26 | 3222.74 | 0 | 0 | 142492.9115 | 1175775.48 | 228137.38 | 1549628.5115 | 3528.02 | 1580266.7915 | 0 |  |  |  |  | 8289.9996 |  | EC10B | 100% | bar: Regulatory Outputs OMG-19
403102 | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | WWINF | Ring Fenced Environmental | MS0 | 2012-11-21 | 2019-06-17 | 2019-09-04 | 2020-06-01 | 2020-09-01 | Glasgow City | 31778 | 2550.56 | 1049.44 | 0 | 116369 | 866332.96 | 210756.5 | 1197058.46 | 3699.58 | 1232536.04 | 0 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
403103 | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | WWINF | Ring Fenced Environmental | MS2 | 2012-11-22 | 2019-03-13 | 2020-01-13 | 2020-04-01 | 2020-09-01 | Glasgow City | 22825 | 417 | -417 | 0 | 9523.95 | 65665.3 | 6198.21 | 81387.46 | 0 | 104212.46 | 0 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
403104 | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | WWINF | Ring Fenced Environmental | MS0 | 2012-11-22 | 2019-07-29 | 2019-10-16 | 2020-10-01 | 2021-02-01 | Glasgow City | 32865.7 | 49043.3 | 2587 | 769 | 95276 | 862232.24 | 704319.71 | 1714227.25 | 0 | 1747092.95 | 0 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
403105 | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | WWINF | Ring Fenced Environmental | MS3 | 2012-11-22 | 2018-03-28 | 2018-06-29 | 2019-08-01 | 2021-03-01 | Glasgow City | 48878 | 3622 | 63285.42 | 73581.58 | 126432.7 | 39119.3 | 2631.83 | 308672.83 | 0.16 | 357550.99 | 0 |  |  |  |  | 2379.9996 |  | EC10B | 100% | bar: Regulatory Outputs OMG-19
403106 | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | WWINF | Ring Fenced Environmental | MS3 | 2012-11-22 | 2018-06-07 | 2018-06-25 | 2020-12-01 | 2021-03-01 | Glasgow City | 45703 | 72797 | 151548 | 156613.12 | 525203.16 | 463032.6 | 0.12 | 1369194 | 328746.97 | 1743643.97 | 0 |  |  |  |  | 4119.9997 |  | EC10B | 100% | bar: Regulatory Outputs OMG-19
403107 | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | WWINF | Ring Fenced Environmental | MS3 | 2012-11-22 | 2018-10-24 | 2019-01-14 | 2019-06-01 | 2021-03-01 | Glasgow City | 44967 | -3967 | 7802 | 79655.12 | 482488.88 | 132015.99 | 0 | 697994.99 | 0 | 742961.99 | 0 |  |  |  |  | 6270 |  | EC10B | 100% | bar: Regulatory Outputs OMG-19
403108 | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | Wastewater |  | SWMD | Ring Fenced Environmental | MS7 | 2012-11-22 | 2018-03-30 | 2018-03-15 | 2018-03-30 | 2018-03-30 | Glasgow City | 70143 | 5365 | 278635 | -4797.92 | 0 | -0.39 | 0 | 279201.69 | 0 | 349344.69 | 0 | [6 empty] | EC10B | 100%
403109 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-11-22 | 2014-12-19 | 2015-04-13 | 2015-11-01 | 2016-01-01 | East Dunbartonshire | 248417 | 175195.06 | 450.55 | 469.39 | -82.37 | 0 | 0 | 176032.63 | 0 | 424449.63 | 209743 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
403110 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MS7 | 2012-11-22 | 2018-11-06 | 2018-12-17 | 2018-11-05 | 2018-12-17 | East Dunbartonshire | 44206 | 6400 | 17800 | 6000 | -5109.755 | 0 | 0 | 25090.245 | 0 | 69296.245 | 187891 | [6 empty] | EC10B | 100%
403111 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-11-22 | 2015-02-03 | 2015-02-03 | 2015-03-10 | 2015-03-10 | East Dunbartonshire | 90980 | -513.84 | 0 | 0 | 0 | 0 | 0 | -513.84 | 0 | 90466.16 | 0 | [6 empty] | EC10B | 100%
403112 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-11-22 | 2014-11-24 | 2015-03-09 | 2015-09-01 | 2015-10-01 | East Dunbartonshire | 190902 | 46254 | 1199.98 | -789.05 | 0 | 0 | 0 | 46664.93 | 0 | 237566.93 | 50233 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
403113 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-11-22 | 2016-03-22 | 2016-03-23 | 2016-03-01 | 2016-04-01 | East Dunbartonshire | 46255 | 253206 | 41648 | 1968 | -358.32 | 0 | 0 | 296463.68 | 0 | 342718.68 | 160020 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
403115 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MS7 | 2012-11-22 | 2018-11-05 | 2018-12-17 | 2018-11-05 | 2018-12-17 | East Dunbartonshire | 51572 | -2156 | 3000.36 | 998.71 | -238.839 | 0 | 0 | 1604.231 | 0 | 53176.231 | 605497.0001 | [6 empty] | EC10B | 100%
403116 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MS0 | 2012-11-22 | 2019-12-02 | 2020-02-28 | 2020-09-30 | 2020-12-31 | East Dunbartonshire | 37826 | 6656 | -3020 | 6000 | 5000 | 229870.34 | 61.68 | 244568.02 | 950 | 283344.02 | 21754 | [6 empty] | EC10B | 100%
403117 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-11-22 | 2015-02-03 | 2015-02-03 | 2015-03-10 | 2015-03-10 | East Dunbartonshire | 40092 | -12626.27 | 0 | 0 | 0 | 0 | 0 | -12626.27 | 0 | 27465.73 | 0 | [6 empty] | EC10B | 100%
403118 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2012-12-07 | 2016-12-22 | 2017-01-23 | 2017-09-01 | 2018-01-01 | East Dunbartonshire | 56905.19 | 18182.01 | 449506.8 | 262219 | 4154.9215 | 40.03 | 0 | 734102.7615 | 0 | 791007.9515 | 272469.9999 | [6 empty] | CM_WWNI | 31.5% | EC10B | 68.5% | bar: Regulatory Outputs OMG-19
403119 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-11-22 | 2015-02-16 | 2015-03-18 | 2015-03-20 | 2015-03-25 | West Dunbartonshire | 59014 | -1153 | 520.94 | -620.4 | 0 | 0 | 0 | -1252.46 | 0 | 57761.54 | 5419 | [6 empty] | EC10B | 100%
403121 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-11-22 | 2014-11-28 | 2015-01-24 | 2015-02-26 | 2015-03-11 | West Dunbartonshire | 56644.83 | 8890.17 | 545.87 | -1606.72 | 0 | 0 | 0 | 7829.32 | 0 | 64474.15 | 3372.0001 |  |  |  |  | 12831.5346 |  | EC10B | 100%
403356 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS5 | 2013-03-04 | 2017-06-27 | 2017-09-18 | 2018-12-01 | 2019-03-01 | South Lanarkshire | 29905 | -4444.91 | 88248.91 | 1765050 | 373019 | 0 | 0 | 2221873 | 0 | 2251778 | 112386 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
403086 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2013-02-20 | 2014-10-24 | 2014-10-24 | 2014-10-24 | 2014-10-24 | East Renfrewshire | 231779.18 | 20994.25 | -20108.3 | 0 | 0 | 0 | 0 | 885.95 | 0 | 232665.13 | 0 | [6 empty] | DW25 | 100%
403957 | Q&S3B | Completion | OMG180 |  |  | Water |  | WINF | OMG180 | MS7 | 2014-11-24 | 2016-05-30 | 2016-05-30 | 2016-06-02 | 2016-06-23 | East Renfrewshire | 53192.17 | -42599.93 | -1340.6 | 0 | 0 | 0 | 0 | -43940.53 | 0 | 9251.64 | 0 | [6 empty] | DW23 | 50% | DW3C | 50%
402936 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2012-12-07 | 2013-05-31 | 2013-06-28 | 2014-03-14 | 2014-03-14 | Scottish Water Wide | 773631 | 0 | -176.56 | 0 | 0 | 0 | 0 | -176.56 | 0 | 773454.44 | 6002 | [6 empty] | DW5A | 100%
403501 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2013-09-03 | 2015-11-17 | 2015-11-17 | 2016-02-01 | 2016-02-01 | Argyll and Bute-North Argyll | 22215.7 | 97264.8 | 5158.7 | -1180.1 | -1348.923 | 0 | 0 | 99894.477 | 0 | 122110.177 | 76986.0001 | [6 empty] | WR1 | 100% | bar: Regulatory Outputs OMG-48
402929 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-09-18 | 2013-09-23 | 2013-11-06 | 2014-08-18 | 2014-11-14 | Argyll and Bute-North Argyll | 233415 | 585 | 484.7 | 0 | 0 | 0 | 0 | 1069.7 | 0 | 234484.7 | 0 | [6 empty] | EC01A | 100%
403088 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2013-01-17 | 2015-03-06 | 2014-12-12 | 2014-12-12 | 2014-12-12 | Highland | 301686.7 | 0 | 94.9 | 0 | 0 | 0 | 0 | 94.9 | 0 | 301781.6 | 0 | [6 empty] | DW25 | 100%
403222 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-01-14 | 2015-02-19 | 2015-03-09 | 2015-12-01 | 2016-03-01 | Aberdeenshire | 1171213.1 | 1741332.23 | -46950.64 | 562.67 | -69349.2724 | 0 | 0 | 1625594.9876 | 0 | 2796808.0876 | 439668.534 | [6 empty] | EC10A | 40.91% | CM_WWNI | 59.09% | bar: Regulatory Outputs OMG-48
501678 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | GW2 | 2019-07-01 | 2019-10-17 | 2019-10-17 | 2020-04-28 | 2018-01-08 | Scottish Water Wide | 0 | 0 | 22209.44 | 8568.8 | 6450 | 55656.12 | 40264.62 | 133148.98 | 0 | 133148.98 | 0 | [6 empty] | CM_M&G | 100%
045803 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2011-03-21 | 2011-07-29 | 2012-02-06 | 2012-02-13 | South Lanarkshire | 700959.78 | 7562.04 | -12097.51 | 0 | 0 | 0 | 0 | -4535.47 | 0 | 696424.31 | 0 | [6 empty] | WQ01B | 4.308% | WQ01C | 95.69%
403480 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2013-07-11 | 2014-07-30 | 2014-07-30 | 2014-09-03 | 2014-09-03 | Glasgow City | 63714.91 | 4774.57 | 0.01 | 0 | 0 | 0 | 0 | 4774.58 | 0 | 68489.49 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
502937 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-11-30 | 2017-11-30 | 2017-12-20 | 2018-01-09 | 2018-01-09 | Glasgow City | 0 | 0 | 0 | 522681.71 | 0 | 0 | 0 | 522681.71 | 0 | 522681.71 | 0 | [6 empty] | CM_WWNI | 100%
502285 | Q&S4 | Reducing long term cost of service | Research and Innovation |  |  | Wastewater |  | SWD | Research and Innovation | MS3 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2021-01-25 | 2021-01-26 | Scottish Water Wide | 0 | 0 | 11649.09 | 34439.6375 | 209916.409 | 0 | 0 | 256005.1365 | 0 | 256005.1365 | 1706412.2863 | [6 empty] | I2S_WWNI | 100%
500638 | Q&S4 | Improving drinking water availability and resilience of service | Leakage |  |  | Water |  | SWD | Leakage | MS3 | 2015-05-18 | 2015-05-18 | 2015-06-01 | 2021-05-07 | 2021-05-07 | Scottish Water Wide | 0 | 49065.42 | 86310.56 | 88434 | 205451.91 | 150000 | 170738.11 | 750000 | 0 | 750000 | 0 | [6 empty] | CS14 | 100%
500640 | Q&S4 | Reducing long term cost of service | Research and Innovation |  |  | Wastewater |  | SWD | Research and Innovation | MS3 | 2015-05-20 | 2015-05-20 | 2015-06-01 | 2021-02-01 | 2021-02-01 | Scottish Water Wide | 0 | 229898.78 | 381408.84 | 319675.6925 | 359332.6875 | 720000 | 989684 | 3000000 | 0 | 3000000 | 1706412.2863 | [6 empty] | I2S_WWNI | 100% | [18 empty] | Regulatory Outputs OMG-46: 4
500641 | Q&S4 | Reducing long term cost of service | Research and Innovation |  |  | Water |  | SWD | Research and Innovation | MS7 | 2015-05-20 | 2015-05-20 | 2015-10-01 | 2018-09-03 | 2018-09-03 | Scottish Water Wide | 0 | 93194 | 481705 | 195101 | 0 | 0 | 0 | 770000 | 0 | 770000 | 0 | [6 empty] | I2S_WNI | 100%
500639 | Q&S4 | Reducing long term cost of service | Research and Innovation |  |  | Water |  | SWD | Research and Innovation | MS3 | 2015-05-20 | 2015-05-20 | 2015-06-01 | 2021-03-01 | 2021-03-01 | Scottish Water Wide | 0 | 543412 | 503258 | 238060 | -59730 | 540000 | 465000 | 2230000 | 0 | 2230000 | 1706412.2863 |  |  |  |  | 110000 |  | I2S_WNI | 100% | bar: Regulatory Outputs OMG-46
502623 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2022-05-03 | 2025-12-03 | 2026-02-06 | 2027-01-15 | 2027-04-19 | Highland | 0 | 0 | 20930.23 | 374.31 | 915.54 | 8981.46 | 8946.65 | 40148.19 | 9851.75 | 49999.94 | 148885.7057 | [6 empty] | WG1 | 100%
046845 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2011-03-29 | 2011-09-08 | 2013-06-28 | 2013-09-30 | Highland | 2748896.12 | -24865.75 | 0 | 0 | 0 | 0 | 0 | -24865.75 | 0 | 2724030.37 | 3872 | [6 empty] | DW23 | 100%
402493 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-01-13 | 2012-08-18 | 2012-10-02 | 2016-03-22 |  | Aberdeenshire | 203810 | -8810 | 78.13 | 0 | 0 | 0 | 0 | -8731.87 | 0 | 195078.13 | 0 | [6 empty] | CM_M&G | 100%
403408 | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWMD | Renewable power | MS7 | 2013-03-01 | 2016-07-25 | 2016-07-25 | 2016-04-19 | 2016-07-25 | City of Edinburgh | 151966 | 34348 | 3024.69 | 0 | 0 | 0 | 0 | 37372.69 | 0 | 189338.69 | 764721.6298 | [6 empty] | CC1W | 100%
401532 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-02-03 | 2012-06-28 | 2012-07-24 | 2014-06-30 | 2014-08-29 | Scottish Water Wide | 810267 | 1571.09 | 3113.76 | 0 | 0 | 0 | 0 | 4684.85 | 0 | 814951.85 | 15 | [6 empty] | DW24 | 100%
500095 | Q&S4 | Climate Change | Climate Change |  |  | Water |  | SWMD | Climate Change | MS7 | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-16 | 2016-12-22 | Scottish Water Wide | 0 | 16453.5 | 171883.5 | 85010.24 | 57019.464 | 0 | 0 | 330366.704 | 0 | 330366.704 | 69610.8618 | [6 empty] | CC4W | 100%
500036 | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWD | SEMD | MS7 | 2015-02-17 | 2015-06-23 | 2015-06-23 | 2016-07-01 | 2016-07-01 | Scottish Water Wide | 0 | 302831.58 | 213427.42 | 0 | 3263.01 | 0 | 0 | 519522.01 | 0 | 519522.01 | 741411.6518 | [6 empty] | DW9G | 100% | [18 empty] | Regulatory Outputs OMG-47: 6
046378 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-05 | 2014-03-10 | 2014-03-03 | 2014-03-06 | 2014-03-06 | Stirling | 64706.15 | 422 | 0 | 0 | 0 | 0 | 0 | 422 | 0 | 65128.15 | 0 | [6 empty] | DW10 | 100%
046377 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-05 | 2014-02-24 | 2014-03-03 | 2014-03-06 | 2014-03-06 | Stirling | 49719.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49719.49 | 0 | [6 empty] | DW10 | 100%
046376 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-05 | 2011-06-22 | 2011-11-01 | 2013-03-22 | 2013-09-25 | Stirling | 2829666.4 | 6549.32 | 5545.52 | 0 | 0 | 0 | 0 | 12094.84 | 0 | 2841761.24 | 0 | [6 empty] | DW10 | 100%
046379 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-05 | 2011-03-31 | 2011-03-31 | 2012-02-24 | 2012-03-14 | Scottish Borders | 11672.67 | 0.57 | 0 | 0 | 0 | 0 | 0 | 0.57 | 0 | 11673.24 | 0 | [6 empty] | DW10 | 100%
046380 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-05 | 2011-06-22 | 2011-12-19 | 2013-09-30 | 2013-12-10 | Stirling | 2791910.25 | 8317.31 | 19810.69 | 0 | 0 | 0 | 0 | 28128 | 0 | 2820038.25 | 6081 | [6 empty] | DW10 | 100%
503198 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2018-11-30 | 2019-09-30 | 2019-12-10 | 2021-01-01 | 2022-01-01 | Scottish Borders | 0 | 0 | 0 | 0 | 247014.19 | 836456.58 | 696220.36 | 1779691.13 | 598139.79 | 2377830.92 | 0 | [6 empty] | DW5MR | 32% | DW5FS | 68% | [16 empty] | Regulatory Outputs OMG-06: 313.829
501396 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-04-05 | 2022-06-30 | 2022-11-03 | 2024-01-31 | 2024-05-02 | Scottish Borders | 0 | 0 | 45032.93 | 10031.46 | 1158.06 | 0 | 0 | 56222.45 | 3662507.55 | 3718730 | 0 | [6 empty] | CM_WSNI | 100%
502359 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-04-01 | 2022-12-21 | 2023-04-25 | 2024-07-08 | 2024-10-08 | Scottish Borders | 0 | 0 | 42934.57 | 6152.1875 | 6102.4845 | 0 | 44810.75 | 99999.992 | 4209578.95 | 4309578.942 | 0 | [6 empty] | CM_WSNI | 100%
500984 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-12-09 | 2016-02-22 | 2016-03-29 | 2016-10-27 | 2017-01-12 | Highland | 0 | 46323 | 123651.57 | 3825.93 | 7865.9 | 0 | 0 | 181666.4 | 0 | 181666.4 | 0 | [6 empty] | CM_WSI | 100%
500982 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2016-09-05 | 2018-02-21 | 2018-03-19 | 2019-03-22 | 2019-03-22 | Highland | 0 | 0 | 6310.9 | 141719.6 | 540624.88 | 1869.38 | 747.75 | 691272.51 | 727.39 | 691999.9 | 0 | [6 empty] | CM_WSI | 100%
500710 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS3 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2021-10-26 | 2021-10-26 | Scottish Water Wide | 0 | 33890 | 137390.05 | 9313 | 401480.464 | 88937.91 | 88593.18 | 759604.604 | 66875.77 | 826480.374 | 809440.5607 | [6 empty] | DW1A | 100%
502975 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2021-06-02 | 2022-04-15 | 2022-07-08 | 2023-04-11 | 2023-07-12 | North Lanarkshire | 0 | 0 | 0 | 27146.695 | 51487.2665 | 0 | 0 | 78633.9615 | 3472336.85 | 3550970.8115 | 0 | [6 empty] | CM_WWI | 100%
403433 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-04-16 | 2014-09-15 | 2014-09-22 | 2015-03-30 | 2015-03-30 | City of Edinburgh | 655709 | 32421 | 0 | -26131.25 | 0 | 0 | 0 | 6289.75 | 0 | 661998.75 | 229318.7788 |  |  |  |  | 5400 |  | CS11 | 100%
402630 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS7 | 2012-04-17 | 2013-02-20 | 2013-02-20 | 2016-02-10 | 2016-02-10 | Scottish Water Wide | 360247 | 31652.8 | 0 | 0 | 0 | 0 | 0 | 31652.8 | 0 | 391899.8 | 0 | [6 empty] | CM_M&G | 100%
000059 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 |  | 2005-01-19 | 2001-10-01 | 2003-03-31 | 2009-02-28 | Scottish Water Wide | 782069.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 782069.85 | 0 | [6 empty] | DW3 | 33% | Wa13 | 33% | Wa1 | 34%
502391 | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWD | Renewable power | MSU | 2021-04-15 | 2022-03-14 | 2022-05-20 | 2021-04-15 | 2021-04-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 208877.28 | 2308877.25 | 2517754.53 | 0 | 2517754.53 | 2294164.8894 | [6 empty] | I2S_WI | 25% | I2S_WWNI | 25% | I2S_WNI | 50%
403885 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-06-01 | 2014-06-01 | 2014-06-01 | 2014-06-01 | 2015-01-29 | Scottish Water Wide | 3501204.72 | -4.72 | -5505.38 | 0 | 0 | 0 | 0 | -5510.1 | 0 | 3495694.62 | 0 | [6 empty] | CC1W | 100%
403823 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-08-08 | 2014-08-08 | 2014-08-20 | 2014-12-18 | 2015-01-23 | Scottish Water Wide | 1048449 | -42384 | 276.34 | 0 | 0 | 0 | 0 | -42107.66 | 0 | 1006341.34 | 0 | [6 empty] | CC1W | 100%
403824 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-08-04 | 2014-08-04 | 2015-06-09 | 2015-06-10 | 2015-06-10 | Scottish Water Wide | 317483 | -20562.26 | 0 | 0 | 0 | 0 | 0 | -20562.26 | 0 | 296920.74 | 140792 | [6 empty] | CC1W | 100%
403825 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-08-08 | 2014-08-08 | 2014-11-11 | 2015-03-31 | 2015-03-31 | Scottish Water Wide | 1013163 | 15133 | 4704 | 3778.49 | 5248.7895 | 0 | 0 | 28864.2795 | 0 | 1042027.2795 | 63171 | [6 empty] | CC1W | 100%
403826 | Q&S4 | Reducing long term cost of service | Renewable power |  |  | Water |  | SWMD | Renewable power | MS7 | 2014-07-21 | 2014-07-21 | 2014-10-27 | 2015-03-01 | 2015-03-01 | Scottish Water Wide | 1458555 | -3683.63 | 107293.63 | 26898.919 | 0.001 | 0 | 0 | 130508.92 | 0 | 1589063.92 | 764721.6298 | [6 empty] | CC1W | 100% | [18 empty] | Regulatory Outputs OMG-43: 0.52
403827 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS5 | 2014-08-08 | 2014-08-08 | 2014-11-28 | 2015-03-26 | 2015-03-26 | Scottish Water Wide | 927766 | 299321 | 78583 | 117262.53 | 180283.01 | 17872.24 | 181.76 | 693503.54 | 0 | 1621269.54 | 193814 | [6 empty] | CC1W | 100%
403828 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-08-08 | 2014-08-08 | 2014-08-20 | 2015-01-23 | 2015-01-29 | Scottish Water Wide | 1032758 | 74094 | 77012.04 | 3946.89 | 0 | 0 | 0 | 155052.93 | 0 | 1187810.93 | 2433.0001 | [6 empty] | CC1W | 100%
403877 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-08-08 | 2014-08-08 | 2014-08-20 | 2014-11-07 | 2014-11-07 | Scottish Water Wide | 313666 | -5631 | -999.59 | 0 | 0 | 0 | 0 | -6630.59 | 0 | 307035.41 | 0 | [6 empty] | CC1W | 100%
403876 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-08-08 | 2014-08-08 | 2014-08-20 | 2014-11-11 | 2014-11-11 | Scottish Water Wide | 292000 | -4906 | -813.67 | 0 | 0 | 0 | 0 | -5719.67 | 0 | 286280.33 | 0 | [6 empty] | CC1W | 100%
403875 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-07-31 | 2014-07-31 | 2014-08-20 | 2014-11-11 | 2014-11-11 | Scottish Water Wide | 253767 | -3349 | -813.77 | 0 | 0 | 0 | 0 | -4162.77 | 0 | 249604.23 | 0 | [6 empty] | CC1W | 100%
403874 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-07-31 | 2014-07-31 | 2014-08-20 | 2014-11-06 | 2014-11-06 | Scottish Water Wide | 315910 | -5838 | -813.5 | 0 | 0 | 0 | 0 | -6651.5 | 0 | 309258.5 | 0 | [6 empty] | CC1W | 100%
403873 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-07-31 | 2014-07-31 | 2014-08-20 | 2014-11-06 | 2014-11-06 | Scottish Water Wide | 313234 | -5592 | -813.38 | 0 | 0 | 0 | 0 | -6405.38 | 0 | 306828.62 | 0 | [6 empty] | CC1W | 100%
403878 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2014-07-30 | 2014-07-30 | 2014-08-20 | 2014-11-06 | 2014-11-06 | Scottish Water Wide | 361340 | -6829 | -813.38 | 0 | 0 | 0 | 0 | -7642.38 | 0 | 353697.62 | 0 | [6 empty] | CC1W | 100%
403577 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-08-08 | 2015-11-09 | 2015-11-10 | 2015-11-10 | 2015-11-10 | Scottish Water Wide | 851727 | -85397.54 | 3811.85 | -4701.2 | 0 | 0 | 0 | -86286.89 | 0 | 765440.11 | 0 | [6 empty] | CM_M&G | 100%
500929 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2017-11-20 | 2017-11-20 | 2017-10-19 | 2017-10-19 | East Renfrewshire | 0 | 5000 | 2000 | -4577.97 | 0 | 0 | 0 | 2422.03 | 0 | 2422.03 | 144841.4737 | [6 empty] | CS15A | 100%
500983 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-12-01 | 2015-12-01 | 2016-03-08 | 2017-03-06 | 2017-03-06 | Scottish Water Wide | 0 | 41920 | 215595.71 | -30678.36 | 2145.46 | 0 | 0 | 228982.81 | 0 | 228982.81 | 0 | [6 empty] | CM_WSI | 100%
403264 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2013-02-06 | 2015-12-16 | 2016-01-29 | 2017-06-30 |  | All East Unitary Authorities | 219801 | 1179233 | 1698270.39 | 317291.56 | 489 | 2810.99 | 0 | 3198094.94 | 0 | 3417895.94 | 0 | [6 empty] | CM_WWNI | 100%
503478 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2021-04-01 | 2022-01-31 | 2022-05-02 | 2022-11-25 | 2023-02-27 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 8416.32 | 8383.7 | 16800.02 | 333200.01 | 350000.03 | 0 | [6 empty] | CM_WSI | 100%
400802 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-05-05 | 2010-05-05 | 2010-05-01 | 2016-09-20 |  | Scottish Water Wide | 111903.4 | 26010.6 | 2679.79 | 0 | 0 | 0 | 0 | 28690.39 | 0 | 140593.79 | 0 | [6 empty] | CM_WWI | 100%
500945 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWD | Wastewater infrastructure | MS7 | 2016-01-26 | 2016-01-26 | 2016-01-26 | 2016-09-01 | 2016-09-28 | Scottish Water Wide | 0 | 155735.23 | 0 | 92.43 | 0 | 0 | 0 | 155827.66 | 0 | 155827.66 | 0 | [6 empty] | CM_M&G | 100%
401976 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2011-03-24 | 2012-05-23 | 2012-07-02 | 2018-05-11 | 2018-05-11 | Aberdeenshire | 1193302.89 | 76197.11 | -73765.76 | 22.32 | 61.22 | 0 | 0 | 2514.89 | 0 | 1195817.78 | 0 | [6 empty] | WG5 | 100%
503267 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-04-01 | 2021-04-01 | 2021-07-28 | 2022-03-10 | 2022-06-10 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299999.97 | 299999.97 | 0 | [6 empty] | CM_WWNI | 100%
500787 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-08-13 | 2015-08-13 | 2018-03-22 | 2018-03-14 | 2018-03-05 | Scottish Water Wide | 0 | 114436.17 | 596239.54 | 39974.53 | 0 | 0 | 0 | 750650.24 | 0 | 750650.24 | 0 | [6 empty] | CM_WSI | 100%
402741 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-07 | 2012-09-20 | 2012-11-12 | 2014-02-12 |  | Scottish Borders | 222737.32 | 155.83 | 0 | 0 | 0 | 0 | 0 | 155.83 | 0 | 222893.15 | 0 | [6 empty] | CM_WSI | 100%
402663 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-05-29 | 2013-02-11 | 2013-05-31 | 2014-08-27 |  | Renfrewshire | 298797.82 | 1156.05 | -5832.19 | 0 | 0 | 0 | 0 | -4676.14 | 0 | 294121.68 | 0 | [6 empty] | CM_WSI | 100%
402720 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-05-29 | 2013-02-07 | 2013-07-15 | 2014-03-06 |  | South Ayrshire | 20217.05 | 1044.63 | 0 | 0 | 0 | 0 | 0 | 1044.63 | 0 | 21261.68 | 0 | [6 empty] | CM_WSI | 100%
402721 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-15 | 2013-02-07 | 2013-05-31 | 2014-09-16 |  | North Ayrshire | 111225.75 | -5038.04 | -93.75 | 0 | 0 | 0 | 0 | -5131.79 | 0 | 106093.96 | 0 | [6 empty] | CM_WSI | 100%
402664 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-05-01 | 2012-08-29 | 2013-02-25 | 2014-03-13 |  | Stirling | 231042.77 | 2910.78 | 0 | 0 | 0 | 0 | 0 | 2910.78 | 0 | 233953.55 | 0 | [6 empty] | CM_WSI | 100%
402665 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-05-01 | 2012-09-05 | 2012-11-12 | 2014-03-19 |  | Dumfries and Galloway | 316739.68 | 1134.23 | 0 | 0 | 0 | 0 | 0 | 1134.23 | 0 | 317873.91 | 0 | [6 empty] | CM_WSI | 100%
402742 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-15 | 2012-09-05 | 2012-11-19 | 2013-12-22 |  | Scottish Borders | 203750.67 | 362.12 | 0 | 0 | 0 | 0 | 0 | 362.12 | 0 | 204112.79 | 0 | [6 empty] | CM_WSI | 100%
402666 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-05-01 | 2012-11-29 | 2013-02-25 | 2014-08-04 |  | Midlothian | 187330.67 | 890.97 | -871.01 | 0 | 0 | 0 | 0 | 19.96 | 0 | 187350.63 | 0 | [6 empty] | CM_WSI | 100%
402743 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-07 | 2012-08-23 | 2012-11-05 | 2014-01-15 |  | Perth and Kinross | 180562.13 | 171.21 | 0 | 0 | 0 | 0 | 0 | 171.21 | 0 | 180733.34 | 0 | [6 empty] | CM_WSI | 100%
402722 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-20 | 2013-02-07 | 2013-06-03 | 2014-02-27 | 2014-02-27 | Inverclyde | 231365.74 | 151.55 | 0 | 0 | 0 | 0 | 0 | 151.55 | 0 | 231517.29 | 0 | [6 empty] | CM_WSI | 100%
402723 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-15 | 2012-11-14 | 2013-02-18 | 2014-03-31 | 2014-03-31 | Inverclyde | 534455.75 | 13036.82 | 341.9 | 0 | 0 | 0 | 0 | 13378.72 | 0 | 547834.47 | 0 | [6 empty] | CM_WSI | 100%
402744 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-07 | 2012-08-23 | 2012-11-05 | 2013-12-22 |  | Scottish Borders | 128042.11 | 764.17 | 0 | 0 | 0 | 0 | 0 | 764.17 | 0 | 128806.28 | 0 | [6 empty] | CM_WSI | 100%
402667 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-05-01 | 2012-09-20 | 2012-11-19 | 2013-09-23 |  | East Lothian | 177924.25 | 893.45 | 0 | 0 | 0 | 0 | 0 | 893.45 | 0 | 178817.7 | 0 | [6 empty] | CM_WSI | 100%
402745 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-07 | 2012-09-20 | 2013-02-26 | 2013-09-23 |  | Midlothian | 123819.4 | -876.74 | 0 | 0 | 0 | 0 | 0 | -876.74 | 0 | 122942.66 | 0 | [6 empty] | CM_WSI | 100%
402719 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-06 | 2013-05-03 | 2013-05-22 | 2013-05-22 |  | Scottish Water Wide | 7274.52 | -265.62 | 0 | 0 | 0 | 0 | 0 | -265.62 | 0 | 7008.9 | 0 | [6 empty] | CM_WSI | 100%
046337 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-04-01 | 2011-11-14 | 2011-12-01 | 2011-12-06 | 2011-12-06 | Scottish Water Wide | 115498.84 | -132.35 | 0 | 0 | 0 | 0 | 0 | -132.35 | 0 | 115366.49 | 0 | [6 empty] | CM_WSI | 100%
403616 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2013-10-22 | 2013-10-22 | 2013-10-22 | 2015-06-10 |  | Scottish Water Wide | 27752.94 | 2578.89 | 0 | 0 | 0 | 0 | 0 | 2578.89 | 0 | 30331.83 | 0 | [6 empty] | CM_WSI | 100%
500741 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWD | Reservoirs | GW2 | 2019-04-01 | 2019-06-24 | 2019-07-15 | 2020-02-06 | 2020-02-07 | Scottish Water Wide | 0 | 4186.05 | 21264.35 | -4329.42 | 13.4 | 123651.67 | 120909 | 265695.05 | 574301 | 839996.05 | 0 | [6 empty] | WR6 | 100%
500595 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | GW2 | 2019-04-01 | 2019-05-27 | 2019-05-27 | 2019-05-27 | 2019-05-27 | Scottish Water Wide | 0 | 26500.27 | 17550.62 | 105945.11 | 78280.75 | 1097719.25 | 0 | 1325996 | 0 | 1325996 | 639260.3798 | [6 empty] | CS16WR | 100%
503111 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MSU | 2020-03-31 | 2021-02-15 | 2021-05-06 | 2022-06-06 | 2022-09-06 | Scottish Water Wide | 0 | 0 | 0 | 581085.645 | 131026.215 | 970226.81 | 907372.49 | 2589711.16 | 1163288.88 | 3753000.04 | 2689627.8112 | [6 empty] | CS16WRID | 100%
503347 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS1 | 2018-08-20 | 2019-07-01 | 2019-07-01 | 2019-10-31 | 2019-10-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 49869.33 | 450115.93 | 0 | 499985.26 | 0 | 499985.26 | 0 | [6 empty] | CM_M&G | 100%
503363 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2022-10-17 | 2027-12-20 | 2028-04-17 | 2029-04-12 | 2029-07-13 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 20153.02 | 27477.44 | 7995.63 | 55626.09 | 4964526.79 | 5020152.88 | 148885.7057 | [6 empty] | WG1 | 100%
500810 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2016-10-19 | 2017-08-10 | 2017-09-22 | 2018-06-01 | 2018-12-01 | Aberdeenshire | 0 | 569.73 | 510.66 | 7389.96 | 13900.97 | 749.99 | 0 | 23121.31 | 0 | 23121.31 | 2009.1625 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 2.87
502420 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW2 | 2021-05-13 | 2022-09-20 | 2023-01-10 | 2023-12-29 | 2024-04-01 | Aberdeenshire | 0 | 0 | 20496.52 | 30.81 | 129.125 | 0 | 0 | 20656.455 | 27343.54 | 47999.995 | 0 | [6 empty] | CM_WWNI | 100%
403255 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-01-18 | 2016-10-31 | 2016-10-31 | 2016-11-02 |  | Aberdeenshire | 21759.04 | 6219.99 | 4517.13 | 0 | 0 | 0 | 0 | 10737.12 | 0 | 32496.16 | 0 | [6 empty] | CM_WWNI | 100%
503273 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-10 | 2023-06-26 | 2023-10-27 | 2024-10-24 | 2025-01-24 | South Lanarkshire | 0 | 0 | 0 | 0 | 74437.32 | 15871.87 | 27561.21 | 117870.4 | 24129.38 | 141999.78 | 148885.7057 | [6 empty] | SG1 | 100%
501511 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2016-04-14 | 2020-11-02 | 2020-11-23 | 2022-02-14 | 2022-05-17 | South Lanarkshire | 0 | 0 | 140883.69 | 273681.96 | 39816.74 | 0 | 560460 | 1014842.39 | 2680341.64 | 3695184.03 | 0 | [6 empty] | CM_WWNI | 100%
500246 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS1 | 2017-07-28 | 2019-09-14 | 2020-02-07 | 2021-03-01 | 2021-06-01 | Dumfries and Galloway | 0 | 15732.21 | 64763 | 206670.72 | 58425.93 | 155028.86 | 269713.81 | 770334.53 | 109144.57 | 879479.1 | 1402309.0671 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
400633 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-04-06 | 2012-02-23 | 2012-03-14 | 2014-12-04 |  | Falkirk | 335876 | 151.93 | 0 | 0 | 0 | 0 | 0 | 151.93 | 0 | 336027.93 | 0 | [6 empty] | CM_WWI | 100%
500214 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS3 | 2015-03-20 | 2016-09-14 | 2016-09-26 | 2019-08-01 | 2019-11-01 | Scottish Water Wide | 0 | 11732 | 154334.13 | 154324.87 | 167774 | 11834.66 | 0.34 | 500000 | 0 | 500000 | 101993.458 | [6 empty] | EC01G | 10% | EC10H | 90% | bar: Regulatory Outputs OMG-23
500090 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS3 | 2015-03-20 | 2016-12-20 | 2017-01-26 | 2020-04-01 | 2020-06-01 | Scottish Water Wide | 0 | 9185 | 81214.68 | 257316.32 | 292130 | 60227.37 | 4573.63 | 704647 | 0 | 704647 | 201016.0504 | [6 empty] | EC10E | 50% | EC10H | 50% | bar: Regulatory Outputs OMG-23
500106 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2015-03-31 | 2016-12-14 | 2017-01-06 | 2019-07-12 | 2019-10-14 | Scottish Water Wide | 0 | 22136 | 82403.66 | 339099.34 | 85335 | 21024.46 | 1.53 | 549999.99 | 0 | 549999.99 | 284045.2454 | [6 empty] | EC01G | 0.3636% | CS16D | 1.455% | EC10E | 49.09% | EC10H | 49.09%
500100 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2015-03-20 | 2017-03-28 | 2017-03-28 | 2019-12-20 | 2020-03-26 | Scottish Water Wide | 0 | 16694 | 110505.38 | 118997.62 | 666587.16 | 36143.97 | 0.01 | 948928.14 | 0 | 948928.14 | 489882.7384 | [6 empty] | CS16D | 14.44% | EC10E | 42.78% | EC10H | 42.78%
500101 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2015-03-20 | 2017-02-28 | 2017-03-09 | 2020-01-16 | 2020-04-16 | Scottish Water Wide | 0 | 12208 | 89258.13 | 219227.87 | 279335.91 | 63797.92 | 75274.2 | 739102.03 | 0 | 739102.03 | 222516.2716 | [6 empty] | CS16D | 21.28% | EC10E | 39.36% | EC10H | 39.36%
502199 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWMD | Supply Resilience | MS6 | 2016-06-01 | 2016-07-29 | 2016-08-11 | 2017-12-15 | 2017-12-15 | Scottish Water Wide | 0 | 0 | 19600 | 62200 | 1200 | 4000 | 0 | 87000 | 0 | 87000 | 639469.8706 | [6 empty] | WR7 | 100%
501715 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS5 | 2017-04-28 | 2018-05-25 | 2018-08-08 | 2019-02-19 | 2019-02-19 | Glasgow City | 0 | 0 | 0 | 4773 | 244736.57 | 19473.01 | 545.9 | 269528.48 | 471.56 | 270000.04 | 0 | [6 empty] | CM_WWI | 100%
501660 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-07-19 | 2017-02-28 | 2017-03-17 | 2017-12-04 | 2017-12-04 | Fife | 0 | 0 | 12000 | 35721.5925 | 0 | 0 | 0 | 47721.5925 | 0 | 47721.5925 | 0 | [6 empty] | CM_WWI | 100%
501193 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-12-03 | 2016-08-02 | 2016-08-22 | 2016-11-02 | 2016-11-02 | Fife | 0 | 7794.37 | 104574.72 | -369.14 | 25.0093 | 0 | 0 | 112024.9593 | 0 | 112024.9593 | 0 | [6 empty] | CM_WWI | 100%
402770 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-09-03 | 2013-05-13 | 2013-08-30 | 2014-10-24 |  | Aberdeenshire | 742867 | 11599.49 | 43071.47 | 0 | 0 | 0 | 0 | 54670.96 | 0 | 797537.96 | 0 | [6 empty] | CM_WSI | 100%
403544 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-09-27 | 2015-01-29 | 2015-02-16 | 2017-03-01 | 2017-06-01 | South Ayrshire | 219562 | 709100 | 388924.1 | 100180.28 | 0 | 0 | 0 | 1198204.38 | 0 | 1417766.38 | 1186562 | [6 empty] | EC10B | 0.7053% | EC16 | 99.29% | bar: Regulatory Outputs OMG-48
400593 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All East Unitary Authorities | 2504343.53 | 558810 | 987611.88 | 363029.35 | -357683.69 | 0 | 0 | 1551767.54 | 0 | 4056111.07 | 0 | [6 empty] | CM_WWI | 100%
400594 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2015-01-21 |  | All North Unitary Authorities | 2047056.48 | 0 | 0 | 62155 | -62155 | 0 | 0 | 0 | 0 | 2047056.48 | 0 | [6 empty] | CM_WWI | 100%
400595 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All East Unitary Authorities | 6753275.32 | 1177798.4 | 1488342.97 | 8576.66 | 0 | 0 | 0 | 2674718.03 | 0 | 9427993.35 | 0 | [6 empty] | CM_WWI | 100%
400596 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All North Unitary Authorities | 2553230.4 | 197238.53 | 236949.07 | 7460.32 | 0 | 0 | 0 | 441647.92 | 0 | 2994878.32 | 0 | [6 empty] | CM_WWI | 100%
400597 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All South Unitary Authorities | 2529132 | 497820 | 696780.57 | 5345.66 | 0 | 0 | 0 | 1199946.23 | 0 | 3729078.23 | 0 | [6 empty] | CM_WWI | 100%
400598 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All West Unitary Authorities | 2367230 | 472324.63 | 695013.76 | 5345.66 | 0 | 0 | 0 | 1172684.05 | 0 | 3539914.05 | 0 | [6 empty] | CM_WWI | 100%
400599 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All South Unitary Authorities | 6702907.8 | 1362416.37 | 1792668.06 | 594631 | -589285.34 | 0 | 0 | 3160430.09 | 0 | 9863337.89 | 0 | [6 empty] | CM_WWI | 100%
400600 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All West Unitary Authorities | 5204837.06 | 991533.12 | 1421440.91 | 680907.66 | -675562 | 0 | 0 | 2418319.69 | 0 | 7623156.75 | 0 | [6 empty] | CM_WWI | 100%
400581 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All East Unitary Authorities | 4136030.07 | 969008.39 | 92340.39 | 317672.82 | -308093.22 | 0 | 0 | 1070928.38 | 0 | 5206958.45 | 0 | [6 empty] | CM_WSI | 100%
400582 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All North Unitary Authorities | 4662501.65 | 989264.2 | 99915.4 | 396337.86 | -386757.26 | 0 | 0 | 1098760.2 | 0 | 5761261.85 | 0 | [6 empty] | CM_WSI | 100%
400583 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All South Unitary Authorities | 11130129.73 | 2709757.91 | 104167.76 | 1119543.79 | -1109964.19 | 0 | 0 | 2823505.27 | 0 | 13953635 | 0 | [6 empty] | CM_WSI | 100%
400584 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All West Unitary Authorities | 13756430.89 | 2862936.84 | 110887.6 | 1289452.91 | -1279873.31 | 0 | 0 | 2983404.04 | 0 | 16739834.93 | 0 | [6 empty] | CM_WSI | 100%
400585 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All East Unitary Authorities | 7037156.79 | 1423764.06 | -87945.51 | 589293.49 | -585334.89 | 0 | 0 | 1339777.15 | 0 | 8376933.94 | 0 | [6 empty] | CM_WSI | 100%
400586 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All North Unitary Authorities | 2569930.24 | 635030.87 | -184208.71 | 97852.48 | -93893.88 | 0 | 0 | 454780.76 | 0 | 3024711 | 0 | [6 empty] | CM_WSI | 100%
400587 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All South Unitary Authorities | 5411099.17 | 1080390.56 | 51155.41 | 329204.76 | -325246.16 | 0 | 0 | 1135504.57 | 0 | 6546603.74 | 0 | [6 empty] | CM_WSI | 100%
400588 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All West Unitary Authorities | 2140824.78 | 439363.67 | 82164.95 | 174168.56 | -170209.96 | 0 | 0 | 525487.22 | 0 | 2666312 | 0 | [6 empty] | CM_WSI | 100%
400573 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All East Unitary Authorities | 9522415.05 | 1760182.49 | 791139.81 | 822002.85 | -820042.54 | 0 | 0 | 2553282.61 | 0 | 12075697.66 | 0 | [6 empty] | CM_WWNI | 100%
400574 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All North Unitary Authorities | 2015842 | 45081.6 | -97.43 | 173812.33 | -171852.02 | 0 | 0 | 46944.48 | 0 | 2062786.48 | 0 | [6 empty] | CM_WWNI | 100%
400575 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All South Unitary Authorities | 9276281.51 | 1784705.14 | 844947.92 | 866542.94 | -893730.92 | 0 | 0 | 2602465.08 | 0 | 11878746.59 | 0 | [6 empty] | CM_WWNI | 100%
400576 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All West Unitary Authorities | 9164354.26 | 1775417.29 | 827201.32 | 984293.43 | -982333.12 | 0 | 0 | 2604578.92 | 0 | 11768933.18 | 0 | [6 empty] | CM_WWNI | 100%
500542 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 2017-08-31 | 2017-08-31 | All East Unitary Authorities | 0 | 56706 | 1599048.64 | 176.8 | 95.19 | 0 | 0 | 1656026.63 | 0 | 1656026.63 | 0 | [6 empty] | CM_WSI | 100%
500543 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-27 | 2015-04-27 | 2015-04-27 | 2017-08-31 | 2017-08-31 | All East Unitary Authorities | 0 | 4782 | 184250.13 | 0 | 0 | 0 | 0 | 189032.13 | 0 | 189032.13 | 0 | [6 empty] | CM_WSNI | 100%
500544 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2017-08-31 | 2017-08-31 | All East Unitary Authorities | 0 | 6832 | 292833.38 | 0 | 0 | 0 | 0 | 299665.38 | 0 | 299665.38 | 0 | [6 empty] | CM_WSNI | 100%
400577 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All East Unitary Authorities | 3100000 | 624922.86 | 2654.55 | 273108.73 | -271148.42 | 0 | 0 | 629537.72 | 0 | 3729537.72 | 0 | [6 empty] | CM_WSNI | 100%
400578 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All North Unitary Authorities | 2058992 | 441192.96 | 2988.75 | 253335.75 | -253335.75 | 0 | 0 | 444181.71 | 0 | 2503173.71 | 0 | [6 empty] | CM_WSNI | 100%
400579 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All South Unitary Authorities | 2575019.22 | 494071.61 | 42835.41 | 271789.27 | -269828.96 | 0 | 0 | 538867.33 | 0 | 3113886.55 | 0 | [6 empty] | CM_WSNI | 100%
400580 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2017-08-31 |  | All West Unitary Authorities | 2601663.58 | 589048.86 | 102792.21 | 266511.44 | -264551.13 | 0 | 0 | 693801.38 | 0 | 3295464.96 | 0 | [6 empty] | CM_WSNI | 100%
500545 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 2017-08-31 | 2017-08-31 | All North Unitary Authorities | 0 | 36454 | 2263653 | -69412.55 | 0 | 0 | 0 | 2230694.45 | 0 | 2230694.45 | 0 | [6 empty] | CM_WSI | 100%
500546 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-27 | 2015-04-27 | 2015-04-27 | 2017-08-31 | 2017-08-31 | All North Unitary Authorities | 0 | 3074 | 188582.44 | 0 | 0 | 0 | 0 | 191656.44 | 0 | 191656.44 | 0 | [6 empty] | CM_WSNI | 100%
500547 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-27 | 2015-04-27 | 2015-04-27 | 2017-08-31 | 2017-08-31 | All North Unitary Authorities | 0 | 4392 | 228086.31 | 0 | 0 | 0 | 0 | 232478.31 | 0 | 232478.31 | 0 | [6 empty] | CM_WSNI | 100%
500551 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 2017-08-31 | 2017-08-31 | All South Unitary Authorities | 0 | 74932 | 3431713.64 | 0 | 0 | 0 | 0 | 3506645.64 | 0 | 3506645.64 | 0 | [6 empty] | CM_WSI | 100%
500552 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-05-26 | 2015-05-26 | 2015-05-26 | 2017-08-31 | 2017-08-31 | All South Unitary Authorities | 0 | 6320 | 162624.29 | 0 | 0 | 0 | 0 | 168944.29 | 0 | 168944.29 | 0 | [6 empty] | CM_WSNI | 100%
500553 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-05-26 | 2015-05-26 | 2015-05-26 | 2017-08-31 | 2017-08-31 | All South Unitary Authorities | 0 | 9028 | 621292.09 | 0 | 0 | 0 | 0 | 630320.09 | 0 | 630320.09 | 0 | [6 empty] | CM_WSNI | 100%
500548 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 2017-08-31 | 2017-08-31 | All West Unitary Authorities | 0 | 76958 | 3274326.7 | 0 | 534446.72 | 0 | 0 | 3885731.42 | 0 | 3885731.42 | 0 | [6 empty] | CM_WSI | 100%
500549 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-05-26 | 2015-05-26 | 2015-05-26 | 2017-08-31 | 2017-08-31 | All West Unitary Authorities | 0 | 6490 | 193273.2 | 0 | 0 | 0 | 0 | 199763.2 | 0 | 199763.2 | 0 | [6 empty] | CM_WSNI | 100%
500550 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-05-26 | 2015-05-26 | 2015-05-26 | 2017-08-31 | 2017-08-31 | All West Unitary Authorities | 0 | 9272 | 301306.91 | 318.56 | 150944.09 | 0 | 0 | 461841.56 | 0 | 461841.56 | 0 | [6 empty] | CM_WSNI | 100%
501264 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2016-02-10 | 2017-01-19 | 2017-03-28 | 2017-06-30 | 2017-06-30 | Fife | 0 | 3282 | 134327 | -3604 | -2475.47 | 3999.91 | 0 | 135529.44 | 0 | 135529.44 | 0 | [6 empty] | CM_WWI | 100%
502935 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS2 | 2018-03-29 | 2019-02-26 | 2019-05-23 | 2019-08-20 | 2019-11-21 | Aberdeenshire | 0 | 0 | 0 | 14300.702 | 73004.298 | 121916.05 | 2249.95 | 211471 | 0 | 211471 | 0 | [6 empty] | CM_WWI | 100%
503199 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2018-10-26 | 2019-09-02 | 2019-11-12 | 2020-12-01 | 2021-12-01 | Scottish Borders | 0 | 0 | 0 | 0 | 275000 | 1015234.89 | 802920.95 | 2093155.84 | 626197.48 | 2719353.32 | 0 | [6 empty] | DW5MR | 15% | DW5FS | 85% | [16 empty] | Regulatory Outputs OMG-06: 343.5619
500047 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS1 | 2015-06-23 | 2019-08-19 | 2019-10-08 | 2021-09-06 | 2021-09-07 | Scottish Borders | 0 | 98749 | 316067.11 | 109039.73 | 218646.53 | 1245092.21 | 1503799.5 | 3491394.08 | 62141.35 | 3553535.43 | 0 | [6 empty] | CM_WSNI | 100%
501291 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2015-12-04 | 2017-03-29 | 2017-05-19 | 2019-05-30 | 2019-05-31 | Scottish Borders | 0 | 5481.61 | 92255.69 | 129863.49 | 376999.66 | 6955.32 | 586.93 | 612142.7 | 840.42 | 612983.12 | 0 |  |  |  |  | 351.9804 |  | CM_WSNI | 100%
401311 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-27 | 2013-07-30 | 2013-08-13 | 2014-12-02 | 2014-07-01 | Moray | 567875 | 699.38 | -1673.8 | 0 | 0 | 0 | 0 | -974.42 | 0 | 566900.58 | 0 | [6 empty] | CM_WSI | 100%
046853 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2012-09-11 | 2012-09-24 | 2013-03-28 | 2013-03-29 | Moray | 1254002.54 | -894.07 | 0 | 0 | 0 | 0 | 0 | -894.07 | 0 | 1253108.47 | 0 | [6 empty] | DW23 | 100%
403951 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS0 | 2014-11-19 | 2021-02-08 | 2021-03-22 | 2022-09-01 | 2023-02-01 | Dumfries and Galloway | 99678 | 1665 | 13107 | 168598 | 152297 | 234587.29 | 52077.45 | 622331.74 | 6377990.21 | 7099999.95 | 4452799 | [6 empty] | EC16 | 100% | bar: Regulatory Outputs OMG-48
402772 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-09-10 | 2013-07-24 | 2013-08-30 | 2015-03-13 |  | Dumfries and Galloway | 743005 | 3538 | 2137 | 0 | 0 | 0 | 0 | 5675 | 0 | 748680 | 0 | [6 empty] | CM_WWI | 100%
501566 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-09-22 | 2021-11-22 | 2022-03-08 | 2023-02-17 | 2023-05-22 | Shetland Islands | 0 | 84187.13 | 22577.06 | 999.81 | 66062 | 0 | 0 | 173826 | 1724601 | 1898427 | 0 | [6 empty] | CM_WSI | 100%
046572 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2009-07-14 | 2012-01-26 | 2012-02-20 | 2017-06-30 |  | Scottish Water Wide | 19392597.96 | 1598801.08 | 1770939.22 | 286927.27 | -314845.9415 | 32450 | 0 | 3374271.6285 | 0 | 22766869.5885 | 0 |  |  |  |  | 1237230.2695 |  | CM_WSNI | 100%
046081 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-07-31 | 2010-03-11 | 2010-07-28 | 2015-05-29 |  | Scottish Water Wide | 5077805 | 21783.19 | 0 | 0 | 0 | 0 | 0 | 21783.19 | 0 | 5099588.19 | 0 | [6 empty] | CM_WSNI | 100%
400085 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-11-04 | 2010-11-05 | 2010-11-12 | 2015-03-31 |  | Scottish Water Wide | 8595523.47 | 195342.85 | -35396.21 | 0 | 0 | 0 | 0 | 159946.64 | 0 | 8755470.11 | 0 | [6 empty] | CM_WSNI | 100%
500870 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-08-17 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | East Lothian | 0 | 5298.78 | 4844.52 | 17739 | -17729.8925 | 0 | 0 | 10152.4075 | 0 | 10152.4075 | 321640.5723 | [6 empty] | DW5FS | 100%
503148 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS5 | 2018-03-15 | 2018-03-30 | 2018-04-19 | 2018-11-30 | 2018-11-16 | Midlothian | 0 | 0 | 0 | 56033.04 | 929858.84 | 5159.42 | 955.71 | 992007.01 | 0 | 992007.01 | 0 | [6 empty] | CM_WSNI | 100%
502246 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2016-08-15 | 2019-07-08 | 2019-07-19 | 2020-05-28 | 2020-08-28 | Midlothian | 0 | 0 | 13827.66 | 47520.37 | 805881.81 | 377129.49 | 347494.95 | 1591854.28 | 1345.71 | 1593199.99 | 0 | [6 empty] | CM_WSNI | 100%
403217 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-01-07 | 2014-05-13 | 2014-04-16 | 2014-04-16 |  | East Lothian | 98709.96 | 835.7 | 0 | 0 | 0 | 0 | 0 | 835.7 | 0 | 99545.66 | 0 | [6 empty] | CM_WSNI | 100%
403220 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-01-07 | 2014-05-15 | 2014-06-09 | 2015-02-27 |  | Midlothian | 1002055.18 | -48127.1 | 680.68 | 0 | 0 | 0 | 0 | -47446.42 | 0 | 954608.76 | 0 | [6 empty] | CM_WSNI | 100%
403970 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2016-07-19 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | East Lothian | 904.37 | 16351.35 | 64164.65 | 109540.7275 | 24383.6771 | 0 | 0 | 214440.4046 | 0 | 215344.7746 | 0 | [6 empty] | SG1 | 100%
046124 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-16 | 2010-06-28 | 2010-08-09 | 2011-01-26 |  | Midlothian | 297647 | 199.93 | 0 | 0 | 0 | 0 | 0 | 199.93 | 0 | 297846.93 | 0 | [6 empty] | CM_WWNI | 100%
503260 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-28 | 2023-07-20 | 2023-11-14 | 2024-11-07 | 2025-02-07 | Midlothian | 0 | 0 | 0 | 0 | 74866.553 | 0 | 38455.38 | 113321.933 | 32320.42 | 145642.353 | 148885.7057 | [6 empty] | SG1 | 100%
502951 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2019-07-24 | 2020-10-26 | 2021-03-03 | 2021-10-13 | 2022-01-13 | West Dunbartonshire | 0 | 0 | 0 | 6475.1 | 4282.7271 | 31168.54 | 116319.05 | 158245.4171 | 142069.66 | 300315.0771 | 0 | [6 empty] | CM_WSNI | 100%
502927 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-07-06 | 2022-05-06 | 2022-08-08 | 2023-03-10 | 2023-06-12 | Glasgow City | 0 | 0 | 0 | 6024.665 | 4966.515 | 0 | 0 | 10991.18 | 264008.78 | 274999.96 | 0 | [6 empty] | CM_WSI | 100%
503276 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-24 | 2023-06-07 | 2023-10-10 | 2024-10-07 | 2025-01-07 | Moray | 0 | 0 | 0 | 0 | 78497.03 | 0 | 35816.92 | 114313.95 | 29545.41 | 143859.36 | 148885.7057 | [6 empty] | SG1 | 100%
501638 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW0 | 2021-09-16 | 2022-08-10 | 2022-12-13 | 2023-04-13 | 2023-07-14 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 166.36 | 19862.39 | 1439.8 | 1725.68 | 23194.23 | 476805.74 | 499999.97 | 0 | [6 empty] | CM_WWNI | 100%
501165 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2015-12-03 | 2018-11-29 | 2018-12-17 | 2020-05-06 | 2020-05-07 | Argyll and Bute-Cowal & Bute | 0 | 12056 | 255828.88 | 40930.71 | 352778.46 | 1261688.36 | 215004.34 | 2138286.75 | 6636.29 | 2144923.04 | 0 | [6 empty] | CM_WWNI | 100%
502724 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS5 | 2018-02-23 | 2018-08-28 | 2018-11-26 | 2019-02-19 | 2019-02-19 | Aberdeenshire | 0 | 0 | 0 | 11822.041 | 36108.489 | 3264.3 | 371.75 | 51566.58 | 431.05 | 51997.63 | 0 | [6 empty] | CM_WWI | 100%
400068 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-10-06 | 2012-09-05 | 2013-01-07 | 2014-03-19 | 2014-03-26 | Aberdeenshire | 1109218.07 | 45081.75 | -1694.79 | 0 | 0 | 0 | 0 | 43386.96 | 0 | 1152605.03 | 10063.1344 | [6 empty] | SG1 | 20% | WQ01 | 80%
503222 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-11-15 | 2023-04-21 | 2023-08-23 | 2024-08-19 | 2024-11-19 | Aberdeenshire | 0 | 0 | 0 | 0 | 89094.82 | 9232.58 | 28587.63 | 126915.03 | 18020.18 | 144935.21 | 148885.7057 | [6 empty] | SG1 | 100%
500940 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2015-09-04 | 2018-09-18 | 2018-10-29 | 2019-06-11 | 2019-09-13 | North Lanarkshire | 0 | 26881.08 | 26102.92 | 197586 | 1533546 | 338886.06 | 4276.93 | 2127278.99 | 0.02 | 2127279.01 | 0 | [6 empty] | CM_WWI | 100%
045362 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-12-07 | 2012-01-30 | 2012-09-27 | 2012-12-11 | Orkney Islands | 1140367.08 | 11889.84 | -16046.76 | 0 | 0 | 0 | 0 | -4156.92 | 0 | 1136210.16 | 0 | [6 empty] | WG1 | 6.758% | DW13 | 7.984% | DW23 | 85.26%
402602 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-03-27 | 2014-05-23 | 2014-08-29 | 2014-09-01 |  | All East Unitary Authorities | 7460 | -1638.64 | 0 | 0 | 0 | 0 | 0 | -1638.64 | 0 | 5821.36 | 0 | [6 empty] | CM_WWNI | 100%
502200 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 | Shetland Islands | 0 | 0 | 15906.98 | 249.02 | 47.595 | 0 | 0 | 16203.595 | 0 | 16203.595 | 0 | [6 empty] | CM_WWNI | 100%
500491 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS5 | 2015-04-21 | 2016-11-30 | 2017-03-24 | 2018-12-17 | 2018-12-17 | Shetland Islands | 0 | 73000 | 388298 | 773512 | 119183 | 0 | 465 | 1354458 | 0 | 1354458 | 0 | [6 empty] | CM_WWNI | 100%
503041 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2018-08-15 | 2018-10-31 | 2019-01-14 | 2019-07-19 | 2019-08-15 | East Ayrshire | 0 | 0 | 0 | 6395.2 | 365260.58 | 156497.7 | 1037.03 | 529190.51 | 1311.41 | 530501.92 | 0 | [6 empty] | CM_WSI | 100%
502911 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | GW1 | 2019-05-30 | 2020-03-16 | 2020-03-16 | 1933-08-18 | 1933-08-18 | Aberdeen City | 0 | 0 | 0 | 0 | 31343.51 | 300624.41 | 171115.2 | 503083.12 | 2157419.79 | 2660502.91 | 0 | [6 empty] | SG5 | 100%
502692 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS5 | 2017-04-21 | 2018-02-21 | 2018-02-21 | 2018-09-28 | 2018-09-28 | Renfrewshire | 0 | 0 | 0 | 697.5625 | 66829.05 | 51955.89 | 0 | 119482.5025 | 0 | 119482.5025 | 0 | [6 empty] | CM_WSNI | 100%
501180 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS3 | 2015-12-07 | 2015-12-07 | 2016-02-10 | 2021-02-02 | 2021-02-03 | Scottish Water Wide | 0 | 82424 | -3233.77 | 977 | 0 | 32200 | 29874.77 | 142242 | 0 | 142242 | 0 | [6 empty] | CM_WSNI | 100%
502876 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS0 | 2018-08-15 | 2020-05-04 | 2020-11-20 | 2021-05-14 | 2021-08-18 | Perth and Kinross | 0 | 0 | 0 | 14679.696 | 49361.304 | 64808.08 | 244040.29 | 372889.37 | 128580.6 | 501469.97 | 0 | [6 empty] | CM_WWI | 100%
501676 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-06-02 | 2016-08-31 | Aberdeenshire | 0 | 0 | 12994.67 | 0 | 0 | 0 | 0 | 12994.67 | 0 | 12994.67 | 0 | [6 empty] | CM_WSNI | 100%
501912 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2022-02-14 | 2023-05-26 | 2023-09-29 | 2024-09-23 | 2024-12-24 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1609900.02 | 1609900.02 | 0 | [6 empty] | CM_WSI | 100%
402016 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-08-11 | 2013-10-31 | 2014-01-27 | 2015-03-26 |  | Orkney Islands | 158625 | 22309 | 0.34 | -57.15 | 0 | 0 | 0 | 22252.19 | 0 | 180877.19 | 0 | [6 empty] | CM_M&G | 100%
502782 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2017-12-22 | 2017-12-22 | 2018-07-02 | 2018-08-27 | 2018-08-27 | East Renfrewshire | 0 | 0 | 0 | 69300 | 802553.4944 | 10 | 0 | 871863.4944 | 0 | 871863.4944 | 0 | [6 empty] | CM_WSI | 100%
401637 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-25 | 2013-03-18 | 2013-11-25 | 2014-02-26 | 2014-03-18 | Glasgow City | 147401 | 0 | 0 | 0 | -3697.4 | 0 | 0 | -3697.4 | 0 | 143703.6 | 0 | [6 empty] | EC04B | 100%
401638 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-29 | 2013-05-13 | 2013-05-13 | 2014-03-26 | 2014-03-27 | Glasgow City | 858894 | 0 | 0 | 0 | -2118.51 | 0 | 0 | -2118.51 | 0 | 856775.49 | 0 | [6 empty] | EC04B | 100%
401640 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-25 | 2012-06-21 | 2012-06-25 | 2013-03-01 | 2013-05-30 | Glasgow City | 723704 | -5510.77 | 0 | 0 | 0 | 0 | 0 | -5510.77 | 0 | 718193.23 | 0 | [6 empty] | EC04B | 100%
401642 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS5 | 2010-12-15 | 2017-09-21 | 2017-09-25 | 2019-02-01 | 2019-03-01 | Glasgow City | 248427 | 346389 | 1280138.7 | 3700201.48 | 5954831.64 | 360410.2 | 3604.5 | 11645575.52 | 3997.22 | 11897999.74 | 1601836 |  |  |  |  | 21270 |  | EC04B | 38% | CM_WWNI | 62% | bar: Regulatory Outputs OMG-19
401608 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-17 | 2012-11-30 | 2013-01-14 | 2013-06-06 | 2013-09-12 | Renfrewshire | 549863.1 | 14786.15 | 0 | 0 | 0 | 0 | 0 | 14786.15 | 0 | 564649.25 | 5 | [6 empty] | EC04B | 100%
401643 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-01 | 2014-06-30 | 2015-05-25 | 2015-10-01 | 2018-03-01 | Renfrewshire | 201610 | 235520 | -49551.07 | 0 | -5880.2465 | 0 | 0 | 180088.6835 | 0 | 381698.6835 | 64855.0001 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401610 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-18 | 2013-09-18 | 2013-11-04 | 2014-05-26 | 2014-10-27 | Renfrewshire | 796012 | 91098 | 8049.2 | 0 | 0 | 0 | 0 | 99147.2 | 0 | 895159.2 | 2831 | [6 empty] | EC04B | 100%
401645 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-09-13 | 2013-09-23 | 2015-02-17 | 2015-03-24 | Renfrewshire | 37343.79 | 1244.21 | -62.03 | 0 | 0 | 0 | 0 | 1182.18 | 0 | 38525.97 | 1721 | [6 empty] | EC10B | 100%
401646 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-19 | 2014-08-12 | 2015-07-01 | 2015-09-01 | Glasgow City | 44582 | 0 | 0 | -646.33 | 0 | 0 | 0 | -646.33 | 0 | 43935.67 | 329 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401647 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-18 | 2014-08-12 | 2015-07-01 | 2015-09-01 | Glasgow City | 1276232 | 80691.87 | 4867.82 | 1131.22 | 0 | 0 | 0 | 86690.91 | 0 | 1362922.91 | 71978 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401649 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-09-13 | 2013-09-23 | 2015-02-17 | 2015-03-24 | Glasgow City | 46859 | 141 | -250.78 | 0 | 0 | 0 | 0 | -109.78 | 0 | 46749.22 | 141 | [6 empty] | EC10B | 100%
401611 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-18 | 2013-12-30 | 2014-05-05 | 2014-10-14 | 2015-03-25 | Glasgow City | 866356 | 5571.14 | 0 | 0 | 0 | 0 | 0 | 5571.14 | 0 | 871927.14 | 6717 | [6 empty] | EC10B | 100%
401650 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-19 | 2014-08-12 | 2015-07-01 | 2015-09-01 | Glasgow City | 40667 | 283.06 | 1066.25 | -481.62 | 0 | 0 | 0 | 867.69 | 0 | 41534.69 | 129 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401651 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-09-13 | 2013-09-23 | 2015-02-17 | 2015-03-24 | Glasgow City | 2693040 | 34089 | 1696.71 | 0 | 0 | 0 | 0 | 35785.71 | 0 | 2728825.71 | 21445 | [6 empty] | EC10B | 100%
401653 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-27 | 2014-05-05 | 2015-01-19 | 2015-03-24 | Glasgow City | 1358188.53 | 50458.47 | 2439.67 | 0 | 0 | 0 | 0 | 52898.14 | 0 | 1411086.67 | 8424 | [6 empty] | EC04B | 100%
401613 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-18 | 2013-12-23 | 2014-05-05 | 2014-10-14 | 2015-03-25 | Renfrewshire | 47133 | 1113 | -2649.71 | 0 | 0 | 0 | 0 | -1536.71 | 0 | 45596.29 | 488 | [6 empty] | EC10B | 100%
401654 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-19 | 2014-01-06 | 2015-11-01 | 2016-03-01 | Glasgow City | 67927 | 1376.83 | 1861.1 | -114.5 | 0 | 0 | 0 | 3123.43 | 0 | 71050.43 | 866 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401655 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-18 | 2014-01-06 | 2015-11-01 | 2016-02-01 | Glasgow City | 3055520 | 379657 | 19944 | 30908.44 | 11451.625 | 0 | 0 | 441961.065 | 0 | 3497481.065 | 266968 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401656 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS5 | 2010-12-15 | 2014-05-30 | 2014-09-22 | 2018-06-01 | 2018-10-01 | Glasgow City | 100499 | 0 | 0 | 0 | 0 | 5942.05 | 0.94 | 5942.99 | 0 | 106441.99 | 5798.9999 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401657 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-19 | 2014-01-06 | 2015-11-01 | 2016-03-01 | Glasgow City | 53746 | 1213.92 | 598.8 | -190.55 | 0 | 0 | 0 | 1622.17 | 0 | 55368.17 | 232 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401658 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-12-23 | 2014-05-05 | 2014-10-14 | 2015-03-25 | Glasgow City | 44865 | 0 | -1435.18 | 0 | 0 | 0 | 0 | -1435.18 | 0 | 43429.82 | 135 | [6 empty] | EC10B | 100%
401659 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-19 | 2014-01-06 | 2015-11-01 | 2016-03-01 | Glasgow City | 54752 | 0 | 457.62 | 0 | 0 | 0 | 0 | 457.62 | 0 | 55209.62 | 228 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401660 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-09-30 | 2013-10-21 | 2014-11-13 | 2015-03-06 | South Lanarkshire | 764717 | 2455 | -2012.23 | 0 | 0 | 0 | 0 | 442.77 | 0 | 765159.77 | 2076 | [6 empty] | EC04B | 100%
401661 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-09-30 | 2013-10-21 | 2014-11-13 | 2015-03-06 | Glasgow City | 50131.61 | 79.39 | 0 | 0 | 0 | 0 | 0 | 79.39 | 0 | 50211 | 234 | [6 empty] | EC04B | 100%
401662 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-19 | 2013-12-09 | 2014-07-30 | 2014-10-27 | Glasgow City | 62420 | 0 | 822.24 | 0 | 0 | 0 | 0 | 822.24 | 0 | 63242.24 | 0 | [6 empty] | EC04B | 100%
401663 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS0 | 2010-12-15 | 2019-10-21 | 2020-01-13 | 2020-09-01 | 2020-12-01 | South Lanarkshire | 207195.17 | 13292.83 | 8559 | 68130.8546 | 152992.1454 | 842225.1 | 1198814.21 | 2284014.14 | 8790.73 | 2500000.04 | 1916335 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401664 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-11-18 | 2013-12-09 | 2014-07-30 | 2014-10-27 | Glasgow City | 1004447.51 | 903.49 | -836.26 | 0 | 0 | 0 | 0 | 67.23 | 0 | 1004514.74 | 1693.3562 | [6 empty] | CM_WWI | 2.331% | CS11A | 5.995% | EC04B | 91.67%
401665 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-12-11 | 2014-09-01 | 2015-02-10 | 2015-03-20 | Glasgow City | 53736 | 447 | -285.66 | 0 | 0 | 0 | 0 | 161.34 | 0 | 53897.34 | 3375 | [6 empty] | EC10B | 100%
401666 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-12-10 | 2014-09-01 | 2015-02-10 | 2015-03-20 | Renfrewshire | 854401 | -21849 | 11405.16 | 0 | 0 | 0 | 0 | -10443.84 | 0 | 843957.16 | 66106 | [6 empty] | EC10B | 100%
401667 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-02 | 2011-12-07 | 2011-12-19 | 2012-01-25 | 2012-03-23 | South Lanarkshire | 20999.23 | 0 | 0 | 277.29 | 0 | 0 | 0 | 277.29 | 0 | 21276.52 | 0 | [6 empty] | EC04B | 100%
401668 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS2 | 2010-12-02 | 2019-03-26 | 2019-04-29 | 2019-12-01 | 2020-03-01 | South Lanarkshire | 174698 | 36209 | 10953.38 | 76885.15 | 306790.47 | 1760803.01 | 29706.5 | 2221347.51 | 2324.18 | 2398369.69 | 2348796 |  |  |  |  | 8280 |  | EC04B | 100% | bar: Regulatory Outputs OMG-19
401669 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-02 | 2013-05-27 | 2013-08-12 | 2014-02-17 | 2014-02-28 | South Lanarkshire | 498527 | 1623 | -1085.38 | 0 | 0 | 0 | 0 | 537.62 | 0 | 499064.62 | 3534 | [6 empty] | EC04B | 100%
401614 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS3 | 2010-11-17 | 2018-09-25 | 2019-01-11 | 2019-06-01 | 2019-08-01 | South Lanarkshire | 107706.31 | 15389.93 | 53873.78 | 98909.98 | 602339 | 30792.02 | 2261.96 | 803566.67 | 0.02 | 911273 | 410766 |  |  |  |  | 4160.0004 |  | EC04B | 100% | bar: Regulatory Outputs OMG-19
401685 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS0 | 2010-12-03 | 2020-06-15 | 2020-08-24 | 2021-02-01 | 2021-03-01 | South Lanarkshire | 90517 | 5290.44 | 13209.48 | 47328.08 | 181469 | 20211.95 | 1587490.23 | 1854999.18 | 465400.99 | 2410917.17 | 397695 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401686 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2015-06-25 | 2015-08-03 | 2015-08-12 | 2015-08-12 | South Lanarkshire | 54503 | -991.23 | 0 | 0 | 0 | 0 | 0 | -991.23 | 0 | 53511.77 | 0 | [6 empty] | EC04B | 100%
401687 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS0 | 2010-12-03 | 2020-06-15 | 2020-08-04 | 2021-02-01 | 2021-03-01 | South Lanarkshire | 29320 | 7758 | 6878 | 39700 | 1442 | 26 | 11414.66 | 67218.66 | 3461.38 | 100000.04 | 455597 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401688 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-02-20 | 2013-03-28 | 2014-11-13 | 2015-03-06 | South Lanarkshire | 905260 | 60350 | -12975.08 | -108.76 | 0 | 0 | 0 | 47266.16 | 0 | 952526.16 | 67933 | [6 empty] | EC04B | 100%
401689 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-02-19 | 2013-03-28 | 2014-11-13 | 2015-03-06 | South Lanarkshire | 19930 | -1636.96 | 0 | 0 | 0 | 0 | 0 | -1636.96 | 0 | 18293.04 | 0 | [6 empty] | EC04B | 100%
401616 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS3 | 2010-11-18 | 2018-03-22 | 2018-03-28 | 2019-10-01 | 2019-12-01 | Glasgow City | 172414 | 17738 | 46269.43 | 326611.77 | 950913 | 1181631.88 | 0 | 2523164.08 | 0 | 2695578.08 | 728927 |  |  |  |  | 6009.9997 |  | EC10B | 100% | bar: Regulatory Outputs OMG-19
401618 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-01 | 2014-12-23 | 2015-09-14 | 2017-02-01 | 2017-03-01 | Glasgow City | 502945 | 290095 | 352959.98 | 210444.43 | 45.016 | 0 | 0 | 853544.426 | 0 | 1356489.426 | 498170.0001 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401619 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-26 | 2014-12-23 | 2015-09-14 | 2016-09-01 | 2017-02-01 | Glasgow City | 388377 | 795900 | 369661.84 | -8439.04 | 2146.5875 | 0 | 0 | 1159269.3875 | 0 | 1547646.3875 | 707835.0001 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401620 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-25 | 2014-12-22 | 2015-09-14 | 2016-11-01 | 2017-03-01 | Glasgow City | 361706 | 122769 | 695569.66 | 20455.7 | 2608.84 | 0 | 0 | 841403.2 | 0 | 1203109.2 | 383746.0001 | [6 empty] | CM_WWI | 13.64% | EC10B | 86.36% | bar: Regulatory Outputs OMG-19
401622 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-26 | 2013-02-20 | 2013-08-29 | 2014-03-24 | 2014-03-28 | Glasgow City | 597653.74 | 8442.09 | 0 | 0 | 0 | 0 | 0 | 8442.09 | 0 | 606095.83 | 4174 | [6 empty] | EC10B | 100%
401623 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-26 | 2013-09-16 | 2013-11-04 | 2014-03-24 | 2014-03-31 | Glasgow City | 324073 | 25308 | -325.99 | 0 | 0 | 0 | 0 | 24982.01 | 0 | 349055.01 | 2352 | [6 empty] | EC10B | 100%
401400 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-09-10 | 2011-08-22 | 2013-08-19 | 2014-03-12 | 2014-03-28 | Glasgow City | 818243 | 0 | 0 | -39179.19 | 0 | 0 | 0 | -39179.19 | 0 | 779063.81 | 24757 | [6 empty] | EC10B | 100%
401690 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-11-11 | 2014-09-22 | 2015-02-05 | 2015-03-11 | Glasgow City | 588476 | 59438 | -382.79 | 0 | 0 | 0 | 0 | 59055.21 | 0 | 647531.21 | 65156 | [6 empty] | EC04B | 100%
401692 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-05-15 | 2013-10-28 | 2015-01-19 | 2015-02-16 | East Renfrewshire | 351278.66 | 20784.34 | 2999.87 | -14974.14 | 0 | 0 | 0 | 8810.07 | 0 | 360088.73 | 4176 | [6 empty] | EC04B | 100%
401693 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-05-16 | 2013-10-28 | 2015-01-19 | 2015-02-16 | East Renfrewshire | 21597.1 | 129.16 | 0 | 0 | 0 | 0 | 0 | 129.16 | 0 | 21726.26 | 76 | [6 empty] | EC04B | 100%
401694 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-01-09 | 2013-03-21 | 2013-07-04 | 2013-09-12 | East Renfrewshire | 59980 | -656.74 | 0 | 0 | 0 | 0 | 0 | -656.74 | 0 | 59323.26 | 133 | [6 empty] | EC04B | 100%
401626 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-27 | 2015-10-30 | 2015-10-30 | 2015-10-30 | 2015-10-30 | Glasgow City | 69769 | -3777.73 | 0 | 0 | 0 | 0 | 0 | -3777.73 | 0 | 65991.27 | 5004 | [6 empty] | EC04B | 100%
401696 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2015-02-12 | 2015-03-30 | 2015-10-01 | 2016-03-01 | Glasgow City | 437780 | 671621 | -21212.18 | -1642.62 | 2.12 | 0 | 0 | 648768.32 | 0 | 1086548.32 | 638439 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401697 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS5 | 2010-12-03 | 2016-03-14 | 2016-03-22 | 2019-01-01 | 2019-06-01 | Glasgow City | 5560 | 1527.05 | 2294.06 | 271.28 | 0 | 0 | 0 | 4092.39 | 0 | 9652.39 | 3283 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401698 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS5 | 2010-12-03 | 2016-03-15 | 2016-03-22 | 2019-01-01 | 2019-03-01 | Glasgow City | 109367.15 | 502080.85 | 808540.82 | 55906.96 | 1361866.24 | 60479.78 | 2758.23 | 2791632.88 | 0 | 2901000.03 | 3279862 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401699 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-05-21 | 2013-08-12 | 2014-01-10 | 2014-02-03 | Glasgow City | 283653.19 | 1830.97 | 471.46 | 0 | 0 | 0 | 0 | 2302.43 | 0 | 285955.62 | 3538 | [6 empty] | EC04B | 100%
401700 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-05-20 | 2014-01-27 | 2014-11-10 | 2015-02-06 | East Renfrewshire | 514292 | 29253 | 1750.57 | 0 | 0 | 0 | 0 | 31003.57 | 0 | 545295.57 | 4467.0001 | [6 empty] | EC04B | 100%
401702 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2012-11-30 | 2013-02-04 | 2013-03-25 | 2013-05-21 | Glasgow City | 33021 | 849.16 | 0 | 0 | 0 | 0 | 0 | 849.16 | 0 | 33870.16 | 304 | [6 empty] | EC04B | 100%
401703 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2013-07-30 | 2014-03-03 | 2014-11-09 | 2015-01-28 | East Renfrewshire | 705152 | -27124 | -8144.4 | 1.05 | 0 | 0 | 0 | -35267.35 | 0 | 669884.65 | 10365 | [6 empty] | EC04B | 100%
401856 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-09-02 | 2013-07-19 | 2014-02-24 | 2014-11-09 | 2015-01-27 | East Renfrewshire | 357124 | 9911 | 1952.41 | 0 | 0 | 0 | 0 | 11863.41 | 0 | 368987.41 | 7776 | [6 empty] | EC04B | 100%
401705 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS0 | 2010-12-03 | 2019-10-21 | 2020-01-10 | 2020-11-01 | 2021-02-01 | East Renfrewshire | 22780.69 | 26463.49 | 77503.31 | 227139.31 | 326614.2 | 1652501.12 | 3195913.11 | 5506134.54 | 23024.8 | 5551940.03 | 3110294 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401706 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-05-20 | 2013-10-21 | 2014-10-09 | 2015-01-28 | East Renfrewshire | 251567 | 1993.79 | 1160.85 | 0 | 0 | 0 | 0 | 3154.64 | 0 | 254721.64 | 5718 | [6 empty] | EC04B | 100%
401707 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-05-20 | 2013-10-21 | 2014-10-09 | 2015-03-06 | East Renfrewshire | 338502 | -10367 | 39.62 | 0 | 0 | 0 | 0 | -10327.38 | 0 | 328174.62 | 3619 | [6 empty] | EC04B | 100%
401708 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-03 | 2013-05-16 | 2014-01-27 | 2014-11-10 | 2015-02-06 | East Renfrewshire | 16218.86 | 100.14 | -100.14 | 0 | 0 | 0 | 0 | 0 | 0 | 16218.86 | 274 | [6 empty] | EC04B | 100%
401630 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-27 | 2013-01-22 | 2013-01-28 | 2013-06-06 | 2013-09-12 | Glasgow City | 740679.28 | 2526.3 | 0 | 0 | 0 | 0 | 0 | 2526.3 | 0 | 743205.58 | 0 | [6 empty] | EC04B | 100%
401709 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS6 | 2010-12-15 | 2016-12-21 | 2017-01-23 | 2017-12-01 | 2018-02-01 | East Renfrewshire | 531925 | 88182 | 2127406 | 3715323 | -45114.5248 | 1850 | 0 | 5887646.4752 | 0 | 6419571.4752 | 4793730 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401631 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-27 | 2012-11-09 | 2012-11-19 | 2012-12-17 | 2013-01-17 | Glasgow City | 26803 | 3313.97 | 0 | 0 | 0 | 0 | 0 | 3313.97 | 0 | 30116.97 | 1159 | [6 empty] | EC04B | 100%
401710 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2010-12-09 | 2016-07-21 | 2016-10-03 | 2017-10-01 | 2018-01-01 | Renfrewshire | 372283 | 153652 | 364372.88 | 1486484.24 | 0 | 1500.02 | 0 | 2006009.14 | 0 | 2378292.14 | 807733 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401633 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-27 | 2012-07-17 | 2012-11-14 | 2012-12-01 | 2016-10-01 | Glasgow City | 1201151 | 1468404 | 1751817.62 | 13210.68 | 12512.772 | 0 | 0 | 3245945.072 | 0 | 4447096.072 | 745277.0001 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401718 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2013-07-24 | 2014-03-31 | 2015-01-19 | 2015-03-06 | Glasgow City | 894098 | 24073 | -10347.37 | 0 | 0 | 0 | 0 | 13725.63 | 0 | 907823.63 | 20137 | [6 empty] | EC04B | 100%
401719 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2014-04-28 | 2015-04-01 | 2015-04-17 | 2015-04-17 | Renfrewshire | 94561 | -120.52 | 0 | 0 | 0 | 0 | 0 | -120.52 | 0 | 94440.48 | 0 | [6 empty] | EC10B | 100%
401721 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2013-07-23 | 2014-03-31 | 2015-01-19 | 2015-03-06 | Glasgow City | 24500.59 | 1620.85 | 1272.03 | 0 | 0 | 0 | 0 | 2892.88 | 0 | 27393.47 | 0 | [6 empty] | EC04B | 100%
401722 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2013-07-23 | 2014-03-31 | 2015-01-19 | 2015-03-06 | Glasgow City | 34998 | 1094.67 | 1238.95 | 0 | 0 | 0 | 0 | 2333.62 | 0 | 37331.62 | 466 | [6 empty] | EC04B | 100%
401635 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-27 | 2012-07-17 | 2012-11-15 | 2012-12-07 | 2013-01-17 | Renfrewshire | 84062 | 73.41 | 1453.68 | -78.876 | 17.1975 | 0 | 0 | 1465.4115 | 0 | 85527.4115 | 7804 | [6 empty] | EC10B | 100%
401723 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2013-05-22 | 2013-10-21 | 2014-10-09 | 2014-12-19 | Glasgow City | 332879 | 383 | 429.7 | 0 | 0 | 0 | 0 | 812.7 | 0 | 333691.7 | 2644 | [6 empty] | EC04B | 100%
401744 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-10-15 | 2014-11-17 | 2015-05-01 | 2015-07-01 | Glasgow City | 788607 | 79830 | 1417.71 | -1073.35 | 0 | 0 | 0 | 80174.36 | 0 | 868781.36 | 94950 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401745 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2010-12-08 | 2014-12-05 | 2015-02-18 | 2017-12-01 | 2018-02-01 | Glasgow City | 1319164 | -498084 | 416920 | 4577 | 1731 | 769 | 0 | -74087 | 0 | 1245077 | 570745 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401746 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS3 | 2010-12-15 | 2014-12-05 | 2015-07-08 | 2019-09-01 | 2019-12-01 | Glasgow City | 786743 | 3995559.65 | 3438578.12 | 1220658.21 | 4431310.11 | 2263975.24 | 210440.85 | 15560522.18 | 199189.65 | 16546454.83 | 5121897.0644 |  |  |  |  | 1689.9996 |  | EC10B | 100% | bar: Regulatory Outputs OMG-19
401747 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-10-14 | 2015-02-18 | 2015-05-01 | 2015-07-01 | Glasgow City | 46682.5 | 900.5 | 279.17 | -248.24 | 0 | 0 | 0 | 931.43 | 0 | 47613.93 | 0 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401748 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-11-28 | 2015-03-02 | 2015-03-19 | 2015-03-31 | Glasgow City | 95250.39 | 359.55 | 141.23 | 0 | 0 | 0 | 0 | 500.78 | 0 | 95751.17 | 1552 | [6 empty] | EC10B | 100%
401749 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2014-12-05 | 2015-09-09 | 2016-03-01 | 2016-03-01 | Glasgow City | 281109 | 576163 | 7347.28 | 1405.01 | -383.5175 | 0 | 0 | 584531.7725 | 0 | 865640.7725 | 516437 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401750 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2016-03-15 | 2016-03-24 | 2017-01-01 | 2017-03-01 | Glasgow City | 144601 | 349619 | 2228968.03 | 18909.29 | -1267.8925 | 0 | 0 | 2596228.4275 | 0 | 2740829.4275 | 469621 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401751 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2016-03-14 | 2016-03-24 | 2017-01-01 | 2017-03-01 | Glasgow City | 104453 | 6789 | -0.21 | 0 | 1183.9875 | 0 | 0 | 7972.7775 | 0 | 112425.7775 | 590383 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401752 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-11-28 | 2015-06-16 | 2016-03-01 | 2016-03-01 | Glasgow City | 17000 | 0 | 484 | -334.32 | 0 | 0 | 0 | 149.68 | 0 | 17149.68 | 0 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401753 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2010-12-15 | 2016-03-29 | 2016-10-31 | 2017-11-01 | 2018-02-01 | Glasgow City | 45620 | 2783 | 4302.15 | 1572.0375 | 517.9025 | 483.99 | 0 | 9659.08 | 0 | 55279.08 | 2498 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401754 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2010-12-15 | 2016-03-29 | 2016-10-31 | 2017-12-01 | 2018-03-01 | Glasgow City | 90215 | 178011 | 1500183.7 | 1821773.97 | 9711.33 | 5.01 | 0 | 3509685.01 | 0 | 3599900.01 | 410689 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401755 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2010-12-15 | 2016-03-29 | 2016-05-16 | 2017-06-01 | 2017-08-01 | Glasgow City | 106896 | 117903 | 1829168.2 | 668603.9795 | 440992.218 | 116.01 | 0 | 3056783.4075 | 0 | 3163679.4075 | 610494 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401756 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2010-12-15 | 2016-03-22 | 2016-10-10 | 2017-06-01 | 2017-08-01 | Glasgow City | 19447.73 | 2972.27 | 4223 | -2848.07 | 1558.76 | 177 | 0 | 6082.96 | 0 | 25530.69 | 4994 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401757 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2010-12-15 | 2016-03-29 | 2016-06-29 | 2017-08-01 | 2017-10-01 | Glasgow City | 95717 | 28913 | 12776.02 | 290847.51 | 1438.962 | 627 | 0 | 334602.492 | 0 | 430319.492 | 524390.0001 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401759 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2018-03-30 | 2018-03-15 | 2018-03-30 | 2018-03-30 | Glasgow City | 200227 | 18206 | 4337.77 | -4933.12 | 0 | 0 | 0 | 17610.65 | 0 | 217837.65 | 956503.0001 | [6 empty] | EC10B | 100%
401762 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2012-03-27 | 2015-01-05 | 2015-01-08 | 2015-01-08 | Glasgow City | 205924.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205924.99 | -2971 | [6 empty] | EC10B | 100%
401764 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2012-03-26 | 2015-01-05 | 2015-01-09 | 2015-01-09 | Glasgow City | 48327.85 | 50.63 | 0 | 0 | 0 | 0 | 0 | 50.63 | 0 | 48378.48 | 0 | [6 empty] | EC10B | 100%
401773 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2010-12-15 | 2016-03-22 | 2016-03-29 | 2017-05-01 | 2017-08-01 | Glasgow City | 170582 | 85200 | 1997602.51 | 424098.49 | 2637.693 | 187.01 | 0 | 2509725.703 | 0 | 2680307.703 | 743049 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401774 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2011-09-30 | 2011-09-30 | 2015-05-13 | 2015-06-08 | Glasgow City | 1596.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1596.22 | 1064 | [6 empty] | EC10B | 100%
401775 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2010-12-15 | 2016-03-14 | 2016-03-24 | 2017-05-01 | 2017-08-01 | Glasgow City | 117002 | 376543 | 2489028.09 | 653666.8625 | 11832.75 | 377 | 0 | 3531447.7025 | 0 | 3648449.7025 | 947501.0001 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401776 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2016-03-11 | 2016-03-16 | 2017-01-01 | 2017-03-01 | Glasgow City | 107379.23 | 766059.77 | 2117683.52 | -160315.69 | 38798.46 | 0 | 0 | 2762226.06 | 0 | 2869605.29 | 1002838.9999 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401782 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-05-20 | 2013-08-26 | 2014-10-09 | 2014-12-19 | Glasgow City | 696259 | -3962.11 | 1050.8 | 0 | 0 | 0 | 0 | -2911.31 | 0 | 693347.69 | 17898 | [6 empty] | EC04B | 100%
401783 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-05-16 | 2013-08-26 | 2014-10-09 | 2014-12-19 | Glasgow City | 14953 | -1459 | -100.03 | 0 | 0 | 0 | 0 | -1559.03 | 0 | 13393.97 | 0 | [6 empty] | EC04B | 100%
401784 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-05-20 | 2013-08-26 | 2014-10-09 | 2014-12-19 | Glasgow City | 14436.08 | 99.92 | 29.67 | 0 | 0 | 0 | 0 | 129.59 | 0 | 14565.67 | 0 | [6 empty] | EC04B | 100%
401785 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-05-20 | 2013-08-26 | 2014-10-09 | 2014-12-19 | Glasgow City | 14286 | -1666.93 | 0 | 0 | 0 | 0 | 0 | -1666.93 | 0 | 12619.07 | 0 | [6 empty] | EC04B | 100%
401787 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2013-05-20 | 2013-08-26 | 2014-10-09 | 2014-12-19 | Glasgow City | 14991.74 | 100.26 | -100.26 | 0 | 0 | 0 | 0 | 0 | 0 | 14991.74 | 0 | [6 empty] | EC04B | 100%
401788 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS6 | 2010-12-15 | 2016-09-14 | 2016-09-21 | 2017-05-01 | 2018-09-01 | East Renfrewshire | 204647 | 77586 | 800305 | 120942.32 | 27496.74 | 2761.29 | 0 | 1029091.35 | 0 | 1233738.35 | 480445.0001 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401789 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS5 | 2010-12-15 | 2014-05-30 | 2014-09-22 | 2018-08-01 | 2018-10-01 | South Lanarkshire | 21093880 | 32624429.96 | 55445463.24 | 11542999.6 | 4587122.19 | 239122.75 | 5084709.1 | 109523846.84 | 0 | 130617726.84 | 95337328.0001 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401790 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS5 | 2010-12-15 | 2014-05-30 | 2014-09-22 | 2018-06-01 | 2018-10-01 | South Lanarkshire | 114680 | 0 | 0 | 0 | 0 | 1093.93 | 2442.07 | 3536 | 0 | 118216 | 3443.0001 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401791 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS5 | 2010-12-15 | 2014-05-30 | 2014-09-22 | 2018-06-01 | 2018-10-01 | South Lanarkshire | 99683 | 0 | 0 | 0 | 0 | 1056.9 | 1479.1 | 2536 | 0 | 102219 | 2474 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401792 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS5 | 2010-12-15 | 2016-02-29 | 2016-06-20 | 2017-11-01 | 2018-01-01 | Renfrewshire | 18662 | -3035 | 0 | 1074.821 | 15.305 | 0 | 0 | -1944.874 | 0 | 16717.126 | 0 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401793 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-15 | 2016-08-02 | 2016-08-03 | 2016-08-01 | 2016-10-01 | Renfrewshire | 19618 | -3963 | -3298.39 | 0 | 0 | 0 | 0 | -7261.39 | 0 | 12356.61 | 0 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401794 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS4 | 2010-12-15 | 2016-02-29 | 2016-06-20 | 2018-02-01 | 2019-11-01 | Renfrewshire | 352644.32 | 279429.93 | 1066187.75 | 1139373 | 49349 | 102142.8 | 0.21 | 2636482.69 | 0 | 2989127.01 | 3345359 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401795 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS3 | 2010-12-15 | 2016-09-29 | 2017-11-13 | 2020-05-01 | 2020-07-01 | Renfrewshire | 270046 | 58430 | 95533.85 | 117437.56 | 93799.15 | 1143410.01 | 259365 | 1767975.57 | 3485.99 | 2041507.56 | 1421093 |  |  |  |  | 5210.0004 |  | EC10B | 100% | bar: Regulatory Outputs OMG-19
401798 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-04-30 | 2014-09-09 | 2015-10-01 | 2016-01-01 | Renfrewshire | 991076 | 220182 | 2999.97 | -2271.98 | 0 | 0 | 0 | 220909.99 | 0 | 1211985.99 | 17030 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401799 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-04-30 | 2014-09-09 | 2015-10-01 | 2016-01-01 | Renfrewshire | 65129.71 | 17360.29 | 50.02 | -962.31 | 0 | 0 | 0 | 16448 | 0 | 81577.71 | 4554 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401800 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-04-30 | 2014-09-09 | 2015-10-01 | 2016-01-01 | Renfrewshire | 19980 | 1001 | -0.2 | -3385.85 | 0 | 0 | 0 | -2385.05 | 0 | 17594.95 | 286.0001 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401801 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-04-28 | 2014-06-09 | 2015-10-01 | 2016-01-01 | Renfrewshire | 1001259 | 20674.94 | 685034.39 | -24037 | 0 | 0 | 0 | 681672.33 | 0 | 1682931.33 | 9017 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401803 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-08-26 | 2014-12-15 | 2015-07-01 | 2015-09-01 | Renfrewshire | 410628.39 | 104956.61 | 11290.12 | -2159.21 | 0 | 0 | 0 | 114087.52 | 0 | 524715.91 | 28238 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401804 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-08 | 2014-04-25 | 2014-11-28 | 2015-02-26 | 2015-03-25 | Renfrewshire | 121429 | 215 | 4619.03 | 2660.13 | 0 | 0 | 0 | 7494.16 | 0 | 128923.16 | 1593 | [6 empty] | EC04B | 100%
401817 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2014-02-12 | 2014-04-01 | 2016-03-01 | 2016-03-01 | Glasgow City | 1755444 | 786200 | 3632 | 0 | -463.56 | 0 | 0 | 789368.44 | 0 | 2544812.44 | 1054 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401819 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2013-07-23 | 2013-09-02 | 2014-02-27 | 2014-03-25 | Glasgow City | 916410 | 1000 | -0.08 | 0 | -3002.06 | 0 | 0 | -2002.14 | 0 | 914407.86 | 0 | [6 empty] | EC04B | 100%
401820 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-13 | 2013-07-23 | 2013-11-29 | 2014-05-29 | 2014-10-28 | Renfrewshire | 491178 | 1537.4 | 252.56 | 0 | 0 | 0 | 0 | 1789.96 | 0 | 492967.96 | 800 | [6 empty] | EC04B | 100%
401823 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-13 | 2013-03-26 | 2013-03-27 | 2015-02-26 | 2015-03-31 | Glasgow City | 27630.14 | 243.82 | 0 | 0 | 0 | 0 | 0 | 243.82 | 0 | 27873.96 | 0 | [6 empty] | EC04B | 100%
401824 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-13 | 2013-03-26 | 2013-03-27 | 2015-02-26 | 2015-03-31 | Glasgow City | 809798 | 15626.93 | 2309 | 0 | -285.5 | 0 | 0 | 17650.43 | 0 | 827448.43 | 1719 | [6 empty] | EC04B | 100%
401825 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-13 | 2013-03-27 | 2014-03-31 | 2015-02-19 | 2015-03-27 | Glasgow City | 2052217 | 20598 | 0.28 | 0 | -191.92 | 0 | 0 | 20406.36 | 0 | 2072623.36 | 2187 | [6 empty] | EC04B | 100%
401826 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-13 | 2013-03-28 | 2013-03-28 | 2015-02-19 | 2015-03-27 | Glasgow City | 25936.31 | 13.69 | 1240.69 | 0 | -388.69 | 0 | 0 | 865.69 | 0 | 26802 | 0 | [6 empty] | EC04B | 100%
401827 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-13 | 2013-03-28 | 2013-03-28 | 2015-02-19 | 2015-03-27 | Glasgow City | 27121 | 694 | 134.89 | 0 | -239.6 | 0 | 0 | 589.29 | 0 | 27710.29 | 0 | [6 empty] | EC04B | 100%
401828 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-12-13 | 2013-03-27 | 2013-03-27 | 2014-01-28 | 2014-03-25 | Glasgow City | 2880550 | 2087.82 | 1740.45 | 7591.22 | -7591.22 | 0 | 0 | 3828.27 | 0 | 2884378.27 | 482 | [6 empty] | EC04B | 33.42% | CS15 | 66.58%
401829 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-13 | 2013-07-08 | 2013-11-27 | 2014-03-12 | 2014-03-28 | Glasgow City | 369585 | 0 | 700 | 0 | -7519.52 | 0 | 0 | -6819.52 | 0 | 362765.48 | 348 | [6 empty] | EC04B | 100%
401830 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2013-05-29 | 2014-01-06 | 2014-08-14 | 2015-03-19 | Glasgow City | 12882 | 0 | 0 | 0 | -679.5 | 0 | 0 | -679.5 | 0 | 12202.5 | 0 | [6 empty] | EC04B | 100%
401831 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2013-05-13 | 2014-01-13 | 2014-08-14 | 2015-03-19 | Glasgow City | 897049 | 54620 | 0 | 0 | -7924.08 | 0 | 0 | 46695.92 | 0 | 943744.92 | 0 | [6 empty] | EC04B | 100%
401832 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2013-05-15 | 2014-01-20 | 2014-08-14 | 2015-02-16 | Glasgow City | 876360 | 0 | 0 | 0 | -4073.78 | 0 | 0 | -4073.78 | 0 | 872286.22 | 0 | [6 empty] | EC04B | 100%
401833 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2013-06-27 | 2013-06-28 | 2016-10-01 | 2016-12-01 | Glasgow City | 5747.47 | 194.82 | 70.98 | 0 | 0 | 0 | 0 | 265.8 | 0 | 6013.27 | 0 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401834 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-12-09 | 2013-06-26 | 2013-06-28 | 2016-10-01 | 2016-12-01 | Glasgow City | 1061129 | 5312.37 | 170340.69 | 25443.01 | 29448.9825 | 0 | 0 | 230545.0525 | 0 | 1291674.0525 | 4525 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401835 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2010-12-09 | 2014-03-19 | 2014-03-24 | 2014-06-10 | 2015-02-04 | Glasgow City | 648671 | 27135 | 0.27 | 0 | 51000 | 0 | 0 | 78135.27 | 0 | 726806.27 | 27137.9999 | [6 empty] | EC04B | 100%
401671 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-11-27 | 2015-04-10 | 2015-04-22 | 2015-04-29 | 2015-06-08 | Glasgow City | 150546.22 | 2025.77 | 0 | 0 | 0 | 0 | 0 | 2025.77 | 0 | 152571.99 | 0 | [6 empty] | EC10B | 100%
401960 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2011-03-21 | 2013-05-24 | 2013-09-16 | 2014-08-11 | 2014-12-19 | Glasgow City | 418129 | -2286 | -284 | 0 | 0 | 0 | 0 | -2570 | 0 | 415559 | 2581 | [6 empty] | EC04B | 100%
401961 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS6 | 2011-03-21 | 2016-12-20 | 2017-01-20 | 2017-08-01 | 2017-10-01 | Glasgow City | 18502 | 23413 | 85812 | 157793 | 2078.45 | 0 | 0 | 269096.45 | 0 | 287598.45 | 12883 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401962 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS5 | 2011-03-21 | 2013-03-26 | 2017-03-29 | 2019-02-01 | 2019-03-01 | Glasgow City | 52000 | 0 | 29972 | 278718.57 | 28297 | 276.02 | 371.4 | 337634.99 | 352.6 | 389987.59 | 67739 | [6 empty] | EC04B | 100% | bar: Regulatory Outputs OMG-19
401967 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS3 | 2011-03-21 | 2017-12-21 | 2017-12-22 | 2019-02-01 | 2019-03-01 | Glasgow City | 60000 | 1621.48 | 616641.52 | 1944337 | 3406564 | 2261818.01 | 3554.66 | 8234536.67 | 5463.39 | 8300000.06 | 529643 |  |  |  |  | 21270 |  | EC04B | 38% | CM_WWNI | 62% | bar: Regulatory Outputs OMG-19
401969 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2011-03-21 | 2016-03-29 | 2016-11-07 | 2017-06-01 | 2017-08-01 | Glasgow City | 43268.4 | 2070.6 | 6763.8 | -6064.8 | 1495 | 396.99 | 0 | 4661.59 | 0 | 47929.99 | 6434 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
401970 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2011-03-21 | 2016-03-14 | 2016-03-24 | 2017-01-01 | 2017-03-01 | Glasgow City | 31764 | -134 | -0.43 | 0 | 180.8605 | 0 | 0 | 46.4305 | 0 | 31810.4305 | 2968 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
402483 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2011-11-16 | 2013-05-27 | 2013-08-19 | 2014-03-21 | 2014-03-31 | Glasgow City | 727845 | 0 | -0.1 | 0 | -5160.89 | 0 | 0 | -5160.99 | 0 | 722684.01 | 0 | [6 empty] | EC04B | 100%
402491 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2011-12-14 | 2013-05-16 | 2013-08-12 | 2014-01-10 | 2014-02-03 | Glasgow City | 2855 | 573.29 | -471.46 | 0 | 0 | 0 | 0 | 101.83 | 0 | 2956.83 | 145 | [6 empty] | EC04B | 100%
402752 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-06-28 | 2013-03-20 | 2013-05-20 | 2013-08-30 | 2013-11-28 | East Renfrewshire | 180757 | -141.27 | 0 | 0 | 0 | 0 | 0 | -141.27 | 0 | 180615.73 | 515 | [6 empty] | EC04B | 100%
402753 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS3 | 2012-06-28 | 2016-03-15 | 2016-03-22 | 2019-12-01 | 2020-03-01 | Glasgow City | 90623 | 225799 | 99356.3 | 9696.78 | 0 | 1139659.6 | 38630.24 | 1513141.92 | 3279.14 | 1607044.06 | 1636394 |  |  |  |  | 1800 |  | EC10B | 100% | bar: Regulatory Outputs OMG-19
402830 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-31 | 2013-03-20 | 2013-03-28 | 2013-11-26 | 2014-01-30 | Renfrewshire | 96583 | 461.12 | 0 | 0 | 0 | 0 | 0 | 461.12 | 0 | 97044.12 | 267 | [6 empty] | EC04B | 100%
402831 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-31 | 2013-03-20 | 2013-03-28 | 2013-08-30 | 2013-11-25 | Renfrewshire | 93481 | -331.14 | 0 | 0 | 0 | 0 | 0 | -331.14 | 0 | 93149.86 | 159 | [6 empty] | EC04B | 100%
402832 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-31 | 2015-03-25 | 2015-03-25 | 2015-03-25 | 2015-03-27 | Renfrewshire | 22980.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22980.29 | 53754 | [6 empty] | EC04B | 100%
402755 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | WWINF | OMG180 | MS4 | 2012-07-10 | 2017-12-20 | 2018-03-26 | 2019-03-01 | 2019-07-01 | Glasgow City | 88596.93 | 58103.29 | 23592.16 | 508965.62 | 901187 | 0.01 | 514.99 | 1492363.07 | 0 | 1580960 | 1127279 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
402756 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-10 | 2013-03-20 | 2013-03-28 | 2013-11-26 | 2014-01-21 | Glasgow City | 98331.76 | 675.03 | 0 | 0 | 0 | 0 | 0 | 675.03 | 0 | 99006.79 | 260 | [6 empty] | EC10B | 100%
402757 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-10 | 2015-02-27 | 2015-06-29 | 2015-10-01 | 2016-01-01 | Glasgow City | 161661 | 199818 | 1358.71 | -1506.28 | 0 | 0 | 0 | 199670.43 | 0 | 361331.43 | 295069 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
402758 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-10 | 2015-02-27 | 2015-08-07 | 2015-12-01 | 2016-01-01 | Glasgow City | 219495 | 324824 | 908.73 | 147.24 | 0 | 0 | 0 | 325879.97 | 0 | 545374.97 | 396268 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
402759 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-10 | 2015-02-27 | 2015-06-18 | 2015-10-01 | 2016-01-01 | West Dunbartonshire | 154731 | 194867.75 | 6.59 | -69.25 | 0 | 0 | 0 | 194805.09 | 0 | 349536.09 | 221953 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
402760 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-10 | 2015-02-26 | 2015-05-18 | 2015-10-01 | 2016-01-01 | West Dunbartonshire | 144915 | 265170.34 | 1647.6 | -301.32 | 0 | 0 | 0 | 266516.62 | 0 | 411431.62 | 326098 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-19
402833 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-31 | 2014-12-22 | 2015-01-12 | 2015-03-30 | 2015-03-31 | Glasgow City | 818636.97 | 167645.96 | 2436.75 | -305.5 | 0 | 0 | 0 | 169777.21 | 0 | 988414.18 | 2594 | [6 empty] | EC04B | 100%
402834 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-07-31 | 2014-10-31 | 2014-11-06 | 2015-02-19 | 2015-03-23 | Glasgow City | 499757.51 | 131962.49 | -123.67 | 0 | 0 | 0 | 0 | 131838.82 | 0 | 631596.33 | 2800 | [6 empty] | EC04B | 100%
403140 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2012-12-18 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 2015-04-30 | Glasgow City | 2239336.14 | 1650.48 | 0 | 0 | 0 | 0 | 0 | 1650.48 | 0 | 2240986.62 | 5002 | [6 empty] | EC10B | 100%
403362 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-03-18 | 2013-05-16 | 2013-10-21 | 2014-01-17 | 2014-03-20 | Glasgow City | 82514 | -3298.09 | 198.8 | 0 | 0 | 0 | 0 | -3099.29 | 0 | 79414.71 | 3916 | [6 empty] | EC04B | 100%
403474 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-05-13 | 2014-08-29 | 2014-09-01 | 2014-09-03 | 2014-10-27 | Glasgow City | 9904.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9904.75 | 438 | [6 empty] | EC10B | 100%
403564 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-08-27 | 2014-11-28 | 2014-12-03 | 2015-01-12 | 2015-02-27 | Glasgow City | 17536 | 7714 | -4718.24 | 0 | 0 | 0 | 0 | 2995.76 | 0 | 20531.76 | 7936 | [6 empty] | EC10B | 100%
403689 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2014-01-30 | 2014-07-22 | 2014-08-11 | 2014-08-28 | 2014-10-27 | Glasgow City | 16261 | 1031.62 | 0 | 0 | 0 | 0 | 0 | 1031.62 | 0 | 17292.62 | 393.0001 | [6 empty] | EC04B | 100%
404009 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MS7 | 2014-11-27 | 2015-02-27 | 2017-06-15 | 2017-05-18 | 2017-05-18 | Renfrewshire | 191106 | 618.08 | 6300 | -1381.27 | 0 | 0 | 0 | 5536.81 | 0 | 196642.81 | 618547 | [6 empty] | EC10B | 100%
502608 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2017-10-31 | 2018-08-30 | 2018-10-26 | 2019-09-25 | 2019-09-26 | Scottish Water Wide | 0 | 0 | 1555.14 | 90171.95 | 120274.29 | 44074.62 | 0 | 256076 | 0 | 256076 | 0 | [6 empty] | CM_M&G | 100%
503371 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-05-09 | 2023-03-16 | 2023-07-19 | 2024-01-09 | 2024-04-10 | Fife | 0 | 0 | 0 | 0 | 77497.489 | 13617.11 | 25028.53 | 116143.129 | 29789.12 | 145932.249 | 148885.7057 | [6 empty] | SG1 | 100%
030737 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-09-08 | 2012-01-24 | 2012-06-11 | 2013-06-20 | 2013-07-12 | North Lanarkshire | 2346209.8 | -3846.6 | 0 | 0 | 0 | 0 | 0 | -3846.6 | 0 | 2342363.2 | 5903.4228 | [6 empty] | CM_WWNI | 20% | EC04A | 20% | EC10B | 25% | EC10A | 35%
403547 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-09-23 | 2015-02-16 | 2015-04-22 | 2015-06-18 | 2015-06-18 | North Ayrshire | 134499 | 5450.97 | 0 | 0 | 0 | 0 | 0 | 5450.97 | 0 | 139949.97 | 30819 | [6 empty] | EC16A | 100%
501653 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2016-07-19 | 2018-03-29 | 2018-08-27 | 2019-08-14 | 2019-08-14 | North Ayrshire | 0 | 0 | 45064 | 402621 | 2392014 | 376705 | 0 | 3216404 | 0 | 3216404 | 0 | [6 empty] | CM_WWNI | 100%
402938 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-10-30 | 2015-02-13 | 2015-01-15 | 2015-01-16 |  | North Ayrshire | 46432 | -1200.52 | 0 | 0 | 0 | 0 | 0 | -1200.52 | 0 | 45231.48 | 0 | [6 empty] | CM_WWNI | 100%
503445 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2019-01-23 | 2019-01-23 | 2019-05-01 | 2019-12-20 | 2020-02-06 | Scottish Water Wide | 0 | 0 | 0 | 0 | 26228.6575 | 271915.15 | 1728.71 | 299872.5175 | 1237.66 | 301110.1775 | 0 | [6 empty] | CM_WSNI | 100%
500952 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-10-12 | 2015-12-14 | 2015-12-14 | 2016-08-11 |  | Scottish Water Wide | 0 | 59841 | 46252.81 | 0 | 0 | 0 | 0 | 106093.81 | 0 | 106093.81 | 0 | [6 empty] | CM_M&G | 100%
045809 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2012-07-09 | 2012-12-03 | 2013-03-25 | 2013-03-26 | Na H-Eileanan an Iar | 511272.82 | -1112.93 | 142.84 | 0 | 0 | 0 | 0 | -970.09 | 0 | 510302.73 | 0 | [6 empty] | WQ01C | 100%
500871 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-09-20 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Orkney Islands | 0 | 1866.84 | 3808.48 | 7110 | -7021.6 | 0 | 0 | 5763.72 | 0 | 5763.72 | 130344.3601 | [6 empty] | DW5FS | 100%
501258 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2016-07-29 | 2018-02-28 | 2018-04-26 | 2020-04-07 | 2020-07-03 | Orkney Islands | 0 | 2924.96 | 74994.65 | 192461.77 | 268030.77 | 641374.08 | 27970.34 | 1207756.57 | 6433.36 | 1214189.93 | 0 | [6 empty] | CM_WSNI | 100%
501211 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | GW1 | 2019-06-20 | 2020-10-26 | 2020-12-11 | 2021-09-01 | 2022-01-01 | Orkney Islands | 0 | 5860.47 | 417.88 | 5605.82 | 108269.1025 | 27000.48 | 154621.03 | 301774.7825 | 255523.78 | 557298.5625 | 99146.6083 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
501539 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2022-10-17 | 2023-08-25 | 2023-12-29 | 2024-08-14 | 2024-11-14 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286838.02 | 286838.02 | 0 | [6 empty] | CM_WSNI | 100%
402989 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-10-01 | 2012-12-04 | 2013-02-25 | 2013-10-31 | 2013-10-31 | Aberdeenshire | 82983 | -955.58 | 0 | 0 | 0 | 0 | 0 | -955.58 | 0 | 82027.42 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
503261 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-31 | 2023-07-14 | 2023-11-14 | 2024-11-08 | 2025-02-10 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 87156.36 | 0 | 31516.35 | 118672.71 | 26611.14 | 145283.85 | 148885.7057 | [6 empty] | SG1 | 100%
503407 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2021-04-01 | 2021-04-29 | 2021-05-20 | 2022-01-12 | 2022-04-14 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395999.96 | 395999.96 | 0 | [6 empty] | CM_M&G | 18.75% | CM_WWNI | 37.5% | CM_WWI | 43.75%
050011 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MSU | 2019-04-01 | 2019-04-01 | 2019-04-01 | 2020-12-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | DW25 | 100% | bar: Regulatory Outputs OMG-47
500018 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-02-04 | 2016-06-17 | 2016-06-20 | 2016-06-23 | 2016-06-30 | Shetland Islands | 0 | 28198 | -11247.84 | 6161.24 | 0 | 0 | 0 | 23111.4 | 0 | 23111.4 | 0 | [6 empty] | CM_WSI | 100%
502311 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2016-09-14 | 2022-04-01 | 2022-04-08 | 2023-02-20 | 2023-05-23 | Shetland Islands | 0 | 0 | 7599 | 1761 | 439 | 0 | 0 | 9799 | 1109701 | 1119500 | 0 | [6 empty] | CM_WSI | 100%
500087 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-03-13 | 2016-06-17 | 2016-07-27 | 2016-07-12 | 2016-07-27 | Shetland Islands | 0 | 15268.37 | -9407.2 | 5115.33 | 0 | 0 | 0 | 10976.5 | 0 | 10976.5 | 0 | [6 empty] | CM_WSI | 100%
500086 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2015-03-13 | 2016-08-30 | 2016-10-13 | 2017-06-21 | 2017-06-21 | Shetland Islands | 0 | 24797 | 107380.1 | 12320.08 | 4798.05 | 0 | 0 | 149295.23 | 0 | 149295.23 | 0 | [6 empty] | CM_WSI | 100%
501067 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2016-04-06 | 2023-06-01 | 2023-07-13 | 2025-06-11 | 2025-08-06 | Shetland Islands | 0 | 94092 | -31736 | 50644 | 76644.9 | 0 | 0 | 189644.9 | 2268135.15 | 2457780.05 | 0 | [6 empty] | CM_WSI | 100%
501066 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | Shetland Islands | 0 | 26770.15 | -26770.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
500958 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2015-09-11 | 2018-05-31 | 2018-07-30 | 2020-01-20 | 2020-03-17 | Shetland Islands | 0 | 31155 | 141879.91 | 170683.805 | 514217.505 | 1008156.18 | 9292.22 | 1875384.62 | 7484.38 | 1882869 | 0 |  |  |  |  | 4749.9996 |  | CM_WSNI | 100%
500872 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-08-03 | 2018-08-29 | 2018-11-27 | 2019-03-01 | 2019-12-01 | Highland | 0 | 544.89 | 2224.49 | 2000 | 22298.49 | 8868.01 | 1010.46 | 36946.34 | 0 | 36946.34 | 9712.8806 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 3.36
502624 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-03 | 2027-11-11 | 2028-01-18 | 2028-12-25 | 2029-03-27 | Highland | 0 | 0 | 20930.23 | 520.75 | 1385.35 | 12091.71 | 12044.86 | 46972.9 | 4953031.15 | 5000004.05 | 148885.7057 | [6 empty] | WG1 | 100%
503219 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-05 | 2023-06-20 | 2023-10-13 | 2024-10-09 | 2025-01-09 | Aberdeenshire | 0 | 0 | 0 | 0 | 83105.48 | 10510.25 | 32543.65 | 126159.38 | 25199.17 | 151358.55 | 148885.7057 | [6 empty] | SG1 | 100%
500841 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS6 | 2015-10-28 | 2016-02-23 | 2016-03-28 | 2017-02-01 | 2018-04-01 | Highland | 0 | 14190 | 36371.91 | 18098.2446 | 18743.0454 | 1000.02 | 0 | 88403.22 | 0 | 88403.22 | 145636.593 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 46.84
502281 | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater |  | SWMD | Sludge | MS2 | 2017-06-27 | 2019-02-28 | 2020-04-13 | 2021-05-01 | 2021-07-01 | Highland | 0 | 0 | 20223.16 | 12546.72 | 49851.0365 | 70219.62 | 394079.99 | 546920.5265 | 135837.94 | 682758.4665 | 288017.4877 | [6 empty] | LA01 | 100% | bar: Regulatory Outputs OMG-24
045715 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-07-18 | 2012-03-01 | 2012-03-30 | Highland | 83209.32 | 27 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 83236.32 | 0 | [6 empty] | DW13 | 100%
402945 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-10-01 | 2014-08-28 | 2014-09-18 | 2015-01-28 | 2015-01-28 | Glasgow City | 626693 | 45583 | -1238.03 | -3965.49 | 0 | 0 | 0 | 40379.48 | 0 | 667072.48 | 229318.7788 | [6 empty] | CS11 | 100%
502353 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS3 | 2016-11-08 | 2016-11-08 | 2016-12-01 | 2019-09-27 | 2019-09-27 | Scottish Water Wide | 0 | 0 | 252242.41 | 0 | 35863.2 | 41000 | 0 | 329105.61 | 0 | 329105.61 | 0 | [6 empty] | CM_M&G | 100%
500489 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-06-05 | 2015-06-05 | 2015-06-05 | 2021-06-30 | 2021-06-30 | Scottish Water Wide | 0 | 1110480 | 537819 | 422903 | 973286 | 589000 | 286512 | 3920000 | 0 | 3920000 | 0 | [6 empty] | CM_M&G | 100%
400606 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-03-29 | 2011-01-13 | 2011-05-02 | 2015-11-10 |  | Scottish Water Wide | 956683 | -4390.95 | 871.25 | 0 | 0 | 0 | 0 | -3519.7 | 0 | 953163.3 | 0 | [6 empty] | CM_M&G | 100%
400607 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-03-31 | 2011-01-13 | 2011-05-02 | 2015-11-10 |  | Scottish Water Wide | 895136.6 | 38255.6 | 0 | 0 | 0 | 0 | 0 | 38255.6 | 0 | 933392.2 | 0 | [6 empty] | CM_M&G | 100%
503380 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-14 | 2022-12-22 | 2023-04-26 | 2023-10-17 | 2024-01-17 | Perth and Kinross | 0 | 0 | 0 | 0 | 79058.58 | 0 | 6430.03 | 85488.61 | 63461.64 | 148950.25 | 148885.7057 | [6 empty] | SG1 | 100%
502868 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW1 | 2021-04-01 | 2022-06-08 | 2022-09-30 | 2023-05-19 | 2023-08-21 | Fife | 0 | 0 | 0 | 34014.48 | 16801.345 | 10157.37 | 13229.17 | 74202.365 | 713259.99 | 787462.355 | 0 | [6 empty] | CM_WWNI | 100%
400061 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-12-07 | 2010-11-05 | 2011-01-26 | 2016-03-22 |  | Scottish Water Wide | 1014081.54 | 82778.69 | -31127.98 | 662.28 | 0 | 0 | 0 | 52312.99 | 0 | 1066394.53 | 0 | [6 empty] | CM_WSI | 100%
500930 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2017-01-31 | 2017-01-31 | 2016-12-16 | 2017-01-31 | Scottish Borders | 0 | 5927.7 | 1778.05 | 0 | 0 | 0 | 0 | 7705.75 | 0 | 7705.75 | 144841.4737 | [6 empty] | CS15A | 100%
045413 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-06-21 | 2010-06-28 | 2013-01-28 | 2016-04-01 | Scottish Water Wide | 3815887.15 | -506.11 | 0 | 0 | 0 | 0 | 0 | -506.11 | 0 | 3815381.04 | 0 | [6 empty] | DW11 | 100%
009617 | Q&S2 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 |  | 2004-03-24 | 2005-03-31 | 2006-03-31 |  | Scottish Water Wide | 3841386.28 | 0 | 139 | 0 | 0 | 0 | 0 | 139 | 0 | 3841525.28 | 0 | [6 empty] | SM3 | 100%
500873 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-08-29 | 2018-08-29 | 2018-11-27 | 2019-03-01 | 2020-03-01 | Highland | 0 | 564.92 | 1604.84 | 757.24 | 14833.16 | 8411.4 | 1467.1 | 27638.66 | 0 | 27638.66 | 12504.2586 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 4.46
500629 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 698481.79 | 1609278.26 | 1594575.7495 | 1448356.4625 | 0 | 0 | 5350692.262 | 0 | 5350692.262 | 0 | [6 empty] | CM_OVH | 100%
500628 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 254433.96 | 747731.44 | 1683188.34 | 1934990.32 | 0 | 0 | 4620344.06 | 0 | 4620344.06 | 0 | [6 empty] | CM_OVH | 100%
500627 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 111843.89 | 154129.87 | 104825.8897 | 483156.7865 | 0 | 0 | 853956.4362 | 0 | 853956.4362 | 0 | [6 empty] | CM_OVH | 100%
500626 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 345933.08 | 380937.92 | 1156929.1991 | 1272922.78 | 0 | 0 | 3156722.9791 | 0 | 3156722.9791 | 0 | [6 empty] | CM_OVH | 100%
403016 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS4 | 2012-11-30 | 2013-09-30 | 2013-11-04 | 2018-03-02 |  | Scottish Borders | 375274 | 42500 | 79941.88 | 386399.12 | 8000 | 0 | 0 | 516841 | 0 | 892115 | 0 | [6 empty] | CM_WWNI | 100%
500668 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2019-07-15 | 2019-07-15 | 2019-07-15 | 2019-07-15 | 2019-07-15 | Dumfries and Galloway | 0 | 56912 | 27890.84 | 54138.0371 | 31293.1229 | 84766 | 0 | 255000 | 0 | 255000 | 229318.7788 | [6 empty] | CS11 | 100%
500011 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW2 | 2020-04-01 | 2020-10-19 | 2021-01-08 | 2021-01-08 | 2021-02-18 | Scottish Borders | 0 | 44707 | -40777.53 | 12070.53 | 129000 | 39999.99 | 91841.49 | 276841.48 | 6222.52 | 283064 | 277530.2517 | [6 empty] | CS11 | 100%
403236 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS6 | 2013-01-23 | 2016-03-22 | 2016-05-13 | 2016-12-21 | 2017-03-14 | South Lanarkshire | 110784 | 454700 | 2086522.01 | 32985.99 | 15884 | 0 | 0 | 2590092 | 0 | 2700876 | 760005.9708 | [6 empty] | CS11 | 20% | EC01F | 80%
500654 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS0 | 2018-07-09 | 2020-01-27 | 2020-04-06 | 2020-10-08 | 2021-01-22 | Dumfries and Galloway | 0 | 80610 | 27390 | 23558.3831 | 104352.6169 | 258873.17 | 741799.13 | 1236583.3 | 6416.66 | 1242999.96 | 229318.7788 | [6 empty] | CS11 | 100%
502582 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2019-07-08 | 2020-01-29 | 2020-01-29 | 2020-01-29 | 2020-01-29 | Scottish Borders | 0 | 0 | 44060.47 | 11939.53 | 31000 | 86999.99 | 0 | 173999.99 | 0 | 173999.99 | 240495.8008 | [6 empty] | CS11A | 100%
502581 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-05-11 | 2021-04-30 | 2021-07-20 | 2022-02-21 | 2022-05-24 | Scottish Borders | 0 | 0 | 43060.47 | 4938.53 | 61481.3415 | 9273.72 | 9311.21 | 128065.2715 | 313415.04 | 441480.3115 | 240495.8008 | [6 empty] | CS11A | 100%
502583 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2019-06-04 | 2019-06-17 | 2019-04-08 | 2019-05-17 | 2019-05-20 | Scottish Borders | 0 | 0 | 43060.47 | 13939.53 | 36000 | 20000 | 0 | 113000 | 0 | 113000 | 240495.8008 | [6 empty] | CS11A | 100%
500652 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS0 | 2018-03-14 | 2019-10-07 | 2020-01-06 | 2020-12-16 | 2021-04-01 | Scottish Borders | 0 | 77062 | 86857.1 | 102921.7081 | 240277.1919 | 1270532.53 | 1744145.5 | 3521796.03 | 264121.05 | 3785917.08 | 229318.7788 | [6 empty] | CS11 | 100%
403549 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2013-09-23 | 2017-08-03 | 2017-07-19 | 2017-02-03 | 2017-07-31 | North Ayrshire | 53726 | 12272 | 25829.05 | -3151.75 | 0 | 0 | 0 | 34949.3 | 0 | 88675.3 | 131547 | [6 empty] | EC16A | 100%
500683 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2015-06-03 | 2016-03-01 | 2016-05-31 | 2017-02-10 | 2017-02-10 | Aberdeen City | 0 | 85178.25 | 153604.75 | 20995 | -7541.0021 | 0 | 0 | 252236.9979 | 0 | 252236.9979 | 0 | [6 empty] | CM_WWNI | 100%
500594 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2016-03-14 | 2016-09-09 | 2016-09-09 | 2021-05-31 | 2021-06-01 | Scottish Water Wide | 0 | 169798 | 190517.85 | 163053.01 | 78768.54 | 105600 | 126651 | 834388.4 | 2 | 834390.4 | 0 | [6 empty] | CM_M&G | 100%
404035 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2015-02-03 | 2015-09-08 | 2015-09-21 | 2016-03-23 | 2016-03-23 | Scottish Water Wide | 13813.01 | 2772140.99 | 376570 | 2229.476 | 78.75 | 0 | 0 | 3151019.216 | 0 | 3164832.226 | 2627561.9999 | [6 empty] | CM_WSNI | 48% | DW9A | 52%
500990 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS3 | 2015-11-17 | 2016-09-21 | 2016-09-21 | 2019-05-01 | 2019-05-01 | Scottish Water Wide | 0 | 200064 | 2211188.52 | 599023.99 | 493120.83 | 29490.5 | 0 | 3532887.84 | 0 | 3532887.84 | 0 |  |  |  |  | 739677.27 |  | CM_M&G | 100%
404034 | Q&S3A | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS6 | 2015-02-27 | 2015-09-24 | 2015-11-09 | 2018-03-29 | 2018-03-29 | Scottish Water Wide | 9088 | 337398 | 1064498.59 | -251032.1 | 0 | 2154.19 | 3845.81 | 1156864.49 | 0 | 1165952.49 | 2919520.9999 | [6 empty] | DW9A | 100%
501640 | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWD | SEMD | MS7 | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-03-30 | 2016-03-31 | Scottish Water Wide | 0 | 8000 | 3007.49 | 11168.13 | 0 | 0 | 0 | 22175.62 | 0 | 22175.62 | 183369.5948 | [6 empty] | DW9F | 100%
501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWMD | SEMD | MS6 | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-29 | 2018-07-27 | Scottish Water Wide | 0 | 95883 | 179559.77 | 1111586.81 | 8418.51 | 5701.62 | 5679.55 | 1406829.26 | 618.79 | 1407448.05 | 920691.6252 | [6 empty] | DW9F | 100%
501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWMD | SEMD | MS5 | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-17 | 2019-03-29 | Scottish Water Wide | 0 | 0 | 36386.12 | 261448.1 | 333655.96 | 4497.32 | 2778.41 | 638765.91 | 2724.35 | 641490.26 | 928743.807 | [6 empty] | DW9F | 100%
501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWMD | SEMD | MS3 | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-07-29 | 2019-10-29 | Scottish Water Wide | 0 | 0 | 17790.14 | 298445.85 | 1506511.65 | 231098.35 | 4027.61 | 2057873.6 | 1269.41 | 2059143.01 | 954962.8868 | [6 empty] | CM_WSNI | 5.869% | DW9F | 94.13%
501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWMD | SEMD | MS3 | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-14 | 2020-10-14 | Scottish Water Wide | 0 | 0 | 65391.05 | 65357.95 | 284295.52 | 1469253.38 | 200671.96 | 2084969.86 | 5580.96 | 2090550.82 | 964035.1518 | [6 empty] | CM_WSNI | 3.257% | DW9F | 96.74%
402766 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2012-06-12 | 2012-06-12 | 2012-07-02 | 2017-06-26 |  | Scottish Water Wide | 31837 | 964 | 0.02 | -1882.99 | 0 | 0 | 0 | -918.97 | 0 | 30918.03 | 15177 | [6 empty] | DW9A | 100%
402626 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2012-07-13 | 2012-10-25 | 2012-10-25 | 2015-03-23 |  | Scottish Water Wide | 372475.24 | 1462.5 | 0 | 0 | 0 | 0 | 0 | 1462.5 | 0 | 373937.74 | 0 | [6 empty] | CM_M&G | 100%
500703 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater |  | SWMD | Compliance Assessment Scheme | MS7 | 2015-12-21 | 2016-05-25 | 2016-05-30 | 2016-08-22 | 2017-03-15 | Scottish Water Wide | 0 | 18717 | 8318.02 | 0 | 0 | 0 | 0 | 27035.02 | 0 | 27035.02 | 173787.447 | [6 empty] | WQ01E | 100%
501622 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater |  | SWMD | Compliance Assessment Scheme | MS6 | 2015-12-21 | 2016-09-26 | 2016-09-29 | 2017-10-31 | 2018-01-15 | Scottish Water Wide | 0 | 886 | 34841.12 | 10591.935 | -3701.525 | 0 | 0 | 42617.53 | 0 | 42617.53 | 173787.447 | [6 empty] | WQ01E | 100%
500702 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater |  | SWMD | Compliance Assessment Scheme | MS7 | 2015-12-21 | 2016-06-27 | 2016-06-29 | 2016-12-06 | 2017-03-31 | Scottish Water Wide | 0 | 20910 | 47724.9 | 410.1 | 0 | 0 | 0 | 69045 | 0 | 69045 | 208853.939 | [6 empty] | WQ01D | 100%
501621 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme |  |  | Wastewater |  | SWMD | Compliance Assessment Scheme | MS3 | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2019-05-07 | 2019-07-30 | Scottish Water Wide | 0 | 3395.51 | 47007.8 | 528530.82 | 580214.06 | 81525.17 | 3609.53 | 1244282.89 | 4971.89 | 1249254.78 | 208853.939 | [6 empty] | WQ01D | 100%
404116 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS5 | 2015-03-18 | 2015-03-18 | 2015-03-18 | 2017-04-06 | 2017-04-06 | Scottish Water Wide | 49974 | -48389.36 | 124839.62 | -12526.25 | 0 | 0 | 0 | 63924.01 | 0 | 113898.01 | 0 | [6 empty] | WWI | 100%
050014 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 18883205.253 | 18883205.253 | 0 | 18883205.253 | 0 | [6 empty] | CM_WSNI | 100%
503293 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS0 | 2018-07-17 | 2019-09-09 | 2019-09-16 | 2020-01-30 | 2020-01-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 1096017.89 | 3632802.11 | 168180 | 4897000 | 0 | 4897000 | 0 | [6 empty] | CM_M&G | 100%
403623 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-12-24 | 2014-04-11 | 2014-04-11 | 2015-01-13 |  | Scottish Water Wide | 210531.99 | -1260.34 | 0 | 0 | 0 | 0 | 0 | -1260.34 | 0 | 209271.65 | 0 | [6 empty] | CM_M&G | 100%
501937 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2016-02-23 | 2017-08-29 | 2017-08-30 | 2018-06-28 | 2018-06-28 | Dumfries and Galloway | 0 | 1185.3 | 14452.93 | 507088.35 | 310346.98 | 8574.68 | 10155.27 | 851803.51 | 5057.87 | 856861.38 | 0 | [6 empty] | CM_WSI | 100%
502397 | Q&S4 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWD | Revised Bathing Waters Directive | MS3 | 2017-01-31 | 2017-01-31 | 2017-03-01 | 2019-07-19 | 2019-07-19 | Scottish Water Wide | 0 | 0 | 9158.88 | 1212 | 343.12 | 129286 | 0 | 140000 | 0 | 140000 | 0 | [6 empty] | EC16B | 100%
502604 | Q&S4 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | Wastewater |  | SWD | Revised Bathing Waters Directive | GW2 | 2020-07-15 | 2020-07-15 | 2020-07-15 | 2020-07-15 | 2020-07-15 | Scottish Water Wide | 0 | 0 | 176912.11 | 122631.9053 | 39482.1247 | 57476.58 | 16708.3 | 413211.02 | 0 | 413211.02 | 0 | [6 empty] | EC16B | 100%
402536 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-02-29 | 2013-11-18 | 2014-01-31 | 2014-06-18 | 2014-06-18 | Dumfries and Galloway | 585684 | -46812 | -1476.24 | 0 | 0 | 0 | 0 | -48288.24 | 0 | 537395.76 | 1105.1999 | [6 empty] | CM_WWI | 40% | CS11A | 60%
402362 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-10-13 | 2013-10-17 | 2013-11-11 | 2014-02-10 | 2014-02-10 | Perth and Kinross | 390503 | -3508.64 | 72.06 | 0 | 0 | 0 | 0 | -3436.58 | 0 | 387066.42 | 0 | [6 empty] | CM_WWI | 40% | CS11A | 60%
402197 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS1 | 2011-06-10 | 2019-07-01 | 2019-09-24 | 2020-05-07 | 2020-08-11 | North Lanarkshire | 330000 | 145015 | 174951 | 113180 | 152439 | 1915074.61 | 413260.51 | 2913920.12 | 79.88 | 3244000 | 229318.7788 | [6 empty] | CS11 | 100%
403498 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS5 | 2013-10-04 | 2013-10-04 | 2013-10-07 | 2019-02-25 | 2019-02-25 | Scottish Water Wide | 27439.02 | 17534.02 | 270016.37 | -111992.365 | 35941.531 | 0 | 0 | 211499.556 | 0 | 238938.576 | 0 | [6 empty] | CM_WWNI | 100%
402533 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-02-28 | 2012-05-25 | 2013-04-22 | 2013-08-01 |  | South Lanarkshire | 52542 | -528.67 | 0 | 0 | 0 | 0 | 0 | -528.67 | 0 | 52013.33 | 0 | [6 empty] | CM_WWI | 100%
402236 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-07-22 | 2014-04-02 | 2014-04-02 | 2014-12-16 | 2014-12-16 | Inverclyde | 1727977.31 | 112489.48 | 36.75 | 0 | 0 | 0 | 0 | 112526.23 | 0 | 1840503.54 | 1179 | [6 empty] | CM_WWI | 40% | CS11A | 60%
503073 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS3 | 2018-04-06 | 2018-08-29 | 2018-09-24 | 2019-09-16 | 2019-12-17 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 557223.39 | 180547.51 | 0.1 | 737771 | 0 | 737771 | 0 | [6 empty] | EC16 | 100%
045667 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2008-10-15 | 2010-03-24 | 2010-06-01 | 2014-12-08 |  | Scottish Water Wide | 2420315 | 19025.64 | 0 | 0 | 0 | 0 | 0 | 19025.64 | 0 | 2439340.64 | 0 | [6 empty] | CM_WWI | 100%
046622 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2009-03-19 | 2011-05-05 | 2011-05-16 | 2012-07-05 |  | Argyll and Bute-Cowal & Bute | 938353 | 64 | 0 | -48794.84 | 0 | 0 | 0 | -48730.84 | 0 | 889622.16 | 0 | [6 empty] | CM_WWI | 100%
400510 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-03-24 | 2011-10-31 | 2011-12-12 | 2013-05-24 |  | Shetland Islands | 819365 | -1543.71 | 0 | 0 | 0 | 0 | 0 | -1543.71 | 0 | 817821.29 | 0 | [6 empty] | CM_WWI | 100%
402526 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-05 | 2012-04-24 | 2012-04-24 | 2013-08-12 |  | Scottish Water Wide | 1728836 | -4866.77 | 0 | 0 | 0 | 0 | 0 | -4866.77 | 0 | 1723969.23 | 0 | [6 empty] | CM_WWI | 100%
403349 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-18 | 2013-05-29 | 2013-05-29 | 2014-06-04 |  | Scottish Water Wide | 1639081 | 0 | -6060.88 | 0 | 0 | 0 | 0 | -6060.88 | 0 | 1633020.12 | 0 | [6 empty] | CM_WWI | 100%
403348 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-28 | 2014-03-25 | 2014-03-26 | 2015-09-21 |  | Scottish Water Wide | 1090001 | 71217 | 2550.06 | -796.19 | 0 | 0 | 0 | 72970.87 | 0 | 1162971.87 | 0 | [6 empty] | CM_WWI | 100%
046148 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2008-08-20 | 2012-03-08 | 2012-04-30 | 2014-06-06 |  | South Ayrshire | 4286075 | 0 | -1922.89 | 0 | 0 | 0 | 0 | -1922.89 | 0 | 4284152.11 | 0 | [6 empty] | CM_WWI | 100%
502286 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS7 | 2017-04-03 | 2017-04-10 | 2017-04-10 | 2017-03-14 | 2017-03-14 | Scottish Water Wide | 0 | 0 | 39957.34 | -7943.42 | 0 | 0 | 0 | 32013.92 | 0 | 32013.92 | 0 | [6 empty] | CM_M&G | 100%
503452 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWD | Environmental Studies | MS0 | 2019-02-13 | 2019-06-03 | 2019-06-03 | 2020-02-06 | 2020-04-02 | Scottish Water Wide | 0 | 0 | 0 | 0 | 1308.41 | 248081.63 | 5276.63 | 254666.67 | 0 | 254666.67 | 294750.8556 | [6 empty] | CS25 | 100%
403183 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-12-17 | 2013-12-11 | 2013-12-12 | 2014-08-26 | 2014-10-01 | Glasgow City | 1953340 | 15173.45 | 6194.21 | 772.98 | 0 | 0 | 0 | 22140.64 | 0 | 1975480.64 | 451.2001 | [6 empty] | CM_WWI | 40% | CS11A | 60%
403583 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2013-09-09 | 2013-12-23 | 2014-02-10 | 2014-06-30 | 2014-06-30 | City of Edinburgh | 395847 | 778 | -5213.62 | 0 | 0 | 0 | 0 | -4435.62 | 0 | 391411.38 | 2295.6 | [6 empty] | CM_WWI | 40% | CS11A | 60%
030875 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-12 | 2012-01-31 | 2012-02-28 | 2013-03-01 | 2013-03-18 | Orkney Islands | 3353865.31 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 3353870.31 | 43 | [6 empty] | DW23 | 100%
503239 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | GW1 | 2019-04-01 | 2019-12-23 | 2020-03-13 | 2020-07-23 | 2020-10-23 | North Ayrshire | 0 | 0 | 0 | 0 | 20946.1 | 29053.9 | 0 | 50000 | 0 | 50000 | 587726.5342 | [6 empty] | WG5 | 100%
502924 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS3 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2019-07-29 | 2019-07-30 | Midlothian | 0 | 0 | 0 | 41259.81 | 0 | 552723.6 | 224945.65 | 818929.06 | 0 | 818929.06 | 0 | [6 empty] | SG5 | 100%
500740 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2015-07-27 | 2015-07-27 | 2015-07-27 | 2018-10-25 | 2018-10-25 | East Lothian | 0 | 175962 | 0 | -87999.99 | 0 | 0 | 0 | 87962.01 | 0 | 87962.01 | 587726.5342 | [6 empty] | WG5 | 100%
502942 | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWD | SOSI | GW2 | 2019-06-21 | 2020-05-25 | 2020-09-21 | 2021-05-06 | 2021-08-06 | Shetland Islands | 0 | 0 | 0 | 85259.9025 | 229114.7585 | 23995.93 | 0 | 338370.591 | 0 | 338370.591 | 3243356.8919 | [6 empty] | WG4 | 100%
404123 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-04-17 | 2015-04-17 | 2015-05-11 | 2016-01-21 | 2016-01-21 | Highland | 0 | 315740.5 | -19.14 | 0 | 0 | 0 | 0 | 315721.36 | 0 | 315721.36 | 0 | [6 empty] | CM_WSI | 100%
045414 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-03-29 | 2011-09-01 | 2013-03-01 | 2013-03-27 | Highland | 3372234.89 | 45 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 3372279.89 | 0 | [6 empty] | DW13 | 50% | DW23 | 50%
500717 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-07-23 | 2015-12-22 | 2016-01-19 | 2017-03-28 | 2017-05-15 | Glasgow City | 0 | 261208 | 56166.43 | 35.36 | 0 | 0 | 0 | 317409.79 | 0 | 317409.79 | 144841.4737 | [6 empty] | CS15A | 100%
403772 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2014-05-21 | 2014-05-26 | 2014-05-26 | 2016-08-16 |  | Glasgow City | 676556 | 448549.58 | 13544.76 | 5591.42 | -3962.51 | 0 | 0 | 463723.25 | 0 | 1140279.25 | 0 | [6 empty] | CM_WWNI | 100%
501637 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-03-16 | 2017-11-07 | 2018-01-30 | 2019-05-09 | 2019-05-09 | Glasgow City | 0 | 0 | 179192 | -118989.87 | 514734.68 | 11508.16 | 0 | 586444.97 | 0 | 586444.97 | 0 | [6 empty] | CM_WWNI | 100%
501172 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-03-02 | 2017-10-30 | 2017-11-06 | 2020-10-08 | 2021-01-05 | Renfrewshire | 0 | 5161.68 | 1032338.15 | 942738.78 | 5167940.47 | 1946336.6 | 1505139.62 | 10599655.3 | 81501.72 | 10681157.02 | 0 | [6 empty] | CM_WWNI | 100%
030878 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-15 | 2011-09-23 | 2011-09-23 | 2013-11-27 |  | Glasgow City | 6343385.08 | -6149.5 | 0 | 0 | 0 | 0 | 0 | -6149.5 | 0 | 6337235.58 | 0 |  |  |  |  | 41553 |  | CM_WWNI | 100%
401241 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS7 | 2010-07-19 | 2011-01-14 | 2011-01-27 | 2011-01-27 | 2011-03-14 | Glasgow City | 3021.99 | 0 | 0 | 1195.7125 | 228.59 | 0 | 0 | 1424.3025 | 0 | 4446.2925 | 0 | [6 empty] | EC10B | 100%
502938 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2017-12-11 | 2017-12-11 | 2018-01-08 | 2018-01-09 | 2018-01-09 | Glasgow City | 0 | 0 | 0 | 662951.506 | 0 | 0 | 0 | 662951.506 | 0 | 662951.506 | 0 | [6 empty] | CM_WWNI | 100%
500757 | Q&S4 | Protecting and enhancing the environment | Odour |  |  | Wastewater |  | SWMD | Odour | MS6 | 2015-08-12 | 2015-10-26 | 2016-02-05 | 2017-04-10 | 2017-05-09 | Glasgow City | 0 | 47000 | 705043.97 | -150546.54 | 0 | 2389.01 | 540.43 | 604426.87 | 0 | 604426.87 | 830077.9634 | [6 empty] | CS2 | 100%
501683 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-05-16 | 2017-02-13 | 2017-02-17 | 2020-01-24 | 2020-01-24 | Glasgow City | 0 | 0 | 471779.17 | 539039.83 | 190500 | 1162523 | 0 | 2363842 | 0 | 2363842 | 0 | [6 empty] | CM_WWI | 100%
501747 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS0 | 2016-10-31 | 2019-05-13 | 2019-06-17 | 2019-11-14 | 2020-02-12 | Glasgow City | 0 | 0 | 4795.67 | 48.62 | 73732.71 | 119225.74 | 913.32 | 198716.06 | 653.88 | 199369.94 | 0 | [6 empty] | CM_WWI | 100%
501281 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-01-20 | 2018-01-31 | 2018-01-31 | 2019-10-16 | 2019-10-17 | Glasgow City | 0 | 14033 | 228154.86 | 269413.75 | 1090389.41 | 739678.69 | 106534.81 | 2448204.52 | 20631.32 | 2468835.84 | 0 | [6 empty] | CM_WWNI | 100%
500197 | Q&S4 | Protecting and enhancing the environment | Odour |  |  | Wastewater |  | NONINF | Odour | MS6 | 2015-07-21 | 2016-09-16 | 2017-02-27 | 2017-06-01 | 2017-11-01 | Glasgow City | 0 | 39577 | 283295.06 | 426634.32 | -57439.96 | 34777.71 | 0 | 726844.13 | 0 | 726844.13 | 830077.9634 | [6 empty] | CS2 | 100% | bar: Regulatory Outputs OMG-29
502400 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS5 | 2017-01-26 | 2017-01-26 | 2017-06-13 | 2018-05-01 | 2018-11-01 | Glasgow City | 0 | 0 | 326367 | 357093.42 | 59347.1185 | 0 | 0 | 742807.5385 | 0 | 742807.5385 | 10994109.1109 | [6 empty] | EC01A | 100% | [18 empty] | Regulatory Outputs OMG-23: 2
403479 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2013-07-11 | 2016-04-08 | 2016-04-11 | 2017-01-25 | 2017-01-25 | North Lanarkshire | 134441 | 589763 | 1236071.78 | 20475.22 | 5257.4739 | 0 | 0 | 1851567.4739 | 0 | 1986008.4739 | 0 | [6 empty] | CM_M&G | 14.29% | CM_WWI | 85.71%
500177 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2015-11-30 | 2016-01-18 | 2018-02-01 | 2018-03-01 | North Lanarkshire | 0 | 80361 | 65629.65 | 31230 | 30919.318 | 0 | 0 | 208139.968 | 0 | 208139.968 | 72474.3726 | [6 empty] | CS11 | 43.84% | CS16D | 56.16% | bar: Regulatory Outputs OMG-22
030880 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-15 | 2012-01-24 | 2012-07-09 | 2013-01-07 | 2013-02-21 | North Lanarkshire | 1601398.3 | 801 | -18226.57 | 0 | 0 | 0 | 0 | -17425.57 | 0 | 1583972.73 | 0 | [6 empty] | EC10A | 11.6% | EC01A | 11.7% | EC04A | 11.7% | CM_WWNI | 65%
503209 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-05 | 2023-06-20 | 2023-10-19 | 2024-10-15 | 2025-01-15 | North Lanarkshire | 0 | 0 | 0 | 0 | 81775.66 | 5863.55 | 10210.04 | 97849.25 | 45780.89 | 143630.14 | 148885.7057 | [6 empty] | SG1 | 100%
500698 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-07-22 | 2015-07-22 | 2015-07-22 | 2016-05-11 |  | Scottish Water Wide | 0 | 1359603 | -53016.17 | 0 | 0 | 0 | 0 | 1306586.83 | 0 | 1306586.83 | 0 | [6 empty] | CM_M&G | 100%
501701 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS5 | 2016-11-17 | 2017-05-23 | 2017-08-09 | 2019-02-14 | 2019-02-14 | Fife | 0 | 0 | 11110 | 38449 | 17802 | 1243 | 0 | 68604 | 0 | 68604 | 0 | [6 empty] | CM_WWI | 100%
403762 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS7 | 2014-05-02 | 2015-03-30 | 2015-03-30 | 2017-02-22 | 2017-05-16 | Scottish Water Wide | 73057 | 268995 | 454948 | 15412.52 | 0 | 0 | 0 | 739355.52 | 0 | 812412.52 | 113151.4635 | [6 empty] | DW25PS | 10% | DW2_S | 90%
404099 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | NONINF | Non OMG180 | MS5 | 2015-03-06 | 2016-09-02 | 2016-10-17 | 2017-05-05 | 2017-05-05 | South Lanarkshire | 9728.02 | 265470.38 | 1554463.33 | 796925.21 | -267464.6 | 73378.88 | 542482.94 | 2965256.14 | 2374.76 | 2977358.92 | 0 |  |  |  |  | 29740 |  | EC01A | 14.33% | EC04A | 14.33% | EC10A | 14.33% | CM_WWNI | 57%
030881 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-27 | 2011-03-29 | 2012-12-11 | 2016-02-11 | 2016-10-31 | South Lanarkshire | 3362266.45 | 72347.5 | 12732.53 | 692.79 | 0 | 0 | 0 | 85772.82 | 0 | 3448039.27 | 1671325.0936 | [6 empty] | CM_WWNI | 19.97% | EC01A | 19.97% | EC04A | 60.05%
500178 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS5 | 2015-03-20 | 2015-11-30 | 2016-01-12 | 2018-11-26 | 2019-03-28 | South Lanarkshire | 0 | 108775 | 107165 | 44040 | 65020 | 0 | 0 | 325000 | 0 | 325000 | 82836.9006 | [6 empty] | EC01G | 1.003% | CS11 | 44.36% | CS16D | 54.64%
503328 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2022-02-09 | 2023-02-07 | 2023-04-04 | 2023-11-27 | 2024-02-27 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 6093.33 | 6093.33 | 481405.73 | 487499.06 | 0 | [6 empty] | CM_M&G | 100%
503212 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-05 | 2023-06-20 | 2023-10-19 | 2024-10-15 | 2025-01-15 | South Lanarkshire | 0 | 0 | 0 | 0 | 76112.23 | 23808.11 | 23715.85 | 123636.19 | 18363.58 | 141999.77 | 148885.7057 | [6 empty] | SG1 | 100%
501205 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS3 | 2017-03-28 | 2017-12-27 | 2018-09-21 | 2019-12-01 | 2020-03-01 | Shetland Islands | 0 | 1710.33 | 11767.64 | 44307.11 | 68078.73 | 130868.4 | 41602.16 | 298334.37 | 1848.94 | 300183.31 | 62391.5379 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
403402 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-04-27 | 2013-04-27 | 2014-08-19 | 2015-10-07 |  | Highland | 182976.33 | 9713.72 | 85.2 | 0 | 0 | 0 | 0 | 9798.92 | 0 | 192775.25 | 0 | [6 empty] | CM_WSI | 100%
501300 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-12-02 | 2017-05-26 | 2017-05-26 | 2017-04-04 | 2017-04-04 | Scottish Water Wide | 0 | 21300 | -299.13 | -58.24 | 0 | 0 | 0 | 20942.63 | 0 | 20942.63 | 0 | [6 empty] | CM_M&G | 100%
501283 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-04-15 |  |  | 2021-04-15 | 2021-04-15 | Scottish Water Wide | 0 | 0 | 131.08 | 0 | 0 | 0 | 8446666.67 | 8446797.75 | 0 | 8446797.75 | 0 | [6 empty] | CM_WWI | 34% | CM_WWNI | 66%
501284 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-04-15 |  |  | 2021-04-15 | 2021-04-15 | Scottish Water Wide | 0 | 92.23 | 0 | 0 | 140.88 | 0 | 16893333.31 | 16893566.42 | 0 | 16893566.42 | 0 | [6 empty] | CM_WWI | 34% | CM_WWNI | 66%
501285 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2021-04-15 |  |  | 2021-04-15 | 2021-04-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 11317857.15 | 11317857.15 | 0 | 11317857.15 | 0 | [6 empty] | CM_WSI | 48% | CM_WSNI | 52%
501286 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2021-04-15 |  |  | 2021-04-15 | 2021-04-15 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 20372142 | 20372142 | 0 | 20372142 | 0 | [6 empty] | CM_WSI | 48% | CM_WSNI | 52%
502959 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2021-04-01 | 2021-04-01 | 2021-06-11 | 2022-01-13 | 2022-04-15 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 349999.99 | 349999.99 | 0 | [6 empty] | CM_WWI | 100%
401883 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2011-03-10 | 2011-04-04 | 2011-04-04 | 2014-06-06 |  | Scottish Water Wide | 2113143.51 | -4028 | 0 | 0 | 0 | 0 | 0 | -4028 | 0 | 2109115.51 | 0 | [6 empty] | CM_M&G | 100%
403868 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-08-20 | 2014-12-19 | 2014-12-19 | 2015-07-07 |  | Scottish Water Wide | 2165495 | -258737.66 | 0 | 0 | 0 | 0 | 0 | -258737.66 | 0 | 1906757.34 | 0 | [6 empty] | CM_M&G | 100%
403043 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-23 | 2012-11-13 | 2012-12-17 | 2013-04-29 |  | Na H-Eileanan an Iar | 147648 | 155.03 | 0 | 0 | 0 | 0 | 0 | 155.03 | 0 | 147803.03 | 0 | [6 empty] | CM_WSI | 100%
501317 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2017-02-27 | 2018-06-05 | 2018-09-03 | 2019-05-03 | 2019-08-08 | Scottish Water Wide | 0 | 0 | 55035.59 | 58430.41 | 451894 | 25096.44 | 1000 | 591456.44 | 0 | 591456.44 | 0 | [6 empty] | CM_WWNI | 100%
400818 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-05-18 | 2012-03-27 | 2012-03-27 | 2012-03-30 |  | North Lanarkshire | 61726.93 | 0 | 0 | 1421.472 | 0 | 0 | 0 | 1421.472 | 0 | 63148.402 | 0 | [6 empty] | CM_WWI | 100%
500509 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | WINF | Supply Resilience | MS3 | 2016-03-23 | 2018-02-26 | 2018-03-26 | 2020-01-01 | 2021-01-01 | All South Unitary Authorities | 0 | 131852.98 | 341784.02 | 1923969 | 9660635.41 | 5798633.62 | 259780.63 | 18116655.66 | 0 | 18116655.66 | 5970783.1595 | [6 empty] | CS16WR | 100% | bar: Regulatory Outputs OMG-07
502567 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2019-09-27 | 2020-08-03 | 2020-10-05 | 2021-09-17 | 2021-12-20 | Orkney Islands | 0 | 0 | 20930.23 | 3708.1175 | 99061.7055 | 55349.59 | 407479.66 | 586529.303 | 477757.72 | 1064287.023 | 148885.7057 | [6 empty] | WG1 | 100%
500931 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-27 | 2016-11-04 | 2016-11-04 | 2016-10-25 | 2016-11-04 | South Lanarkshire | 0 | 8001.06 | 490.05 | 0 | 0 | 0 | 0 | 8491.11 | 0 | 8491.11 | 144841.4737 | [6 empty] | CS15A | 100%
500700 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2015-08-03 | 2016-07-27 | 2016-08-17 | 2017-10-26 | 2017-10-26 | Scottish Borders | 0 | 4080 | 60431.06 | 128235.66 | 9220.18 | 0 | 0 | 201966.9 | 0 | 201966.9 | 0 | [6 empty] | CM_WSI | 100%
500874 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2016-09-20 | 2018-09-26 | 2018-12-03 | 2019-09-01 | 2020-08-01 | East Renfrewshire | 0 | 10252.59 | 12747.41 | 35476.14 | 135071.89 | 0 | 52375.17 | 245923.2 | 12837.06 | 258760.26 | 894552.6629 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 85.03
503286 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-14 | 2023-06-28 | 2023-10-31 | 2024-10-28 | 2025-01-28 | West Lothian | 0 | 0 | 0 | 0 | 75860.69 | 0 | 30039.99 | 105900.68 | 36099.27 | 141999.95 | 148885.7057 | [6 empty] | SG1 | 100%
403193 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-01-14 | 2013-04-25 | 2013-08-12 | 2015-01-26 |  | All South Unitary Authorities | 105295 | -3580.5 | 0 | 0 | 0 | 0 | 0 | -3580.5 | 0 | 101714.5 | 0 | [6 empty] | CM_WWI | 100%
403044 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-23 | 2012-11-13 | 2012-12-03 | 2013-10-01 |  | Na H-Eileanan an Iar | 198401.69 | 19.77 | 0 | 0 | 0 | 0 | 0 | 19.77 | 0 | 198421.46 | 0 | [6 empty] | CM_WSI | 100%
503082 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS1 | 2015-11-02 | 2020-08-17 | 2020-11-30 | 2022-03-28 | 2022-07-22 | Na H-Eileanan an Iar | 0 | 0 | 0 | 16149.5825 | 38587.4175 | 377382.54 | 1679653.54 | 2111773.08 | 2683325.68 | 4795098.76 | 4350216.3534 | [6 empty] | DW3B | 7.484% | DW3C | 7.484% | WG4 | 24.95% | DW25P | 60.08%
403594 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-10-02 | 2013-10-02 | 2013-10-02 | 2015-09-01 |  | All South Unitary Authorities | 430299.85 | 48331.02 | 0 | 0 | 0 | 0 | 0 | 48331.02 | 0 | 478630.87 | 0 | [6 empty] | CM_WWNI | 100%
501550 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-01-21 | 2016-02-29 | 2016-02-29 | 2016-11-21 | 2018-03-22 | Scottish Water Wide | 0 | 157730.98 | 471676.93 | 0 | 0 | 0 | 0 | 629407.91 | 0 | 629407.91 | 0 | [6 empty] | CM_M&G | 100%
403067 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-10-16 | 2012-10-16 | 2012-10-16 | 2015-06-11 |  | All South Unitary Authorities | 520000 | 7824.56 | 0 | 0 | 0 | 0 | 0 | 7824.56 | 0 | 527824.56 | 0 | [6 empty] | CM_WWNI | 100%
502231 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2017-06-29 | 2018-12-19 | 2019-03-04 | 2020-01-16 | 2020-04-21 | Scottish Water Wide | 0 | 0 | 26001.93 | 159111.07 | 1052348 | 1743631.93 | 258491.07 | 3239584 | 220239 | 3459823 | 0 | [6 empty] | CM_WWNI | 100%
030891 | Q&S3A | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2006-06-07 | 2007-09-26 | 2007-11-30 | 2012-03-26 | 2012-03-30 | Shetland Islands | 8603592.02 | 30559.38 | 0 | 0 | 0 | 0 | 0 | 30559.38 | 0 | 8634151.4 | 0 | [6 empty] | DW13 | 19% | DW2 | 19% | DW3G | 19% | WSNI | 43%
045415 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-12-20 | 2012-07-30 | 2013-05-29 | 2013-08-22 | Scottish Borders | 940494.06 | -24762.39 | 0 | 0 | 0 | 0 | 0 | -24762.39 | 0 | 915731.67 | 2136 | [6 empty] | DW23 | 100%
501599 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2017-01-19 | 2019-02-25 | 2019-03-25 | 2019-12-11 | 2020-03-26 | Renfrewshire | 0 | 0 | 11388 | 197363.19 | 344702.81 | 1448523.99 | 17484.8 | 2019462.79 | 1001.2 | 2020463.99 | 0 | [6 empty] | CM_WWI | 100%
403529 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-07-12 | 2014-12-16 | 2015-01-05 | 2016-03-22 | 2016-04-01 | South Lanarkshire | 318870 | 54633 | 45497 | 0 | -4115.9 | 0 | 0 | 96014.1 | 0 | 414884.1 | 229318.7788 | [6 empty] | CS11A | 100%
503340 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-10-02 | 2018-10-02 | 2018-10-08 | 2019-06-10 | 2019-06-10 | Moray | 0 | 0 | 0 | 0 | 1085031.12 | 4231.43 | 734.29 | 1089996.84 | 1034.3 | 1091031.14 | 0 | [6 empty] | CM_WSNI | 100%
045614 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-06-30 | 2011-07-13 | 2014-01-08 | 2014-03-21 | Moray | 627236.87 | 2006.11 | 0 | 0 | 0 | 0 | 0 | 2006.11 | 0 | 629242.98 | 1300 | [6 empty] | DW1A | 100%
503490 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 18600000 | 0 | 18600000 | 0 | 18600000 | 0 | [6 empty] | CM_M&G | 100%
402355 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2011-08-26 | 2011-08-26 | 2011-08-26 | 2015-09-30 |  | Scottish Water Wide | 1188218 | 44582.08 | 0 | 0 | 0 | 0 | 0 | 44582.08 | 0 | 1232800.08 | 0 | [6 empty] | CM_WSNI | 100%
400927 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2010-04-21 | 2013-05-08 | 2013-05-09 | 2018-06-22 | 2011-03-14 | Glasgow City | 301676.37 | 6000.63 | 0.44 | 0 | -1125.03 | 0 | 0 | 4876.04 | 0 | 306552.41 | 0 | [6 empty] | EC04C | 33.33% | EC10E | 33.33% | EC01D | 33.34%
502830 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS2 | 2018-03-29 | 2018-11-21 | 2019-04-01 | 2019-07-09 | 2019-10-09 | Perth and Kinross | 0 | 0 | 0 | 13684.3955 | 51221.6045 | 143594.05 | 3577.41 | 212077.46 | 0.04 | 212077.5 | 0 | [6 empty] | CM_WWI | 100%
500784 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-09-07 | 2019-02-01 | 2019-03-29 | 2020-05-25 | 2020-05-25 | Fife | 0 | 108131 | 100990 | 204703.93 | 659425.76 | 1702320.67 | 353370.65 | 3128942.01 | 18546.96 | 3147488.97 | 0 | [6 empty] | CM_WWNI | 100%
503287 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-31 | 2023-06-14 | 2023-10-17 | 2024-10-14 | 2025-01-14 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 65954.87 | 10356.34 | 41977.79 | 118289 | 28640.09 | 146929.09 | 148885.7057 | [6 empty] | SG1 | 100%
401739 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2011-01-10 | 2011-05-16 | 2011-06-15 | 2016-01-27 |  | Scottish Water Wide | 212157 | -2222.44 | 0 | 0 | 0 | 0 | 0 | -2222.44 | 0 | 209934.56 | 0 | [6 empty] | CM_WSNI | 100%
501362 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS5 | 2016-07-19 | 2017-07-17 | 2018-01-08 | 2019-03-14 | 2019-03-14 | East Lothian | 0 | 0 | 32194 | 516016 | 414115 | 340655.98 | 2400.02 | 1305381 | 0 | 1305381 | 0 | [6 empty] | CM_WWNI | 100%
502406 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS0 | 2017-11-07 | 2019-05-13 | 2021-10-01 | 2022-11-01 | 2022-11-01 | Scottish Water Wide | 0 | 0 | 2814.95 | 22170.165 | 40406.71 | 41347.55 | 33787.79 | 140527.165 | 70873.71 | 211400.875 | 0 | [6 empty] | CM_WSNI | 100%
501364 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS0 | 2016-08-29 | 2022-02-02 | 2022-06-08 | 2023-01-23 | 2023-04-25 | South Lanarkshire | 0 | 0 | 21521 | -8673 | 0 | 0 | 0 | 12848 | 4736 | 17584 | 0 | [6 empty] | CM_WWNI | 100%
503200 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS0 | 2018-12-20 | 2019-09-02 | 2019-10-28 | 2020-07-01 | 2021-04-01 | Moray | 0 | 0 | 0 | 0 | 181983.162 | 672787.8 | 142369.99 | 997140.952 | 0 | 997140.952 | 0 | [6 empty] | DW5MR | 30% | DW5FS | 70% | [16 empty] | Regulatory Outputs OMG-06: 149.5785
404066 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2015-01-05 | 2015-07-30 | 2015-10-12 | 2019-06-28 | 2018-09-04 | Glasgow City | 50457 | 1141083.7 | 1947685.3 | 2718082 | 829969.89 | 0 | 0 | 6636820.89 | 0 | 6687277.89 | 0 | [6 empty] | CM_WSI | 100%
404081 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS0 | 2015-07-27 | 2020-06-29 | 2020-09-21 | 2021-08-23 | 2021-11-22 | Glasgow City | 0 | 30000 | 0 | 3894 | 13106 | 12900.3 | 36632.77 | 96533.07 | 589466.93 | 686000 | 240495.8008 | [6 empty] | CS11 | 100%
500438 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2017-03-03 | 2017-03-03 | All East Unitary Authorities | 0 | 865019.51 | 101287.61 | -72858.42 | 0 | 0 | 0 | 893448.7 | 0 | 893448.7 | 0 | [6 empty] | CM_WWI | 100%
501951 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2016-02-15 | 2016-02-15 | 2016-04-26 | 2020-04-13 | 2020-04-14 | All North Unitary Authorities | 0 | 435588.61 | 1029390.99 | 381953.9 | 178775.04 | 433258.2 | 48178.99 | 2507145.73 | 4397.74 | 2511543.47 | 0 | [6 empty] | CM_WSNI | 100%
400921 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS7 | 2010-06-02 | 2011-01-18 | 2011-01-18 | 2016-06-07 |  | Scottish Water Wide | 1057007 | 53761 | -54375.89 | 0 | -89697.58 | 0 | 0 | -90312.47 | 0 | 966694.53 | 0 | [6 empty] | CM_WWNI | 100%
500079 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-02-27 | 2015-03-25 | 2015-03-25 | 2017-08-18 | 2017-10-02 | Scottish Water Wide | 0 | 152689 | -94078 | -7556.63 | 0 | 0 | 0 | 51054.37 | 0 | 51054.37 | 0 | [6 empty] | CM_WSI | 100%
500083 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-02-27 | 2015-03-25 | 2015-03-25 | 2020-05-08 | 2020-05-08 | Scottish Water Wide | 0 | 119135 | 74295 | 34778 | 66734 | 75657 | 7549.36 | 378148.36 | 0 | 378148.36 | 0 | [6 empty] | CM_WSI | 100%
500084 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-11 | 2015-03-30 | 2015-03-30 | 2020-05-08 | 2020-05-08 | Scottish Water Wide | 0 | 385150 | 293876 | 169763.36 | 231610.64 | 308830 | 2174.08 | 1391404.08 | 0 | 1391404.08 | 0 | [6 empty] | CM_WSI | 100%
500085 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-03-11 | 2015-03-25 | 2015-03-25 | 2020-05-08 | 2020-05-08 | Scottish Water Wide | 0 | 260879 | 101882 | 200992 | 196164 | 163776 | 8545.2 | 932238.2 | 0 | 932238.2 | 0 | [6 empty] | CM_WSI | 100%
037714 | Q&S3A | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-12-02 | 2013-07-11 | 2008-12-02 | 2008-12-02 | 2011-01-01 | Scottish Water Wide | 327104 | 2586.48 | 440.93 | 0 | 0 | 0 | 0 | 3027.41 | 0 | 330131.41 | 806 | [6 empty] | WR1 | 100%
400609 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2004-03-30 | 2010-06-07 | 2010-06-07 | 2015-10-01 |  | Scottish Water Wide | 41631 | -3537.58 | 0 | 0 | 0 | 0 | 0 | -3537.58 | 0 | 38093.42 | 0 | [6 empty] | CM_M&G | 100%
403041 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-26 | 2013-03-25 | 2013-04-25 | 2014-11-03 |  | Na H-Eileanan an Iar | 206343 | 0 | -1718.41 | 0 | 0 | 0 | 0 | -1718.41 | 0 | 204624.59 | 0 | [6 empty] | CM_WSI | 100%
402532 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-02-09 | 2012-02-09 | 2012-04-02 | 2015-06-15 |  | Scottish Water Wide | 238970 | -25768.73 | 0 | 0 | 0 | 0 | 0 | -25768.73 | 0 | 213201.27 | 0 | [6 empty] | CM_WSI | 100%
400610 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-03-30 | 2014-06-23 | 2014-06-24 | 2015-12-08 |  | Scottish Water Wide | 750000 | -57291.57 | 0 | 42515 | 0 | 0 | 0 | -14776.57 | 0 | 735223.43 | 0 | [6 empty] | CM_M&G | 100%
402459 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-02-22 | 2012-09-27 | 2012-09-28 | 2014-03-11 | 2014-03-27 | Scottish Water Wide | 28434.08 | 860 | 0 | 0 | 0 | 0 | 0 | 860 | 0 | 29294.08 | 587 | [6 empty] | CS1 | 100%
400261 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-04-14 | 2012-02-09 | 2012-03-05 | 2014-03-28 | 2013-11-07 | All East Unitary Authorities | 142000 | 0 | -999.84 | 0 | 0 | 0 | 0 | -999.84 | 0 | 141000.16 | 0 | [6 empty] | CM_WSI | 29.08% | CS1 | 70.92%
400262 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS6 | 2010-04-14 | 2012-01-30 | 2012-02-14 | 2016-11-15 | 2015-03-09 | Aberdeenshire | 353098.8 | 3747.2 | 21351.73 | 10130.77 | -93.4 | 0 | 0 | 35136.3 | 0 | 388235.1 | 6361 | [6 empty] | CS1 | 100%
400263 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-04-14 | 2011-01-18 | 2011-02-07 | 2013-09-30 | 2013-03-31 | Highland | 357574 | -1793.51 | 0 | 0 | 0 | 0 | 0 | -1793.51 | 0 | 355780.49 | 0 | [6 empty] | CS1 | 100%
400264 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-04-14 | 2011-03-10 | 2011-03-14 | 2013-08-12 | 2013-08-20 | Perth and Kinross | 406748 | -4451.26 | 0 | 0 | 0 | 0 | 0 | -4451.26 | 0 | 402296.74 | 252.0001 | [6 empty] | CS1 | 100%
400269 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-04-14 | 2012-11-19 | 2013-03-12 | 2014-06-09 | 2014-03-19 | Argyll and Bute-North Argyll | 147536.55 | 147.65 | 0 | 0 | 0 | 0 | 0 | 147.65 | 0 | 147684.2 | 0 | [6 empty] | CS1 | 100%
400272 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-04-14 | 2011-11-22 | 2012-03-05 | 2013-03-29 | 2013-03-29 | Argyll and Bute-North Argyll | 560049.77 | 181.4 | 0 | 0 | 0 | 0 | 0 | 181.4 | 0 | 560231.17 | 0 | [6 empty] | CS1 | 100%
400273 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-04-14 | 2012-06-29 | 2012-07-30 | 2013-01-15 | 2013-01-15 | Orkney Islands | 471168.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 471168.67 | 0 | [6 empty] | CS1 | 50% | DW5 | 50%
403999 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-11-21 | 2014-11-21 | 2014-11-24 | 2016-07-04 |  | Scottish Water Wide | 1479670 | 37191.44 | 0 | 0 | 0 | 0 | 0 | 37191.44 | 0 | 1516861.44 | 0 | [6 empty] | CM_WSNI | 100%
400611 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-03-30 | 2013-03-05 | 2010-06-15 | 2015-10-01 |  | Scottish Water Wide | 204150 | -2511.5 | 0 | 0 | 0 | 0 | 0 | -2511.5 | 0 | 201638.5 | 0 | [6 empty] | CM_M&G | 100%
403042 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-26 | 2013-08-22 | 2014-04-08 | 2015-03-03 |  | Na H-Eileanan an Iar | 295618 | 500 | -1676.36 | 0 | 0 | 0 | 0 | -1176.36 | 0 | 294441.64 | 0 | [6 empty] | CM_WSI | 100%
046150 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2008-10-15 | 2010-03-24 | 2010-06-01 | 2015-03-11 |  | Scottish Water Wide | 452054 | 2544.13 | 0 | 0 | 0 | 0 | 0 | 2544.13 | 0 | 454598.13 | 0 | [6 empty] | CM_WWI | 100%
400727 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-22 | 2011-06-08 | 2011-06-08 | 2015-07-02 |  | Scottish Water Wide | 1318480.55 | 74517.32 | 13929.55 | 0 | 0 | 0 | 0 | 88446.87 | 0 | 1406927.42 | 0 | [6 empty] | CM_WSI | 100%
400728 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-22 | 2011-06-06 | 2011-06-08 | 2015-07-02 |  | Scottish Water Wide | 1893371 | -57216.24 | 214.5 | 0 | 0 | 0 | 0 | -57001.74 | 0 | 1836369.26 | 0 | [6 empty] | CM_WSI | 100%
400729 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-22 | 2011-06-09 | 2011-06-08 | 2015-07-02 |  | Scottish Water Wide | 204535 | -70.85 | 0 | 0 | 0 | 0 | 0 | -70.85 | 0 | 204464.15 | 0 | [6 empty] | CM_WSI | 100%
400726 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-22 | 2011-06-06 | 2011-06-08 | 2015-07-02 |  | Scottish Water Wide | 257228 | -47486.49 | 0 | 0 | 0 | 0 | 0 | -47486.49 | 0 | 209741.51 | 0 | [6 empty] | CM_WSI | 100%
400086 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2009-12-17 | 2011-02-03 | 2011-04-04 | 2017-11-01 |  | Glasgow City | 538492 | 25363.01 | 66144.99 | -29590.36 | 0 | 0 | 0 | 61917.64 | 0 | 600409.64 | 0 | [6 empty] | CM_WSI | 100%
400872 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-04-21 | 2011-09-14 | 2011-09-14 | 2015-12-01 |  | Scottish Water Wide | 375022.09 | 73675 | 0 | 0 | 0 | 0 | 0 | 73675 | 0 | 448697.09 | 0 | [6 empty] | CM_M&G | 100%
400612 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-03-30 | 2010-06-15 | 2010-06-15 | 2015-10-01 |  | Scottish Water Wide | 448460 | -17155.07 | 0 | 0 | 0 | 0 | 0 | -17155.07 | 0 | 431304.93 | 0 | [6 empty] | CM_M&G | 100%
400752 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2011-06-30 | 2011-07-04 | 2015-07-02 |  | Scottish Water Wide | 272261 | -28507 | -6469 | -5307.29 | 0 | 0 | 0 | -40283.29 | 0 | 231977.71 | 0 | [6 empty] | CM_WSI | 100%
400613 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-03-30 | 2010-06-15 | 2010-06-15 | 2015-10-01 |  | Scottish Water Wide | 222390 | 4857.53 | 0 | 0 | 0 | 0 | 0 | 4857.53 | 0 | 227247.53 | 0 | [6 empty] | CM_M&G | 100%
502422 | Q&S4 | Improving drinking water availability and resilience of service | SEMD |  |  | Water |  | SWD | SEMD | MS5 | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-09-01 | 2017-09-14 | Scottish Water Wide | 0 | 0 | 7194.94 | -2289.28 | 1723.76 | 0 | 0 | 6629.42 | 0 | 6629.42 | 274541.7759 | [6 empty] | DW9D | 100%
400750 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2011-06-06 | 2011-06-20 | 2015-07-02 |  | Scottish Water Wide | 825774 | 12448.37 | 979.27 | 0 | 0 | 0 | 0 | 13427.64 | 0 | 839201.64 | 0 | [6 empty] | CM_WSI | 100%
402531 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-02-07 | 2012-02-07 | 2012-04-02 | 2015-06-15 |  | Scottish Water Wide | 73297 | -4304.37 | 0 | 0 | 0 | 0 | 0 | -4304.37 | 0 | 68992.63 | 0 | [6 empty] | CM_WSI | 100%
402505 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2012-01-27 | 2012-05-16 | 2012-06-06 | 2013-05-23 |  | Scottish Water Wide | 53570.03 | 0.97 | -974.87 | 0 | 0 | 0 | 0 | -973.9 | 0 | 52596.13 | 0 | [6 empty] | QS4EQS | 100%
402740 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2012-06-12 | 2012-12-10 | 2016-03-03 | 2016-03-03 |  | Scottish Water Wide | 621170.81 | -60854.82 | 0 | 0 | 0 | 0 | 0 | -60854.82 | 0 | 560315.99 | 0 | [6 empty] | CM_M&G | 100%
502904 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW1 | 2021-08-05 | 2023-03-01 | 2023-07-12 | 2024-09-27 | 2024-12-30 | South Lanarkshire | 0 | 0 | 0 | 36613.025 | 8653.255 | 629.02 | 950.49 | 46845.79 | 2753154.08 | 2799999.87 | 0 | [6 empty] | CM_WWNI | 100%
500503 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-15 | 2021-03-05 | 2021-03-05 | Scottish Water Wide | 0 | 102535.26 | 27164.74 | -28700 | 71568.58 | 60000 | 119582.25 | 352150.83 | 0 | 352150.83 | 0 | [6 empty] | CM_M&G | 100%
404067 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS3 | 2015-06-15 | 2015-07-22 | 2015-07-22 | 2021-02-01 | 2021-05-01 | Scottish Water Wide | 0 | 36200 | 1252.6 | 0 | 154319.4 | 551704.97 | 633900.66 | 1377377.63 | 98622.41 | 1476000.04 | 809440.5607 | [6 empty] | DW1B | 100%
500962 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2015-12-09 | 2015-12-09 | 2016-01-05 | 2021-03-01 | 2021-03-01 | Scottish Water Wide | 0 | 106216 | 5863 | 19156 | 2416 | 33173.52 | 33175.48 | 200000 | 0 | 200000 | 0 | [6 empty] | CM_WWI | 100%
500975 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-11-26 | 2016-07-13 | 2016-09-07 | 2020-02-14 | 2020-02-17 | Scottish Water Wide | 0 | 129944.09 | 936820.91 | 102512.7815 | 395762.7085 | 348173.75 | 171315.79 | 2084530.03 | 155910.78 | 2240440.81 | 0 | [6 empty] | CM_WSI | 100%
502274 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-06-02 | 2022-12-20 | 2023-04-10 | 2024-03-29 | 2024-03-29 | Scottish Water Wide | 0 | 0 | 4500 | 24720.73 | 3721.764 | 5564.79 | 5543.23 | 44050.514 | 1783404.03 | 1827454.544 | 0 | [6 empty] | CM_WSI | 100%
500625 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | -34702577.7 | -44115891.23 | -39541230.0096 | -43137127.9089 | 0 | 0 | -161496826.8485 | 0 | -161496826.8485 | 0 | [6 empty] | CM_OVH | 100%
500936 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-12-16 | 2015-12-16 | 2016-02-01 | 2016-06-29 | 2016-07-29 | Scottish Water Wide | 0 | 933715.54 | 0 | 0 | 0 | 0 | 0 | 933715.54 | 0 | 933715.54 | 0 | [6 empty] | CM_WWI | 100%
502283 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2016-08-19 | 2016-08-19 | 2016-09-01 | 2017-04-06 | 2017-04-28 | Scottish Water Wide | 0 | 0 | 900000.13 | 0 | 0 | 0 | 0 | 900000.13 | 0 | 900000.13 | 0 | [6 empty] | CM_WWI | 100%
502717 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-04-24 | 2017-04-24 | 2017-08-15 | 2018-08-21 | 2018-08-21 | Scottish Water Wide | 0 | 0 | 0 | 829912.14 | 28758.87 | 0 | 0 | 858671.01 | 0 | 858671.01 | 0 | [6 empty] | CM_WWI | 100%
503233 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2019-05-15 | 2019-05-16 | Scottish Water Wide | 0 | 0 | 0 | 0 | 860214.1 | 107026.76 | 0 | 967240.86 | 0 | 967240.86 | 0 | [6 empty] | CM_WWI | 100%
503561 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2019-05-13 | 2019-05-13 | 2019-07-19 | 2020-02-20 | 2020-02-20 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 900000 | 0 | 900000 | 0 | [6 empty] | CM_WWI | 100%
402734 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2012-06-05 | 2012-08-07 | 2012-08-07 | 2015-11-02 |  | Scottish Water Wide | 346644.96 | 4293.72 | 0 | -1602.35 | 0 | 0 | 0 | 2691.37 | 0 | 349336.33 | 0 | [6 empty] | CM_M&G | 100%
500582 | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Wastewater |  | SWD | Energy efficiency | MS7 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2017-04-13 | 2017-05-15 | Scottish Water Wide | 0 | 670608.82 | 434191.63 | -54695.7885 | 0 | 0 | 0 | 1050104.6615 | 0 | 1050104.6615 | 142915.5062 | [6 empty] | I2S_WNI | 4.484% | I2S_WWNI | 95.52%
500488 | Q&S4 | Improving the customer experience | Meter Accuracy |  |  | Water |  | SWD | Meter Accuracy | MS3 | 2015-08-21 | 2017-02-16 | 2017-02-16 | 2021-02-26 | 2021-02-26 | Scottish Water Wide | 0 | 598398 | 3540587.47 | 2846271.62 | 3014742.91 | 2234000 | 2234000 | 14468000 | 0 | 14468000 | 4007137.1184 | [6 empty] | CS4 | 100%
500648 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-09-02 | 2015-09-02 | 2015-09-02 | 2021-03-05 | 2021-03-05 | Scottish Water Wide | 0 | 2254837 | 1460752.51 | 1795834.49 | 898486.43 | 344721.21 | 335368.36 | 7090000 | 0 | 7090000 | 0 | [6 empty] | CM_M&G | 100%
403962 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2015-05-08 | 2018-09-20 | 2018-09-24 | 2019-11-05 | 2019-11-06 | All West Unitary Authorities | 416.92 | 56415.08 | 73026.3 | 168417.32 | 384498.78 | 31188.18 | 3747.88 | 717293.54 | 2289.57 | 720000.03 | 0 |  |  |  |  | 1410 |  | CM_WSNI | 100%
403961 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2015-07-06 | 2018-09-25 | 2018-10-02 | 2019-10-11 | 2019-10-14 | All West Unitary Authorities | 1592 | 79112 | 90786.65 | 411886.8 | 750001.34 | 314260.75 | 9840.77 | 1655888.31 | 5399.02 | 1662879.33 | 0 |  |  |  |  | 12828 |  | CM_WSNI | 100%
403124 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS6 | 2013-01-14 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-03-01 | Highland | 124761.87 | 248383.46 | 745428.63 | 1239258.04 | 336579.23 | 0 | 0 | 2569649.36 | 0 | 2694411.23 | 777599.162 | [6 empty] | DW25P | 10% | DW2 | 90% | bar: Regulatory Outputs OMG-01
403912 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS0 | 2017-03-30 | 2019-12-02 | 2020-02-21 | 2020-10-01 | 2021-01-01 | East Dunbartonshire | 2862 | 100419.25 | 198122.71 | 112857.57 | 96770.47 | 328895.31 | 382008.78 | 1219074.09 | 3854.89 | 1225790.98 | 1439847.3197 | [6 empty] | EC01C | 100% | bar: Regulatory Outputs OMG-18
403332 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS1 | 2013-03-11 | 2021-01-11 | 2021-02-03 | 2021-03-31 | 2021-07-02 | North Lanarkshire | 153299.6 | 151055.4 | 107149.83 | 41027.8796 | -32532.7096 | 33182.84 | 218561.08 | 518444.32 | 328256.1 | 1000000.02 | 1528054.7284 | [6 empty] | CS11A | 5.6% | CS15 | 94.4%
403339 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS3 | 2013-03-08 | 2015-10-01 | 2016-01-05 | 2019-10-01 | 2020-02-01 | Glasgow City | 48494.57 | 322929.43 | 121396 | 2883 | -84190 | 148664 | 0 | 511682.43 | 0 | 560177 | 134102.4971 | [6 empty] | CS15 | 100%
403146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS4 | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2019-03-18 | 2019-05-16 | East Ayrshire | 184566.88 | 11479642.12 | 31562741 | 10316182.6945 | 990858.235 | 129986.88 | 0 | 54479410.9295 | 0 | 54663977.8095 | 4534308.9311 | [6 empty] | SR15_EXC_EXC | 4.3% | DW2 | 38.7% | CM_WSNI | 57%
403886 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | Highland | 5971.54 | 10521.58 | -16374.67 | 72.56 | 0 | 0 | 0 | -5780.53 | 0 | 191.01 | 1817908.3275 | [6 empty] | CS16W | 100%
403578 | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater |  | SWMD | Sludge | MS7 | 2013-10-02 | 2015-03-26 | 2015-03-31 | 2015-11-01 | 2016-03-01 | Highland | 102089.25 | 451535.75 | 289362.83 | 6160 | -4194.01 | 0 | 0 | 742864.57 | 0 | 844953.82 | 386799.4094 | [6 empty] | LA01 | 100% | bar: Regulatory Outputs OMG-24
403132 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS7 | 2012-12-10 | 2015-06-25 | 2015-09-15 | 2017-03-16 | 2017-03-16 | Glasgow City | 272215 | 2577916.96 | 613135.7 | 50348.75 | -4402.0868 | 0 | 0 | 3236999.3232 | 0 | 3509214.3232 | 2177735.1989 | [6 empty] | CS11 | 100%
403989 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-05-18 | 2018-01-23 | 2017-12-12 | 2017-12-12 | 2017-12-20 | Na H-Eileanan an Iar | 469.7 | 2055.3 | -2525 | 5691.226 | 70.44 | 0 | 0 | 5291.966 | 0 | 5761.666 | 1510557.3352 | [6 empty] | DW3B | 10% | DW25 | 90%
404037 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2015-02-17 | 2017-06-30 | 2017-09-11 | 2019-07-05 | 2018-03-26 | North Lanarkshire | 1240.88 | 9265.12 | 89805 | 740954 | 951091.8 | 6183.74 | 0 | 1797299.66 | 0 | 1798540.54 | 0 | [6 empty] | CM_WSI | 100%
404036 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-02-17 | 2021-05-10 | 2021-06-08 | 2023-03-02 | 2023-06-01 | North Lanarkshire | 2572.61 | 9110.76 | 171397.63 | 64409 | -6074 | 0 | 0 | 238843.39 | 3274473.94 | 3515889.94 | 0 | [6 empty] | CM_WSI | 100%
403773 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS6 | 2015-05-08 | 2016-03-30 | 2016-06-30 | 2017-06-01 | 2017-10-01 | Stirling | 464 | 87176 | 195777.05 | 114061.64 | -1638.08 | 12202.39 | 0 | 407579 | 0 | 408043 | 270597.9016 | [6 empty] | DW25P | 6.127% | CM_WSI | 19.61% | CM_WSNI | 74.27% | bar: Regulatory Outputs OMG-04
403126 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | WINF | DWQ Compliance | MS3 | 2013-02-06 | 2016-07-22 | 2016-09-12 | 2019-06-01 | 2019-09-01 | Na H-Eileanan an Iar | 115146.46 | 434026.54 | 1902777 | 179318 | 170104.64 | 5617.67 | 0 | 2691843.85 | 0 | 2806990.31 | 3246725.5604 |  |  |  |  | -190949.0003 |  | DW25 | 10% | DW3G | 20% | DW2 | 70% | bar: Regulatory Outputs OMG-01
403699 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS6 | 2014-03-31 | 2016-03-23 | 2016-03-28 | 2017-11-23 | 2020-10-27 | Dumfries and Galloway | 123564.93 | 334376.41 | 1263109.66 | 2469421.75 | 16588.2 | 10340.4 | 7815.42 | 4101651.84 | 0 | 4225216.77 | 745353.0903 |  |  |  |  | 8662 |  | DW3J | 9.313% | DW25P | 17.59% | DW3C | 73.1%
404052 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-02-17 | 2022-06-07 | 2022-08-24 | 2023-01-03 | 2023-03-28 | South Ayrshire | 960.29 | 1576.71 | 6608 | 0 | 54134 | 0 | 0 | 62318.71 | 724161 | 787440 | 0 | [6 empty] | CM_WSI | 100%
404051 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-02-17 | 2021-06-21 | 2021-07-12 | 2023-02-14 | 2023-05-17 | South Ayrshire | 2137.71 | 170738.29 | 351711 | -313672.87 | 85515 | 0 | 0 | 294291.42 | 1461891.99 | 1758321.12 | 0 | [6 empty] | CM_WSI | 100%
403821 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS7 | 2015-07-16 | 2018-06-28 | 2018-06-22 | 2018-06-20 | 2018-06-28 | South Ayrshire | 133140.04 | 177866.96 | -311007 | 471183.53 | -336267.1575 | 0 | 0 | 1776.3325 | 0 | 134916.3725 | 1582934.7791 | [6 empty] | DW25 | 100%
403453 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2013-05-08 | 2015-02-27 | 2015-04-09 | 2015-07-01 | 2015-09-01 | Argyll and Bute-North Argyll | 128562 | 99557.72 | 1185.91 | 12.36 | 0 | 0 | 0 | 100755.99 | 0 | 229317.99 | 445403.3913 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
403900 | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWD | SOSI | MS7 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-06-01 | 2016-07-01 | Stirling | 576.81 | 48350.75 | -48927.56 | 0 | 0 | 0 | 0 | -576.81 | 0 | 2.2737e-12 | 240464.472 | [6 empty] | WR1 | 100%
403333 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2013-03-11 | 2017-04-07 | 2017-08-09 | 2016-10-11 | 2017-08-09 | Glasgow City | 54885 | 7541 | 29116.75 | -8192.38 | 0 | 0 | 0 | 28465.37 | 0 | 83350.37 | 1635990.1045 | [6 empty] | CS11 | 100%
403964 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-07-23 | 2022-08-08 | 2022-09-08 | 2023-11-20 | 2024-08-16 | North Ayrshire | 1369 | 52099 | -5027 | 740.47 | 5752.19 | 0 | 0 | 53564.66 | 2844618.02 | 2899551.68 | 0 | [6 empty] | CM_WSI | 100%
403703 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2014-03-17 | 2018-12-17 | 2019-02-28 | 2018-11-20 | 2018-11-20 | Fife | 90696 | 25304 | 47801.81 | 32198.19 | 12726.649 | 0 | 0 | 118030.649 | 0 | 208726.649 | 229318.7788 | [6 empty] | CS11 | 100%
403986 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS0 | 2015-07-06 | 2019-05-13 | 2019-10-09 | 2021-03-23 | 2021-07-06 | Stirling | 4578 | 45522 | 61549.95 | 134763.29 | 270042.19 | 756502.62 | 1807271.69 | 3075651.74 | 114416.45 | 3194646.19 | 0 | [6 empty] | CM_WSNI | 100%
403340 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS6 | 2013-03-08 | 2015-11-24 | 2016-04-04 | 2017-03-31 | 2017-03-31 | Glasgow City | 94114 | 1388608 | 419184 | 9406.05 | 5933.6487 | 0 | 0 | 1823131.6987 | 0 | 1917245.6987 | 904764.0232 | [6 empty] | CS15 | 100%
403985 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2025-05-12 | 2026-09-18 | 2027-01-18 | 2027-09-03 | 2027-12-06 | West Dunbartonshire | 457 | 154.96 | 6682.74 | 12781.92 | 0 | 0 | 0 | 19619.62 | 2479923.31 | 2499999.93 | 0 | [6 empty] | CM_WSNI | 100%
404046 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-02-03 | 2016-04-22 | 2016-04-08 | 2017-05-30 | 2017-05-26 | Argyll and Bute-Cowal & Bute | 9046.26 | 1051930.74 | 1247733 | 1015124 | 25.9962 | 0 | 0 | 3314813.7362 | 0 | 3323859.9962 | 0 | [6 empty] | CM_WWI | 100%
403321 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS0 | 2013-02-26 | 2020-05-18 | 2020-07-10 | 2022-03-21 | 2022-03-21 | North Lanarkshire | 219212 | 108646 | 81632 | 12281 | 115328 | 499561.36 | 4446086.46 | 5263534.82 | 5250366.17 | 10733112.99 | 3900700.8261 | [6 empty] | CS11 | 100%
403341 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS0 | 2013-03-11 | 2020-01-27 | 2020-04-08 | 2021-05-01 | 2021-08-01 | North Lanarkshire | 47744 | 8110 | -608.41 | 60557.4116 | 120196.9984 | 185769.99 | 1541290.48 | 1915316.47 | 536939.55 | 2500000.02 | 999635.3673 | [6 empty] | CS15 | 100%
404068 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS3 | 2015-03-19 | 2015-09-08 | 2015-10-01 | 2021-03-01 | 2021-03-01 | Scottish Water Wide | 0 | 500800 | 1118772.17 | 831609.17 | 607138.78 | 366902.79 | 1059325.12 | 4484548.03 | 310966.19 | 4795514.22 | 2009645.5303 | [6 empty] | DW1C | 100%
403822 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2014-05-27 | 2015-12-04 | 2016-01-08 | 2017-03-01 | 2017-05-01 | South Lanarkshire | 268.29 | 63731.71 | 58000 | -694.21 | 652.6 | 0 | 0 | 121690.1 | 0 | 121958.39 | 118018.5592 | [6 empty] | DW25TS | 100% | bar: Regulatory Outputs OMG-47
403517 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2013-08-20 | 2015-03-23 | 2015-03-23 | 2020-07-06 | 2020-07-06 | Falkirk | 187681 | 8427.43 | 0 | 0 | 0 | 0 | 0 | 8427.43 | 0 | 196108.43 | 0 | [6 empty] | EC06 | 100%
403696 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS7 | 2014-03-03 | 2014-12-05 | 2015-01-12 | 2015-09-28 | 2015-09-28 | East Renfrewshire | 731680 | 160320 | 0 | 6568.36 | 0 | 0 | 0 | 166888.36 | 0 | 898568.36 | 603987.952 | [6 empty] | CS11 | 100%
404043 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-01-21 | 2016-01-11 | 2016-02-15 | 2016-04-22 | 2016-08-08 | West Lothian | 762.62 | 143071.38 | 10671.53 | 358.8 | -2527.9553 | 0 | 0 | 151573.7547 | 0 | 152336.3747 | 0 | [6 empty] | CM_WWI | 100%
403074 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS7 | 2013-07-29 | 2013-12-20 | 2013-12-20 | 2015-04-08 | 2015-04-08 | Scottish Water Wide | 248517 | -3112.38 | 0 | 0 | 0 | 0 | 0 | -3112.38 | 0 | 245404.62 | 5792.4564 | [6 empty] | DW5A | 100%
403963 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2015-07-06 | 2018-03-01 | 2018-03-16 | 2020-02-01 | 2020-02-01 | Renfrewshire | 903 | 119394 | 20772.71 | 320664.15 | 2240762.01 | 1946969.46 | 175420.03 | 4823982.36 | 25920.39 | 4850805.75 | 0 | [6 empty] | CM_M&G | 3.7% | CM_WSNI | 8.07% | DW25 | 88.23% | bar: Regulatory Outputs OMG-05
403695 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2014-04-09 | 2017-02-10 | 2016-06-28 | 2016-06-28 | 2017-02-10 | West Dunbartonshire | 8887 | 113 | -6.49 | 0 | 0 | 0 | 0 | 106.51 | 0 | 8993.51 | 145185.8872 | [6 empty] | CS11 | 100%
403223 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2012-12-20 | 2015-12-18 | 2016-02-22 | 2016-07-01 | 2017-03-01 | North Lanarkshire | 69532.94 | 168732.06 | 100767.23 | 1681.99 | -5603.9225 | 0 | 0 | 265577.3575 | 0 | 335110.2975 | 292799.6085 | [6 empty] | EC01F | 100% | [18 empty] | Regulatory Outputs OMG-18: 4
403224 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2012-12-21 | 2015-05-21 | 2016-03-08 | 2016-06-23 | 2017-03-31 | North Lanarkshire | 20388.55 | 45678.45 | 10898.6 | 0.02 | 1538.9582 | 0 | 0 | 58116.0282 | 0 | 78504.5782 | 292799.6085 | [6 empty] | EC01F | 100%
403225 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2012-12-20 | 2015-07-23 | 2015-07-29 | 2015-08-11 | 2015-08-11 | Na H-Eileanan an Iar | 8010 | -60.59 | -637.62 | 0 | 0 | 0 | 0 | -698.21 | 0 | 7311.79 | 0 | [6 empty] | EC10B | 100%
403226 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS5 | 2012-12-20 | 2018-11-21 | 2019-01-18 | 2019-02-01 | 2019-03-01 | North Lanarkshire | 8700.18 | 3490.81 | 4084.86 | 53724.15 | 11816 | 406.34 | 233.16 | 73755.32 | 210.48 | 82665.98 | 45737.7598 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
403227 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS1 | 2012-12-21 | 2019-05-20 | 2019-07-19 | 2019-09-25 | 2019-09-25 | North Lanarkshire | 10425.84 | 61.56 | 2269.21 | 23243.39 | 22220 | 156780 | 0 | 204574.16 | 0 | 215000 | 292799.6085 | [6 empty] | EC10B | 100%
403228 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2012-12-21 | 2015-05-20 | 2015-08-30 | 2016-06-23 | 2016-06-23 | North Lanarkshire | 80851 | 800519 | 223218.25 | 8411.75 | -4571.4384 | 0 | 0 | 1027577.5616 | 0 | 1108428.5616 | 292799.6085 | [6 empty] | EC01C | 100%
403229 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2012-12-20 | 2015-10-09 | 2015-10-12 | 2015-10-01 | 2015-10-01 | East Renfrewshire | 4032 | 111.61 | 0 | 0 | 0 | 0 | 0 | 111.61 | 0 | 4143.61 | 41237.6041 | [6 empty] | EC10B | 100% | [18 empty] | Regulatory Outputs OMG-18: 2
403230 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2012-12-21 | 2015-08-27 | 2015-08-27 | 2015-08-01 | 2015-11-01 | East Renfrewshire | 32828 | -635.43 | 0 | 0 | 0 | 0 | 0 | -635.43 | 0 | 32192.57 | 323691.1705 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-18
403231 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2012-12-20 | 2016-03-21 | 2016-03-29 | 2016-12-01 | 2017-03-01 | Renfrewshire | 24966.1 | 137033.9 | 503705.12 | -762.6075 | 3947.277 | 0 | 0 | 643923.6895 | 0 | 668889.7895 | 432627.2362 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
403232 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWD | UWWTD - UID | MS7 | 2012-12-21 | 2017-03-27 | 2017-03-27 | 2016-09-12 | 2017-03-27 | East Renfrewshire | 38936 | 3607.64 | -40950.01 | 317.9 | 49.308 | 0 | 0 | -36975.162 | 0 | 1960.838 | 19932.9779 | [6 empty] | EC01F | 100%
403233 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWD | UWWTD - Works | MS7 | 2012-12-21 | 2018-01-31 | 2018-01-31 | 2016-02-23 | 2018-01-31 | East Renfrewshire | 3657.39 | 77.97 | 62.88 | 61.56 | 0 | 0 | 0 | 202.41 | 0 | 3859.8 | 0 | [6 empty] | EC01B | 100%
403234 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS6 | 2012-12-20 | 2016-03-31 | 2016-03-31 | 2018-07-01 | 2018-10-01 | East Renfrewshire | 41666 | 332748 | 300030 | 1206760.6455 | 386457.0461 | 3014.98 | 0.02 | 2229010.6916 | 0 | 2270676.6916 | 222066.9736 | [6 empty] | EC01F | 100% | [18 empty] | Regulatory Outputs OMG-18: 2
403235 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2012-12-20 | 2015-02-25 | 2015-02-25 | 2015-02-26 | 2015-02-26 | East Renfrewshire | 5437.62 | 1027.19 | -3700.97 | 0 | 0 | 0 | 0 | -2673.78 | 0 | 2763.84 | 0 | [6 empty] | EC10B | 100%
403237 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2012-12-21 | 2015-07-24 | 2015-09-01 | 2016-12-01 | 2017-03-01 | South Lanarkshire | 77028.21 | 322971.79 | 35277 | 0 | -17784.9556 | 0 | 0 | 340463.8344 | 0 | 417492.0444 | 530687.192 | [6 empty] | EC01F | 100% | [18 empty] | Regulatory Outputs OMG-18: 3
403238 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS1 | 2012-12-21 | 2019-06-17 | 2019-09-16 | 2020-09-01 | 2020-12-01 | Renfrewshire | 71950 | -6946 | 16017.85 | 83978.15 | 138362 | 856980.08 | 587044.67 | 1675436.75 | 3671.35 | 1751058.1 | 394570.2845 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
403239 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2012-12-21 | 2015-05-18 | 2015-08-03 | 2015-09-07 | 2016-01-28 | South Lanarkshire | 6249 | 29129 | 1609 | 769 | -940.0312 | 0 | 0 | 30566.9688 | 0 | 36815.9688 | 41237.6041 | [6 empty] | EC01F | 100%
403240 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2012-12-21 | 2015-08-06 | 2015-11-09 | 2016-08-01 | 2017-03-01 | South Lanarkshire | 109784.3 | 1086326.7 | 268191 | -14511.82 | 1569.097 | 0 | 0 | 1341574.977 | 0 | 1451359.277 | 400840.7103 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
403241 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2012-12-21 | 2016-02-24 | 2016-03-31 | 2016-09-01 | 2017-03-01 | East Renfrewshire | 145218.94 | 351196.06 | 543503 | 0 | -20315.0298 | 0 | 0 | 874384.0302 | 0 | 1019602.9702 | 169820.6819 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
403242 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2012-12-20 | 2015-03-30 | 2015-03-30 | 2015-07-01 | 2015-11-01 | East Renfrewshire | 65947 | -823.51 | 142.35 | 0 | 0 | 0 | 0 | -681.16 | 0 | 65265.84 | 687137.827 | [6 empty] | EC10B | 100% | bar: Regulatory Outputs OMG-18
403243 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS5 | 2013-02-11 | 2018-05-25 | 2018-07-06 | 2019-02-01 | 2019-03-01 | East Renfrewshire | 82052 | 37660 | 40158 | 170133 | 363640 | 9078.71 | 220.28 | 620889.99 | 0 | 702941.99 | 257933.2894 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
403244 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS3 | 2013-02-18 | 2018-06-27 | 2018-08-17 | 2019-11-01 | 2020-02-01 | East Renfrewshire | 36223 | 14990 | 23121 | 145959 | 2094062 | 1095166 | 0 | 3373298 | 0 | 3409521 | 738056.9161 |  |  |  |  | 12780 |  | CS11 | 49.19% | EC01F | 50.81% | [16 empty] | Regulatory Outputs OMG-18: 4
403245 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS5 | 2013-02-13 | 2018-06-27 | 2018-06-27 | 2018-06-28 | 2018-06-28 | East Renfrewshire | 14875 | -1968.8 | 293.8 | 707 | -221 | 0 | 0 | -1189 | 0 | 13686 | 217925.0763 | [6 empty] | EC01F | 100%
403246 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS5 | 2013-02-13 | 2018-06-27 | 2018-06-27 | 2018-06-28 | 2018-06-28 | East Renfrewshire | 14897 | -1610 | -87 | 909 | -840.84 | 0 | 0 | -1628.84 | 0 | 13268.16 | 217925.0763 | [6 empty] | EC01F | 100%
403247 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS5 | 2013-02-18 | 2018-06-27 | 2018-06-27 | 2018-06-28 | 2018-06-28 | East Renfrewshire | 5745 | -698.56 | 153.56 | 601 | 1247.145 | 0 | 0 | 1303.145 | 0 | 7048.145 | 217925.0763 | [6 empty] | EC01F | 100%
403248 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2013-03-08 | 2015-07-30 | 2015-09-07 | 2016-02-01 | 2016-04-01 | Glasgow City | 51628.36 | 294074.64 | 7888.5 | 809.5 | -4047.0858 | 0 | 0 | 298725.5542 | 0 | 350353.9142 | 165625.947 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
403249 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS6 | 2013-02-18 | 2016-12-13 | 2017-01-23 | 2018-03-01 | 2018-03-01 | East Renfrewshire | 71777 | 14454 | 532981 | 268563.32 | -26961.6106 | 0 | 0 | 789036.7094 | 0 | 860813.7094 | 635193.3411 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
403250 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2013-02-18 | 2015-08-11 | 2015-10-26 | 2016-02-01 | 2016-04-01 | North Lanarkshire | 51161.17 | 186672.83 | -2155.91 | 658.22 | -1733.6304 | 0 | 0 | 183441.5096 | 0 | 234602.6796 | 347157.6864 | [6 empty] | EC01F | 3.036% | EC01B | 96.96% | bar: Regulatory Outputs OMG-18
403251 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS7 | 2013-02-11 | 2015-10-27 | 2016-01-25 | 2016-09-20 | 2017-03-31 | South Lanarkshire | 79127.31 | 425520.69 | 405314 | 5038 | -12783.9706 | 0 | 0 | 823088.7194 | 0 | 902216.0294 | 530687.192 | [6 empty] | EC01F | 100%
403640 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS7 | 2013-12-06 | 2016-12-14 | 2016-12-14 | 2016-12-15 | 2017-01-13 | East Renfrewshire | 5656.83 | 2640.68 | -7465.53 | 0 | 0 | 0 | 0 | -4824.85 | 0 | 831.98 | 222066.9736 | [6 empty] | EC01F | 100%
403639 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS6 | 2013-12-17 | 2018-02-26 | 2018-03-13 | 2018-06-26 | 2018-10-16 | East Renfrewshire | 420.54 | 160.98 | 149.88 | 18698.6 | 3488 | 0 | 0 | 22497.46 | 0 | 22918 | 222066.9736 | [6 empty] | EC01F | 100%
403747 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS4 | 2014-03-17 | 2018-11-22 | 2019-01-18 | 2019-02-01 | 2019-03-01 | North Lanarkshire | 105900 | 77125 | 75913.11 | 54061.89 | 79000 | 527.18 | 553.87 | 287181.05 | 512.91 | 393593.96 | 45737.7598 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
403746 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2014-03-17 | 2015-02-25 | 2015-03-09 | 2015-02-26 | 2020-02-11 | East Renfrewshire | 16150.62 | -0.01 | -427.05 | 0 | 0 | 0 | 0 | -427.06 | 0 | 15723.56 | 0 | [6 empty] | EC01B | 100%
403913 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS5 | 2015-10-27 | 2017-06-30 | 2017-12-05 | 2019-01-01 | 2019-03-01 | South Lanarkshire | 2994.55 | 28764.45 | 48579 | 494189 | 722792.32 | 9916 | 0 | 1304240.77 | 0 | 1307235.32 | 375545.442 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
404031 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWD | UWWTD - UID | MS7 | 2018-05-10 | 2018-08-16 | 2018-08-16 | 2018-08-16 | 2018-08-16 | East Renfrewshire | 1040 | 7210 | 84923.72 | 38009.2346 | 20210.99 | 0 | 0 | 150353.9446 | 0 | 151393.9446 | 854007.5029 | [6 empty] | EC01B | 100%
403922 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2019-06-03 | 2019-10-21 | 2019-10-28 | 2019-10-28 | 2019-10-28 | City of Edinburgh | 610 | 18500 | 39493.61 | 24896.39 | 37500 | 305000 | 0 | 425390 | 0 | 426000 | 229318.7788 | [6 empty] | CS11 | 100%
404039 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2018-06-07 | 2018-09-17 | 2018-09-17 | 2018-09-17 | 2018-09-17 | West Lothian | 976 | 8000 | 43718.92 | 43207.08 | 3256.4905 | 0 | 0 | 98182.4905 | 0 | 99158.4905 | 586049.2492 | [6 empty] | CS11 | 100%
404027 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW2 | 2019-07-01 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | East Lothian | 610 | 12000 | 44545.69 | 17844.31 | 20000 | 202000 | 0 | 296390 | 0 | 297000 | 581579.34 | [6 empty] | CS11 | 100%
403919 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2016-12-16 | 2016-12-16 | 2016-12-16 | 2016-06-28 | 2016-12-16 | Falkirk | 0 | 37221 | -37221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CS11 | 100%
404083 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2016-10-14 | 2016-10-14 | 2016-10-14 | 2016-09-06 | 2016-10-14 | Fife | 0 | 37062 | -17890.07 | 0 | 0 | 0 | 0 | 19171.93 | 0 | 19171.93 | 65127.3387 | [6 empty] | CS11 | 100%
404023 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW2 | 2019-09-02 | 2020-01-13 | 2020-01-20 | 2020-01-20 | 2020-01-20 | Fife | 244 | 36256 | 33122.89 | 31801.4975 | 8575.6125 | 0 | 0 | 109756 | 0 | 110000 | 32111.6878 | [6 empty] | CS11 | 100%
404028 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2017-10-17 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | Fife | 610 | 10000 | 28818.95 | -39428.95 | 0 | 0 | 0 | -610 | 0 | 0 | 32514.3933 | [6 empty] | CS11 | 100%
403923 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS0 | 2018-02-28 | 2019-10-21 | 2020-02-03 | 2021-02-17 | 2021-05-25 | Dumfries and Galloway | 1053 | 89584 | 19354.29 | 42161.2886 | 249364.4214 | 1895259.82 | 2947030.1 | 5242753.92 | 141975.14 | 5385782.06 | 229318.7788 | [6 empty] | CS11 | 100%
403924 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-06-05 | 2018-06-05 | 2018-02-26 | 2018-06-05 | 2018-06-05 | Dumfries and Galloway | 702 | 35056 | 28244 | -63433.0704 | 222.2004 | 0 | 0 | 89.13 | 0 | 791.13 | 229318.7788 | [6 empty] | CS11 | 100%
403133 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS2 | 2012-11-30 | 2019-03-29 | 2019-05-01 | 2019-05-01 | 2019-05-01 | East Renfrewshire | 217087.56 | 144912.44 | 29853 | -10860.8159 | 37007.8159 | 0 | 0 | 200912.44 | 0 | 418000 | 736691.1226 | [6 empty] | CS11 | 100%
402948 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS1 | 2012-09-17 | 2019-12-16 | 2020-04-06 | 2021-05-25 | 2021-08-27 | Argyll and Bute-North Argyll | 76322 | 179928 | 378616 | 130911.78 | 805375.3 | 726039.9 | 2682381.08 | 4903252.06 | 517086.96 | 5496661.02 | 0 | [6 empty] | CM_WWI | 100%
402868 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2012-08-21 | 2012-08-21 | 2012-09-05 | 2016-06-28 | 2016-09-29 | Scottish Water Wide | 439421.78 | 0.22 | 0 | 0 | 0 | 0 | 0 | 0.22 | 0 | 439422 | 0 | [6 empty] | QS4EQS | 50% | QS4EQW | 50%
403641 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS0 | 2014-01-13 | 2019-05-27 | 2019-05-27 | 2019-05-27 | 2019-05-27 | Shetland Islands | 66493.66 | 807226.83 | 350121.99 | 32658.13 | 6091.48 | 870.25 | 0 | 1196968.68 | 0 | 1263462.34 | 1375891.4543 | [6 empty] | DW23 | 50% | DW25 | 50%
404019 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2021-06-03 | 2022-04-01 | 2022-06-13 | 2022-12-23 | 2022-12-26 | Aberdeen City | 1830 | 25289.01 | 26223.67 | 728.63 | 0 | 0 | 0 | 52241.31 | 894135.71 | 948207.02 | 0 | [6 empty] | SG1 | 100%
403511 | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2013-09-09 | 2014-05-30 | 2014-06-23 | 2018-11-26 | 2017-03-26 | Scottish Water Wide | 2081306 | 43366 | 333457 | 2500 | 193414.2 | 0 | 0 | 572737.2 | 0 | 2654043.2 | 561676.3877 | [6 empty] | CS11 | 50% | CS15 | 50%
402747 | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS7 | 2012-11-27 | 2013-08-20 | 2014-04-28 | 2018-12-12 | 2017-09-15 | Scottish Water Wide | 96082 | 35531 | 38287 | 39700 | 50551.904 | 0 | 0 | 164069.904 | 0 | 260151.904 | 0 | [6 empty] | WG4 | 100%
403714 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2014-04-08 | 2014-09-30 | 2014-11-03 | 2015-02-01 | 2015-06-01 | Argyll and Bute-Cowal & Bute | 123559.37 | -11670.37 | 0 | 0 | 0 | 0 | 0 | -11670.37 | 0 | 111889 | 0 | [6 empty] | EC06 | 100% | bar: Regulatory Outputs OMG-24
404006 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2014-11-27 | 2015-07-22 | 2015-07-22 | 2015-07-22 |  | Scottish Water Wide | 365.85 | 949.71 | 0 | 0 | 0 | 0 | 0 | 949.71 | 0 | 1315.56 | 0 | [6 empty] | DW5 | 100%
403304 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2013-01-11 | 2013-07-08 | 2013-07-15 | 2016-09-27 |  | Scottish Water Wide | 69898 | 0 | 0 | 0 | -733.84 | 0 | 0 | -733.84 | 0 | 69164.16 | 0 | [6 empty] | QS4EQS | 100%
403715 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2014-05-21 | 2014-11-21 | 2014-12-08 | 2015-03-01 | 2015-06-01 | Aberdeenshire | 77085.5 | -22774.08 | 0 | 0 | 0 | 0 | 0 | -22774.08 | 0 | 54311.42 | 0 | [6 empty] | EC06 | 100% | bar: Regulatory Outputs OMG-24
403987 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2015-05-08 | 2021-12-06 | 2022-03-03 | 2023-01-04 | 2023-04-19 | Falkirk | 1037 | 115199 | 126148.87 | -43517.72 | 8889.91 | 0 | 0 | 206720.06 | 1451815.99 | 1659573.05 | 0 | [6 empty] | CM_WSNI | 100%
403134 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS1 | 2012-12-10 | 2021-07-02 | 2021-07-29 | 2022-01-24 | 2022-01-24 | East Renfrewshire | 157504.8 | 89711.2 | 31098 | 39104.5057 | 34581.4943 | 5000 | 0 | 199495.2 | 0 | 357000 | 1797150 | [6 empty] | CS11 | 100%
404093 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS0 | 2015-07-06 | 2019-10-28 | 2019-11-04 | 2021-04-30 | 2021-08-19 | Inverclyde | 0 | 49622 | 35985.38 | 127284.67 | 57923.55 | 428371.04 | 2441722.44 | 3140909.08 | 53736.93 | 3194646.01 | 0 | [6 empty] | CM_WSNI | 100%
404022 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-10-16 | 2021-10-18 | 2021-12-31 | 2022-07-28 | 2022-10-26 | Perth and Kinross | 610 | 9000 | 1699 | 3691 | 10000 | 3612.24 | 61025.48 | 89027.72 | 210362.19 | 299999.91 | 229318.7788 | [6 empty] | CS11 | 100%
403334 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS1 | 2013-03-08 | 2019-09-20 | 2019-10-10 | 2019-10-01 | 2020-01-01 | North Lanarkshire | 103900 | 369283 | -155711.77 | 44484.234 | 57044.536 | 221000 | 0 | 536100 | 0 | 640000 | 386295.6974 | [6 empty] | CS11A | 100%
403978 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS6 | 2015-03-10 | 2016-03-23 | 2016-03-29 | 2018-06-01 | 2018-08-01 | Argyll and Bute-Cowal & Bute | 294.85 | 75490.15 | 132349.34 | 623547.66 | 15230 | 109 | 1777 | 848503.15 | 0 | 848798 | 386043.824 | [6 empty] | EC01A | 100% | [18 empty] | Regulatory Outputs OMG-17: 2
403977 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS7 | 2015-03-10 | 2016-03-23 | 2016-03-29 | 2018-06-21 | 2018-06-21 | All West Unitary Authorities | 4055.75 | 5727.25 | 1217 | 0 | -3508.155 | 0 | 0 | 3436.095 | 0 | 7491.845 | 386043.824 | [6 empty] | EC01A | 100%
404077 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-01-26 | 2016-07-06 | 2016-07-06 | 2016-07-06 | 2016-07-06 | Aberdeen City | 10.63 | 0 | 955.43 | 0 | 0 | 0 | 0 | 955.43 | 0 | 966.06 | 0 | [6 empty] | CM_WSI | 100%
404076 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-01-23 | 2016-03-02 | 2016-03-02 | 2016-02-25 | 2016-03-02 | Aberdeen City | 173.85 | 5707.27 | 955.44 | 0 | 0 | 0 | 0 | 6662.71 | 0 | 6836.56 | 0 | [6 empty] | CM_WSI | 100%
404078 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-01-26 | 2016-03-02 | 2016-03-02 | 2016-03-02 | 2016-03-02 | Aberdeen City | 129.07 | 3621.82 | 955.45 | 0 | 0 | 0 | 0 | 4577.27 | 0 | 4706.34 | 0 | [6 empty] | CM_WSI | 100%
404079 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS7 | 2015-01-26 | 2016-03-02 | 2016-03-02 | 2016-03-02 | 2016-03-02 | Aberdeenshire | 54.27 | 4018.52 | 1715.52 | -45.97 | 0 | 0 | 0 | 5688.07 | 0 | 5742.34 | 0 | [6 empty] | CM_WSI | 100%
403965 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-11-02 | 2018-08-15 | 2018-10-08 | 2020-08-04 | 2020-08-04 | Stirling | 4148 | 122014 | 325241.13 | 161719.87 | 2853686.95 | 6752416.72 | 2291922.58 | 12507001.25 | 12876.72 | 12524025.97 | 0 | [6 empty] | CM_WSI | 100%
403754 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS6 | 2014-04-04 | 2015-03-24 | 2016-03-29 | 2017-03-01 | 2018-03-01 | Stirling | 44420.33 | 135629.67 | 186254.23 | 323509.695 | 65756.635 | 1724.18 | 391.86 | 713266.27 | 0 | 757686.6 | 490207.4615 | [6 empty] | DW3C | 3.33% | CM_WSNI | 96.67% | bar: Regulatory Outputs OMG-01
403971 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS3 | 2015-03-10 | 2016-03-23 | 2016-04-01 | 2019-05-01 | 2019-06-01 | Argyll and Bute-Cowal & Bute | 8825.01 | 26162.08 | 285814.91 | 254671 | -49000 | 12081 | 0 | 529728.99 | 0 | 538554 | 432097.299 |  |  |  |  | 1500 |  | EC01A | 100% | bar: Regulatory Outputs OMG-17
403335 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS1 | 2013-03-08 | 2019-12-20 | 2019-12-20 | 2019-12-20 | 2019-12-20 | East Renfrewshire | 135662 | 201461 | 2251 | 3626 | 34498.9499 | 0 | 0 | 241836.9499 | 0 | 377498.9499 | 176952.2387 | [6 empty] | CS11 | 100%
403532 | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS3 | 2013-08-27 | 2016-10-31 | 2017-03-27 | 2020-07-01 | 2020-10-01 | Highland | 298171 | 119457 | 131619.98 | 689711.18 | 54630.26 | 8246.56 | 276910.79 | 1280575.77 | 8246.92 | 1586993.69 | 997705.3078 |  |  |  |  | 15000 |  | WG4A | 10% | WG4 | 90% | bar: Regulatory Outputs OMG-08
404007 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-03-26 | 2019-03-13 | 2019-03-15 | 2021-06-11 | 2021-09-06 | Renfrewshire | 2446.9 | 80574.1 | 145801.3 | -476.98 | 450339.82 | 1461868.89 | 2206433.1 | 4344540.23 | 464546.82 | 4811533.95 | 0 | [6 empty] | CM_WWNI | 100%
403671 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS5 | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2019-02-27 | 2019-03-28 | Scottish Water Wide | 142211.46 | 645864.54 | 272100.84 | 371172.33 | 273425.5 | 197338.49 | 18293.85 | 1778195.55 | 0 | 1920407.01 | 0 | [6 empty] | EC06 | 100%
404092 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2015-05-08 | 2016-12-21 | 2017-01-24 | 2017-10-25 | 2017-10-25 | Scottish Water Wide | 0 | 65609 | 91570 | 214265 | 6868.91 | 1687.09 | 0 | 380000 | 0 | 380000 | 0 | [6 empty] | CM_WWNI | 100%
404054 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS4 | 2015-01-05 | 2016-09-23 | 2016-10-17 | 2017-08-10 | 2017-09-12 | Perth and Kinross | 26905 | 117253 | 736079 | 379687 | 148192.43 | 0 | 0 | 1381211.43 | 0 | 1408116.43 | 0 | [6 empty] | CM_WSI | 100%
403452 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2013-05-08 | 2015-03-10 | 2015-06-22 | 2015-12-01 | 2016-02-01 | Argyll and Bute-North Argyll | 45212.23 | 122343.32 | 6983.74 | -3939.25 | 0 | 0 | 0 | 125387.81 | 0 | 170600.04 | 142961.7788 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
404044 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2014-12-19 | 2021-07-19 | 2021-08-23 | 2021-12-10 | 2018-06-28 | Highland | 4644 | 74372 | -35878 | 44477 | 14924.43 | 0 | 0 | 97895.43 | 839195.56 | 941734.99 | 0 | [6 empty] | CM_WSI | 100%
404045 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS0 | 2015-01-05 | 2021-05-10 | 2021-06-07 | 2022-04-13 | 2022-05-16 | Highland | 1760.27 | 37997.73 | 15157 | 12962.46 | 38605.54 | 0 | 0 | 104722.73 | 641667.02 | 748150.02 | 0 | [6 empty] | CM_WSI | 100%
403127 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS3 | 2013-03-04 | 2018-02-28 | 2018-03-27 | 2020-09-01 | 2022-03-01 | Highland | 339720.5 | 331010.5 | 332847.72 | 1797860.93 | 8866701.47 | 9603878.5 | 744397.63 | 21676696.75 | 194030.75 | 22210448 | 4871598.0264 | [6 empty] | DW25P | 8.232% | DW3G | 8.232% | CM_WSI | 9.655% | DW2 | 73.88% | [12 empty] | Regulatory Outputs OMG-01: 2
403996 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS3 | 2016-04-25 | 2018-11-30 | 2019-01-07 | 2019-08-20 | 2019-08-26 | Highland | 3416 | 61388.08 | 61046.45 | 299936.29 | 777663.69 | 667691.97 | 8671.6 | 1876398.08 | 3407.91 | 1883221.99 | 1858328.8226 |  |  |  |  | 16640.0004 |  | DW23 | 100%
403774 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS6 | 2015-05-08 | 2016-03-31 | 2016-08-02 | 2017-06-01 | 2018-03-01 | Stirling | 700 | 98793 | 206717.76 | 153149.62 | -17264.03 | 1595 | 0 | 442991.35 | 0 | 443691.35 | 539388.337 | [6 empty] | DW3C | 5.68% | CM_WSNI | 94.32% | bar: Regulatory Outputs OMG-01
403995 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS0 | 2016-04-01 | 2020-05-11 | 2020-09-18 | 2022-07-01 | 2022-08-01 | Highland | 0 | 644.54 | 3773.58 | 67044.82 | -17463.93 | 79851.46 | 425624.26 | 559474.73 | 940525.21 | 1499999.94 | 2380293.752 | [6 empty] | DW25 | 100% | bar: Regulatory Outputs OMG-04
403604 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2014-05-21 | 2015-03-10 | 2015-03-23 | 2015-10-01 | 2016-03-01 | Highland | 97229.41 | 103702.59 | -11534.14 | 0 | 0 | 0 | 0 | 92168.45 | 0 | 189397.86 | 0 | [6 empty] | EC06 | 100% | bar: Regulatory Outputs OMG-24
402949 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS3 | 2012-10-30 | 2018-12-01 | 2018-12-01 | 2023-08-21 | 2023-09-25 | Glasgow City | 1820434 | 1130117.6 | 2092680.58 | 6926138.82 | -2905717 | 3075900.79 | 6073391.41 | 16392512.2 | 20254054.32 | 38467000.52 | 12751577.528 |  |  |  |  | 207000 |  | EC10B | 6.4% | EC10A | 93.6%
404026 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS0 | 2015-10-12 | 2020-01-13 | 2020-02-24 | 2021-10-06 | 2021-11-05 | Highland | 244 | 41126 | 187359 | 166004 | 56695.6818 | 216999.26 | 524971.82 | 1193155.7618 | 603243.74 | 1796643.5018 | 0 | [6 empty] | CS11A | 100%
404048 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS3 | 2015-01-05 | 2016-12-19 | 2017-01-30 | 2019-07-26 | 2018-08-24 | Glasgow City | 12059 | 162196 | 293871 | 1842709 | -51126.53 | 16617.11 | 0 | 2264266.58 | 0 | 2276325.58 | 0 | [6 empty] | CM_WSI | 100%
404049 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS0 | 2015-01-05 | 2023-08-08 | 2023-11-01 | 2025-02-04 | 2019-08-27 | Glasgow City | 6780 | 260236 | -114904 | 169966 | -52858.42 | 0 | 0 | 262439.58 | 835110.4 | 1104329.98 | 0 | [6 empty] | CM_WSI | 100%
404050 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS1 | 2015-01-05 | 2021-04-12 | 2021-05-31 | 2022-06-16 | 2019-01-28 | Glasgow City | 6112 | 123117 | 66329 | 25847 | -78507.25 | 0 | 0 | 136785.75 | 1484838.7 | 1627736.45 | 0 | [6 empty] | CM_WSI | 100%
403694 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS6 | 2014-03-31 | 2016-08-02 | 2016-08-31 | 2017-10-31 | 2017-10-31 | Glasgow City | 84629 | 166871 | 2343175 | 121304 | -5652 | 5652 | 0 | 2631350 | 0 | 2715979 | 3180037.6428 | [6 empty] | CS11 | 42.22% | CS15 | 57.78%
403693 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS6 | 2014-04-28 | 2016-07-22 | 2016-09-05 | 2017-05-29 | 2017-05-29 | Glasgow City | 35139 | 320861 | 1286538 | -49219.8155 | 1788.8155 | 2636.29 | 0 | 1562604.29 | 0 | 1597743.29 | 1064623.022 | [6 empty] | CS11 | 100%
403692 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2014-04-28 | 2019-03-28 | 2019-03-28 | 2019-01-28 | 2019-03-28 | Glasgow City | 91368 | 265132 | -70491 | 111991 | -4073.9175 | 0 | 0 | 302558.0825 | 0 | 393926.0825 | 1708475.1334 | [6 empty] | CS11 | 100%
403579 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWD | UWWTD - Works | MS7 | 2013-10-08 | 2013-12-13 | 2013-12-13 | 2016-09-29 | 2016-10-26 | Scottish Water Wide | 19064.8 | 2435.2 | -260.2 | 0 | 0 | 0 | 0 | 2175 | 0 | 21239.8 | 0 | [6 empty] | EC10A | 100%
404024 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS3 | 2018-04-11 | 2019-02-07 | 2019-02-25 | 2019-07-18 | 2019-10-22 | Fife | 366 | 1500 | 14986.31 | 17129.7275 | 68494.9625 | 258569 | 2249.96 | 362929.96 | 0.04 | 363296 | 229318.7788 | [6 empty] | CS11 | 100%
404038 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2017-06-29 | 2017-06-29 | 2017-06-29 | 2017-05-25 | 2017-05-25 | Aberdeenshire | 488 | 26000 | 4922.11 | 2654.09 | 0 | 0 | 0 | 33576.2 | 0 | 34064.2 | 62492.8879 | [6 empty] | CS11 | 100%
403926 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2019-05-02 | 2020-04-20 | 2020-07-13 | 2021-01-28 | 2021-01-29 | Angus | 893 | 3700 | 36413.94 | 43993.06 | 56000 | 18082.57 | 26917.46 | 185107.03 | 0 | 186000.03 | 229318.7788 | [6 empty] | CS11 | 100%
403925 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS6 | 2015-11-11 | 2017-10-25 | 2018-01-29 | 2019-01-15 | 2019-01-15 | Moray | 610 | 34190.61 | 73980.39 | 289156.02 | 253056.98 | 16108 | 123 | 666615 | 0 | 667225 | 229318.7788 | [6 empty] | CS11 | 100%
403336 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS6 | 2013-03-11 | 2016-03-02 | 2017-01-23 | 2018-03-21 | 2018-03-21 | Glasgow City | 139543.94 | 520803.06 | 1101543 | 2342888.98 | 9595.0284 | 0 | 0 | 3974830.0684 | 0 | 4114374.0084 | 1549518.405 | [6 empty] | CS11 | 100%
403990 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2017-04-28 | 2017-04-28 | 2017-04-28 | 2017-04-28 | 2017-04-28 | Na H-Eileanan an Iar | 0 | 0 | 396 | 211.29 | 311.192 | 0 | 0 | 918.482 | 0 | 918.482 | 1017925.3446 | [6 empty] | DW25 | 100%
403944 | Q&S4 | Improving drinking water availability and resilience of service | Interruptions to Supply |  |  | Water |  | SWMD | Interruptions to Supply | MS3 | 2014-10-13 | 2015-10-16 | 2015-10-19 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 106206 | 710125 | 879993.95 | 559554.98 | 639866.14 | 188583.75 | 383538.25 | 3361662.07 | 59720.94 | 3527589.01 | 2084642.8434 | [6 empty] | CM_WSI | 12.32% | CS12 | 43.84% | CS16W | 43.84%
403991 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2016-04-01 | 2018-08-29 | 2018-09-28 | 2020-11-01 | 2021-03-01 | Highland | 0 | 3639.03 | 309249.46 | 459203.43 | 852209.52 | 3182108.97 | 2248952.15 | 7055362.56 | 427264.28 | 7482626.84 | 1739717.2 |  |  |  |  | 245040 |  | DW25P | 35% | CM_WSNI | 65% | bar: Regulatory Outputs OMG-04
403992 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2016-04-01 | 2018-02-28 | 2018-03-28 | 2019-09-01 | 2019-12-01 | Na H-Eileanan an Iar | 0 | 1219.51 | 42732.58 | 220633.8 | 1117098.61 | 443555.01 | 10497.37 | 1835736.88 | 4533.89 | 1840270.77 | 428213.4073 |  |  |  |  | 14199.9996 |  | DW25 | 100% | bar: Regulatory Outputs OMG-04
403691 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS5 | 2014-04-25 | 2017-06-30 | 2017-09-18 | 2018-12-11 | 2018-12-11 | South Lanarkshire | 44470 | 260905 | 104023 | 259728.68 | 43226.32 | 0 | 0 | 667883 | 0 | 712353 | 72592.956 | [6 empty] | CS11 | 100%
404020 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS0 | 2017-11-27 | 2019-12-02 | 2019-12-02 | 2019-12-02 | 2019-12-02 | Highland | 1220 | 193590 | 846 | 54601.3991 | 11459.94 | 0 | 0 | 260497.3391 | 0 | 261717.3391 | 229318.7788 | [6 empty] | CS11 | 100%
403630 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2014-02-11 | 2015-03-02 | 2015-03-30 | 2015-05-01 | 2015-05-01 | Highland | 39547.38 | 200730.54 | 0 | 30.88 | 0 | 0 | 0 | 200761.42 | 0 | 240308.8 | 0 | [6 empty] | CM_WWNI | 100% | bar: Regulatory Outputs OMG-24
403135 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS7 | 2012-12-10 | 2015-08-06 | 2015-09-21 | 2016-07-29 | 2016-07-29 | Glasgow City | 137215.96 | 1604972.04 | 64671 | 17907 | -35788.9933 | 0 | 0 | 1651761.0467 | 0 | 1788977.0067 | 1691921.8189 | [6 empty] | CS11 | 100%
403337 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS4 | 2013-03-08 | 2019-05-01 | 2019-05-01 | 2019-02-25 | 2019-05-01 | North Lanarkshire | 95524.22 | 173523.78 | 35996.04 | 32947.1337 | 9134.1076 | 0 | 0 | 251601.0613 | 0 | 347125.2813 | 470562.9546 | [6 empty] | CS11A | 100%
403631 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS0 | 2016-09-28 | 2019-05-27 | 2019-05-27 | 2019-05-27 | 2019-05-27 | Shetland Islands | 34087.82 | 8713.18 | 25968.59 | -17959.89 | 489.67 | 0 | 0 | 17211.55 | 0 | 51299.37 | 402791.3168 | [6 empty] | DW25 | 10% | DW23 | 40% | DW2 | 50%
403958 | Q&S4 | Improving the customer experience | Meter Accuracy |  |  | Water |  | SWD | Meter Accuracy | MS7 | 2016-12-21 | 2017-01-18 | 2017-01-18 | 2016-10-26 |  | Scottish Water Wide | 185621.8 | 196563.7 | -172732.48 | 0 | 0 | 0 | 0 | 23831.22 | 0 | 209453.02 | 4007137.1184 | [6 empty] | CS4 | 100%
403587 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | General |  | SWMD | Wastewater non infrastructure | MS7 | 2013-09-17 | 2014-07-10 | 2016-08-23 | 2016-08-23 | 2016-08-23 | Scottish Water Wide | 952475.44 | -256552.7 | 40048.41 | 0 | 0 | 0 | 0 | -216504.29 | 0 | 735971.15 | 0 | [6 empty] | CM_WSNI | 25% | CM_WWNI | 25% | WG1 | 25% | WQ01 | 25%
404075 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2015-01-26 | 2015-05-21 | 2015-06-15 | 2017-03-24 | 2016-12-16 | Scottish Water Wide | 23000 | 1243563 | 614632.42 | 32049.7 | 0 | 0 | 0 | 1890245.12 | 0 | 1913245.12 | 0 | [6 empty] | CM_WSNI | 46.88% | CM_WWI | 53.12%
404002 | Q&S3B | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | WINF | Exceptional Capital Maintenance | GW2 | 2020-04-27 | 2020-08-17 | 2020-10-13 | 2021-12-03 | 2022-01-31 | West Dunbartonshire | 41.1 | 164111.9 | -63335 | 110610 | -6379 | 128094.53 | 147486 | 480588.43 | 143590.07 | 624219.6 | 0 | [6 empty] | SR15_EXC_EXC | 100%
404003 | Q&S3B | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | WINF | Exceptional Capital Maintenance | MS3 | 2016-01-29 | 2016-09-29 | 2016-09-29 | 2019-06-19 | 2018-05-14 | North Ayrshire | 1470.59 | 3427861.41 | 12866245 | 4900423 | 2360218.97 | 2328.5 | 0 | 23557076.88 | 0 | 23558547.47 | 0 | [6 empty] | SR15_EXC_EXC | 100%
404004 | Q&S3B | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | WINF | Exceptional Capital Maintenance | MS6 | 2015-08-19 | 2015-10-16 | 2015-10-19 | 2017-03-31 | 2017-03-31 | North Lanarkshire | 1952 | 512225 | 201288 | 19931 | -23948 | 0 | 0 | 709496 | 0 | 711448 | 0 | [6 empty] | SR15_EXC_EXC | 100%
404005 | Q&S3B | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | WINF | Exceptional Capital Maintenance | GW2 | 2020-04-13 | 2021-01-18 | 2021-02-12 | 2021-08-11 | 2022-06-24 | Highland | 244 | 53159 | 42940 | 103126 | 3777.07 | 18000 | 167490.9 | 388492.97 | 0 | 388736.97 | 0 | [6 empty] | SR15_EXC_EXC | 100%
403982 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS6 | 2015-03-10 | 2017-02-21 | 2018-03-27 | 2018-08-30 | 2018-08-30 | Argyll and Bute-Cowal & Bute | 3938 | 3000 | 0 | 1129.6 | 2875.4 | 0 | 0 | 7005 | 0 | 10943 | -1018842.4391 | [6 empty] | EC01A | 100%
403981 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS6 | 2015-03-10 | 2017-02-11 | 2018-03-27 | 2018-08-30 | 2018-08-30 | Argyll and Bute-Cowal & Bute | 3938 | 31229 | 301811 | 179004.71 | 350017.29 | 0 | 0 | 862062 | 0 | 866000 | -1018842.4391 | [6 empty] | EC01A | 100%
403983 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS6 | 2015-03-10 | 2016-03-23 | 2016-03-29 | 2018-05-18 | 2018-11-01 | Argyll and Bute-Cowal & Bute | 3930 | 61549 | 143268.49 | 884537.19 | -48104.68 | 0 | 0 | 1041250 | 0 | 1045180 | -1018842.4391 | [6 empty] | EC01A | 100%
403700 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS6 | 2014-02-17 | 2016-03-23 | 2016-03-28 | 2017-03-01 | 2021-03-01 | Scottish Borders | 76358.91 | 355686.09 | 701969.63 | 31569.95 | 7028.16 | 6019.86 | 5996.52 | 1108270.21 | 3686.58 | 1188315.7 | 818769.6468 | [6 empty] | DW25P | 21.36% | DW3C | 78.64% | bar: Regulatory Outputs OMG-01
403595 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS5 | 2014-01-29 | 2018-06-29 | 2018-06-29 | 2018-06-28 | 2018-06-28 | East Renfrewshire | 114677 | 72063 | 63795 | 134382.34 | 76828.86 | 0 | 0 | 347069.2 | 0 | 461746.2 | 520131.8398 | [6 empty] | CS11 | 100%
401806 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS3 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-08-01 | 2019-11-01 | Renfrewshire | 16089 | -1532 | 7699.37 | -5116.37 | 800 | 9.81 | 100.81 | 1961.62 | 89.44 | 18140.06 | 1411052.3761 | [6 empty] | EC04B | 100% | [18 empty] | Regulatory Outputs OMG-18: 9
401808 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS3 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-08-23 | 2019-11-25 | Renfrewshire | 6898 | 0 | 642 | 83 | 4275 | 98.2 | 960.57 | 6058.77 | 482.24 | 13439.01 | 1411052.3761 | [6 empty] | EC04B | 100%
401812 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS3 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-08-23 | 2019-11-25 | Renfrewshire | 10864 | -1579 | 150 | 158 | 550 | 1248.99 | 0 | 527.99 | 0 | 11391.99 | 1411052.3761 | [6 empty] | EC04B | 100%
401813 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS3 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-08-23 | 2019-11-25 | Renfrewshire | 10138 | -5053 | 56.08 | 1643.92 | 1569 | 2124 | 0 | 340 | 0 | 10478 | 1411052.3761 | [6 empty] | EC04B | 100%
401814 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS3 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-08-23 | 2019-11-25 | Renfrewshire | 852148.01 | 858162.99 | 1062885 | 7722678 | 3931849 | 501323.13 | 968.04 | 14077866.16 | 858.87 | 14930873.04 | 1411052.3761 |  |  |  |  | 2379.9996 |  | EC04B | 100%
401815 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS3 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-08-23 | 2019-11-25 | Renfrewshire | 4825 | 0 | 2000 | 1017 | 4305 | 125.84 | 1237.91 | 8685.75 | 634.25 | 14145 | 1411052.3761 | [6 empty] | EC04B | 100%
401816 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWMD | UWWTD - UID | MS3 | 2010-12-09 | 2016-02-29 | 2016-06-20 | 2019-08-23 | 2019-11-25 | Renfrewshire | 6711 | -711 | 712 | 488 | 2709 | 711 | 0 | 3909 | 0 | 10620 | 1411052.3761 | [6 empty] | EC04B | 100%
403716 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS0 | 2014-04-08 | 2020-02-24 | 2020-06-01 | 2021-04-01 | 2021-07-01 | Orkney Islands | 26305.36 | 45419.64 | 3003.16 | 29924.84 | 18591.54 | 4073.6 | 211001.47 | 312014.25 | 127233.9 | 465553.51 | 0 | [6 empty] | EC06 | 100% | bar: Regulatory Outputs OMG-24
404086 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS4 | 2015-01-26 | 2016-09-20 | 2017-08-09 | 2018-05-23 | 2017-09-07 | Shetland Islands | 3486 | 33255 | 50419 | 195036.71 | 77459.79 | 39974.55 | 0 | 396145.05 | 0 | 399631.05 | 0 | [6 empty] | CM_WSI | 100%
404085 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2015-01-26 | 2016-08-31 | 2016-11-21 | 2017-08-31 | 2017-06-09 | Shetland Islands | 650 | 25426 | 291414 | 175367 | -35684.52 | 0 | 0 | 456522.48 | 0 | 457172.48 | 0 | [6 empty] | CM_WSI | 100%
403629 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2014-02-11 | 2015-03-12 | 2015-03-23 | 2015-10-01 | 2016-03-01 | Highland | 119710.12 | 88280.88 | -2316.97 | 0 | 0 | 0 | 0 | 85963.91 | 0 | 205674.03 | 0 | [6 empty] | EC06 | 100% | bar: Regulatory Outputs OMG-24
403917 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS3 | 2016-03-29 | 2018-03-29 | 2018-03-29 | 2020-01-01 | 2021-03-01 | Highland | 0 | 39934.41 | 171557.33 | 688634.15 | 2636722.35 | 2981004 | 101459.53 | 6619311.77 | 41209.47 | 6660521.24 | 2759827.591 |  |  |  |  | 77246.9904 |  | DW25 | 13% | DW2 | 87% | bar: Regulatory Outputs OMG-01
404040 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW2 | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-07-01 | Midlothian | 2440 | 6500 | 39544.07 | 22515.93 | 79556.7741 | 0 | 0 | 148116.7741 | 0 | 150556.7741 | 156073.4338 | [6 empty] | CS15 | 100%
404029 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2017-02-08 | 2017-11-08 | 2017-11-08 | 2017-05-23 | 2017-11-08 | City of Edinburgh | 976 | 17768 | 43112.66 | -61803.62 | 0 | 0 | 0 | -922.96 | 0 | 53.04 | 78036.7169 | [6 empty] | CS11 | 100%
404025 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | West Lothian | 244 | 37000 | 6293 | 31544.3191 | -75080.3191 | 0 | 0 | -243 | 0 | 1 | 229318.7788 | [6 empty] | CS11A | 100%
402746 | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWMD | SOSI | MS7 | 2012-08-08 | 2013-02-06 | 2013-02-07 | 2017-08-08 | 2017-09-15 | Scottish Water Wide | 121680 | 40837.8 | 42982.2 | 7807.53 | 0 | 0 | 0 | 91627.53 | 0 | 213307.53 | 0 | [6 empty] | WG4 | 100%
403993 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS0 | 2015-11-02 | 2019-07-22 | 2019-08-12 | 2019-09-23 | 2019-12-23 | Na H-Eileanan an Iar | 101.77 | 8398.78 | -8500.55 | 8399.9275 | 9.3525 | 179.91 | 0 | 8487.42 | 0 | 8589.19 | 3204232.2373 | [6 empty] | WG4 | 8.13% | DW25 | 10% | DW3B | 10% | DW3C | 71.87%
404053 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2016-11-22 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | Highland | 0 | 0 | 356.51 | 8.84 | 0 | 0 | 0 | 365.35 | 0 | 365.35 | 0 | [6 empty] | CM_WSNI | 100%
402924 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS6 | 2012-12-10 | 2013-10-24 | 2013-11-29 | 2017-03-27 | 2017-03-27 | Scottish Water Wide | 1907722 | 330992 | 142938.72 | 148437.28 | 0 | 0 | 0 | 622368 | 0 | 2530090 | 217088.9154 | [6 empty] | DW5A | 100%
403125 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS6 | 2013-01-14 | 2016-03-31 | 2016-07-18 | 2017-12-01 | 2019-03-01 | Highland | 164265.76 | 122286.34 | 2636754.28 | 1068327.48 | 63204.78 | 4238.36 | 0 | 3894811.24 | 0 | 4059077 | 2388696.3918 | [6 empty] | DW23 | 50% | DW25P | 50% | bar: Regulatory Outputs OMG-01
403013 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-11-19 | 2012-11-19 | 2013-11-19 | 2013-12-13 | 2016-01-27 | Highland | 25239.04 | 1760.96 | -1487.51 | 0 | 0 | 0 | 0 | 273.45 | 0 | 25512.49 | 0 | [6 empty] | CM_WWNI | 100%
403753 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS6 | 2014-04-04 | 2015-03-24 | 2016-03-31 | 2018-01-01 | 2018-10-01 | Stirling | 40033.25 | 95509.75 | 105723.06 | 376392.955 | 56183.545 | 1639.74 | 286 | 635735.05 | 0 | 675768.3 | 520196.3054 | [6 empty] | DW25P | 3.4% | CM_WSNI | 96.6% | bar: Regulatory Outputs OMG-04
403980 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS5 | 2015-03-17 | 2016-03-23 | 2016-03-29 | 2019-02-01 | 2019-03-01 | Argyll and Bute-Cowal & Bute | 4700.32 | 83170.68 | 84606.08 | 684974.37 | 5854.55 | 22747 | 2247.8 | 883600.48 | 312.2 | 888613 | 447814.5757 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
403702 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS7 | 2014-04-28 | 2015-06-25 | 2015-08-03 | 2016-03-11 | 2016-03-11 | Glasgow City | 42977 | 1103672 | 69893 | 410 | -13697.379 | 0 | 0 | 1160277.621 | 0 | 1203254.621 | 229318.7788 | [6 empty] | CS11A | 100%
403930 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS0 | 2018-08-23 | 2019-10-21 | 2020-01-06 | 2020-06-22 | 2020-09-14 | Glasgow City | 732 | 28888 | 14112 | 55474.8291 | 95681.1709 | 456587.16 | 301489.74 | 952232.9 | 4293.12 | 957258.02 | 229318.7788 | [6 empty] | CS11 | 100%
404080 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS5 | 2015-05-11 | 2015-11-19 | 2016-03-22 | 2019-01-28 | 2019-01-28 | Glasgow City | 0 | 3000 | 10260.76 | 0 | 75688.41 | 0 | 0 | 88949.17 | 0 | 88949.17 | 229318.7788 | [6 empty] | CS11 | 100%
403920 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-03-27 | 2018-02-23 | 2018-02-19 | 2018-02-19 | 2018-02-19 | South Lanarkshire | 488 | 32012 | 34512 | -67012 | 0 | 0 | 0 | -488 | 0 | 0 | 229318.7788 | [6 empty] | CS11 | 100%
403929 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS6 | 2015-10-13 | 2018-03-20 | 2018-04-03 | 2018-08-21 | 2018-08-21 | South Lanarkshire | 488 | 44122 | 29960.38 | 463655.62 | 214597.1946 | 0 | 0 | 752335.1946 | 0 | 752823.1946 | 229318.7788 | [6 empty] | CS11 | 100%
403655 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2014-02-03 | 2016-09-21 | 2016-09-21 | 2016-08-23 | 2016-11-28 | Scottish Water Wide | 1271837.55 | 373397.45 | -161315.26 | 0 | 0 | 0 | 0 | 212082.19 | 0 | 1483919.74 | 0 | [6 empty] | DW23 | 100%
403895 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS3 | 2015-04-27 | 2016-09-30 | 2017-03-20 | 2017-03-01 | 2019-10-01 | Argyll and Bute-Cowal & Bute | 15000 | 60178 | 155004.5 | 603987.98 | -43516.4 | 320357.91 | 3727.35 | 1099739.34 | 855.69 | 1115595.03 | 1584350.8576 | [6 empty] | DW25P | 13% | DW3C | 38% | DW25T | 49% | bar: Regulatory Outputs OMG-01
403713 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2014-05-21 | 2015-03-26 | 2015-05-11 | 2015-07-01 | 2015-08-01 | Argyll and Bute-Cowal & Bute | 16907.4 | 30250.21 | 0 | 0 | 0 | 0 | 0 | 30250.21 | 0 | 47157.61 | 0 | [6 empty] | EC06 | 100% | bar: Regulatory Outputs OMG-24
403712 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2014-05-22 | 2014-12-18 | 2015-01-26 | 2015-03-01 | 2016-03-01 | Argyll and Bute-North Argyll | 57358.58 | 8917.42 | -5545.44 | 0 | 0 | 0 | 0 | 3371.98 | 0 | 60730.56 | 0 | [6 empty] | EC06 | 100% | bar: Regulatory Outputs OMG-24
403979 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS6 | 2015-03-10 | 2016-03-22 | 2016-03-29 | 2017-03-01 | 2017-05-01 | Argyll and Bute-Cowal & Bute | 3938 | 54576 | 202288.71 | -79487.71 | 205.1105 | 0 | 0 | 177582.1105 | 0 | 181520.1105 | 138286.8983 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
403816 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2014-06-20 | 2016-12-12 | 2016-12-12 | 2017-01-25 | 2017-01-25 | Scottish Water Wide | 5475.3 | 28802.7 | -7100.46 | 0 | 0 | 0 | 0 | 21702.24 | 0 | 27177.54 | 1138717.0712 | [6 empty] | CS16W | 100%
404094 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2015-07-06 | 2021-08-30 | 2022-01-31 | 2023-05-04 | 2023-08-02 | All West Unitary Authorities | 0 | 44370 | 4050.5 | -204.34 | 0 | 0 | 0 | 48216.16 | 917575.84 | 965792 | 0 | [6 empty] | CM_WSNI | 100%
403994 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2016-02-29 | 2018-03-30 | 2018-06-27 | 2020-05-01 | 2020-05-01 | Na H-Eileanan an Iar | 0 | 2237.14 | 235534.58 | 516568.22 | 161408.22 | 2498142.66 | 367382.03 | 3781272.85 | 21911.73 | 3803184.58 | 740773.2556 |  |  |  |  | 2180.0003 |  | DW25 | 100% | bar: Regulatory Outputs OMG-04
403338 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS5 | 2013-03-11 | 2018-12-06 | 2018-12-07 | 2018-12-07 | 2018-12-07 | North Lanarkshire | 150441.4 | 190700.6 | 14775 | 16298 | 76214.19 | 0 | 0 | 297987.79 | 0 | 448429.19 | 1460895.4319 | [6 empty] | CS11 | 100%
403949 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2020-12-18 | 2020-12-24 | 2020-12-30 | 2021-01-05 | 2021-01-05 | Glasgow City | 1425 | 25862.22 | 54137.78 | 37632.5691 | 304452.646 | 111670.55 | 327904.47 | 861660.2351 | 0 | 863085.2351 | 240495.8008 | [6 empty] | CS11 | 100%
404041 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS0 | 2018-02-26 | 2019-05-13 | 2019-07-12 | 2020-01-01 | 2020-04-01 | South Lanarkshire | 976 | 42524 | 12722.01 | 29606.3475 | 119993.6425 | 733433.37 | 55696.78 | 993976.15 | 1600.86 | 996553.01 | 347699.6399 | [6 empty] | CS11 | 100%
403921 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-03-30 | 2018-07-09 | 2018-07-09 | 2018-04-18 | 2018-04-18 | South Lanarkshire | 976 | 37000 | 34505.91 | 4397.6491 | 1336.9709 | 0 | 0 | 77240.53 | 0 | 78216.53 | 229318.7788 | [6 empty] | CS11 | 100%
404042 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS0 | 2018-07-25 | 2019-10-07 | 2020-01-13 | 2020-04-28 | 2020-07-21 | South Lanarkshire | 488 | 3000 | 30512 | 21117.9741 | 98746.0259 | 387136.26 | 280209.22 | 820721.48 | 2780.56 | 823990.04 | 435813.1581 | [6 empty] | CS11 | 100%
403948 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWD | UWWTD - UID | MS4 | 2019-04-08 | 2019-04-08 | 2019-04-08 | 2019-01-16 | 2019-04-08 | City of Edinburgh | 4500.97 | 52617.03 | 418833.97 | -407652.9904 | -61675.2646 | 0 | 0 | 2122.745 | 0 | 6623.715 | 117578.8269 | [6 empty] | EC10B | 100%
403817 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS4 | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2016-07-01 | 2020-12-18 | Scottish Water Wide | 305681.28 | 557605.72 | 1085514.81 | 277459.19 | 77470.245 | 105120 | 85990.81 | 2189160.775 | 0 | 2494842.055 | 1138717.0712 | [6 empty] | CS16W | 100%
403690 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS4 | 2014-04-28 | 2018-03-12 | 2019-04-01 | 2018-03-14 | 2019-04-19 | Renfrewshire | 108048 | 110960.51 | -9695.51 | 3687 | 29255.29 | 0 | 0 | 134207.29 | 0 | 242255.29 | 2433696.9892 | [6 empty] | CS11 | 100%
403697 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS0 | 2014-04-28 | 2021-06-28 | 2021-09-10 | 2022-09-29 | 2022-12-28 | Glasgow City | 89131 | 44422 | 8612.03 | 35911.0166 | 97923.9534 | 122751.25 | 345422.77 | 655043.02 | 1327877.91 | 2072051.93 | 2667516.9654 | [6 empty] | CS15 | 100%
403988 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2016-09-30 | 2018-02-28 | 2018-03-28 | 2019-09-01 | 2019-09-01 | Na H-Eileanan an Iar | 0 | 10691.12 | 42469.69 | 217914.571 | 864642.929 | 149466.01 | 6691.62 | 1291875.94 | 2994.29 | 1294870.23 | 2019242.0641 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
403998 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2019-08-01 | 2020-06-29 | 2020-09-21 | 2021-10-21 | 2022-01-18 | Fife | 1220 | 29500 | 64668.97 | 50361.215 | 120249.815 | 496724.98 | 1415059.48 | 2176564.46 | 1438215.57 | 3616000.03 | 229318.7788 | [6 empty] | CS11 | 100%
403128 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS0 | 2013-03-18 | 2020-03-02 | 2020-12-17 | 2021-09-01 | 2021-09-01 | Scottish Borders | 127138.87 | 17399.4 | 37572.39 | 159540.87 | -14789.85 | 4543.87 | 810142.74 | 1014409.42 | 2114189.31 | 3255737.6 | 711981.6113 | [6 empty] | DW25 | 100% | bar: Regulatory Outputs OMG-04
403605 | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater |  | SWMD | Sludge | MS3 | 2013-10-31 | 2018-03-20 | 2018-03-26 | 2020-04-24 | 2020-07-27 | Highland | 123835.35 | 503725.65 | 150267 | 276438.087 | 967203.563 | 2730672.81 | 2017149.22 | 6645456.33 | 11240.33 | 6780532.01 | 5679280.1135 | [6 empty] | LA01 | 100%
500653 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2015-06-29 | 2015-06-29 | 2015-08-31 | 2017-09-12 | 2017-09-12 | Scottish Water Wide | 0 | 225769 | 259370.22 | 452492.36 | -103028.98 | 0 | 0 | 834602.6 | 0 | 834602.6 | 805711.0404 | [6 empty] | CS11 | 19.24% | CS11A | 80.76%
502020 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS3 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2022-07-22 | 2022-07-22 | Scottish Water Wide | 0 | 3248659 | 2290134.6 | 2221100.48 | -1048799.05 | -4373793.6 | -1293270.6 | 1044030.83 | -1044030.84 | -0.01 | 3921621.8173 | [6 empty] | CM_WSNI | 25% | CM_WWNI | 25% | DW2 | 50%
500584 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-06-02 | 2015-06-02 | 2015-06-02 | 2017-01-19 | 2017-05-15 | Scottish Water Wide | 0 | 1556315 | -128066.18 | 0 | 0 | 0 | 0 | 1428248.82 | 0 | 1428248.82 | 0 | [6 empty] | CM_M&G | 100%
502939 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS5 | 2017-10-11 | 2017-10-11 | 2017-11-01 | 2019-03-14 | 2019-03-14 | Scottish Water Wide | 0 | 0 | 0 | 569917.99 | 726547.23 | 2720.43 | 3862.71 | 1303048.36 | 916.83 | 1303965.19 | 603224.8064 | [6 empty] | CS11A | 3.097% | CS11 | 96.9%
502976 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS3 | 2017-12-12 | 2017-12-12 | 2018-02-08 | 2019-07-05 | 2019-07-05 | Scottish Water Wide | 0 | 0 | 0 | 296794.39 | 1177800.04 | 67772.43 | 1248.9 | 1543615.76 | 656.04 | 1544271.8 | 469814.5796 | [6 empty] | CS11A | 100%
503080 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS3 | 2018-02-26 | 2018-02-26 | 2018-04-02 | 2019-08-23 | 2019-08-23 | Scottish Water Wide | 0 | 0 | 0 | 93859.49 | 771792.73 | 264999.37 | 0 | 1130651.59 | 0 | 1130651.59 | 469814.5796 | [6 empty] | CS11A | 100%
503294 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS5 | 2018-07-04 | 2018-07-04 | 2018-07-09 | 2019-03-05 | 2019-03-05 | Scottish Water Wide | 0 | 0 | 0 | 0 | 441794.39 | 118837.5 | 3541.34 | 564173.23 | 826.77 | 565000 | 240495.8008 | [6 empty] | CS11A | 100%
503389 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS3 | 2018-10-01 | 2018-10-01 | 2018-10-15 | 2019-10-09 | 2019-10-09 | Scottish Water Wide | 0 | 0 | 0 | 0 | 395511.17 | 297993.31 | 3701.65 | 697206.13 | 2794.23 | 700000.36 | 240495.8008 | [6 empty] | CS11A | 100%
503390 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS3 | 2018-10-01 | 2018-10-01 | 2018-10-15 | 2020-02-28 | 2020-02-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 158404.7185 | 691246.59 | 2754.1 | 852405.4085 | 4245.89 | 856651.2985 | 240495.8008 | [6 empty] | CS11A | 100%
503489 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS2 | 2019-02-28 | 2019-02-28 | 2019-06-10 | 2020-03-16 | 2020-06-16 | Scottish Water Wide | 0 | 0 | 0 | 0 | 106086.14 | 1499300.2 | 7012.33 | 1612398.67 | 9203.7 | 1621602.37 | 2862025.6396 | [6 empty] | CS11A | 11.26% | CS11 | 88.74%
500504 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-03-05 | 2021-03-05 | Scottish Water Wide | 0 | 70532 | 199468 | 0 | 47500 | 100000 | 202500 | 620000 | 0 | 620000 | 0 | [6 empty] | CM_M&G | 100%
500583 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-06-02 | 2015-06-02 | 2015-06-02 | 2017-01-19 | 2017-05-15 | Scottish Water Wide | 0 | 3286121.99 | -153159.01 | 0 | 0 | 0 | 0 | 3132962.98 | 0 | 3132962.98 | 0 | [6 empty] | CM_M&G | 100%
500487 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2021-02-26 | 2021-02-26 | Scottish Water Wide | 0 | 3117885.42 | 386245.58 | 1417021.8 | 1491308 | 2190000 | 2190000 | 10792460.8 | 0 | 10792460.8 | 0 | [6 empty] | CM_WWI | 100%
500505 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-15 | 2021-03-05 | 2021-03-05 | Scottish Water Wide | 0 | 70745.59 | 26421.97 | 72932.44 | 85762.427 | 75000 | 92752.19 | 423614.617 | 0 | 423614.617 | 0 | [6 empty] | CM_M&G | 100%
500486 | Q&S4 | Supporting economic development | First Time Meters |  |  | General |  | SWD | First Time Meters | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2021-02-26 | 2021-02-26 | Scottish Water Wide | 0 | 842536 | 2163574.9 | 909392.2 | 1484611.9 | 2146500 | 2146500 | 9693115 | 0 | 9693115 | 10130931.1265 | [6 empty] | WG6 | 100%
500506 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-03-05 | 2021-03-05 | Scottish Water Wide | 0 | 6892 | 2108 | 5900 | 4500 | 8000 | 20600 | 48000 | 0 | 48000 | 0 | [6 empty] | CM_M&G | 100%
402243 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2011-08-01 | 2012-10-22 | 2012-11-12 | 2016-06-14 |  | Scottish Water Wide | 831840.17 | 213570.68 | 49699.57 | 2416.25 | 0 | 0 | 0 | 265686.5 | 0 | 1097526.67 | 0 | [6 empty] | QS4EQS | 100%
500585 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-06-02 | 2015-06-02 | 2015-06-02 | 2016-12-19 | 2017-05-15 | Scottish Water Wide | 0 | 112694.23 | -26613.11 | 0 | 0 | 0 | 0 | 86081.12 | 0 | 86081.12 | 0 | [6 empty] | CM_M&G | 100%
500507 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2021-03-12 | 2021-03-12 | Scottish Water Wide | 0 | 776 | 408499 | 396808.95 | 492585.955 | 450000 | 626737.74 | 2375407.645 | 0 | 2375407.645 | 0 | [6 empty] | CM_M&G | 100%
500574 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-18 | 2015-05-18 | 2015-05-18 | 2021-03-12 | 2021-03-12 | Scottish Water Wide | 0 | 94837.75 | 46162.25 | 91925.27 | 81074.73 | 84404 | 117596 | 516000 | 0 | 516000 | 0 | [6 empty] | CM_M&G | 100%
502041 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWMD | Wastewater infrastructure | MS7 | 2016-08-23 | 2017-03-23 | 2017-06-22 | 2017-12-19 | 2017-12-19 | Scottish Water Wide | 0 | 0 | 13327.74 | 81707.355 | 0 | 0 | 0 | 95035.095 | 0 | 95035.095 | 0 | [6 empty] | CM_WSNI | 100%
502042 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWMD | Wastewater infrastructure | MS6 | 2016-08-23 | 2017-02-24 | 2017-04-20 | 2017-12-12 | 2017-12-12 | Scottish Water Wide | 0 | 0 | 18306.39 | 166315.486 | 1659.744 | 0 | 0 | 186281.62 | 0 | 186281.62 | 0 | [6 empty] | CM_WSNI | 100%
502044 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWMD | Wastewater infrastructure | MS7 | 2016-08-23 | 2017-08-16 | 2017-08-16 | 2017-08-03 | 2017-08-03 | Scottish Water Wide | 0 | 0 | 6208.69 | -2726.15 | 0 | 0 | 0 | 3482.54 | 0 | 3482.54 | 0 | [6 empty] | CM_WSNI | 100%
502255 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWD | Wastewater infrastructure | MS3 | 2017-11-08 | 2018-02-21 | 2018-03-15 | 2020-02-10 | 2020-02-10 | Scottish Water Wide | 0 | 0 | 25805.39 | 98357.6 | 50680.55 | 468110.38 | 130122.08 | 773076 | 0 | 773076 | 0 | [6 empty] | CM_WSNI | 100%
502596 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWMD | Wastewater infrastructure | MS1 | 2017-10-30 | 2019-06-24 | 2019-07-08 | 2020-07-06 | 2020-10-06 | Scottish Water Wide | 0 | 0 | 2093.02 | 26067.44 | 72082.58 | 1208917.41 | 205564.01 | 1514724.46 | 3886.63 | 1518611.09 | 0 | [6 empty] | CM_WSNI | 100%
502597 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWMD | Wastewater infrastructure | MS2 | 2017-10-24 | 2018-10-29 | 2019-04-29 | 2019-11-29 | 2019-11-29 | Scottish Water Wide | 0 | 0 | 1046.51 | 4932.82 | 33722.03 | 185171.87 | 26988.42 | 251861.65 | 690.35 | 252552 | 0 | [6 empty] | CM_WSNI | 100%
502594 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWD | Wastewater infrastructure | MS3 | 2017-10-24 | 2018-06-11 | 2018-07-10 | 2020-04-15 | 2020-04-16 | Scottish Water Wide | 0 | 0 | 2093.02 | 2906.98 | 5932.64 | 33861.51 | 2570.35 | 47364.5 | 1886.54 | 49251.04 | 0 | [6 empty] | CM_WSNI | 100%
502595 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWMD | Wastewater infrastructure | MS1 | 2017-10-24 | 2019-05-13 | 2019-06-03 | 2020-02-13 | 2020-02-14 | Scottish Water Wide | 0 | 0 | 2093.02 | 4779.5 | 8968.68 | 551329.84 | 164599.07 | 731770.11 | 1616.8 | 733386.91 | 0 | [6 empty] | CM_WSNI | 100%
502254 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Water |  | SWD | Wastewater infrastructure | MS3 | 2016-11-30 | 2017-03-28 | 2017-03-29 | 2021-02-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 98699.92 | 93300.08 | 22889.14 | 68233.59 | 66382.31 | 349505.04 | 0 | 349505.04 | 0 | [6 empty] | CM_WSNI | 100%
500980 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2016-05-31 | 2016-11-08 | 2016-11-30 | 2019-07-26 | 2019-07-26 | Scottish Water Wide | 0 | 0 | 105487.75 | 149063.7 | 60067.54 | 86864.99 | 1358.82 | 402842.8 | 2157.2 | 405000 | 0 | [6 empty] | CM_WSNI | 100%
501192 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2015-11-23 | 2015-11-23 | 2016-01-14 | 2017-07-10 | 2017-07-10 | All North Unitary Authorities | 0 | 351514 | 838956.23 | -158862.81 | 105.07 | 207.01 | 0 | 1031919.5 | 0 | 1031919.5 | 0 | [6 empty] | CM_WSNI | 100%
403730 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2015-12-01 |  | Scottish Water Wide | 20000 | -159.27 | 389.43 | 42.545 | 0 | 0 | 0 | 272.705 | 0 | 20272.705 | 0 | [6 empty] | CM_WWNI | 100%
403732 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-09-30 | 2016-09-30 | All East Unitary Authorities | 432263.69 | 250862.31 | 1140.09 | 455.1435 | 0 | 0 | 0 | 252457.5435 | 0 | 684721.2335 | 0 | [6 empty] | CM_WWNI | 100%
403734 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-01-13 | 2016-02-17 | All North Unitary Authorities | 4341 | -2833.53 | 0 | 0 | 0 | 0 | 0 | -2833.53 | 0 | 1507.47 | 0 | [6 empty] | CM_WWNI | 100%
403728 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-12-15 | 2017-05-15 | All South Unitary Authorities | 337395.87 | 383353.58 | -34579.15 | 2051.89 | 0 | 0 | 0 | 350826.32 | 0 | 688222.19 | 0 | [6 empty] | CM_WWNI | 100%
403731 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-12-07 |  | Scottish Water Wide | 361041.47 | 132065.53 | 8673.13 | 1362.705 | 0 | 0 | 0 | 142101.365 | 0 | 503142.835 | 0 | [6 empty] | CM_WSNI | 100%
403733 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-06-07 | 2016-06-07 | All East Unitary Authorities | 240906.27 | 182605.79 | 5545.02 | 0 | 0 | 0 | 0 | 188150.81 | 0 | 429057.08 | 0 | [6 empty] | CM_WSNI | 100%
403735 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-12-08 | 2016-12-08 | All North Unitary Authorities | 171670.62 | 426948.38 | -25211.45 | 1712.66 | 0 | 0 | 0 | 403449.59 | 0 | 575120.21 | 0 | [6 empty] | CM_WSNI | 100%
403729 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-12-19 | 2017-02-01 | All South Unitary Authorities | 156565.39 | -6565.39 | -17405.82 | 0 | 0 | 0 | 0 | -23971.21 | 0 | 132594.18 | 0 | [6 empty] | CM_WSNI | 100%
403737 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-05-10 | 2016-05-12 | All West Unitary Authorities | 277227.52 | 34192.9 | 0 | 0 | 0 | 0 | 0 | 34192.9 | 0 | 311420.42 | 0 | [6 empty] | CM_WSNI | 100%
403736 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-02-25 | 2014-02-25 | 2014-04-04 | 2016-12-15 | 2017-11-22 | All West Unitary Authorities | 194289.16 | 183500.17 | 15479.81 | -8604.1 | 0 | 0 | 0 | 190375.88 | 0 | 384665.04 | 0 | [6 empty] | CM_WWNI | 100%
501001 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | NONINF | DWQ Compliance | MS3 | 2015-09-28 | 2018-09-21 | 2018-09-24 | 2020-05-01 | 2020-07-01 | Shetland Islands | 0 | 31287 | 141658.16 | 361096.395 | 1376955.685 | 3847380.84 | 104019.47 | 5862397.55 | 36534.67 | 5898932.22 | 0 |  |  |  |  | -5000.0003 |  | DW25D | 100% | bar: Regulatory Outputs OMG-05
403424 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2013-03-14 | 2013-03-14 | 2013-04-03 | 2018-03-12 |  | Scottish Water Wide | 174282.61 | 0.39 | 0 | 0 | 0 | 0 | 0 | 0.39 | 0 | 174283 | 0 | [6 empty] | CM_M&G | 100%
501005 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2016-02-25 | 2016-07-22 | 2016-08-31 | 2019-10-07 | 2019-10-07 | Scottish Water Wide | 0 | 14482.71 | 588592.43 | 182330.85 | 37624.64 | 23904.6 | 3578.76 | 850513.99 | 6377.7 | 856891.69 | 0 | [6 empty] | CM_WWNI | 23.59% | CM_WSNI | 76.41%
501006 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS6 | 2016-01-25 | 2016-05-26 | 2016-06-10 | 2017-11-30 | 2017-11-30 | Scottish Water Wide | 0 | 198402 | 146023.97 | -2525.145 | 12.46 | 0 | 0 | 341913.285 | 0 | 341913.285 | 0 | [6 empty] | CM_WSNI | 40.13% | CM_WWNI | 59.87%
501007 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2016-09-22 | 2017-07-26 | 2017-08-31 | 2020-03-05 | 2020-06-05 | Scottish Water Wide | 0 | 0 | 145119.88 | 657878.56 | 289095.84 | 285016.69 | 83756.26 | 1460867.23 | 9984.07 | 1470851.3 | 0 | [6 empty] | CM_WWNI | 28.21% | CM_WSNI | 71.79%
501008 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2016-09-22 | 2018-01-25 | 2018-02-28 | 2020-03-26 | 2020-03-26 | Scottish Water Wide | 0 | 0 | 38882.64 | 228845.78 | 329270.5 | 398198.45 | 48034.39 | 1043231.76 | 7278.18 | 1050509.94 | 0 | [6 empty] | CM_WWNI | 38.1% | CM_WSNI | 61.9%
501009 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2016-09-22 | 2017-12-15 | 2018-02-05 | 2020-07-03 | 2020-07-03 | Scottish Water Wide | 0 | 0 | 42565.39 | 225201.29 | 696607.96 | 525163.23 | 313368 | 1802905.87 | 14234.6 | 1817140.47 | 0 | [6 empty] | CM_WWNI | 36.89% | CM_WSNI | 63.11%
502234 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2016-09-22 | 2018-05-31 | 2018-07-30 | 2021-01-14 | 2021-01-14 | Scottish Water Wide | 0 | 0 | 38317.97 | 75109.82 | 172048.43 | 570548.05 | 673501.45 | 1529525.72 | 140728.95 | 1670254.67 | 0 | [6 empty] | CM_WWNI | 41.29% | CM_WSNI | 58.71%
500948 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS3 | 2016-05-13 | 2016-12-13 | 2016-12-14 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 54909.96 | 117508.41 | 10424.25 | 31647.51 | 0 | 214490.13 | 0 | 214490.13 | 0 | [6 empty] | CM_WWNI | 100%
500949 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2016-08-18 | 2017-03-30 | 2017-06-01 | 2020-02-05 | 2020-02-05 | Scottish Water Wide | 0 | 0 | 18917.56 | 303371 | 87504.25 | 156273.04 | 25082.4 | 591148.25 | 0 | 591148.25 | 0 | [6 empty] | CM_WWNI | 24.68% | CM_WSNI | 75.32%
500502 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2021-06-08 | 2021-06-08 | Scottish Water Wide | 0 | 37532.26 | 18047.74 | 29798.9 | 27969.89 | 30000 | 38575 | 181923.79 | 0 | 181923.79 | 0 | [6 empty] | CM_M&G | 100%
500201 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-03-23 | 2015-03-23 | 2015-03-23 | 2018-08-09 | 2018-08-09 | Scottish Water Wide | 0 | 146264.15 | -14402.15 | 36408 | 10317.265 | 0 | 0 | 178587.265 | 0 | 178587.265 | 0 | [6 empty] | CM_WSNI | 100%
049576 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5678420 | [6 empty] | SR15_CMA_MAG | 100%
049580 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2847851.0652 | [6 empty] | SR15_CMA_WSI | 100%
049585 | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2645228.9355 | [6 empty] | SR15_CMP_LATE | 100%
049584 | Q&S3B | Completion | OMG180 |  |  | General |  | SWD | OMG180 | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20920880.6263 | [6 empty] | SR15_CMP_PLAN | 100%
049575 | Q&S4 | Reducing long term cost of service | Research and Innovation |  |  | General |  | SWD | Research and Innovation | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634026.814 | [6 empty] | SR15_COS_RAI | 100%
049542 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | General |  | SWD | DWQ Compliance | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1763319.3739 | [6 empty] | SR15_DWQ_COM | 100%
049543 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | General |  | SWD | DWQ Reliability | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7805343.0384 | [6 empty] | SR15_DWQ_REL | 100%
049561 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | General |  | SWD | Environmental Studies | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4223694.3766 | [6 empty] | SR15_ENV_ENVS | 100%
049554 | Q&S4 | Protecting and enhancing the environment | Revised Bathing Waters Directive |  |  | General |  | SWD | Revised Bathing Waters Directive | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296908.3084 | [6 empty] | SR15_ENV_RBWD | 100%
049556 | Q&S4 | Protecting and enhancing the environment | Ring Fenced Environmental |  |  | General |  | SWD | Ring Fenced Environmental | MS0 | 2018-04-01 |  |  |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34997195.2675 | [6 empty] | SR15_ENV_SHEL | 100%
049555 | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | General |  | SWD | Sludge | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1083503.227 | [6 empty] | SR15_ENV_SLU | 100%
049612 | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | Water |  | SWD | Exceptional Capital Maintenance | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157187730.0767 | [6 empty] | SR15_EXC_EXC | 100%
049538 | Q&S4 | IR18 Allowance | IR18 |  |  | Wastewater |  | SWD | IR18 | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14865540.566 | [6 empty] | SR15_IR18_IR18 | 100%
049536 | Q&S4 | Programme Risk | Maintenance Risk |  |  | General |  | SWD | Maintenance Risk | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271230926.8593 | [6 empty] | SR15_RSK_CMR | 100%
049535 | Q&S4 | Programme Risk | Completion Risk |  |  | General |  | SWD | Completion Risk | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000000 | [6 empty] | SR15_RSK_COMP | 100%
049537 | Q&S4 | Programme Risk | Enhanced Risk |  |  | General |  | SWD | Enhanced Risk | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133308478.2832 | [6 empty] | SR15_RSK_EHR | 100%
050003 | Q&S4 | Programme Risk | Enhanced Risk - Forecast Variance |  |  | General |  | SWD | Enhanced Risk - Forecast Variance | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82543000 | [6 empty] | SR15_RSK_EHU | 100%
049586 | Q&S4 | Programme Risk | Ringfenced for Inflation |  |  | General |  | SWD | Ringfenced for Inflation | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73991834.6444 | [6 empty] | SR15_RSK_RINF | 100%
049569 | Q&S4 | Supporting economic development | Developer Asset Adoption |  |  | General |  | SWD | Developer Asset Adoption | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2177374.984 | [6 empty] | SR15_SED_DAA | 100%
049567 | Q&S4 | Supporting economic development | RCC |  |  | General |  | SWD | RCC | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64181996.1736 | [6 empty] | SG2 | 50% | WG2 | 50%
049568 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | General |  | SWD | Strategic Capacity | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73749124.2489 | [6 empty] | SR15_SED_SCAP | 100%
049564 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218364.334 | [6 empty] | SR15_SEW_IFR | 100%
049613 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWD | UWWTD - UID | MS2 | 2015-03-31 | 2015-03-31 |  |  |  | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1933149.838 | [6 empty] | SR15_UID_UWWD | 100%
502443 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-10 | 2017-02-10 | 2017-02-10 | 2019-12-11 | 2019-12-11 | Scottish Water Wide | 0 | 0 | 10509.26 | 9004.01 | 29654.7 | 64706.64 | 1338.3 | 115212.91 | 0 | 115212.91 | 0 | [6 empty] | CM_WSI | 100%
050033 | Q&S5 | SR21 Early Start | SR21 Early Start |  |  | General |  | SWD | Non Reg | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 10000000 | 20000000 | 30000000 | 0 | 30000000 | 0
502925 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2021-04-01 | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-08-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 999999.99 | 999999.99 | 0 | 999999.99 | 0 | [6 empty] | CM_WWI | 100%
500173 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS4 | 2015-03-20 | 2016-04-29 | 2016-06-20 | 2019-03-27 | 2019-09-09 | Fife | 0 | 13937 | 153569.12 | 83863.88 | 71014 | 4349.98 | 0.03 | 326734.01 | 0 | 326734.01 | 45522.8097 | [6 empty] | EC01D | 12.3% | EC01G | 17.1% | CS16D | 33.63% | EC10E | 36.97%
502814 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2021-04-09 | 2022-07-22 | 2022-11-14 | 2023-11-02 | 2024-02-02 | Fife | 0 | 0 | 0 | 97236.6525 | 36451.5875 | 12369.06 | 4166.12 | 150223.42 | 51.59 | 150275.01 | 148885.7057 | [6 empty] | SG1 | 100%
500695 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2015-06-30 | 2018-09-18 | 2019-03-29 | 2020-01-13 | 2020-01-13 | Fife | 0 | 130610 | 46330.1 | 122609.4 | 398068.48 | 844835.74 | 17633.62 | 1560087.34 | 6542.6 | 1566629.94 | 0 | [6 empty] | CM_WWNI | 100%
500174 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2017-02-27 | 2017-02-27 | 2017-03-01 | 2017-03-01 | Scottish Borders | 0 | 13526 | 7500 | -8014.76 | 0 | 0 | 0 | 13011.24 | 0 | 13011.24 | 81381.7871 | [6 empty] | EC01D | 100% | bar: Regulatory Outputs OMG-23
502428 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | WWINF | UWWTD - Works | MS6 | 2016-11-21 | 2018-01-29 | 2018-02-19 | 2018-03-01 | 2018-03-01 | Fife | 0 | 0 | 9239.06 | 93697.94 | 76740 | 0 | 0 | 179677 | 0 | 179677 | 30795.6344 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
500577 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | Orkney Islands | 0 | 24641.68 | 6457.9 | 841.892 | 35.218 | 0 | 0 | 31976.69 | 0 | 31976.69 | 148885.7057 | [6 empty] | SG1 | 100%
500055 | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWD | WFD | MS7 | 2015-02-18 | 2015-03-09 | 2015-03-09 | 2015-11-01 | 2016-03-01 | Scottish Borders | 4670 | 223830 | 153.53 | 0 | 0 | 0 | 0 | 223983.53 | 0 | 228653.53 | 344261.4046 | [6 empty] | WR2A | 100% | bar: Regulatory Outputs OMG-20
402748 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2012-07-20 | 2014-10-30 | 2014-11-24 | 2016-07-29 | 2016-07-29 | Orkney Islands | 175129 | 79634 | 65000 | 0 | -1821.475 | 0 | 0 | 142812.525 | 0 | 317941.525 | 0 | [6 empty] | SG1 | 100%
500175 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2015-09-28 | 2015-11-13 | 2017-05-30 | 2018-01-30 | Fife | 0 | 64064 | 54379 | 12619.995 | 123.845 | 0 | 0 | 131186.84 | 0 | 131186.84 | 143167.9906 | [6 empty] | EC01G | 4.722% | CS11 | 22.55% | CS16D | 27.6% | EC01D | 45.13%
501817 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-07-27 | 2016-07-27 | Fife | 0 | 10465 | 0.12 | 0 | 0 | 0 | 0 | 10465.12 | 0 | 10465.12 | 148885.7057 | [6 empty] | SG1 | 100%
503476 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWMD | Supply Resilience | MS5 | 2019-02-20 | 2019-02-20 | 2019-02-21 | 2019-03-14 | 2019-03-14 | East Renfrewshire | 0 | 0 | 0 | 0 | 45732.77 | 1709.95 | 153.49 | 47596.21 | 162.45 | 47758.66 | 5970783.1595 | [6 empty] | CS16WR | 100%
500876 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-08-19 | 2018-11-21 | 2018-11-21 | 2018-11-30 | 2018-11-30 | Highland | 0 | 1267.34 | 2229.31 | 4197.8 | -4197.8 | 0 | 0 | 3496.65 | 0 | 3496.65 | 76457.0927 | [6 empty] | DW5FS | 100%
500752 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS5 | 2015-08-25 | 2017-05-12 | 2017-07-31 | 2018-08-30 | 2018-08-30 | Highland | 0 | 93419 | 136262.78 | 681176.41 | 156789.76 | 200 | 0 | 1067847.95 | 0 | 1067847.95 | 0 | [6 empty] | CM_WSNI | 100%
045416 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS6 | 2009-03-18 | 2011-09-28 | 2011-11-14 | 2016-06-21 | 2016-06-29 | Highland | 2709580.83 | 531173.1 | 422069.57 | 0 | 45945.7915 | 0 | 0 | 999188.4615 | 0 | 3708769.2915 | 589524.0001 |  |  |  |  | 20540 |  | DW23 | 100%
400928 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2010-04-21 | 2013-05-08 | 2013-05-09 | 2018-06-22 | 2011-03-14 | Glasgow City | 266000 | 9001 | 0 | 0 | -6589.084 | 0 | 0 | 2411.916 | 0 | 268411.916 | 0 | [6 empty] | EC01D | 33.33% | EC04C | 33.33% | EC10E | 33.33%
500104 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2015-05-19 | 2016-03-29 | 2016-04-19 | 2020-01-14 | 2020-01-14 | Scottish Water Wide | 0 | 540169 | 976312.31 | 1088756.86 | 367321.28 | 423531.96 | 8883.82 | 3404975.23 | 2236.84 | 3407212.07 | 0 | [6 empty] | CM_WSNI | 100%
502337 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2016-09-23 | 2018-10-25 | 2019-01-28 | 2020-07-03 | 2020-10-05 | Scottish Water Wide | 0 | 0 | 8307.47 | 225073.04 | 353804.88 | 1599930.66 | 778543.74 | 2965659.79 | 6950.06 | 2972609.85 | 0 |  |  |  |  | 43700.0004 |  | CM_WSNI | 100%
501687 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS1 | 2017-11-15 | 2021-09-27 | 2022-01-19 | 2023-04-07 | 2023-04-07 | Scottish Water Wide | 0 | 0 | 12087.64 | 60587.36 | 364733.73 | 0 | 0 | 437408.73 | 6022030.55 | 6459439.28 | 0 | [6 empty] | CM_WSNI | 100%
402867 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-09-21 | 2012-11-27 | 2013-02-25 | 2014-11-05 | 2014-11-05 | Renfrewshire | 237484 | 7170.37 | 0 | 0 | 0 | 0 | 0 | 7170.37 | 0 | 244654.37 | 0 | [6 empty] | CM_WSI | 100%
501339 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-05-03 | 2022-08-18 | 2022-12-22 | 2024-03-20 | 2024-06-20 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9299999.99 | 9299999.99 | 0 | [6 empty] | CM_WSNI | 100%
502763 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2020-07-01 | 2021-11-29 | 2022-03-29 | 2023-03-17 | 2023-06-19 | Perth and Kinross | 0 | 0 | 0 | 36725.755 | 31403.751 | 4323.11 | 1547.37 | 73999.986 | 0 | 73999.986 | 148885.7057 | [6 empty] | SG1 | 100%
501703 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2018-08-27 | 2022-01-13 | 2022-04-06 | 2022-07-26 | 2022-10-26 | Highland | 0 | 0 | 2418.28 | 7529.504 | 7923.919 | 0 | 0 | 17871.703 | 598795 | 616666.703 | 0 | [6 empty] | CM_WWI | 100%
400926 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-05-31 | 2011-10-31 | 2012-10-31 | 2013-06-20 |  | Highland | 386000 | -1048.5 | 0 | 0 | 0 | 0 | 0 | -1048.5 | 0 | 384951.5 | 0 | [6 empty] | CM_WWI | 100%
402168 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2011-06-13 | 2014-03-17 | 2014-05-28 | 2014-11-27 |  | Orkney Islands | 29749 | 694.46 | 0 | 0 | 0 | 0 | 0 | 694.46 | 0 | 30443.46 | 0 | [6 empty] | CM_WWNI | 100%
500176 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS3 | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2019-09-09 | 2019-12-03 | North Ayrshire | 0 | 58109 | 284709 | 290872.6125 | 273798.3875 | 149741.72 | 3499.28 | 1060730 | 0 | 1060730 | 411296.5619 | [6 empty] | EC01G | 0.35% | EC01D | 1.33% | EC10E | 5.65% | CS11 | 20.23% | CS16D | 72.44%
403513 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 2016-06-30 |  | North Ayrshire | 519494.81 | 25000.19 | -23678.78 | 0 | 0 | 0 | 0 | 1321.41 | 0 | 520816.22 | 0 | [6 empty] | CM_WWNI | 100%
502779 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS1 | 2017-06-20 | 2019-08-12 | 2019-11-12 | 2020-06-26 | 2020-06-29 | North Ayrshire | 0 | 0 | 0 | 3207.75 | 135734.43 | 830665.27 | 427071.87 | 1396679.32 | 5567.43 | 1402246.75 | 0 | [6 empty] | CM_WWNI | 100%
500932 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | North Ayrshire | 0 | 6000 | 2000 | -4075.53 | 0 | 0 | 0 | 3924.47 | 0 | 3924.47 | 144841.4737 | [6 empty] | CS15A | 100%
501518 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-09-05 | 2019-03-13 | 2019-03-28 | 2020-04-06 | 2020-07-06 | North Ayrshire | 0 | 0 | 16616.29 | 334708.33 | 774930.14 | 2754666.47 | 203246.75 | 4084167.98 | 24422.01 | 4108589.99 | 0 | [6 empty] | CM_WWNI | 100%
502249 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS0 | 2017-06-29 | 2022-05-02 | 2022-06-30 | 2022-10-05 | 2023-01-19 | Na H-Eileanan an Iar | 0 | 0 | 16665.34 | 3766.06 | 9462.41 | 0 | 0 | 29893.81 | 333999.19 | 363893 | 0 | [6 empty] | CM_WWI | 100%
502617 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS0 | 2018-07-31 | 2019-08-19 | 2019-10-14 | 2020-07-17 | 2020-10-19 | Argyll and Bute-North Argyll | 0 | 0 | 18400 | 409.92 | 26024.95 | 365445.25 | 283638.85 | 693918.97 | 1498.86 | 695417.83 | 0 | [6 empty] | CM_WSI | 100%
500179 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS4 | 2015-03-20 | 2016-06-21 | 2016-08-24 | 2019-01-31 | 2019-06-10 | East Ayrshire | 0 | 12315 | 39020 | 83759.78 | 66446.63 | 9398.09 | 0 | 210939.5 | 0 | 210939.5 | 74920.4746 | [6 empty] | EC01G | 0.9852% | EC10E | 22.17% | EC01D | 32.02% | CS16D | 44.83%
045019 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2009-03-13 | 2012-09-26 | 2013-01-14 | 2014-01-06 | 2014-04-17 | East Ayrshire | 1773514.9 | 1356.47 | 0 | 0 | 0 | 0 | 0 | 1356.47 | 0 | 1774871.37 | 0 | [6 empty] | CM_WWNI | 100%
403939 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS0 | 2018-06-13 | 2020-01-13 | 2020-03-30 | 2021-05-18 | 2021-05-19 | East Ayrshire | 0 | 21902 | 20763.9 | 29496.6705 | 27638.2595 | 348892.89 | 667364.37 | 1116058.09 | 307790.62 | 1423848.71 | 0 | [6 empty] | SG1 | 100%
502216 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS2 | 2017-04-28 | 2019-02-12 | 2019-05-03 | 2020-02-24 | 2020-06-01 | Scottish Borders | 0 | 0 | 20488.01 | 87105.99 | 207009 | 409647.9 | 106551.8 | 830802.7 | 1246.55 | 832049.25 | 0 | [6 empty] | CM_WWI | 100%
500180 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act |  |  | Wastewater |  | SWMD | Flood Risk Management Act | MS3 | 2015-03-26 | 2016-05-31 | 2016-06-27 | 2019-06-10 | 2019-07-08 | Stirling | 0 | 36395 | 167369 | 89745 | 125000 | 103295 | 0 | 521804 | 0 | 521804 | 288365.2949 | [6 empty] | EC01G | 16.49% | CS16D | 83.51%
402779 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2012-06-27 | 2012-06-27 | 2012-08-01 | 2016-05-19 |  | Stirling | 406809.05 | 26858.71 | 0 | 0 | 0 | 0 | 0 | 26858.71 | 0 | 433667.76 | 0 | [6 empty] | CM_WWNI | 100%
500933 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2015-10-26 | 2016-11-04 | 2016-11-04 | 2016-10-25 | 2016-11-04 | Stirling | 0 | 6000 | -918.81 | 0 | 0 | 0 | 0 | 5081.19 | 0 | 5081.19 | 144841.4737 | [6 empty] | CS15A | 100%
502952 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-07-22 | 2022-09-28 | 2023-01-24 | 2023-09-05 | 2023-12-06 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 350000 | 0 | [6 empty] | CM_WWNI | 100%
403542 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2015-04-01 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2015-04-13 | Stirling | 57217.35 | 2276.45 | 0 | 0 | 0 | 0 | 0 | 2276.45 | 0 | 59493.8 | 0 | [6 empty] | SG1 | 100%
403656 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS7 | 2014-01-23 | 2014-01-23 | 2014-01-23 | 2015-02-05 |  | Dundee City | 40000 | -4807.02 | 0 | 0 | 0 | 0 | 0 | -4807.02 | 0 | 35192.98 | 0 | [6 empty] | CM_M&G | 100%
030909 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-15 | 2010-09-20 | 2010-11-29 | 2015-03-25 | 2015-03-31 | South Lanarkshire | 3384163.86 | -1850.83 | -15828.93 | 10 | 0 | 0 | 0 | -17669.76 | 0 | 3366494.1 | -144.16 | [6 empty] | CM_WWNI | 30.06% | EC04A | 69.94%
501560 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-02-22 | 2017-03-28 | 2017-03-29 | 2019-01-30 | 2019-01-30 | Scottish Water Wide | 0 | 3271.03 | -3271.03 | 585229.18 | 488936.63 | 0 | 0 | 1074165.81 | 0 | 1074165.81 | 0 | [6 empty] | CM_WWI | 100%
502230 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-05 | 2017-10-25 | Na H-Eileanan an Iar | 0 | 0 | 29318.35 | 3748.32 | 0 | 0 | 0 | 33066.67 | 0 | 33066.67 | 0 | [6 empty] | CM_WWI | 100%
403040 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-10-26 | 2013-12-13 | 2014-02-11 | 2014-09-01 |  | Na H-Eileanan an Iar | 60675.52 | 1662.48 | -198.03 | 0 | 0 | 0 | 0 | 1464.45 | 0 | 62139.97 | 0 | [6 empty] | CM_WSI | 100%
503421 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2018-10-31 | 2019-12-09 | 2020-03-16 | 2020-10-23 | 2021-01-29 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 15992.7 | 325530.37 | 401423.12 | 742946.19 | 7053.74 | 749999.93 | 0 | [6 empty] | CM_WSNI | 100%
046842 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2013-01-30 | 2015-01-13 | 2015-01-13 | 2015-01-13 | Highland | 1195343.9 | 1096.16 | 0 | 0 | 0 | 0 | 0 | 1096.16 | 0 | 1196440.06 | 0 | [6 empty] | DW23 | 100%
045556 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-29 | 2011-03-21 | 2011-07-29 | 2011-10-20 | 2011-11-28 | South Lanarkshire | 158832.66 | 750 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 159582.66 | 0 | [6 empty] | WQ01 | 100%
502829 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2021-07-05 | 2022-07-15 | 2022-11-07 | 2023-10-26 | 2024-01-26 | Aberdeen City | 0 | 0 | 0 | 64381.93 | 32910.79 | 34225.65 | 14056.35 | 145574.72 | 1606.87 | 147181.59 | 148885.7057 | [6 empty] | SG1 | 100%
501488 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS0 | 2016-07-19 | 2019-11-04 | 2020-01-13 | 2020-06-02 | 2020-09-04 | Dumfries and Galloway | 0 | 0 | 36764 | 127915 | 37261 | 291097.71 | 351385.28 | 844422.99 | 5460.27 | 849883.26 | 0 | [6 empty] | CM_WWNI | 100%
400097 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-12-04 | 2011-10-13 | 2012-01-16 | 2013-03-12 | 2013-03-29 | Dumfries and Galloway | 240483 | -3079.97 | 0 | 0 | 0 | 0 | 0 | -3079.97 | 0 | 237403.03 | 0 | [6 empty] | EC01C | 35.24% | EC01B | 64.76%
402629 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-03-23 | 2012-08-24 | 2012-10-22 | 2013-03-28 | 2013-03-28 | Dumfries and Galloway | 1074575 | 18325 | 1362 | -2818.2 | 0 | 0 | 0 | 16868.8 | 0 | 1091443.8 | 33240.0494 | [6 empty] | CS11A | 4.398% | CM_WWI | 26.13% | EC01B | 69.47%
402004 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-03-21 | 2012-03-27 | 2012-05-21 | 2014-03-31 | 2014-02-14 | Dumfries and Galloway | 1530026 | 0 | 3244 | -574.62 | 0 | 0 | 0 | 2669.38 | 0 | 1532695.38 | 0 | [6 empty] | EC01B | 100%
402130 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | SWD | Infra Charge | MS7 | 2011-07-19 | 2011-08-18 | 2011-08-18 | 2011-12-09 |  | City of Edinburgh | 13656.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13656.78 | 0 | [6 empty] | SG5 | 100%
500014 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-04-26 | 2022-09-23 | 2023-01-17 | 2024-04-10 | 2024-07-26 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2447845.08 | 2447845.08 | 0 | [6 empty] | CM_WSI | 100%
503532 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS2 | 2019-03-26 | 2019-03-26 | 2019-08-01 | 2021-03-08 | 2021-06-08 | Scottish Water Wide | 0 | 0 | 0 | 0 | 20934.58 | 133262.28 | 132745.76 | 286942.62 | 33057.31 | 319999.93 | 19186.1679 | [6 empty] | DW25TS | 100%
501784 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2021-05-03 | 2022-09-21 | 2023-01-25 | 2024-04-23 | 2024-07-24 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2700000 | 2700000 | 0 | [6 empty] | CM_WWI | 100%
030913 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-15 | 2010-09-20 | 2010-11-29 | 2012-03-16 | 2012-03-21 | South Lanarkshire | 1421096.89 | 256.56 | 0 | 0 | 0 | 0 | 0 | 256.56 | 0 | 1421353.45 | 0 | [6 empty] | CM_WWNI | 25% | EC10A | 75%
503274 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-10 | 2023-06-26 | 2023-10-27 | 2024-10-24 | 2025-01-24 | South Lanarkshire | 0 | 0 | 0 | 0 | 78644.4 | 0 | 0 | 78644.4 | 0 | 78644.4 | 148885.7057 | [6 empty] | SG1 | 100%
501365 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS0 | 2016-07-11 | 2022-04-11 | 2022-04-11 | 2022-04-11 | 2022-04-11 | Stirling | 0 | 0 | 61666.51 | 157031.29 | -13994.03 | 9132.91 | 33205.65 | 247042.33 | 951413.68 | 1198456.01 | 0 | [6 empty] | CM_WWNI | 100%
500110 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS3 | 2015-03-20 | 2017-03-28 | 2017-03-28 | 2019-09-01 | 2019-12-01 | Scottish Water Wide | 0 | 6834 | 60093.09 | 110167.91 | 246119 | 226678.64 | 80001.36 | 729894 | 0 | 729894 | 0 | [6 empty] | EC16 | 100% | bar: Regulatory Outputs OMG-21
045805 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2012-02-21 | 2012-07-31 | 2013-03-22 | 2013-03-22 | North Lanarkshire | 865314.3 | -1126.52 | 0 | 0 | 0 | 0 | 0 | -1126.52 | 0 | 864187.78 | 0 | [6 empty] | CM_WWNI | 10% | WQ01C | 90%
045557 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-26 | 2010-09-20 | 2011-07-07 | 2012-03-15 | 2012-03-26 | Fife | 880246.03 | 63492.33 | 0 | 0 | 0 | 0 | 0 | 63492.33 | 0 | 943738.36 | 0 | [6 empty] | CM_WWNI | 40% | WQ01 | 60%
501590 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2016-06-29 | 2017-09-12 | 2018-01-22 | 2019-05-06 | 2019-05-06 | Highland | 0 | 0 | 21107 | 403681 | 64765 | 0.03 | 450.94 | 490003.97 | 0 | 490003.97 | 0 | [6 empty] | CM_WWI | 100%
045369 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-31 | 2011-10-03 | 2012-07-29 | 2015-03-06 | Stirling | 211152.95 | 40.93 | 0 | 0 | 0 | 0 | 0 | 40.93 | 0 | 211193.88 | 0 | [6 empty] | DW13 | 100%
046846 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2012-05-25 | 2012-06-25 | 2012-08-02 | 2012-09-05 | Highland | 163858.09 | 2506.89 | 0 | 0 | 0 | 0 | 0 | 2506.89 | 0 | 166364.98 | 0 | [6 empty] | DW23 | 100%
403938 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | WWINF | Non OMG180 | MS6 | 2009-11-16 | 2015-10-29 | 2015-11-23 | 2018-02-23 | 2018-03-02 | Orkney Islands | 96078.05 | 3722788.95 | 4047033 | 537937 | 31163 | 0 | 0 | 8338921.95 | 0 | 8435000 | 8757358.1249 | [6 empty] | CM_WWI | 8% | EC01A | 92%
400089 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-11-16 | 2015-03-23 | 2014-12-01 | 2014-12-01 | 2015-02-03 | Orkney Islands | 1710547.5 | 1717.3 | -4686.13 | 20.795 | 0 | 0 | 0 | -2948.035 | 0 | 1707599.465 | 0 | [6 empty] | EC01A | 100%
500877 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-09-06 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Orkney Islands | 0 | 1392.07 | 2846.53 | 4955.33 | -4955.33 | 0 | 0 | 4238.6 | 0 | 4238.6 | 88222.4967 | [6 empty] | DW5FS | 100%
501092 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2016-10-28 | 2018-03-16 | 2018-03-27 | 2019-10-01 | 2020-01-01 | Orkney Islands | 0 | 27114.34 | 73480.8 | 514856.22 | 2447921.68 | 1008562.21 | 22087.78 | 4094023.03 | 12461.96 | 4106484.99 | 3611933.0944 |  |  |  |  | 2747.9304 |  | CM_WSI | 4.112% | DW25P | 95.89% | bar: Regulatory Outputs OMG-04
500878 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-10-28 | 2018-09-27 | 2018-12-04 | 2019-03-01 | 2019-11-01 | Highland | 0 | 691.03 | 1308.97 | 3005.65 | 13696.33 | 9378.98 | 0 | 28080.96 | 0 | 28080.96 | 36286.7908 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 10.71
045370 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-18 | 2011-07-22 | 2012-02-09 | 2012-03-14 | Highland | 189878.28 | 670.2 | 0 | 0 | 0 | 0 | 0 | 670.2 | 0 | 190548.48 | 0 | [6 empty] | DW13 | 100%
501553 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-02-23 | 2016-02-23 | 2016-04-01 | 2017-08-15 | 2017-08-15 | Scottish Water Wide | 0 | 99367.08 | 187182.91 | 4996.8 | 0 | 0 | 0 | 291546.79 | 0 | 291546.79 | 0 | [6 empty] | CM_WSI | 100%
500809 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS0 | 2018-04-16 | 2020-09-07 | 2021-01-15 | 2022-04-06 | 2022-07-07 | Aberdeenshire | 0 | 21343.43 | 78503.63 | 31227.73 | 23929.21 | 326322.64 | 168351.6 | 649678.24 | 813627.69 | 1463305.93 | 148885.7057 | [6 empty] | CM_WWNI | 1% | SG1 | 99%
500212 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS5 | 2015-03-20 | 2016-04-25 | 2016-06-20 | 2017-03-01 | 2018-06-01 | Na H-Eileanan an Iar | 0 | 422.12 | 32168.73 | -10634.73 | 1360 | 3000.01 | 0 | 26316.13 | 0 | 26316.13 | 39205.7757 | [6 empty] | DW5FS | 100% | bar: Regulatory Outputs OMG-02
500879 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS6 | 2016-03-31 | 2016-03-31 | 2016-07-18 | 2017-01-01 | 2017-11-01 | Na H-Eileanan an Iar | 0 | 2783.36 | 13967.64 | 21110.69 | 1137.945 | 1499.98 | 0 | 40499.615 | 0 | 40499.615 | 11582.9625 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 3.69
501647 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWMD | Water infrastructure | MS7 | 2017-04-20 | 2017-08-10 | 2017-09-08 | 2018-01-30 | 2018-02-14 | Scottish Water Wide | 0 | 0 | 0 | 188568.53 | 102.9 | 0 | 0 | 188671.43 | 0 | 188671.43 | 0 | [6 empty] | CM_M&G | 100%
502795 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2017-07-26 | 2017-07-26 | 2017-12-04 | 2018-05-24 | 2018-05-24 | Dumfries and Galloway | 0 | 0 | 0 | 383643 | 138894.41 | 2510.57 | 0 | 525047.98 | 0 | 525047.98 | 0 | [6 empty] | CM_WWI | 100%
046231 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2008-10-01 | 2019-02-05 | 2019-02-01 | 2019-02-01 | 2017-09-15 | Highland | 60708.56 | 0.44 | 0 | 0 | 0 | 0 | 0 | 0.44 | 0 | 60709 | 0 | [6 empty] | CM_WWI | 100%
402078 | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS1 | 2011-03-23 | 2021-03-02 | 2021-03-02 | 2021-03-02 |  | Scottish Water Wide | -23954419.94 | -3689233.89 | 0 | 0 | 0 | 0 | 0 | -3689233.89 | 0 | -27643653.83 | 0 | [6 empty] | REB | 100%
050008 | Q&S3B | Completion | OMG180 |  |  | General |  | SWD | OMG180 | MS3 | 2017-03-31 | 2017-03-31 | 2017-03-31 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | -10383243 | 0 | 0 | 0 | 0 | -10383243 | 0 | -10383243 | 0 | [6 empty] | SR15_ENV_WFD | 0.0001085% | SR15_DWA_PRE | 0.009395% | SR15_DWA_LEAK | 0.01532% | SR15_SEW_SWO | 0.02115% | SR15_ENV_CAS | 0.02447% | SR15_DWA_EFA | 0.03352% | SR15_SED_INFC | 0.05294% | SR15_CCH_CC | 0.07516% | SR15_COS_REN | 0.08947% | SR15_ENV_SLU | 0.09255%
050013 | Q&S3B | Exceptional Capital Maintenance | Exceptional Capital Maintenance |  |  | General |  | SWD | Exceptional Capital Maintenance | MS3 | 2017-04-01 | 2017-04-01 | 2017-04-01 |  |  | Scottish Water Wide | 0 | 0 | 0 | -7474506.12 | 0 | 0 | 0 | -7474506.12 | 0 | -7474506.12 | 0 | [6 empty] | WG3 | 0.002109% | SR15_IR18_IR18 | 0.008054% | SR15_DWA_LEAK | 0.01539% | SR15_DWQ_FUT | 0.02204% | SR15_DWA_PRE | 0.02407% | SR15_DWA_EFA | 0.02429% | SR15_CEX_IT | 0.0302% | SR15_ENV_WFD | 0.03341% | SR15_ENV_RBWD | 0.04742% | SR15_SEW_SWO | 0.05643%
050024 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | General |  | SWD | DWQ Compliance | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | -7809782.84 | 0 | 0 | -7809782.84 | 0 | -7809782.84 | 0 | [6 empty] | SR15_ENV_HABD | -0.2674% | SR15_DWA_PRE | -0.0005847% | SR15_CCH_CC | 0.006813% | SR15_IR18_IR18 | 0.01037% | SR15_CMP_PFI | 0.01121% | SR15_ENV_ODO | 0.01572% | SR15_CEX_CMGT | 0.01941% | WG3 | 0.02008% | SR15_CEX_STU | 0.02632% | SR15_DWA_EFA | 0.02635%
050025 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | General |  | SWD | DWQ Compliance | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2020-03-31 | 2020-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | -8000000 | 0 | -8000000 | 0 | -8000000 | 0 | [6 empty] | SR15_SEW_SWO | 0.006442% | SR15_DWA_PRE | 0.008092% | SR15_CEX_CMGT | 0.008444% | SR15_CEX_STU | 0.01429% | SR15_DWA_ITS | 0.01442% | SR15_DWA_EFA | 0.02385% | SR15_DWA_LEAK | 0.02574% | SR15_ENV_HABD | 0.03379% | SR15_ENV_ODO | 0.03431% | WG3 | 0.0382%
050026 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | General |  | SWD | DWQ Compliance | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | -5000000 | -5000000 | 0 | -5000000 | 0 | [6 empty] | SR15_SEW_SWO | 0.0002503% | SR15_ENV_ODO | 0.0002885% | SR15_CEX_STU | 0.005966% | SR15_DWA_EFA | 0.01108% | SR15_DWA_PRE | 0.02191% | WG3 | 0.02243% | SR15_CCH_CC | 0.02466% | SR15_DWA_ITS | 0.02602% | SR15_DWA_LEAK | 0.02642% | SR15_ENV_HABD | 0.03326%
502802 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2018-08-30 | 2018-08-31 | 2018-08-31 | 2018-09-03 | 2018-09-03 | South Lanarkshire | 0 | 0 | 0 | 149563.71 | -149562.71 | 0 | 0 | 1 | 0 | 1 | 10994109.1109 | [6 empty] | EC01A | 100%
502805 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS7 | 2018-09-03 | 2018-08-31 | 2018-08-31 | 2018-09-03 | 2018-09-03 | Glasgow City | 0 | 0 | 0 | 350093.375 | -350092.375 | 0 | 0 | 1 | 0 | 1 | 10994109.1109 | [6 empty] | EC01A | 100%
502900 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | General |  | SWD | Wastewater infrastructure | MS3 | 2017-09-20 | 2017-09-20 | 2017-12-20 | 2020-12-16 | 2021-02-17 | Scottish Water Wide | 0 | 0 | 0 | 237464 | 20390 | 141062.73 | 101083.25 | 499999.98 | 0 | 499999.98 | 0 | [6 empty] | CM_M&G | 100%
503096 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS0 | 2019-01-04 | 2019-04-15 | 2019-04-22 | 2021-01-14 | 2021-01-14 | Scottish Water Wide | 0 | 0 | 0 | 0 | 56000 | 121103.26 | 77896.74 | 255000 | 0 | 255000 | 294750.8556 | [6 empty] | CS25 | 100%
402124 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2011-06-20 | 2012-09-26 | 2012-10-22 | 2014-12-22 | 2015-03-10 | Scottish Water Wide | 1669909 | -7521.29 | 0 | 0 | 0 | 0 | 0 | -7521.29 | 0 | 1662387.71 | 0 | [6 empty] | DW23A | 100%
401268 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-09-15 | 2012-05-28 | 2012-09-24 | 2017-06-01 | 2017-09-01 | Scottish Water Wide | 989839.74 | 286982.51 | 120045.03 | 72219.37 | 0 | 0 | 0 | 479246.91 | 0 | 1469086.65 | 207999 | [6 empty] | CC5S | 100% | bar: Regulatory Outputs OMG-45
401270 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-09-15 | 2011-02-18 | 2011-02-21 | 2014-12-24 | 2015-03-27 | Aberdeenshire | 364159 | 440.69 | 0 | 0 | 0 | 0 | 0 | 440.69 | 0 | 364599.69 | 0 | [6 empty] | CC5S | 100%
503022 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2018-03-16 | 2018-03-16 | 2018-04-02 | 2018-12-12 | 2018-12-12 | Scottish Water Wide | 0 | 0 | 0 | 6214.95 | -6214.95 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSNI | 100%
502335 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2021-04-15 | 2021-03-31 | 2021-03-31 | 2021-04-15 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 2666665.98 | 2666667.98 | 5333333.96 | 0 | 5333333.96 | 0 | [6 empty] | CM_WSI | 100%
502087 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-02-29 | 2016-02-29 | 2016-04-01 | 2019-12-20 | 2019-12-23 | All East Unitary Authorities | 0 | 34383 | 298008 | 436585.64 | 181180.51 | 6926.07 | 1744.93 | 958828.15 | 0 | 958828.15 | 0 | [6 empty] | CM_WSI | 100%
502090 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-02-19 | 2016-02-19 | 2016-05-02 | 2019-10-07 | 2020-01-07 | All North Unitary Authorities | 0 | 16355.14 | 390215.03 | 500605.17 | 24827.71 | 72601.37 | 0 | 1004604.42 | 0 | 1004604.42 | 0 | [6 empty] | CM_WSI | 100%
502088 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-03-01 | 2016-03-01 | 2016-05-02 | 2019-08-30 | 2019-08-30 | All South Unitary Authorities | 0 | 69905 | 337763.25 | 1416479.05 | 345608.35 | 259168.4 | 0 | 2428924.05 | 0 | 2428924.05 | 0 | [6 empty] | CM_WSI | 100%
502089 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-03-01 | 2016-03-01 | 2016-05-13 | 2019-09-06 | 2019-09-09 | All West Unitary Authorities | 0 | 98130.84 | 956621.3 | 2088023.29 | 516442.95 | 168624.22 | 0 | 3827842.6 | 0 | 3827842.6 | 0 | [6 empty] | CM_WSI | 100%
502590 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2017-02-14 | 2017-02-14 | 2017-05-30 | 2020-04-27 | 2020-04-27 | All East Unitary Authorities | 0 | 0 | 49065.42 | 128742.276 | 256842.314 | 0 | 0 | 434650.01 | 0 | 434650.01 | 0 | [6 empty] | CM_WSI | 100%
502591 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2017-02-13 | 2017-02-13 | 2017-07-11 | 2019-08-20 | 2019-11-20 | All North Unitary Authorities | 0 | 0 | 34653.45 | 95661.83 | 137348.48 | 133822.78 | 0 | 401486.54 | 0 | 401486.54 | 0 | [6 empty] | CM_WSI | 100%
502592 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2017-02-14 | 2017-02-14 | 2017-05-01 | 2019-02-14 | 2019-02-14 | All South Unitary Authorities | 0 | 0 | 65552.1 | 638097.6 | 309920.44 | 0 | 0 | 1013570.14 | 0 | 1013570.14 | 0 | [6 empty] | CM_WSI | 100%
502593 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2017-02-28 | 2017-02-28 | 2018-06-05 | 2019-05-13 | 2019-07-25 | Scottish Water Wide | 0 | 0 | 51321.72 | 569457.615 | 152782.0425 | 37760.53 | 0 | 811321.9075 | 0 | 811321.9075 | 0 | [6 empty] | CM_WSI | 100%
502589 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS3 | 2017-02-17 | 2017-02-17 | 2017-04-17 | 2019-08-01 | 2019-08-01 | All West Unitary Authorities | 0 | 0 | 130841.12 | 1396243 | 1114617.28 | 272444.29 | 0 | 2914145.69 | 0 | 2914145.69 | 355374.0471 | [6 empty] | WR6 | 17% | CM_WSI | 83% | bar: Regulatory Outputs OMG-13
502291 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-08-03 | 2016-08-03 | 2016-10-25 | 2017-11-06 | 2017-11-06 | All East Unitary Authorities | 0 | 0 | 147749.31 | 82951.19 | -37048.53 | 0 | 0 | 193651.97 | 0 | 193651.97 | 0 | [6 empty] | CM_WWNI | 100%
502292 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-08-03 | 2016-08-03 | 2017-01-23 | 2017-05-22 | 2017-05-22 | All North Unitary Authorities | 0 | 0 | 891.04 | 0 | 0 | 0 | 0 | 891.04 | 0 | 891.04 | 0 | [6 empty] | CM_WWI | 50% | CM_WWNI | 50%
502293 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-08-03 | 2016-08-03 | 2016-10-25 | 2017-04-21 | 2017-04-21 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WWI | 100%
502294 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-08-03 | 2016-08-03 | 2017-05-22 | 2017-05-22 | 2017-05-22 | All West Unitary Authorities | 0 | 0 | 8618.63 | 0 | 0 | 0 | 0 | 8618.63 | 0 | 8618.63 | 0 | [6 empty] | CM_WWI | 50% | CM_WWNI | 50%
502295 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS5 | 2016-08-04 | 2016-08-04 | 2016-10-25 | 2018-02-06 | 2018-02-06 | All East Unitary Authorities | 0 | 0 | 239987.32 | 397254.35 | 994.51 | 0 | 0 | 638236.18 | 0 | 638236.18 | 0 | [6 empty] | CM_WSI | 25% | CM_WSNI | 75%
502296 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2016-08-04 | 2016-08-04 | 2017-01-23 | 2017-05-22 | 2017-05-22 | All North Unitary Authorities | 0 | 0 | 14833.02 | 631.08 | 0 | 0 | 0 | 15464.1 | 0 | 15464.1 | 0 | [6 empty] | CM_WSI | 25.34% | CM_WSNI | 74.66%
502297 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-08-04 | 2016-08-04 | 2016-10-25 | 2017-04-21 | 2017-04-21 | All South Unitary Authorities | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [6 empty] | CM_WSI | 100%
502298 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2016-08-04 | 2016-08-04 | 2017-03-01 | 2017-05-22 | 2017-05-22 | All West Unitary Authorities | 0 | 0 | 13711.75 | 84086.365 | 0 | 0 | 0 | 97798.115 | 0 | 97798.115 | 0 | [6 empty] | CM_WSI | 25% | CM_WSNI | 75%
503414 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2018-10-25 | 2018-10-25 | 2018-10-31 | 2021-02-19 | 2021-05-24 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 130841.12 | 1214950.02 | 523367.16 | 1869158.3 | 130841.79 | 2000000.09 | 0 | [6 empty] | CM_WWI | 100%
503477 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 | 2019-03-01 | 2019-03-01 | 2019-06-26 | 2019-11-27 | 2020-03-04 | Scottish Water Wide | 0 | 0 | 0 | 0 | 213271.03 | 3014499.83 | 19063.01 | 3246833.87 | 13166.07 | 3259999.94 | 0 | [6 empty] | CM_WWI | 100%
503005 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2018-01-29 | 2018-01-29 | 2018-04-02 | 2019-05-28 | 2019-05-28 | All East Unitary Authorities | 0 | 0 | 0 | 53644.86 | 1501977.0357 | 0 | 0 | 1555621.8957 | 0 | 1555621.8957 | 0 | [6 empty] | CM_WWI | 100%
503483 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MSU | 2019-07-01 | 2019-07-29 | 2019-10-17 | 2020-12-22 | 2021-03-30 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 67496.64 | 319504.5 | 474639.63 | 861640.77 | 25855.86 | 887496.63 | 0 | [6 empty] | CM_WWI | 100%
502979 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-15 | 2018-01-15 | 2018-01-23 | 2020-10-19 | 2020-10-19 | All East Unitary Authorities | 0 | 0 | 0 | 39906.54 | 219508.07 | 376366.52 | 38329.29 | 674110.42 | 0 | 674110.42 | 0 | [6 empty] | CM_WWI | 100%
502980 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2019-06-21 | 2019-06-21 | All East Unitary Authorities | 0 | 0 | 0 | 18009 | 255441.9 | 0 | 0 | 273450.9 | 0 | 273450.9 | 0 | [6 empty] | CM_WWI | 100%
503482 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 | 2019-03-01 | 2019-03-01 | 2019-06-26 | 2020-10-06 | 2021-01-12 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 410964.265 | 1708953.99 | 1401115.97 | 3521034.225 | 30116.91 | 3551151.135 | 0 | [6 empty] | CM_WWNI | 100%
503484 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 | 2019-02-28 | 2019-02-28 | 2019-06-04 | 2020-09-01 | 2020-11-26 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 157009.35 | 110000.01 | 0 | 267009.36 | 0 | 267009.36 | 0 | [6 empty] | CM_WWI | 33.33% | CM_WWNI | 66.67%
503485 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS2 | 2019-02-28 | 2019-02-28 | 2019-06-04 | 2020-05-28 | 2020-10-13 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 78700.31 | 306000.01 | 807120.05 | 1191820.37 | 8375.3 | 1200195.67 | 0 | [6 empty] | CM_WWNI | 43.33% | CM_WWI | 56.67%
503006 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2018-01-29 | 2018-01-29 | 2018-04-02 | 2019-05-28 | 2019-05-28 | All East Unitary Authorities | 0 | 0 | 0 | 128644.86 | 827793.1142 | 58581.78 | 0 | 1015019.7542 | 0 | 1015019.7542 | 0 | [6 empty] | CM_WWI | 100%
502981 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-15 | 2018-01-15 | 2018-01-23 | 2020-05-04 | 2020-05-04 | All East Unitary Authorities | 0 | 0 | 0 | 40176.875 | 424985.605 | 49999.99 | 0 | 515162.47 | 0 | 515162.47 | 0 | [6 empty] | CM_WWI | 100%
502982 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2019-09-13 | 2019-09-13 | All East Unitary Authorities | 0 | 0 | 0 | 19009 | 325323.74 | 44326.14 | 0 | 388658.88 | 0 | 388658.88 | 0 | [6 empty] | CM_WWI | 100%
503007 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2018-01-31 | 2018-01-31 | 2018-04-02 | 2019-05-28 | 2019-05-28 | All East Unitary Authorities | 0 | 0 | 0 | 288694.3475 | 1722125.9052 | 30047.7 | 0 | 2040867.9527 | 0 | 2040867.9527 | 0 | [6 empty] | CM_WWI | 100%
502983 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-31 | 2018-01-31 | 2018-02-08 | 2020-06-30 | 2020-06-30 | All East Unitary Authorities | 0 | 0 | 0 | 80696.035 | 118971.255 | 372509.15 | 39490.85 | 611667.29 | 0 | 611667.29 | 0 | [6 empty] | CM_WWI | 100%
502984 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2019-12-06 | 2019-12-06 | All East Unitary Authorities | 0 | 0 | 0 | 69257 | 1061028.79 | 558202.31 | 0 | 1688488.1 | 0 | 1688488.1 | 0 | [6 empty] | CM_WWI | 100%
503003 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2021-02-15 | 2021-02-15 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 436945.8895 | 74900 | 0 | 511845.8895 | 0 | 511845.8895 | 0 | [6 empty] | CM_WWI | 100%
503472 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 | 2019-03-01 | 2019-03-01 | 2019-06-10 | 2021-01-11 | 2021-04-13 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 153267.7 | 131521.55 | 778.46 | 285567.71 | 23000.01 | 308567.72 | 0 | [6 empty] | CM_WWI | 13.48% | CM_WWNI | 86.52%
503442 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2019-07-01 | 2019-07-01 | 2019-10-29 | 2020-12-29 | 2020-12-30 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 236.8 | 1463383.68 | 2046616.3 | 3510236.78 | 0 | 3510236.78 | 0 | [6 empty] | CM_WWI | 7.193% | CM_WWNI | 92.81%
503008 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2018-01-31 | 2018-01-31 | 2018-02-05 | 2019-09-02 | 2019-09-02 | All North Unitary Authorities | 0 | 0 | 0 | 70626.17 | 575220.5107 | 0 | 0 | 645846.6807 | 0 | 645846.6807 | 0 | [6 empty] | CM_WWI | 100%
502985 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-29 | 2018-01-29 | 2018-02-21 | 2020-01-06 | 2020-01-07 | All North Unitary Authorities | 0 | 0 | 0 | 22562.99 | -20231.77 | 0 | 0 | 2331.22 | 0 | 2331.22 | 0 | [6 empty] | CM_WWI | 100%
502986 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-29 | 2018-01-29 | 2018-02-21 | 2020-01-06 | 2020-01-07 | All North Unitary Authorities | 0 | 0 | 0 | 12524.805 | 53236.495 | 220.88 | 0 | 65982.18 | 0 | 65982.18 | 0 | [6 empty] | CM_WWI | 100%
503009 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2018-01-31 | 2018-01-31 | 2018-02-05 | 2019-09-02 | 2019-09-02 | All North Unitary Authorities | 0 | 0 | 0 | 98495.33 | 774630.1292 | 122280.37 | 0 | 995405.8292 | 0 | 995405.8292 | 0 | [6 empty] | CM_WWI | 100%
502987 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-29 | 2018-01-29 | 2018-02-21 | 2020-01-06 | 2020-01-07 | All North Unitary Authorities | 0 | 0 | 0 | 22758.61 | 83179.65 | 74119.69 | 0 | 180057.95 | 0 | 180057.95 | 0 | [6 empty] | CM_WWI | 100%
502988 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-29 | 2018-01-29 | 2018-02-21 | 2019-07-08 | 2019-07-09 | All North Unitary Authorities | 0 | 0 | 0 | 9478.88 | 19803.37 | 0 | 0 | 29282.25 | 0 | 29282.25 | 0 | [6 empty] | CM_WWI | 100%
503010 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2018-01-31 | 2018-01-31 | 2018-02-05 | 2019-09-02 | 2019-09-02 | All North Unitary Authorities | 0 | 0 | 0 | 272626.17 | 2165938.19 | 214435.64 | 0 | 2653000 | 0 | 2653000 | 0 | [6 empty] | CM_WWI | 100%
502989 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-31 | 2018-01-31 | 2018-02-21 | 2019-09-09 | 2019-09-10 | All North Unitary Authorities | 0 | 0 | 0 | 119553.64 | 537082.12 | 5246.74 | 0 | 661882.5 | 0 | 661882.5 | 0 | [6 empty] | CM_WWI | 100%
502990 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-30 | 2018-01-30 | 2018-02-21 | 2019-05-06 | 2019-05-07 | All North Unitary Authorities | 0 | 0 | 0 | 18637.76 | 48403.33 | 0 | 0 | 67041.09 | 0 | 67041.09 | 0 | [6 empty] | CM_WWI | 100%
503465 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 | 2019-03-12 | 2019-03-12 | 2019-05-27 | 2021-03-29 | 2021-03-29 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 170093.46 | 121999.98 | 0 | 292093.44 | 0 | 292093.44 | 0 | [6 empty] | CM_WWI | 28.85% | CM_WWNI | 71.15%
503466 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2019-03-12 | 2019-03-12 | 2019-03-26 | 2020-11-12 | 2021-02-10 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 105673.38 | 55000 | 0 | 160673.38 | 0 | 160673.38 | 0 | [6 empty] | CM_WWI | 31.25% | CM_WWNI | 68.75%
503011 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2018-01-22 | 2018-01-22 | 2018-04-02 | 2019-06-14 | 2019-06-14 | All South Unitary Authorities | 0 | 0 | 0 | 179964.33 | 1651499.22 | 0 | 0 | 1831463.55 | 0 | 1831463.55 | 0 | [6 empty] | CM_WWI | 100%
503460 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 | 2019-02-28 | 2019-02-28 | 2019-06-26 | 2020-10-16 | 2020-10-16 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 204161.74 | 604062.21 | 517433.11 | 1325657.06 | 0 | 1325657.06 | 0 | [6 empty] | CM_WWI | 100%
502991 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-29 | 2018-01-29 | 2018-02-08 | 2020-06-19 | 2020-06-19 | All South Unitary Authorities | 0 | 0 | 0 | 58878.5 | 114151 | 116949 | 0 | 289978.5 | 0 | 289978.5 | 0 | [6 empty] | CM_WWI | 100%
502992 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-26 | 2018-01-26 | 2018-02-08 | 2019-09-17 | 2019-05-13 | All South Unitary Authorities | 0 | 0 | 0 | 90093.46 | 1020084.33 | 79004.42 | 0 | 1189182.21 | 0 | 1189182.21 | 0 | [6 empty] | CM_WWI | 100%
503459 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 | 2019-03-20 | 2019-03-20 | 2019-04-01 | 2020-07-21 | 2020-07-21 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 247242.705 | 2101785.42 | 1262700.54 | 3611728.665 | 0 | 3611728.665 | 0 | [6 empty] | CM_WWNI | 100%
503012 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2018-01-31 | 2018-01-31 | 2018-02-26 | 2019-06-14 | 2019-06-14 | All South Unitary Authorities | 0 | 0 | 0 | 87081.56 | 496275.2832 | 637324.45 | 0 | 1220681.2932 | 0 | 1220681.2932 | 0 | [6 empty] | CM_WWI | 100%
502993 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-15 | 2018-01-15 | 2018-01-30 | 2020-06-29 | 2020-06-29 | All South Unitary Authorities | 0 | 0 | 0 | 58920.09 | 124866.91 | 211709.99 | 0 | 395496.99 | 0 | 395496.99 | 0 | [6 empty] | CM_WWI | 100%
502994 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-26 | 2018-01-26 | 2018-02-08 | 2019-09-13 | 2019-09-13 | All South Unitary Authorities | 0 | 0 | 0 | 24859.81 | 205646.57 | 94965.99 | 0 | 325472.37 | 0 | 325472.37 | 0 | [6 empty] | CM_WWI | 100%
503013 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2018-01-31 | 2018-01-31 | 2018-02-26 | 2019-06-14 | 2019-06-14 | All South Unitary Authorities | 0 | 0 | 0 | 226700.96 | 3374770.66 | 0 | 0 | 3601471.62 | 0 | 3601471.62 | 0 | [6 empty] | CM_WWI | 100%
502995 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-17 | 2018-01-17 | 2018-01-30 | 2020-06-19 | 2020-06-19 | All South Unitary Authorities | 0 | 0 | 0 | 117102.8 | 731507.26 | 550432.97 | 0 | 1399043.03 | 0 | 1399043.03 | 0 | [6 empty] | CM_WWI | 100%
502996 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-29 | 2018-01-29 | 2018-02-08 | 2019-12-06 | 2019-05-13 | All South Unitary Authorities | 0 | 0 | 0 | 50373.83 | 1248908.87 | 471550.32 | 0 | 1770833.02 | 0 | 1770833.02 | 0 | [6 empty] | CM_WWI | 100%
503004 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-01-22 | 2018-01-22 | 2018-01-30 | 2021-06-28 | 2021-06-28 | All South Unitary Authorities | 0 | 0 | 0 | 98130.84 | 31000 | 686462.92 | 457971.2 | 1273564.96 | 226435.04 | 1500000 | 0 | [6 empty] | CM_WWI | 100%
503471 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 | 2019-03-12 | 2019-03-12 | 2019-04-01 | 2020-07-21 | 2020-10-13 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 137671.18 | 30000.01 | 0 | 167671.19 | 0 | 167671.19 | 0 | [6 empty] | CM_WWI | 33.33% | CM_WWNI | 66.67%
503468 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS2 | 2019-03-12 | 2019-03-12 | 2019-04-01 | 2020-07-21 | 2020-10-13 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 78504.67 | 0 | 0 | 78504.67 | 0 | 78504.67 | 0 | [6 empty] | CM_WWI | 16.67% | CM_WWNI | 83.33%
503014 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2018-01-31 | 2018-01-31 | 2018-02-01 | 2019-07-31 | 2019-07-31 | All West Unitary Authorities | 0 | 0 | 0 | 230015.05 | 2828179.0307 | 0 | 0 | 3058194.0807 | 0 | 3058194.0807 | 0 | [6 empty] | CM_WWI | 100%
503458 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS2 | 2019-02-27 | 2019-02-27 | 2019-06-26 | 2020-10-16 | 2020-10-16 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 280093.17 | 503385.18 | 431194.28 | 1214672.63 | 0 | 1214672.63 | 0 | [6 empty] | CM_WWI | 100%
502997 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-02-27 | 2018-02-27 | 2018-04-09 | 2019-09-05 | 2019-09-06 | All West Unitary Authorities | 0 | 0 | 0 | 42523.36 | 24098.29 | 185901.72 | 0 | 252523.37 | 0 | 252523.37 | 0 | [6 empty] | CM_WWI | 100%
502998 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-02-26 | 2018-02-26 | 2018-06-08 | 2019-09-16 | 2019-09-17 | All West Unitary Authorities | 0 | 0 | 0 | 22897.2 | 921874.19 | 496329.89 | 0 | 1441101.28 | 0 | 1441101.28 | 0 | [6 empty] | CM_WWI | 100%
503457 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS2 | 2019-03-13 | 2019-03-13 | 2019-04-01 | 2020-07-21 | 2020-07-21 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 311070.09 | 2370346.89 | 1424045.6 | 4105462.58 | 0 | 4105462.58 | 0 | [6 empty] | CM_WWNI | 100%
503015 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2018-01-31 | 2018-01-31 | 2018-02-01 | 2019-07-31 | 2019-07-31 | All West Unitary Authorities | 0 | 0 | 0 | 128794.68 | 1099398.57 | 186806.74 | 0 | 1414999.99 | 0 | 1414999.99 | 0 | [6 empty] | CM_WWI | 100%
502999 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-02-28 | 2018-02-28 | 2018-04-09 | 2019-09-11 | 2019-09-12 | All West Unitary Authorities | 0 | 0 | 0 | 34866.481 | 156015.079 | 153443.84 | 0 | 344325.4 | 0 | 344325.4 | 0 | [6 empty] | CM_WWI | 100%
503000 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-02-28 | 2018-02-28 | 2018-06-08 | 2019-09-16 | 2019-09-17 | All West Unitary Authorities | 0 | 0 | 0 | 21588.79 | 46941.93 | 480269.36 | 0 | 548800.08 | 0 | 548800.08 | 0 | [6 empty] | CM_WWI | 100%
503016 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2018-01-31 | 2018-01-31 | 2018-02-01 | 2019-07-31 | 2019-07-31 | All West Unitary Authorities | 0 | 0 | 0 | 243794.17 | 2902456.98 | 0 | 0 | 3146251.15 | 0 | 3146251.15 | 0 | [6 empty] | CM_WWI | 100%
503001 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-02-27 | 2018-02-27 | 2018-04-09 | 2019-09-06 | 2019-09-09 | All West Unitary Authorities | 0 | 0 | 0 | 65420.56 | 251819.79 | 114728.46 | 0 | 431968.81 | 0 | 431968.81 | 0 | [6 empty] | CM_WWI | 100%
503002 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2018-02-27 | 2018-02-27 | 2018-06-08 | 2019-09-16 | 2019-09-17 | All West Unitary Authorities | 0 | 0 | 0 | 36064.49 | 466483.56 | 251650.99 | 0 | 754199.04 | 0 | 754199.04 | 0 | [6 empty] | CM_WWI | 100%
502444 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS5 | 2017-01-19 | 2017-01-19 | 2017-04-03 | 2018-06-21 | 2018-06-21 | All East Unitary Authorities | 0 | 0 | 40209.39 | 259372.15 | 20728 | 74696.99 | 0 | 395006.53 | 0 | 395006.53 | 0 | [6 empty] | CM_WWI | 100%
502445 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-04-12 | 2018-07-12 | 2018-07-12 | All East Unitary Authorities | 0 | 0 | 17271.81 | 289275.37 | -26808.171 | 0 | 0 | 279739.009 | 0 | 279739.009 | 0 | [6 empty] | CM_WWI | 100%
502446 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2017-01-19 | 2017-01-19 | 2017-04-03 | 2019-05-28 | 2019-05-28 | All East Unitary Authorities | 0 | 0 | 54130.98 | 794080.88 | 1107052 | 0 | 0 | 1955263.86 | 0 | 1955263.86 | 0 | [6 empty] | CM_WWI | 100%
502447 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-05-09 | 2019-02-14 | 2019-02-14 | All North Unitary Authorities | 0 | 0 | 23030.38 | 349732.23 | 108802.9105 | 0 | 0 | 481565.5205 | 0 | 481565.5205 | 0 | [6 empty] | CM_WWI | 100%
502448 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2017-01-12 | 2017-01-12 | 2017-06-05 | 2018-03-01 | 2018-03-01 | All North Unitary Authorities | 0 | 0 | 9158.88 | 21530.4475 | 122.985 | 0 | 0 | 30812.3125 | 0 | 30812.3125 | 0 | [6 empty] | CM_WWI | 100%
502449 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2017-01-17 | 2017-01-17 | 2017-04-04 | 2019-04-15 | 2019-04-15 | All North Unitary Authorities | 0 | 0 | 58048.82 | 511951.18 | -9999.996 | 0 | 0 | 560000.004 | 0 | 560000.004 | 0 | [6 empty] | CM_WWI | 100%
502450 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2017-01-19 | 2017-01-19 | 2017-04-12 | 2019-12-20 | 2019-12-20 | All South Unitary Authorities | 0 | 0 | 58878.5 | 159000 | 128071 | 0 | 0 | 345949.5 | 0 | 345949.5 | 0 | [6 empty] | CM_WWI | 100%
502451 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2017-01-17 | 2017-01-17 | 2017-04-03 | 2019-06-14 | 2019-06-14 | All South Unitary Authorities | 0 | 0 | 29859.81 | 1188240.72 | 131076.16 | 0 | 0 | 1349176.69 | 0 | 1349176.69 | 0 | [6 empty] | CM_WWI | 100%
502452 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS5 | 2017-01-31 | 2017-01-31 | 2017-04-10 | 2019-03-13 | 2019-03-13 | All South Unitary Authorities | 0 | 0 | 78504.67 | 951441.69 | 1144589.39 | 68217.25 | 0 | 2242753 | 0 | 2242753 | 0 | [6 empty] | CM_WWI | 100%
502453 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS3 | 2017-01-19 | 2017-01-19 | 2017-04-12 | 2020-01-30 | 2020-01-31 | All West Unitary Authorities | 0 | 0 | 50373.83 | 287587.66 | 499933.33 | 118952.69 | 0 | 956847.51 | 0 | 956847.51 | 0 | [6 empty] | CM_WWI | 100%
502454 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS5 | 2017-01-17 | 2017-01-17 | 2017-04-14 | 2019-02-04 | 2019-02-04 | All West Unitary Authorities | 0 | 0 | 21588.79 | 431943.8715 | -57922.5085 | 0 | 0 | 395610.153 | 0 | 395610.153 | 0 | [6 empty] | CM_WWI | 100%
502455 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS5 | 2017-01-31 | 2017-01-31 | 2017-11-17 | 2019-03-12 | 2019-03-12 | All West Unitary Authorities | 0 | 0 | 118889.89 | 682155.96 | 1074403.71 | 59861.47 | 0 | 1935311.03 | 0 | 1935311.03 | 0 | [6 empty] | CM_WWI | 100%
502475 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-02-07 | 2017-02-07 | 2017-05-09 | 2019-09-06 | 2019-09-06 | All South Unitary Authorities | 0 | 0 | 50373.83 | 731308.98 | 519465.24 | 0 | 0 | 1301148.05 | 0 | 1301148.05 | 0 | [6 empty] | CM_WWNI | 100%
502456 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS5 | 2017-01-19 | 2017-01-19 | 2017-04-03 | 2018-06-21 | 2018-06-21 | All East Unitary Authorities | 0 | 0 | 40169.02 | 9921.77 | -43592.23 | 0 | 0 | 6498.56 | 0 | 6498.56 | 0 | [6 empty] | CM_WWNI | 100%
502457 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS5 | 2017-01-17 | 2017-01-17 | 2017-05-18 | 2019-02-06 | 2019-02-06 | All East Unitary Authorities | 0 | 0 | 17261.7 | 320845.65 | 373084.19 | 0 | 0 | 711191.54 | 0 | 711191.54 | 0 | [6 empty] | CM_WWNI | 100%
502458 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2017-01-19 | 2017-01-19 | 2017-04-03 | 2019-05-28 | 2019-05-28 | All East Unitary Authorities | 0 | 0 | 57984.24 | 899798.95 | 423490.27 | 0 | 0 | 1381273.46 | 0 | 1381273.46 | 0 | [6 empty] | CM_WWNI | 100%
502459 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-01-17 | 2017-01-17 | 2017-05-09 | 2018-03-01 | 2018-03-01 | All North Unitary Authorities | 0 | 0 | 22529.71 | 2366.7195 | 123.225 | 0 | 0 | 25019.6545 | 0 | 25019.6545 | 0 | [6 empty] | CM_WWNI | 100%
502460 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-01-12 | 2017-01-12 | 2017-06-05 | 2018-04-23 | 2018-04-23 | All North Unitary Authorities | 0 | 0 | 9158.88 | 31153.46 | -38090.3925 | 0 | 0 | 2221.9475 | 0 | 2221.9475 | 0 | [6 empty] | CM_WWNI | 100%
502461 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS5 | 2017-01-17 | 2017-01-17 | 2017-05-09 | 2019-03-19 | 2019-03-19 | All North Unitary Authorities | 0 | 0 | 37148.49 | 456010.3 | 271350.532 | 0 | 0 | 764509.322 | 0 | 764509.322 | 0 | [6 empty] | CM_WWNI | 100%
502463 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-01-17 | 2017-01-17 | 2017-04-03 | 2019-06-21 | 2019-06-21 | All South Unitary Authorities | 0 | 0 | 24859.81 | 431596 | 371520 | 0 | 0 | 827975.81 | 0 | 827975.81 | 0 | [6 empty] | CM_WWNI | 100%
502462 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-01-19 | 2017-01-19 | 2017-05-18 | 2019-12-20 | 2019-12-20 | All South Unitary Authorities | 0 | 0 | 58878.5 | 237285 | 169121 | 0 | 0 | 465284.5 | 0 | 465284.5 | 0 | [6 empty] | CM_WWNI | 100%
502464 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS5 | 2017-01-31 | 2017-01-31 | 2017-11-17 | 2019-03-13 | 2019-03-13 | All South Unitary Authorities | 0 | 0 | 100800.1 | 486923.44 | 221643.565 | 0 | 0 | 809367.105 | 0 | 809367.105 | 0 | [6 empty] | CM_WWNI | 100%
502465 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS5 | 2017-01-19 | 2017-01-19 | 2017-04-24 | 2019-03-05 | 2019-03-05 | All West Unitary Authorities | 0 | 0 | 50373.83 | 170024.68 | 292801.17 | 0 | 0 | 513199.68 | 0 | 513199.68 | 0 | [6 empty] | CM_WWNI | 100%
502466 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS5 | 2017-01-17 | 2017-01-17 | 2017-06-05 | 2018-09-27 | 2018-09-27 | All West Unitary Authorities | 0 | 0 | 21588.79 | 153500 | 98000 | 0 | 0 | 273088.79 | 0 | 273088.79 | 0 | [6 empty] | CM_WWNI | 100%
502467 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS5 | 2017-01-13 | 2017-01-13 | 2017-11-17 | 2019-03-12 | 2019-03-12 | All West Unitary Authorities | 0 | 0 | 117589.11 | 970455.163 | 211791.45 | 19588.5 | 0 | 1319424.223 | 0 | 1319424.223 | 0 | [6 empty] | CM_WWNI | 100%
502468 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-02-11 | 2017-02-11 | 2017-04-03 | 2019-05-15 | 2019-08-15 | All East Unitary Authorities | 0 | 0 | 80810.37 | 545906.92 | 439971.76 | 0 | 0 | 1066689.05 | 0 | 1066689.05 | 0 | [6 empty] | CM_WWNI | 100%
502469 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-02-24 | 2017-02-24 | 2017-06-06 | 2019-06-14 | 2019-06-14 | All East Unitary Authorities | 0 | 0 | 34915.11 | 1444276.71 | 1417660.79 | 0 | 0 | 2896852.61 | 0 | 2896852.61 | 0 | [6 empty] | CM_WWNI | 100%
502470 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2017-02-11 | 2017-02-11 | 2017-04-03 | 2019-05-28 | 2019-05-28 | All East Unitary Authorities | 0 | 0 | 250598.84 | 1340246.5615 | 813085.7385 | 0 | 0 | 2403931.14 | 0 | 2403931.14 | 0 | [6 empty] | CM_WWNI | 100%
502471 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-02-24 | 2017-02-24 | 2017-07-18 | 2019-07-01 | 2019-10-01 | All North Unitary Authorities | 0 | 0 | 44160.79 | 592584.24 | 300191.07 | 0 | 0 | 936936.1 | 0 | 936936.1 | 0 | [6 empty] | CM_WWNI | 100%
502472 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2017-02-24 | 2017-02-24 | 2017-06-05 | 2018-04-19 | 2018-04-19 | All North Unitary Authorities | 0 | 0 | 18317.76 | 212592 | -2031.77 | 0 | 0 | 228877.99 | 0 | 228877.99 | 0 | [6 empty] | CM_WWNI | 100%
502473 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS5 | 2017-02-24 | 2017-02-24 | 2017-05-09 | 2019-03-19 | 2019-03-19 | All North Unitary Authorities | 0 | 0 | 61701.45 | 1493864.88 | 189210.7995 | 0 | 0 | 1744777.1295 | 0 | 1744777.1295 | 0 | [6 empty] | CM_WWNI | 100%
502474 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-02-11 | 2017-02-11 | 2017-03-06 | 2020-04-23 | 2020-04-23 | All South Unitary Authorities | 0 | 0 | 122102.8 | 633470.69 | 1044401.21 | 312440.26 | 0 | 2112414.96 | 0 | 2112414.96 | 0 | [6 empty] | CM_WWNI | 100%
502476 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2017-02-21 | 2017-02-21 | 2017-11-17 | 2019-07-16 | 2019-07-17 | All South Unitary Authorities | 0 | 0 | 267845.74 | 2324769.4575 | 655911.415 | 30681.12 | 0 | 3279207.7325 | 0 | 3279207.7325 | 0 | [6 empty] | CM_WWNI | 100%
502477 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2017-02-11 | 2017-02-11 | 2017-04-17 | 2019-07-05 | 2019-07-08 | All West Unitary Authorities | 0 | 0 | 100093.46 | 4171.775 | 141863.585 | 0 | 0 | 246128.82 | 0 | 246128.82 | 0 | [6 empty] | CM_WWNI | 100%
502478 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS5 | 2017-02-24 | 2017-02-24 | 2017-06-05 | 2019-01-18 | 2019-01-18 | All West Unitary Authorities | 0 | 0 | 43177.57 | 253073.106 | 462100.994 | 0 | 0 | 758351.67 | 0 | 758351.67 | 0 | [6 empty] | CM_WWNI | 100%
502479 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS5 | 2017-02-11 | 2017-02-11 | 2017-11-24 | 2019-03-12 | 2019-03-12 | All West Unitary Authorities | 0 | 0 | 162750.5 | 2210274.085 | 624813.652 | 66348.68 | 0 | 3064186.917 | 0 | 3064186.917 | 0 | [6 empty] | CM_WWNI | 100%
501946 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-01 | 2018-08-22 | 2018-08-22 | All East Unitary Authorities | 0 | 80284.31 | 93835.69 | 42115.26 | -45735.6315 | 0 | 0 | 170499.6285 | 0 | 170499.6285 | 0 | [6 empty] | CM_WWI | 100%
502107 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-01 | 2018-04-11 | 2018-04-11 | All East Unitary Authorities | 0 | 0 | 941016.01 | 44658.66 | 0 | 0 | 0 | 985674.67 | 0 | 985674.67 | 0 | [6 empty] | CM_WWI | 100%
502110 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-01 | 2017-11-07 | 2017-11-07 | All East Unitary Authorities | 0 | 69226 | 202912.72 | 93310.0615 | 0 | 0 | 0 | 365448.7815 | 0 | 365448.7815 | 0 | [6 empty] | CM_WWNI | 100%
502115 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-01 | 2019-03-01 | 2019-03-01 | All East Unitary Authorities | 0 | 0 | 1160765.69 | 291718.1 | 49803.285 | 0 | 0 | 1502287.075 | 0 | 1502287.075 | 0 | [6 empty] | CM_WWNI | 100%
502116 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-01 | 2017-11-06 | 2017-11-06 | All East Unitary Authorities | 0 | 138452 | 350558.18 | -12279.7565 | 395.515 | 0 | 0 | 477125.9385 | 0 | 477125.9385 | 0 | [6 empty] | CM_WWNI | 100%
502117 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-03-22 | 2016-03-22 | 2016-03-31 | 2019-03-01 | 2019-03-01 | All East Unitary Authorities | 0 | 69566.77 | 2689689.9 | 325123.9 | 33171.56 | 0 | 0 | 3117552.13 | 0 | 3117552.13 | 0 |  |  |  |  | 26166 |  | CM_WWNI | 100%
502118 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-03-21 | 2016-03-21 | 2016-04-08 | 2018-06-01 | 2018-06-01 | All North Unitary Authorities | 0 | 0 | 165357.12 | 159245.06 | 1637.102 | 0 | 0 | 326239.282 | 0 | 326239.282 | 0 | [6 empty] | CM_WWI | 100%
502119 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2016-03-21 | 2016-03-21 | 2016-04-08 | 2017-11-07 | 2017-11-07 | All North Unitary Authorities | 0 | 21261.68 | 348851.63 | 14068.72 | 0 | 0 | 0 | 384182.03 | 0 | 384182.03 | 0 | [6 empty] | CM_WWI | 100%
502120 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-04-01 | 2016-04-01 | 2016-07-12 | 2018-02-12 | 2018-02-12 | All North Unitary Authorities | 0 | 0 | 46596.44 | 66090.32 | 0 | 0 | 0 | 112686.76 | 0 | 112686.76 | 0 | [6 empty] | CM_WWNI | 100%
502121 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-07-15 | 2017-11-07 | 2017-11-07 | All North Unitary Authorities | 0 | 0 | 872058.84 | 26855.82 | 0 | 0 | 0 | 898914.66 | 0 | 898914.66 | 0 | [6 empty] | CM_WWNI | 100%
502122 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-03-31 | 2016-03-31 | 2016-04-08 | 2018-02-12 | 2018-02-12 | All North Unitary Authorities | 0 | 99766 | 418520.19 | 184681.895 | 6335.465 | 0 | 0 | 709303.55 | 0 | 709303.55 | 0 | [6 empty] | CM_WWNI | 100%
502123 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-03-29 | 2016-03-29 | 2016-07-05 | 2017-12-11 | 2017-12-11 | All North Unitary Authorities | 0 | 789.82 | 1601184.3 | 485071.12 | -34756 | 0 | 0 | 2052289.24 | 0 | 2052289.24 | 0 | [6 empty] | CM_WWNI | 100%
502108 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-04-22 | 2016-04-22 | 2016-05-03 | 2017-11-02 | 2017-11-02 | All South Unitary Authorities | 0 | 0 | 1382308.47 | -314033.12 | -15967.481 | 0 | 0 | 1052307.869 | 0 | 1052307.869 | 0 | [6 empty] | CM_WWI | 100%
502109 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-08-22 | 2018-03-07 | 2018-03-07 | All South Unitary Authorities | 0 | 0 | 715123.96 | 152602.15 | 0 | 0 | 0 | 867726.11 | 0 | 867726.11 | 0 | [6 empty] | CM_WWI | 100%
502111 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-06-01 | 2017-09-18 | 2017-09-18 | All South Unitary Authorities | 0 | 85049 | 240592.28 | 163393.66 | -29604.72 | 0 | 0 | 459430.22 | 0 | 459430.22 | 0 | [6 empty] | CM_WWNI | 100%
502112 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-08-22 | 2018-03-07 | 2018-03-07 | All South Unitary Authorities | 0 | 0 | 710417.27 | 56800.92 | 0 | 0 | 0 | 767218.19 | 0 | 767218.19 | 0 | [6 empty] | CM_WWNI | 100%
502113 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS5 | 2016-03-01 | 2016-03-01 | 2016-04-22 | 2018-08-22 | 2018-08-22 | All South Unitary Authorities | 0 | 174054 | 1485077.91 | 437811.62 | -183756.91 | 0 | 0 | 1913186.62 | 0 | 1913186.62 | 0 | [6 empty] | CM_WWNI | 100%
502114 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-06-22 | 2018-03-30 | 2018-03-30 | All South Unitary Authorities | 0 | 0 | 3072628.91 | 399426.78 | 0 | 0 | 0 | 3472055.69 | 0 | 3472055.69 | 0 | [6 empty] | CM_WWNI | 100%
502101 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS5 | 2016-02-29 | 2016-02-29 | 2016-04-22 | 2019-02-04 | 2019-02-04 | All West Unitary Authorities | 0 | 0 | 898415.53 | 606132.34 | 150456.15 | 0 | 0 | 1655004.02 | 0 | 1655004.02 | 0 | [6 empty] | CM_WWI | 100%
502102 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2016-03-01 | 2016-03-01 | 2016-04-22 | 2018-11-01 | 2018-11-01 | All West Unitary Authorities | 0 | 100000 | 895393.46 | 11368.5 | -16603.94 | 0 | 0 | 990158.02 | 0 | 990158.02 | 0 | [6 empty] | CM_WWI | 100%
502103 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS5 | 2016-02-29 | 2016-02-29 | 2016-04-22 | 2019-01-08 | 2019-01-08 | All West Unitary Authorities | 0 | 0 | 445790.08 | 295399.79 | 31726.99 | 0 | 0 | 772916.86 | 0 | 772916.86 | 0 | [6 empty] | CM_WWNI | 100%
502104 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-22 | 2018-11-01 | 2018-11-01 | All West Unitary Authorities | 0 | 0 | 1150817.3 | 141092.275 | 62554.285 | 0 | 0 | 1354463.86 | 0 | 1354463.86 | 0 | [6 empty] | CM_WWNI | 100%
502105 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2016-03-01 | 2016-03-01 | 2016-04-22 | 2018-08-24 | 2018-08-24 | All West Unitary Authorities | 0 | 0 | 942656.67 | 292059.72 | -25524.2615 | 0 | 0 | 1209192.1285 | 0 | 1209192.1285 | 0 | [6 empty] | CM_WWNI | 100%
502106 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-22 | 2018-11-01 | 2018-11-01 | All West Unitary Authorities | 0 | 0 | 2538780.7 | 458187.21 | 119331.16 | 0 | 0 | 3116299.07 | 0 | 3116299.07 | 0 | [6 empty] | CM_WWNI | 100%
502482 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2017-02-17 | 2017-02-17 | 2017-11-22 | 2019-07-05 | 2019-07-18 | Scottish Water Wide | 0 | 0 | 17009.35 | 161645.82 | -5482.44 | 0 | 0 | 173172.73 | 0 | 173172.73 | 0 | [6 empty] | CM_WSI | 100%
502484 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2017-02-14 | 2017-02-14 | 2017-05-08 | 2018-12-10 | 2018-12-10 | All East Unitary Authorities | 0 | 0 | 33364.49 | 313277.0925 | 239090.9595 | 0 | 0 | 585732.542 | 0 | 585732.542 | 0 | [6 empty] | CM_WSI | 100%
502485 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2017-02-17 | 2017-02-17 | 2017-04-03 | 2019-07-01 | 2019-07-01 | All East Unitary Authorities | 0 | 0 | 147850.47 | 307366.7739 | 2239581.092 | 0 | 0 | 2694798.3359 | 0 | 2694798.3359 | 0 | [6 empty] | CM_WSI | 100%
502487 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2017-02-13 | 2017-02-13 | 2017-06-05 | 2019-01-17 | 2019-01-17 | All North Unitary Authorities | 0 | 0 | 29439.25 | 86552.4585 | 52894.1695 | 0 | 0 | 168885.878 | 0 | 168885.878 | 0 | [6 empty] | CM_WSI | 100%
502488 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2017-02-17 | 2017-02-17 | 2017-05-05 | 2018-11-29 | 2018-11-29 | All North Unitary Authorities | 0 | 0 | 134724.68 | 467986.4494 | 1462279.402 | 0 | 0 | 2064990.5314 | 0 | 2064990.5314 | 0 | [6 empty] | CM_WSI | 100%
502490 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2017-02-13 | 2017-02-13 | 2017-05-17 | 2018-06-07 | 2018-06-07 | All South Unitary Authorities | 0 | 0 | 31401.87 | 181507 | 69097 | 0 | 0 | 282005.87 | 0 | 282005.87 | 0 | [6 empty] | CM_WSI | 100%
502491 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2017-02-17 | 2017-02-17 | 2017-11-10 | 2019-07-15 | 2019-07-15 | All South Unitary Authorities | 0 | 0 | 152104.4 | 715323.0304 | 3255613.812 | 0 | 0 | 4123041.2424 | 0 | 4123041.2424 | 0 | [6 empty] | CM_WSI | 100%
502493 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2017-02-24 | 2017-02-24 | 2017-06-05 | 2018-11-05 | 2018-11-05 | All West Unitary Authorities | 0 | 0 | 35327.1 | 116871.76 | 102885.86 | 0 | 0 | 255084.72 | 0 | 255084.72 | 0 | [6 empty] | CM_WSI | 100%
502494 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2017-02-23 | 2017-02-23 | 2017-11-24 | 2019-07-04 | 2019-08-21 | All West Unitary Authorities | 0 | 0 | 157009.35 | 289282.6287 | 3921969.3713 | 0 | 0 | 4368261.35 | 0 | 4368261.35 | 0 | [6 empty] | CM_WSI | 100%
502481 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2017-02-10 | 2017-02-10 | 2017-04-28 | 2019-06-21 | 2019-09-23 | Scottish Water Wide | 0 | 0 | 15046.73 | 8000 | 53274.25 | 987.82 | 0 | 77308.8 | 0 | 77308.8 | 0 | [6 empty] | CM_WSI | 100%
502483 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2017-02-17 | 2017-02-17 | 2017-05-17 | 2020-07-31 | 2020-08-03 | All East Unitary Authorities | 0 | 0 | 78504.67 | 122522 | 178973.33 | 225000.02 | 0 | 605000.02 | 0 | 605000.02 | 0 | [6 empty] | CM_WSI | 100%
502486 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2017-02-17 | 2017-02-17 | 2017-05-17 | 2020-01-06 | 2020-01-10 | All North Unitary Authorities | 0 | 0 | 68217.38 | 708205.98 | 1060727.58 | 1229.86 | 0 | 1838380.8 | 0 | 1838380.8 | 0 | [6 empty] | CM_WSI | 100%
502489 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2017-02-17 | 2017-02-17 | 2017-05-17 | 2019-01-18 | 2019-01-18 | All South Unitary Authorities | 0 | 0 | 72616.82 | 329027.71 | 78385.82 | 1548.26 | 1722.52 | 483301.13 | 1729.21 | 485030.34 | 0 | [6 empty] | CM_WSI | 100%
502492 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2017-02-17 | 2017-02-17 | 2017-04-24 | 2019-10-11 | 2019-10-14 | All West Unitary Authorities | 0 | 0 | 81775.7 | 563023 | 450110.57 | 150453.06 | 0 | 1245362.33 | 0 | 1245362.33 | 0 | [6 empty] | CM_WSI | 100%
502495 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS5 | 2017-02-13 | 2017-02-13 | 2017-04-24 | 2018-09-06 | 2018-09-06 | Scottish Water Wide | 0 | 0 | 28130.84 | 76905.27 | 557.79 | 0 | 0 | 105593.9 | 0 | 105593.9 | 0 | [6 empty] | CM_WSNI | 100%
502496 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-01-31 | 2017-01-31 | 2017-06-22 | 2020-10-29 | 2020-10-30 | All East Unitary Authorities | 0 | 0 | 16355.14 | -367.02 | 4708.48 | 50000 | 0 | 70696.6 | 0 | 70696.6 | 0 | [6 empty] | CM_WSNI | 100%
502499 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-01 | 2017-02-01 | 2017-06-05 | 2020-01-10 | 2020-04-13 | All North Unitary Authorities | 0 | 0 | 13738.32 | 300564.4 | 218564.64 | 53499.31 | 0 | 586366.67 | 0 | 586366.67 | 0 | [6 empty] | CM_WSNI | 100%
502502 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-01 | 2017-02-01 | 2017-06-05 | 2020-03-20 | 2020-06-22 | All South Unitary Authorities | 0 | 0 | 15046.73 | 16335 | 37460 | 147047 | 0 | 215888.73 | 0 | 215888.73 | 0 | [6 empty] | CM_WSNI | 100%
502505 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-01-31 | 2017-01-31 | 2017-04-17 | 2019-06-03 | 2019-06-04 | All West Unitary Authorities | 0 | 0 | 16355.14 | 1161.5425 | 20369.7075 | 0 | 0 | 37886.39 | 0 | 37886.39 | 0 | [6 empty] | CM_WSNI | 100%
502508 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS5 | 2017-02-09 | 2017-02-09 | 2017-06-05 | 2018-11-29 | 2018-11-29 | All East Unitary Authorities | 0 | 0 | 8504.67 | 73000 | 107902.442 | 0 | 0 | 189407.112 | 0 | 189407.112 | 0 | [6 empty] | CM_WSNI | 100%
502511 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-13 | 2017-02-13 | 2017-06-05 | 2019-10-07 | 2019-12-18 | All North Unitary Authorities | 0 | 0 | 7196.26 | 33135.09 | 96370.82 | 136000 | 0 | 272702.17 | 0 | 272702.17 | 0 | [6 empty] | CM_WSNI | 100%
502514 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2017-02-09 | 2017-02-09 | 2017-05-05 | 2018-06-26 | 2018-06-26 | All South Unitary Authorities | 0 | 0 | 7226.53 | 25269.73 | -6290.605 | 0 | 0 | 26205.655 | 0 | 26205.655 | 0 | [6 empty] | CM_WSNI | 100%
502517 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-10 | 2017-02-10 | 2017-04-17 | 2019-08-30 | 2019-09-02 | All West Unitary Authorities | 0 | 0 | 8504.67 | 28000 | 49037.57 | 4500 | 0 | 90042.24 | 0 | 90042.24 | 0 | [6 empty] | CM_WSNI | 100%
502520 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-10 | 2017-02-10 | 2017-04-17 | 2018-09-26 | 2018-09-26 | Scottish Water Wide | 0 | 0 | 15046.73 | 1354.333 | 162661.099 | 0 | 0 | 179062.162 | 0 | 179062.162 | 0 | [6 empty] | CM_WSNI | 100%
502522 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-24 | 2017-02-24 | 2017-07-25 | 2020-12-11 | 2021-03-19 | All East Unitary Authorities | 0 | 0 | 54299.07 | 437948.09 | 47984.65 | 150000 | 0 | 690231.81 | 0 | 690231.81 | 0 | [6 empty] | CM_WSNI | 100%
502525 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-14 | 2017-02-14 | 2017-05-25 | 2020-01-06 | 2020-01-08 | All North Unitary Authorities | 0 | 0 | 47222.8 | 298041.76 | 898741.96 | 256070.88 | 0 | 1500077.4 | 0 | 1500077.4 | 0 | [6 empty] | CM_WSNI | 100%
502528 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-14 | 2017-02-14 | 2017-04-03 | 2020-11-06 | 2021-02-12 | All South Unitary Authorities | 0 | 0 | 51155.71 | 390012.085 | 406816.325 | 104420.21 | 57855.2 | 1010259.53 | 0 | 1010259.53 | 0 | [6 empty] | CM_WSNI | 100%
502531 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-14 | 2017-02-14 | 2017-04-24 | 2019-06-03 | 2019-06-04 | All West Unitary Authorities | 0 | 0 | 57570.09 | 18500 | 4581.97 | 28.82 | 0 | 80680.88 | 0 | 80680.88 | 0 | [6 empty] | CM_WSNI | 100%
502497 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-01-31 | 2017-01-31 | 2017-05-15 | 2019-04-26 | 2019-04-26 | All East Unitary Authorities | 0 | 0 | 7196.26 | 186881.82 | 368988.77 | 0 | 0 | 563066.85 | 0 | 563066.85 | 0 | [6 empty] | CM_WSNI | 100%
502500 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-01 | 2017-02-01 | 2017-06-05 | 2019-07-08 | 2019-07-09 | All North Unitary Authorities | 0 | 0 | 5887.85 | 67664.62 | 15030.37 | 0 | 0 | 88582.84 | 0 | 88582.84 | 0 | [6 empty] | CM_WSNI | 100%
502503 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS5 | 2017-02-09 | 2017-02-09 | 2017-05-01 | 2018-10-16 | 2018-10-16 | All South Unitary Authorities | 0 | 0 | 6542.06 | 138266 | 132663.48 | 0 | 0 | 277471.54 | 0 | 277471.54 | 0 | [6 empty] | CM_WSNI | 100%
502506 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-09 | 2017-02-09 | 2017-06-05 | 2019-07-22 | 2019-07-23 | All West Unitary Authorities | 0 | 0 | 7196.26 | 417547.2125 | 3587.2475 | 0 | 0 | 428330.72 | 0 | 428330.72 | 0 | [6 empty] | CM_WSNI | 100%
502509 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-09 | 2017-02-09 | 2017-06-05 | 2018-08-06 | 2018-08-06 | All East Unitary Authorities | 0 | 0 | 3271.03 | 9739.25 | -13009.28 | 0 | 0 | 1 | 0 | 1 | 0 | [6 empty] | CM_WSNI | 100%
502512 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-13 | 2017-02-13 | 2017-06-05 | 2018-04-19 | 2018-04-19 | All North Unitary Authorities | 0 | 0 | 3271.03 | 144435.23 | -5610.9485 | 0 | 0 | 142095.3115 | 0 | 142095.3115 | 0 | [6 empty] | CM_WSNI | 100%
502515 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2017-02-09 | 2017-02-09 | 2017-06-05 | 2018-11-05 | 2018-11-05 | All South Unitary Authorities | 0 | 0 | 3271.03 | 4000 | 7082.194 | 0 | 0 | 14353.224 | 0 | 14353.224 | 0 | [6 empty] | CM_WSNI | 100%
502518 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS5 | 2017-02-09 | 2017-02-09 | 2017-06-05 | 2018-09-28 | 2018-09-28 | All West Unitary Authorities | 0 | 0 | 3271.03 | 66085.96 | 11.465 | 0 | 0 | 69368.455 | 0 | 69368.455 | 0 | [6 empty] | CM_WSNI | 100%
502523 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS5 | 2017-02-13 | 2017-02-13 | 2017-06-22 | 2019-01-21 | 2019-01-21 | All East Unitary Authorities | 0 | 0 | 23551.4 | 476577.86 | 30344.87 | 0 | 0 | 530474.13 | 0 | 530474.13 | 0 | [6 empty] | CM_WSNI | 100%
502526 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS5 | 2017-02-13 | 2017-02-13 | 2017-06-05 | 2019-03-04 | 2019-03-04 | All North Unitary Authorities | 0 | 0 | 20280.37 | 309836.02 | 180527.243 | 0 | 0 | 510643.633 | 0 | 510643.633 | 0 | [6 empty] | CM_WSNI | 100%
502529 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-13 | 2017-02-13 | 2017-04-24 | 2019-08-16 | 2019-08-19 | All South Unitary Authorities | 0 | 0 | 21588.79 | 91954 | 93663 | 0 | 0 | 207205.79 | 0 | 207205.79 | 0 | [6 empty] | CM_WSNI | 100%
502532 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-02-13 | 2017-02-13 | 2017-06-05 | 2019-05-27 | 2019-05-28 | All West Unitary Authorities | 0 | 0 | 24859.81 | 251781.6575 | 7582.5225 | 2734.13 | 0 | 286958.12 | 0 | 286958.12 | 0 |  |  |  |  | 251457.43 |  | CM_WSNI | 100%
502498 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-17 | 2017-02-17 | 2017-04-03 | 2019-07-01 | 2019-07-01 | All East Unitary Authorities | 0 | 0 | 30093.46 | 476924.73 | 48640.61 | 0 | 0 | 555658.8 | 0 | 555658.8 | 0 | [6 empty] | CM_WSNI | 100%
502501 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-15 | 2017-02-15 | 2017-05-09 | 2018-10-23 | 2018-10-23 | All North Unitary Authorities | 0 | 0 | 25514.02 | 126581.97 | 25889.425 | 0 | 0 | 177985.415 | 0 | 177985.415 | 0 | [6 empty] | CM_WSNI | 100%
502504 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-13 | 2017-02-13 | 2017-11-03 | 2019-07-15 | 2019-07-15 | All South Unitary Authorities | 0 | 0 | 36829.43 | 243343.72 | 125745.0675 | 0 | 0 | 405918.2175 | 0 | 405918.2175 | 0 | [6 empty] | CM_WSNI | 100%
502507 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-13 | 2017-02-13 | 2017-11-24 | 2019-06-13 | 2019-09-13 | All West Unitary Authorities | 0 | 0 | 31601.87 | 252881.98 | 130734.12 | 0 | 0 | 415217.97 | 0 | 415217.97 | 0 | [6 empty] | CM_WSNI | 100%
502510 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-16 | 2017-02-16 | 2017-04-03 | 2019-07-01 | 2019-07-01 | All East Unitary Authorities | 0 | 0 | 17224.93 | 178302.8 | 1938209.6845 | 0 | 0 | 2133737.4145 | 0 | 2133737.4145 | 0 | [6 empty] | CM_WSNI | 100%
502513 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-24 | 2017-02-24 | 2017-05-05 | 2018-08-01 | 2018-08-01 | All North Unitary Authorities | 0 | 0 | 21368.42 | 95116.91 | -10926.972 | 0 | 0 | 105558.358 | 0 | 105558.358 | 0 | [6 empty] | CM_WSNI | 100%
502516 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-09 | 2017-02-09 | 2017-11-17 | 2019-07-15 | 2019-07-15 | All South Unitary Authorities | 0 | 0 | 14392.52 | 26318 | 1365314.36 | 0 | 0 | 1406024.88 | 0 | 1406024.88 | 0 | [6 empty] | CM_WSNI | 100%
502519 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-09 | 2017-02-09 | 2017-11-24 | 2019-06-05 | 2019-06-06 | All West Unitary Authorities | 0 | 0 | 15046.73 | 74121.03 | 1260551.48 | 3 | 0 | 1349722.24 | 0 | 1349722.24 | 0 | [6 empty] | CM_WSNI | 100%
502521 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2017-02-13 | 2017-02-13 | 2017-11-15 | 2018-08-09 | 2018-08-09 | Scottish Water Wide | 0 | 0 | 17009.35 | 222365.372 | 27709.4345 | 0 | 0 | 267084.1565 | 0 | 267084.1565 | 0 | [6 empty] | CM_WSNI | 100%
502524 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-23 | 2017-02-23 | 2017-04-03 | 2019-07-01 | 2019-07-01 | All East Unitary Authorities | 0 | 0 | 126302.07 | 1583071.1595 | 528832.9305 | 0 | 0 | 2238206.16 | 0 | 2238206.16 | 0 | [6 empty] | CM_WSNI | 100%
502527 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-17 | 2017-02-17 | 2017-05-05 | 2019-04-15 | 2019-04-15 | All North Unitary Authorities | 0 | 0 | 121398.58 | 1476037.16 | 564341.532 | 0 | 0 | 2161777.272 | 0 | 2161777.272 | 0 | [6 empty] | CM_WSNI | 100%
502530 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-17 | 2017-02-17 | 2017-11-24 | 2019-07-15 | 2019-07-15 | All South Unitary Authorities | 0 | 0 | 149801.52 | 1548484.605 | 768112.99 | 33600.89 | 0 | 2500000.005 | 0 | 2500000.005 | 0 | [6 empty] | CM_WSNI | 100%
502533 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-02-17 | 2017-02-17 | 2017-11-24 | 2019-07-11 | 2019-08-28 | All West Unitary Authorities | 0 | 0 | 108598.13 | 1437275.46 | 1632266.81 | 0 | 0 | 3178140.4 | 0 | 3178140.4 | 0 | [6 empty] | CM_WSNI | 100%
503515 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2019-03-21 | 2019-03-21 | 2019-04-02 | 2020-03-10 | 2020-06-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 29439.25 | 0 | 0 | 29439.25 | 0 | 29439.25 | 0 | [6 empty] | CM_WSI | 37.5% | CM_WSNI | 62.5%
503516 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2019-03-21 | 2019-03-21 | 2019-04-02 | 2020-03-10 | 2020-06-10 | Scottish Water Wide | 0 | 0 | 0 | 0 | 19626.17 | 277572 | 2802 | 300000.17 | 0 | 300000.17 | 0 | [6 empty] | CM_WSI | 37.5% | CM_WSNI | 62.5%
502032 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-03-01 | 2016-03-01 | 2016-05-23 | 2017-11-22 | 2017-11-22 | Scottish Water Wide | 0 | 0 | 45000 | 0 | -44999 | 0 | 0 | 1 | 0 | 1 | 0 | [6 empty] | CM_WSI | 100%
502033 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-02-29 | 2018-03-29 | 2018-03-29 | Scottish Water Wide | 0 | 32710.28 | 502748.49 | -334919.11 | -13294.48 | 0 | 0 | 187245.18 | 0 | 187245.18 | 0 | [6 empty] | CM_WSI | 100%
503031 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-02-23 | 2018-02-23 | 2018-04-02 | 2019-09-20 | 2019-09-23 | Scottish Water Wide | 0 | 0 | 0 | 98130.84 | 445611.51 | 176409.02 | 0 | 720151.37 | 0 | 720151.37 | 0 | [6 empty] | CM_WSNI | 100%
503021 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2018-02-23 | 2018-02-23 | 2018-04-02 | 2019-09-30 | 2019-09-30 | Scottish Water Wide | 0 | 0 | 0 | 130841.12 | 894315.38 | 674843.5 | 0 | 1700000 | 0 | 1700000 | 0 | [6 empty] | CM_WSNI | 100%
502138 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 2017-03-27 | 2017-03-27 | Scottish Water Wide | 0 | 0 | 67316.24 | -67316.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WSI | 100%
502139 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-04-06 | 2016-04-06 | 2016-04-06 | 2018-03-19 | 2018-03-19 | Scottish Water Wide | 0 | 0 | 121710.28 | 101500 | -7255.1 | 0 | 0 | 215955.18 | 0 | 215955.18 | 0 | [6 empty] | CM_WSI | 100%
502140 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2018-03-29 | 2018-03-29 | Scottish Water Wide | 0 | 32710.28 | 202735.38 | 7542.0375 | -16813.89 | 0 | 0 | 226173.8075 | 0 | 226173.8075 | 0 | [6 empty] | CM_WSI | 100%
503520 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2019-03-11 | 2019-03-11 | 2019-08-01 | 2021-04-26 | 2021-04-26 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 23704.55 | 0 | 0 | 23704.55 | 0 | 23704.55 | 0 | [6 empty] | CM_WSI | 25% | CM_WSNI | 75%
503521 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2019-03-12 | 2019-03-12 | 2019-06-03 | 2021-02-04 | 2021-05-07 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 107512.98 | 0 | 0 | 107512.98 | 0 | 107512.98 | 0 | [6 empty] | CM_WSI | 25% | CM_WSNI | 75%
503519 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2019-03-13 | 2019-03-13 | 2019-08-01 | 2021-03-08 | 2021-06-08 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 256947.94 | 1565619.78 | 1559551.49 | 3382119.21 | 388370.8 | 3770490.01 | 0 | [6 empty] | CM_WSI | 35% | CM_WSNI | 65%
502034 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-03-22 | 2016-03-22 | 2016-03-31 | 2018-09-21 | 2018-09-21 | All East Unitary Authorities | 0 | 145953.27 | 255999.73 | 32587 | -41812.6175 | 0 | 0 | 392727.3825 | 0 | 392727.3825 | 0 | [6 empty] | CM_WSI | 100%
502035 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2016-02-29 | 2016-02-29 | 2016-04-01 | 2019-07-01 | 2019-07-01 | All East Unitary Authorities | 0 | 62542.06 | 204859 | 14148 | -47931.31 | 16382.26 | 0 | 250000.01 | 0 | 250000.01 | 0 | [6 empty] | CM_WSI | 100%
503027 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-01-25 | 2018-01-25 | 2018-01-30 | 2021-01-22 | 2021-04-23 | All East Unitary Authorities | 0 | 0 | 0 | 141075 | 183536.47 | 477638.34 | 398665.67 | 1200915.48 | 0 | 1200915.48 | 0 | [6 empty] | CM_WSNI | 100%
503028 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-01-30 | 2018-01-30 | 2018-02-20 | 2019-12-06 | 2019-12-06 | All East Unitary Authorities | 0 | 0 | 0 | 203521.9564 | 203593.1236 | 992884.92 | 0 | 1400000 | 0 | 1400000 | 0 | [6 empty] | CM_WSNI | 100%
503019 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2018-01-30 | 2018-01-30 | 2018-04-02 | 2019-06-28 | 2019-06-28 | All East Unitary Authorities | 0 | 0 | 0 | 337074.1684 | 5862329.7716 | 1940596.07 | 0 | 8140000.01 | 0 | 8140000.01 | 0 | [6 empty] | CM_WSNI | 100%
502141 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-04-06 | 2016-04-06 | 2016-04-18 | 2017-08-29 | 2017-08-29 | All East Unitary Authorities | 0 | 0 | 269177.57 | 37130.235 | 0 | 0 | 0 | 306307.805 | 0 | 306307.805 | 0 | [6 empty] | CM_WSI | 100%
502142 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2016-03-30 | 2016-03-30 | 2016-04-08 | 2019-07-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 388640.88 | 127289.64 | -34226.25 | 87369.39 | 0 | 569073.66 | 0 | 569073.66 | 0 | [6 empty] | CM_WSI | 100%
502143 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-03-29 | 2016-03-29 | 2016-04-08 | 2019-12-19 | 2019-12-20 | All East Unitary Authorities | 0 | 0 | 24588.79 | 80000 | 228.8775 | 0 | 0 | 104817.6675 | 0 | 104817.6675 | 0 | [6 empty] | CM_WSI | 100%
502144 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2016-03-29 | 2016-03-29 | 2016-04-01 | 2019-07-01 | 2019-07-01 | All East Unitary Authorities | 0 | 0 | 271746.44 | 66372.56 | -32058.85 | 26316.78 | 0 | 332376.93 | 0 | 332376.93 | 0 | [6 empty] | CM_WSI | 100%
502145 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-04-22 | 2016-04-22 | 2016-04-27 | 2020-07-16 | 2020-07-17 | All East Unitary Authorities | 0 | 0 | 673737.69 | 951148.04 | -241284.5 | 59031.79 | 325.23 | 1442958.25 | 0 | 1442958.25 | 0 | [6 empty] | CM_WSI | 100%
502146 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2016-03-29 | 2016-03-29 | 2016-04-01 | 2019-07-01 | 2019-07-01 | All East Unitary Authorities | 0 | 43766.36 | 1637034.29 | 522640.495 | 61527.125 | 0 | 0 | 2264968.27 | 0 | 2264968.27 | 0 | [6 empty] | CM_WSI | 100%
503509 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS2 | 2019-03-21 | 2019-03-21 | 2019-06-10 | 2021-04-05 | 2021-07-06 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 106670.38 | 0 | 0 | 106670.38 | 16305.31 | 122975.69 | 0 | [6 empty] | CM_WSNI | 45% | CM_WSI | 55%
503510 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2019-03-20 | 2019-03-20 | 2019-08-01 | 2021-03-08 | 2021-06-08 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 23704.55 | 0 | 0 | 23704.55 | 3623.4 | 27327.95 | 0 | [6 empty] | CM_WSI | 50% | CM_WSNI | 50%
503508 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2019-07-01 | 2019-08-05 | 2019-12-05 | 2021-07-12 | 2021-10-12 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 200.365 | 1235027.7 | 1889298.32 | 3124526.385 | 1175103.01 | 4299629.395 | 0 | [6 empty] | CM_WSI | 50% | CM_WSNI | 50%
502036 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-03-22 | 2016-03-22 | 2016-04-08 | 2018-12-11 | 2018-12-11 | All North Unitary Authorities | 0 | 110757.01 | 652461.22 | 1081310.1 | 116422.089 | 0 | 0 | 1960950.419 | 0 | 1960950.419 | 0 | [6 empty] | CM_WSI | 100%
502037 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-02-29 | 2016-02-29 | 2016-04-15 | 2017-11-02 | 2017-11-02 | All North Unitary Authorities | 0 | 49720 | 348294.43 | -9814.17 | 0 | 0 | 0 | 388200.26 | 0 | 388200.26 | 0 | [6 empty] | CM_WSI | 100%
503023 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-02-07 | 2018-02-07 | 2018-02-21 | 2020-04-01 | 2020-06-26 | All North Unitary Authorities | 0 | 0 | 0 | 362716.97 | 3048347.65 | 810925.69 | 0 | 4221990.31 | 0 | 4221990.31 | 0 | [6 empty] | CM_WSNI | 100%
503024 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-01-31 | 2018-01-31 | 2018-02-21 | 2020-01-06 | 2020-04-01 | All North Unitary Authorities | 0 | 0 | 0 | 70456.686 | 441765.394 | 197631.61 | 3654.02 | 713507.71 | 0 | 713507.71 | 0 | [6 empty] | CM_WSNI | 100%
503017 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2019-09-30 | 2019-09-30 | All North Unitary Authorities | 0 | 0 | 0 | 252897.2 | 4588934.28 | 0 | 0 | 4841831.48 | 0 | 4841831.48 | 0 | [6 empty] | CM_WSNI | 100%
502147 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-04-11 | 2016-04-11 | 2016-04-25 | 2018-09-03 | 2018-09-03 | All North Unitary Authorities | 0 | 0 | 209475.38 | 230476.25 | -102975.1185 | 0 | 0 | 336976.5115 | 0 | 336976.5115 | 0 | [6 empty] | CM_WSI | 100%
502148 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-30 | 2016-03-30 | 2016-04-08 | 2018-07-26 | 2018-07-26 | All North Unitary Authorities | 0 | 15832 | 146168 | 26135.14 | 0 | 0 | 0 | 188135.14 | 0 | 188135.14 | 0 | [6 empty] | CM_WSI | 100%
502149 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-03-29 | 2016-03-29 | 2016-04-08 | 2018-04-19 | 2018-04-19 | All North Unitary Authorities | 0 | 12300 | 1285.71 | 9841.53 | -32.785 | 0 | 0 | 23394.455 | 0 | 23394.455 | 0 | [6 empty] | CM_WSI | 100%
502150 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-30 | 2016-03-30 | 2016-04-08 | 2017-11-01 | 2017-11-01 | All North Unitary Authorities | 0 | 5299 | 125701 | -3882.42 | 0 | 0 | 0 | 127117.58 | 0 | 127117.58 | 0 | [6 empty] | CM_WSI | 100%
502151 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2016-04-22 | 2016-04-22 | 2016-04-25 | 2018-09-03 | 2018-09-03 | All North Unitary Authorities | 0 | 0 | 218846.77 | 340785.59 | 17515.535 | 0 | 0 | 577147.895 | 0 | 577147.895 | 0 | [6 empty] | CM_WSI | 100%
502152 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2016-03-29 | 2016-03-29 | 2016-04-08 | 2018-07-26 | 2018-07-26 | All North Unitary Authorities | 0 | 36897.2 | 1392363.33 | 325043.84 | 0 | 0 | 0 | 1754304.37 | 0 | 1754304.37 | 0 | [6 empty] | CM_WSNI | 100%
503513 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2019-03-26 | 2019-03-26 | 2019-08-01 | 2021-04-07 | 2021-04-07 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 35556.79 | 0 | 0 | 35556.79 | 0 | 35556.79 | 0 | [6 empty] | CM_WSI | 25% | CM_WSNI | 75%
503514 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS2 | 2019-03-26 | 2019-03-26 | 2019-08-01 | 2021-04-06 | 2021-04-06 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 47409.04 | 0 | 0 | 47409.04 | 0 | 47409.04 | 0 | [6 empty] | CM_WSI | 40% | CM_WSNI | 60%
503512 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2019-03-21 | 2019-03-21 | 2019-10-31 | 2020-12-15 | 2020-12-22 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 2870084.69 | 2813251.34 | 5683336.03 | 0 | 5683336.03 | 0 | [6 empty] | CM_WSI | 50% | CM_WSNI | 50%
502038 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2016-03-22 | 2016-03-22 | 2016-04-08 | 2018-06-26 | 2018-06-26 | All South Unitary Authorities | 0 | 165579.44 | 253284.43 | 2138667.06 | 415059.18 | 0 | 0 | 2972590.11 | 0 | 2972590.11 | 0 | [6 empty] | CM_WSI | 100%
502039 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-01 | 2016-03-01 | 2016-08-24 | 2018-02-01 | 2018-02-01 | All South Unitary Authorities | 0 | 70981.31 | 482034.06 | 54779.435 | 0 | 0 | 0 | 607794.805 | 0 | 607794.805 | 0 | [6 empty] | CM_WSI | 100%
503025 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-02-06 | 2018-02-06 | 2018-02-08 | 2020-07-27 | 2020-07-28 | All South Unitary Authorities | 0 | 0 | 0 | 140367.72 | 626293.31 | 719495.24 | 364778.53 | 1850934.8 | 0 | 1850934.8 | 0 | [6 empty] | CM_WSNI | 100%
503026 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-02-06 | 2018-02-06 | 2018-02-08 | 2019-09-13 | 2019-09-13 | All South Unitary Authorities | 0 | 0 | 0 | 52336.45 | 834902.36 | 503240.21 | 0 | 1390479.02 | 0 | 1390479.02 | 0 | [6 empty] | CM_WSNI | 100%
503018 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2018-02-21 | 2018-02-21 | 2018-02-21 | 2019-12-19 | 2019-12-19 | All South Unitary Authorities | 0 | 0 | 0 | 413617.36 | 6053747.6607 | 1030953.45 | 0 | 7498318.4707 | 0 | 7498318.4707 | 0 | [6 empty] | CM_WSNI | 100%
502153 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2016-04-06 | 2016-04-06 | 2016-04-25 | 2018-09-27 | 2018-09-27 | All South Unitary Authorities | 0 | 0 | 70949.7 | 381751.72 | 109276.173 | 0 | 0 | 561977.593 | 0 | 561977.593 | 0 | [6 empty] | CM_WSI | 100%
502154 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-29 | 2016-03-29 | 2016-06-08 | 2017-09-08 | 2017-09-08 | All South Unitary Authorities | 0 | 0 | 127167.83 | 56685.77 | 0 | 0 | 0 | 183853.6 | 0 | 183853.6 | 0 | [6 empty] | CM_WSI | 100%
502155 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS6 | 2016-03-29 | 2016-03-29 | 2016-04-08 | 2017-11-21 | 2017-11-21 | All South Unitary Authorities | 0 | 0 | 17595.14 | 79419.08 | -8664.795 | 0 | 0 | 88349.425 | 0 | 88349.425 | 0 | [6 empty] | CM_WSI | 100%
502156 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-03-29 | 2016-03-29 | 2016-04-08 | 2017-09-08 | 2017-09-08 | All South Unitary Authorities | 0 | 0 | 53560.59 | 53286.22 | 0 | 0 | 0 | 106846.81 | 0 | 106846.81 | 0 | [6 empty] | CM_WSI | 100%
502157 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-04-22 | 2016-04-22 | 2016-04-25 | 2019-07-29 | 2019-07-29 | All South Unitary Authorities | 0 | 0 | 99583.18 | 107261.4725 | 162301.455 | 0 | 0 | 369146.1075 | 0 | 369146.1075 | 0 | [6 empty] | CM_WSI | 100%
502158 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2016-04-11 | 2016-04-11 | 2016-05-09 | 2018-02-01 | 2018-02-01 | All South Unitary Authorities | 0 | 0 | 1077856.28 | 330233.695 | 0 | 0 | 0 | 1408089.975 | 0 | 1408089.975 | 0 | [6 empty] | CM_WSI | 100%
503535 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2019-03-29 | 2019-03-29 | 2019-04-01 | 2020-03-31 | 2020-04-27 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 826629.95 | 79222.03 | 905851.98 | 0 | 905851.98 | 0 | [6 empty] | CM_WSI | 30% | CM_WSNI | 70%
503536 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2019-04-01 | 2019-04-29 | 2019-08-29 | 2020-09-16 | 2020-09-22 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 716446.32 | 370575.68 | 1087022 | 0 | 1087022 | 0 | [6 empty] | CM_WSI | 50% | CM_WSNI | 50%
503534 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MSU | 2019-04-01 | 2019-04-29 | 2019-08-29 | 2020-09-16 | 2020-09-22 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 4086977.9 | 2113954.09 | 6200931.99 | 0 | 6200931.99 | 0 | [6 empty] | CM_WSNI | 40% | CM_WSI | 60%
502048 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-03-02 | 2016-03-02 | 2016-05-19 | 2019-06-07 | 2019-06-10 | All West Unitary Authorities | 0 | 183439.25 | 281320.18 | 507766.29 | 16550.5275 | 161715.65 | 0 | 1150791.8975 | 0 | 1150791.8975 | 0 | [6 empty] | CM_WSI | 100%
502047 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS5 | 2016-03-01 | 2016-03-01 | 2016-05-13 | 2019-02-20 | 2019-02-20 | All West Unitary Authorities | 0 | 78635.51 | 60045.48 | 32529.88 | -74136.95 | 0 | 0 | 97073.92 | 0 | 97073.92 | 0 | [6 empty] | CM_WSI | 100%
503029 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-02-23 | 2018-02-23 | 2018-04-02 | 2019-11-29 | 2019-12-02 | All West Unitary Authorities | 0 | 0 | 0 | 213640.19 | 1051143.9 | 1077846.43 | 0 | 2342630.52 | 0 | 2342630.52 | 0 | [6 empty] | CM_WSNI | 100%
503030 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-02-23 | 2018-02-23 | 2018-04-02 | 2019-09-16 | 2019-09-17 | All West Unitary Authorities | 0 | 0 | 0 | 249845.79 | 1106561.6791 | 647187.88 | 0 | 2003595.3491 | 0 | 2003595.3491 | 0 | [6 empty] | CM_WSNI | 100%
503020 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2018-02-26 | 2018-02-26 | 2018-03-01 | 2019-09-26 | 2019-09-26 | All West Unitary Authorities | 0 | 0 | 0 | 219485.98 | 6637546.2547 | 0 | 0 | 6857032.2347 | 0 | 6857032.2347 | 0 | [6 empty] | CM_WSNI | 100%
502160 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-03-30 | 2016-03-30 | 2016-04-22 | 2019-06-21 | 2019-06-24 | All West Unitary Authorities | 0 | 0 | 138020.41 | 186358.95 | -15285.3275 | 60500 | 0 | 369594.0325 | 0 | 369594.0325 | 0 | [6 empty] | CM_WSI | 100%
502161 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2016-03-30 | 2016-03-30 | 2016-05-23 | 2019-07-19 | 2019-10-21 | All West Unitary Authorities | 0 | 0 | 105365.81 | 41659.55 | 0.004 | 0 | 0 | 147025.364 | 0 | 147025.364 | 0 | [6 empty] | CM_WSI | 100%
502162 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 2019-08-30 | 2019-09-02 | All West Unitary Authorities | 0 | 0 | 237004.65 | 146493.16 | 49794.97 | 123400 | 0 | 556692.78 | 0 | 556692.78 | 0 | [6 empty] | CM_WSI | 100%
502163 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2016-04-06 | 2016-04-06 | 2016-06-13 | 2019-06-20 | 2019-07-16 | All West Unitary Authorities | 0 | 0 | 165119.01 | 57968 | 40937.33 | 0 | 0 | 264024.34 | 0 | 264024.34 | 0 | [6 empty] | CM_WSI | 100%
502164 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2016-04-11 | 2016-04-11 | 2016-04-11 | 2019-08-23 | 2019-08-26 | All West Unitary Authorities | 0 | 0 | 319960.53 | 491106 | 20074.578 | 284046.85 | 0 | 1115187.958 | 0 | 1115187.958 | 0 | [6 empty] | CM_WSI | 100%
502165 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2016-04-06 | 2016-04-06 | 2016-06-13 | 2019-06-20 | 2019-07-16 | All West Unitary Authorities | 0 | 0 | 624710.98 | 130681.074 | 51154.946 | 0 | 0 | 806547 | 0 | 806547 | 0 | [6 empty] | CM_WSI | 100%
402878 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-08-31 | 2013-02-11 | 2013-03-04 | 2013-07-23 |  | Aberdeenshire | 142224.8 | 7729.6 | 0 | 0 | 0 | 0 | 0 | 7729.6 | 0 | 149954.4 | 0 | [6 empty] | CM_WSNI | 100%
402291 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-08-29 | 2014-11-03 | 2014-11-03 | 2015-10-30 |  | Scottish Water Wide | 75444.39 | 12743.6 | 0 | 0 | 0 | 0 | 0 | 12743.6 | 0 | 88187.99 | 0 | [6 empty] | CM_WSI | 100%
401355 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-27 | 2011-11-18 | 2011-12-05 | 2015-10-02 | 2012-06-20 | Fife | 32773 | -2504.75 | 0 | 0 | 0 | 0 | 0 | -2504.75 | 0 | 30268.25 | 0 | [6 empty] | CM_WSI | 100%
400851 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-05-10 | 2011-10-03 | 2012-01-13 | 2015-08-20 |  | Aberdeenshire | 48958 | 0 | 0.28 | -206.91 | 0 | 0 | 0 | -206.63 | 0 | 48751.37 | 0 | [6 empty] | CM_WSI | 100%
402458 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-12-01 | 2012-01-16 | 2012-01-16 | 2017-06-12 |  | Scottish Water Wide | 141733 | 0 | 0 | -136295.02 | 0 | 0 | 0 | -136295.02 | 0 | 5437.98 | 0 | [6 empty] | CM_WSI | 100%
500554 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-06-30 | 2015-06-30 | 2015-07-24 | 2018-02-12 | 2018-02-12 | All East Unitary Authorities | 0 | 840292 | 515764.24 | 391710.3805 | 0 | 0 | 0 | 1747766.6205 | 0 | 1747766.6205 | 0 | [6 empty] | CM_WSI | 100%
500522 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2019-07-05 | 2019-07-05 | All East Unitary Authorities | 0 | 562180 | -93179 | 180067 | -211699.91 | 57031.91 | 0 | 494400 | 0 | 494400 | 0 | [6 empty] | CM_WSI | 100%
402677 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-06-07 | 2013-01-18 | 2013-04-23 | 2016-08-08 |  | North Lanarkshire | 70817 | 336926.18 | 47013.59 | 118.59 | 554.49 | 0 | 0 | 384612.85 | 0 | 455429.85 | 0 | [6 empty] | CM_WWNI | 100%
403258 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-01-14 | 2013-04-18 | 2013-09-10 | 2015-02-10 |  | Moray | 251584.98 | -584.98 | 0 | -776.74 | 0 | 0 | 0 | -1361.72 | 0 | 250223.26 | 0 | [6 empty] | CM_WWNI | 100%
402693 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-06-13 | 2012-09-14 | 2012-11-28 | 2014-01-13 |  | North Lanarkshire | 109228 | -155.99 | 0 | 0 | 0 | 0 | 0 | -155.99 | 0 | 109072.01 | 0 | [6 empty] | CM_WWI | 100%
401867 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-12-22 | 2016-06-29 | 2016-07-01 | 2018-02-16 | 2018-02-16 | Scottish Borders | 40851 | 23526 | 16363.87 | -113.38 | 0 | 0 | 0 | 39776.49 | 0 | 80627.49 | 0 | [6 empty] | CM_WSI | 100%
401359 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-10 | 2012-10-29 | 2013-02-11 | 2013-08-02 | 2013-08-02 | Fife | 211365 | -183.73 | 0 | 0 | 0 | 0 | 0 | -183.73 | 0 | 211181.27 | 0 | [6 empty] | CM_WSI | 100%
401422 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-09-23 | 2011-06-21 | 2011-05-24 | 2011-07-30 |  | Argyll and Bute-Cowal & Bute | 25106.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25106.47 | 0 | [6 empty] | CM_WSNI | 100%
403560 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-08-26 | 2014-01-24 | 2014-02-20 | 2014-09-17 |  | Dumfries and Galloway | 182048 | 0 | -268.82 | 0 | 0 | 0 | 0 | -268.82 | 0 | 181779.18 | 0 | [6 empty] | CM_WSNI | 100%
402189 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-08-15 | 2017-11-28 | 2017-11-28 | 2017-09-29 |  | Aberdeenshire | 3000 | 0 | 2962.5 | 3968.51 | 0 | -5552.45 | 0 | 1378.56 | 0 | 4378.56 | 0 | [6 empty] | CM_WSI | 100%
400875 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-05-20 | 2012-01-12 | 2012-01-30 | 2012-07-16 |  | Orkney Islands | 65294 | 4255.47 | 0 | 0 | 0 | 0 | 0 | 4255.47 | 0 | 69549.47 | 0 | [6 empty] | CM_WSNI | 100%
402249 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-08-18 | 2011-12-21 | 2012-01-30 | 2013-12-18 |  | Falkirk | 195235 | -176.88 | 0 | 0 | 0 | 0 | 0 | -176.88 | 0 | 195058.12 | 0 | [6 empty] | CM_WSI | 100%
403194 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-01-18 | 2013-09-26 | 2013-12-05 | 2014-07-07 |  | West Lothian | 160073 | 904 | -475.73 | 0 | 0 | 0 | 0 | 428.27 | 0 | 160501.27 | 0 | [6 empty] | CM_WWI | 100%
403783 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-05-07 | 2014-05-07 | 2014-11-17 | 2015-10-30 |  | Scottish Water Wide | 597788 | -53131.97 | 0 | 0 | 0 | 0 | 0 | -53131.97 | 0 | 544656.03 | 0 | [6 empty] | CM_M&G | 100%
402977 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-19 | 2013-04-24 | 2013-12-13 | 2016-04-29 |  | Dumfries and Galloway | 180690 | 3000 | 108895.97 | 0 | -2394.77 | 0 | 0 | 109501.2 | 0 | 290191.2 | 0 | [6 empty] | CM_WWI | 100%
400976 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-15 | 2011-06-28 | 2011-10-24 | 2012-12-18 | 2012-12-18 | Fife | 32244 | 261.71 | 0 | 0 | 0 | 0 | 0 | 261.71 | 0 | 32505.71 | 0 | [6 empty] | CM_WSI | 100%
403049 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-05-17 | 2014-02-04 | 2014-02-17 | 2014-08-22 |  | Glasgow City | 257873 | 401 | -798.67 | 0 | 0 | 0 | 0 | -397.67 | 0 | 257475.33 | 0 | [6 empty] | CM_WWI | 100%
500637 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-05-26 | 2015-06-17 | 2015-09-11 | 2015-10-02 | 2016-01-25 | Na H-Eileanan an Iar | 0 | 195031.16 | 0 | 0 | 0 | 0 | 0 | 195031.16 | 0 | 195031.16 | 0 | [6 empty] | CM_WWNI | 100%
400897 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-05-25 | 2012-10-31 | 2012-11-19 | 2015-06-25 |  | South Lanarkshire | 151320 | 37704.53 | 0 | 0 | 0 | 0 | 0 | 37704.53 | 0 | 189024.53 | 0 | [6 empty] | CM_WSNI | 100%
403892 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2014-06-30 | 2014-10-23 | 2014-12-19 | 2015-05-04 |  | Fife | 222925 | -1330 | -0.3 | -237.35 | 0 | 0 | 0 | -1567.65 | 0 | 221357.35 | 0 | [6 empty] | CM_WWI | 100%
401966 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-04-01 | 2011-10-25 | 2011-11-21 | 2012-10-22 | 2012-10-22 | Fife | 26953 | -368.26 | 0 | 0 | 0 | 0 | 0 | -368.26 | 0 | 26584.74 | 0 | [6 empty] | CM_WSI | 100%
403492 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-05-15 | 2013-08-12 | 2013-08-26 | 2014-03-25 |  | West Lothian | 272203 | 619 | -1246.19 | 0 | 0 | 0 | 0 | -627.19 | 0 | 271575.81 | 0 | [6 empty] | CM_WWI | 100%
403632 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-01-24 | 2016-10-13 | 2016-10-13 | 2016-09-23 |  | Scottish Water Wide | 127094.78 | 1.22 | 0 | 0 | 0 | 0 | 0 | 1.22 | 0 | 127096 | 0 | [6 empty] | CM_WSI | 100%
403719 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-04-24 | 2014-05-12 | 2014-05-12 | 2015-10-26 |  | Scottish Water Wide | 100000 | -4099.41 | 0 | 0 | 0 | 0 | 0 | -4099.41 | 0 | 95900.59 | 0 | [6 empty] | CM_WSI | 100%
403720 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-04-24 | 2014-05-12 | 2014-05-12 | 2015-10-26 |  | Scottish Water Wide | 143000 | -40405.45 | 0 | 0 | 0 | 0 | 0 | -40405.45 | 0 | 102594.55 | 0 | [6 empty] | CM_WSI | 100%
403083 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2012-11-12 | 2012-11-12 | 2012-12-10 | 2019-07-24 |  | All East Unitary Authorities | 177164.84 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0.16 | 0 | 177165 | 0 | [6 empty] | CM_WSNI | 100%
401214 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-07-15 | 2013-07-28 | 2013-11-28 | 2016-05-20 |  | Aberdeenshire | 42093 | 142263 | 6182 | 831.14 | -221.875 | 0 | 0 | 149054.265 | 0 | 191147.265 | 0 | [6 empty] | CM_WSI | 100%
403056 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-02-04 | 2016-06-13 | 2016-06-13 | 2016-06-13 |  | North Ayrshire | 30390 | 9056 | -511.3 | 0 | 0 | 0 | 0 | 8544.7 | 0 | 38934.7 | 0 | [6 empty] | CM_WWI | 100%
402570 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-02-21 | 2012-02-21 | 2012-04-23 | 2015-04-24 |  | All East Unitary Authorities | 175520 | -3520 | 0 | -1916.37 | 0 | 0 | 0 | -5436.37 | 0 | 170083.63 | 0 | [6 empty] | CM_WWI | 100%
402569 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-02-21 | 2012-02-21 | 2012-04-09 | 2015-07-14 |  | All East Unitary Authorities | 261995 | 5 | 0 | -2460.31 | 0 | 0 | 0 | -2455.31 | 0 | 259539.69 | 0 | [6 empty] | CM_WWI | 100%
402562 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-02-22 | 2012-02-22 | 2012-04-23 | 2015-07-14 |  | All East Unitary Authorities | 345333 | 7483.79 | 7183.46 | -6875.05 | 0 | 0 | 0 | 7792.2 | 0 | 353125.2 | 0 | [6 empty] | CM_WSI | 100%
402543 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2012-02-24 | 2012-02-24 | 2012-04-23 | 2016-05-30 |  | All East Unitary Authorities | 1214989 | -5250.47 | 0 | 0 | 0 | 0 | 0 | -5250.47 | 0 | 1209738.53 | 0 | [6 empty] | CM_WSNI | 100%
402561 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-02-24 | 2012-02-24 | 2012-04-23 | 2016-09-26 | 2015-08-26 | All East Unitary Authorities | 472428 | 47865.24 | 18536.06 | 1401.7 | 0 | 0 | 0 | 67803 | 0 | 540231 | 0 | [6 empty] | CM_WSNI | 100%
403508 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-04-29 | 2015-06-22 | 2015-06-22 | 2015-06-18 |  | Scottish Water Wide | 65000 | -5797 | 0 | 0 | 0 | 0 | 0 | -5797 | 0 | 59203 | 0 | [6 empty] | CM_M&G | 100%
403509 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-04-29 | 2015-06-08 | 2015-06-08 | 2015-06-08 |  | Highland | 5000 | -3837.5 | 0 | 0 | 0 | 0 | 0 | -3837.5 | 0 | 1162.5 | 0 | [6 empty] | CM_M&G | 100%
403173 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-11-21 | 2017-08-22 | 2017-10-24 | 2018-01-18 |  | Highland | 24971 | 60 | 12908.06 | 46880.38 | 280 | 0 | 0 | 60128.44 | 0 | 85099.44 | 0 | [6 empty] | CM_WWNI | 100%
402954 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-10-19 | 2018-03-23 | 2018-03-23 | 2018-03-23 |  | Dumfries and Galloway | 44238 | 0 | 1732.15 | 5480.06 | 0 | 0 | 0 | 7212.21 | 0 | 51450.21 | 0 | [6 empty] | CM_WWI | 100%
402639 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2012-03-29 | 2012-03-29 | 2012-10-10 | 2019-05-15 |  | Glasgow City | 35000 | 0 | -3132.34 | -641.2435 | 0.0035 | 0 | 0 | -3773.58 | 0 | 31226.42 | 0 | [6 empty] | CM_WWNI | 100%
401358 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-09-10 | 2012-11-30 | 2013-01-09 | 2014-04-17 | 2014-04-07 | Perth and Kinross | 99055 | -1558 | 174.82 | 0 | 0 | 0 | 0 | -1383.18 | 0 | 97671.82 | 0 | [6 empty] | CM_WSI | 100%
402504 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-02-02 | 2013-12-17 | 2014-02-24 | 2014-08-15 | 2014-05-01 | Perth and Kinross | 28574 | -4127.67 | 0 | 0 | 0 | 0 | 0 | -4127.67 | 0 | 24446.33 | 0 | [6 empty] | CM_WSI | 100%
401360 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-10 | 2012-02-17 | 2012-08-27 | 2013-07-11 | 2013-07-11 | Angus | 65091.92 | 3392.39 | 0 | 0 | 0 | 0 | 0 | 3392.39 | 0 | 68484.31 | 0 | [6 empty] | CM_WSI | 100%
401363 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-10 | 2013-05-28 | 2013-08-08 | 2014-10-10 | 2014-12-10 | Perth and Kinross | 155192 | -913 | -259.51 | 0 | 0 | 0 | 0 | -1172.51 | 0 | 154019.49 | 0 | [6 empty] | CM_WSI | 100%
402699 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-07-23 | 2014-05-16 | 2014-07-01 | 2014-12-17 |  | Shetland Islands | 28303 | -20043.02 | 0 | 0 | 0 | 0 | 0 | -20043.02 | 0 | 8259.98 | 0 | [6 empty] | CM_WSI | 100%
401986 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-06-23 | 2012-02-23 | 2012-04-23 | 2015-01-12 |  | Falkirk | 65817 | -10228.77 | 0 | 0 | 0 | 0 | 0 | -10228.77 | 0 | 55588.23 | 0 | [6 empty] | CM_WSI | 100%
403740 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2014-02-26 | 2014-03-11 | 2014-03-11 | 2015-01-13 |  | Highland | 82655.27 | 71.69 | 0 | 0 | 0 | 0 | 0 | 71.69 | 0 | 82726.96 | 0 | [6 empty] | CM_WWNI | 100%
402163 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2011-08-01 | 2012-07-31 | 2012-11-12 | 2015-03-25 |  | Orkney Islands | 143701 | -7018.14 | 0 | 0 | 0 | 0 | 0 | -7018.14 | 0 | 136682.86 | 0 | [6 empty] | CM_M&G | 100%
403073 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-11-07 | 2012-11-07 | 2013-01-04 | 2017-03-17 |  | Scottish Water Wide | 532500 | 17500 | -100492.18 | -2451.02 | 0 | 0 | 0 | -85443.2 | 0 | 447056.8 | 0 | [6 empty] | CM_WSI | 100%
403072 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2012-11-07 | 2012-11-07 | 2013-01-04 | 2016-12-07 |  | Scottish Water Wide | 581099 | 618901 | -144867.18 | -3263 | 0 | 0 | 0 | 470770.82 | 0 | 1051869.82 | 0 | [6 empty] | CM_WSNI | 100%
403366 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-04-30 | 2016-02-01 |  | All East Unitary Authorities | 23510 | 51146.37 | 2398.26 | -1518.57 | 0 | 0 | 0 | 52026.06 | 0 | 75536.06 | 0 | [6 empty] | CM_WWI | 100%
403364 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-01 | 2016-06-17 |  | All East Unitary Authorities | 250000 | -10000 | -41888.96 | 0 | 0 | 0 | 0 | -51888.96 | 0 | 198111.04 | 0 | [6 empty] | CM_WWI | 100%
403365 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-01 | 2016-08-01 |  | All East Unitary Authorities | 6000000 | -436606 | -153872.78 | -3441 | 0 | 0 | 0 | -593919.78 | 0 | 5406080.22 | 0 | [6 empty] | CM_WWI | 100%
403367 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-04-30 | 2016-01-05 |  | All East Unitary Authorities | 151539 | 92090 | -17848 | -973.95 | 0 | 0 | 0 | 73268.05 | 0 | 224807.05 | 0 | [6 empty] | CM_WWNI | 100%
403384 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2013-02-25 | 2013-02-25 | 2013-03-01 | 2016-06-29 |  | All East Unitary Authorities | 1047033 | 194319 | -103308.95 | 0 | 0 | 0 | 0 | 91010.05 | 0 | 1138043.05 | 0 | [6 empty] | CM_WSI | 100%
403386 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-08 | 2016-12-20 |  | All East Unitary Authorities | 628606 | 270671 | -142822.88 | -10514.7015 | 0 | 0 | 0 | 117333.4185 | 0 | 745939.4185 | 0 | [6 empty] | CM_WSI | 100%
403385 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2013-02-25 | 2013-02-25 | 2013-03-01 | 2018-08-14 |  | All East Unitary Authorities | 2899130 | 231703.85 | 17163 | -5626.81 | 0 | 0 | 0 | 243240.04 | 0 | 3142370.04 | 0 | [6 empty] | CM_WSNI | 100%
403387 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-04-30 | 2017-01-23 |  | All East Unitary Authorities | 1169471 | 217035 | -38245.73 | 354.86 | 140.295 | 0 | 0 | 179284.425 | 0 | 1348755.425 | 0 | [6 empty] | CM_WSNI | 100%
403370 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-04-12 | 2015-01-06 |  | All North Unitary Authorities | 1436032.84 | -1151.65 | 0 | 0 | 0 | 0 | 0 | -1151.65 | 0 | 1434881.19 | 0 | [6 empty] | CM_WWI | 100%
403388 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2013-02-15 | 2013-02-15 | 2013-03-29 | 2015-08-19 |  | All North Unitary Authorities | 530000 | 121604.76 | 0 | 0 | 0 | 0 | 0 | 121604.76 | 0 | 651604.76 | 0 | [6 empty] | CM_WSI | 100%
403390 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-04-08 | 2015-12-15 |  | All North Unitary Authorities | 1054647 | 162833.39 | 1638.05 | -5140.5 | 0 | 0 | 0 | 159330.94 | 0 | 1213977.94 | 0 | [6 empty] | CM_WSI | 100%
403391 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-08 | 2015-12-15 |  | All North Unitary Authorities | 1239176 | 365485.68 | 0 | 0 | 0 | 0 | 0 | 365485.68 | 0 | 1604661.68 | 0 | [6 empty] | CM_WSNI | 100%
403372 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-01 | 2015-09-01 |  | All South Unitary Authorities | 300000 | 126662.21 | 0 | 0 | 0 | 0 | 0 | 126662.21 | 0 | 426662.21 | 0 | [6 empty] | CM_WWI | 100%
403374 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-01 | 2017-03-01 |  | All South Unitary Authorities | 238883 | 214057 | -85874.38 | 13231.27 | 0 | 0 | 0 | 141413.89 | 0 | 380296.89 | 0 | [6 empty] | CM_WWI | 100%
403373 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-04-01 | 2016-05-30 |  | All South Unitary Authorities | 4571700 | 481915.02 | 60 | 0 | 0 | 0 | 0 | 481975.02 | 0 | 5053675.02 | 0 | [6 empty] | CM_WWI | 100%
403392 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2013-02-15 | 2013-02-15 | 2013-03-29 | 2015-09-10 |  | All South Unitary Authorities | 1408805.24 | -36530.38 | 0 | 0 | 0 | 0 | 0 | -36530.38 | 0 | 1372274.86 | 0 | [6 empty] | CM_WSI | 100%
403394 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-04-08 | 2015-11-27 |  | All South Unitary Authorities | 44268 | 532 | -1228.4 | 17.68 | 0 | 0 | 0 | -678.72 | 0 | 43589.28 | 0 | [6 empty] | CM_WSI | 100%
403393 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2013-02-21 | 2013-02-21 | 2013-03-29 | 2015-10-08 |  | All South Unitary Authorities | 2800000 | -73845.04 | 0 | 0 | 0 | 0 | 0 | -73845.04 | 0 | 2726154.96 | 0 | [6 empty] | CM_WSNI | 100%
403377 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-02-20 | 2013-02-20 | 2013-03-01 | 2016-06-30 |  | All West Unitary Authorities | 1088995.75 | 257342.25 | 871.4 | 0 | 0 | 0 | 0 | 258213.65 | 0 | 1347209.4 | 0 | [6 empty] | CM_WWI | 100%
403396 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-29 | 2016-05-30 |  | All West Unitary Authorities | 275000 | 49000 | -74700.09 | 0 | 0 | 0 | 0 | -25700.09 | 0 | 249299.91 | 0 | [6 empty] | CM_WSI | 100%
403398 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2013-03-05 | 2013-03-05 | 2013-04-08 | 2020-05-04 |  | All West Unitary Authorities | 890559 | 72519 | 0.09 | -28901.37 | 0 | 0 | 0 | 43617.72 | 0 | 934176.72 | 0 | [6 empty] | CM_WSI | 100%
403397 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2013-03-05 | 2013-03-05 | 2013-05-01 | 2016-05-31 |  | All West Unitary Authorities | 1320165.79 | 489483.22 | 110.85 | 0 | 0 | 0 | 0 | 489594.07 | 0 | 1809759.86 | 0 | [6 empty] | CM_WSNI | 100%
403399 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2013-03-05 | 2013-03-05 | 2013-04-15 | 2019-05-27 |  | All West Unitary Authorities | 1096526 | 655561 | -183354.22 | 51430 | 500 | 0 | 0 | 524136.78 | 0 | 1620662.78 | 0 | [6 empty] | CM_WSNI | 100%
403160 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-11-20 | 2015-01-29 | 2015-08-24 | 2017-06-21 |  | Highland | 151032 | 1041321 | 102666.21 | 14074.1 | 3753.995 | 0 | 0 | 1161815.305 | 0 | 1312847.305 | 0 | [6 empty] | CM_WSNI | 100%
403188 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-01-14 | 2013-10-31 | 2014-02-17 | 2014-06-17 |  | Midlothian | 159355 | 1072 | -1826.11 | 0 | 0 | 0 | 0 | -754.11 | 0 | 158600.89 | 0 | [6 empty] | CM_WSI | 100%
402169 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-09-26 | 2012-09-28 | 2012-11-26 | 2013-11-19 | 2013-11-28 | Angus | 127509 | -1774.82 | 0 | 0 | 0 | 0 | 0 | -1774.82 | 0 | 125734.18 | 0 | [6 empty] | CM_WSI | 100%
403178 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-01-10 | 2013-07-01 | 2013-07-01 | 2014-07-07 |  | City of Edinburgh | 529369 | 665 | -2226.34 | 0 | 0 | 0 | 0 | -1561.34 | 0 | 527807.66 | 0 | [6 empty] | CM_WWI | 100%
403530 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-07-26 | 2016-07-20 | 2017-10-19 | 2018-02-05 |  | Highland | 7185.63 | 7174.37 | 7979.31 | 7215.463 | 175.44 | 0 | 0 | 22544.583 | 0 | 29730.213 | 0 | [6 empty] | CM_WWI | 100%
402765 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-07-05 | 2013-10-16 | 2013-11-29 | 2017-05-04 |  | Highland | 91999 | 0 | 23001 | -82340.3 | 0 | 0 | 0 | -59339.3 | 0 | 32659.7 | 0 | [6 empty] | CM_WSI | 100%
403123 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-11-06 | 2015-08-27 | 2015-09-18 | 2016-05-17 | 2016-05-17 | South Lanarkshire | 107413.31 | 78968.69 | -0.42 | -254.11 | 0 | 0 | 0 | 78714.16 | 0 | 186127.47 | 0 | [6 empty] | CM_WSI | 100%
402941 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-02-06 | 2013-02-06 | 2013-02-07 | 2013-12-23 |  | Renfrewshire | 33930.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33930.21 | 0 |  |  |  |  | 11007 |  | CM_M&G | 100%
402636 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2012-04-23 | 2018-03-27 | 2018-04-25 | 2019-05-28 | 2019-07-29 | South Ayrshire | 98320.44 | 15179.56 | 96660 | 175889.77 | 655226.23 | 658.08 | 2238.87 | 945852.51 | 0.03 | 1044172.98 | 0 |  |  |  |  | 5220 |  | CM_WWNI | 100%
401474 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-11-25 | 2011-12-09 | 2011-12-12 | 2015-07-23 |  | Shetland Islands | 148835 | -3828 | -3178.34 | -288.15 | 0 | 0 | 0 | -7294.49 | 0 | 141540.51 | 0 | [6 empty] | CM_WSNI | 100%
402344 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-09-07 | 2014-10-20 | 2014-10-20 | 2014-10-20 |  | Angus | 25393.08 | 0 | 161.4 | 40.43 | 0 | 0 | 0 | 201.83 | 0 | 25594.91 | 0 | [6 empty] | CM_WSI | 100%
401356 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-27 | 2011-08-19 | 2011-11-29 | 2015-10-02 | 2012-09-21 | Fife | 34940.52 | -97.06 | 0 | 0 | 0 | 0 | 0 | -97.06 | 0 | 34843.46 | 0 | [6 empty] | CM_WSI | 100%
400971 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-15 | 2011-06-28 | 2011-09-26 | 2013-07-15 | 2013-07-15 | Aberdeenshire | 40653 | -493.88 | 0 | 0 | 0 | 0 | 0 | -493.88 | 0 | 40159.12 | 0 | [6 empty] | CM_WSI | 100%
403551 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-09-11 | 2014-07-09 | 2014-08-19 | 2015-02-27 | 2015-02-27 | Scottish Water Wide | 103149 | 0 | -637.99 | 0 | 0 | 0 | 0 | -637.99 | 0 | 102511.01 | 0 | [6 empty] | CM_WSI | 100%
403599 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-10-23 | 2013-11-22 | 2014-02-25 | 2015-08-07 |  | Argyll and Bute-North Argyll | 25372 | 174802.58 | 757.38 | 0 | 0 | 0 | 0 | 175559.96 | 0 | 200931.96 | 0 | [6 empty] | CM_WWI | 100%
403608 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-10-22 | 2013-11-22 | 2013-11-28 | 2015-02-02 |  | Na H-Eileanan an Iar | 83920.69 | 13517.31 | 0 | 0 | 0 | 0 | 0 | 13517.31 | 0 | 97438 | 0 | [6 empty] | CM_WWI | 100%
402465 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-11-23 | 2013-07-18 | 2013-08-12 | 2015-03-24 | 2015-03-24 | Dumfries and Galloway | 161203 | 51172.04 | 0 | 0 | 0 | 0 | 0 | 51172.04 | 0 | 212375.04 | 0 | [6 empty] | CM_WSI | 100%
402729 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-06-07 | 2013-10-21 | 2014-03-28 | 2015-01-14 |  | Renfrewshire | 288005 | 8891.39 | 0 | 0 | 0 | 0 | 0 | 8891.39 | 0 | 296896.39 | 0 | [6 empty] | CM_WWI | 100%
401310 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-27 | 2011-07-15 | 2012-01-13 | 2015-10-02 | 2013-03-15 | Perth and Kinross | 190986 | -466.83 | 0 | 0 | 0 | 0 | 0 | -466.83 | 0 | 190519.17 | 0 | [6 empty] | CM_WSI | 100%
402953 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-10-29 | 2016-12-11 | 2016-12-13 | 2016-12-13 |  | Fife | 2337.89 | 18604.11 | 36613.29 | 0 | 0 | 0 | 0 | 55217.4 | 0 | 57555.29 | 0 | [6 empty] | CM_WWI | 100%
402696 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-06-19 | 2012-11-30 | 2012-12-10 | 2013-09-01 |  | Fife | 86331.34 | 366.03 | 0 | 0 | 0 | 0 | 0 | 366.03 | 0 | 86697.37 | 0 | [6 empty] | CM_WSI | 100%
046668 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-30 | 2012-11-14 | 2012-12-03 | 2013-04-12 |  | Aberdeenshire | 110871 | -437.57 | 0 | 0 | 0 | 0 | 0 | -437.57 | 0 | 110433.43 | 0 | [6 empty] | CM_WSI | 100%
046665 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-06 | 2009-03-06 | 2012-09-26 | 2014-07-17 |  | Angus | 61984 | 73 | -272 | 0 | 0 | 0 | 0 | -199 | 0 | 61785 | 0 | [6 empty] | CM_WSI | 100%
046666 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2009-03-06 | 2009-03-06 | 2012-10-08 | 2013-05-13 |  | Angus | 156842 | -797.97 | 0 | 0 | 0 | 0 | 0 | -797.97 | 0 | 156044.03 | 0 | [6 empty] | CM_WSI | 100%
402587 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-03-23 | 2012-09-25 | 2012-11-12 | 2013-03-05 |  | East Dunbartonshire | 233172.08 | -31.72 | 0 | 0 | 0 | 0 | 0 | -31.72 | 0 | 233140.36 | 0 | [6 empty] | CM_WSI | 100%
403282 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-02-18 | 2015-10-05 | 2015-10-05 | 2015-10-05 |  | East Renfrewshire | 35958 | -1908.81 | 0 | 0 | 0 | 0 | 0 | -1908.81 | 0 | 34049.19 | 0 | [6 empty] | CM_WSI | 100%
402009 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-03-21 | 2013-11-18 | 2013-12-02 | 2014-07-07 |  | Highland | 113585.03 | -257.76 | 0 | 0 | 0 | 0 | 0 | -257.76 | 0 | 113327.27 | 0 | [6 empty] | CM_WSI | 100%
403443 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-05-16 | 2013-05-16 | 2014-04-04 | 2016-01-13 |  | All North Unitary Authorities | 1830750 | 224248.71 | 0 | 0 | 0 | 0 | 0 | 224248.71 | 0 | 2054998.71 | 0 |  |  |  |  | 105104 |  | CM_WWI | 100%
403441 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2013-05-22 | 2013-05-22 | 2013-05-22 | 2016-01-13 |  | All North Unitary Authorities | 527800 | 41660.88 | 0 | 0 | 0 | 0 | 0 | 41660.88 | 0 | 569460.88 | 0 | [6 empty] | CM_WWI | 100%
403442 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-05-13 | 2013-05-13 | 2013-05-13 | 2016-01-13 |  | All North Unitary Authorities | 1052185 | 176625.31 | 0 | 0 | 0 | 0 | 0 | 176625.31 | 0 | 1228810.31 | 0 | [6 empty] | CM_WWNI | 100%
401299 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-08-19 | 2012-08-03 | 2013-05-20 | 2015-03-02 |  | Orkney Islands | 52102 | -2815.54 | 0 | 0 | 0 | 0 | 0 | -2815.54 | 0 | 49286.46 | 0 |  |  |  |  | 50000 |  | CM_WSNI | 100%
402584 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-03-09 | 2012-03-09 | 2012-04-23 | 2015-03-10 |  | All North Unitary Authorities | 814970 | 927.5 | 0 | 0 | 0 | 0 | 0 | 927.5 | 0 | 815897.5 | 0 | [6 empty] | CM_WSI | 100%
403308 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2013-02-25 | 2014-11-14 | 2015-01-16 | 2017-10-27 |  | All East Unitary Authorities | 83558 | 80721 | 22504 | -19283 | 0 | 0 | 0 | 83942 | 0 | 167500 | 0 | [6 empty] | CM_WSNI | 100%
500581 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-06-05 | 2015-06-05 | 2015-06-10 | 2019-07-19 | 2019-07-19 | Scottish Water Wide | 0 | 1514816 | 2059139.23 | 3051188.96 | -367633.44 | 6075 | 0 | 6263585.75 | 0 | 6263585.75 | 0 | [6 empty] | CM_WSI | 100%
500646 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS5 | 2015-05-18 | 2015-05-18 | 2015-05-18 | 2018-05-30 | 2018-05-30 | Scottish Water Wide | 0 | 359243.03 | 761822.98 | 251719.77 | 92152.18 | 0 | 0 | 1464937.96 | 0 | 1464937.96 | 0 | [6 empty] | CM_WSI | 100%
402555 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-02-24 | 2012-02-24 | 2012-04-23 | 2017-06-28 | 2017-06-28 | Scottish Water Wide | 3200167 | 216805 | 251042.99 | 34654.78 | 0 | 0 | 0 | 502502.77 | 0 | 3702669.77 | 0 | [6 empty] | CM_WSI | 100%
402541 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS5 | 2012-02-13 | 2012-02-13 | 2012-02-13 | 2018-07-19 | 2018-07-19 | Scottish Water Wide | 1065234.29 | 208099.25 | 46881.4 | 10207.67 | 0 | 0 | 0 | 265188.32 | 0 | 1330422.61 | 0 | [6 empty] | CM_WSI | 100%
400977 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-09-27 | 2011-05-30 | 2011-08-08 | 2012-08-01 | 2012-08-01 | Fife | 58732.06 | -531.94 | 0 | 0 | 0 | 0 | 0 | -531.94 | 0 | 58200.12 | 0 | [6 empty] | CM_WSI | 100%
403500 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | General |  | SWD | Strategic Capacity | MS7 | 2013-07-03 | 2013-07-03 | 2013-08-01 | 2016-01-13 | 2016-02-11 | Scottish Water Wide | 118256.02 | 3050 | 0 | 0 | 0 | 0 | 0 | 3050 | 0 | 121306.02 | 0 | [6 empty] | SG1 | 50% | WG1 | 50%
403053 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2013-03-15 | 2014-09-30 | 2014-10-06 | 2015-02-24 |  | Renfrewshire | 906306 | -38847.82 | 0 | 0 | 0 | 0 | 0 | -38847.82 | 0 | 867458.18 | 0 | [6 empty] | CM_WWI | 100%
402560 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-02-21 | 2012-02-21 | 2012-03-01 | 2015-03-10 |  | All South Unitary Authorities | 1066868.46 | 84.38 | 0 | 0 | 0 | 0 | 0 | 84.38 | 0 | 1066952.84 | 0 | [6 empty] | CM_WWI | 100%
402553 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2012-02-15 | 2012-02-15 | 2012-04-02 | 2013-12-16 |  | All South Unitary Authorities | 1189244.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1189244.93 | 0 | [6 empty] | CM_WSNI | 100%
402558 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-02-22 | 2012-02-22 | 2012-04-23 | 2015-11-04 |  | All South Unitary Authorities | 157706.3 | 1529.42 | 0 | 0 | 0 | 0 | 0 | 1529.42 | 0 | 159235.72 | 0 | [6 empty] | CM_WSNI | 100%
402435 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-10-31 | 2011-10-31 | 2011-11-07 | 2014-12-18 |  | All East Unitary Authorities | 257031 | 1500 | -1246.83 | 0 | 0 | 0 | 0 | 253.17 | 0 | 257284.17 | 0 | [6 empty] | CM_WSI | 50% | CM_WWI | 50%
402432 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-10-31 | 2011-10-31 | 2011-11-07 | 2015-04-02 |  | All East Unitary Authorities | 85089 | 4400.45 | 0 | 0 | 0 | 0 | 0 | 4400.45 | 0 | 89489.45 | 0 | [6 empty] | CM_WSNI | 100%
402400 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-11-16 | 2011-11-16 | 2011-12-07 | 2015-12-11 |  | All South Unitary Authorities | 178187 | -9957.11 | 0 | 0 | 0 | 0 | 0 | -9957.11 | 0 | 168229.89 | 0 | [6 empty] | CM_WSNI | 100%
401115 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2010-07-01 | 2010-07-01 | 2011-04-29 | 2012-10-03 |  | All West Unitary Authorities | 446434.74 | 0 | 0 | 41.59 | 0 | 0 | 0 | 41.59 | 0 | 446476.33 | 0 | [6 empty] | CM_WSI | 100%
402268 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2011-10-25 | 2012-02-23 | 2012-07-31 | 2012-11-29 |  | Aberdeen City | 125845 | -1549.47 | 0 | 0 | 0 | 0 | 0 | -1549.47 | 0 | 124295.53 | 0 | [6 empty] | CM_M&G | 100%
403153 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-01-15 | 2013-09-19 | 2014-04-04 | 2015-06-25 |  | Na H-Eileanan an Iar | 220541 | 31727.61 | 0 | 0 | 0 | 0 | 0 | 31727.61 | 0 | 252268.61 | 0 | [6 empty] | CM_WSI | 100%
402106 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-05-18 | 2013-01-26 | 2013-02-25 | 2014-11-24 |  | Orkney Islands | 63535 | -508.25 | 0 | 0 | 0 | 0 | 0 | -508.25 | 0 | 63026.75 | 0 | [6 empty] | CM_WSI | 100%
403184 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS3 | 2013-02-04 | 2015-03-06 | 2018-12-03 | 2019-06-27 |  | North Lanarkshire | 140973.67 | 355844.33 | -7999.52 | 1243.899 | 1551.708 | 1182197.98 | 162335.79 | 1695174.187 | 148398.73 | 1984546.587 | 0 | [6 empty] | CM_WWI | 100%
401223 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-07-15 | 2012-03-19 | 2012-05-04 | 2014-05-21 |  | Perth and Kinross | 468915 | -743.96 | -187.77 | 0 | 0 | 0 | 0 | -931.73 | 0 | 467983.27 | 0 | [6 empty] | CM_WSI | 100%
401221 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-07-15 | 2012-07-30 | 2012-08-29 | 2014-04-23 |  | Dundee City | 97438 | 8079.82 | 99.5 | 0 | 0 | 0 | 0 | 8179.32 | 0 | 105617.32 | 0 | [6 empty] | CM_WSI | 100%
403137 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS7 | 2013-03-06 | 2013-11-13 | 2013-12-02 | 2016-08-30 |  | Scottish Water Wide | 142804 | 66060.46 | 19480.21 | 5308.65 | 0 | 0 | 0 | 90849.32 | 0 | 233653.32 | 0 | [6 empty] | CM_WSNI | 50% | CM_WWNI | 50%
403138 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2013-01-17 | 2013-07-24 | 2013-09-09 | 2015-07-31 |  | Scottish Water Wide | 247968 | -1769 | -1157.62 | 0 | 0 | 0 | 0 | -2926.62 | 0 | 245041.38 | 0 | [6 empty] | CM_WWNI | 46.99% | CM_WSNI | 53.01%
403739 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2014-08-25 | 2015-04-27 | 2015-04-27 | 2015-04-27 |  | South Lanarkshire | 18157.18 | -1272.93 | 0 | 0 | 0 | 0 | 0 | -1272.93 | 0 | 16884.25 | 0 | [6 empty] | CM_WWI | 100%
403490 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-07-05 | 2013-07-05 | 2013-07-05 | 2016-10-10 |  | Dumfries and Galloway | 48713.41 | 11286.59 | -11561.88 | 0 | 0 | 0 | 0 | -275.29 | 0 | 48438.12 | 0 | [6 empty] | CM_WWNI | 100%
402365 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2011-09-28 | 2011-10-07 | 2012-01-09 | 2016-10-10 |  | Dumfries and Galloway | 174168.61 | 7831.39 | -7728.2 | 0 | 0 | 0 | 0 | 103.19 | 0 | 174271.8 | 0 | [6 empty] | CM_WWNI | 100%
401494 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-04-22 | 2012-07-24 | 2012-10-22 | 2013-04-26 |  | Aberdeenshire | 111363 | -1841.58 | 0 | 0 | 0 | 0 | 0 | -1841.58 | 0 | 109521.42 | 0 | [6 empty] | CM_WSNI | 100%
403167 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2013-01-16 | 2014-02-07 | 2014-06-30 | 2018-07-09 |  | Highland | 164354 | 29705 | -15311.51 | 126731.92 | -45843.47 | 0 | 0 | 95281.94 | 0 | 259635.94 | 0 | [6 empty] | CM_WSNI | 100%
403019 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2012-11-30 | 2016-03-29 | 2016-06-10 | 2016-11-17 |  | West Lothian | 33410 | 103470 | 282094 | 3207 | -1136.3719 | 0 | 0 | 387634.6281 | 0 | 421044.6281 | 0 | [6 empty] | CM_WWI | 100%
403312 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-01-30 | 2015-07-13 | 2015-07-13 | 2014-04-22 | 2014-04-22 | West Lothian | 14962 | -1602.8 | 0 | 0 | 0 | 0 | 0 | -1602.8 | 0 | 13359.2 | 0 | [6 empty] | CM_WSI | 100%
403701 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-02-12 | 2014-04-24 | 2014-04-24 | 2015-10-30 |  | Scottish Water Wide | 93797 | -283.65 | 0 | 0 | 0 | 0 | 0 | -283.65 | 0 | 93513.35 | 0 | [6 empty] | CM_WSI | 100%
500570 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-06-05 | 2015-06-05 | 2015-06-22 | 2016-11-24 | 2016-11-24 | Scottish Water Wide | 0 | 250300.53 | -200357.95 | 20.795 | 0 | 0 | 0 | 49963.375 | 0 | 49963.375 | 0 | [6 empty] | CM_WSI | 100%
500539 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2016-12-21 | 2016-12-21 | Scottish Water Wide | 0 | 249979.18 | -1228.46 | 17.8 | 0 | 0 | 0 | 248768.52 | 0 | 248768.52 | 0 | [6 empty] | CM_WSI | 100%
500572 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-05-22 | 2015-05-22 | 2015-05-27 | 2017-04-28 | 2017-04-28 | Scottish Water Wide | 0 | 78328.28 | 9841.64 | -1399.36 | 0 | 0 | 0 | 86770.56 | 0 | 86770.56 | 0 | [6 empty] | CM_WSNI | 100%
500541 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-21 | 2015-04-21 | 2015-04-21 | 2016-12-21 | 2016-12-21 | Scottish Water Wide | 0 | 16836 | -14264.54 | 0 | 0 | 0 | 0 | 2571.46 | 0 | 2571.46 | 0 | [6 empty] | CM_WSNI | 100%
500571 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-06-05 | 2015-06-05 | 2015-06-22 | 2016-08-23 | 2016-08-23 | Scottish Water Wide | 0 | 177650.35 | -133356.32 | 3877.32 | 0 | 0 | 0 | 48171.35 | 0 | 48171.35 | 0 | [6 empty] | CM_WSNI | 100%
500540 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2018-02-26 | 2018-02-26 | Scottish Water Wide | 0 | 149499.68 | 316799.56 | 15709.28 | 98.63 | 0 | 0 | 482107.15 | 0 | 482107.15 | 0 | [6 empty] | CM_WSNI | 100%
500557 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2015-05-22 | 2015-05-22 | 2015-05-29 | 2020-02-10 | 2020-02-11 | All East Unitary Authorities | 0 | 197317 | 288945.53 | 306580.94 | 199228.29 | 8000 | 0 | 1000071.76 | 0 | 1000071.76 | 0 | [6 empty] | CM_WSNI | 100%
500526 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2015-04-28 | 2015-04-28 | 2015-04-28 | 2019-07-01 | 2019-07-01 | All East Unitary Authorities | 0 | 206922 | 81201 | 15254 | -25006.8 | 0 | 0 | 278370.2 | 0 | 278370.2 | 0 | [6 empty] | CM_WSNI | 100%
500555 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-05-22 | 2015-05-22 | 2015-05-29 | 2016-09-28 | 2016-09-28 | All East Unitary Authorities | 0 | 8792.52 | 0 | 0 | 0 | 0 | 0 | 8792.52 | 0 | 8792.52 | 0 | [6 empty] | CM_WSNI | 100%
500524 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2015-04-28 | 2015-04-28 | 2015-04-28 | 2019-07-01 | 2019-07-01 | All East Unitary Authorities | 0 | 265988 | 187409.69 | 62692 | -64990.2 | 8900.51 | 0 | 460000 | 0 | 460000 | 0 | [6 empty] | CM_WSNI | 100%
500556 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-06-05 | 2015-06-05 | 2015-06-22 | 2018-02-08 | 2018-02-08 | All East Unitary Authorities | 0 | 491516 | 694380.58 | 12552.78 | 0 | 0 | 0 | 1198449.36 | 0 | 1198449.36 | 0 | [6 empty] | CM_WSNI | 100%
500525 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2019-07-01 | 2019-07-01 | All East Unitary Authorities | 0 | 2306909.23 | 709531.32 | 249391.45 | -238806.23 | 0 | 0 | 3027025.77 | 0 | 3027025.77 | 0 | [6 empty] | CM_WSNI | 100%
500558 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-05-19 | 2015-05-19 | 2015-05-25 | 2018-03-21 | 2018-03-21 | All North Unitary Authorities | 0 | 669722 | 815300.91 | 597568.777 | 1849.514 | 0 | 0 | 2084441.201 | 0 | 2084441.201 | 0 | [6 empty] | CM_WSI | 100%
500527 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2017-01-04 | 2017-01-04 | All North Unitary Authorities | 0 | 380900 | 74723.83 | 728.89 | 0 | 0 | 0 | 456352.72 | 0 | 456352.72 | 0 | [6 empty] | CM_WSI | 100%
500561 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-04-30 | 2015-04-30 | 2015-05-25 | 2018-07-11 | 2018-07-11 | All North Unitary Authorities | 0 | 306765 | 51933.99 | 68044.42 | -11716.1175 | 0 | 0 | 415027.2925 | 0 | 415027.2925 | 0 | [6 empty] | CM_WSNI | 100%
500530 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2016-12-15 | 2017-01-31 | All North Unitary Authorities | 0 | 219313 | 41874.68 | 0 | 0 | 0 | 0 | 261187.68 | 0 | 261187.68 | 0 | [6 empty] | CM_WSNI | 100%
500559 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-04-30 | 2015-04-30 | 2015-05-25 | 2017-02-21 | 2017-02-21 | All North Unitary Authorities | 0 | 11131 | 7874.01 | 53.04 | 0 | 0 | 0 | 19058.05 | 0 | 19058.05 | 0 | [6 empty] | CM_WSNI | 100%
500528 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2016-08-31 | 2016-09-13 | All North Unitary Authorities | 0 | 65138.21 | 9165.42 | 0 | 0 | 0 | 0 | 74303.63 | 0 | 74303.63 | 0 | [6 empty] | CM_WSNI | 100%
500560 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-05-19 | 2015-05-19 | 2015-05-25 | 2018-06-22 | 2018-06-22 | All North Unitary Authorities | 0 | 808598 | 120025.43 | 52462.62 | -28429.3635 | 0 | 0 | 952656.6865 | 0 | 952656.6865 | 0 | [6 empty] | CM_WSNI | 100%
500529 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-21 | 2015-04-21 | 2015-04-21 | 2017-01-04 | 2017-01-04 | All North Unitary Authorities | 0 | 1694113.79 | 614611.46 | 1701.315 | 0 | 0 | 0 | 2310426.565 | 0 | 2310426.565 | 0 | [6 empty] | CM_WSNI | 100%
500643 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS5 | 2015-05-11 | 2015-05-11 | 2015-05-11 | 2018-08-10 | 2018-08-10 | Scottish Water Wide | 0 | 302440 | 98911.91 | 3129 | 3139.13 | 0 | 0 | 407620.04 | 0 | 407620.04 | 0 | [6 empty] | CM_WSI | 100%
500566 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-06-05 | 2015-06-05 | 2015-06-22 | 2017-11-22 | 2017-11-22 | All South Unitary Authorities | 0 | 116855 | 832361.93 | 170684.51 | -6424.1335 | 0 | 0 | 1113477.3065 | 0 | 1113477.3065 | 0 | [6 empty] | CM_WSI | 100%
500535 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-21 | 2015-04-21 | 2015-04-21 | 2017-02-01 | 2017-02-17 | All South Unitary Authorities | 0 | 859734 | 709.66 | 0 | 0 | 0 | 0 | 860443.66 | 0 | 860443.66 | 0 | [6 empty] | CM_WSI | 100%
500569 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-05-22 | 2015-05-22 | 2015-05-25 | 2016-03-03 | 2016-03-03 | All South Unitary Authorities | 0 | 3011.43 | 0 | 0 | 0 | 0 | 0 | 3011.43 | 0 | 3011.43 | 0 | [6 empty] | CM_WSNI | 100%
500538 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-02-08 | 2017-03-16 | All South Unitary Authorities | 0 | 286276 | -25443.47 | 0 | 0 | 0 | 0 | 260832.53 | 0 | 260832.53 | 0 | [6 empty] | CM_WSNI | 100%
500567 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-05-22 | 2015-05-22 | 2015-05-25 | 2016-03-03 | 2016-03-03 | All South Unitary Authorities | 0 | 6869.16 | 0 | 0 | 0 | 0 | 0 | 6869.16 | 0 | 6869.16 | 0 | [6 empty] | CM_WSNI | 100%
500536 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2016-08-02 | 2016-08-02 | All South Unitary Authorities | 0 | 63788 | -1703.29 | 0 | 0 | 0 | 0 | 62084.71 | 0 | 62084.71 | 0 | [6 empty] | CM_WSNI | 100%
500568 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-06-05 | 2015-06-05 | 2015-06-22 | 2018-05-30 | 2018-05-30 | All South Unitary Authorities | 0 | 198027 | 320140.89 | 233840.24 | 36667.744 | 0 | 0 | 788675.874 | 0 | 788675.874 | 0 | [6 empty] | CM_WSNI | 100%
500537 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-21 | 2015-04-21 | 2015-04-21 | 2017-06-01 | 2017-06-01 | All South Unitary Authorities | 0 | 1971276 | 27327 | -69741.79 | 0 | 0 | 0 | 1928861.21 | 0 | 1928861.21 | 0 | [6 empty] | CM_WSNI | 100%
500562 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-06-05 | 2015-06-05 | 2015-06-25 | 2019-06-04 | 2019-06-04 | All West Unitary Authorities | 0 | 551946 | 2071586.31 | 962346.85 | 17136.41 | 3000 | 0 | 3606015.57 | 0 | 3606015.57 | 0 | [6 empty] | CM_WSI | 100%
500531 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2019-02-08 | 2019-02-08 | All West Unitary Authorities | 0 | 161402 | -42252.53 | 45850.53 | -66161.03 | 0 | 0 | 98838.97 | 0 | 98838.97 | 0 | [6 empty] | CM_WSI | 100%
500565 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-05-25 | 2015-05-25 | 2015-05-27 | 2017-06-09 | 2017-06-09 | All West Unitary Authorities | 0 | 261073 | 71787.36 | 1044.68 | 0 | 0 | 0 | 333905.04 | 0 | 333905.04 | 0 | [6 empty] | CM_WSNI | 100%
500534 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-21 | 2015-04-21 | 2015-04-21 | 2019-02-08 | 2019-02-08 | All West Unitary Authorities | 0 | 217820.42 | 98500.5 | 11060.02 | 24145.25 | 0 | 0 | 351526.19 | 0 | 351526.19 | 0 | [6 empty] | CM_WSNI | 100%
500563 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-05-25 | 2015-05-25 | 2015-05-27 | 2018-03-07 | 2018-03-07 | All West Unitary Authorities | 0 | 417698 | 448826.6 | 94730.29 | -17225.21 | 0 | 0 | 944029.68 | 0 | 944029.68 | 0 | [6 empty] | CM_WSNI | 100%
500532 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-21 | 2015-04-21 | 2015-04-21 | 2019-02-08 | 2019-02-08 | All West Unitary Authorities | 0 | 46708 | 8395.79 | 14896.21 | -20374.27 | 0 | 0 | 49625.73 | 0 | 49625.73 | 0 | [6 empty] | CM_WSNI | 100%
500564 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-11-02 | 2015-06-05 | 2015-06-25 | 2017-08-24 | 2017-09-01 | All West Unitary Authorities | 0 | 275953.49 | 299227.23 | 15731.05 | 0 | 0 | 0 | 590911.77 | 0 | 590911.77 | 0 | [6 empty] | CM_WSNI | 100%
500533 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2019-02-08 | 2019-02-08 | All West Unitary Authorities | 0 | 674910.5 | 280780.26 | 0 | 9419.5075 | 0 | 0 | 965110.2675 | 0 | 965110.2675 | 0 | [6 empty] | CM_WSNI | 100%
402556 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-02-24 | 2012-02-24 | 2012-04-09 | 2016-01-14 |  | All West Unitary Authorities | 1002831 | -28267.36 | 0 | 0 | 0 | 0 | 0 | -28267.36 | 0 | 974563.64 | 0 | [6 empty] | CM_WSNI | 100%
402199 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2011-09-12 | 2012-05-21 | 2012-06-25 | 2016-06-17 |  | Orkney Islands | 10000 | 0 | -2675.68 | 0 | 0 | 0 | 0 | -2675.68 | 0 | 7324.32 | 0 | [6 empty] | CM_M&G | 100%
402112 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-05-18 | 2012-05-15 | 2012-05-30 | 2012-07-13 | 2012-07-13 | Shetland Islands | 30631.65 | 62.5 | 0 | 0 | 0 | 0 | 0 | 62.5 | 0 | 30694.15 | 0 | [6 empty] | CM_WSI | 100%
403471 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-04-18 | 2014-05-12 | 2014-07-21 | 2016-03-09 |  | Orkney Islands | 233231 | 32979 | 11294.63 | 40.67 | -430.16 | 0 | 0 | 43884.14 | 0 | 277115.14 | 0 | [6 empty] | CM_WSNI | 100%
403448 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-05-13 | 2015-03-12 | 2015-03-02 | 2015-03-03 |  | Highland | 103000 | -27.1 | 0 | 0 | 0 | 0 | 0 | -27.1 | 0 | 102972.9 | 0 | [6 empty] | CM_WSNI | 100%
403449 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-04-23 | 2013-07-29 | 2013-09-09 | 2015-03-30 |  | Scottish Water Wide | 590036 | -14947.82 | 88.75 | 0 | 0 | 0 | 0 | -14859.07 | 0 | 575176.93 | 0 | [6 empty] | CM_WSNI | 100%
401865 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-12-23 | 2012-07-24 | 2012-09-28 | 2013-04-25 |  | Angus | 54674 | -2065.62 | 0 | 0 | 0 | 0 | 0 | -2065.62 | 0 | 52608.38 | 0 | [6 empty] | CM_WSI | 100%
400797 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-06-21 | 2011-06-23 | 2010-08-23 | 2012-03-29 |  | Dundee City | 100098 | -8492.87 | 0 | 0 | 0 | 0 | 0 | -8492.87 | 0 | 91605.13 | 0 | [6 empty] | CM_WSI | 100%
402019 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2011-04-27 | 2014-12-17 | 2015-03-26 | 2017-06-21 |  | Shetland Islands | 194347 | 358958 | 65000 | 56453.09 | 0 | 0 | 0 | 480411.09 | 0 | 674758.09 | 0 | [6 empty] | CM_M&G | 100%
401051 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-05-06 | 2014-06-30 | 2015-01-23 | 2016-03-29 |  | Orkney Islands | 352366 | 55145.9 | 91109.3 | 0 | -6595.29 | 0 | 0 | 139659.91 | 0 | 492025.91 | 0 | [6 empty] | CM_WSNI | 100%
400978 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-05-31 | 2010-05-24 | 2013-02-08 | 2015-12-14 | 2017-01-05 08:00 | Highland | 91772 | 197113.42 | 0 | 0 | 0 | 0 | 0 | 197113.42 | 0 | 288885.42 | 0 | [6 empty] | CM_WWI | 100%
402077 | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2011-09-20 | 2011-09-20 | 2011-09-20 | 2015-03-17 |  | Scottish Water Wide | 2231.71 | -677.27 | 0 | 0 | 0 | 0 | 0 | -677.27 | 0 | 1554.44 | 0 | [6 empty] | CS20 | 100%
502639 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS3 | 2017-03-09 | 2017-03-09 | 2017-03-13 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 18938.32 | 110072.03 | 265654.41 | 31533.54 | 508006.7 | 934205 | 0 | 934205 | 0 | [6 empty] | CM_M&G | 100%
404118 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2016-01-22 |  | Scottish Water Wide | 0 | 447836.14 | 0 | 0 | 0 | 0 | 0 | 447836.14 | 0 | 447836.14 | 0 | [6 empty] | CM_M&G | 100%
403580 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2013-09-25 | 2018-12-19 | 2018-12-19 | 2019-08-30 |  | Scottish Water Wide | 124143.59 | 51328.41 | 91609.79 | 8000 | -15455.58 | 40373.79 | 0 | 175856.41 | 0 | 300000 | 0 | [6 empty] | CM_WSI | 100%
501017 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS1 | 2018-01-30 | 2019-06-03 | 2019-08-21 | 2020-04-06 | 2020-09-29 | Glasgow City | 0 | 21930 | 66070 | 87000 | 135431 | 1174611.39 | 55247.72 | 1540290.11 | 709.81 | 1540999.92 | 229318.7788 | [6 empty] | CS11 | 100%
500651 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2017-02-08 | 2018-03-27 | 2018-03-27 | 2017-10-17 | 2018-03-27 | East Ayrshire | 0 | 38389 | 46428 | -79879.745 | 968.97 | 0 | 0 | 5906.225 | 0 | 5906.225 | 229318.7788 | [6 empty] | CS11 | 100%
502895 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-02-20 | 2021-02-08 | 2021-04-21 | 2021-11-23 | 2022-02-23 | Glasgow City | 0 | 0 | 0 | 41860.47 | 97139.53 | 27921 | 183055.12 | 349976.12 | 555023.93 | 905000.05 | 240495.8008 | [6 empty] | CS11A | 100%
502228 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2019-12-20 | 2020-07-01 | 2020-07-01 | 2020-07-01 | 2020-07-01 | Glasgow City | 0 | 0 | 37030.23 | 43969.77 | 85000 | 116506.17 | 157493.82 | 439999.99 | 0 | 439999.99 | 240495.8008 | [6 empty] | CS11A | 100%
503318 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-11-30 | 2021-11-04 | 2022-01-18 | 2022-08-22 | 2022-11-22 | Glasgow City | 0 | 0 | 0 | 0 | 44000 | 44132.11 | 43661.89 | 131794 | 468206 | 600000 | 240495.8008 | [6 empty] | CS11A | 100%
500999 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS0 | 2018-03-30 | 2019-05-13 | 2019-07-29 | 2019-11-14 | 2020-02-20 | East Renfrewshire | 0 | 22930 | 46633.66 | 57997.4887 | 113889.8513 | 490240.01 | 4165 | 735856.01 | 3144.02 | 739000.03 | 229318.7788 | [6 empty] | CS11 | 100%
500202 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW2 | 2019-12-02 | 2019-12-02 | 2019-12-02 | 2019-12-02 | 2019-12-02 | Glasgow City | 0 | 66930 | 57070 | 15000 | 45000 | 16341 | 0 | 200341 | 0 | 200341 | 520131.8398 | [6 empty] | CS11 | 100%
503172 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-06-23 | 2021-06-04 | 2021-08-25 | 2022-03-29 | 2022-06-29 | Stirling | 0 | 0 | 0 | 0 | 84000 | 45076.2 | 45195.1 | 174271.3 | 141728.73 | 316000.03 | 240495.8008 | [6 empty] | CS11A | 100%
500743 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-03-22 | 2019-03-22 | 2019-03-22 | 2019-02-25 | 2019-02-25 | South Lanarkshire | 0 | 15500 | 19500 | 12000 | -45905.09 | 0 | 0 | 1094.91 | 0 | 1094.91 | 229318.7788 | [6 empty] | CS11 | 100%
500003 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS6 | 2015-03-26 | 2015-06-25 | 2015-06-26 | 2017-12-20 | 2017-12-20 | West Dunbartonshire | 0 | 848820 | -19597.9 | 560701.7875 | 1369.1125 | 742 | 0 | 1392035 | 0 | 1392035 | 240495.8008 | [6 empty] | CS11A | 100%
501016 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | WWINF | Infra Charge | MS0 | 2018-02-22 | 2019-04-29 | 2019-06-24 | 2020-05-13 | 2020-08-14 | East Dunbartonshire | 0 | 0 | 65306.81 | 120693.19 | 202200.64 | 308455.07 | 152576.32 | 849232.03 | 716 | 849948.03 | 3783756.1971 | [6 empty] | SG5 | 100%
502891 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-02-19 | 2021-02-08 | 2021-04-21 | 2021-11-23 | 2022-02-23 | Glasgow City | 0 | 0 | 0 | 43000 | 96000 | 40000 | 69651.35 | 248651.35 | 62348.7 | 311000.05 | 240495.8008 | [6 empty] | CS11A | 100%
502892 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-02-20 | 2021-02-08 | 2021-04-21 | 2022-01-25 | 2022-04-27 | East Renfrewshire | 0 | 0 | 0 | 42564.5675 | 91935.4325 | 39000 | 294277.18 | 467777.18 | 733722.81 | 1201499.99 | 240495.8008 | [6 empty] | CS11A | 100%
500748 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2019-06-14 | 2020-05-04 | 2020-07-29 | 2021-03-03 | 2021-06-01 | North Ayrshire | 0 | 23500 | 24530.23 | 55435.3031 | 44534.4669 | 11815.18 | 314428.04 | 474243.22 | 87256.76 | 561499.98 | 229318.7788 | [6 empty] | CS11 | 100%
501011 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2019-07-01 | 2019-07-01 | 2019-07-03 | 2019-07-05 | 2019-07-05 | Glasgow City | 0 | 31056.93 | 34027.07 | 22916 | 6000 | 0 | 0 | 94000 | 0 | 94000 | 229318.7788 | [6 empty] | CS11 | 100%
500663 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW2 | 2020-12-18 | 2020-12-24 | 2020-12-30 | 2021-01-05 | 2021-01-05 | East Ayrshire | 0 | 23100 | 30930.23 | 16969.77 | 20000 | 3000 | 492500 | 586500 | 0 | 586500 | 362001.5575 | [6 empty] | CS11 | 100%
502425 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-03-27 | 2021-01-11 | 2021-03-26 | 2021-08-09 | 2021-11-09 | South Lanarkshire | 0 | 0 | 41860.47 | 16139.53 | 34000 | 18664.86 | 71756.48 | 182421.34 | 492101.66 | 674523 | 240495.8008 | [6 empty] | CS11A | 100%
501000 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2019-12-02 | 2019-12-03 | 2019-12-03 | 2019-12-03 | 2019-12-03 | East Ayrshire | 0 | 26523 | 42109 | 12369 | 29581.7741 | 0 | 0 | 110582.7741 | 0 | 110582.7741 | 229318.7788 | [6 empty] | CS11 | 100%
502376 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-04-21 | 2021-03-22 | 2021-05-24 | 2021-08-27 | 2021-11-29 | Stirling | 0 | 0 | 42522.01 | 2477.99 | 29000 | 24980.69 | 48389.32 | 147370.01 | 152630.05 | 300000.06 | 240495.8008 | [6 empty] | CS11A | 100%
502894 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2021-05-04 | 2022-03-29 | 2022-06-10 | 2023-01-12 | 2023-04-14 | Inverclyde | 0 | 0 | 0 | 41860.47 | 4139.53 | 1036.37 | 10230.3 | 57266.67 | 242733.31 | 299999.98 | 240495.8008 | [6 empty] | CS11A | 100%
501014 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS0 | 2019-02-08 | 2019-11-18 | 2020-01-06 | 2020-06-01 | 2020-09-03 | Argyll and Bute-Cowal & Bute | 0 | 22930 | 44566.68 | 51503.32 | 93383.9726 | 251516.86 | 293337.72 | 757238.5526 | 1886.39 | 759124.9426 | 229318.7788 | [6 empty] | CS11 | 100%
502328 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2019-11-04 | 2020-10-19 | 2021-01-13 | 2021-10-11 | 2022-01-07 | East Ayrshire | 0 | 0 | 43360.47 | 25639.53 | 77000 | 32858 | 177329.13 | 356187.13 | 372812.96 | 729000.09 | 240495.8008 | [6 empty] | CS11A | 100%
500681 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW1 | 2019-11-01 | 2021-02-22 | 2021-05-21 | 2021-12-23 | 2022-03-17 | South Lanarkshire | 0 | 62556 | 20783.9 | 24660.1 | 31000 | 54200.52 | 538242.71 | 731443.23 | 1572556.76 | 2303999.99 | 280399.7974 | [6 empty] | CS11 | 100%
500682 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW2 | 2019-04-01 | 2020-06-15 | 2020-08-24 | 2021-04-01 | 2021-06-24 | South Lanarkshire | 0 | 56500 | 20886.26 | 26210.108 | 37403.632 | 90532.54 | 828974.67 | 1060507.21 | 314492.8 | 1375000.01 | 458341.6551 | [6 empty] | CS11 | 100%
500732 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MS7 | 2019-03-14 | 2019-03-14 | 2019-03-14 | 2019-02-25 | 2019-02-25 | South Ayrshire | 0 | 22930 | 23500 | 20570 | -66999 | 0 | 0 | 1 | 0 | 1 | 59216.7756 | [6 empty] | CS11 | 100%
403300 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-01-17 | 2013-01-17 | 2013-03-21 | 2018-08-13 |  | Highland | 32987.1 | -0.1 | 120 | 0 | 0 | 0 | 0 | 119.9 | 0 | 33107 | 0 | [6 empty] | CM_WWI | 100%
049605 | Q&S4 | Programme Risk | Enhanced Risk |  |  | General |  | SWD | Enhanced Risk | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 50875708.07 | 53888088.7159 | 104763796.7859 | 0 | 104763796.7859 | 0 | [6 empty] | RISK | 100%
403710 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-02-20 | 2014-02-20 | 2014-04-04 | 2015-11-18 | 2016-03-31 | Highland | 2200000 | 727291.7 | -2033 | 0 | 0 | 0 | 0 | 725258.7 | 0 | 2925258.7 | 0 | [6 empty] | CM_WSNI | 100%
500711 | Q&S4 | Supporting economic development | Infra Charge |  |  | Wastewater |  | WWINF | Infra Charge | MS1 | 2018-03-28 | 2019-07-15 | 2019-10-01 | 2020-04-06 | 2020-07-06 | South Lanarkshire | 0 | 85125 | 50875 | 28855.8816 | 117628.1184 | 613781.73 | 152445.86 | 1048711.59 | 6856.13 | 1055567.72 | 3783756.1971 | [6 empty] | SG5 | 100%
030934 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-08 | 2010-11-16 | 2011-07-11 | 2012-03-16 | 2012-03-26 | North Lanarkshire | 966437.16 | 738.1 | 0 | 0 | 0 | 0 | 0 | 738.1 | 0 | 967175.26 | 0 | [6 empty] | CM_WWNI | 100%
500183 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-19 | 2015-11-30 | 2016-01-18 | 2018-01-01 | 2018-01-01 | North Lanarkshire | 0 | 90527 | 79975 | 30582.11 | 141.17 | 0 | 0 | 201225.28 | 0 | 201225.28 | 0 | [6 empty] | CS16D | 100% | bar: Regulatory Outputs OMG-22
501314 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS5 | 2015-12-23 | 2018-01-23 | 2018-01-24 | 2019-02-13 | 2019-02-13 | South Lanarkshire | 0 | 289255 | 174822 | 775529 | 2337639.6 | 30000.51 | 2249.89 | 3609496 | 0 | 3609496 | 0 | [6 empty] | CM_WWI | 100%
501166 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2015-11-25 | 2018-06-22 | 2018-06-28 | 2020-02-17 | 2020-02-17 | South Lanarkshire | 0 | 17500 | 136005.61 | 72979.6 | 1052101.05 | 825608.06 | 129288.74 | 2233483.06 | 5687.67 | 2239170.73 | 0 | [6 empty] | CM_WWNI | 100%
403191 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-12-18 | 2013-03-25 | 2013-04-15 | 2015-09-25 |  | South Lanarkshire | 414909 | 0 | 177 | 7722.33 | 0 | 0 | 0 | 7899.33 | 0 | 422808.33 | 0 | [6 empty] | CM_WWI | 100%
045558 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-05-29 | 2011-02-14 | 2011-08-26 | 2012-03-21 | 2012-03-30 | Scottish Borders | 866115.65 | 542.49 | 0 | 0 | 0 | 0 | 0 | 542.49 | 0 | 866658.14 | 0 | [6 empty] | WQ01 | 50% | CM_WWNI | 50%
500970 | Q&S4 | Reducing flooding and pollution from sewers | Surface Water |  |  | Wastewater |  | SWD | Surface Water | MS3 | 2016-03-15 | 2016-03-15 | 2016-06-24 | 2021-04-23 | 2021-04-23 | Scottish Water Wide | 0 | 58977.37 | 101022.63 | 326694.298 | 376600.432 | 37538.17 | 1617.51 | 902450.41 | 0 | 902450.41 | 1343527.3003 | [6 empty] | CS15C | 100%
030947 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-21 | 2011-10-27 | 2012-01-16 | 2014-03-07 | 2014-03-24 | West Lothian | 191500 | 7.27 | 0 | 0 | 0 | 0 | 0 | 7.27 | 0 | 191507.27 | 0 | [6 empty] | EC09B | 50% | EC10D | 50%
045240 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-21 | 2011-11-24 | 2012-02-06 | 2014-03-07 | 2014-03-24 | Midlothian | 157383 | -0.2 | 0 | 0 | 0 | 0 | 0 | -0.2 | 0 | 157382.8 | 0 | [6 empty] | EC09B | 50% | EC10D | 50%
030948 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-21 | 2011-10-27 | 2012-01-18 | 2013-07-24 | 2013-10-09 | West Lothian | 139722 | -125.19 | 0 | 0 | 0 | 0 | 0 | -125.19 | 0 | 139596.81 | 509 | [6 empty] | EC09B | 50% | EC10D | 50%
030952 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-21 | 2011-11-14 | 2012-02-07 | 2014-08-22 | 2014-08-29 | Midlothian | 178935 | 734 | 0 | 0 | 0 | 0 | 0 | 734 | 0 | 179669 | 733 | [6 empty] | EC09B | 50% | EC10D | 50%
030953 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-21 | 2011-11-14 | 2012-02-06 | 2014-08-28 | 2014-10-22 | Midlothian | 192617 | 271.57 | 0 | 0 | 0 | 0 | 0 | 271.57 | 0 | 192888.57 | 393.0002 | [6 empty] | EC09B | 50% | EC10D | 50%
030943 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-21 | 2011-11-24 | 2012-02-08 | 2014-08-22 | 2014-10-02 | North Lanarkshire | 237194 | 3003.4 | 0 | 0 | 0 | 0 | 0 | 3003.4 | 0 | 240197.4 | 47 | [6 empty] | EC09B | 50% | EC10D | 50%
300031 | Q&S3A | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2011-11-15 | 2011-11-15 | 2011-11-15 | 2015-11-03 | 2016-03-01 | Scottish Water Wide | 652554 | -25204.52 | 0 | 0 | 0 | 0 | 0 | -25204.52 | 0 | 627349.48 | 0 | [6 empty] | CM_M&G | 100%
300030 | Q&S3A | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2011-11-15 | 2011-11-15 | 2011-11-15 | 2015-11-03 | 2016-03-01 | Scottish Water Wide | 529090.85 | 7926.05 | 0 | 0 | 0 | 0 | 0 | 7926.05 | 0 | 537016.9 | 0 | [6 empty] | CM_M&G | 100%
300036 | Q&S3A | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2012-07-31 | 2012-07-31 | 2012-08-06 | 2015-11-03 | 2016-02-03 | Scottish Water Wide | 421388.47 | 1575.16 | 0 | 0 | 0 | 0 | 0 | 1575.16 | 0 | 422963.63 | 0 | [6 empty] | CM_M&G | 100%
401033 | Q&S3A | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWS1 | Management and General | MS0 | 2010-04-01 |  |  |  |  | Scottish Water Wide | 288394.24 | 2.76 | 0 | 0 | 0 | 0 | 0 | 2.76 | 0 | 288397 | 0 | [6 empty] | OHDW1 | 100%
401031 | Q&S3A | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWS1 | Management and General | MS0 | 2010-04-01 |  |  |  |  | Scottish Water Wide | 154448.05 | 1.95 | 0 | 0 | 0 | 0 | 0 | 1.95 | 0 | 154450 | 0 | [6 empty] | OHDS1 | 100%
401030 | Q&S3A | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWS1 | Management and General | MS0 | 2010-04-01 |  |  |  |  | Scottish Water Wide | -18550.59 | 33.32 | 114.45 | 0 | 0 | 0 | 0 | 147.77 | 0 | -18402.82 | 0 | [6 empty] | OHDW1 | 100%
047196 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS2 | 2001-02-25 | 2017-03-27 | 2020-04-30 | 2020-04-30 |  | Scottish Water Wide | 444841.06 | -57358.55 | -199844.5 | 313291.28 | -141782.533 | 221774.96 | 80435.42 | 216516.077 | 0 | 661357.137 | 0 | [6 empty] | OHDS1 | 100%
402011 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-02-24 | 2016-04-18 | 2016-03-08 | 2016-03-08 | 2016-03-08 | Scottish Water Wide | -487440 | 487440 | 0 | 0 | 0 | 0 | 0 | 487440 | 0 | 0 | 0 | [6 empty] | WSNI | 100%
402010 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWMD | Management and General | MS4 | 2011-02-24 |  |  | 2019-01-15 |  | Scottish Water Wide | -800000 | 1330580 | 2484997 | 661852.9741 | -942668.5389 | 0 | 0 | 3534761.4352 | 0 | 2734761.4352 | 0 | [6 empty] | OHDS1 | 50% | OHDW1 | 50%
047197 | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWMD | Non OMG180 | MS4 | 2001-02-25 | 2012-01-04 | 2018-04-30 | 2019-02-13 |  | Scottish Water Wide | -2150000 | -20771288 | 0 | 0 | 0 | 0 | 0 | -20771288 | 0 | -22921288 | -21921586.73 | [6 empty] | RISK_SWS2 | 100%
402382 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-09-29 | 2012-06-05 | 2012-07-25 | 2014-09-01 |  | Scottish Water Wide | 4056919 | 3800 | -3629.15 | 0 | 0 | 0 | 0 | 170.85 | 0 | 4057089.85 | 0 | [6 empty] | CM_WSNI | 100%
501154 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2016-02-17 | 2018-11-05 | 2019-02-04 | 2019-08-23 | 2019-11-26 | North Lanarkshire | 0 | 909.35 | 70857.33 | 34689.32 | 544359.36 | 420317 | 5019.59 | 1076151.95 | 0.05 | 1076152 | 0 |  |  |  |  | 1500 |  | CM_WWNI | 100%
045540 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-05 | 2011-02-07 | 2011-07-04 | 2012-03-16 | 2012-03-22 | South Lanarkshire | 1003868.54 | 311.36 | 0 | 0 | 0 | 0 | 0 | 311.36 | 0 | 1004179.9 | 0 | [6 empty] | CM_WWI | 2.471% | CS11A | 6.355% | WQ01 | 91.17%
045541 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-05 | 2011-02-07 | 2011-10-24 | 2012-06-24 | 2012-06-28 | South Lanarkshire | 1066244.65 | 812.77 | 0 | 0 | 0 | 0 | 0 | 812.77 | 0 | 1067057.42 | 0 | [6 empty] | WQ01 | 100%
502182 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2016-06-29 | 2016-10-28 | 2016-10-28 | 2019-05-24 | 2019-07-12 | Scottish Water Wide | 0 | 0 | 389447.89 | 561273.96 | 127091.1 | 134631.19 | 0 | 1212444.14 | 0 | 1212444.14 | 0 |  |  |  |  | 24999.9996 |  | CM_M&G | 100%
501645 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | GW2 | 2021-03-01 | 2021-03-01 | 2021-03-01 | 2021-03-12 | 2021-03-12 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 1495819.87 | 1495819.87 | 0 | 1495819.87 | 0 | [6 empty] | CM_M&G | 100%
501253 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS3 | 2016-03-02 | 2018-09-28 | 2018-10-30 | 2019-12-19 | 2020-03-26 | Highland | 0 | 5728.8 | 215606.6 | 136996.21 | 646956.48 | 903365.6 | 16384.25 | 1925037.94 | 9478.05 | 1934515.99 | 148885.7057 |  |  |  |  | 2940 |  | CM_WWNI | 35% | SG1 | 65%
501420 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2022-01-28 | 2023-01-09 | 2023-03-23 | 2024-04-23 | 2024-07-16 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 4500000 | 0 | [6 empty] | CM_WSI | 100%
501617 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2021-07-23 | 2022-06-10 | 2022-08-29 | 2023-09-28 | 2023-12-27 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4971751 | 4971751 | 0 | [6 empty] | CM_WSI | 100%
503366 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS2 | 2018-09-28 | 2018-09-28 | 2019-05-22 | 2019-09-30 | 2020-01-06 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 28976.4845 | 169888.83 | 1173.52 | 200038.8345 | 621.02 | 200659.8545 | 0 | [6 empty] | CM_WSI | 100%
045651 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2008-07-31 | 2012-08-30 | 2012-09-17 | 2015-07-30 |  | Scottish Borders | 7179571 | 121113 | 199945.35 | -5520.805 | 0 | 0 | 0 | 315537.545 | 0 | 7495108.545 | 0 | [6 empty] | CM_WSNI | 100%
401972 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-04-01 | 2014-03-31 | 2014-04-21 | 2015-01-12 | 2015-01-12 | Scottish Borders | 641437 | -7222 | -249.73 | 0 | 0 | 0 | 0 | -7471.73 | 0 | 633965.27 | 0 | [6 empty] | CM_WSI | 100%
045280 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2010-06-14 | 2011-03-30 | 2011-06-23 | East Dunbartonshire | 547741.6 | 1.3 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 547742.9 | 0 | [6 empty] | DW8 | 100%
045282 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2012-01-16 | 2012-02-23 | 2012-03-14 | West Dunbartonshire | 263100.22 | 108.68 | 0 | 0 | 0 | 0 | 0 | 108.68 | 0 | 263208.9 | 0 | [6 empty] | DW8 | 100%
045284 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2010-10-11 | 2011-01-28 | 2011-06-23 | Falkirk | 190609.51 | -22.51 | 0 | 0 | 0 | 0 | 0 | -22.51 | 0 | 190587 | 0 | [6 empty] | DW8 | 100%
045285 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-09-24 | 2010-11-08 | 2011-05-24 | 2012-03-30 | City of Edinburgh | 339120.29 | 498.71 | 0 | -22.02 | 0 | 0 | 0 | 476.69 | 0 | 339596.98 | 0 | [6 empty] | DW8 | 100%
045286 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2010-08-02 | 2011-07-29 | 2011-10-05 | Fife | 436124.05 | 6019.55 | -6019.58 | 0 | 0 | 0 | 0 | -0.03 | 0 | 436124.02 | 0 | [6 empty] | DW8 | 100%
045287 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2010-08-09 | 2011-03-29 | 2011-06-23 | Aberdeenshire | 351447.31 | 242.99 | 0 | 0 | 0 | 0 | 0 | 242.99 | 0 | 351690.3 | 0 | [6 empty] | DW8 | 100%
045288 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2010-08-23 | 2012-02-23 | 2012-03-14 | Aberdeen City | 483724.01 | 286 | 0 | 0 | 0 | 0 | 0 | 286 | 0 | 484010.01 | 0 | [6 empty] | DW8 | 100%
045289 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2011-01-17 | 2012-02-19 | 2012-03-14 | Inverclyde | 471461.33 | 6.89 | 0 | 0 | 0 | 0 | 0 | 6.89 | 0 | 471468.22 | 0 | [6 empty] | DW8 | 100%
045291 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2010-08-02 | 2011-03-03 | 2011-06-23 | Perth and Kinross | 367773.39 | 214.72 | 0 | 0 | 0 | 0 | 0 | 214.72 | 0 | 367988.11 | 0 | [6 empty] | DW8 | 100%
045292 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-03-10 | 2010-11-08 | 2011-03-02 | 2011-06-23 | Angus | 272223.68 | 158.16 | 0 | 0 | 0 | 0 | 0 | 158.16 | 0 | 272381.84 | 0 | [6 empty] | DW8 | 100%
502872 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2021-05-18 | 2027-11-29 | 2028-03-21 | 2029-03-13 | 2029-06-13 | Na H-Eileanan an Iar | 0 | 0 | 0 | 21237.996 | 1489.879 | 12868.05 | 12818.19 | 48414.115 | 7951645.88 | 8000059.995 | 148885.7057 | [6 empty] | WG1 | 100%
500184 | Q&S4 | Reducing flooding and pollution from sewers | Flood Assessments |  |  | Wastewater |  | SWMD | Flood Assessments | MS7 | 2015-03-20 | 2015-11-30 | 2016-01-11 | 2017-02-01 | 2017-05-01 | Argyll and Bute-Cowal & Bute | 0 | 42286 | 40471 | 15399.18 | 41.28 | 0 | 0 | 98197.46 | 0 | 98197.46 | 72474.3726 | [6 empty] | CS16D | 40.17% | CS11 | 59.83% | bar: Regulatory Outputs OMG-22
500880 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-09-20 | 2018-09-18 | 2018-12-13 | 2019-03-27 | 2020-01-22 | Na H-Eileanan an Iar | 0 | 1581.68 | 3568.21 | 6367 | 73562.87 | 13883.94 | 807.21 | 99770.91 | 0 | 99770.91 | 0 | [6 empty] | DW5FS | 100%
502835 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2018-07-18 | 2018-07-17 | 2018-07-17 | 2018-07-17 | 2018-07-17 | Na H-Eileanan an Iar | 0 | 0 | 0 | 57254.8075 | 23277.4115 | 0 | 0 | 80532.219 | 0 | 80532.219 | 0 | [6 empty] | CM_WSNI | 100%
500686 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-06-11 | 2016-05-18 | 2016-06-13 | 2016-09-30 | 2016-09-30 | South Ayrshire | 0 | 66557 | 738874 | 26386.76 | 20214.1779 | 0 | 0 | 852031.9379 | 0 | 852031.9379 | 0 | [6 empty] | CM_WWI | 100%
501270 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS6 | 2016-07-19 | 2017-11-07 | 2018-03-26 | 2018-10-30 | 2018-10-30 | South Ayrshire | 0 | 0 | 30180 | 318820 | 424542.9179 | 0 | 0 | 773542.9179 | 0 | 773542.9179 | 0 | [6 empty] | CM_WWNI | 100%
500881 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-09-20 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Highland | 0 | 490.79 | 1083.55 | 0 | 0 | 0 | 0 | 1574.34 | 0 | 1574.34 | 10044.4472 | [6 empty] | DW5FS | 100%
046847 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2011-03-01 | 2011-03-14 | 2014-12-01 | 2015-03-27 | Na H-Eileanan an Iar | 1053408.29 | 44948.52 | -10506.85 | 24820.97 | -11082.133 | 0 | 0 | 48180.507 | 0 | 1101588.797 | 3002 | [6 empty] | DW23 | 100%
502827 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW1 | 2021-06-02 | 2022-07-15 | 2022-11-07 | 2023-10-26 | 2024-01-26 | Aberdeenshire | 0 | 0 | 0 | 64604.4475 | 17150.6325 | 16778.98 | 28712.23 | 127246.29 | 23568.91 | 150815.2 | 148885.7057 | [6 empty] | SG1 | 100%
400279 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-03-30 | 2012-07-31 | 2012-09-03 | 2013-08-02 |  | Perth and Kinross | 886307 | 2696.48 | 0 | 0 | 0 | 0 | 0 | 2696.48 | 0 | 889003.48 | 0 | [6 empty] | CM_WSI | 100%
401222 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-07-15 | 2012-12-11 | 2013-01-30 | 2014-05-09 |  | Perth and Kinross | 1175950 | 25185 | -5181.03 | 0 | 0 | 0 | 0 | 20003.97 | 0 | 1195953.97 | 0 | [6 empty] | CM_WSI | 100%
500108 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2015-03-20 | 2016-12-14 | 2016-12-19 | 2020-03-20 | 2020-06-16 | Scottish Water Wide | 0 | 21309 | 41063.07 | 29834.93 | 60313 | 7477.22 | 2.76 | 159999.98 | 0 | 159999.98 | 218065.2698 | [6 empty] | EC01G | 0.5128% | EC10E | 49.74% | EC10H | 49.74%
501048 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-10-09 | 2018-06-26 | 2018-08-06 | 2019-10-24 | 2019-10-25 | Fife | 0 | 30750 | 55000 | 30950.11 | 478929.8845 | 111907.02 | 3409.45 | 710946.4645 | 3295.79 | 714242.2545 | 0 | [6 empty] | CM_WSI | 100%
401491 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-08 | 2012-03-15 | 2012-03-15 | 2015-07-31 |  | All East Unitary Authorities | 1188388 | 73871 | 0 | -1383.22 | 0 | 0 | 0 | 72487.78 | 0 | 1260875.78 | 0 | [6 empty] | CM_WSI | 100%
501105 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-09-30 | 2016-12-19 | 2017-01-20 | 2018-06-01 | 2018-12-01 | Dundee City | 0 | 608 | 14339.25 | 22299.75 | 13647.85 | 0 | 0 | 50894.85 | 0 | 50894.85 | 74491.9452 | [6 empty] | EC01G | 3.809% | EC10E | 96.19% | bar: Regulatory Outputs OMG-23
501831 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW2 | 2021-04-06 | 2021-09-01 | 2021-10-07 | 2021-11-17 | 2021-12-15 | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29179.02 | 29179.02 | 0 | [6 empty] | CM_WWI | 100%
403899 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-07-30 | 2014-10-08 | 2014-10-08 | 2017-01-26 | 2017-01-26 | Scottish Water Wide | 1813801 | 374097 | 40578.37 | 1123.2 | 0 | 0 | 0 | 415798.57 | 0 | 2229599.57 | 0 | [6 empty] | CM_M&G | 100%
402679 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-05-21 | 2012-09-21 | 2012-10-22 | 2013-09-23 |  | Highland | 650602 | 29593 | 3425.08 | -44789.92 | -644.4 | 0 | 0 | -12416.24 | 0 | 638185.76 | 0 | [6 empty] | CM_WSI | 100%
402952 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-04-09 | 2014-06-20 | 2014-06-23 | 2015-07-17 |  | Highland | 1280423 | 229577 | 0 | 160.05 | 0 | 0 | 0 | 229737.05 | 0 | 1510160.05 | 0 | [6 empty] | CM_WSNI | 100%
503365 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-13 | 2022-11-04 | 2023-03-03 | 2024-02-28 | 2024-05-30 | Highland | 0 | 0 | 0 | 0 | 20233.02 | 15161.74 | 29258.88 | 64653.64 | 7955579.33 | 8020232.97 | 148885.7057 | [6 empty] | WG1 | 100%
400486 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | MS5 | 2001-02-25 | 2005-01-21 | 2005-02-21 | 2018-10-08 | 2018-10-08 | Highland | 1195.74 | 75.23 | 0 | 0 | 0 | 0 | 0 | 75.23 | 0 | 1270.97 | 0 | [6 empty] | WG1 | 100%
404108 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-03-04 | 2016-03-03 | 2016-03-03 | 2016-03-03 | 2016-03-03 | Scottish Water Wide | 50000 | 1219.51 | 0 | 0 | 0 | 0 | 0 | 1219.51 | 0 | 51219.51 | 0 | [6 empty] | CM_M&G | 100%
500624 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 5728557.08 | 5006873.51 | 10092169.84 | 10310257.531 | 0 | 0 | 31137857.961 | 0 | 31137857.961 | 0 | [6 empty] | CM_OVH | 100%
502288 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS6 | 2016-09-15 | 2016-12-20 | 2017-01-16 | 2018-01-18 | 2018-01-18 | Scottish Water Wide | 0 | 0 | 21380.91 | 16985.9225 | 905.9475 | 0 | 0 | 39272.78 | 0 | 39272.78 | 0 | [6 empty] | CM_WSNI | 17.17% | CM_WWNI | 82.83%
502237 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2016-08-18 | 2017-03-23 | 2017-05-15 | 2019-06-03 | 2019-06-04 | Scottish Water Wide | 0 | 0 | 30207.82 | 179639.03 | 30883.71 | 11227.8 | 0 | 251958.36 | 0 | 251958.36 | 0 | [6 empty] | CM_WWNI | 31.93% | CM_WSNI | 68.07%
502238 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2016-08-18 | 2017-03-30 | 2017-06-26 | 2019-06-07 | 2019-06-07 | Scottish Water Wide | 0 | 0 | 33520.74 | 118436.78 | 142538.21 | 105205.62 | 0 | 399701.35 | 0 | 399701.35 | 0 | [6 empty] | CM_WWNI | 29.7% | CM_WSNI | 70.3%
502239 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2016-08-18 | 2017-03-28 | 2017-06-05 | 2020-01-09 | 2020-04-09 | Scottish Water Wide | 0 | 0 | 26143.22 | 136793.19 | 108175.33 | 83018.91 | 13919.99 | 368050.64 | 0 | 368050.64 | 0 | [6 empty] | CM_WWNI | 13.3% | CM_WSNI | 86.7%
035821 | Q&S3A | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2007-05-09 | 2007-06-26 | 2007-07-16 | 2015-12-21 | 2015-10-13 | Scottish Water Wide | 4687190 | -200.12 | 0 | 0 | 0 | 0 | 0 | -200.12 | 0 | 4686989.88 | 0 | [6 empty] | DW14 | 100%
404017 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-01-06 | 2015-01-06 | 2015-01-06 | 2017-11-08 |  | Scottish Water Wide | 15000 | 10000 | -3024.24 | 0 | 0 | 0 | 0 | 6975.76 | 0 | 21975.76 | 0 | [6 empty] | CM_WSNI | 50% | CM_WWNI | 50%
401200 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2010-08-19 | 2012-12-10 | 2013-01-22 | 2014-12-01 |  | Scottish Water Wide | 250819.49 | 98.85 | 0 | 0 | 0 | 0 | 0 | 98.85 | 0 | 250918.34 | 0 | [6 empty] | CM_WSNI | 100%
401199 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2010-08-19 | 2011-03-01 | 2011-04-25 | 2015-11-20 |  | Scottish Water Wide | 1149804 | 12077.72 | 120 | 0 | 0 | 0 | 0 | 12197.72 | 0 | 1162001.72 | 0 | [6 empty] | CM_WSNI | 100%
401201 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2010-08-19 | 2011-02-28 | 2011-04-01 | 2016-02-25 |  | Scottish Water Wide | 658829.62 | 1493.55 | 0 | 0 | 0 | 0 | 0 | 1493.55 | 0 | 660323.17 | 0 | [6 empty] | CM_WSNI | 100%
500490 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS3 | 2015-06-05 | 2015-06-05 | 2015-06-25 | 2019-11-29 | 2019-11-29 | Scottish Water Wide | 0 | 309469 | 220032.46 | 229508.85 | 203791.53 | 332462.76 | 20053.24 | 1315317.84 | 0 | 1315317.84 | 0 | [6 empty] | CM_WSNI | 100%
500736 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2018-07-12 | 2018-07-12 | Scottish Water Wide | 0 | 29174 | 38482 | 68418 | 6953.36 | 0 | 0 | 143027.36 | 0 | 143027.36 | 0 | [6 empty] | CM_WWNI | 100%
500944 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2015-09-07 | 2015-09-07 | 2015-11-02 | 2016-10-20 | 2016-10-20 | Scottish Water Wide | 0 | 5290 | 21658.54 | 0 | 0 | 0 | 0 | 26948.54 | 0 | 26948.54 | 0 | [6 empty] | CM_WWNI | 100%
501639 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2016-02-15 | 2016-08-29 | 2016-08-29 | 2019-12-13 |  | Scottish Water Wide | 0 | 173356 | 855060.64 | 487281.96 | 788910.87 | 356898.49 | 0 | 2661507.96 | 0 | 2661507.96 | 0 |  |  |  |  | 73550.0004 |  | CM_M&G | 100%
403947 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-10-29 | 2015-05-05 | 2015-05-05 | 2015-09-14 |  | Fife | 96952 | 170635.88 | 0 | 0 | 0 | 0 | 0 | 170635.88 | 0 | 267587.88 | 0 | [6 empty] | CM_M&G | 100%
502721 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2017-05-12 | 2017-05-12 | 2017-06-15 | 2020-06-30 | 2020-06-30 | Scottish Water Wide | 0 | 0 | 0 | 91469.43 | 115461.23 | 97645.41 | 0 | 304576.07 | 0 | 304576.07 | 0 | [6 empty] | CM_WSNI | 100%
402582 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2012-03-15 | 2017-01-23 | 2017-01-23 | 2016-07-01 |  | Scottish Water Wide | 1533818 | 612688 | 53108.1 | 0 | 0 | 0 | 0 | 665796.1 | 0 | 2199614.1 | 0 | [6 empty] | CM_M&G | 100%
403603 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2016-08-15 |  | Scottish Water Wide | 90870 | 1650.61 | 79.88 | 0 | 0 | 0 | 0 | 1730.49 | 0 | 92600.49 | 0 | [6 empty] | CM_WWNI | 100%
400341 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS7 | 2008-11-25 | 2009-07-28 | 2010-07-29 | 2015-02-19 |  | Scottish Water Wide | 8206 | -149.84 | 0 | 0 | 0 | 0 | 0 | -149.84 | 0 | 8056.16 | 0 | [6 empty] | CM_WWNI | 100%
501679 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2016-11-28 | 2017-03-22 | 2017-03-22 | 2018-03-28 | 2018-03-28 | Scottish Water Wide | 0 | 0 | 1014968.9 | 92217.05 | -33.21 | 0 | 0 | 1107152.74 | 0 | 1107152.74 | 0 | [6 empty] | CM_M&G | 100%
403593 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2013-12-03 | 2014-06-17 | 2014-06-17 | 2015-07-24 |  | Fife | 358938.66 | 117815.56 | 0 | 0 | 0 | 0 | 0 | 117815.56 | 0 | 476754.22 | 0 | [6 empty] | CM_M&G | 100%
402690 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2012-06-13 | 2013-02-20 | 2013-03-04 | 2017-04-25 |  | Scottish Water Wide | 299353 | 151221 | 35770.21 | -6265.13 | 0 | 0 | 0 | 180726.08 | 0 | 480079.08 | 0 | [6 empty] | CM_WSNI | 100%
402689 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWMD | Management and General | MS7 | 2012-06-21 | 2013-02-20 | 2013-03-06 | 2017-03-28 |  | Scottish Water Wide | 2574126 | 328317 | -2790.63 | 100.56 | 0 | 0 | 0 | 325626.93 | 0 | 2899752.93 | 0 | [6 empty] | CM_WSNI | 100%
502774 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWD | UWWTD - Works | MS7 | 2017-08-01 | 2017-08-01 | 2017-12-05 | 2017-12-01 | 2018-01-01 | Scottish Borders | 0 | 0 | 0 | 15151.06 | -15151.06 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | EC01A | 100% | bar: Regulatory Outputs OMG-17
403033 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-02-04 | 2014-07-31 | 2014-07-31 | 2015-09-21 |  | Dumfries and Galloway | 1140346 | 320930 | 2799.26 | 7058.45 | 0 | 0 | 0 | 330787.71 | 0 | 1471133.71 | 0 | [6 empty] | CM_WSNI | 100%
500477 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS2 | 2017-07-21 | 2018-11-27 | 2019-06-27 | 2020-03-01 | 2020-06-01 | Dumfries and Galloway | 0 | 13294.54 | 33699.51 | 23994.85 | 12209.8295 | 2851.05 | 939.29 | 86989.0695 | 0 | 86989.0695 | 460483.1872 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
045572 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-01-13 | 2011-09-22 | 2011-05-03 | 2011-12-01 | 2011-03-14 | Dumfries and Galloway | 73079.17 | 314.53 | 0 | 0 | 0 | 0 | 0 | 314.53 | 0 | 73393.7 | 0 | [6 empty] | DW1A | 100%
501299 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-12-02 | 2017-04-25 | 2017-04-25 | 2018-04-18 | 2018-04-18 | Scottish Water Wide | 0 | 93569 | 169065.48 | 45688.39 | 0 | 0 | 0 | 308322.87 | 0 | 308322.87 | 0 | [6 empty] | CM_M&G | 100%
501685 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS0 | 2016-07-19 | 2021-04-30 | 2021-07-20 | 2021-11-25 | 2022-07-22 | South Lanarkshire | 0 | 0 | 5700 | 2000 | 0 | 0 | 0 | 7700 | 61800 | 69500 | 0 | [6 empty] | CM_WWI | 100%
402961 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-09-28 | 2014-12-15 | 2015-09-01 | 2016-01-11 | 2016-01-11 | Perth and Kinross | 235559 | 395012 | -3542.22 | 1016.72 | 0 | 0 | 0 | 392486.5 | 0 | 628045.5 | 229318.7788 | [6 empty] | CS11A | 100%
403273 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-02-01 | 2014-12-05 | 2015-04-13 | 2015-09-29 | 2015-10-01 | Clackmannanshire | 578381 | 685403 | 0.42 | -39152.78 | 0 | 0 | 0 | 646250.64 | 0 | 1224631.64 | 229318.7788 | [6 empty] | CS11 | 100%
403001 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2012-10-04 | 2017-05-08 | 2017-06-30 | 2018-01-17 | 2018-01-17 | Aberdeen City | 1000 | 14585.88 | 16263.12 | 56627 | 3903.9292 | 0 | 0 | 91379.9292 | 0 | 92379.9292 | 0 | [6 empty] | CM_WWI | 100%
502771 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment |  |  | Water |  | SWD | DWQ - Preparing for Future Investment | MS5 | 2017-06-21 | 2019-04-18 | 2019-04-19 | 2020-03-01 | 2020-03-01 | All North Unitary Authorities | 0 | 0 | 0 | 3662.62 | -39.85 | 0 | 0 | 3622.77 | 0 | 3622.77 | 167174.9233 | [6 empty] | DW25PS | 100% | bar: Regulatory Outputs OMG-47
503302 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MSU | 2021-05-11 | 2022-02-07 | 2022-04-26 | 2022-09-09 | 2022-12-12 | East Dunbartonshire | 0 | 0 | 0 | 0 | 51000 | 21942.58 | 24399.11 | 97341.69 | 202658.26 | 299999.95 | 240495.8008 | [6 empty] | CS11A | 100%
503386 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-05-27 | 2023-04-05 | 2023-08-08 | 2024-01-29 | 2024-04-30 | Stirling | 0 | 0 | 0 | 0 | 80052.86 | 0 | 4632.69 | 84685.55 | 60627.74 | 145313.29 | 148885.7057 | [6 empty] | SG1 | 100%
046412 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2009-08-25 | 2011-12-20 | 2011-12-29 | 2011-12-19 |  | Glasgow City | 46611.64 | 1343.85 | 0 | 0 | 0 | 0 | 0 | 1343.85 | 0 | 47955.49 | 0 | [6 empty] | CM_WSNI | 100%
500434 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2015-06-11 | 2017-02-17 | 2017-03-27 | 2017-08-28 | 2017-08-28 | Fife | 0 | 9631 | -379.02 | 33108.925 | 0.005 | 0 | 0 | 42360.91 | 0 | 42360.91 | 0 | [6 empty] | CM_WWI | 100%
045808 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-08 | 2011-02-24 | 2011-04-11 | 2014-03-31 | 2014-03-31 | South Lanarkshire | 1668302.47 | 5850.63 | -7830.11 | 0 | 0 | 0 | 0 | -1979.48 | 0 | 1666322.99 | 7917.2968 | [6 empty] | CM_WWNI | 10% | WQ01C | 90%
500185 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2015-12-02 | 2016-01-11 | 2017-05-01 | 2017-07-01 | Highland | 0 | 55719 | 164000.19 | 18344.09 | 0 | 0 | 0 | 238063.28 | 0 | 238063.28 | 72474.3726 | [6 empty] | CS11 | 47.31% | CS16D | 52.69% | bar: Regulatory Outputs OMG-22
502284 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-07-13 | 2017-02-24 | 2017-02-24 | 2017-07-03 |  | Scottish Water Wide | 0 | 0 | 449768.03 | 74721.03 | 0 | 0 | 0 | 524489.06 | 0 | 524489.06 | 0 | [6 empty] | CM_M&G | 100%
502124 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS3 | 2016-03-25 | 2017-04-04 | 2017-04-04 | 2019-10-01 |  | Scottish Water Wide | 0 | 36200.61 | 699080.87 | 675812 | 555790.83 | 426801.52 | 0 | 2393685.83 | 0 | 2393685.83 | 0 |  |  |  |  | 132999.9997 |  | CM_M&G | 100%
502219 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2016-04-29 | 2017-03-30 | 2017-03-30 | 2017-03-03 | 2017-03-03 | Scottish Water Wide | 0 | 0 | 91554.02 | 0 | 0 | 0 | 0 | 91554.02 | 0 | 91554.02 | 0 | [6 empty] | CM_M&G | 100%
501308 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2019-06-03 | 2016-02-17 | Scottish Water Wide | 0 | 341940 | 956278.05 | 785286.34 | 307441.51 | 172960.62 | 0 | 2563906.52 | 0 | 2563906.52 | 0 | [6 empty] | CM_M&G | 100%
502351 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWD | Management and General | MS7 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2017-02-02 | 2016-12-12 | Scottish Water Wide | 0 | 0 | 457663.94 | 0 | 0 | 0 | 0 | 457663.94 | 0 | 457663.94 | 0 | [6 empty] | CM_M&G | 100%
501540 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-04-01 | 2021-12-06 | 2022-04-08 | 2022-08-18 | 2022-11-18 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126077.01 | 126077.01 | 0 | [6 empty] | CM_WSNI | 100%
502432 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2017-03-21 | 2019-05-22 | 2019-05-22 | 2019-05-22 | 2019-05-22 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 166.63 | 340.64 | 0 | 0 | 507.27 | 0 | 507.27 | 0 | [6 empty] | DW25T | 100%
502310 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS6 | 2015-04-27 | 2016-09-30 | 2018-02-21 | 2018-07-01 | 2018-10-01 | Argyll and Bute-Cowal & Bute | 0 | 0 | 8967.13 | 44642.05 | 60990.03 | 204.24 | 57.79 | 114861.24 | 0 | 114861.24 | 0 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
502431 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS0 | 2017-04-06 | 2019-05-22 | 2019-05-22 | 2019-05-22 | 2019-05-22 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0.02 | 0 | 85.16 | 1 | 0 | 86.18 | 0 | 86.18 | 0 | [6 empty] | DW25T | 100%
502575 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2021-06-04 | 2021-12-06 | 2022-02-16 | 2023-01-26 | 2023-04-28 | Argyll and Bute-Cowal & Bute | 0 | 0 | 20930.23 | 276.28 | 6167.27 | 10423.35 | 10382.94 | 48180.07 | 951858.35 | 1000038.42 | 148885.7057 | [6 empty] | WG1 | 100%
500181 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-12-19 | 2016-12-20 | 2017-01-01 | 2017-02-01 | Clackmannanshire | 0 | 13425 | 5203 | -5389.94 | 0 | 0 | 0 | 13238.06 | 0 | 13238.06 | 84921.3452 | [6 empty] | EC01D | 100% | bar: Regulatory Outputs OMG-23
501156 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-07-11 | 2018-12-20 | 2019-02-04 | 2020-04-14 | 2020-06-16 | Clackmannanshire | 0 | 0 | 148181.94 | 252197.65 | 461532.27 | 1288535.74 | 78929.5 | 2229377.1 | 11450.62 | 2240827.72 | 0 | [6 empty] | CM_WWNI | 100%
503305 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-03-23 | 2023-09-12 | 2024-01-11 | 2025-01-06 | 2025-04-08 | Clackmannanshire | 0 | 0 | 0 | 0 | 24921.031 | 0 | 0 | 24921.031 | 0 | 24921.031 | 148885.7057 | [6 empty] | SG1 | 100%
403131 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-11-30 | 2013-09-17 | 2014-01-21 | 2014-11-01 | 2015-03-01 | Argyll and Bute-North Argyll | 310492 | 2000 | 5259.41 | 0 | 0 | 0 | 0 | 7259.41 | 0 | 317751.41 | 146759001.7953 | [6 empty] | CM_WWNI | 100% | bar: Regulatory Outputs OMG-17
500900 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS3 | 2015-11-18 | 2017-02-27 | 2017-02-27 | 2020-04-20 | 2020-04-21 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 186.92 | 0 | 0 | 186.92 | 0 | 186.92 | 0 | [6 empty] | DW25D | 100%
500910 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2017-03-15 | 2017-03-23 | 2017-03-23 | 2019-11-01 | 2020-05-01 | Argyll and Bute-North Argyll | 0 | 16704 | 7033.02 | 574.14 | 2382 | 0 | 0 | 26693.16 | 0 | 26693.16 | 466391.8995 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
500902 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS5 | 2016-03-30 | 2016-03-30 | 2016-03-30 | 2018-03-01 | 2018-03-01 | Argyll and Bute-North Argyll | 0 | 83.72 | -83.72 | 123.03 | 0 | 0 | 0 | 123.03 | 0 | 123.03 | 1777.3932 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
501199 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2016-07-13 | 2017-08-23 | 2017-09-25 | 2022-01-11 | 2022-01-11 | Argyll and Bute-North Argyll | 0 | 0 | 42762.22 | 95686.73 | 32236.48 | 28005.78 | 3.17 | 198694.38 | 339809.68 | 538504.06 | 0 | [6 empty] | CM_WSNI | 100%
404033 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS3 | 2009-03-12 | 2012-11-01 | 2013-11-20 | 2019-07-22 | 2019-08-26 | Argyll and Bute-North Argyll | 26875 | 289842.67 | 3007982.5 | 1834478.49 | 1087259 | 57376.87 | 7182.93 | 6284122.46 | 5514.43 | 6316511.89 | 1848054.6 |  |  |  |  | 64160.0004 |  | DW23 | 30.5% | WG1 | 69.5%
403165 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-01-07 | 2014-07-28 | 2014-07-23 | 2014-05-16 | 2014-05-16 | Argyll and Bute-North Argyll | 63442.19 | 1452 | 0 | 0 | 0 | 0 | 0 | 1452 | 0 | 64894.19 | 0 | [6 empty] | CM_WSI | 100%
500912 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-09-01 | 2016-09-01 | Argyll and Bute-North Argyll | 0 | 6480 | -3258.38 | 231.9 | 0 | 0 | 0 | 3453.52 | 0 | 3453.52 | 0 | [6 empty] | DW25D | 100% | bar: Regulatory Outputs OMG-05
500882 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2016-11-02 | 2018-09-21 | 2018-11-20 | 2019-09-30 | 2020-10-01 | Na H-Eileanan an Iar | 0 | 5113.05 | 7883.52 | 18934.79 | 109738.09 | 34727.4 | 27166.33 | 203563.18 | 0 | 203563.18 | 427951.3829 | [6 empty] | DW5FS | 100%
404134 | Q&S3B | Completion | OMG180 |  |  | Water |  | NONINF | OMG180 | MS3 | 2016-03-31 | 2018-12-20 | 2018-12-21 | 2020-06-01 | 2020-09-01 | Highland | 0 | 0 | 0 | 500250.07 | 1803305.64 | 2255495.48 | 146763.35 | 4705814.54 | 30606.07 | 4736420.61 | 0 |  |  |  |  | 219279.9996 |  | DW25 | 100% | bar: Regulatory Outputs OMG-03
404103 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWD | OMG180 | MS7 | 2016-03-31 | 2018-01-23 | 2017-12-12 | 2017-12-12 | 2017-12-20 | Highland | 0 | 22912.75 | -22912.75 | 6776.6455 | 0.0045 | 0 | 0 | 6776.65 | 0 | 6776.65 | 0 | [6 empty] | DW25 | 100%
503527 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MSU | 2021-06-15 | 2023-01-23 | 2023-05-26 | 2024-08-15 | 2024-11-15 | Highland | 0 | 0 | 0 | 0 | 59441.86 | 72711.51 | 57689.93 | 189843.3 | 1869598.3 | 2059441.6 | 148885.7057 | [6 empty] | SG1 | 100%
502576 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-18 | 2027-07-22 | 2027-10-05 | 2028-09-13 | 2028-12-14 | Highland | 0 | 0 | 20930.23 | 671.6785 | 2160.9015 | 12352.56 | 12304.68 | 48420.05 | 4951579.8 | 4999999.85 | 148885.7057 | [6 empty] | WG1 | 100%
403588 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-09-17 | 2013-10-14 | 2013-11-08 | 2015-02-12 |  | Moray | 264315 | 20484.38 | 151.33 | 64.22 | 0 | 0 | 0 | 20699.93 | 0 | 285014.93 | 0 | [6 empty] | CM_WSI | 100%
501201 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-04-01 | 2022-11-04 | 2023-03-09 | 2024-05-23 | 2024-08-23 | Aberdeenshire | 0 | 14830.71 | 0 | 0 | 0 | 0 | 0 | 14830.71 | 0 | 14830.71 | 0 | [6 empty] | CM_WSNI | 100%
501736 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2022-07-25 | 2023-05-10 | 2023-09-13 | 2024-01-23 | 2024-04-24 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000.01 | 100000.01 | 0 | [6 empty] | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 33.33% | CM_WSI | 42.86%
502387 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MS7 | 2018-12-18 | 2018-12-18 | 2019-02-04 | 2019-02-21 | 2019-02-21 | Highland | 0 | 0 | 0 | 0 | 856598.13 | 0 | 0 | 856598.13 | 0 | 856598.13 | 587726.5342 | [6 empty] | WG5 | 100%
031091 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-29 | 2010-11-01 | 2011-02-01 | 2014-01-07 | 2014-01-24 | West Lothian | 3119049.89 | 154475.41 | 11385.81 | 0 | 0 | 0 | 0 | 165861.22 | 0 | 3284911.11 | 31762 | [6 empty] | EC10A | 10% | EC04A | 90%
403427 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-04-03 | 2013-09-24 | 2013-09-30 | 2015-01-07 |  | West Lothian | 793801 | 14217 | -3705.55 | 0 | 0 | 0 | 0 | 10511.45 | 0 | 804312.45 | 0 | [6 empty] | CM_WSI | 100%
045543 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-06-29 | 2012-03-27 | 2012-11-12 | 2014-02-21 | 2014-02-25 | Aberdeenshire | 1096857.19 | 22714.05 | 0 | 0 | 0 | 0 | 0 | 22714.05 | 0 | 1119571.24 | 121969.6014 | [6 empty] | CM_WWNI | 20% | WQ01 | 80%
500883 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-10-06 | 2018-09-18 | 2018-11-19 | 2019-03-01 | 2019-11-01 | Argyll and Bute-North Argyll | 0 | 1899.35 | 8208.97 | 11362.09 | 42833.48 | 14567.48 | 0 | 78871.37 | 0 | 78871.37 | 124876.8571 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 18.37
502371 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-04-02 | 2022-05-23 | 2022-09-23 | 2024-04-18 | 2024-07-19 | Argyll and Bute-North Argyll | 0 | 0 | 10046.51 | 410.1 | 1489.68 | 0 | 0 | 11946.29 | 0 | 11946.29 | 0 | [6 empty] | CM_WSNI | 100%
500901 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-12-22 | 2017-03-01 | 2017-03-01 | 2017-12-01 | 2017-12-01 | Argyll and Bute-North Argyll | 0 | 3139.53 | 0 | 451.11 | 0 | 0 | 0 | 3590.64 | 0 | 3590.64 | 466391.8995 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
502374 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2022-04-29 | 2024-04-23 | 2024-08-20 | 2025-12-22 | 2026-03-20 | Argyll and Bute-North Argyll | 0 | 0 | 8583.6 | 1212.876 | 13318.804 | 70044.18 | 69772.69 | 162932.15 | 11840828.53 | 12003760.68 | 148885.7057 | [6 empty] | WG1 | 100%
503551 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MSU | 2019-05-01 | 2019-06-03 | 2019-06-10 | 2019-07-19 | 2019-10-21 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 19999.99 | 0 | 19999.99 | 0 | 19999.99 | 148885.7057 | [6 empty] | SG1 | 100%
503562 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MSU | 2019-05-01 | 2020-10-19 | 2021-02-24 | 2022-02-08 | 2022-05-11 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 121455.89 | 394816.84 | 516272.73 | 983727.26 | 1499999.99 | 148885.7057 | [6 empty] | SG1 | 100%
502279 | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater |  | SWMD | Sludge | MS6 | 2017-06-16 | 2018-03-21 | 2018-05-28 | 2018-11-01 | 2019-01-01 | Highland | 0 | 0 | 21819.82 | 72449.5975 | 69587.6825 | 302.1 | 159.24 | 164318.44 | 0 | 164318.44 | 205929.1173 | [6 empty] | LA01 | 100% | bar: Regulatory Outputs OMG-24
500842 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS5 | 2015-10-28 | 2017-03-23 | 2017-04-25 | 2017-06-01 | 2018-03-01 | Highland | 0 | 3000 | 10403.97 | 11972.43 | 12450.16 | 700.45 | 0 | 38527.01 | 0 | 38527.01 | 13337.3267 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 4.07
500903 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2017-02-27 | 2017-03-16 | 2017-03-16 | 2017-07-01 | 2017-07-01 | Highland | 0 | 2160 | 2171.48 | -792.99 | 0 | 0 | 0 | 3538.49 | 0 | 3538.49 | 466391.8995 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
046826 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-19 | 2012-06-20 | 2012-11-19 | 2015-03-31 | 2015-03-31 | Highland | 7865477.59 | 387478.79 | 10084.71 | -15946.3035 | 0.0035 | 0 | 0 | 381617.2 | 0 | 8247094.79 | 386275.0001 | [6 empty] | WG4 | 20.04% | DW23 | 79.96%
402676 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS1 | 2012-06-19 | 2020-01-13 | 2020-03-09 | 2021-05-03 | 2021-05-03 | Falkirk | 236252 | 112617 | 7437.6 | 14127.4 | 71434.5 | 161173.82 | 1645796.32 | 2012586.64 | 79354.98 | 2328193.62 | 0 | [6 empty] | SG1 | 100%
403613 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-05-21 | 2014-05-21 | 2014-05-21 | 2015-03-12 |  | Scottish Water Wide | 4546746 | -55361.66 | 0 | 0 | 0 | 0 | 0 | -55361.66 | 0 | 4491384.34 | 0 | [6 empty] | CM_M&G | 100%
502973 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS0 | 2018-06-18 | 2022-01-21 | 2022-04-08 | 2022-11-09 | 2023-02-09 | East Ayrshire | 0 | 0 | 0 | 13214.185 | 6301.352 | 0 | 0 | 19515.537 | 565986.13 | 585501.667 | 0 | [6 empty] | CM_WWI | 100%
403411 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2013-03-04 | 2013-03-04 | 2013-04-01 | 2016-02-02 |  | Scottish Water Wide | 27297.44 | 5940 | 0 | 0 | 0 | 0 | 0 | 5940 | 0 | 33237.44 | 0 | [6 empty] | WSI | 0.25% | WSNI | 0.25% | WWNI | 0.25% | WWI | 99.25%
501327 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS4 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2019-03-04 | 2018-02-12 | Scottish Water Wide | 0 | 0 | 90592.02 | 409407.98 | 365980.55 | 0 | 0 | 865980.55 | 0 | 865980.55 | 0 | [6 empty] | CM_M&G | 100%
050032 | Q&S4 | Sustaining existing high service for customers | Transformation Demonstrators |  |  | General |  | SWD | Transformation Demonstrators | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 4000000 | 0 | 4000000 | 0
402152 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-06-13 | 2011-08-08 | 2011-09-12 | 2013-10-08 |  | Scottish Water Wide | 1843533.56 | 3.59 | 0 | 0 | 0 | 0 | 0 | 3.59 | 0 | 1843537.15 | 0 | [6 empty] | CM_WSNI | 100%
401431 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2010-09-24 | 2011-11-04 | 2012-02-01 | 2015-11-20 |  | Scottish Water Wide | 279973 | -2103.28 | 0 | 0 | 0 | 0 | 0 | -2103.28 | 0 | 277869.72 | 0 | [6 empty] | CM_WSNI | 100%
503253 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2021-04-07 | 2021-04-12 | 2021-04-19 | 2021-05-28 | 2021-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 1496070.64 | 811858.34 | 376382.83 | 2684311.81 | 3188.16 | 2687499.97 | 0 | [6 empty] | CM_WSNI | 100%
503065 | IR18 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-04-19 | 2018-06-21 | 2018-06-21 | 2019-08-01 | 2019-08-01 | All East Unitary Authorities | 0 | 0 | 0 | 53891.195 | 2011256.735 | 434852.07 | 0 | 2500000 | 0 | 2500000 | 0 | [6 empty] | CM_WSI | 20% | CM_WSNI | 80%
503066 | IR18 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-04-19 | 2018-06-21 | 2018-06-21 | 2019-08-01 | 2019-08-01 | All North Unitary Authorities | 0 | 0 | 0 | 18837.21 | 306326.12 | 174836.69 | 0 | 500000.02 | 0 | 500000.02 | 0 | [6 empty] | CM_WSI | 20% | CM_WSNI | 80%
503067 | IR18 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-04-17 | 2018-06-18 | 2018-06-18 | 2019-08-01 | 2019-08-01 | All South Unitary Authorities | 0 | 0 | 0 | 12558.14 | 741048.22 | 246393.64 | 0 | 1000000 | 0 | 1000000 | 0 | [6 empty] | CM_WSI | 20% | CM_WSNI | 80%
503068 | IR18 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2018-04-17 | 2018-06-18 | 2018-06-18 | 2019-08-01 | 2019-08-01 | All West Unitary Authorities | 0 | 0 | 0 | 12558.14 | 1495718.6 | 241723.26 | 0 | 1750000 | 0 | 1750000 | 0 | [6 empty] | CM_WSI | 20% | CM_WSNI | 80%
503553 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2019-03-25 | 2019-03-25 | 2019-04-01 | 2020-03-30 | 2020-06-22 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 5845650.16 | 1454349.85 | 7300000.01 | 0 | 7300000.01 | 0 | [6 empty] | CM_WSI | 10% | CM_WSNI | 90%
503554 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2019-03-25 | 2019-03-25 | 2019-04-01 | 2020-03-30 | 2020-06-22 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 1761702.79 | 438297.22 | 2200000.01 | 0 | 2200000.01 | 0 | [6 empty] | CM_WSI | 10% | CM_WSNI | 90%
503555 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2019-03-25 | 2019-03-25 | 2019-04-01 | 2020-03-30 | 2020-06-22 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 1441393.2 | 358606.81 | 1800000.01 | 0 | 1800000.01 | 0 | [6 empty] | CM_WSI | 10% | CM_WSNI | 90%
503556 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS2 | 2019-03-25 | 2019-03-25 | 2019-04-01 | 2020-03-30 | 2020-06-22 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 2562476.78 | 637523.22 | 3200000 | 0 | 3200000 | 0 | [6 empty] | CM_WSI | 10% | CM_WSNI | 90%
500238 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-05-07 | 2016-12-14 | 2017-02-28 | 2017-10-23 | 2017-10-23 | City of Edinburgh | 0 | 86983 | 325249 | 422267.63 | 0.37 | 0 | 0 | 834500 | 0 | 834500 | 0 | [6 empty] | CM_WWI | 100%
402824 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-09-14 | 2014-01-30 | 2014-02-24 | 2015-03-25 |  | City of Edinburgh | 209763 | 929 | 925.72 | -4288.08 | 0 | 0 | 0 | -2433.36 | 0 | 207329.64 | 0 | [6 empty] | CM_WWI | 100%
500851 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS6 | 2015-11-04 | 2016-03-25 | 2016-05-24 | 2018-03-01 | 2018-06-01 | Highland | 0 | 1736.99 | 6788.87 | 456.88 | 45638.47 | 423.92 | 0 | 55045.13 | 0 | 55045.13 | 5888.3478 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 33.34
402263 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2011-08-17 | 2013-09-30 | 2013-12-02 | 2014-03-28 | 2014-03-28 | Shetland Islands | 349978.5 | 1181.5 | -214.63 | 0 | 0 | 0 | 0 | 966.87 | 0 | 350945.37 | 0 | [6 empty] | SG1 | 100%
402520 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-02-06 | 2016-02-15 | 2016-02-01 | 2016-02-19 |  | South Ayrshire | 49398.28 | 3152.8 | 0 | 0 | 0 | 0 | 0 | 3152.8 | 0 | 52551.08 | 0 | [6 empty] | CM_WWI | 100%
403550 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-08-02 | 2014-01-15 | 2014-01-15 | 2015-11-05 |  | Dumfries and Galloway | 530000 | 81884.68 | 4940 | 0 | 0 | 0 | 0 | 86824.68 | 0 | 616824.68 | 0 | [6 empty] | CM_WWNI | 100%
500182 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2015-03-20 | 2016-05-27 | 2016-06-20 | 2020-01-17 | 2020-04-15 | Dumfries and Galloway | 0 | 15707 | 39892.66 | 73449.34 | 37250 | 6115.38 | 7585.6 | 179999.98 | 0 | 179999.98 | 116609.9831 | [6 empty] | EC01G | 6.06% | EC01D | 44.79% | CS16D | 49.15%
402881 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS7 | 2012-08-27 | 2017-06-20 | 2017-06-20 | 2017-06-20 |  | Dumfries and Galloway | 235896 | 185439 | 232493.57 | 4132.234 | 419.391 | 0 | 0 | 422484.195 | 0 | 658380.195 | 0 | [6 empty] | CM_WWNI | 100%
402628 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2012-04-16 | 2012-08-08 | 2012-09-28 | 2013-09-16 |  | Dumfries and Galloway | 336759.98 | 466.27 | 0 | 0 | 0 | 0 | 0 | 466.27 | 0 | 337226.25 | 0 | [6 empty] | CM_WWNI | 100%
400605 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | -1577562.8 | 26893.83 | 28990.15 | -113146.2575 | 146799.594 | 0 | 0 | 89537.3165 | 0 | -1488025.4835 | 0 | [6 empty] | OHDS1 | 100%
403896 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-07-29 | 2019-03-28 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 625772.54 | 9696.46 | 0 | 0 | 0 | 0 | 0 | 9696.46 | 0 | 635469 | 0 | [6 empty] | OHDS1 | 50% | OHDW1 | 50%
400479 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 9050647.78 | 14880.53 | -2872.23 | 499.08 | 0 | 0 | 0 | 12507.38 | 0 | 9063155.16 | 0 | [6 empty] | OHDS1 | 100%
403897 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-07-29 | 2019-03-27 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 202665.79 | 185.64 | 0 | 368.78 | 0 | 0 | 0 | 554.42 | 0 | 203220.21 | 0 | [6 empty] | OHDS1 | 50% | OHDW1 | 50%
400541 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 3623275.23 | 7037.13 | 0 | 2651.96 | 0 | 0 | 0 | 9689.09 | 0 | 3632964.32 | 0 | [6 empty] | OHDS1 | 100%
400537 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWD | Non OMG180 | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 1771807.55 | 96120 | 0 | 3306.485 | 0 | 0 | 0 | 99426.485 | 0 | 1871234.035 | 0 | [6 empty] | EC01A | 100%
400477 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 5361088.34 | 0 | 0 | 5182.327 | 0 | 0 | 0 | 5182.327 | 0 | 5366270.667 | 0 | [6 empty] | OHDS1 | 100%
400539 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 23134684.93 | -70104.94 | 611.64 | 0 | 0 | 0 | 0 | -69493.3 | 0 | 23065191.63 | 0 | [6 empty] | OHDS1 | 50% | OHDW1 | 50%
400542 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 3163070.15 | 2136.94 | 0 | 0 | 0 | 0 | 0 | 2136.94 | 0 | 3165207.09 | 0 | [6 empty] | OHDS1 | 100%
400543 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | -63886696.7 | -922004.76 | 0 | 0 | 0 | 0 | 0 | -922004.76 | 0 | -64808701.46 | 0 | [6 empty] | OHDS1 | 100%
400474 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2010-04-01 | 2019-02-05 | 2018-10-08 | 2018-10-08 | 2018-10-08 | Scottish Water Wide | 19124680.68 | 12228.52 | -13293.38 | -4185.27 | 170.32 | 0 | 0 | -5079.81 | 0 | 19119600.87 | 0 | [6 empty] | OHDS1 | 100%
403499 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-06-12 | 2014-03-20 | 2014-03-27 | 2014-11-13 |  | Perth and Kinross | 503061 | 673.32 | 393.91 | 0 | 0 | 0 | 0 | 1067.23 | 0 | 504128.23 | 0 | [6 empty] | CM_WSI | 100%
500852 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS6 | 2015-12-10 | 2016-03-30 | 2016-08-08 | 2017-07-03 | 2018-03-08 | Argyll and Bute-North Argyll | 0 | 6651.26 | 23530.25 | 38979.6033 | 4076.6867 | 4442.33 | 0 | 77680.13 | 0 | 77680.13 | 65565.1831 | [6 empty] | DW5FS | 100%
500573 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS0 | 2015-06-08 | 2019-08-05 | 2019-09-16 | 2020-12-11 | 2021-03-11 | Highland | 0 | 103505 | 155182.55 | 195899.59 | 302107 | 1267703.03 | 6430475.45 | 8454872.62 | 45127.34 | 8499999.96 | 0 | [6 empty] | CM_WSNI | 100%
501111 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | NONINF | Water infrastructure | MS0 | 2017-03-21 | 2021-02-08 | 2021-02-08 | 2021-02-08 | 2021-02-08 | Argyll and Bute-North Argyll | 0 | 36000 | 9752.93 | 96614.05 | 74192.43 | 0.01 | 0 | 216559.42 | 0 | 216559.42 | 0 | [6 empty] | CM_WSI | 100%
500054 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS5 | 2015-02-18 | 2016-11-18 | 2017-06-26 | 2018-09-11 | 2018-09-11 | Argyll and Bute-North Argyll | 0 | 8235 | 40129 | 145882.98 | -30676.99 | 0 | 0 | 163569.99 | 0 | 163569.99 | 0 | [6 empty] | CM_WSI | 100%
502233 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2017-01-25 | 2017-01-25 | Highland | 0 | 0 | 1418228.74 | -20597.01 | 572.75 | 0 | 0 | 1398204.48 | 0 | 1398204.48 | 0 | [6 empty] | CM_WSNI | 100%
046838 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2015-03-27 | 2016-04-01 | 2014-10-24 | 2016-04-01 | Argyll and Bute-North Argyll | 1956538.93 | 776.76 | 142.35 | 0 | 0 | 0 | 0 | 919.11 | 0 | 1957458.04 | 31759.8 | [6 empty] | CM_WSNI | 40% | DW23 | 60%
403862 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | NONINF | Non OMG180 | MS5 | 2014-06-24 | 2015-10-29 | 2016-01-18 | 2019-03-01 | 2019-03-01 | Argyll and Bute-North Argyll | 273058 | 2137845 | 13785345.59 | 11311547.68 | 4309739.19 | -2044783.56 | 82814.42 | 29582508.32 | 4010.12 | 29859576.44 | 7947519.6001 | [6 empty] | DW23 | 40% | CM_WSNI | 60% | bar: Regulatory Outputs OMG-03
501633 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2021-10-07 | 2022-12-14 | 2023-04-18 | 2024-03-26 | 2024-06-26 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529999.99 | 529999.99 | 0 | [6 empty] | CM_WSNI | 100%
046181 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2008-07-21 | 2012-02-20 | 2012-04-24 | 2013-03-15 |  | South Ayrshire | 744283.11 | -187.14 | 0 | 0 | 0 | 0 | 0 | -187.14 | 0 | 744095.97 | 0 | [6 empty] | CM_WWNI | 100%
502409 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2017-07-25 | 2018-12-20 | 2019-03-08 | 2019-07-12 | 2019-10-16 | South Ayrshire | 0 | 0 | 4083.9 | 61710.57 | 282400.53 | 337375.01 | 2344.99 | 687915 | 0 | 687915 | 0 | [6 empty] | CM_WWI | 100%
500889 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2016-11-21 | 2018-09-26 | 2018-11-29 | 2019-09-01 | 2020-10-01 | Falkirk | 0 | 7916.89 | 7696.89 | 11925.39 | 36955.5 | 25452.83 | 19324.51 | 109272.01 | 0 | 109272.01 | 405994.3586 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 34.05
500888 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS7 | 2016-10-06 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Stirling | 0 | 2431.21 | 1345.28 | 1427.16 | -1427.16 | 0 | 0 | 3776.49 | 0 | 3776.49 | 69472.2012 | [6 empty] | DW5FS | 100%
402737 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS1 | 2012-07-23 | 2019-05-27 | 2019-06-03 | 2019-06-04 |  | Stirling | 23500 | 69914.83 | 10224.17 | 93286 | 103890.2 | 569819.27 | 0 | 847134.47 | 0 | 870634.47 | 0 | [6 empty] | CM_WSI | 100%
503525 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2019-04-15 | 2020-03-02 | 2020-05-04 | 2020-11-27 | 2021-03-11 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 126879.12 | 623120.89 | 750000.01 | 0 | 750000.01 | 0 | [6 empty] | CM_WSNI | 100%
502586 | Q&S4 | Protecting and enhancing the environment | Sludge |  |  | Wastewater |  | SWMD | Sludge | MS0 | 2017-12-29 | 2020-06-08 | 2020-10-02 | 2022-01-28 | 2022-05-02 | Perth and Kinross | 0 | 0 | 35216.4 | 42964.4225 | 169993.2875 | 118357.55 | 949023.12 | 1315554.78 | 1126582.17 | 2442136.95 | 2040647.2421 | [6 empty] | LA01 | 100%
500213 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS5 | 2015-03-20 | 2016-03-30 | 2016-05-30 | 2017-03-01 | 2018-06-01 | Aberdeenshire | 0 | 15457 | 15932.34 | 12093.36 | 1400 | 3399.98 | 0 | 48282.68 | 0 | 48282.68 | 127730.0162 | [6 empty] | DW5FS | 100% | bar: Regulatory Outputs OMG-02
500890 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2016-10-13 | 2018-09-26 | 2018-11-30 | 2019-06-28 | 2020-06-26 | Aberdeenshire | 0 | 26600 | 18676.6 | 37000 | 112827.28 | 33584.34 | 14067.44 | 242755.66 | 0 | 242755.66 | 1294401.3524 | [6 empty] | DW5FS | 100%
501195 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-05-06 | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2021-05-24 | Aberdeenshire | 0 | 12679.79 | 1278.36 | 641.93 | 0 | 0 | 0 | 14600.08 | 0 | 14600.08 | 0 | [6 empty] | CM_WSNI | 100%
502731 | Q&S4 | Protecting and enhancing the environment | WFD |  |  | Water |  | SWD | WFD | MS0 | 2018-07-02 | 2020-01-20 | 2020-05-08 | 2020-11-01 | 2021-02-01 | Aberdeenshire | 0 | 0 | 0 | 9566.31 | 5123.95 | 93981.31 | 119328.42 | 227999.99 | 0 | 227999.99 | 131455.2678 | [6 empty] | WR1 | 100% | bar: Regulatory Outputs OMG-20
501002 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-04-01 | 2023-02-15 | 2023-04-20 | 2026-04-30 | 2026-07-31 | Aberdeenshire | 0 | 107967.82 | 12302.74 | 106357.551 | 877424.944 | 0 | 0 | 1104053.055 | 117809161.34 | 118913214.395 | 0 | [6 empty] | CM_WSNI | 100%
503537 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2019-03-19 | 2020-11-09 | 2021-03-08 | 2021-12-23 | 2022-03-24 | Aberdeenshire | 0 | 0 | 0 | 0 | 7001.41 | 13242.67 | 169812.8 | 190056.88 | 530636.12 | 720693 | 0 | [6 empty] | CM_WSNI | 100%
503072 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2019-06-04 | 2021-08-02 | 2021-11-17 | 2023-10-19 | 2024-01-19 | Aberdeenshire | 0 | 0 | 0 | 58430.17 | 6012.6135 | 306737.5 | 778335.14 | 1149515.4235 | 10061129.34 | 11210644.7635 | 0 | [6 empty] | CM_WSNI | 100%
503054 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2018-01-24 | 2018-01-24 | 2018-02-12 | 2018-12-03 | 2018-12-03 | Aberdeenshire | 0 | 0 | 0 | 1454419.03 | 905667.32 | 513.93 | 511.93 | 2361112.21 | 474.07 | 2361586.28 | 0 | [6 empty] | CM_WSNI | 100%
502781 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2017-08-29 | 2017-08-29 | 2017-09-25 | 2019-10-28 | 2019-10-28 | Aberdeenshire | 0 | 0 | 0 | 215793.35 | 101408.15 | 123679 | 1702 | 442582.5 | 3132.49 | 445714.99 | 0 | [6 empty] | CM_WSNI | 100%
501027 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWMD | DWQ Reliability | MS4 | 2016-03-25 | 2017-10-27 | 2018-02-28 | 2018-10-01 | 2019-04-01 | Aberdeenshire | 0 | 18483 | 24190.54 | 166279.82 | 57089.98 | 4877.24 | 257.24 | 271177.82 | 208.19 | 271386.01 | 474534.1812 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
403307 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-04-29 | 2015-08-10 | 2015-07-29 | 2015-07-29 |  | Aberdeenshire | 665889.26 | -4538.14 | 0 | 0 | 0 | 0 | 0 | -4538.14 | 0 | 661351.12 | 0 | [6 empty] | CM_WSNI | 100%
045615 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2010-06-30 | 2011-07-08 | 2013-10-03 | 2014-03-21 | Aberdeenshire | 638026.03 | -2852.39 | 23.73 | 0 | 0 | 0 | 0 | -2828.66 | 0 | 635197.37 | 2334 | [6 empty] | DW1A | 100%
503277 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-01-20 | 2022-06-10 | 2022-10-13 | 2023-10-11 | 2024-01-11 | Moray | 0 | 0 | 0 | 0 | 82034.53 | 12887.28 | 48663.48 | 143585.29 | 0 | 143585.29 | 148885.7057 | [6 empty] | SG1 | 100%
401377 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2011-02-07 | 2014-10-31 | 2015-07-06 | 2015-07-06 | 2015-07-06 | Aberdeenshire | 1239884.83 | -5432.72 | 0 | 0 | 0 | 0 | 0 | -5432.72 | 0 | 1234452.11 | 0 | [6 empty] | SG1 | 30% | CM_WWNI | 70%
045376 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-18 | 2011-09-28 | 2012-02-20 | 2015-02-13 | 2015-09-18 | Scottish Borders | 2959028.28 | 240268.92 | 31454.31 | -4235.02 | -1642.92 | 0 | 0 | 265845.29 | 0 | 3224873.57 | 311388 | [6 empty] | DW23 | 100%
402206 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-08-19 | 2011-10-10 | 2012-01-23 | 2012-09-06 |  | Perth and Kinross | 151129 | 472.01 | 0 | 0 | 0 | 0 | 0 | 472.01 | 0 | 151601.01 | 0 | [6 empty] | CM_WSNI | 100%
402385 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2011-09-27 | 2012-12-07 | 2013-02-18 | 2013-08-30 |  | Aberdeen City | 388655.95 | 122929.4 | 0 | 0 | 0 | 0 | 0 | 122929.4 | 0 | 511585.35 | 0 | [6 empty] | CM_WSNI | 100%
501950 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2016-03-31 | 2019-03-01 | 2019-03-01 | 2020-10-12 | 2020-10-12 | All West Unitary Authorities | 0 | 1942 | 139658.24 | 420963.08 | 329702.78 | 801012.18 | 923523.43 | 2616801.71 | 4585.31 | 2621387.02 | 0 | [6 empty] | CM_WSNI | 100%
500853 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS4 | 2016-04-07 | 2017-03-23 | 2017-05-23 | 2018-11-01 | 2019-09-01 | Stirling | 0 | 1409.4 | 1982.6 | 9674.87 | 3270.82 | 9811.43 | 0 | 26149.12 | 0 | 26149.12 | 12249.4549 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 2.44
500724 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW2 | 2019-05-01 | 2021-12-08 | 2022-04-06 | 2023-03-09 | 2023-06-09 | Aberdeenshire | 0 | 27767.26 | 58914.31 | 81297.3275 | 10654.6885 | 62414.89 | 56623.85 | 297672.326 | 2687172.99 | 2984845.316 | 148885.7057 | [6 empty] | SG1 | 100%
500725 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS0 | 2018-03-27 | 2020-06-01 | 2020-10-05 | 2021-12-27 | 2022-03-25 | Aberdeenshire | 0 | 28907.67 | 51671.7 | 81673.28 | 11458.99 | 288464.94 | 501244.96 | 963421.54 | 630290.41 | 1593711.95 | 148885.7057 | [6 empty] | SG1 | 100%
031251 | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-01-06 | 2010-08-23 | 2010-09-06 | 2014-03-21 | 2014-03-24 | Fife | 8791421 | 4000 | -60245.46 | 0 | 0 | 0 | 0 | -56245.46 | 0 | 8735175.54 | 19752 |  |  |  |  | 10506 |  | EC01 | 50% | EC10 | 50%
037781 | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-11 | 2011-02-24 | 2011-03-07 | 2013-02-07 | 2013-02-26 | North Lanarkshire | 3551162 | -3483.02 | 0 | 0 | 0 | 0 | 0 | -3483.02 | 0 | 3547678.98 | 0 | [6 empty] | EC09 | 50% | EC10 | 50%
031284 | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-08-13 | 2009-10-06 | 2009-09-14 | 2010-03-22 | 2010-06-07 | Renfrewshire | 2610022.19 | 374.85 | 0 | 0 | 0 | 0 | 0 | 374.85 | 0 | 2610397.04 | 0 | [6 empty] | EC01 | 33.33% | EC04 | 33.33% | EC10 | 33.33%
031388 | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-12-21 | 2010-08-23 | 2010-09-20 | 2011-03-24 | 2011-03-25 | South Lanarkshire | 571183.12 | 104.21 | 0 | 0 | 0 | 0 | 0 | 104.21 | 0 | 571287.33 | 0 | [6 empty] | EC04 | 33.21% | EC10 | 33.21% | EC01 | 33.58%
300014 | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2011-01-31 | 2011-10-14 | 2011-10-31 | 2012-03-16 | 2012-03-30 | North Ayrshire | 342236 | -1509.63 | 0 | 0 | 0 | 0 | 0 | -1509.63 | 0 | 340726.37 | 0 | [6 empty] | EC02 | 33% | EC10 | 33% | EC01 | 34%
031412 | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-13 | 2011-03-07 | 2011-07-05 | 2011-11-17 | 2011-12-15 | South Lanarkshire | 665235.75 | 87.58 | 0 | 0 | 0 | 0 | 0 | 87.58 | 0 | 665323.33 | 0 | [6 empty] | EC04 | 33.02% | EC10 | 33.02% | EC01 | 33.96%
031417 | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-13 | 2011-03-07 | 2011-05-20 | 2011-12-15 | 2011-12-15 | South Lanarkshire | 555406 | -772 | 0 | 0 | 0 | 0 | 0 | -772 | 0 | 554634 | 0 | [6 empty] | EC01 | 33.33% | EC04 | 33.33% | EC10 | 33.33%
031426 | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-03-13 | 2011-01-25 | 2011-02-21 | 2012-03-22 | 2012-03-23 | South Lanarkshire | 5037430 | -896.37 | 0 | 0 | 0 | 0 | 0 | -896.37 | 0 | 5036533.63 | 0 | [6 empty] | EC04 | 33.33% | EC10 | 33.33% | EC01 | 33.33%
031429 | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-12-21 | 2010-03-25 | 2010-04-06 | 2011-03-24 | 2011-03-25 | South Lanarkshire | 843318.96 | 87.59 | 0 | 0 | 0 | 0 | 0 | 87.59 | 0 | 843406.55 | 0 | [6 empty] | EC01 | 33.33% | EC04 | 33.33% | EC10 | 33.33%
031439 | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-12-21 | 2010-03-25 | 2010-03-05 | 2010-12-15 | 2010-12-21 | South Lanarkshire | 693080.99 | 104.21 | 0 | 0 | 0 | 0 | 0 | 104.21 | 0 | 693185.2 | 0 | [6 empty] | EC01 | 33.33% | EC04 | 33.33% | EC10 | 33.33%
049514 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWD | OMG180 | MSU | [5 empty] | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11469103.6699 | [6 empty] | EC04B | 100%
403807 | Q&S3B | Completion | OMG180 |  |  | Wastewater |  | SWMD | OMG180 | MS6 | 2014-06-23 | 2015-02-12 | 2015-02-19 | 2018-02-23 | 2018-02-26 | Glasgow City | 262022 | 1248840 | 129327.93 | 171199.43 | 5743.12 | 250 | 0 | 1555360.48 | 0 | 1817382.48 | 1305151.0001 | [6 empty] | EC10B | 100%
031434 | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-02-20 | 2010-01-14 | 2011-11-08 | 2013-10-23 | 2013-12-23 | East Ayrshire | 25070886.8 | 153702.21 | 56789.08 | 1241.2365 | 2293.2 | 0 | 0 | 214025.7265 | 0 | 25284912.5265 | 15866.9997 | [6 empty] | EC02 | 33.33% | EC10 | 33.33% | EC01 | 33.33%
036868 | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-02-20 | 2010-01-14 | 2010-12-08 | 2012-03-16 | 2012-03-30 | East Ayrshire | 15410452.69 | 54051.19 | 30946.28 | 11109.28 | 764.4 | 0 | 0 | 96871.15 | 0 | 15507323.84 | 14974.9998 | [6 empty] | EC10 | 33.33% | EC01 | 33.33% | EC02 | 33.33%
036860 | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-02-21 | 2010-01-14 | 2010-12-08 | 2013-01-31 | 2013-02-26 | North Ayrshire | 24666791 | 23582.35 | 95.13 | 7.41 | 0 | 0 | 0 | 23684.89 | 0 | 24690475.89 | 45486 |  |  |  |  | 18747 |  | EC02 | 33.33% | EC01 | 33.33% | EC10 | 33.33%
403468 | Q&S3A | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2013-07-12 | 2014-06-30 | 2014-08-01 | 2015-12-07 | 2016-01-08 | All West Unitary Authorities | 215071.05 | 99547.95 | 0 | -3911.63 | 0 | 0 | 0 | 95636.32 | 0 | 310707.37 | 52470 | [6 empty] | EC01D | 100%
402611 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-04-24 | 2012-04-24 | 2012-05-29 | 2015-11-20 |  | Scottish Water Wide | 3677107 | 180946 | 123187.85 | 2756.28 | 0 | 0 | 0 | 306890.13 | 0 | 3983997.13 | 0 | [6 empty] | CM_WSI | 100%
500907 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS6 | 2016-01-12 | 2016-03-30 | 2016-03-30 | 2019-07-01 | 2019-08-01 | Highland | 0 | 0.35 | 0 | 8.84 | 407.07 | 0 | 0 | 416.26 | 0 | 416.26 | 466391.8995 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
050031 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MSU | 2019-09-30 | 2021-01-31 | 2021-02-28 | 2021-03-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 558.41
050030 | Q&S3B | Completion | OMG180 |  |  | General |  | SWD | OMG180 | MS3 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 23000000 | 23000000 | 0 | 23000000 | 0 | [6 empty] | SR15_ENV_SGR | 0.00119% | SR15_CEX_STU | 0.007595% | SR15_DWA_PRE | 0.01045% | WG3 | 0.0137% | SR15_DWA_LEAK | 0.02062% | SR15_DWA_EFA | 0.02223% | SR15_SEW_SWO | 0.02556% | SR15_ENV_HABD | 0.03466% | SR15_CCH_CC | 0.04235% | SR15_IR18_IR18 | 0.05059%
500966 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-11-16 | 2016-03-30 | 2016-09-26 | 2017-03-30 | 2017-04-10 | East Ayrshire | 0 | 1087.98 | 218352.27 | 2438.36 | -1209.04 | 0 | 0 | 220669.57 | 0 | 220669.57 | 0 | [6 empty] | CM_WWNI | 100%
031596 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-15 | 2010-12-23 | 2011-02-14 | 2014-03-27 | 2014-05-12 | East Ayrshire | 5374135.85 | 295403.3 | 680174.44 | 372.47 | 0 | 0 | 0 | 975950.21 | 0 | 6350086.06 | 104837.9527 |  |  |  |  | 32779 |  | EC04A | 3.025% | EC10A | 9.188% | CM_WWNI | 32.83% | EC01A | 54.95%
500186 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2016-04-29 | 2016-06-29 | 2018-02-27 | 2018-06-25 | East Ayrshire | 0 | 2000 | 21798.7 | 14298.31 | -865.45 | 0 | 0 | 37231.56 | 0 | 37231.56 | 10362.528 | [6 empty] | EC01G | 46.22% | CS16D | 53.78%
503420 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS0 | 2018-10-31 | 2020-06-22 | 2020-10-19 | 2021-09-14 | 2021-12-13 | Shetland Islands | 0 | 0 | 0 | 0 | 16736.04 | 128260.55 | 336242.87 | 481239.46 | 268760.57 | 750000.03 | 0 | [6 empty] | CM_WSNI | 100%
502568 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2019-05-24 | 2019-06-10 | 2019-06-10 | 2019-06-10 | 2019-06-10 | Shetland Islands | 0 | 0 | 20930.23 | 0 | -20695.43 | 0 | 0 | 234.8 | 0 | 234.8 | 148885.7057 | [6 empty] | SG1 | 100%
046856 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-20 | 2011-03-29 | 2011-09-15 | 2013-02-08 | 2013-02-21 | Shetland Islands | 3933525.59 | -38444.27 | 166.09 | 0 | 0 | 0 | 0 | -38278.18 | 0 | 3895247.41 | 0 | [6 empty] | DW23 | 100%
500672 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS5 | 2015-09-07 | 2016-03-21 | 2016-03-30 | 2018-06-01 | 2019-03-01 | Scottish Water Wide | 0 | 120000 | 608983.33 | 742453.7065 | 200115.9635 | 2447.01 | 0 | 1674000.01 | 0 | 1674000.01 | 0 | [6 empty] | EC06C | 100% | bar: Regulatory Outputs OMG-23
503211 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS5 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-02-04 | 2019-02-04 | Fife | 0 | 0 | 0 | 0 | 25841.58 | 0 | 0 | 25841.58 | 0 | 25841.58 | 148885.7057 | [6 empty] | SG1 | 100%
031598 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2009-04-29 | 2011-06-10 | 2011-09-30 | 2012-03-26 | 2012-04-26 | East Renfrewshire | 268383.52 | 816.3 | 0 | 0 | 0 | 0 | 0 | 816.3 | 0 | 269199.82 | 0 | [6 empty] | SG1 | 3.019% | EC10A | 8.388% | EC04A | 12.58% | CM_WWNI | 76.01%
503304 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-03-07 | 2023-08-25 | 2023-12-28 | 2024-08-21 | 2024-11-21 | East Renfrewshire | 0 | 0 | 0 | 0 | 28480.15 | 18956.77 | 22872.77 | 70309.69 | 71690.02 | 141999.71 | 148885.7057 | [6 empty] | SG1 | 100%
501514 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS3 | 2016-08-19 | 2018-12-20 | 2019-03-15 | 2020-03-06 | 2020-06-05 | East Renfrewshire | 0 | 0 | 69116.28 | 173603.27 | 428299.17 | 540497.49 | 102718.45 | 1314234.66 | 3073.33 | 1317307.99 | 0 | [6 empty] | CM_WWNI | 100%
500109 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS3 | 2015-03-23 | 2017-06-30 | 2017-06-30 | 2020-04-16 | 2020-07-13 | Scottish Water Wide | 0 | 14176 | 83616.52 | 235096.48 | 504047 | 804430.07 | 163046.56 | 1804412.63 | 0 | 1804412.63 | 703082.8878 | [6 empty] | EC01G | 0.1114% | CS16D | 9.192% | EC10H | 45.35% | EC10E | 45.35%
400506 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2010-04-28 | 2011-06-15 | 2011-07-25 | 2012-01-16 |  | South Lanarkshire | 137308.01 | 0 | 0 | 124.77 | 0 | 0 | 0 | 124.77 | 0 | 137432.78 | 0 | [6 empty] | CM_WWNI | 100%
502419 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS3 | 2017-03-30 | 2017-03-30 | 2018-06-01 | 2021-04-30 | 2021-04-30 | Aberdeenshire | 0 | 0 | 0 | 5578.53 | -3090 | 0 | 35550.47 | 38039 | 0 | 38039 | 148885.7057 | [6 empty] | SG1 | 100%
402731 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2012-06-13 | 2012-06-13 | 2012-07-02 | 2015-10-26 |  | Scottish Water Wide | 5168000 | 29924.22 | 0 | 0 | 0 | 0 | 0 | 29924.22 | 0 | 5197924.22 | 0 | [6 empty] | CM_WSI | 100%
500727 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS3 | 2016-01-08 | 2016-03-21 | 2016-03-22 | 2019-02-01 | 2019-02-01 | Scottish Water Wide | 0 | 213282.25 | 99529.75 | -85812 | 43479.38 | 0 | 0 | 270479.38 | 0 | 270479.38 | 144841.4737 | [6 empty] | CS15A | 100%
500187 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2015-03-20 | 2015-12-21 | 2016-02-15 | 2018-04-01 | 2018-07-01 | Fife | 0 | 85850 | 101081.21 | 33947 | 35631.808 | 0 | 0 | 256510.018 | 0 | 256510.018 | 72474.3726 | [6 empty] | CS11 | 45.89% | CS16D | 54.11% | bar: Regulatory Outputs OMG-22
401339 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-13 | 2012-10-31 | 2012-11-29 | 2015-10-15 | 2015-10-15 | Scottish Water Wide | 119774 | -9759.31 | 0 | 0 | 0 | 0 | 0 | -9759.31 | 0 | 110014.69 | 31875 | [6 empty] | CS1 | 100%
003495 | Q&S2 | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2003-05-19 | 2004-02-13 | 2004-05-24 | 2007-12-21 | 2011-03-15 | Scottish Water Wide | 2367792.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2367792.7 | 0 | [6 empty] | EC1/2 | 50% | WQ1/1 | 50%
500096 | Q&S4 | Climate Change | Climate Change |  |  | Wastewater |  | SWD | Climate Change | MS5 | 2015-03-31 | 2017-09-25 | 2017-10-25 | 2018-03-01 | 2019-01-01 | Scottish Water Wide | 0 | 163.55 | 0 | 66297.48 | 5066.529 | 0 | 0 | 71527.559 | 0 | 71527.559 | 34274.2748 | [6 empty] | CC3S | 100% | [18 empty] | Regulatory Outputs OMG-45: 2
402846 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2012-08-15 | 2014-09-04 | 2014-10-20 | 2015-02-11 | 2015-02-11 | South Lanarkshire | 366946 | 87276 | -3771.83 | 0 | 0 | 0 | 0 | 83504.17 | 0 | 450450.17 | 229318.7788 | [6 empty] | CS11 | 100%
500678 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-07-28 | 2021-07-05 | 2021-09-23 | 2022-04-26 | 2022-07-25 | Argyll and Bute-Cowal & Bute | 0 | 23500 | 1339.12 | 4460.88 | 16700 | 32794.28 | 125278.77 | 204073.05 | 402221.97 | 606295.02 | 229318.7788 | [6 empty] | CS11 | 100%
500769 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-07-27 | 2016-07-20 | 2016-10-24 | 2017-08-24 | 2017-08-24 | Moray | 0 | 30000 | 148446 | 74979 | 258.33 | 0 | 0 | 253683.33 | 0 | 253683.33 | 0 | [6 empty] | CM_WWI | 100%
502633 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2017-03-15 | 2018-01-29 | 2018-02-13 | 2018-09-25 | 2018-09-25 | Dumfries and Galloway | 0 | 0 | 2355.14 | 48069.8565 | 299033.0875 | 723.72 | 720.92 | 350902.724 | 555.41 | 351458.134 | 0 | [6 empty] | CM_WWI | 100%
403360 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWMD | Flooding Named | MS7 | 2013-03-04 | 2015-10-15 | 2015-10-15 | 2015-10-15 | 2015-11-02 | South Lanarkshire | 248868 | -248489.1 | 207.4 | 116.69 | 0 | 0 | 0 | -248165.01 | 0 | 702.99 | 72592.956 | [6 empty] | CS11 | 100%
404112 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2015-03-04 | 2015-03-31 | 2015-03-31 | 2016-03-03 |  | Scottish Water Wide | 1174445 | 271.67 | 0 | 0 | 0 | 0 | 0 | 271.67 | 0 | 1174716.67 | 0 | [6 empty] | CM_M&G | 100%
501646 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2016-08-29 | 2017-09-27 | 2017-09-27 | 2019-05-17 | 2019-05-17 | Scottish Water Wide | 0 | 0 | 326336.5 | 1417280.21 | 1716223.4 | 71255.02 | 0 | 3531095.13 | 0 | 3531095.13 | 0 |  |  |  |  | -148191 |  | CM_M&G | 100%
502207 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS6 | 2017-03-31 | 2017-09-26 | 2018-01-08 | 2018-11-30 | 2018-11-30 | Inverclyde | 0 | 0 | 386909.09 | 1405261.71 | 1102047.2 | 0.02 | 608.98 | 2894827 | 0 | 2894827 | 240495.8008 | [6 empty] | CS11A | 100%
503074 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2019-05-01 | 2020-02-24 | 2020-05-08 | 2021-06-04 | 2021-09-06 | Inverclyde | 0 | 0 | 0 | 20930.23 | 25069.77 | 195000.01 | 494322.62 | 735322.63 | 195677.41 | 931000.04 | 240495.8008 | [6 empty] | CS11A | 100%
500664 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | WWINF | Flooding Named | MS0 | 2019-02-08 | 2020-11-30 | 2021-07-02 | 2022-07-18 | 2022-10-20 | South Ayrshire | 0 | 30430 | 49600 | 74891.1001 | 135923.8999 | 79999.93 | 127594.63 | 498439.56 | 223720.45 | 722160.01 | 2666700.415 | [6 empty] | CS11 | 100%
500301 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2019-05-13 | 2019-05-16 | 2019-05-16 | 2019-05-16 | 2019-05-16 | East Ayrshire | 0 | 23813 | 70425.89 | 31649.5651 | 26111.5449 | 58000 | 0 | 210000 | 0 | 210000 | 229318.7788 | [6 empty] | CS11 | 50% | CS15 | 50%
501543 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-07-01 | East Dunbartonshire | 0 | 22930 | 25661.23 | 111223.2746 | 190518.144 | 0 | 0 | 350332.6486 | 0 | 350332.6486 | 229318.7788 | [6 empty] | CS11 | 100%
503538 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | MSU | 2020-05-29 | 2021-05-17 | 2021-08-02 | 2022-03-25 | 2022-06-27 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 50150 | 382011.02 | 432161.02 | 1930838.96 | 2362999.98 | 1460895.4319 | [6 empty] | CS11 | 100%
500302 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS0 | 2018-10-08 | 2019-12-16 | 2020-03-04 | 2020-12-02 | 2021-03-18 | South Lanarkshire | 0 | 58000 | 74971.65 | 44021.6426 | 92898.7074 | 447426.53 | 785679.72 | 1502998.25 | 73189.64 | 1576187.89 | 229318.7788 | [6 empty] | CS11 | 100%
500017 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS1 | 2018-12-07 | 2019-05-20 | 2019-07-02 | 2021-02-11 | 2021-05-13 | East Dunbartonshire | 0 | 35685.64 | 81314.36 | 100000 | 547559 | 1881208.42 | 1701256.53 | 4347023.95 | 200147.95 | 4547171.9 | 1937793.9122 | [6 empty] | CS11 | 100%
501020 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW2 | 2019-09-27 | 2019-10-07 | 2019-10-07 | 2019-10-07 | 2019-10-07 | East Dunbartonshire | 0 | 21930 | 46086 | 73251.052 | 6870.098 | 0 | 0 | 148137.15 | 0 | 148137.15 | 229318.7788 | [6 empty] | CS11 | 100%
502327 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-02-10 | 2021-01-25 | 2021-04-15 | 2021-11-10 | 2022-02-08 | Glasgow City | 0 | 0 | 44060.47 | 27939.53 | 80004.9055 | 54212.77 | 101947.88 | 308165.5555 | 2752162.42 | 3060327.9755 | 240495.8008 | [6 empty] | CS11A | 100%
502375 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2019-12-03 | 2020-10-26 | 2021-03-03 | 2021-10-12 | 2022-01-12 | Glasgow City | 0 | 0 | 0 | 57000 | 58000 | 80900 | 485808.45 | 681708.45 | 820291.55 | 1502000 | 240495.8008 | [6 empty] | CS11A | 100%
502907 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | Glasgow City | 0 | 0 | 0 | 12000 | -756.5959 | 0 | 0 | 11243.4041 | 0 | 11243.4041 | 240495.8008 | [6 empty] | CS11A | 100%
500913 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS0 | 2018-11-22 | 2019-07-29 | 2019-09-18 | 2020-02-20 | 2020-05-28 | Glasgow City | 0 | 341602 | 52835.14 | 33478.8966 | 124988.9634 | 421965.78 | 121887.77 | 1096758.55 | 562.97 | 1097321.52 | 229318.7788 | [6 empty] | CS11 | 100%
502887 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW1 | 2019-09-20 | 2020-09-21 | 2020-11-26 | 2021-07-06 | 2021-10-06 | East Ayrshire | 0 | 0 | 0 | 42398.1446 | 54601.8554 | 37033.69 | 90406.89 | 224440.58 | 75559.38 | 299999.96 | 240495.8008 | [6 empty] | CS11A | 100%
500662 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named |  |  | Wastewater |  | SWD | Flooding Named | GW2 | 2020-12-18 | 2020-12-24 | 2020-12-30 | 2021-01-05 | 2021-01-05 | South Ayrshire | 0 | 23500 | 17530.23 | 28343.4036 | 73626.3664 | 767.99 | 641231.99 | 784999.98 | 0 | 784999.98 | 298221.3137 | [6 empty] | CS11 | 100%
502689 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | GW0 | 2020-03-17 | 2021-03-08 | 2021-05-25 | 2021-12-27 | 2022-03-29 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 58628.2625 | 21598.7375 | 30153.17 | 71828.23 | 182208.4 | 417791.47 | 599999.87 | 240495.8008 | [6 empty] | CS11A | 100%
501191 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-03-13 | 2019-03-13 | 2019-03-13 | 2019-02-25 | 2019-02-25 | North Lanarkshire | 0 | 23611 | 13419.23 | 32525.9087 | 13266.8045 | 0 | 0 | 82822.9432 | 0 | 82822.9432 | 229318.7788 | [6 empty] | CS11 | 100%
502410 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS7 | 2019-03-22 | 2019-03-22 | 2019-03-22 | 2019-02-25 | 2019-02-25 | West Dunbartonshire | 0 | 0 | 12465.12 | 13534.88 | -24650.14 | 0 | 0 | 1349.86 | 0 | 1349.86 | 240495.8008 | [6 empty] | CS11A | 100%
501542 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | WWINF | Flooding Demand Driven | MS0 | 2018-12-17 | 2019-10-07 | 2019-11-18 | 2020-12-16 | 2021-03-16 | Renfrewshire | 0 | 29855 | 48219.66 | 31925.34 | 159371 | 364145.29 | 415067.88 | 1048584.17 | 47700.83 | 1096285 | 469814.5796 | [6 empty] | CS11A | 33.33% | CS11 | 66.67%
500941 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-09-02 | 2017-10-27 | 2017-12-01 | 2018-03-22 | 2018-03-22 | Renfrewshire | 0 | 6000 | 4544 | 102040.47 | 23631.92 | 0 | 0 | 136216.39 | 0 | 136216.39 | 0 | [6 empty] | CM_WWI | 100%
502602 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | SWD | Infra Charge | MSU | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2021-04-14 | 2021-07-07 | East Lothian | 0 | 0 | 0 | 0 | 0 | 219745.33 | 292614.24 | 512359.57 | 95640.45 | 608000.02 | 587726.5342 | [6 empty] | WG5 | 100%
501689 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2018-07-10 | 2018-07-10 | 2018-07-10 | 2019-05-31 | 2019-05-31 | Scottish Water Wide | 0 | 0 | 0 | 0 | 375217.61 | 474756.52 | 0 | 849974.13 | 0 | 849974.13 | 0 |  |  |  |  | 354057.8004 |  | CM_M&G | 100%
500439 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2015-05-15 | 2015-05-15 | 2015-05-15 | 2019-07-04 | 2019-07-04 | All East Unitary Authorities | 0 | 101933 | 804842.88 | 533492.3775 | 281392.8825 | 0 | 0 | 1721661.14 | 0 | 1721661.14 | 0 | [6 empty] | CM_WWNI | 100%
500440 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2015-11-25 | 2015-11-26 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WWNI | 100%
500441 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2016-11-23 | 2017-02-07 | All East Unitary Authorities | 0 | 1095069 | 215104.32 | 126.21 | 0 | 0 | 0 | 1310299.53 | 0 | 1310299.53 | 0 | [6 empty] | CM_WWNI | 100%
500442 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS5 | 2015-05-18 | 2015-05-18 | 2015-05-18 | 2018-12-19 | 2018-12-19 | All East Unitary Authorities | 0 | 711824 | 1420372.47 | 1486222.83 | -600528.4335 | 0 | 0 | 3017890.8665 | 0 | 3017890.8665 | 0 | [6 empty] | CM_WWNI | 100%
500443 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2015-11-26 | 2015-11-26 | All East Unitary Authorities | 0 | 59.06 | 0 | 0 | 0 | 0 | 0 | 59.06 | 0 | 59.06 | 0 | [6 empty] | CM_WWNI | 100%
500444 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-05-17 | 2017-05-17 | All East Unitary Authorities | 0 | 3175049.85 | 703786.15 | 53107.5975 | 0 | 0 | 0 | 3931943.5975 | 0 | 3931943.5975 | 0 | [6 empty] | CM_WWNI | 100%
500445 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2017-02-21 | 2017-02-21 | All North Unitary Authorities | 0 | 108943 | 111609.62 | 3626.2965 | 0 | 0 | 0 | 224178.9165 | 0 | 224178.9165 | 0 | [6 empty] | CM_WWI | 100%
500446 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-09 | 2015-04-09 | 2015-04-09 | 2015-08-03 | 2015-08-21 | All North Unitary Authorities | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [6 empty] | CM_WWI | 100%
500447 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-01-19 | 2017-01-19 | All North Unitary Authorities | 0 | 547194 | 93210.28 | 0 | 0 | 0 | 0 | 640404.28 | 0 | 640404.28 | 0 | [6 empty] | CM_WWI | 100%
500448 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-05-13 | 2015-05-13 | 2015-05-13 | 2017-02-01 | 2017-02-01 | All North Unitary Authorities | 0 | 8420 | 291866.13 | 352.25 | 0 | 0 | 0 | 300638.38 | 0 | 300638.38 | 0 | [6 empty] | CM_WWNI | 100%
500449 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-09 | 2015-04-09 | 2015-04-09 | 2015-08-03 | 2015-08-21 | All North Unitary Authorities | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [6 empty] | CM_WWNI | 100%
500450 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-09 | 2015-04-09 | 2015-04-09 | 2017-01-19 | 2017-01-19 | All North Unitary Authorities | 0 | 694036.16 | 139180.94 | 2332 | 0 | 0 | 0 | 835549.1 | 0 | 835549.1 | 0 | [6 empty] | CM_WWNI | 100%
500451 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-06-02 | 2015-06-02 | 2015-06-08 | 2017-08-10 | 2017-08-10 | All North Unitary Authorities | 0 | 578912 | 466341.71 | 55571.52 | 0 | 0 | 0 | 1100825.23 | 0 | 1100825.23 | 0 | [6 empty] | CM_WWNI | 100%
500452 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-09 | 2015-04-09 | 2015-04-09 | 2015-08-03 | 2015-08-03 | All North Unitary Authorities | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [6 empty] | CM_WWNI | 100%
500453 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-01-19 | 2017-01-19 | All North Unitary Authorities | 0 | 2532790 | 310809.16 | 23984.78 | 0 | 0 | 0 | 2867583.94 | 0 | 2867583.94 | 0 | [6 empty] | CM_WWNI | 100%
500454 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2017-02-20 | 2017-02-20 | All South Unitary Authorities | 0 | 1162069 | 772870.46 | -215007.27 | 0 | 0 | 0 | 1719932.19 | 0 | 1719932.19 | 0 | [6 empty] | CM_WWI | 100%
500455 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-02-07 | 2018-09-26 | All South Unitary Authorities | 0 | 1335925 | -82223.9 | 18645.28 | 0 | 0 | 0 | 1272346.38 | 0 | 1272346.38 | 0 | [6 empty] | CM_WWI | 100%
500456 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-02-07 | 2018-09-26 | All South Unitary Authorities | 0 | 538257 | -538257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WWI | 100%
500457 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2017-02-20 | 2017-02-20 | All South Unitary Authorities | 0 | 768013 | 1402632.3 | 70694.4675 | 4310.56 | 0 | 0 | 2245650.3275 | 0 | 2245650.3275 | 0 | [6 empty] | CM_WWNI | 100%
500458 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2017-02-07 | 2018-09-26 | All South Unitary Authorities | 0 | 565459.64 | 218822.43 | 10099.74 | 0 | 0 | 0 | 794381.81 | 0 | 794381.81 | 0 | [6 empty] | CM_WWNI | 100%
500459 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2017-02-07 | 2018-09-26 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | CM_WWNI | 100%
500460 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2015-06-02 | 2015-06-02 | 2015-06-29 | 2017-03-21 | 2017-03-21 | All South Unitary Authorities | 0 | 2085118 | 1850463.43 | -9132.4315 | 0 | 0 | 0 | 3926448.9985 | 0 | 3926448.9985 | 0 | [6 empty] | CM_WWNI | 100%
500461 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-02-07 | 2018-09-26 | All South Unitary Authorities | 0 | 2596838.58 | 927113.79 | 20053.27 | 18.215 | 0 | 0 | 3544023.855 | 0 | 3544023.855 | 0 | [6 empty] | CM_WWNI | 100%
500462 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2018-09-19 | 2018-09-19 | All South Unitary Authorities | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [6 empty] | CM_WWNI | 100%
401136 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2010-07-01 | 2010-07-01 | 2011-05-02 | 2016-01-13 |  | All North Unitary Authorities | 45998.58 | -6120 | 4602.75 | 0 | 0 | 0 | 0 | -1517.25 | 0 | 44481.33 | 0 | [6 empty] | CM_WWI | 100%
403306 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-02-14 | 2013-11-05 | 2013-11-06 | 2016-01-28 |  | Scottish Water Wide | 637205 | -17916.95 | 16.14 | 0 | 0 | 0 | 0 | -17900.81 | 0 | 619304.19 | 0 | [6 empty] | CM_WWNI | 100%
503150 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS3 | 2018-03-29 | 2018-03-29 | 2018-09-03 | 2019-11-28 | 2019-11-28 | Scottish Water Wide | 0 | 0 | 0 | 0 | 1056012.95 | 1587021.24 | 0 | 2643034.19 | 0 | 2643034.19 | 0 |  |  |  |  | -204000 |  | CM_WWNI | 100%
502777 | Q&S4 | Reducing long term cost of service | Energy efficiency |  |  | Wastewater |  | SWD | Energy efficiency | MSU | 2019-07-01 | 2019-07-01 | 2019-11-25 | 2020-04-06 | 2020-07-07 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0.7 | 0.31 | 1.01 | 0 | 1.01 | 1709913.541 | [6 empty] | I2S_WWNI | 100%
501786 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2022-01-24 | 2023-05-31 | 2023-10-04 | 2024-12-31 | 2025-04-02 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 166795.86 | 166602.59 | 333398.45 | 166601.55 | 500000 | 0 | [6 empty] | CM_WWNI | 100%
402530 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2012-03-09 | 2013-10-29 | 2013-11-08 | 2014-11-28 |  | Scottish Water Wide | 597701 | 20591 | -1379.64 | 0 | 0 | 0 | 0 | 19211.36 | 0 | 616912.36 | 0 | [6 empty] | CM_M&G | 100%
500463 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2018-07-10 | 2018-07-10 | All West Unitary Authorities | 0 | 122076 | 359263.45 | 206931.01 | 7628.77 | 0 | 0 | 695899.23 | 0 | 695899.23 | 0 | [6 empty] | CM_WWI | 100%
500464 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-01-02 | 2017-09-01 | All West Unitary Authorities | 0 | 1131944.59 | 68297.16 | -77608.44 | 0 | 0 | 0 | 1122633.31 | 0 | 1122633.31 | 0 | [6 empty] | CM_WWI | 100%
500465 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-01-16 | 2017-09-01 | All West Unitary Authorities | 0 | 82196 | -60900.49 | 0 | 0 | 0 | 0 | 21295.51 | 0 | 21295.51 | 0 | [6 empty] | CM_WWI | 100%
500466 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2015-05-19 | 2015-05-19 | 2015-05-19 | 2019-05-10 | 2019-05-10 | All West Unitary Authorities | 0 | 106735 | 427628.57 | 285937.5 | -7590.9225 | 1186.84 | 0 | 813896.9875 | 0 | 813896.9875 | 0 | [6 empty] | CM_WWNI | 100%
500467 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | MS7 | 2015-04-13 | 2015-04-13 | 2015-04-13 | 2017-01-17 | 2018-01-17 | All West Unitary Authorities | 0 | 1438300 | 541198.46 | -277.955 | 0 | 0 | 0 | 1979220.505 | 0 | 1979220.505 | 0 | [6 empty] | CM_WWI | 100%
403376 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2013-02-26 | 2013-02-26 | 2013-03-01 | 2017-03-03 |  | All West Unitary Authorities | 6215000 | 675425 | 20377.03 | -41861.475 | 0 | 0 | 0 | 653940.555 | 0 | 6868940.555 | 0 | [6 empty] | CM_WWI | 100%
500468 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-15 | 2015-04-15 | 2015-04-15 | 2017-01-02 | 2018-01-02 | All West Unitary Authorities | 0 | 46252 | -16108.07 | -2439.93 | 0 | 0 | 0 | 27704 | 0 | 27704 | 0 | [6 empty] | CM_WWNI | 100%
500469 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2015-05-20 | 2015-05-20 | 2015-05-20 | 2019-05-15 | 2019-05-15 | All West Unitary Authorities | 0 | 649389 | 1105633.37 | 635561.76 | -33020.57 | 0 | 0 | 2357563.56 | 0 | 2357563.56 | 0 | [6 empty] | CM_WWNI | 100%
500470 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-01-17 | 2018-01-15 | All West Unitary Authorities | 0 | 3903196.55 | 1089666.73 | -1072781.69 | 0 | 0 | 0 | 3920081.59 | 0 | 3920081.59 | 0 | [6 empty] | CM_WWNI | 100%
500471 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MS7 | 2015-04-20 | 2015-04-20 | 2015-04-20 | 2017-01-17 | 2018-01-17 | All West Unitary Authorities | 0 | 305166.13 | 67274.19 | 9826.12 | 0 | 0 | 0 | 382266.44 | 0 | 382266.44 | 0 | [6 empty] | CM_WWNI | 100%
502722 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2019-07-01 | 2019-07-04 | 2019-07-04 | 2019-07-04 | 2019-07-04 | Scottish Water Wide | 0 | 0 | 0 | 259404.713 | 280625.0958 | 132688.89 | 0 | 672718.6988 | 0 | 672718.6988 | 0 | [6 empty] | CM_WWNI | 100%
500065 | Q&S4 | Protecting and enhancing the environment | Scottish Government Requirements |  |  | Wastewater |  | SWD | Scottish Government Requirements | MS7 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | Scottish Water Wide | 0 | 21986.16 | 0 | 0 | 0 | 0 | 0 | 21986.16 | 0 | 21986.16 | 0 | [6 empty] | EC21D | 100%
403771 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS3 | 2014-04-25 | 2014-10-15 | 2014-10-08 | 2020-04-06 |  | Scottish Water Wide | 3034266 | 6061547 | 3222277.44 | 1525021.0955 | 325443.8945 | 105188 | 1207.19 | 11240684.62 | 3792.82 | 14278743.44 | 0 | [6 empty] | CM_M&G | 100%
402052 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-15 | 2014-04-16 | 2014-04-16 | 2015-10-30 |  | Scottish Water Wide | 122490 | 3108.57 | 0 | 0 | 0 | 0 | 0 | 3108.57 | 0 | 125598.57 | 0 | [6 empty] | CM_WSI | 100%
402055 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-15 | 2014-11-03 | 2014-11-03 | 2015-10-30 |  | Scottish Water Wide | 33640 | 8787.44 | 0 | 0 | 0 | 0 | 0 | 8787.44 | 0 | 42427.44 | 0 | [6 empty] | CM_WSI | 100%
402057 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-15 | 2015-11-13 | 2016-02-29 | 2015-10-30 |  | Scottish Water Wide | 5690.39 | -592.93 | 0 | 0 | 0 | 0 | 0 | -592.93 | 0 | 5097.46 | 0 | [6 empty] | CM_WSI | 100%
402049 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-20 | 2015-01-23 | 2015-01-23 | 2015-10-30 |  | Scottish Water Wide | 13453 | -241.04 | 0 | 0 | 0 | 0 | 0 | -241.04 | 0 | 13211.96 | 0 | [6 empty] | CM_WSI | 100%
402050 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-04-15 | 2015-11-13 | 2016-02-01 | 2015-10-30 |  | Scottish Water Wide | 39034.83 | -334.65 | 0 | 0 | 0 | 0 | 0 | -334.65 | 0 | 38700.18 | 0 | [6 empty] | CM_WSI | 100%
401974 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2011-02-15 | 2011-08-02 | 2011-08-02 | 2015-10-30 |  | Scottish Water Wide | 114252.1 | -79.92 | 0 | 0 | 0 | 0 | 0 | -79.92 | 0 | 114172.18 | 0 | [6 empty] | CM_WSI | 100%
502188 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS6 | 2016-08-04 | 2017-04-27 | 2017-05-15 | 2018-02-14 | 2018-02-14 | Scottish Water Wide | 0 | 0 | 72419.76 | 651751.14 | -10067.211 | 0 | 0 | 714103.689 | 0 | 714103.689 | 0 | [6 empty] | CM_WSNI | 9.911% | CM_WWNI | 90.09%
502325 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS6 | 2017-02-27 | 2017-05-23 | 2017-07-19 | 2018-12-18 | 2018-12-18 | Scottish Water Wide | 0 | 0 | 9438.82 | 270716.721 | 221358.009 | 2509.74 | 2490.28 | 506513.57 | 0 | 506513.57 | 0 | [6 empty] | CM_WWNI | 48% | CM_WSNI | 52%
503053 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2018-02-26 | 2018-02-26 | 2018-03-05 | 2018-03-20 | 2018-03-20 | Scottish Water Wide | 0 | 0 | 0 | 291484.71 | 0 | 0 | 0 | 291484.71 | 0 | 291484.71 | 0 | [6 empty] | CM_WSNI | 100%
500431 | Q&S4 | Improving drinking water availability and resilience of service | Efficency Advice |  |  | Water |  | SWD | Efficency Advice | MS3 | 2015-04-02 | 2015-04-02 | 2015-04-02 | 2021-03-31 | 2021-03-31 | Scottish Water Wide | 0 | 118343 | 188916.58 | 139547.49 | 153589.93 | 139000 | 71603 | 811000 | 0 | 811000 | 673005.1466 | [6 empty] | CS18W | 100%
402771 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MS7 | 2012-07-09 | 2014-04-29 | 2014-04-29 | 2016-05-06 | 2016-06-09 | Scottish Water Wide | 1400000 | -48721.45 | 142.35 | 871.72 | 0 | 0 | 0 | -47707.38 | 0 | 1352292.62 | 0 | [6 empty] | CS19 | 100%
503202 | Q&S4 | Improving the customer experience | Customer Experience Studies |  |  | Wastewater |  | SWD | Customer Experience Studies | GW1 | 2019-04-29 | 2019-12-23 | 2020-03-18 | 2020-07-30 | 2020-10-30 | Scottish Water Wide | 0 | 0 | 0 | 0 | 19302.22 | 41336.55 | 38551.04 | 99189.81 | 810.21 | 100000.02 | 1084791.0982 | [6 empty] | CS17_S | 100%
500636 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2015-11-02 | 2015-11-02 | 2015-12-01 | 2020-12-18 | 2021-03-19 | Scottish Water Wide | 0 | 247489 | 928755.72 | 465090.96 | 317056.61 | 130395.56 | 181212.37 | 2270000.22 | 0 | 2270000.22 | 0 | [6 empty] | CM_WSI | 100%
500473 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS4 | 2015-03-31 | 2016-03-01 | 2016-03-14 | 2018-11-01 | 2019-04-01 | City of Edinburgh | 0 | 121378 | 273843.73 | 435256.27 | 550968 | 18553.97 | 0 | 1399999.97 | 0 | 1399999.97 | 203986.9158 | [6 empty] | EC01D | 50% | EC10E | 50% | bar: Regulatory Outputs OMG-23
400113 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2010-02-23 | 2011-01-17 | 2011-01-17 | 2013-03-13 | 2013-05-14 | City of Edinburgh | 338663.04 | 0 | 0 | 1081.74 | 1541.97 | 0 | 0 | 2623.71 | 0 | 341286.75 | 0 | [6 empty] | EC04C | 100%
502764 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS0 | 2017-06-02 | 2020-02-10 | 2021-08-03 | 2022-02-04 | 2022-05-12 | City of Edinburgh | 0 | 0 | 0 | 82811 | 50783 | 74983.89 | 0 | 208577.89 | 303061.44 | 511639.33 | 117578.8269 | [6 empty] | EC01F | 100%
502751 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWD | UWWTD - UID | MS7 | 2017-05-16 | 2017-07-14 | 2017-07-14 | 2017-05-31 | 2017-10-30 | City of Edinburgh | 0 | 0 | 0 | 48304.64 | 0 | 0 | 0 | 48304.64 | 0 | 48304.64 | 117578.8269 | [6 empty] | EC01F | 100%
502740 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS2 | 2017-05-31 | 2019-03-27 | 2020-01-06 | 2020-03-01 | 2020-06-01 | City of Edinburgh | 0 | 0 | 0 | 54066 | 2638 | 45566.88 | 11416.64 | 113687.52 | 778.28 | 114465.8 | 117578.8269 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
502749 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS0 | 2017-10-31 | 2019-10-07 | 2021-03-15 | 2021-11-19 | 2022-03-07 | City of Edinburgh | 0 | 0 | 0 | 125823 | 17418 | 124497.69 | 63552.45 | 331291.14 | 797905.6 | 1129196.74 | 117578.8269 | [6 empty] | EC01F | 100%
502750 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | SWD | UWWTD - UID | MS7 | 2017-10-24 | 2017-12-19 | 2018-01-17 | 2018-01-01 | 2018-05-01 | City of Edinburgh | 0 | 0 | 0 | 42645.34 | 108592.01 | 0 | 0 | 151237.35 | 0 | 151237.35 | 235157.6538 | [6 empty] | EC10B | 50% | EC01F | 50% | bar: Regulatory Outputs OMG-18
502741 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS0 | 2017-06-01 | 2019-09-09 | 2020-08-10 | 2021-01-26 | 2021-04-30 | City of Edinburgh | 0 | 0 | 0 | 113342 | 23332 | 50481.46 | 322446.72 | 509602.18 | 14443.78 | 524045.96 | 117578.8269 | [6 empty] | EC01F | 100%
502742 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS0 | 2017-06-01 | 2019-09-09 | 2020-11-09 | 2021-05-01 | 2021-08-01 | City of Edinburgh | 0 | 0 | 0 | 93222 | 29088 | 57410.13 | 272543.82 | 452263.95 | 121147.97 | 573411.92 | 117578.8269 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
502743 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS0 | 2017-06-02 | 2019-09-09 | 2020-01-06 | 2020-08-01 | 2020-11-01 | City of Edinburgh | 0 | 0 | 0 | 118843 | 64688 | 329233.35 | 347140.88 | 859905.23 | 7058.52 | 866963.75 | 117578.8269 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
502744 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS0 | 2017-06-02 | 2019-10-07 | 2020-01-06 | 2020-07-24 | 2020-10-28 | City of Edinburgh | 0 | 0 | 0 | 101315 | 21298 | 167641.89 | 150890.25 | 441145.14 | 3105.06 | 444250.2 | 117578.8269 | [6 empty] | EC01F | 100%
502745 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS0 | 2017-06-02 | 2019-11-04 | 2020-09-28 | 2021-03-12 | 2021-06-18 | City of Edinburgh | 0 | 0 | 0 | 120424 | 39702 | 66413.22 | 356138.49 | 582677.71 | 16386.82 | 599064.53 | 117578.8269 | [6 empty] | EC01F | 100%
502746 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS0 | 2017-10-30 | 2019-10-07 | 2020-01-06 | 2020-10-02 | 2021-01-18 | City of Edinburgh | 0 | 0 | 0 | 206894 | 109276 | 734494.06 | 993261.15 | 2043925.21 | 0 | 2043925.21 | 117578.8269 | [6 empty] | EC01F | 100%
502747 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS0 | 2017-10-31 | 2019-09-09 | 2020-01-06 | 2020-08-01 | 2020-11-01 | City of Edinburgh | 0 | 0 | 0 | 107885 | 44340 | 379628.56 | 438311.03 | 970164.59 | 0 | 970164.59 | 117578.8269 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
502748 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS0 | 2017-10-30 | 2019-11-04 | 2021-03-22 | 2021-07-01 | 2021-11-01 | City of Edinburgh | 0 | 0 | 0 | 88031 | 28114 | 57323.97 | 10661.01 | 184129.98 | 121441.03 | 305571.01 | 117578.8269 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
502765 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID |  |  | Wastewater |  | WWINF | UWWTD - UID | MS0 | 2017-10-31 | 2020-02-10 | 2020-08-24 | 2021-09-01 | 2022-01-01 | City of Edinburgh | 0 | 0 | 0 | 130610 | 89354 | 196992.87 | 602411.53 | 1019368.4 | 510793.91 | 1530162.31 | 117578.8269 | [6 empty] | EC01F | 100% | bar: Regulatory Outputs OMG-18
503355 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | GW0 | 2019-04-26 | 2020-03-16 | 2020-05-26 | 2021-06-25 | 2021-09-27 | East Ayrshire | 0 | 0 | 0 | 0 | 45627.91 | 1326958.44 | 1878643.8 | 3251230.15 | 1093075.86 | 4344306.01 | 0 | [6 empty] | DW5FS | 100%
503336 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS0 | 2018-06-28 | 2019-11-25 | 2020-01-06 | 2021-01-01 | 2021-02-01 | Highland | 0 | 0 | 0 | 0 | 40498.941 | 1204244.14 | 2124286.45 | 3369029.531 | 31560.5 | 3400590.031 | 1796650.7376 | [6 empty] | DW5MR | 100% | bar: Regulatory Outputs OMG-02
501184 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS7 | 2015-11-04 | 2016-04-12 | 2016-04-18 | 2017-01-01 | 2017-07-01 | Scottish Water Wide | 0 | 3262 | 82693.21 | 8520.775 | 7116.56 | 0 | 0 | 101592.545 | 0 | 101592.545 | 0 | [6 empty] | DW5A | 100% | bar: Regulatory Outputs OMG-47
402613 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2012-03-27 | 2012-03-27 | 2012-05-01 | 2014-08-04 |  | Scottish Water Wide | 9898107.1 | -238 | 0 | 0 | 0 | 0 | 0 | -238 | 0 | 9897869.1 | 0 |  |  |  |  | 156863 |  | CM_WSNI | 100%
403794 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-05-19 | 2014-06-25 | 2014-06-25 | 2015-09-11 |  | Scottish Water Wide | 2005500 | 149372.52 | 0 | 0 | 0 | 0 | 0 | 149372.52 | 0 | 2154872.52 | 0 | [6 empty] | CM_WSNI | 100%
402612 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2012-02-22 | 2012-03-22 | 2012-04-02 | 2015-01-23 |  | All North Unitary Authorities | 269091.86 | 281.81 | 0 | 0 | 0 | 0 | 0 | 281.81 | 0 | 269373.67 | 0 | [6 empty] | CM_WSNI | 100%
500623 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 243588.37 | 549819.68 | 931123.5582 | 1140392.35 | 0 | 0 | 2864923.9582 | 0 | 2864923.9582 | 0 | [6 empty] | CM_OVH | 100%
502673 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-05-18 | 2022-04-01 | 2022-06-16 | 2023-01-12 | 2023-04-14 | Highland | 0 | 0 | 0 | 13509.54 | 1394.34 | 20866.08 | 20785.2 | 56555.16 | 480444.9 | 537000.06 | 0 | [6 empty] | CM_WSI | 100%
502625 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW1 | 2021-05-05 | 2024-12-04 | 2025-02-07 | 2026-01-16 | 2026-04-20 | Highland | 0 | 0 | 20930.23 | 207.95 | 2310.72 | 12029.34 | 11982.71 | 47460.95 | 7953119.09 | 8000580.04 | 148885.7057 | [6 empty] | WG1 | 100%
045573 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-04-27 | 2011-03-11 | 2011-07-22 | 2012-01-16 | 2012-03-14 | Highland | 183693.07 | 76.2 | 0 | 0 | 0 | 0 | 0 | 76.2 | 0 | 183769.27 | 0 | [6 empty] | DW13 | 100%
502433 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS5 | 2018-01-31 | 2018-01-31 | 2018-03-01 | 2019-01-11 | 2019-01-11 | East Renfrewshire | 0 | 0 | 0 | 63084.25 | 373377.58 | -36881.58 | 607.58 | 400187.83 | 1018.93 | 401206.76 | 0 | [6 empty] | CM_WSI | 100%
404104 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2015-03-06 | 2015-12-11 | 2015-12-14 | 2016-01-05 | 2016-01-05 | East Renfrewshire | 19.98 | 340555.88 | 0 | 0 | 0 | 0 | 0 | 340555.88 | 0 | 340575.86 | 0 | [6 empty] | CM_WSI | 100%
403080 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWMD | Strategic Capacity | MS7 | 2012-12-10 | 2014-09-18 | 2014-11-28 | 2015-08-27 | 2015-08-28 | Angus | 829865 | 321825 | 19998.62 | 16318.66 | 0 | 0 | 0 | 358142.28 | 0 | 1188007.28 | 0 | [6 empty] | SG1 | 100%
403636 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-12-30 | 2013-12-30 | 2014-07-02 | 2017-03-06 |  | All West Unitary Authorities | 368488 | 32630 | -3266.53 | -16.72 | 0 | 0 | 0 | 29346.75 | 0 | 397834.75 | 0 | [6 empty] | CM_WSI | 100%
404032 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-12-05 | 2014-12-05 | 2015-01-19 | 2015-11-06 |  | Highland | 153993 | 142499 | -0.05 | -2158.28 | 0 | 0 | 0 | 140340.67 | 0 | 294333.67 | 0 | [6 empty] | CM_WSI | 100%
500766 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS7 | 2015-07-24 | 2016-06-16 | 2016-08-23 | 2017-03-23 | 2017-03-23 | Angus | 0 | 37000 | 336649 | 9353 | 1422.5821 | 0 | 0 | 384424.5821 | 0 | 384424.5821 | 0 | [6 empty] | CM_WWI | 100%
400761 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2010-04-30 | 2010-05-04 | 2010-05-04 | 2015-10-26 |  | Glasgow City | 266000 | -35171.29 | 0 | 0 | 0 | 0 | 0 | -35171.29 | 0 | 230828.71 | 0 | [6 empty] | CM_WSI | 100%
503425 | Q&S4 | Improving drinking water availability and resilience of service | SOSI |  |  | Water |  | SWD | SOSI | MS0 | 2016-03-29 | 2020-03-31 | 2020-04-30 | 2021-07-01 | 2021-10-01 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 62500 | 123780.07 | 477036.91 | 663316.98 | 601227.05 | 1264544.03 | 255781.031 | [6 empty] | WG4 | 100% | bar: Regulatory Outputs OMG-08
401404 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-13 | 2014-03-27 | 2014-05-07 | 2015-12-01 |  | Na H-Eileanan an Iar | 353440 | 44151.24 | 2287.23 | 0 | 0 | 0 | 0 | 46438.47 | 0 | 399878.47 | 0 | [6 empty] | CM_WSI | 100%
500884 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2016-04-07 | 2018-09-26 | 2018-12-11 | 2019-09-30 | 2020-10-02 | Na H-Eileanan an Iar | 0 | 4355.08 | 10309.92 | 9115.35 | 40172.78 | 12448.96 | 10930.79 | 87332.88 | 0 | 87332.88 | 191954.6101 | [6 empty] | DW5FS | 100%
500216 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWD | DWQ Compliance | MS5 | 2015-03-20 | 2016-03-30 | 2016-06-20 | 2017-03-15 | 2018-12-21 | Na H-Eileanan an Iar | 0 | 527.16 | 31842.97 | 28932.81 | 2913.03 | 21684.93 | 0 | 85900.9 | 0 | 85900.9 | 263584.2274 | [6 empty] | DW5FS | 100%
502752 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2024-06-20 | 2025-04-08 | 2025-06-26 | 2026-04-09 | 2026-07-10 | Na H-Eileanan an Iar | 0 | 0 | 0 | 42478.982 | 11674.306 | 380.16 | 378.69 | 54912.138 | 1048051.02 | 1102963.158 | 0 | [6 empty] | CM_WSI | 100%
502619 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW2 | 2021-04-06 | 2021-09-13 | 2021-12-27 | 2022-09-26 | 2022-12-27 | Na H-Eileanan an Iar | 0 | 0 | 20128.53 | 3205.53 | 2009.49 | 859.89 | 856.55 | 27059.99 | 395478.17 | 422538.16 | 0 | [6 empty] | CM_WSI | 100%
402212 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-03-20 | 2013-02-11 | 2013-03-18 | 2014-06-10 |  | Na H-Eileanan an Iar | 595500 | 0 | 956.26 | 0 | 0 | 0 | 0 | 956.26 | 0 | 596456.26 | 0 | [6 empty] | CM_WSNI | 100%
502133 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience |  |  | Water |  | SWD | Supply Resilience | MS7 | 2016-03-24 | 2016-03-29 | 2016-03-29 | 2016-03-01 | 2016-03-01 | Na H-Eileanan an Iar | 0 | 65.42 | 0 | 0 | 0 | 0 | 0 | 65.42 | 0 | 65.42 | 1817908.3275 | [6 empty] | CS16WR | 100% | bar: Regulatory Outputs OMG-07
402207 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-07-13 | 2012-09-13 | 2012-10-31 | 2013-05-20 |  | Highland | 279431 | -1713.3 | 0 | 0 | 0 | 0 | 0 | -1713.3 | 0 | 277717.7 | 0 | [6 empty] | CM_WSI | 100%
031772 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2008-07-08 | 2010-09-20 | 2010-11-29 | 2013-03-29 | 2013-05-14 | Scottish Borders | 1225231.7 | 12387.27 | 0 | 0 | 0 | 0 | 0 | 12387.27 | 0 | 1237618.97 | 0 | [6 empty] | SG1 | 5% | CM_WWNI | 25% | EC10A | 70%
403972 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS0 | 2016-10-04 | 2020-04-20 | 2020-05-26 | 2021-02-11 | 2021-02-12 | Scottish Borders | 9516.54 | 12552.46 | 20498.13 | 1954.36 | 18109.88 | 104940.01 | 946951.88 | 1105006.72 | 13295.46 | 1127818.72 | 0 | [6 empty] | CM_WWNI | 41.25% | SG1 | 58.75%
501100 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works |  |  | Wastewater |  | SWMD | UWWTD - Works | MS3 | 2015-09-30 | 2016-09-27 | 2016-09-29 | 2019-10-01 | 2020-01-01 | West Lothian | 0 | 10169 | 132650.84 | 60055.4965 | 58124.6635 | 54000 | 0 | 315000 | 0 | 315000 | 0 | [6 empty] | EC10D | 100% | [18 empty] | Regulatory Outputs OMG-23: 6
403275 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWMD | Flooding Demand Driven | MS7 | 2013-01-23 | 2014-10-02 | 2014-10-15 | 2015-03-30 | 2015-03-30 | Midlothian | 421690 | 25992 | 8679.56 | -3204.03 | 0 | 0 | 0 | 31467.53 | 0 | 453157.53 | 229318.7788 | [6 empty] | CS11 | 100%
400634 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2010-04-06 | 2013-02-13 | 2013-05-20 | 2014-05-27 |  | All West Unitary Authorities | 123734 | 0 | -1737.84 | 0 | 0 | 0 | 0 | -1737.84 | 0 | 121996.16 | 0 | [6 empty] | CM_WWI | 100%
502257 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2016-09-22 | 2018-06-07 | 2018-11-12 | 2019-07-05 | 2019-10-09 | Scottish Water Wide | 0 | 0 | 52083 | 143590 | 808664 | 55062.01 | 2045 | 1061444.01 | 409 | 1061853.01 | 0 | [6 empty] | CM_WWNI | 100%
502247 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-05-05 | 2022-10-24 | 2023-02-20 | 2024-02-09 | 2024-05-13 | Scottish Water Wide | 0 | 0 | 0 | 23926.389 | 43.716 | 0 | 17363.55 | 41333.655 | 639352.21 | 680685.865 | 0 | [6 empty] | CM_WWNI | 100%
501315 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | NONINF | Wastewater non infrastructure | MS0 | 2016-10-04 | 2020-04-20 | 2020-05-25 | 2023-06-06 | 2023-06-06 | Scottish Water Wide | 0 | 0 | 4043.08 | 52875.44 | 0.005 | 0 | 0 | 56918.525 | 0 | 56918.525 | 0 | [6 empty] | CM_WWNI | 100%
501310 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-12-01 | 2018-01-29 | 2018-02-19 | 2018-05-25 | 2018-05-25 | South Lanarkshire | 0 | 6101 | 129172 | 287073 | 258654 | 0 | 0 | 681000 | 0 | 681000 | 0 | [6 empty] | CM_WWI | 100%
503033 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWD | Wastewater infrastructure | GW1 | 2019-08-16 | 2020-06-01 | 2020-08-20 | 2021-01-08 | 2021-04-12 | Fife | 0 | 0 | 0 | 6768.752 | 16565.968 | 85258.09 | 111432.22 | 220025.03 | 10363.1 | 230388.13 | 0 | [6 empty] | CM_WWI | 100%
500492 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS7 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-25 | 2016-07-31 | West Lothian | 0 | 60228 | 1874.57 | 360 | 0 | 0 | 0 | 62462.57 | 0 | 62462.57 | 148885.7057 | [6 empty] | SG1 | 100%
503228 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-21 | 2023-07-13 | 2023-11-06 | 2024-10-31 | 2025-01-31 | West Lothian | 0 | 0 | 0 | 0 | 78171.442 | 10152.13 | 31434.7 | 119758.272 | 25808.35 | 145566.622 | 148885.7057 | [6 empty] | SG1 | 100%
500771 | Q&S4 | Supporting economic development | Infra Charge |  |  | Water |  | NONINF | Infra Charge | MS3 | 2016-08-31 | 2018-09-12 | 2019-01-08 | 2020-02-06 | 2020-05-08 | Aberdeenshire | 0 | 11045.68 | 92934.07 | 436972.33 | 500389.27 | 1426100.33 | 23684.12 | 2491125.8 | 5338.58 | 2496464.38 | 587726.5342 |  |  |  |  | 2820 |  | WG5 | 100%
402769 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-08-09 | 2014-03-26 | 2014-03-27 | 2014-10-14 |  | Angus | 57695 | 909.09 | 0 | 0 | 0 | 0 | 0 | 909.09 | 0 | 58604.09 | 0 | [6 empty] | CM_WSI | 100%
402716 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-07-03 | 2014-12-05 | 2014-12-16 | 2015-06-25 | 2015-03-27 | Angus | 67572.41 | 3318.57 | 0 | 0 | 0 | 0 | 0 | 3318.57 | 0 | 70890.98 | 2629 | [6 empty] | CS1 | 100%
501704 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2016-11-17 | 2017-05-23 | 2017-07-24 | 2017-09-26 | 2017-09-26 | Fife | 0 | 0 | 11235 | 45926 | 1456.0105 | 0 | 0 | 58617.0105 | 0 | 58617.0105 | 0 | [6 empty] | CM_WWI | 100%
501255 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS0 | 2016-07-29 | 2019-04-15 | 2019-05-14 | 2019-11-07 | 2020-02-13 | Orkney Islands | 0 | 2338 | 89382.98 | 0 | -5994.74 | 0 | 0 | 85726.24 | 0 | 85726.24 | 0 | [6 empty] | CM_WSNI | 100%
500720 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | WWINF | Wastewater non infrastructure | MS3 | 2015-07-07 | 2018-03-28 | 2018-03-29 | 2019-06-19 | 2019-09-23 | Orkney Islands | 0 | 75025 | 33565 | 214114 | 546554 | 44038.01 | 20556.96 | 933852.97 | 0.03 | 933853 | 0 | [6 empty] | CM_WWNI | 100%
500194 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Water |  | SWD | Environmental Studies | MS5 | 2015-03-26 | 2016-09-30 | 2016-10-03 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 5535 | 31508 | 61181.813 | 2889.637 | 0 | 0 | 101114.45 | 0 | 101114.45 | 660565 | [6 empty] | WR1A | 100% | [18 empty] | Regulatory Outputs OMG-23: 8
402618 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2012-03-26 | 2012-10-09 | 2012-10-22 | 2014-12-02 |  | Scottish Water Wide | 632000 | -8000 | -1409.92 | 0 | 0 | 0 | 0 | -9409.92 | 0 | 622590.08 | 0 | [6 empty] | CM_WSNI | 100%
500193 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Water |  | SWD | Environmental Studies | MS5 | 2015-03-20 | 2016-09-29 | 2016-09-29 | 2018-03-29 | 2018-03-29 | Scottish Water Wide | 0 | 8693 | 23241 | 126232.679 | 26517.521 | 0 | 0 | 184684.2 | 0 | 184684.2 | 100856.5233 | [6 empty] | WR2B | 100%
500891 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | WINF | DWQ Reliability | MS3 | 2016-10-19 | 2018-09-21 | 2019-03-18 | 2019-06-01 | 2020-04-01 | Shetland Islands | 0 | 857.04 | 8543.79 | 4347.36 | 30780.99 | 7900.09 | 2154.59 | 54583.86 | 0 | 54583.86 | 42610.1646 | [6 empty] | DW5FS | 100% | [18 empty] | Regulatory Outputs OMG-06: 14.65
403670 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance |  |  | Water |  | SWMD | DWQ Compliance | MS6 | 2014-02-17 | 2016-01-29 | 2016-03-23 | 2018-01-01 | 2018-12-01 | Shetland Islands | 57282.47 | 1497383.53 | 3113151.78 | 495600.34 | 135167.17 | 10100.03 | 0 | 5251402.85 | 0 | 5308685.32 | 3605707.4967 |  |  |  |  | 72080 |  | DW25P | 10% | DW2 | 45% | DW23 | 45% | bar: Regulatory Outputs OMG-01
503245 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | MSU | 2021-04-01 | 2022-02-16 | 2022-06-15 | 2022-10-20 | 2023-01-20 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294433.87 | 294433.87 | 0 | [6 empty] | CM_WWNI | 100%
500687 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS0 | 2015-06-11 | 2020-04-06 | 2020-06-05 | 2021-06-11 | 2021-09-15 | East Renfrewshire | 0 | 6750 | 12029 | 70243 | 79577 | 109596.47 | 685304.94 | 963500.41 | 297011.22 | 1260511.63 | 0 | [6 empty] | CM_WWI | 100%
502823 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2021-08-16 | 2022-07-22 | 2022-11-14 | 2023-11-02 | 2024-02-02 | West Lothian | 0 | 0 | 0 | 74965.673 | 37811.645 | 10147.09 | 11927.82 | 134852.228 | 7147.78 | 142000.008 | 148885.7057 | [6 empty] | SG1 | 100%
503384 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-02-07 | 2022-12-15 | 2023-04-19 | 2023-10-10 | 2024-01-10 | Aberdeenshire | 0 | 0 | 0 | 0 | 66450.701 | 0 | 7726.59 | 74177.291 | 74578.47 | 148755.761 | 148885.7057 | [6 empty] | SG1 | 100%
501200 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS0 | 2018-12-21 | 2019-10-28 | 2019-11-27 | 2021-03-01 | 2021-06-01 | Orkney Islands | 0 | 18092.93 | 30822.63 | 25151.73 | 21899.66 | 306022.34 | 616382.33 | 1018371.62 | 27342.29 | 1045713.91 | 1271477.0703 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
401293 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-10-05 | 2010-10-05 | 2011-02-01 | 2014-02-21 | 2014-03-28 | Angus | 9573350 | 77571 | 35856.42 | 0 | 0 | 0 | 0 | 113427.42 | 0 | 9686777.42 | 109244.7 | [6 empty] | CM_WSI | 1% | DW5 | 99%
401294 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-09-22 | 2010-09-22 | 2011-02-01 | 2014-11-24 | 2015-03-17 | Angus | 7308600.95 | 156462.05 | 13190.64 | 0 | 0 | 0 | 0 | 169652.69 | 0 | 7478253.64 | 130098.5998 | [6 empty] | CM_WSI | 13% | DW5 | 87%
500023 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS6 | 2015-02-13 | 2016-09-12 | 2016-10-31 | 2018-01-26 | 2018-01-26 | Aberdeenshire | 0 | 44644 | 439358 | -93806.505 | 75586.415 | 0 | 0 | 465781.91 | 0 | 465781.91 | 0 | [6 empty] | CM_WSI | 100%
500022 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | WINF | Water infrastructure | MS5 | 2015-02-09 | 2016-09-12 | 2017-06-26 | 2018-03-29 | 2018-03-29 | Aberdeenshire | 0 | 54300 | 68457 | 244187 | 30983.4 | 0 | 0 | 397927.4 | 0 | 397927.4 | 0 | [6 empty] | CM_WSI | 100%
502204 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS3 | 2016-03-24 | 2016-07-06 | 2016-07-06 | 2019-12-01 | 2020-02-01 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0.98 | 0 | 0.98 | 0 | 0.98 | 1206158.4333 | [6 empty] | DW25T | 100% | bar: Regulatory Outputs OMG-05
501232 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | NONINF | DWQ Reliability | MS3 | 2016-03-31 | 2018-08-29 | 2018-09-07 | 2020-09-16 | 2020-12-15 | Angus | 0 | 41788.23 | 395068.88 | 366498.443 | 3637769.777 | 5109421.67 | 713613.55 | 10264160.55 | 77624.23 | 10341784.78 | 2412316.8666 |  |  |  |  | 145599.9996 |  | CM_WSNI | 12.34% | DW25P | 43.83% | DW25T | 43.83%
502194 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability |  |  | Water |  | SWD | DWQ Reliability | MS4 | 2016-03-22 | 2016-03-30 | 2016-03-30 | 2016-03-01 | 2020-01-01 | Angus | 0 | 0 | 0 | 162.6 | 0 | 0 | 0 | 162.6 | 0 | 162.6 | 1206158.4333 | [6 empty] | DW25P | 100% | bar: Regulatory Outputs OMG-04
045613 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2008-05-30 | 2011-05-23 | 2011-05-23 | 2013-05-01 | 2013-12-30 | Angus | 584561.51 | 508.39 | 0 | 0 | 0 | 0 | 0 | 508.39 | 0 | 585069.9 | 1768 | [6 empty] | DW1A | 100%
501220 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS3 | 2016-07-13 | 2018-08-01 | 2018-08-21 | 2020-02-06 | 2020-05-08 | Fife | 0 | 14503.9 | 99600.94 | 236358.2835 | 689280.4165 | 808910.49 | 21259.24 | 1869913.27 | 8240.58 | 1878153.85 | 0 |  |  |  |  | 7659.9997 |  | CM_WSNI | 100%
502899 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS6 | 2017-09-13 | 2017-09-13 | 2017-11-13 | 2018-06-20 | 2018-06-20 | West Lothian | 0 | 0 | 0 | 493590.4 | -44372.64 | 0 | 0 | 449217.76 | 0 | 449217.76 | 0 | [6 empty] | CM_WWI | 100%
403601 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven |  |  | Wastewater |  | SWD | Flooding Demand Driven | MS1 | 2013-10-23 | 2019-12-03 | 2019-12-03 | 2019-12-03 | 2019-12-03 | West Lothian | 56898.06 | 65132.94 | 10973 | 47226.0266 | 41769.9734 | 18302.29 | 22322.81 | 205727.04 | 374.89 | 262999.99 | 229318.7788 | [6 empty] | CS11A | 100%
403870 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWD | Non OMG180 | MSU | [5 empty] | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49808 | [6 empty] | CS1 | 100%
402697 | Q&S3B | Completion | Non OMG180 |  |  | General |  | SWD | Non OMG180 | MS7 | 2012-06-12 | 2015-05-12 | 2015-05-12 | 2015-03-31 |  | Scottish Water Wide | 283342.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283342.07 | 5006 | [6 empty] | CS20 | 100%
402695 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | Water |  | SWMD | Management and General | MS7 | 2012-06-22 | 2013-01-30 | 2013-02-18 | 2015-02-19 |  | Scottish Water Wide | 698495 | 15431.84 | 218.96 | 0 | 0 | 0 | 0 | 15650.8 | 0 | 714145.8 | 0 | [6 empty] | CM_WSNI | 18.17% | CM_WWNI | 81.83%
402680 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | General |  | SWD | Water infrastructure | MS7 | 2012-05-18 | 2016-05-12 | 2015-11-05 | 2015-11-06 |  | Scottish Water Wide | 1414685.71 | -464.72 | 0 | 0 | 0 | 0 | 0 | -464.72 | 0 | 1414220.99 | 0 | [6 empty] | WSI | 25% | WSNI | 25% | WWI | 25% | WWNI | 25%
503262 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2022-01-31 | 2023-07-21 | 2023-11-14 | 2024-11-08 | 2025-02-10 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 77306.64 | 0 | 37563.63 | 114870.27 | 31717.18 | 146587.45 | 148885.7057 | [6 empty] | SG1 | 100%
500222 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS6 | 2015-03-24 | 2016-08-04 | 2016-09-26 | 2018-04-30 | 2018-04-30 | Perth and Kinross | 0 | 89000 | 1291473 | 514159 | 68886 | 0 | 0 | 1963518 | 0 | 1963518 | 0 | [6 empty] | CM_WWI | 100%
402991 | Q&S3B | Completion | Non OMG180 |  |  | Wastewater |  | SWMD | Non OMG180 | MS7 | 2012-10-01 | 2013-03-15 | 2013-06-05 | 2013-10-25 | 2013-10-25 | Glasgow City | 47367 | -264.19 | 0 | 0 | 0 | 0 | 0 | -264.19 | 0 | 47102.81 | 201 | [6 empty] | CM_WWI | 40% | CS11A | 60%
403967 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | NONINF | Strategic Capacity | MS0 | 2018-11-07 | 2020-08-10 | 2020-08-11 | 2022-05-30 | 2022-05-31 | West Lothian | 13556.56 | 21856.44 | 16739.8 | 46917.586 | 134030.924 | 822552.19 | 2830812.86 | 3872909.8 | 15226428.05 | 19112894.41 | 0 | [6 empty] | SG1 | 100%
503045 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | GW0 | 2019-06-03 | 2020-05-18 | 2020-09-02 | 2021-01-19 | 2021-04-21 | West Lothian | 0 | 0 | 0 | 41883.5775 | 12804.5825 | 121430.95 | 742971.89 | 919091 | 80908.93 | 999999.93 | 148885.7057 | [6 empty] | SG1 | 100%
503125 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Wastewater |  | SWD | Strategic Capacity | MS3 | 2018-03-30 | 2018-03-30 | 2018-05-09 | 2019-07-31 | 2019-07-31 | West Lothian | 0 | 0 | 0 | 40000 | 408131.83 | 0 | 0 | 448131.83 | 0 | 448131.83 | 148885.7057 |  |  |  |  | 6999.9996 |  | SG1 | 100%
403866 | Q&S3B | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2014-09-05 | 2014-09-05 | 2014-10-01 | 2014-12-18 |  | Scottish Water Wide | 152356 | 5942.82 | 0 | 0 | 0 | 0 | 0 | 5942.82 | 0 | 158298.82 | 0 | [6 empty] | CM_M&G | 100%
501756 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW0 | 2021-11-08 | 2023-01-20 | 2023-05-25 | 2024-01-03 | 2024-04-04 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 700000 | 0 | [6 empty] | CM_WSNI | 100%
045027 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-12 | 2011-03-29 | 2011-08-29 | 2013-02-28 | 2013-03-18 | Aberdeenshire | 1636912.53 | -93.97 | 0 | 0 | 0 | 0 | 0 | -93.97 | 0 | 1636818.56 | 0 | [6 empty] | DW23 | 100%
503050 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW1 | 2019-06-28 | 2020-05-25 | 2020-08-05 | 2021-09-03 | 2021-12-06 | North Lanarkshire | 0 | 0 | 0 | 27397.67 | 11643.1635 | 427789.24 | 1277148.52 | 1743978.5935 | 874106.56 | 2618085.1535 | 0 | [6 empty] | CM_WSI | 100%
501204 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS5 | 2015-11-06 | 2016-09-30 | 2016-11-21 | 2019-03-15 | 2019-03-15 | South Lanarkshire | 0 | 1415.44 | 87098.37 | 130707.33 | 126394 | 0 | 0 | 345615.14 | 0 | 345615.14 | 0 | [6 empty] | CM_WSNI | 100%
501004 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | Wastewater |  | SWD | Management and General | MS7 | 2015-09-25 | 2015-11-18 | 2016-02-18 | 2018-04-18 | 2018-04-18 | Scottish Water Wide | 0 | 26721 | 49408 | 43204.03 | 0 | 0 | 0 | 119333.03 | 0 | 119333.03 | 0 | [6 empty] | CM_WWNI | 20% | CM_WSNI | 80%
401091 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-04 | 2012-03-27 | 2012-06-14 | 2013-10-09 |  | Highland | 416635 | -172.18 | 0 | 0 | 0 | 0 | 0 | -172.18 | 0 | 416462.82 | 0 | [6 empty] | CM_WSI | 100%
401309 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-04 | 2013-01-11 | 2013-02-12 | 2015-04-03 |  | City of Edinburgh | 1204188 | 84008 | 703.93 | -892.04 | 0 | 0 | 0 | 83819.89 | 0 | 1288007.89 | 0 | [6 empty] | CM_WSI | 100%
401144 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-10-17 | 2012-11-22 | 2012-12-17 | 2013-10-01 |  | Na H-Eileanan an Iar | 689000 | -9347.8 | 0 | 0 | 0 | 0 | 0 | -9347.8 | 0 | 679652.2 | 0 | [6 empty] | CM_WSI | 100%
401099 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-06-28 | 2012-02-22 | 2012-03-26 | 2013-08-20 |  | Highland | 300712.66 | 109.39 | 0 | 0 | 0 | 0 | 0 | 109.39 | 0 | 300822.05 | 0 | [6 empty] | CM_WSI | 100%
401145 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-04 | 2012-04-24 | 2012-07-23 | 2013-03-20 |  | Argyll and Bute-North Argyll | 872842 | 74.54 | 0 | 0 | 0 | 0 | 0 | 74.54 | 0 | 872916.54 | 0 | [6 empty] | CM_WSI | 100%
401100 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-04 | 2012-04-23 | 2012-08-27 | 2013-01-25 |  | Argyll and Bute-North Argyll | 457000 | -1470.72 | 0 | 0 | 0 | 0 | 0 | -1470.72 | 0 | 455529.28 | 0 | [6 empty] | CM_WSI | 100%
401142 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-10-04 | 2013-12-16 | 2014-01-31 | 2015-09-21 |  | Highland | 662164 | 184623 | 3976.26 | 9908.94 | 0 | 0 | 0 | 198508.2 | 0 | 860672.2 | 0 | [6 empty] | CM_WSI | 100%
501734 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | GW0 | 2022-07-25 | 2023-05-10 | 2023-09-13 | 2024-01-23 | 2024-04-24 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 0 | [6 empty] | CM_WWNI | 4.762% | CM_M&G | 19.05% | CM_WSNI | 33.33% | CM_WSI | 42.86%
501076 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | WWINF | Wastewater infrastructure | MS3 | 2015-11-18 | 2018-04-30 | 2018-06-18 | 2019-10-25 | 2020-02-10 | North Lanarkshire | 0 | 11437.38 | 69577.74 | 204005.88 | 1604185.1023 | 701690 | 0 | 2590896.1023 | 2250 | 2593146.1023 | 0 | [6 empty] | CM_WWI | 100%
500943 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS7 | 2016-03-30 | 2016-09-23 | 2016-09-23 | 2018-07-25 |  | Scottish Water Wide | 0 | 514927 | 1576193.02 | 710046.44 | 321985.2 | 0 | 0 | 3123151.66 | 0 | 3123151.66 | 0 | [6 empty] | CM_M&G | 100%
500622 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 2526708 | 3693138.99 | 2362727.21 | 2082201.7105 | 0 | 0 | 10664775.9105 | 0 | 10664775.9105 | 0 | [6 empty] | CM_OVH | 100%
500977 | Q&S4 | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2016-11-21 | 2017-06-27 | 2017-06-27 | 2017-06-28 | 2018-08-30 | Fife | 0 | 0 | 2106 | 190.63 | 140.65 | 0 | 0 | 2437.28 | 0 | 2437.28 | 0 | [6 empty] | CM_WWI | 100%
502611 | Q&S4 | Protecting and enhancing the environment | Environmental Studies |  |  | Wastewater |  | SWMD | Environmental Studies | MS7 | 2017-02-28 | 2017-10-26 | 2017-12-12 | 2018-08-01 | 2018-11-01 | Fife | 0 | 0 | 657.01 | 15242.99 | 18986.972 | 0 | 0 | 34886.972 | 0 | 34886.972 | 101993.458 | [6 empty] | EC01D | 100% | bar: Regulatory Outputs OMG-23
404063 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-01-15 | 2015-10-21 | 2015-11-27 | 2016-03-29 |  | Scottish Water Wide | 10099 | 664525 | 25629.24 | 0 | 0 | 0 | 0 | 690154.24 | 0 | 700253.24 | 0 | [6 empty] | CM_WSNI | 100%
404062 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-12-16 | 2014-12-16 | 2014-12-16 | 2015-10-27 |  | Scottish Water Wide | 110165 | 888.73 | 0 | 0 | 0 | 0 | 0 | 888.73 | 0 | 111053.73 | 0 | [6 empty] | CM_WSI | 100%
404055 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-01-15 | 2015-08-27 | 2015-10-05 | 2015-10-20 | 2017-05-22 | Scottish Water Wide | 4377 | 19685.84 | 0 | 0 | 0 | 0 | 0 | 19685.84 | 0 | 24062.84 | 0 | [6 empty] | CM_WSNI | 100%
404058 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2014-12-12 | 2014-12-12 | 2015-04-14 | 2016-02-08 |  | Scottish Water Wide | 18395.68 | 318597.82 | 1656.13 | 301.35 | 0 | 0 | 0 | 320555.3 | 0 | 338950.98 | 0 | [6 empty] | CM_WSNI | 100%
404101 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-02-19 | 2015-02-19 | 2015-04-14 | 2015-10-01 |  | Scottish Water Wide | 1624583 | 298217 | -429.35 | 0 | 0 | 0 | 0 | 297787.65 | 0 | 1922370.65 | 0 | [6 empty] | CM_WSNI | 100%
404064 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS7 | 2014-12-16 | 2014-12-16 | 2014-12-16 | 2015-11-09 |  | Scottish Water Wide | 26712 | 564996.65 | 0 | 0 | 0 | 0 | 0 | 564996.65 | 0 | 591708.65 | 0 | [6 empty] | CM_WSI | 100%
404060 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2014-12-16 | 2014-12-16 | 2015-04-13 | 2016-01-11 |  | Scottish Water Wide | 440824.14 | 541936.76 | 0 | 0 | 0 | 0 | 0 | 541936.76 | 0 | 982760.9 | 0 | [6 empty] | CM_WSNI | 100%
404057 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-12-16 | 2014-12-16 | 2014-12-16 | 2018-04-25 |  | Scottish Water Wide | 3761294.75 | 1535056.25 | 452538.1 | 72321.63 | 0 | 0 | 0 | 2059915.98 | 0 | 5821210.73 | 0 | [6 empty] | CM_WSNI | 100%
404084 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-12-11 | 2014-12-11 | 2014-12-11 | 2015-11-12 |  | Scottish Water Wide | 46750.25 | 168197.1 | 0 | 0 | 0 | 0 | 0 | 168197.1 | 0 | 214947.35 | 0 | [6 empty] | CM_WSNI | 100%
404059 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2014-12-16 | 2014-12-16 | 2015-02-02 | 2017-02-23 |  | Scottish Water Wide | 743945 | 2312328 | 297662.03 | 155792.09 | 3792.066 | 0 | 0 | 2769574.186 | 0 | 3513519.186 | 0 | [6 empty] | CM_WSNI | 100%
404065 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2015-01-21 | 2015-09-07 | 2016-01-12 | 2016-02-15 |  | Scottish Water Wide | 19710 | 47808.21 | 17.75 | 335.81 | 0 | 0 | 0 | 48161.77 | 0 | 67871.77 | 0 | [6 empty] | CM_WSNI | 100%
403792 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2014-05-09 | 2014-08-25 | 2014-10-31 | 2015-10-16 |  | Scottish Water Wide | 225271 | 42409.77 | 0 | 0 | 0 | 0 | 0 | 42409.77 | 0 | 267680.77 | 0 | [6 empty] | CM_WSNI | 100%
403906 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2014-08-15 | 2014-10-01 | 2014-10-20 | 2015-04-10 |  | Argyll and Bute-Cowal & Bute | 165023 | 55395 | -0.1 | -9182.26 | 0 | 0 | 0 | 46212.64 | 0 | 211235.64 | 0 | [6 empty] | CM_WSI | 100%
403793 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2014-05-09 | 2014-07-30 | 2014-08-01 | 2015-03-27 |  | Scottish Water Wide | 286638 | 1819.36 | 0 | 0 | 0 | 0 | 0 | 1819.36 | 0 | 288457.36 | 0 | [6 empty] | CM_WSNI | 100%
403789 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-05-19 | 2014-06-25 | 2014-06-25 | 2015-09-10 |  | Scottish Water Wide | 1692101.66 | 6839.77 | 0 | 0 | 0 | 0 | 0 | 6839.77 | 0 | 1698941.43 | 0 | [6 empty] | CM_WSNI | 100%
403472 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2013-05-20 | 2013-08-20 | 2013-10-01 | 2015-02-27 |  | Scottish Water Wide | 1133759.34 | 717.5 | 0 | 0 | 0 | 0 | 0 | 717.5 | 0 | 1134476.84 | 0 | [6 empty] | CM_WSI | 100%
403790 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS7 | 2014-06-02 | 2014-06-23 | 2014-06-23 | 2015-10-30 |  | Scottish Water Wide | 654159.4 | 3903.23 | 0 | 0 | 0 | 0 | 0 | 3903.23 | 0 | 658062.63 | 0 | [6 empty] | CM_WSNI | 100%
403469 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-05-13 | 2013-08-20 | 2013-10-17 | 2016-03-30 |  | Argyll and Bute-North Argyll | 4155573 | 104400 | 15379.12 | 18308.86 | 32164.815 | 0 | 0 | 170252.795 | 0 | 4325825.795 | 0 | [6 empty] | CM_WSNI | 100%
403317 | Q&S3B | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWMD | Water Non infrastructure | MS7 | 2013-04-02 | 2013-04-02 | 2013-05-15 | 2014-11-03 |  | Na H-Eileanan an Iar | 1713029.62 | -25240.62 | -962.34 | 0 | 0 | 0 | 0 | -26202.96 | 0 | 1686826.66 | 0 | [6 empty] | CM_WSNI | 100%
500606 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 2789761.75 | 2292183.51 | 1719779.2441 | 1766143.5123 | 0 | 0 | 8567868.0164 | 0 | 8567868.0164 | 0 | [6 empty] | CM_OVH | 100%
500619 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 138481.55 | 1311142.71 | 1277003.27 | 1284591.45 | 0 | 0 | 4011218.98 | 0 | 4011218.98 | 0 | [6 empty] | CM_OVH | 100%
500618 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 44992.24 | 37689.53 | 169574.08 | 355933.1 | 0 | 0 | 608188.95 | 0 | 608188.95 | 0 | [6 empty] | CM_OVH | 100%
500617 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 21249.19 | 38170.9 | 143819.14 | 196159.95 | 0 | 0 | 399399.18 | 0 | 399399.18 | 0 | [6 empty] | CM_OVH | 100%
500616 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 48698.95 | 95837.94 | 305394.7 | 312064.75 | 0 | 0 | 761996.34 | 0 | 761996.34 | 0 | [6 empty] | CM_OVH | 100%
500615 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 524767.27 | 1208106.89 | 1959818.44 | 1646061.85 | 54301.71 | 54091.25 | 5447147.41 | 36622.1 | 5483769.51 | 0 | [6 empty] | CM_OVH | 100%
500614 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 355193.26 | 1265242.67 | 1613363.54 | 1280316.44 | 0 | 0 | 4514115.91 | 0 | 4514115.91 | 0 | [6 empty] | CM_OVH | 100%
401433 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-01-11 | 2012-10-30 | 2012-12-17 | 2013-06-24 |  | Moray | 343845 | -2850.22 | 0 | 0 | 0 | 0 | 0 | -2850.22 | 0 | 340994.78 | 0 | [6 empty] | CM_WSI | 100%
034916 | Q&S3A | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2006-11-23 | 2008-07-31 | 2008-09-18 | 2009-04-24 |  | Fife | 1561034 | 8129 | 100696.99 | -31822.33 | 0 | 0 | 0 | 77003.66 | 0 | 1638037.66 | 0 | [6 empty] | WSI | 100%
402356 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-11-21 | 2012-12-19 | 2012-12-10 | 2014-09-01 |  | Perth and Kinross | 474225.93 | 3472.34 | 0 | 0 | 0 | 0 | 0 | 3472.34 | 0 | 477698.27 | 0 | [6 empty] | CM_WSI | 100%
402495 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2012-01-30 | 2013-07-29 | 2013-10-21 | 2014-08-01 |  | Angus | 293796 | 0 | -3000.98 | 0 | 0 | 0 | 0 | -3000.98 | 0 | 290795.02 | 0 | [6 empty] | CM_WSI | 100%
402045 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2011-08-29 | 2013-06-13 | 2013-06-18 | 2014-08-01 |  | Angus | 149226 | 55 | -17.01 | 0 | 0 | 0 | 0 | 37.99 | 0 | 149263.99 | 0 | [6 empty] | CM_WSI | 100%
401557 | Q&S3B | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS7 | 2010-11-30 | 2013-09-25 | 2013-10-28 | 2014-12-11 |  | Shetland Islands | 633239.56 | 3642.44 | 1997.49 | 0 | 0 | 0 | 0 | 5639.93 | 0 | 638879.49 | 0 | [6 empty] | CM_WSI | 100%
503104 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS3 | 2018-04-27 | 2018-04-27 | 2018-05-01 | 2021-03-24 | 2021-03-24 | Scottish Water Wide | 0 | 0 | 0 | 0 | 147232.026 | 179079.36 | 174220.61 | 500531.996 | 0 | 500531.996 | 0 |  |  |  |  | 500000.0004 |  | CM_WSNI | 100%
501338 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MS0 | 2017-01-26 | 2022-04-01 | 2022-08-02 | 2023-03-14 | 2023-06-12 | South Lanarkshire | 0 | 0 | 4796.35 | 0 | 1206.2 | 0 | 0 | 6002.55 | 842017.44 | 848019.99 | 0 | [6 empty] | CM_WSNI | 100%
500981 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS1 | 2015-10-23 | 2021-09-27 | 2021-11-29 | 2022-08-16 | 2022-11-16 | South Lanarkshire | 0 | 24168 | 140955.64 | 20239.45 | -4796.09 | 0 | 0 | 180567 | 0 | 180567 | 0 | [6 empty] | CM_WSI | 100%
501332 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | MSU | 2021-11-12 | 2022-08-11 | 2022-12-15 | 2023-04-26 | 2023-07-27 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99999.92 | 99999.92 | 0 | [6 empty] | CM_WSNI | 100%
501403 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW1 | 2021-12-09 | 2022-12-21 | 2023-04-26 | 2023-12-11 | 2024-03-12 | Moray | 0 | 5023.26 | 0 | 0 | 0 | 0 | 0 | 5023.26 | 406644.74 | 411668 | 0 | [6 empty] | CM_WSNI | 100%
402093 | Q&S3B | Completion | OMG180 |  |  | Water |  | SWMD | OMG180 | MS7 | 2011-05-23 | 2012-03-27 | 2013-01-14 | 2014-11-13 | 2014-12-03 | Aberdeenshire | 7799342.91 | 194928.19 | 119.66 | 0 | 0 | 0 | 0 | 195047.85 | 0 | 7994390.76 | 45409.9999 |  |  |  |  | 48825.5237 |  | DW3H | 100%
501388 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS0 | 2017-08-28 | 2019-10-28 | 2019-12-09 | 2021-02-11 | 2021-05-07 | West Lothian | 0 | 0 | 92411.23 | 149801.73 | 342302.04 | 595254.04 | 2753924.25 | 3933693.29 | 359821.72 | 4293515.01 | 0 | [6 empty] | CM_WSNI | 100%
501390 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS1 | 2016-11-17 | 2019-06-24 | 2019-07-29 | 2021-08-02 | 2021-10-29 | Midlothian | 0 | 0 | 101941.76 | 802311.59 | 792354.21 | 3212610.68 | 7583730.93 | 12492949.17 | 1372446.8 | 13865395.97 | 0 | [6 empty] | CM_WSNI | 100%
501382 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | SWD | Water Non infrastructure | GW2 | 2021-04-01 | 2022-08-10 | 2022-12-14 | 2024-03-12 | 2024-06-12 | East Lothian | 0 | 0 | 50145.3 | 46429.805 | 135995.985 | 0 | 0 | 232571.09 | 6271836.91 | 6504408 | 0 | [6 empty] | CM_WSNI | 100%
501379 | Q&S4 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS0 | 2017-03-31 | 2019-10-28 | 2019-11-25 | 2021-03-08 | 2021-06-07 | City of Edinburgh | 0 | 0 | 48016.79 | 221595.61 | 71804 | 288665.26 | 1204376.82 | 1834458.48 | 174766.95 | 2009225.43 | 0 | [6 empty] | CM_WSNI | 100%
501393 | IR18 | Sustaining existing high service for customers | Water Non infrastructure |  |  | Water |  | NONINF | Water Non infrastructure | MS1 | 2017-08-29 | 2019-09-02 | 2019-09-25 | 2021-02-03 | 2021-05-03 | Scottish Borders | 0 | 0 | 66797.3 | 470262.269 | 345056.171 | 1754498.52 | 4143086.8 | 6779701.06 | 734537.96 | 7514239.02 | 0 | [6 empty] | CM_WSNI | 100%
402692 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2012-07-20 | 2014-10-01 | 2014-10-01 | 2014-10-21 | 2014-10-01 | Aberdeenshire | 255864.54 | -5230.71 | 0 | 0 | 0 | 0 | 0 | -5230.71 | 0 | 250633.83 | 0 | [6 empty] | DW3C | 30% | CM_WSNI | 70%
034885 | Q&S3A | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2006-12-14 | 2008-05-28 | 2008-06-23 | 2015-03-04 |  | Scottish Water Wide | 393500 | -797.71 | 0 | 0 | 0 | 0 | 0 | -797.71 | 0 | 392702.29 | 0 | [6 empty] | WWI | 100%
500611 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 80775.91 | 739686.47 | 1090212.41 | 1349659.41 | 0 | 0 | 3260334.2 | 0 | 3260334.2 | 0 | [6 empty] | CM_OVH | 100%
502256 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS3 | 2016-07-29 | 2019-03-29 | 2019-03-29 | 2020-05-29 | 2020-05-29 | Scottish Water Wide | 0 | 0 | 67229.35 | 93820.65 | 549394.137 | 1500432.79 | 1702314.25 | 3913191.177 | 23175.97 | 3936367.147 | 0 |  |  |  |  | -380349.9997 |  | CM_WWNI | 100%
502300 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS1 | 2017-08-16 | 2019-10-21 | 2020-02-25 | 2021-05-25 | 2021-08-25 | Scottish Water Wide | 0 | 0 | 32283.07 | 29669.3575 | 240555.934 | 236601.68 | 593300.99 | 1132411.0315 | 730098.85 | 1862509.8815 | 0 | [6 empty] | CM_WWNI | 100%
502301 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS1 | 2017-11-27 | 2019-11-18 | 2020-03-26 | 2021-06-24 | 2021-09-24 | Scottish Water Wide | 0 | 0 | 26294.46 | 10476.835 | 32935.075 | 93986.07 | 128777.81 | 292470.25 | 83030.05 | 375500.3 | 0 | [6 empty] | CM_WWNI | 100%
502302 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW2 | 2021-04-01 | 2022-12-09 | 2023-04-07 | 2024-06-25 | 2024-09-25 | Scottish Water Wide | 0 | 0 | 38371.6 | 24145.725 | 2825.76 | 0 | 0 | 65343.085 | 2531656.98 | 2597000.065 | 0 | [6 empty] | CM_WWNI | 100%
502303 | Q&S4 | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWD | Wastewater non infrastructure | GW2 | 2021-04-01 | 2022-12-07 | 2023-03-28 | 2024-06-19 | 2024-09-19 | Scottish Water Wide | 0 | 0 | 21103.73 | 14401.03 | 542.606 | 0 | 0 | 36047.366 | 1403952.58 | 1439999.946 | 0 | [6 empty] | CM_WWNI | 100%
500613 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 1412797.66 | 431128.43 | 377446.24 | 269158.7 | 0 | 0 | 2490531.03 | 0 | 2490531.03 | 0 | [6 empty] | CM_OVH | 100%
500612 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 36843.55 | 63168.35 | 97971.08 | 88426.83 | 0 | 0 | 286409.81 | 0 | 286409.81 | 0 | [6 empty] | CM_OVH | 100%
500608 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 285093.28 | 938008.92 | 900162.54 | 1165573.3658 | 0 | 0 | 3288838.1058 | 0 | 3288838.1058 | 0 | [6 empty] | CM_OVH | 100%
500610 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 470815.56 | 1269075.28 | 1787261.27 | 2097023.03 | 0 | 0 | 5624175.14 | 0 | 5624175.14 | 0 | [6 empty] | CM_OVH | 100%
500609 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 104390.26 | 1091334.98 | 1677472.5095 | 1614271.272 | 0 | 0 | 4487469.0215 | 0 | 4487469.0215 | 0 | [6 empty] | CM_OVH | 100%
500607 | Q&S4 | Sustaining existing high service for customers | Management and General |  |  | General |  | SWD | Management and General | MS3 | 2015-04-29 | 2015-04-29 | 2015-04-29 | 2021-09-14 | 2021-09-14 | Scottish Water Wide | 0 | 211082.55 | 337016.64 | 499915.9 | 644814.71 | 0 | 0 | 1692829.8 | 0 | 1692829.8 | 0 | [6 empty] | CM_OVH | 100%
401326 | Q&S3B | Sustaining existing high service for customers | Wastewater non infrastructure |  |  | Wastewater |  | SWMD | Wastewater non infrastructure | MS7 | 2010-02-08 | 2010-08-23 | 2010-08-23 | 2015-06-02 |  | Scottish Water Wide | 309428.15 | -309428.15 | 0 | 0 | 0 | 0 | 0 | -309428.15 | 0 | 0 | 0 | [6 empty] | CM_WWNI | 100%
401441 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2010-10-12 | 2011-09-06 | 2012-06-04 | 2013-06-25 | 2013-06-25 | Scottish Borders | 24267 | -94.24 | 0 | 0 | 0 | 0 | 0 | -94.24 | 0 | 24172.76 | 446 | [6 empty] | CS1 | 100%
403589 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2013-09-06 | 2014-02-03 | 2014-02-10 | 2014-02-25 | 2014-03-20 | Scottish Borders | 22608 | -1293.12 | 0 | 0 | 0 | 0 | 0 | -1293.12 | 0 | 21314.88 | 1027 | [6 empty] | CS16W | 100%
045042 | Q&S3B | Completion | Non OMG180 |  |  | Water |  | SWMD | Non OMG180 | MS7 | 2009-03-17 | 2011-09-26 | 2012-09-17 | 2013-03-28 | 2013-06-24 | Scottish Borders | 831099.67 | 106.27 | 0 | 0 | 0 | 0 | 0 | 106.27 | 0 | 831205.94 | 0 | [6 empty] | DW23 | 100%
502569 | Q&S4 | Supporting economic development | Strategic Capacity |  |  | Water |  | SWD | Strategic Capacity | GW0 | 2019-09-27 | 2020-08-03 | 2020-10-01 | 2021-09-21 | 2021-12-22 | Shetland Islands | 0 | 0 | 20930.23 | 3854.8875 | 73881.458 | 69674.94 | 408166.4 | 576507.9155 | 478546.06 | 1055053.9755 | 148885.7057 | [6 empty] | WG1 | 100%
403709 | Q&S3B | Sustaining existing high service for customers | Wastewater infrastructure |  |  | Wastewater |  | SWMD | Wastewater infrastructure | MS7 | 2014-10-23 | 2017-03-27 | 2017-03-30 | 2017-11-29 |  | Aberdeen City | 23715 | 15592 | 28869 | 56379.788 | 0 | 0 | 0 | 100840.788 | 0 | 124555.788 | 0 | [6 empty] | CM_WWI | 100%
503164 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWD | Reservoirs | MS2 | 2018-05-29 | 2018-05-29 | 2019-05-15 | 2019-06-07 | 2020-12-24 | Scottish Water Wide | 0 | 0 | 0 | 0 | 276105.36 | 389018.29 | 372876.36 | 1038000.01 | 0 | 1038000.01 | 1560467.3848 | [6 empty] | CS22 | 100%
503163 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2018-05-29 | 2018-05-29 | 2018-10-08 | 2019-06-07 | 2021-03-02 | Scottish Water Wide | 0 | 0 | 0 | 0 | 368127.42 | 136195.1 | 533677.48 | 1038000 | 0 | 1038000 | 0 | [6 empty] | CM_WSI | 100%
503160 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS3 | 2018-04-16 | 2018-04-16 | 2018-07-25 | 2021-09-24 | 2021-09-27 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 196592.41 | 272182.01 | 0 | 468774.42 | 531332.04 | 1000106.46 | 1560467.3848 | [6 empty] | CS22 | 100%
503158 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS3 | 2018-04-16 | 2018-04-16 | 2018-08-14 | 2020-04-06 | 2020-07-07 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 206975.37 | 311607.65 | 0 | 518583.02 | 0 | 518583.02 | 1560467.3848 | [6 empty] | CS22 | 100%
503159 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS3 | 2018-04-16 | 2018-04-16 | 2018-08-14 | 2021-08-30 | 2021-11-30 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 239844.3 | 630947.01 | 0 | 870791.31 | 629208.7 | 1500000.01 | 1560467.3848 | [6 empty] | CS22 | 100%
503161 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs |  |  | Water |  | SWMD | Reservoirs | MS3 | 2018-04-16 | 2018-04-16 | 2018-06-11 | 2021-05-18 | 2021-05-19 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 519500.41 | 565456.74 | 0 | 1084957.15 | 0 | 1084957.15 | 1560467.3848 | [6 empty] | CS22 | 100%
503155 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2018-04-16 | 2018-04-16 | 2018-08-14 | 2021-09-24 | 2021-09-27 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 36313.08 | 50000 | 0 | 86313.08 | 263686.92 | 350000 | 0 | [6 empty] | CM_WSI | 100%
503153 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2018-04-16 | 2018-04-16 | 2018-08-14 | 2020-04-22 | 2020-07-23 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 13554.7 | 146258.36 | 0 | 159813.06 | 0 | 159813.06 | 0 | [6 empty] | CM_WSI | 100%
503154 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2018-04-18 | 2018-04-18 | 2018-08-14 | 2021-08-27 | 2021-11-29 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 625680.45 | 719462.02 | 0 | 1345142.47 | 654857.55 | 2000000.02 | 0 | [6 empty] | CM_WSI | 100%
503157 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWD | Water infrastructure | MS3 | 2018-05-28 | 2018-05-28 | 2018-06-01 | 2021-04-15 | 2021-07-16 | Scottish Water Wide | 0 | 0 | 0 | 0 | 148090.799 | 194660.21 | 209035.95 | 551786.959 | 88688.36 | 640475.319 | 0 | [6 empty] | CM_WSI | 100%
503156 | Q&S4 | Sustaining existing high service for customers | Water infrastructure |  |  | Water |  | SWMD | Water infrastructure | MS3 | 2018-04-30 | 2018-04-30 | 2018-06-11 | 2021-06-18 | 2021-06-21 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 700157.39 | 481695.53 | 0 | 1181852.92 | 0 | 1181852.92 | 0 | [6 empty] | CM_WSI | 100%
PH_500112 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50710 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-17 | 2016-12-19 | 2017-01-16 | 2019-02-01 | 2019-06-01 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500112 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_003 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-17 | 2016-12-19 | 2017-01-16 | 2018-12-01 | 2019-01-01 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500112 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Aberlour | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-17 | 2016-12-19 | 2017-01-16 | 2019-02-01 | 2019-06-01 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_501436 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50788 | OMG 04 | Water |  | SWD | DWQ Reliability | MS3 | 2016-07-06 | 2016-07-25 | 2016-07-25 | 2020-12-01 | 2021-03-01 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-04
PH_502690 | Q&S4 | Protecting and enhancing the environment | Odour | 50385 | OMG 29 | Wastewater |  | SWD | Odour | MS7 | 2015-08-01 | 2016-03-01 | 2016-03-01 | 2016-03-01 | 2017-07-23 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-29
PH_500111 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50307_TE_500307_002 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-17 | 2017-03-17 | 2017-05-08 | 2018-02-01 | 2018-08-01 | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500111 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_008 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-17 | 2017-03-17 | 2017-05-08 | 2018-05-01 | 2018-08-01 | Clackmannanshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_503194 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | TE_508019_01 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2018-06-28 | 2019-01-31 | 2019-01-31 | 2021-02-01 | 2021-12-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_503194 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | TE_508018_01 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2018-06-28 | 2019-01-31 | 2019-01-31 | 2021-02-01 | 2021-12-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_503194 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | TE_508020_01 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2018-06-28 | 2019-01-31 | 2019-01-31 | 2021-02-01 | 2021-12-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500114 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_013 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-17 | 2016-02-26 | 2016-08-11 | 2019-02-01 | 2019-03-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500114 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50725 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-17 | 2016-02-26 | 2016-08-11 | 2019-03-01 | 2019-07-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500113 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_028 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-17 | 2016-02-26 | 2016-03-21 | 2018-09-01 | 2018-11-01 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500113 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50837 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-17 | 2016-02-26 | 2016-03-21 | 2018-12-01 | 2019-03-01 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500121 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50801 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-17 | 2016-06-27 | 2016-08-24 | 2019-09-01 | 2019-12-01 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500121 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_015 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-17 | 2016-06-27 | 2016-08-24 | 2019-09-01 | 2019-12-01 | West Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_502278 | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance | TBC_FN_ASR_3 | OMG 07 | Water |  | WINF | Exceptional Capital Maintenance |  | 2016-09-14 | 2017-05-30 | 2017-05-30 | 2019-03-01 | 2019-03-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-07
PH_502278 | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance | TBC_FN_ASR_2 | OMG 07 | Water |  | WINF | Exceptional Capital Maintenance |  | 2016-09-14 | 2017-05-30 | 2017-05-30 | 2019-03-01 | 2019-03-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-07
PH_502278 | Q&S4 | Exceptional Capital Maintenance | Exceptional Capital Maintenance | TBC_FN_ASR_4 | OMG 07 | Water |  | WINF | Exceptional Capital Maintenance |  | 2016-09-14 | 2017-05-30 | 2017-05-30 | 2019-03-01 | 2019-03-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-07
PH_500795 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50200 | OMG 06 | Water |  | SWD | DWQ Reliability |  | 2015-10-28 | 2016-03-31 | 2016-05-30 | 2017-09-01 | 2019-02-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 103.31
PH_500795 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53305 | OMG 06 | Water |  | SWD | DWQ Reliability |  | 2015-10-28 | 2016-03-31 | 2016-05-30 | 2017-09-01 | 2019-02-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 9.47
PH_500844 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53206 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-07-27 | 2018-06-28 | 2018-12-04 | 2019-12-01 | 2020-10-01 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 32.1
PH_500844 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50201 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-07-27 | 2018-06-28 | 2018-12-04 | 2019-12-01 | 2020-10-01 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 89.05
PH_500002 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53187 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2015-11-23 | 2017-12-21 | 2018-03-20 | 2019-12-01 | 2020-03-01 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 2.05
PH_500002 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50247 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2015-11-23 | 2017-12-21 | 2018-03-20 | 2019-12-01 | 2020-03-01 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 90.43
PH_500846 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53188 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-09-20 | 2017-12-20 | 2017-12-20 | 2019-06-01 | 2020-03-01 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 2.01
PH_500846 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50248 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-09-20 | 2017-12-20 | 2017-12-20 | 2019-06-01 | 2020-03-01 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 59.62
PH_500227 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50009_002 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2016-03-30 | 2016-04-20 | 2017-02-01 | 2020-08-01 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500227 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50009_001 | OMG 06 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2016-03-30 | 2016-04-20 | 2017-02-01 | 2020-08-01 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 19.4
PH_500228 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50010_003 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2016-09-29 | 2016-10-31 | 2018-06-01 | 2019-06-01 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500228 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50010_002 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2016-09-29 | 2016-10-31 | 2018-06-01 | 2019-03-01 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500228 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50010_001 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2016-09-29 | 2016-10-31 | 2019-03-01 | 2019-03-01 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500848 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53190 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-03-31 | 2017-12-19 | 2018-03-20 | 2019-03-01 | 2019-04-01 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 9.67
PH_500848 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50236 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-03-31 | 2017-12-19 | 2018-03-20 | 2019-03-01 | 2019-04-01 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 25.75
PH_500116 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_026 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-09-29 | 2016-09-30 | 2018-09-01 | 2018-11-01 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500116 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_003 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-09-29 | 2016-09-30 | 2019-03-01 | 2019-07-01 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500247 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50496_TE_500496_001_N02 | OMG 21 | Wastewater |  | SWMD | UWWTD - Works |  | 2015-03-23 | 2017-11-23 | 2017-11-23 | 2017-10-01 | 2017-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-21
PH_500247 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50496_TE_500496_001_N03 | OMG 21 | Wastewater |  | SWMD | UWWTD - Works |  | 2015-03-23 | 2017-11-23 | 2017-11-23 | 2017-11-01 | 2017-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-21
PH_500247 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50496_TE_500496_001_N05 | OMG 21 | Wastewater |  | SWMD | UWWTD - Works |  | 2015-03-23 | 2017-11-23 | 2017-11-23 | 2017-11-01 | 2017-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-21
PH_500247 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50496_TE_500496_001_N01 | OMG 21 | Wastewater |  | SWMD | UWWTD - Works |  | 2015-03-23 | 2017-11-23 | 2017-11-23 | 2017-10-01 | 2017-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-21
PH_500247 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50496_TE_500496_001_N10 | OMG 21 | Wastewater |  | SWMD | UWWTD - Works |  | 2015-03-23 | 2017-11-23 | 2017-11-23 | 2017-11-01 | 2017-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-21
PH_500247 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50496_TE_500496_001_N07 | OMG 21 | Wastewater |  | SWMD | UWWTD - Works |  | 2015-03-23 | 2017-11-23 | 2017-11-23 | 2017-10-01 | 2017-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-21
PH_500239 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50013_001 | OMG 02 | Water |  | SWD | DWQ Compliance |  | 2015-03-27 | 2016-09-30 | 2017-01-02 | 2018-07-01 | 2019-03-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500239 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50013_002 | OMG 02 | Water |  | SWD | DWQ Compliance |  | 2015-03-27 | 2016-09-30 | 2017-01-02 | 2018-03-01 | 2019-06-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500239 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50013_003 | OMG 02 | Water |  | SWD | DWQ Compliance |  | 2015-03-27 | 2016-09-30 | 2017-01-02 | 2018-03-01 | 2019-03-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500797 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53202 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2015-09-30 | 2018-06-28 | 2018-09-28 | 2020-03-01 | 2021-01-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 253.53
PH_500797 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50237 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2015-09-30 | 2018-06-28 | 2018-09-28 | 2020-03-01 | 2021-01-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 46.23
PH_500800 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50239 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-01-12 | 2017-03-09 | 2017-03-30 | 2019-04-01 | 2019-12-01 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 20
PH_500800 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53207 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-01-12 | 2017-03-09 | 2017-03-30 | 2019-04-01 | 2019-12-01 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 18.57
PH_502412 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50749_TE_500749_01 | OMG 04 | Water |  | NONINF | DWQ Reliability |  | 2015-07-16 | 2017-03-13 | 2017-03-27 | 2021-07-01 | 2021-10-01 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-04
PH_502412 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50749_TE_500749_02 | OMG 01 | Water |  | NONINF | DWQ Reliability |  | 2015-07-16 | 2017-03-13 | 2017-03-27 | 2018-06-01 | 2019-09-01 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-01
PH_502412 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50091_TE_500091_02 | OMG 01 | Water |  | NONINF | DWQ Reliability |  | 2015-07-16 | 2017-03-13 | 2017-03-27 | 2018-09-01 | 2019-09-01 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-01
PH_500123 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Brechin | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-11-24 | 2016-11-25 | 2018-11-01 | 2019-03-01 | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500123 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_036 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-11-24 | 2016-11-25 | 2018-09-01 | 2018-11-01 | Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_502132 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50144 | OMG 01 | Water |  | WINF | DWQ Compliance |  | 2016-03-17 | 2019-03-29 | 2019-03-19 | 2020-12-01 | 2021-11-01 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-01
PH_502132 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50144 | OMG 20 | Water |  | WINF | DWQ Compliance |  | 2016-03-17 | 2019-03-29 | 2019-03-19 | 2020-12-01 | 2021-11-01 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-20: 5
PH_500119 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_042 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-01-19 | 2016-03-21 | 2017-07-01 | 2017-08-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500119 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50803 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-01-19 | 2016-03-21 | 2017-07-01 | 2017-08-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500031 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50186_TE_500186_01_N01 | OMG 47 | Water |  | SWD | DWQ Reliability |  | 2015-02-27 | 2015-07-17 | 2015-07-27 | 2017-07-01 | 2017-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-47: 8
PH_500031 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50186_TE_500186_01_N02 | OMG 47 | Water |  | SWD | DWQ Reliability |  | 2015-02-27 | 2015-07-17 | 2015-07-27 | 2017-07-01 | 2017-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-47: 14
PH_500062 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50000_002 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-19 | 2016-05-26 | 2016-05-30 | 2017-09-01 | 2018-12-01 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500062 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50000_001 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-19 | 2016-05-26 | 2016-05-30 | 2017-09-01 | 2018-12-01 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500006 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50021_002 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-20 | 2016-09-30 | 2016-10-31 | 2018-12-01 | 2019-11-01 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500006 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50021_003 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-20 | 2016-09-30 | 2016-10-31 | 2018-06-01 | 2019-04-01 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500006 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50021_004 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-20 | 2016-09-30 | 2016-10-31 | 2018-03-01 | 2019-07-01 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500006 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50021_005 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-20 | 2016-09-30 | 2016-10-31 | 2018-06-01 | 2019-03-01 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500006 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50021_001 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-20 | 2016-09-30 | 2016-10-31 | 2018-09-01 | 2019-07-01 | Dundee City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_038 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_037 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_036 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_035 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_034 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_033 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-12-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_032 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_030 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_039 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-12-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_050 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_028 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_031 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_040 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_041 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_042 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_043 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_044 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_045 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_046 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-12-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_047 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_049 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_051 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-12-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_026 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_005 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_048 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-12-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_013 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_001 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_002 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_003 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2020-12-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_004 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_029 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_006 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_052 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_008 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_009 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_010 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_007 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_012 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_025 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_014 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_015 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_016 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_017 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_018 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_019 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_020 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_021 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_022 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_023 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_024 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_011 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500190 | Q&S4 | Climate Change | Climate Change | TE_501313_027 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-20 | 2017-09-28 | 2017-09-29 | 2019-03-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500098 | Q&S4 | Climate Change | Climate Change | 51308_TE_501308_002 | OMG 45 | General |  | SWD | Climate Change |  | 2015-03-31 | 2015-09-25 | 2015-09-25 | 2016-06-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500098 | Q&S4 | Climate Change | Climate Change | 51308_TE_501308_001 | OMG 45 | General |  | SWD | Climate Change |  | 2015-03-31 | 2015-09-25 | 2015-09-25 | 2016-06-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Q&S4 | Climate Change | Climate Change | TE_501311_022 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-08-01 | 2019-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Q&S4 | Climate Change | Climate Change | TE_501311_026 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-08-01 | 2019-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Q&S4 | Climate Change | Climate Change | TE_501311_025 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-08-01 | 2019-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Q&S4 | Climate Change | Climate Change | TE_501311_023 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-08-01 | 2019-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Q&S4 | Climate Change | Climate Change | TE_501311_021 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-08-01 | 2019-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Q&S4 | Climate Change | Climate Change | TE_501311_020 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-08-01 | 2019-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Q&S4 | Climate Change | Climate Change | TE_501311_019 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-08-01 | 2019-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Q&S4 | Climate Change | Climate Change | TE_501311_018 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-08-01 | 2019-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Q&S4 | Climate Change | Climate Change | TE_501311_017 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-08-01 | 2019-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Q&S4 | Climate Change | Climate Change | TE_501311_015 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-08-01 | 2019-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Q&S4 | Climate Change | Climate Change | TE_501311_016 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-08-01 | 2019-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500092 | Q&S4 | Climate Change | Climate Change | TE_501311_024 | OMG 45 | Wastewater |  | SWD | Climate Change |  | 2017-08-16 | 2017-11-27 | 2017-12-15 | 2019-08-01 | 2019-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500122 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_049 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-06-21 | 2016-08-18 | 2019-06-01 | 2019-09-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500122 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Corpach | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-06-21 | 2016-08-18 | 2019-06-01 | 2019-09-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500122 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50727 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-06-21 | 2016-08-18 | 2019-06-01 | 2019-09-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_015 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-10-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_024 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_007 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-01-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_023 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-01 | 2016-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_022 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-10-01 | 2016-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_021 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-08-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_020 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-09-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_019 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-08-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_018 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-01 | 2016-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_017 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-01 | 2016-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_016 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2019-06-01 | 2019-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_025 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_014 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_013 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-08-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_012 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-10-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_011 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_010 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_026 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-10-01 | 2016-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_008 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_032 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-01 | 2016-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_006 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-08-01 | 2018-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_004 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-01 | 2016-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_002 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_001 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-09-01 | 2018-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_009 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-08-01 | 2018-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_043 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-03-01 | 2020-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_057 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-10-01 | 2018-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_056 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-03-01 | 2020-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_055 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-06-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_054 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2019-10-01 | 2020-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_053 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-03-01 | 2020-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_052 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-06-01 | 2020-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_051 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-03-01 | 2020-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_050 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-03-01 | 2020-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_049 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-03-01 | 2020-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_048 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-01 | 2016-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_047 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2018-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_046 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-10-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_030 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_044 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-03-01 | 2020-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_027 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-01 | 2016-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_042 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-10-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_041 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-04-01 | 2020-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_040 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-03-01 | 2020-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_039 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-01 | 2016-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_038 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_037 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-10-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_036 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_034 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-01 | 2016-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_033 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-01 | 2016-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_003 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2019-04-01 | 2019-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_031 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-01 | 2016-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_029 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-11-01 | 2016-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_028 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_045 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2020-04-01 | 2020-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500843 | Q&S4 | Improving drinking water availability and resilience of service | Reservoirs | 50311_TE_500311_005 | OMG 13 | Water |  | SWMD | Reservoirs |  | 2015-09-01 | 2015-09-08 | 2015-09-09 | 2017-07-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-13
PH_500124 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_065 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-04-28 | 2016-06-29 | 2018-11-01 | 2019-01-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500124 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_066 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-04-28 | 2016-06-29 | 2018-11-01 | 2019-01-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500124 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50804 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-04-28 | 2016-06-29 | 2019-01-01 | 2019-05-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_046 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_065 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_064 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_063 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_062 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_061 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_055 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_047 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_048 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_049 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_066 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_050 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_074 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_051 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_052 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_053 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_054 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_058 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2019-03-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_078 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_090 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_089 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_088 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_087 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_086 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_085 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_084 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_083 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2019-03-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_082 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_081 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_072 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_079 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_067 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_077 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-06-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_076 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_075 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_034 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_073 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_045 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_071 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_070 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_069 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2019-03-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_068 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2020-03-01 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_080 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_010 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_036 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_020 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_018 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_017 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_016 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_015 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_014 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_013 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_022 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-09-01 | 2017-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_011 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_023 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_009 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_008 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_007 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_006 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_005 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_004 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_003 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_002 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_001 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-09-01 | 2017-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_012 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_033 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_043 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_042 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_041 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_040 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_039 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_038 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_037 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_091 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_021 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_059 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_044 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_032 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_031 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_030 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_029 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_028 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_027 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_026 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_025 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_024 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_035 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_134 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_121 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_122 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_123 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_056 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_126 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_127 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_128 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_129 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_130 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_131 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_120 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_133 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-09-01 | 2017-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_124 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-07-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_135 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_136 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_137 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_138 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_139 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_140 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_141 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-09-01 | 2017-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_142 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_144 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2019-03-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_145 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_092 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_132 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_103 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_093 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_094 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_095 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_096 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_097 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_098 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_099 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_100 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_125 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_102 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2019-03-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_119 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_104 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_106 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_115 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_118 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-09-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_101 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_117 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_107 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_114 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-10-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_108 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-09-01 | 2017-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_112 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_111 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_110 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_109 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500200 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50771_TE_500771_113 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2015-03-26 | 2015-12-02 | 2015-12-14 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_101 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_111 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_110 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_109 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_108 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_107 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_106 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_105 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_104 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_090 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_102 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-09-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_114 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_100 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-09-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_099 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_098 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_097 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_096 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_095 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_093 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-01 | 2017-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_092 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-09-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_103 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_036 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-01 | 2017-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_020 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-09-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_022 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-01 | 2017-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_023 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-09-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_024 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-09-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_025 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_026 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_027 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_028 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_031 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_112 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_035 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_113 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_037 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-01 | 2017-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_038 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_039 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-01 | 2017-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_040 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_041 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_043 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_044 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_045 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_089 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_034 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_056 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-09-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_065 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_064 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_063 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_062 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_061 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_060 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-09-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_059 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-01 | 2017-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_058 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_091 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_019 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_068 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_030 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_054 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-09-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_053 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_046 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_047 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_048 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_049 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_050 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_051 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-01 | 2017-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_057 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_077 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-09-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_088 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_087 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_086 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-01 | 2017-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_085 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-09-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_084 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-09-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_083 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-01 | 2017-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_082 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_081 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-09-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_080 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_066 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_078 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_067 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_076 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_075 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_074 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_073 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-09-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_072 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_071 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_070 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_069 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-09-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_052 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_079 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_004 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_001 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_003 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | 50771_TE_500771_143 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_005 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_006 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_007 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_008 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_018 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_009 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_016 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_002 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_033 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_017 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_015 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_014 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2016-08-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_013 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-01-01 | 2017-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_012 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_011 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500899 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | TE_500358_010 | OMG 47 | General |  | SWD | SOSI |  | 2015-09-14 | 2016-01-28 | 2016-02-22 | 2019-09-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_501271 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_074 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-31 | 2016-07-29 | 2016-08-18 | 2018-09-01 | 2018-11-01 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501271 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_004 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-31 | 2016-07-29 | 2016-08-18 | 2019-03-01 | 2019-08-01 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500128 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_075 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2015-09-27 | 2015-11-02 | 2017-07-01 | 2017-07-01 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500128 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_076 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2015-09-27 | 2015-11-02 | 2017-07-01 | 2017-07-01 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500578 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50167 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-02-01 | 2017-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50162 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-01-01 | 2017-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50175 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50176 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-04-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50164 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-07-01 | 2017-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50163 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-01-01 | 2017-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50174 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-07-01 | 2017-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50172 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50171 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50170 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50169 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-10-01 | 2017-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50165 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-04-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50166 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50173 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500578 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50168 | OMG 47 | Water |  | SWD | DWQ Compliance |  | 2015-04-29 | 2015-06-15 | 2015-06-15 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_501104 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Edin | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-09-30 | 2017-02-27 | 2017-03-27 | 2018-12-01 | 2019-01-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_501104 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50829 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-09-30 | 2017-02-27 | 2017-03-27 | 2018-12-01 | 2019-01-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500223 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50027_003 | OMG 02 | Water |  | SWD | DWQ Compliance |  | 2015-03-27 | 2016-03-30 | 2016-06-15 | 2017-06-01 | 2018-12-01 | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500223 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50027_001 | OMG 02 | Water |  | SWD | DWQ Compliance |  | 2015-03-27 | 2016-03-30 | 2016-06-15 | 2017-06-01 | 2018-06-01 | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500223 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50027_002 | OMG 02 | Water |  | SWD | DWQ Compliance |  | 2015-03-27 | 2016-03-30 | 2016-06-15 | 2017-06-01 | 2019-06-01 | Shetland Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500483 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_009 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-10-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.15
PH_500483 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_010 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.0039
PH_500483 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_012 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.0088
PH_500483 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_013 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.128
PH_500483 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_006 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-09-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.05
PH_500483 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_015 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.0365
PH_500483 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_001 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-10-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.044
PH_500483 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_007 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-09-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.07
PH_500483 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_005 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-10-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.01
PH_500483 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_004 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-10-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.028
PH_500483 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_003 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-10-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.07
PH_500483 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_002 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-10-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.01
PH_500483 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50308_TE_500308_008 | OMG 44 | Water |  | SWD | Energy efficiency |  | 2015-09-16 | 2016-02-29 | 2016-02-29 | 2017-10-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.046
PH_500484 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_010 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2017-05-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.14
PH_500484 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_009 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2017-11-01 | 2018-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.475
PH_500484 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_008 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2018-07-01 | 2018-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.075
PH_500484 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_004 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2016-12-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.16
PH_500484 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_003 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2018-06-01 | 2018-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.081
PH_500484 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_001 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2018-07-01 | 2018-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.046
PH_500484 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_011 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2017-05-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.57
PH_500484 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_018 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.024
PH_500484 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_002 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2017-05-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.15
PH_500484 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_013 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2017-11-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.052
PH_500484 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_014 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2017-05-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.261
PH_500484 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_015 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2016-12-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.05
PH_500484 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_016 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2016-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 5.921
PH_500484 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_017 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2016-12-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.54
PH_500484 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_012 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2017-05-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.41
PH_500484 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_019 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2016-09-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.05
PH_500484 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_022 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2016-10-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.02
PH_500484 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_024 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2018-06-01 | 2018-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 1.212
PH_500484 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_034 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2018-07-01 | 2018-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.051
PH_500484 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_039 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.117
PH_500484 | Q&S4 | Reducing long term cost of service | Energy efficiency | 50309_TE_500309_052 | OMG 44 | Wastewater |  | SWD | Energy efficiency |  | 2015-08-11 | 2016-03-30 | 2016-03-30 | 2019-01-01 | 2019-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-44: 0.011
PH_500064 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-11 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-03-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500064 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-13 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500064 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-14 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500064 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-15 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500064 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-16 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500064 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-12 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-03-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500064 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-10 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-25 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-9 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-20 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-21 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-22 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-23 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-24 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-19 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-26 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-27 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-28 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-5 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-6 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-18 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-8 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-15 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-7 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-8 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-17 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-16 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-5 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-7 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-9 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-10 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-11 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-12 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-13 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-14 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502644 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-6 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2017-02-24 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-37 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-45 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-29 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-3 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-30 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-32 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-34 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-27 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-36 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-26 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-38 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-39 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-4 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-40 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-41 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-42 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-43 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-44 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-35 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-18 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-1 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-10 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-11 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-12 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-13 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-14 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-15 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-28 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-17 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-33 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-19 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-2 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-20 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-21 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-22 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-23 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-24 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-25 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-16 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-6 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-46 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-31 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-9 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-8 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-7 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-55 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-54 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-49 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-47 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-48 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-53 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-5 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-50 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-51 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-01-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500199 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-52 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-30 | 2016-03-30 | 2017-02-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_15 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_20 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-11-01 | 2019-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_28 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-02-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_27 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-06-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_29 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-01-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_22 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-05-01 | 2018-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_23 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-02-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_30 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-03-01 | 2018-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_21 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-04-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_19 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-04-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_11 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-03-01 | 2018-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_12 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-02-01 | 2019-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_13 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-11-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_18 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-04-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_16 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-04-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_14 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2019-04-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_24 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_25 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_17 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-11-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502187 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_26 | OMG 10 | Water |  | SWMD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-07-14 | 2018-05-01 | 2018-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500126 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_083 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-03-28 | 2017-05-16 | 2019-12-01 | 2020-03-01 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500126 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50721 | OMG 23 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-03-28 | 2017-05-16 | 2019-12-01 | 2020-03-01 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500126 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_005 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-03-28 | 2017-05-16 | 2019-12-01 | 2020-03-01 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500135 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Eyemo | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-05-26 | 2016-06-20 | 2019-04-01 | 2019-07-01 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500135 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_084 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-05-26 | 2016-06-20 | 2019-02-01 | 2019-03-01 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500823 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50240 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2015-10-28 | 2017-12-21 | 2017-12-22 | 2019-03-01 | 2019-07-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 12.44
PH_500823 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53192 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2015-10-28 | 2017-12-21 | 2017-12-22 | 2019-03-01 | 2019-07-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 46.07
PH_500241 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50029_003 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2018-09-28 | 2018-09-28 | 2019-02-01 | 2019-11-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500241 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50029_001 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2018-09-28 | 2018-09-28 | 2019-07-01 | 2020-03-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500824 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50241 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-08-03 | 2018-03-23 | 2018-06-14 | 2019-03-01 | 2019-12-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 36.16
PH_500824 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53193 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-08-03 | 2018-03-23 | 2018-06-14 | 2019-03-01 | 2019-12-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 17.7
PH_500074 | Q&S4 | Climate Change | Climate Change | 51315 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-09 | 2015-06-30 | 2015-06-30 | 2016-03-01 | 2016-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500074 | Q&S4 | Climate Change | Climate Change | 51305 | OMG 45 | Water |  | SWD | Climate Change |  | 2015-03-09 | 2015-06-30 | 2015-06-30 | 2016-03-01 | 2016-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_151 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-03-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_167 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-08-01 | 2019-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_166 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-08-01 | 2020-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_165 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-07-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_130 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-08-01 | 2017-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_173 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-03-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_159 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_155 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-08-01 | 2019-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_154 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-06-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_153 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_138 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-08-01 | 2017-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_133 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-05-01 | 2019-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_168 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-12-01 | 2018-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_202 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-02-01 | 2020-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_150 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-07-01 | 2019-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_148 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-07-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_147 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-06-01 | 2019-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_145 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-03-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_144 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-02-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_143 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_139 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-09-01 | 2018-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_152 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-04-01 | 2018-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_203 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-11-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_187 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-10-01 | 2020-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_131 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-01-01 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_126 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-09-01 | 2019-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_174 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-06-01 | 2019-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_175 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-08-01 | 2017-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_176 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-01-01 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_207 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-03-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_206 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-01 | 2019-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_200 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-07-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_204 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-07-01 | 2017-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_169 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_201 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-02-01 | 2020-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_196 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-06-01 | 2018-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_194 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-02-01 | 2020-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_191 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-07-01 | 2017-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_188 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-03-01 | 2020-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_068 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-02-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_172 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_171 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-09-01 | 2019-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_170 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_205 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-07-01 | 2017-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_038 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-08-01 | 2019-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_024 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_002 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-02-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_001 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-09-01 | 2019-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_023 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-01 | 2019-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_045 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-03-01 | 2020-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_019 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-04-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_043 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-08-01 | 2017-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_005 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-03-01 | 2018-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_040 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-12-01 | 2019-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_009 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-10-01 | 2017-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_037 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_031 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-07-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_021 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-05-01 | 2019-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_022 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-03-01 | 2018-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_029 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-01 | 2019-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_027 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-07-01 | 2019-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_025 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-04-01 | 2018-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_046 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-03-01 | 2018-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_056 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-07-01 | 2019-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_047 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-02-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_048 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-01-01 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_050 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-05-01 | 2018-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_053 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-02-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_137 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-05-01 | 2019-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_054 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-07-01 | 2018-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_124 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-11-01 | 2017-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_004 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-07-01 | 2017-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_055 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_039 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-02-01 | 2017-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_057 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_060 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-11-01 | 2017-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_017 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-01-01 | 2017-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_016 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_012 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-07-01 | 2019-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_011 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-04-01 | 2018-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_010 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-03-01 | 2020-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_018 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-02-01 | 2018-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_100 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-01 | 2019-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_119 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-01 | 2019-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_117 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-05-01 | 2019-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_070 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_071 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-02-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_116 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2020-01-01 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_114 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-11-01 | 2019-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_095 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-12-01 | 2018-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_107 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-04-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_123 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-09-01 | 2020-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_101 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-10-01 | 2020-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_115 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-03-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_098 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-11-01 | 2020-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_073 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-02-01 | 2018-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_078 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-11-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_080 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-10-01 | 2020-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_082 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_085 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-10-01 | 2017-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_090 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2018-11-01 | 2019-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_094 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2017-08-01 | 2017-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_106 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-02-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500215 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_113 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-04-01 | 2016-04-22 | 2019-04-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500127 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_087 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-03-14 | 2016-05-09 | 2018-02-01 | 2018-03-01 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500127 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Fochab | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-03-14 | 2016-05-09 | 2018-03-01 | 2018-03-01 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500127 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50730 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-03-14 | 2016-05-09 | 2018-03-01 | 2018-03-01 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500129 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50820 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2017-02-27 | 2017-03-17 | 2019-08-01 | 2019-11-01 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500129 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50307_TE_500307_006 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2017-02-27 | 2017-03-17 | 2018-02-01 | 2018-06-01 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500129 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_089 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2017-02-27 | 2017-03-17 | 2019-06-01 | 2019-09-01 | Moray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500141 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Fraser | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-20 | 2016-03-23 | 2018-03-01 | 2019-02-01 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500141 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_091 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-20 | 2016-03-23 | 2018-03-01 | 2018-03-01 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_038 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-08-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_039 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-02-01 | 2020-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_044 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-02-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_043 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-11-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_040 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_041 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-03-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_012 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-10-01 | 2019-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_013 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-04-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_019 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-03-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_053 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_014 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_015 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_017 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_018 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-05-01 | 2019-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_058 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-08-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_057 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_042 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-03-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_055 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-05-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_020 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-03-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_052 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2017-02-01 | 2017-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_051 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2017-09-01 | 2017-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_050 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_049 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_048 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-01-01 | 2018-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_047 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-06-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_045 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2020-03-01 | 2020-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_056 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2017-07-01 | 2020-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_029 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-04-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_033 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_034 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2020-01-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_035 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-09-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_036 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-07-01 | 2019-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_037 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-04-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_008 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-04-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_007 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_031 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-11-01 | 2020-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_001 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2017-07-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_030 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-02-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_005 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_032 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-11-01 | 2016-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_004 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-08-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_003 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-04-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_025 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2017-08-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_024 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-01-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_009 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-07-01 | 2019-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_028 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-08-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_027 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-02-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_026 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-01-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_010 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-06-01 | 2019-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_022 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_023 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2018-01-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_002 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2016-02-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_500060 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50363_TE_500363_021 | OMG 11 | Water |  | SWMD | Flood Risk Management Act |  | 2015-06-30 | 2015-06-30 | 2015-07-10 | 2019-04-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-11
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_062 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2018-07-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_105 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-04-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_104 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2018-07-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_088 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-12-01 | 2017-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_081 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-06-01 | 2017-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_052 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-10-01 | 2017-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_064 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2018-06-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_035 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-02-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_063 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2018-05-01 | 2018-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_146 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_032 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-10-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_033 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-02-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_120 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_044 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-01-01 | 2017-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_051 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-01-01 | 2017-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_141 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_061 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-01-01 | 2017-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_161 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_177 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2018-05-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_198 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_127 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2018-07-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_156 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_122 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501093 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_157 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-02-29 | 2016-03-22 | 2016-12-01 | 2017-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500133 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50307_TE_500307_007 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-26 | 2016-12-19 | 2017-01-13 | 2018-02-01 | 2018-06-01 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500133 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_093 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-26 | 2016-12-19 | 2017-01-13 | 2018-06-01 | 2018-08-01 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500245 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | 50113 | OMG 04 | Water |  | NONINF | SOSI |  | 2016-12-23 | 2018-09-28 | 2019-03-04 | 2020-10-01 | 2021-01-01 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-04
PH_500245 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | 50113 | OMG 20 | Water |  | NONINF | SOSI |  | 2016-12-23 | 2018-09-28 | 2019-03-04 | 2020-10-01 | 2021-01-01 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-20: 3
PH_500146 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Girvan | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-03-30 | 2016-04-25 | 2018-07-01 | 2019-01-01 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500146 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_097 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-03-30 | 2016-04-25 | 2018-07-01 | 2018-08-01 | South Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500243 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50034_001 | OMG 06 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2018-06-28 | 2018-06-29 | 2019-06-01 | 2020-05-01 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 21.58
PH_500243 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50034_003 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2018-06-28 | 2018-06-29 | 2019-07-01 | 2020-06-01 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500243 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50034_002 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2018-06-28 | 2018-06-29 | 2019-06-01 | 2020-05-01 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_502606 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 59145_02 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2018-06-28 | 2019-07-22 | 2019-08-06 | 2020-10-01 | 2020-10-01 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_502606 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 59145_03 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2018-06-28 | 2019-07-22 | 2019-08-06 | 2020-10-01 | 2021-07-01 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_502606 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 59145_04 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2018-06-28 | 2019-07-22 | 2019-08-06 | 2020-10-01 | 2021-07-01 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_501574 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50782 | OMG 04 | Water |  | SWD | DWQ Reliability |  | 2017-03-31 | 2019-05-05 | 2019-06-05 | 2020-03-01 | 2020-06-01 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-04
PH_501574 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50782 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2017-03-31 | 2019-05-05 | 2019-06-05 | 2020-03-01 | 2020-06-01 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_500136 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_208 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-03-29 | 2016-08-01 | 2018-09-01 | 2019-02-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500136 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50807 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-03-29 | 2016-08-01 | 2018-12-01 | 2019-03-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500137 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50819 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-06-21 | 2016-08-18 | 2019-02-01 | 2019-07-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500137 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_103 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-06-21 | 2016-08-18 | 2019-01-01 | 2019-02-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501233 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50781 | OMG 04 | Water |  | NONINF | DWQ Reliability |  | 2018-03-22 | 2019-10-28 | 2020-03-16 | 2020-12-01 | 2021-04-01 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-04
PH_501233 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50781 | OMG 05 | Water |  | NONINF | DWQ Reliability |  | 2018-03-22 | 2019-10-28 | 2020-03-16 | 2020-12-01 | 2021-04-01 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_500138 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50821 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-02-26 | 2016-04-20 | 2019-03-01 | 2019-06-01 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500138 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_108 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-02-26 | 2016-04-20 | 2019-02-01 | 2019-03-01 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500032 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | 53018 | OMG 04 | Water |  | SWMD | SOSI |  | 2017-03-31 | 2017-12-22 | 2018-03-26 | 2018-12-01 | 2019-03-01 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-04
PH_500032 | Q&S4 | Improving drinking water availability and resilience of service | SOSI | 53018 | OMG 08 | Water |  | SWMD | SOSI |  | 2017-03-31 | 2017-12-22 | 2018-03-26 | 2018-12-01 | 2019-03-01 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-08
PH_500475 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_030 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2015-10-15 | 2017-03-28 | 2017-06-20 | 2019-08-01 | 2019-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_500475 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_029 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2015-10-15 | 2017-03-28 | 2017-06-20 | 2019-08-01 | 2019-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_500475 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_028 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2015-10-15 | 2017-03-28 | 2017-06-20 | 2019-07-01 | 2019-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_500475 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_005 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2015-10-15 | 2017-03-28 | 2017-06-20 | 2018-12-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_500475 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_004 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2015-10-15 | 2017-03-28 | 2017-06-20 | 2019-06-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_500475 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_003 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2015-10-15 | 2017-03-28 | 2017-06-20 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501039 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_002 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-11 | 2018-02-02 | 2018-09-01 | 2019-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501039 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_013 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-11 | 2018-02-02 | 2018-09-01 | 2019-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501039 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_001 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-11 | 2018-02-02 | 2018-09-01 | 2019-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501039 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_006 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-11 | 2018-02-02 | 2018-09-01 | 2019-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501039 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_007 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-11 | 2018-02-02 | 2018-09-01 | 2019-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501039 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_009 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-11 | 2018-02-02 | 2018-09-01 | 2019-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501039 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_010 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-11 | 2018-02-02 | 2018-09-01 | 2019-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501039 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_011 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-11 | 2018-02-02 | 2018-09-01 | 2019-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501039 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_012 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-11 | 2018-02-02 | 2018-09-01 | 2019-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501039 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_008 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2016-07-19 | 2017-12-11 | 2018-02-02 | 2018-09-01 | 2019-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_021 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-05-01 | 2019-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_020 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-04-01 | 2019-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_019 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2020-02-01 | 2020-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_018 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_017 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-04-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_048 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-07-01 | 2019-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_049 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-10-01 | 2020-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_037 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-07-01 | 2019-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_024 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2020-01-01 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_023 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-11-01 | 2020-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_050 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_035 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-09-01 | 2019-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_036 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-05-01 | 2019-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501144 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_022 | OMG 05 | Water |  | SWMD | DWQ Reliability |  | 2017-03-27 | 2018-03-23 | 2018-06-12 | 2019-07-01 | 2019-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501145 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_015 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501145 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_016 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501145 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_031 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501145 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_033 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501145 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_034 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501145 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_014 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501145 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_032 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-19 | 2018-03-26 | 2018-03-27 | 2018-06-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_045 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-07-24 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_046 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-07-24 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_044 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-07-24 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_043 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-07-24 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_042 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-07-24 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_041 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-07-24 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_040 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-07-24 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_039 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-07-24 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_038 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-07-24 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_027 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-07-24 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_025 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-07-24 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_047 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-07-24 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50476_026 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2018-03-26 | 2019-03-27 | 2019-07-24 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_500481 | Q&S4 | Reducing long term cost of service | Renewable power | 50310_001 | OMG 43 | Water |  | SWD | Renewable power |  | 2015-05-19 | 2015-12-23 | 2016-01-07 | 2016-05-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-43: 0.04
PH_500481 | Q&S4 | Reducing long term cost of service | Renewable power | 50310_003 | OMG 43 | Water |  | SWD | Renewable power |  | 2015-05-19 | 2015-12-23 | 2016-01-07 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-43: 0.053
PH_500481 | Q&S4 | Reducing long term cost of service | Renewable power | 50310_004 | OMG 43 | Water |  | SWD | Renewable power |  | 2015-05-19 | 2015-12-23 | 2016-01-07 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-43: 0.05
PH_500481 | Q&S4 | Reducing long term cost of service | Renewable power | 50310_005 | OMG 43 | Water |  | SWD | Renewable power |  | 2015-05-19 | 2015-12-23 | 2016-01-07 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-43: 0.08
PH_500481 | Q&S4 | Reducing long term cost of service | Renewable power | 50310_006 | OMG 43 | Water |  | SWD | Renewable power |  | 2015-05-19 | 2015-12-23 | 2016-01-07 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-43: 0.2
PH_501619 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50778 | OMG 04 | Water |  | SWMD | DWQ Compliance |  | 2016-03-25 | 2016-06-01 | 2016-06-01 | 2016-12-01 | 2020-10-01 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-04
PH_501619 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50112 | OMG 05 | Water |  | SWMD | DWQ Compliance |  | 2016-03-25 | 2016-06-01 | 2016-06-01 | 2016-12-01 | 2020-10-01 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_500140 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_008 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-07-21 | 2016-08-11 | 2019-09-01 | 2019-12-01 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500140 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50719 | OMG 23 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-07-21 | 2016-08-11 | 2019-09-01 | 2019-12-01 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500140 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_110 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-07-21 | 2016-08-11 | 2019-07-01 | 2019-12-01 | Inverclyde | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500150 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_006 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-02-28 | 2017-03-21 | 2019-06-01 | 2019-08-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500150 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_001 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-02-28 | 2017-03-21 | 2019-06-01 | 2019-09-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_502944 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_17 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-26 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_12 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-26 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_13 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-26 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_14 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-26 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_10 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-26 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_16 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-26 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_09 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-26 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_18 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-26 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_15 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-26 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_03 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-26 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_01 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-26 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_11 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-26 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_02 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-26 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_08 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-26 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_04 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-26 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_05 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-26 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_06 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-26 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502944 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_07 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-26 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_39 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-29 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_38 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-29 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_29 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-29 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_36 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-29 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_35 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-29 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_34 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-29 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_33 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-29 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_32 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-29 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_31 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-29 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_24 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-29 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_30 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-29 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_37 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-29 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_27 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-29 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_25 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-29 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_23 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-29 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_22 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-29 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_21 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-29 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_20 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-29 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_19 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-29 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_26 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-29 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502945 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50663_28 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-05-29 | 2020-11-01 | 2021-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502946 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_05 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-06-30 | 2020-12-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502946 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_07 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-06-30 | 2020-12-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502946 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_09 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-06-30 | 2020-12-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502946 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_08 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-06-30 | 2020-12-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502946 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_06 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-27 | 2020-02-24 | 2020-06-30 | 2020-12-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502947 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_10 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-22 | 2020-02-24 | 2020-06-30 | 2020-12-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502947 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_12 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-22 | 2020-02-24 | 2020-06-30 | 2020-12-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502947 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_13 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-22 | 2020-02-24 | 2020-06-30 | 2020-12-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502947 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_11 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-22 | 2020-02-24 | 2020-06-30 | 2020-12-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502947 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_14 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-03-22 | 2020-02-24 | 2020-06-30 | 2020-12-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502943 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_02 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-02-23 | 2020-02-24 | 2020-06-30 | 2020-12-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502943 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_01 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-02-23 | 2020-02-24 | 2020-06-30 | 2020-12-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502943 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_04 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-02-23 | 2020-02-24 | 2020-06-30 | 2020-12-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_502943 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50904_03 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2018-02-23 | 2020-02-24 | 2020-06-30 | 2020-12-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_503103 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 59065_01 | OMG 07 | Water |  | WINF | Supply Resilience |  | 2018-06-26 | 2019-12-16 | 2020-03-02 | 2021-08-01 | 2021-11-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-07
PH_503103 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 59065_01 | OMG 08 | Water |  | WINF | Supply Resilience |  | 2018-06-26 | 2019-12-16 | 2020-03-02 | 2021-08-01 | 2021-11-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-08
PH_503052 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 59017a | OMG 47 | Water |  | SWD | DWQ Reliability |  | 2018-02-02 | 2018-06-26 | 2018-08-01 | 2019-09-01 | 2019-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_503052 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 59129a | OMG 47 | Water |  | SWD | DWQ Reliability |  | 2018-02-02 | 2018-06-26 | 2018-08-01 | 2019-09-01 | 2019-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_502767 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59107a | OMG 47 | Water |  | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-01-01 | 2020-04-01 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_502767 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59106a | OMG 47 | Water |  | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-01-01 | 2020-04-01 | All West Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_502768 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59108a | OMG 47 | Water |  | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-01-01 | 2020-04-01 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_502768 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59122a | OMG 47 | Water |  | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-01-01 | 2020-04-01 | All North Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_502769 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59111a | OMG 47 | Water |  | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-01-01 | 2020-04-01 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_502769 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59112a | OMG 47 | Water |  | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-01-01 | 2020-04-01 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_502769 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59105a | OMG 47 | Water |  | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-29 | 2020-01-01 | 2020-04-01 | All South Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_502770 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59003a | OMG 47 | Water |  | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-08 | 2020-01-01 | 2020-04-01 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_502770 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59109a | OMG 47 | Water |  | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-08 | 2020-01-01 | 2020-04-01 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_502770 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ - Preparing for Future Investment | 59119a | OMG 47 | Water |  | SWD | DWQ - Preparing for Future Investment |  | 2017-06-21 | 2018-01-08 | 2018-01-08 | 2020-01-01 | 2020-04-01 | All East Unitary Authorities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500142 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_112 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-27 | 2016-06-29 | 2016-07-07 | 2019-07-01 | 2019-11-01 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500142 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50307_TE_500307_009 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-27 | 2016-06-29 | 2016-07-07 | 2019-08-01 | 2019-11-01 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500142 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_072 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-27 | 2016-06-29 | 2016-07-07 | 2019-07-01 | 2019-11-01 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500142 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50287 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-27 | 2016-06-29 | 2016-07-07 | 2019-08-01 | 2019-11-01 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500142 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50828 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-27 | 2016-06-29 | 2016-07-07 | 2019-08-01 | 2019-11-01 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_403975 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_501120_001 | OMG 17 | Wastewater |  | WWINF | UWWTD - Works |  | 2015-03-10 | 2016-03-23 | 2016-04-01 | 2018-03-01 | 2018-03-01 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-17
PH_403975 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_501120_003 | OMG 17 | Wastewater |  | WWINF | UWWTD - Works |  | 2015-03-10 | 2016-03-23 | 2016-04-01 | 2018-03-01 | 2018-03-01 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-17
PH_500144 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50824 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-02-26 | 2016-04-19 | 2018-12-01 | 2019-03-01 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500144 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_125 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-02-26 | 2016-04-19 | 2019-01-01 | 2019-03-01 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500145 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50808 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-05-26 | 2016-06-20 | 2018-12-01 | 2019-06-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500145 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_128 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-05-26 | 2016-06-20 | 2019-01-01 | 2019-03-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500152 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_129 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-19 | 2016-03-28 | 2017-11-01 | 2018-01-01 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500152 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Largs | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-19 | 2016-03-28 | 2018-03-01 | 2018-06-01 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500154 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50288 | OMG 23 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-03-28 | 2017-05-30 | 2020-05-01 | 2020-08-01 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500154 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_134 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-03-28 | 2017-05-30 | 2019-12-01 | 2020-03-01 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500154 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_010 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-03-28 | 2017-05-30 | 2020-05-01 | 2020-08-01 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500154 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50407_Leven | OMG 23 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2017-03-28 | 2017-05-30 | 2020-05-01 | 2020-08-01 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500156 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_135 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-19 | 2016-03-22 | 2017-07-01 | 2017-08-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500156 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50809 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-19 | 2016-03-22 | 2017-11-01 | 2018-03-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500159 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50291 | OMG 23 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-07-29 | 2016-07-29 | 2019-03-01 | 2019-07-01 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500159 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_136 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-07-29 | 2016-07-29 | 2018-09-01 | 2018-11-01 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500159 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_011 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-07-29 | 2016-07-29 | 2019-01-01 | 2019-07-01 | West Lothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_501642 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50767 | OMG 05 | Water |  | SWD | DWQ Reliability |  | 2017-03-29 | 2018-12-21 | 2019-05-15 | 2019-08-01 | 2019-11-01 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-05
PH_501642 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50767 | OMG 04 | Water |  | SWD | DWQ Reliability |  | 2017-03-29 | 2018-12-21 | 2019-05-15 | 2019-08-01 | 2019-11-01 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-04
PH_500107 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50305_TE_500305_020 | OMG 22 | Wastewater |  | SWMD | UWWTD - Works |  | 2015-03-20 | 2016-12-20 | 2017-01-23 | 2018-12-01 | 2019-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500107 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50489 | OMG 23 | Wastewater |  | SWMD | UWWTD - Works |  | 2015-03-20 | 2016-12-20 | 2017-01-23 | 2018-12-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500107 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50305_TE_500305_189 | OMG 22 | Wastewater |  | SWMD | UWWTD - Works |  | 2015-03-20 | 2016-12-20 | 2017-01-23 | 2018-12-01 | 2019-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500107 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 50305_TE_500305_086 | OMG 22 | Wastewater |  | SWMD | UWWTD - Works |  | 2015-03-20 | 2016-12-20 | 2017-01-23 | 2018-12-01 | 2019-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500161 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_140 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-05-30 | 2016-08-05 | 2018-12-01 | 2019-02-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500161 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50810 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-05-30 | 2016-08-05 | 2019-06-01 | 2019-06-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500835 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50195 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-03-07 | 2018-03-28 | 2018-06-19 | 2020-03-01 | 2020-10-01 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 183.03
PH_500835 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53194 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-03-07 | 2018-03-28 | 2018-06-19 | 2020-03-01 | 2020-10-01 | Aberdeen City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 18.86
PH_500206 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50051_003 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-09-29 | 2017-09-29 | 2020-06-01 | 2021-03-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500206 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50051_004 | OMG 06 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-09-29 | 2017-09-29 | 2019-10-01 | 2021-03-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 24.64
PH_500206 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50051_002 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-09-29 | 2017-09-29 | 2019-02-01 | 2019-10-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500206 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50051_001 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-09-29 | 2017-09-29 | 2019-07-01 | 2020-04-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500165 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_142 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-11-28 | 2017-01-23 | 2018-09-01 | 2018-10-01 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500165 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50834 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-19 | 2016-11-28 | 2017-01-23 | 2018-12-01 | 2019-03-01 | Scottish Borders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500007 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50053_003 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-25 | 2016-03-31 | 2016-07-31 | 2018-06-01 | 2019-03-01 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500007 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50053_002 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-25 | 2016-03-31 | 2016-07-31 | 2018-03-01 | 2019-03-01 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500007 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50053_001 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-25 | 2016-03-31 | 2016-07-31 | 2018-06-01 | 2019-03-01 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500008 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50054_005 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-26 | 2016-03-31 | 2016-08-22 | 2017-12-01 | 2019-03-01 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500008 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50054_003 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-26 | 2016-03-31 | 2016-08-22 | 2017-12-01 | 2019-02-01 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500008 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50054_004 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-26 | 2016-03-31 | 2016-08-22 | 2018-05-01 | 2019-03-01 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500008 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50054_001 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-26 | 2016-03-31 | 2016-08-22 | 2017-12-01 | 2019-02-01 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500009 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50055_003 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-23 | 2016-03-30 | 2016-05-02 | 2017-12-01 | 2018-12-01 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500009 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50055_001 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-23 | 2016-03-30 | 2016-05-02 | 2017-12-01 | 2018-12-01 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500010 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50056_002 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-25 | 2016-03-31 | 2016-06-20 | 2018-12-01 | 2019-09-01 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500010 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50056_001 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-02-25 | 2016-03-31 | 2016-06-20 | 2018-08-01 | 2019-03-01 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500207 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_001 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-06-01 | 2019-02-01 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500207 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_009 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2020-05-01 | 2021-05-01 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500207 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_003 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-06-01 | 2019-02-01 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500207 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_005 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-06-01 | 2019-02-01 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500207 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_006 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-03-01 | 2019-03-01 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500207 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_008 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-03-01 | 2019-02-01 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500207 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_002 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-06-01 | 2019-02-01 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500207 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_010 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-03-01 | 2019-06-01 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500207 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_011 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2019-10-01 | 2020-10-01 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500207 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_007 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-03-01 | 2019-02-01 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500207 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50059_004 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-27 | 2017-02-07 | 2017-02-09 | 2018-06-01 | 2019-02-01 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500162 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_149 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-19 | 2016-03-23 | 2017-11-01 | 2018-01-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500162 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Nairn | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-01-19 | 2016-03-23 | 2017-12-01 | 2018-03-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500867 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50219 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-09-06 | 2018-09-20 | 2018-12-10 | 2019-12-01 | 2020-12-01 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 90.16
PH_500867 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53196 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-09-06 | 2018-09-20 | 2018-12-10 | 2019-12-01 | 2020-12-01 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 12.7
PH_500088 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named | 50426 | OMG 30 | Wastewater |  | SWD | Flooding Named |  | 2019-06-24 | 2020-06-01 | 2020-08-19 | 2021-03-01 | 2021-02-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_500088 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named | 50426 | OMG 32 | Wastewater |  | SWD | Flooding Named |  | 2019-06-24 | 2020-06-01 | 2020-08-19 | 2021-03-01 | 2021-02-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_500169 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_158 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-03-16 | 2016-05-23 | 2017-07-01 | 2017-09-01 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500169 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50814 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-03-16 | 2016-05-23 | 2017-07-01 | 2018-03-01 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500171 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_160 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-04-29 | 2016-06-30 | 2017-05-01 | 2017-10-01 | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500171 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50826 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-04-29 | 2016-06-30 | 2017-05-01 | 2018-01-01 | Midlothian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500168 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_012 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-09-30 | 2016-09-30 | 2019-05-01 | 2019-08-01 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500168 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_162 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-09-30 | 2016-09-30 | 2019-05-01 | 2019-08-01 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500210 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50063_002 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-20 | 2017-09-29 | 2017-09-29 | 2018-12-01 | 2019-12-01 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500210 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50063_001 | OMG 02 | Water |  | WINF | DWQ Compliance |  | 2015-03-20 | 2017-09-29 | 2017-09-29 | 2019-03-01 | 2020-03-01 | Perth and Kinross | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500170 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_164 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2019-05-01 | 2019-08-01 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500170 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_013 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2019-05-01 | 2019-08-01 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500170 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_007 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2019-05-01 | 2019-08-01 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500211 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50064_003 | OMG 06 | Water |  | SWD | DWQ Compliance |  | 2015-03-27 | 2016-03-31 | 2016-05-30 | 2018-06-01 | 2019-10-01 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 6.37
PH_500211 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50064_001 | OMG 02 | Water |  | SWD | DWQ Compliance |  | 2015-03-27 | 2016-03-31 | 2016-05-30 | 2018-01-01 | 2018-06-01 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500211 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50064_002 | OMG 02 | Water |  | SWD | DWQ Compliance |  | 2015-03-27 | 2016-03-31 | 2016-05-30 | 2018-01-01 | 2018-06-01 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_403090 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50148-OMG01 | OMG 01 | Water |  | WINF | DWQ Compliance |  | 2013-01-17 | 2016-09-26 | 2016-09-27 | 2020-05-01 | 2020-07-01 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-01
PH_403090 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50148-OMG20 | OMG 20 | Water |  | WINF | DWQ Compliance |  | 2013-01-17 | 2016-09-26 | 2016-09-27 | 2020-05-01 | 2020-07-01 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-20
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_043 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_041 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_042 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_045 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_029 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_015 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_016 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_017 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_019 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_044 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_021 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_022 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_023 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_024 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_025 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_026 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_014 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_028 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_018 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_030 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_031 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_032 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_033 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_034 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_035 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_036 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_037 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-11-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_038 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_039 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_040 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_027 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_004 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-03-01 | 2016-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_020 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_013 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_049 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_048 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_047 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_046 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_001 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_003 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_050 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_005 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_006 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_007 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_008 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_009 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_010 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_011 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_012 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500095 | Q&S4 | Climate Change | Climate Change | 51306_TE_501306_002 | OMG 45 | Water |  | SWMD | Climate Change |  | 2015-03-09 | 2015-09-28 | 2015-09-28 | 2016-09-01 | 2016-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-45
PH_500106 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50492 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-12-14 | 2017-01-06 | 2019-07-01 | 2019-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500106 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_067 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-12-14 | 2017-01-06 | 2018-07-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500106 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_RiCarron | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-31 | 2016-12-14 | 2017-01-06 | 2019-02-01 | 2019-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-23: 2
PH_500100 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_109 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2017-03-28 | 2017-03-28 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500100 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_111 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2017-03-28 | 2017-03-28 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500100 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50408 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2017-03-28 | 2017-03-28 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500101 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_180 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2017-02-28 | 2017-03-09 | 2020-01-01 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500101 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50490 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2017-02-28 | 2017-03-09 | 2020-01-01 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500101 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_190 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2017-02-28 | 2017-03-09 | 2020-01-01 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500101 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_059 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2017-02-28 | 2017-03-09 | 2020-01-01 | 2020-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500654 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven | 50443 | OMG 32 | Wastewater |  | WWINF | Flooding Demand Driven |  | 2018-07-09 | 2020-01-27 | 2020-04-06 | 2020-10-01 | 2021-01-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_500654 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven | 50443 | OMG 30 | Wastewater |  | WWINF | Flooding Demand Driven |  | 2018-07-09 | 2020-01-27 | 2020-04-06 | 2020-10-01 | 2021-01-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_501640 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-2 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-1 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-1 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-7 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-3 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-2 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-56 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-57 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-4 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-59 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-1 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-2 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-3 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-4 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-6 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-8 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-9 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50542-58 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-4 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-5 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501640 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-3 | OMG 10 | Water |  | SWD | SEMD |  | 2015-03-31 | 2016-03-22 | 2016-03-29 | 2016-12-01 | 2016-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-18 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-07-01 | 2017-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-100 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-107 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-106 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-105 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-104 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-103 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-102 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-101 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-10 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55051-5 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55051-4 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55051-2 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55051-3 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-02-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-19 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-07-01 | 2017-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-17 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-07-01 | 2017-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-108 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 50525-20 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-07-01 | 2017-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-60 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-72 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-71 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-70 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-69 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-68 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-67 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-66 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-65 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-64 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-63 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-48 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-61 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-75 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-02-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-59 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-58 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-57 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-56 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-55 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-54 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-53 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-52 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-51 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2019-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-50 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-49 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-62 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-88 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-109 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55051-1 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-99 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-98 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-97 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-96 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-95 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-94 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-93 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-92 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-91 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-73 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-02-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-89 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-74 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-87 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-86 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-85 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-84 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-83 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-82 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-81 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-80 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-78 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-76 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-77 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-90 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-118 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-20 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-19 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-18 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-17 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-16 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-15 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-14 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-02-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-13 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-123 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-122 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-21 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-119 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-121 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-117 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-116 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-02-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-115 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-114 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-113 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-112 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-111 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-47 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-79 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-11 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-110 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-120 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-36 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-46 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-44 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-43 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-12 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-22 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-42 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-41 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-40 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-02-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-39 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-45 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-11-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-37 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-35 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-34 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-29 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2019-06-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-38 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-33 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-26 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2018-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-24 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-28 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-25 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2017-12-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-30 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-31 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-32 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-23 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501244 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55055-27 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2016-03-31 | 2016-03-31 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-57 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-56 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-58 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-54 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-59 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-60 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-61 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-67 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-66 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-42 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-65 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-63 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-64 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-62 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-52 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-51 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-50 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-49 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-48 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-47 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-46 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-45 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-43 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-41 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-68 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-95 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-40 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-39 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-44 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-94 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-93 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-87 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-88 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-89 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-90 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-85 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-92 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-84 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-96 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-97 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-98 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-99 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-38 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-53 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-91 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-77 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-70 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-71 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-72 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-73 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-74 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-86 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-76 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-69 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-78 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-79 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-80 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-81 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-82 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-83 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-75 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_14 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-114 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-113 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-112 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-111 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-110 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-109 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-108 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-107 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-106 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-105 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-104 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-103 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-102 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-115 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_06 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-55 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-37 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_01 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_02 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_03 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-101 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_05 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-100 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2017-12-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_08 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_10 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_11 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_12 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_13 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_09 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_04 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-30 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-128 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-129 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-130 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-131 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-132 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-133 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-134 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-135 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-127 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-29 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-136 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-31 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-32 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-33 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-34 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-116 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55052_07 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-36 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-35 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-137 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-120 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-125 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-124 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-123 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-122 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-121 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-12-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-118 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-117 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-119 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501245 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55056-126 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2017-09-20 | 2017-12-04 | 2018-09-01 | 2018-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-49 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-63 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-42 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-41 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-40 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-11 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-99 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-93 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-91 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-98 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-04-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-92 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-94 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-95 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-90 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-96 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-02-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-97 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-04-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-52 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-51 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-53 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-33 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-5 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-50 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-54 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-34 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-56 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-44 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-57 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-58 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-59 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-55 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-02-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-37 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-41 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-04-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-40 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-74 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-6 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-43 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-4 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-46 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-38 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-49 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-36 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-35 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-45 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-42 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-47 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-48 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-39 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-83 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-04-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-79 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-05-01 | 2019-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-8 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-32 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-12 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-02-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-80 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-72 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-82 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-76 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-84 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-85 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-86 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-87 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-88 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-89 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-81 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-04-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-69 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-61 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-62 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-63 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-64 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-65 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-66 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-05-01 | 2019-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-78 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-68 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-77 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-7 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-70 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-71 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-73 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-75 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-60 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-67 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-7 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-11 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-109 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-108 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-107 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-106 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-105 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-02-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-103 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-14 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-101 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-100 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-10 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-13 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-8 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-104 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-02-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-6 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-06-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-5 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-4 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-07-01 | 2019-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-3 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-2 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-08-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-14 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-02-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-13 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-12 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-11 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-10 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2017-12-01 | 2018-08-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-1 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-9 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-1 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-23 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-31 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-30 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-3 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-29 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-04-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-28 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-27 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-26 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-02-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-15 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-24 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-22 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-21 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-102 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-20 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-04-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-2 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-19 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-04-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-18 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-17 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-16 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501246 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55057-25 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-02-19 | 2018-02-19 | 2019-03-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-34 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-24 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-29 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-32 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-31 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-30 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-3 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-33 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-28 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-27 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-22 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-25 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-23 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-35 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-47 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-26 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-21 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-53 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-52 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-51 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-50 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-5 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-48 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-45 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-46 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-36 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-44 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-43 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-4 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-39 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-38 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-37 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-12 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-14 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-14 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-3 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-2 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-19 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-18 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-17 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-5 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-15 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-6 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-13 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-12 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-11 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-10 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-1 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55053-9 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-16 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-101 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-2 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-19 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-18 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-17 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-16 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-15 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-4 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-56 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-20 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-100 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-10 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-1 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-9 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-8 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55054-7 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-13 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-9 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-8 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-80 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-81 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-82 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-83 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-84 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-85 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-86 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-87 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-79 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-89 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-93 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-90 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-91 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-92 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-55 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-94 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-54 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-96 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-97 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-98 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-99 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-88 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-64 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-95 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-78 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-57 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-58 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-59 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-6 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-60 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-62 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-65 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-66 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-67 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-74 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-77 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-76 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-61 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-75 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-68 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-73 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-72 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-71 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-70 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-7 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_501247 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 55058-69 | OMG 10 | Water |  | SWMD | SEMD |  | 2015-03-31 | 2018-11-29 | 2018-11-29 | 2020-07-01 | 2020-10-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_500703 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-3 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-05-25 | 2016-05-30 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_500703 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-2 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-05-25 | 2016-05-30 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_500703 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-1 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-05-25 | 2016-05-30 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_500703 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-4 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-05-25 | 2016-05-30 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_501622 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-7 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-09-26 | 2016-09-29 | 2017-10-01 | 2018-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_501622 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-6 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-09-26 | 2016-09-29 | 2017-10-01 | 2018-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_501622 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-5 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-09-26 | 2016-09-29 | 2017-10-01 | 2018-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_501622 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 53007-8 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-09-26 | 2016-09-29 | 2017-10-01 | 2018-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_500702 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-11 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-06-27 | 2016-06-29 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_500702 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-2 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-06-27 | 2016-06-29 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_500702 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-12 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-06-27 | 2016-06-29 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_500702 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-1 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-06-27 | 2016-06-29 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_500702 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-10 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2016-06-27 | 2016-06-29 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_501621 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-7 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2019-04-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_501621 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-3 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2019-04-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_501621 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-9 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2019-04-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_501621 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-8 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2019-04-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_501621 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-6 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2019-04-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_501621 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-5 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2019-04-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_501621 | Q&S4 | Protecting and enhancing the environment | Compliance Assessment Scheme | 50306-4 | OMG 27 | Wastewater |  | SWMD | Compliance Assessment Scheme |  | 2015-12-21 | 2017-09-28 | 2017-09-29 | 2018-04-01 | 2018-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-27
PH_403762 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 53307 | OMG 47 | Water |  | SWMD | DWQ Compliance |  | 2014-05-02 | 2015-03-30 | 2015-03-30 | 2016-10-01 | 2017-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_403762 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50091_TE_500091_01 | OMG 47 | Water |  | SWMD | DWQ Compliance |  | 2014-05-02 | 2015-03-30 | 2015-03-30 | 2017-02-01 | 2017-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_403762 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50150 | OMG 47 | Water |  | SWMD | DWQ Compliance |  | 2014-05-02 | 2015-03-30 | 2015-03-30 | 2017-01-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_403762 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50750 | OMG 47 | Water |  | SWMD | DWQ Compliance |  | 2014-05-02 | 2015-03-30 | 2015-03-30 | 2017-01-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_403762 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50751 | OMG 47 | Water |  | SWMD | DWQ Compliance |  | 2014-05-02 | 2015-03-30 | 2015-03-30 | 2017-01-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_403762 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50102 | OMG 47 | Water |  | SWMD | DWQ Compliance |  | 2014-05-02 | 2015-03-30 | 2015-03-30 | 2017-02-01 | 2017-05-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_500178 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Skelly | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2015-11-30 | 2016-01-12 | 2018-10-01 | 2019-03-01 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500178 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_179 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2015-11-30 | 2016-01-12 | 2018-11-01 | 2019-03-01 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_503082 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50097 | OMG 01 | Water |  | WINF | DWQ Compliance |  | 2015-11-02 | 2020-08-17 | 2020-11-30 | 2022-03-01 | 2022-07-01 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-01
PH_503082 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 53019 | OMG 08 | Water |  | WINF | DWQ Compliance |  | 2015-11-02 | 2020-08-17 | 2020-11-30 | 2022-03-01 | 2022-07-01 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-08
PH_502422 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_4 | OMG 10 | Water |  | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502422 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_5 | OMG 10 | Water |  | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502422 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_6 | OMG 10 | Water |  | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502422 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_7 | OMG 10 | Water |  | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502422 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_8 | OMG 10 | Water |  | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-09-01 | 2017-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502422 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_9 | OMG 10 | Water |  | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2018-12-01 | 2019-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502422 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_2 | OMG 10 | Water |  | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502422 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_3 | OMG 10 | Water |  | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502422 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_1 | OMG 10 | Water |  | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_502422 | Q&S4 | Improving drinking water availability and resilience of service | SEMD | 402892_10 | OMG 10 | Water |  | SWD | SEMD |  | 2012-09-14 | 2014-05-29 | 2014-05-29 | 2017-09-01 | 2017-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-10
PH_403332 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named | 50411 | OMG 30 | Wastewater |  | SWD | Flooding Named |  | 2013-03-11 | 2021-01-11 | 2021-02-03 | 2021-03-01 | 2021-07-01 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_403332 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named | 50411 | OMG 32 | Wastewater |  | SWD | Flooding Named |  | 2013-03-11 | 2021-01-11 | 2021-02-03 | 2021-03-01 | 2021-07-01 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_403146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50792 | OMG 04 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2018-03-01 | 2018-03-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-04
PH_403146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_004 | OMG 20 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2022-08-01 | 2022-12-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-20
PH_403146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_003 | OMG 20 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2022-08-01 | 2022-12-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-20
PH_403146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_005 | OMG 20 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2022-08-01 | 2022-12-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-20
PH_403146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_006 | OMG 20 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2022-08-01 | 2022-12-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-20
PH_403146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_007 | OMG 20 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2022-08-01 | 2022-12-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-20
PH_403146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_008 | OMG 20 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2022-08-01 | 2022-12-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-20
PH_403146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_009 | OMG 20 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2022-08-01 | 2022-12-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-20
PH_403146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_010 | OMG 20 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2022-08-01 | 2022-12-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-20
PH_403146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50161 | OMG 01 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2018-09-01 | 2018-09-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-01
PH_403146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_001 | OMG 01 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2018-03-01 | 2019-02-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-01
PH_403146 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50149_002 | OMG 20 | Water |  | WINF | DWQ Compliance |  | 2013-06-19 | 2016-01-25 | 2016-02-22 | 2022-08-01 | 2022-12-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-20
PH_403321 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named | 50410 | OMG 32 | Wastewater |  | WWINF | Flooding Named |  | 2013-02-26 | 2020-05-18 | 2020-07-10 | 2022-03-01 | 2022-03-01 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_403321 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named | 50410 | OMG 30 | Wastewater |  | WWINF | Flooding Named |  | 2013-02-26 | 2020-05-18 | 2020-07-10 | 2022-03-01 | 2022-03-01 | North Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_403696 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named | 50482 | OMG 32 | Wastewater |  | SWMD | Flooding Named |  | 2014-03-03 | 2014-12-05 | 2015-01-12 | 2015-09-01 | 2015-09-01 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_403696 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named | 50482 | OMG 30 | Wastewater |  | SWMD | Flooding Named |  | 2014-03-03 | 2014-12-05 | 2015-01-12 | 2015-09-01 | 2015-09-01 | East Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_403671 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_001 | OMG 23 | Wastewater |  | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2018-01-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_403671 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_002 | OMG 23 | Wastewater |  | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2019-02-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_403671 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_003 | OMG 23 | Wastewater |  | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2018-01-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_403671 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_004 | OMG 23 | Wastewater |  | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2018-01-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_403671 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_010 | OMG 23 | Wastewater |  | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2018-11-01 | 2018-11-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_403671 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_009 | OMG 23 | Wastewater |  | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2018-01-01 | 2018-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_403671 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_006 | OMG 23 | Wastewater |  | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2018-11-01 | 2019-01-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_403671 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_51141_007 | OMG 23 | Wastewater |  | SWMD | UWWTD - Works |  | 2014-02-18 | 2015-03-31 | 2015-03-31 | 2019-01-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_402949 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 51163_001 | OMG 17 | Wastewater |  | SWMD | UWWTD - Works |  | 2012-10-30 | 2018-12-01 | 2018-12-01 | 2020-12-01 | 2021-03-01 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-17
PH_402949 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 51163_002 | OMG 18 | Wastewater |  | SWMD | UWWTD - Works |  | 2012-10-30 | 2018-12-01 | 2018-12-01 | 2023-08-01 | 2023-09-01 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-18
PH_402949 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | 51163_001 | OMG 18 | Wastewater |  | SWMD | UWWTD - Works |  | 2012-10-30 | 2018-12-01 | 2018-12-01 | 2023-08-01 | 2023-09-01 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-18
PH_404026 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named | 50439 | OMG 32 | Wastewater |  | WWINF | Flooding Named |  | 2015-10-12 | 2020-01-13 | 2020-02-24 | 2021-10-01 | 2021-11-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_404026 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named | 50439 | OMG 30 | Wastewater |  | WWINF | Flooding Named |  | 2015-10-12 | 2020-01-13 | 2020-02-24 | 2021-10-01 | 2021-11-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_403983 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_501131_001 | OMG 17 | Wastewater |  | WWINF | UWWTD - Works |  | 2015-03-10 | 2016-03-23 | 2016-03-29 | 2018-11-01 | 2018-11-01 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-17
PH_403983 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_501131_003 | OMG 17 | Wastewater |  | WWINF | UWWTD - Works |  | 2015-03-10 | 2016-03-23 | 2016-03-29 | 2018-03-01 | 2018-03-01 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-17
PH_403983 | Q&S4 | Protecting and enhancing the environment | UWWTD - Works | TE_501131_002 | OMG 17 | Wastewater |  | WWINF | UWWTD - Works |  | 2015-03-10 | 2016-03-23 | 2016-03-29 | 2018-05-01 | 2018-11-01 | Argyll and Bute-Cowal & Bute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-17
PH_404042 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named | 50469 | OMG 30 | Wastewater |  | WWINF | Flooding Named |  | 2018-07-25 | 2019-10-07 | 2020-01-13 | 2020-04-01 | 2020-07-01 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_404042 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named | 50469 | OMG 32 | Wastewater |  | WWINF | Flooding Named |  | 2018-07-25 | 2019-10-07 | 2020-01-13 | 2020-04-01 | 2020-07-01 | South Lanarkshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_403817 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50403_TE_500403_001_N03 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2016-07-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-47: 8
PH_403817 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50403_TE_500403_001_N02 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2018-09-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_403817 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50403_TE_500403_001_N04 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2018-09-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-47: 8
PH_403817 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50403_TE_500403_001_N05 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2018-09-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-47: 8
PH_403817 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50403_TE_500403_001_N06 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2018-09-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-47: 8
PH_403817 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50403_TE_500403_001_N07 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2018-09-01 | 2019-04-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-47: 9
PH_403817 | Q&S4 | Improving drinking water availability and resilience of service | Supply Resilience | 50403_TE_500403_001_N01 | OMG 47 | Water |  | SWD | Supply Resilience |  | 2014-05-26 | 2016-02-17 | 2016-02-17 | 2017-06-01 | 2017-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-47
PH_403690 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named | 50479 | OMG 32 | Wastewater |  | SWD | Flooding Named |  | 2014-04-28 | 2018-03-12 | 2019-04-01 | 2018-03-01 | 2019-04-01 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_403690 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named | 50479 | OMG 30 | Wastewater |  | SWD | Flooding Named |  | 2014-04-28 | 2018-03-12 | 2019-04-01 | 2018-03-01 | 2019-04-01 | Renfrewshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_403697 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named | 50456 | OMG 32 | Wastewater |  | SWD | Flooding Named |  | 2014-04-28 | 2021-06-28 | 2021-09-10 | 2022-09-01 | 2022-12-01 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_403697 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Named | 50456 | OMG 30 | Wastewater |  | SWD | Flooding Named |  | 2014-04-28 | 2021-06-28 | 2021-09-10 | 2022-09-01 | 2022-12-01 | Glasgow City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_403605 | Q&S4 | Protecting and enhancing the environment | Sludge | 51145 | OMG 24 | Wastewater |  | SWMD | Sludge |  | 2013-10-31 | 2018-03-20 | 2018-03-26 | 2020-04-01 | 2020-07-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-24
PH_403605 | Q&S4 | Protecting and enhancing the environment | Sludge | 59080_01 | OMG 24 | Wastewater |  | SWMD | Sludge |  | 2013-10-31 | 2018-03-20 | 2018-03-26 | 2020-04-01 | 2020-07-01 | Highland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-24
PH_502976 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven | 51300 | OMG 30 | Wastewater |  | SWMD | Flooding Demand Driven |  | 2017-12-12 | 2017-12-12 | 2018-02-08 | 2019-04-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_502976 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven | 50378 | OMG 30 | Wastewater |  | SWMD | Flooding Demand Driven |  | 2017-12-12 | 2017-12-12 | 2018-02-08 | 2019-04-01 | 2019-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_500173 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_181 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-04-29 | 2016-06-20 | 2018-12-01 | 2019-02-01 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500173 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50290 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-04-29 | 2016-06-20 | 2019-03-01 | 2019-09-01 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500175 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50836 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2015-09-28 | 2015-11-13 | 2017-05-01 | 2018-01-01 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500175 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_182 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2015-09-28 | 2015-11-13 | 2017-05-01 | 2017-07-01 | Fife | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500176 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_184 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2019-07-01 | 2019-12-01 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500176 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50815 | OMG 23 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2019-09-01 | 2019-12-01 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500176 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50407_Steven | OMG 23 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2019-09-01 | 2019-12-01 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500176 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_014 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-27 | 2016-11-02 | 2016-11-28 | 2019-09-01 | 2019-12-01 | North Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500179 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_185 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-06-21 | 2016-08-24 | 2019-01-01 | 2019-03-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500179 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Stewa | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-06-21 | 2016-08-24 | 2019-03-01 | 2019-06-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500179 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50816 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-06-21 | 2016-08-24 | 2018-12-01 | 2019-03-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500180 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50305_TE_500305_186 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-05-31 | 2016-06-27 | 2019-06-01 | 2019-07-01 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500180 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50307_TE_500307_015 | OMG 22 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-05-31 | 2016-06-27 | 2019-06-01 | 2019-07-01 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500180 | Q&S4 | Protecting and enhancing the environment | Flood Risk Management Act | 50407_Stirl | OMG 23 | Wastewater |  | SWMD | Flood Risk Management Act |  | 2015-03-26 | 2016-05-31 | 2016-06-27 | 2019-06-01 | 2019-07-01 | Stirling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_403938 | Q&S3B | Completion | Non OMG180 | 403938 | OMG 48 | Wastewater |  | WWINF | Non OMG180 |  | 2009-11-16 | 2015-10-29 | 2015-11-23 | 2018-02-01 | 2018-03-01 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-48
PH_403938 | Q&S3B | Completion | Non OMG180 | 403938_WORKS | OMG 48 | Wastewater |  | WWINF | Non OMG180 |  | 2009-11-16 | 2015-10-29 | 2015-11-23 | 2018-02-01 | 2018-03-01 | Orkney Islands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-48
PH_500880 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50227 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-09-20 | 2018-09-18 | 2018-12-13 | 2019-03-01 | 2020-01-01 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 31.84
PH_500880 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50905 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-09-20 | 2018-09-18 | 2018-12-13 | 2020-03-01 | 2020-01-01 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 3.7
PH_500108 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50491 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-12-14 | 2016-12-19 | 2020-03-01 | 2020-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500108 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_TayCoast | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-12-14 | 2016-12-19 | 2020-03-01 | 2020-06-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500882 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50229 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-11-02 | 2018-09-21 | 2018-11-20 | 2019-09-01 | 2020-10-01 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 58.69
PH_500882 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53198 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-11-02 | 2018-09-21 | 2018-11-20 | 2019-09-01 | 2020-10-01 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 7.25
PH_500182 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_197 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-05-27 | 2016-06-20 | 2019-09-01 | 2019-12-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500182 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50713 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-05-27 | 2016-06-20 | 2020-01-01 | 2020-04-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500182 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Troqu | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-05-27 | 2016-06-20 | 2020-01-01 | 2020-04-01 | Dumfries and Galloway | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500852 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53199 | OMG 06 | Water |  | SWD | DWQ Reliability |  | 2015-12-10 | 2016-03-30 | 2016-08-08 | 2017-07-01 | 2018-03-01 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 4.67
PH_500852 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50231 | OMG 06 | Water |  | SWD | DWQ Reliability |  | 2015-12-10 | 2016-03-30 | 2016-08-08 | 2017-07-01 | 2018-03-01 | Argyll and Bute-North Argyll | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 14.5
PH_500890 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50198 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-10-13 | 2018-09-26 | 2018-11-30 | 2019-06-01 | 2020-06-01 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 132.95
PH_500890 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53200 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-10-13 | 2018-09-26 | 2018-11-30 | 2019-06-01 | 2020-06-01 | Aberdeenshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 5.85
PH_500186 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_058 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-04-29 | 2016-06-29 | 2018-02-01 | 2018-03-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500186 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_Under | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-20 | 2016-04-29 | 2016-06-29 | 2018-02-01 | 2018-06-01 | East Ayrshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500109 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50407_UppClyde | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-23 | 2017-06-30 | 2017-06-30 | 2020-04-01 | 2020-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-23: 2
PH_500109 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50409 | OMG 23 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-23 | 2017-06-30 | 2017-06-30 | 2020-04-01 | 2020-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500109 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_034 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-23 | 2017-06-30 | 2017-06-30 | 2020-04-01 | 2020-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500109 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50305_TE_500305_041 | OMG 22 | Wastewater |  | SWMD | Environmental Studies |  | 2015-03-23 | 2017-06-30 | 2017-06-30 | 2020-04-01 | 2020-07-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-22
PH_500017 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven | 50484 | OMG 32 | Wastewater |  | WWINF | Flooding Demand Driven |  | 2018-12-07 | 2019-05-20 | 2019-07-02 | 2021-02-01 | 2021-05-01 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_500017 | Q&S4 | Reducing flooding and pollution from sewers | Flooding Demand Driven | 50484 | OMG 30 | Wastewater |  | WWINF | Flooding Demand Driven |  | 2018-12-07 | 2019-05-20 | 2019-07-02 | 2021-02-01 | 2021-05-01 | East Dunbartonshire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_500431 | Q&S4 | Improving drinking water availability and resilience of service | Efficency Advice | 50372_TE_500372_004_N06 | OMG 16 | Water |  | SWD | Efficency Advice |  | 2015-04-02 | 2015-04-02 | 2015-04-02 | 2020-12-01 | 2021-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_500431 | Q&S4 | Improving drinking water availability and resilience of service | Efficency Advice | 50372_TE_500372_004_N05 | OMG 16 | Water |  | SWD | Efficency Advice |  | 2015-04-02 | 2015-04-02 | 2015-04-02 | 2020-06-01 | 2020-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_500431 | Q&S4 | Improving drinking water availability and resilience of service | Efficency Advice | 50372_TE_500372_004_N04 | OMG 16 | Water |  | SWD | Efficency Advice |  | 2015-04-02 | 2015-04-02 | 2015-04-02 | 2019-12-01 | 2020-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_500431 | Q&S4 | Improving drinking water availability and resilience of service | Efficency Advice | 50372_TE_500372_004_N03 | OMG 16 | Water |  | SWD | Efficency Advice |  | 2015-04-02 | 2015-04-02 | 2015-04-02 | 2019-06-01 | 2019-09-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_500431 | Q&S4 | Improving drinking water availability and resilience of service | Efficency Advice | 50372_TE_500372_004_N02 | OMG 16 | Water |  | SWD | Efficency Advice |  | 2015-04-02 | 2015-04-02 | 2015-04-02 | 2019-03-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_500431 | Q&S4 | Improving drinking water availability and resilience of service | Efficency Advice | 50372_TE_500372_004_N01 | OMG 16 | Water |  | SWD | Efficency Advice |  | 2015-04-02 | 2015-04-02 | 2015-04-02 | 2019-03-01 | 2019-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PH_502751 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_003 | OMG 18 | Wastewater |  | SWD | UWWTD - UID |  | 2017-05-16 | 2017-07-14 | 2017-07-14 | 2017-07-01 | 2017-10-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-18
PH_502751 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_007 | OMG 18 | Wastewater |  | SWD | UWWTD - UID |  | 2017-05-16 | 2017-07-14 | 2017-07-14 | 2017-05-01 | 2017-10-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-18
PH_502749 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_016 | OMG 18 | Wastewater |  | WWINF | UWWTD - UID |  | 2017-10-31 | 2019-10-07 | 2021-03-15 | 2021-11-01 | 2022-03-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-18
PH_502749 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_018 | OMG 18 | Wastewater |  | WWINF | UWWTD - UID |  | 2017-10-31 | 2019-10-07 | 2021-03-15 | 2021-11-01 | 2022-03-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-18
PH_502741 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_010 | OMG 18 | Wastewater |  | WWINF | UWWTD - UID |  | 2017-06-01 | 2019-09-09 | 2020-08-10 | 2021-01-01 | 2021-05-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-18
PH_502741 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_009 | OMG 18 | Wastewater |  | WWINF | UWWTD - UID |  | 2017-06-01 | 2019-09-09 | 2020-08-10 | 2021-01-01 | 2021-05-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-18
PH_502746 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_013 | OMG 18 | Wastewater |  | WWINF | UWWTD - UID |  | 2017-10-30 | 2019-10-07 | 2020-01-06 | 2020-10-01 | 2021-01-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-18
PH_502746 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_014 | OMG 18 | Wastewater |  | WWINF | UWWTD - UID |  | 2017-10-30 | 2019-10-07 | 2020-01-06 | 2020-10-01 | 2021-01-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-18
PH_502746 | Q&S4 | Protecting and enhancing the environment | UWWTD - UID | TE_500275_012 | OMG 18 | Wastewater |  | WWINF | UWWTD - UID |  | 2017-10-30 | 2019-10-07 | 2020-01-06 | 2020-10-01 | 2021-01-01 | City of Edinburgh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-18
PH_500884 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 53201 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-04-07 | 2018-09-26 | 2018-12-11 | 2019-09-01 | 2020-10-01 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 1.55
PH_500884 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Reliability | 50232 | OMG 06 | Water |  | WINF | DWQ Reliability |  | 2016-04-07 | 2018-09-26 | 2018-12-11 | 2019-09-01 | 2020-10-01 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | Regulatory Outputs OMG-06: 56.62
PH_500216 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50086_002 | OMG 02 | Water |  | SWD | DWQ Compliance |  | 2015-03-20 | 2016-03-30 | 2016-06-20 | 2017-03-01 | 2018-12-01 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500216 | Q&S4 | Improving drinking water quality compliance and reliability | DWQ Compliance | 50086_001 | OMG 02 | Water |  | SWD | DWQ Compliance |  | 2015-03-20 | 2016-03-30 | 2016-06-20 | 2017-03-01 | 2018-12-01 | Na H-Eileanan an Iar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-02
PH_500193 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50362_TE_500362_012 | OMG 23 | Water |  | SWD | Environmental Studies |  | 2015-03-20 | 2016-09-29 | 2016-09-29 | 2017-12-01 | 2017-12-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500193 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50362_TE_500362_013 | OMG 23 | Water |  | SWD | Environmental Studies |  | 2015-03-20 | 2016-09-29 | 2016-09-29 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500193 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50362_TE_500362_014 | OMG 23 | Water |  | SWD | Environmental Studies |  | 2015-03-20 | 2016-09-29 | 2016-09-29 | 2017-12-01 | 2018-02-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500193 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50362_TE_500362_015 | OMG 23 | Water |  | SWD | Environmental Studies |  | 2015-03-20 | 2016-09-29 | 2016-09-29 | 2017-03-01 | 2017-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500193 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50362_TE_500362_016 | OMG 23 | Water |  | SWD | Environmental Studies |  | 2015-03-20 | 2016-09-29 | 2016-09-29 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
PH_500193 | Q&S4 | Protecting and enhancing the environment | Environmental Studies | 50362_TE_500362_008 | OMG 23 | Water |  | SWD | Environmental Studies |  | 2015-03-20 | 2016-09-29 | 2016-09-29 | 2018-03-01 | 2018-03-01 | Scottish Water Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Regulatory Outputs OMG-23
Prepared by: …………………………………….……………………………….. | Date: ……………………
Checked by: …………………………….………………………………………….. | Date: ……………………
Authorised by: Mark Dickson | Date: 14th June 2019