## G1
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2022
SECTION G: INVESTMENT MONITORING
Table G1: Summary - Investment
|  |  |  | Actual and Forecast | [8 empty] | Confidence Grades
Line | Description | Units | Field | Actual Pre | Report Year | Forecast Year | Forecast Year | Forecast Year | Forecast Year | Forecast Year | ForecastPost | Total | Actual Pre | Report Year | Forecast Year | Forecast Year | Forecast Year | Forecast Year | Forecast Year | ForecastPost
Ref. |  |  | Type | [7 empty] | 2026-27 | [8 empty] | 2026-27
|  |  |  | 2021-22 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2026-27 |  | 2021-22 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2026-27
Repair & Refurbishment - Water
G1.01 | Inspections and testing | £m | I | 11.2391 | 13.661 | 16.5465 | 14.8965 | 6.8589 | 6.345 | 2.8654 | 0.24209 | 61.1732 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.02 | Repair | £m | I | 220.0887 | 98.1054 | 109.9649 | 89.511 | 22.4652 | 21.2226 | 14.9267 | 54.7241 | 356.1958 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.03 | Refurbishment | £m | I | 78.504 | 35.646 | 44.713 | 34.7113 | 34.5935 | 37.6531 | 12.7562 | 12.0604 | 200.0731 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.04 | Total Repair & Refurbishment - Water | £m | C | 309.8319 | 147.4124 | 171.2244 | 139.1188 | 63.9176 | 65.2207 | 30.5482 | 67.0266 | 617.4421
Repair & Refurbishment - Wastewater
G1.05 | Inspections and testing | £m | I | 4.5472 | 12.2812 | 10.1967 | 7.3856 | 5.4714 | 6.6919 | 2.5253 | 1.8371 | 44.5521 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.06 | Repair | £m | I | 80.9132 | 72.0875 | 63.0422 | 47.097 | 5.844 | 2.7943 | 2.005 | 1.6544 | 192.87 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.07 | Refurbishment | £m | I | 37.079 | 12.8676 | 11.3743 | 10.8273 | 14.2424 | 12.9976 | 5.3922 | 1.9217 | 67.7014 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.08 | Total Repair & Refurbishment - Wastewater | £m | C | 122.5394 | 97.2363 | 84.6132 | 65.3098 | 25.5578 | 22.4838 | 9.9226 | 5.4131 | 305.1235
Repair & Refurbishment - General
G1.09 | Inspections and testing | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.10 | Repair | £m | I | 0 | 0.37742 | 0.59353 | 2.4e-07 | 2.4e-07 | 2.4e-07 | 2.4e-07 | 4e-08 | 0.97095 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.11 | Refurbishment | £m | I | 0.72565 | 1.2234 | 1.8833 | 8.7229 | 13.078 | 4.0899 | 0.0007355 | 0 | 28.9983 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.12 | Total Repair & Refurbishment - General | £m | C | 0.72565 | 1.6009 | 2.4768 | 8.7229 | 13.078 | 4.0899 | 0.00073574 | 4e-08 | 29.9692
Asset Replacement
G1.13 | Water Services | £m | I | 409.2851 | 117.0171 | 134.9874 | 89.5238 | 71.2874 | 102.8896 | 40.4481 | 18.7101 | 556.1534 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.14 | Wastewater Services | £m | I | 307.4637 | 74.7794 | 68.9678 | 71.2822 | 44.3699 | 56.5952 | 33.6598 | 34.6863 | 349.6545 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.15 | Business Services | £m | I | 67.1315 | 25.7129 | 59.1115 | 48.1005 | 31.1426 | 0.28703 | -0.00049656 | 4e-08 | 164.3541 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.16 | Total Asset Replacement | £m | C | 783.8804 | 217.5095 | 263.0667 | 208.9066 | 146.7999 | 159.7719 | 74.1075 | 53.3964 | 1070.162
Growth
G1.17 | Growth in the Water Network | £m | I | 48.1422 | 13.6765 | 24.3156 | 23.41 | 16.3136 | 11.911 | 2.491 | 8.2418 | 92.1177 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.18 | Growth in the Wastewater Network | £m | I | 104.4853 | 39.006 | 46.2518 | 75.9175 | 64.9133 | 78.6159 | 72.4173 | 54.0998 | 377.1218 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.19 | Service Relocations Water | £m | I | 33.3132 | 3.5695 | 8.7764 | 4.3547 | 1.2936 | 0.91067 | 0.91067 | 0.48039 | 19.8155 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.20 | Service Relocations Wastewater | £m | I | 5.6002 | 0.77459 | 1.7983 | 1.6604 | 0.69517 | 0.51825 | 0.51825 | 0.25709 | 5.9649 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.21 | Total Growth | £m | C | 191.5409 | 57.0267 | 81.142 | 105.3426 | 83.2156 | 91.9558 | 76.3373 | 63.0791 | 495.0199
Enhancement
G1.22 | Circular Economy | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.23 | Climate Change, Adaptation and Mitigation | £m | I | 3.2371 | 3.2312 | 6.5925 | 6.2066 | 3.7971 | 7.0518 | 2.1796 | 0.27108 | 29.0587 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.24 | Drinking Water | £m | I | 85.8272 | 60.6727 | 43.172 | 53.9756 | 72.104 | 141.5836 | 106.8563 | 312.2919 | 478.3642 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.25 | Environment | £m | I | 41.5548 | 11.0829 | 9.8543 | 9.836 | 11.2045 | 16.4866 | 15.1935 | 58.9368 | 73.6577 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.26 | Flooding/Surface Water Management | £m | I | 2.1122 | -0.44886 | 0.3704 | 0.22439 | 0 | 0 | 0 | 0 | 0.14593 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.27 | Long Term Water Sector Vision | £m | I | 0 | 0.73461 | 1.4352 | 0.85766 | 0 | 0 | 0 | 0 | 3.0275 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.28 | Other | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.29 | Private Finance Initiative Funded Contracts | £m | I | 0.19682 | 0.16084 | 25.8386 | 0.90588 | 0 | 4.0616 | 12.1847 | 8.1231 | 43.1516 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.30 | Security & Resilience | £m | I | 11.5624 | 1.2236 | 0.49638 | 0.59048 | 5.0863 | 0.97755 | 1.8357 | 1.4112 | 10.21 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.31 | Standards of Service | £m | I | 86.5489 | 36.695 | 38.0867 | 55.457 | 31.0445 | 20.6904 | 8.4406 | 8.7902 | 190.4141 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.32 | Total Enhancement | £m | C | 231.0394 | 113.352 | 125.8461 | 128.0536 | 123.2364 | 190.8515 | 146.6903 | 389.8244 | 828.0298
Support
G1.33 | Asset Support Direct | £m | I | 12.5714 | 22.8917 | 17.311 | 11.581 | 6.0758 | 5.1603 | 1.4269 | 0.76448 | 64.4467 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.34 | Asset Support Indirect | £m | I | 11.2418 | -1.9697 | 1.2483 | 1.316 | 1.316 | 1.316 | 1.2064 | 1.2e-07 | 4.433 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.35 | Non Asset Support | £m | I | 0 | 1.3697 | 2.7923 | 2.2497 | 1.7722 | 1.7087 | 1.5972 | 0.31013 | 11.4898 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.36 | Total Support | £m | C | 23.8133 | 22.2917 | 21.3516 | 15.1467 | 9.164 | 8.185 | 4.2305 | 1.0746 | 80.3695
Completion Programme
G1.37 | SR10 Completion | £m | I | 494.9891 | 6.945 | 5.9406 | 6.8514 | 7.7424 | 0.49255 | 0 | 0 | 27.972 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.38 | SR15 Completion - Enhancement | £m | I | 494.3733 | 72.6559 | 32.6663 | 11.4442 | 5.2939 | 1.3687 | 10.1673 | 0.0047379 | 133.5963 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.39 | SR15 Completion - Growth | £m | I | 22.2466 | 6.1342 | 1.4027 | 0.22409 | 0 | 0 | 0 | 0 | 7.761 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.40 | SR15 Completion - Exceptional Asset Maintenance | £m | I | 133.4185 | 32.254 | 18.3929 | 7.4951 | 16.6088 | 0.09981 | 0 | 0 | 74.8506 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.41 | Total Completion Programme | £m | C | 1145.0275 | 117.9891 | 58.4025 | 26.0148 | 29.6452 | 1.9611 | 10.1673 | 0.0047379 | 244.1799
Total Additional Operating Expenditure
G1.42 | Additional Operating Expenditure from Investment | £m | I | 0 | 0.89113 | -1.4695 | -0.135 | 0.23435 | 1.0552 | 2.9825 | -0.018839 | 3.5586 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
Grants and Contributions
G1.43 | Grants for infrastructure assets | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.44 | Grants for non-infrastructure assets | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.45 | Contributions to infrastructure assets | £m | I | 0 | 10.2197 | 8.878 | 8.878 | 8.878 | 8.878 | 8.878 | 0 | 54.6097 | A1 | A1 | B1 | B1 | B1 | B1 | B1 | B1
G1.46 | Contributions to non-infrastructure assets | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.47 | Row intentionally blank
G1.48 | Total capital contributions (excluding infrastructure charge contributions) | £m | C | 0 | 10.2197 | 8.878 | 8.878 | 8.878 | 8.878 | 8.878 | 0 | 54.6097
Unallocated Investment
G1.49 | Allowed For Investment Still to Be Allocated | £m | I |  | -20.2475 | 84.9694 | 340.1952 | 615.8768 | 634.1068 | 905.1559 | 0 | 2560.0566 | B1 | B1 | B1 | B1 | B1 | B1 | B1 | B1
Expenditure Totals
G1.50 | Repair & Refurbishment - Water | £m | C | 309.8319 | 147.4124 | 171.2244 | 139.1188 | 63.9176 | 65.2207 | 30.5482 | 67.0266 | 617.4421
G1.51 | Repair & Refurbishment - Wastewater | £m | C | 122.5394 | 97.2363 | 84.6132 | 65.3098 | 25.5578 | 22.4838 | 9.9226 | 5.4131 | 305.1235
G1.52 | Repair & Refurbishment - General | £m | C | 0.72565 | 1.6009 | 2.4768 | 8.7229 | 13.078 | 4.0899 | 0.00073574 | 4e-08 | 29.9692
G1.53 | Asset Replacement | £m | C | 783.8804 | 217.5095 | 263.0667 | 208.9066 | 146.7999 | 159.7719 | 74.1075 | 53.3964 | 1070.162
G1.54 | Growth | £m | C | 191.5409 | 57.0267 | 81.142 | 105.3426 | 83.2156 | 91.9558 | 76.3373 | 63.0791 | 495.0199
G1.55 | Enhancement | £m | C | 231.0394 | 113.352 | 125.8461 | 128.0536 | 123.2364 | 190.8515 | 146.6903 | 389.8244 | 828.0298
G1.56 | Support | £m | C | 23.8133 | 22.2917 | 21.3516 | 15.1467 | 9.164 | 8.185 | 4.2305 | 1.0746 | 80.3695
G1.57 | Completion Programme | £m | C | 1145.0275 | 117.9891 | 58.4025 | 26.0148 | 29.6452 | 1.9611 | 10.1673 | 0.0047379 | 244.1799
G1.58 | Gross Investment | £m | C | 2808.3983 | 774.4184 | 808.1232 | 696.6157 | 494.6145 | 544.5197 | 352.0043 | 579.8189 | 3670.296
G1.59 | Total capital contributions (excluding infrastructure charge contributions) | £m | C | 0 | 10.2197 | 8.878 | 8.878 | 8.878 | 8.878 | 8.878 | 0 | 54.6097
G1.60 | Net Investment | £m | C | 2808.3983 | 764.1987 | 799.2452 | 687.7377 | 485.7365 | 535.6417 | 343.1263 | 579.8189 | 3615.6863
G1.61 | Total Asset Additions | £m | C | 1591.4211 | 310.6594 | 286.7422 | 274.5576 | 245.2612 | 292.9534 | 237.4253 | 453.9829 | 1647.5992
G1.62 | Total Additional Operating Expenditure | £m | C | 0 | 0.89113 | -1.4695 | -0.135 | 0.23435 | 1.0552 | 2.9825 | -0.018839 | 3.5586
Risk and Overhead Investment Breakdown
G1.63 | Direct costs | £m | I | [8 empty] | 3337.231 | [7 empty] | A1
G1.64 | Project overheads allocated to projects | £m | I | [8 empty] | 257.6164 | [7 empty] | A1
G1.65 | Risk allowance | £m | I | [8 empty] | 75.4486 | [7 empty] | A1
G1.66 | Gross Investment | £m | C | [8 empty] | 3670.296
Primary Purpose Investment Breakdown
G1.67 | Water | £m | I | 1576.4755 | 438.4771 | 448.234 | 358.2098 | 274.844 | 334.6894 | 196.8279 | 417.5783 | 2051.2821 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.68 | Wastewater | £m | I | 1120.3977 | 312.6381 | 304.3159 | 286.2841 | 189.4405 | 198.6386 | 151.955 | 161.166 | 1443.2722 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.69 | General | £m | I | 111.5251 | 23.3033 | 55.5733 | 52.1218 | 30.3301 | 11.1917 | 3.2214 | 1.0746 | 175.7417 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.70 | Gross Investment | £m | C | 2808.3983 | 774.4184 | 808.1232 | 696.6157 | 494.6145 | 544.5197 | 352.0043 | 579.8189 | 3670.296
Planned and Responsive Repair & Refurbishment
G1.71 | Responsive repair and refurbishment investment previously expensed as operating expenditure ('Tier 1') | £m | I | 19.434 | 53 | 55.8161 | 54.2383 | 1.7444e-07 | 1.7444e-07 | 1.7444e-07 | 2.9073e-08 | 163.0543 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.72 | Remaining responsive repair and refurbishment investment ('Tier 1') | £m | I | 268.9301 | 98.6032 | 83.3149 | 56.7016 | 9.2357 | 10.6351 | 2.8713 | 25.1847 | 261.3618 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.73 | Planned repair and refurbishment investment ('Tier 2') | £m | I | 144.7328 | 94.6464 | 119.1834 | 102.2116 | 93.3177 | 81.1593 | 37.6003 | 47.255 | 528.1187 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.74 | Total Repair and Refurbishment | £m | C | 433.0969 | 246.2496 | 258.3144 | 213.1515 | 102.5534 | 91.7945 | 40.4715 | 72.4397 | 952.5348
Tier Investment Breakdown
G1.75 | Tier 1a | £m | I | 294.8313 | 151.8941 | 139.2018 | 111.1958 | 9.9229 | 11.3224 | 3.3825 | 25.1878 | 426.9194 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.76 | Tier 2 - Pre Committed List | £m | I | 522.1896 | 58.8169 | 310.7098 | 458.0787 | 429.6107 | 505.423 | 337.9256 | 547.658 | 2100.5647 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.77 | Tier 2 - Committed List | £m | I | 1991.3774 | 563.7074 | 358.2116 | 127.3412 | 55.0809 | 27.7744 | 10.6962 | 6.9731 | 1142.8118 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.78 | Gross Investment | £m | C | 2808.3983 | 774.4184 | 808.1232 | 696.6157 | 494.6145 | 544.5197 | 352.0043 | 579.8189 | 3670.296
G1.79 | Tier 2 Investment for comparison to FD | £m | C | 1736.1539 | 395.086 | 397.0476 | 367.8912 | 329.7009 | 365.2347 | 266.1476 | 501.2379 | 2121.1082
Comparison to Historical Investment Baseline
G1.80 | Water Reasonable Cost Contributions | £m | I | 52.1108 | 9.8301 | 6.9371 | 6.9389 | 6.9389 | 6.9389 | 6.9389 | 0 | 44.5229 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.81 | Wastewater Reasonable Cost Contributions | £m | I | 34.4024 | 14.734 | 11.205 | 11.205 | 16.3108 | 11.205 | 11.205 | 0 | 75.8648 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.82 | Total Investment including Reasonable Cost Contributions | £m | C | 2894.9115 | 798.9826 | 826.2653 | 714.7596 | 517.8642 | 562.6636 | 370.1482 | 579.8189 | 3790.6837
G1.83 | Infrastructure charge contributions for infrastructure assets | £m | I | 0 | 11.4288 | 16.888 | 16.888 | 16.888 | 16.888 | 16.888 | 0 | 95.8688 | A1 | A1 | B1 | B1 | B1 | B1 | B1 | B1
G1.84 | Total capital contributions (excluding infrastructure charge contributions) | £m | C | 0 | 10.2197 | 8.878 | 8.878 | 8.878 | 8.878 | 8.878 | 0 | 54.6097 | A1 | A1 | B1 | B1 | B1 | B1 | B1 | B1
G1.85 | Net Capital Investment | £m | C | 2894.9115 | 777.3341 | 800.4993 | 688.9936 | 492.0982 | 536.8976 | 344.3822 | 579.8189 | 3640.2051
Prepared by: ……………………………………………...…..
Checked by: ……………………………………………...…..
Authorised by: ……………………………………………...…..

## G2a
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2022
SECTION G: INVESTMENT MONITORING
Table G2a: Summary - Outputs by Ministerial Objective
Line Ref | Field Type | Output Description | Output Units | Output code | Management Approach Reference(s) |  | Number of Outputs
[7 empty] | Pre-2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27 | Total
[8 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Asset Maintenance
G2a.001 | I/C | No outputs identified for this ministerial objective |  | - |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Circular Economy
G2a.002 | I/C | No outputs identified for this ministerial objective |  | - |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Climate Change, Adaptation and Mitigation
G2a.003 | I/C | Number of renewable energy asset interventions | Nr. | O_SE9_M | MA056 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drinking Water
G2a.004 | I/C | Number of Asset Inspections completed | Nr. | O_AI1_M | IR 18, MA006 |  | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2a.005 | I/C | Number of sites where new phosphate monitoring equipment has been provided | Nr. | O_LD1_E3 | MA041 |  | 0 | 0 | 0 | 4 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27
G2a.006 | I/C | Number of lead communication pipes replaced | Nr. | O_LD2_E | MA041 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2a.007 | I/C | Number of WTW sites with auto-shutdown risk control interventions | Nr. | O_OM4_E | MA006 |  | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2a.008 | I/C | Number of WTW sites with improved organics removal | Nr. | O_OM5_E | MA006 |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.009 | I/C | Number of sites with emergency planning equipment interventions | Nr. | O_WR1_M | MA087 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.010 | I/C | Number of Water Supply Zones with improved resilience | Nr. | O_WR6_E | MA087 |  | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2a.011 | I/C | Number of WTW with increased capacity | Nr. | O_WR8_G1 | MA006 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Environment
G2a.012 | I/C | Number of Asset Inspections completed | Nr. | O_AI1_M | MA063 |  | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2a.013 | I/C | Number of Combined Storm Overflow (CSO) screen interventions | Nr. | O_SN1_M8 | MA005 |  | 0 | 0 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2a.014 | I/C | Number of unsatisfactory intermittent discharges (UID) improved or removed | Nr. | O_SN2_E | IR 18, MA005 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2a.015 | I/C | Number of WWTW continuous discharges improved or removed | Nr. | O_WW2_E | MA084 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.016 | I/C | Number of studies complete | Nr. | O_WW3_E | MA076 |  | 0 | 0 | 27 | 191 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291
Flooding and Surface Water Management
G2a.017 | I/C | No outputs identified for this ministerial objective |  | - |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Private Finance Initiative Funded Projects
G2a.018 | I/C | No outputs identified for this ministerial objective |  | - |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Security & Resilience
G2a.019 | I/C | Number of digital systems improved | Nr. | O_DI1_M | MA066 |  | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2a.020 | I/C | Number of sites with water security interventions | Nr. | O_HS1_M10 | MA089 |  | 0 | 4 | 9 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
Standards of service
G2a.021 | I/C | Number of WTW sludge handling asset interventions | Nr. | O_AD1_M | MA033, MA052, MA094 |  | 0 | 40 | 85 | 127 | 161 | 161 | 161 | 161 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163
G2a.022 | I/C | Number of leakage management equipment interventions | Nr. | O_AD5_M | MA073 |  | 0 | 1 | 1 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2a.023 | I/C | Number of Asset Inspections completed | Nr. | O_AI1_M | _SR15, MA002, MA004, MA011, MA012, MA014, MA015, MA016, MA017, MA022, MA023, MA025, MA033, MA035, MA037, MA039, MA042, MA043, MA046, MA052, MA054, MA057, MA058, MA091, MA092, MA094, MA096 |  | 0 | 16 | 88 | 1308 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376
G2a.024 | I/C | Number of sludge treatment centre asset interventions | Nr. | O_BR1_M | MA024, MA043 |  | 0 | 38 | 77 | 121 | 187 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188
G2a.025 | I/C | Length of water mains replaced or refurbished | m | O_DC2_E | MA058 |  | 0 | 0 | 0 | 0 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256
G2a.026 | I/C | Length of water mains cleaned | m | O_DC2_M1 | _SR15, MA016 |  | 0 | 0 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939
G2a.027 | I/C | Length of water mains replaced or refurbished | m | O_DC2_M2 | MA016 |  | 0 | 0 | 0 | 1 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257
G2a.028 | I/C | Number of digital systems improved | Nr. | O_DI1_M | MA066 |  | 0 | 1 | 2 | 4 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2a.029 | I/C | Number of properties removed from internal flooding at risk register. | Nr. | O_FR1_F1 | _SR15, MA020 |  | 0 | 10 | 11 | 149 | 166 | 178 | 182 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194
G2a.030 | I/C | Number of properties with temporary internal flood prevention measures | Nr. | O_FR1_F2 | MA020 |  | 0 | 0 | 1 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2a.031 | I/C | Number of properties removed from external flooding at risk register. | Nr. | O_FR2_F | _SR15, IR 18, MA020 |  | 0 | 8 | 10 | 19 | 49 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
G2a.032 | I/C | Number of Flood risk management (Section 16) model assessments | Nr. | O_FR3_F | IR 18, MA020 |  | 0 | 0 | 1 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2a.033 | I/C | Number of reservoir Interests of Safety interventions | Nr. | O_HS1_M1 | MA004 |  | 0 | 15 | 35 | 77 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128
G2a.034 | I/C | Number of sites with standby power equipment interventions | Nr. | O_HS1_M11 | MA092 |  | 0 | 16 | 22 | 32 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51
G2a.035 | I/C | Number of water sites with telemetry interventions | Nr. | O_HS1_M12 | MA022, MA033, MA044, MA046 |  | 0 | 5 | 10 | 231 | 236 | 236 | 236 | 236 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238
G2a.036 | I/C | Number of water property operational buildings interventions | Nr. | O_HS1_M13 | MA096 |  | 0 | 50 | 228 | 305 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346
G2a.037 | I/C | Number of raw water storage asset interventions | Nr. | O_HS1_M2 | MA074 |  | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2a.038 | I/C | Number of water pipe bridge interventions | Nr. | O_HS1_M3 | MA025 |  | 0 | 101 | 102 | 304 | 311 | 311 | 311 | 311 | 311 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312
G2a.039 | I/C | Number of fixed wire electrical system or statutory maintenance asset interventions | Nr. | O_HS1_M4 | MA068 |  | 0 | 0 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412
G2a.040 | I/C | Number of SCADA, HMI, PLC asset interventions | Nr. | O_HS1_M5 | MA022, MA033, MA046 |  | 0 | 6 | 31 | 64 | 76 | 77 | 77 | 78 | 81 | 82 | 82 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83
G2a.041 | I/C | Number of WTW Chemical Storage and Dosing Vessel interventions | Nr. | O_HS1_M6 | MA037, MA046, MA094 |  | 0 | 6 | 14 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132
G2a.042 | I/C | Number of street furniture interventions | Nr. | O_HS1_M7 | MA018 |  | 0 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535
G2a.043 | I/C | Number of high voltage system interventions | Nr. | O_HS1_M8 | MA091, MA094 |  | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2a.044 | I/C | Number of water sites with Motor Control Centre interventions | Nr. | O_HS1_M9 | MA082 |  | 0 | 1 | 2 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2a.045 | I/C | Number of sites with water security enhancements | Nr. | O_HS2_E | MA089 |  | 0 | 1 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66
G2a.046 | I/C | Number of sites with reservoir drawdown enhancements | Nr. | O_HS3_E | MA004 |  | 0 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2a.047 | I/C | Number of Innovation pilot programmes undertaken | Nr. | O_IN1_M | _SR15 |  | 0 | 0 | 0 | 20 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
G2a.048 | I/C | Number of Phosphate Equipment asset interventions | Nr. | O_LD1_M1 | MA046, MA094 |  | 0 | 0 | 1 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2a.049 | I/C | Number of WTW Instrumentation interventions | Nr. | O_LD1_M2 | MA095 |  | 0 | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2a.050 | I/C | Number of lead communication pipes replaced | Nr. | O_LD2_E | _SR15, MA025, MA096 |  | 0 | 0 | 2 | 8380 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422
G2a.051 | I/C | Number of vehicle or plant item interventions | Nr. | O_LV1_M | MA071 |  | 0 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174
G2a.052 | I/C | Number of WTW membranes replaced | Nr. | O_OM1_M1 | MA033 |  | 0 | 2 | 3 | 8 | 24 | 24 | 24 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
G2a.053 | I/C | Number of WTW sand filters with media replaced | Nr. | O_OM1_M2 | MA033, MA094 |  | 0 | 2 | 11 | 30 | 46 | 46 | 56 | 56 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57
G2a.054 | I/C | Number of WTW Granular Activated Carbon (GAC) filters with media replaced | Nr. | O_OM1_M3 | MA033 |  | 0 | 0 | 1 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53
G2a.055 | I/C | Number of WTW chemical storage and dosing interventions | Nr. | O_OM1_M4 | MA033, MA046 |  | 0 | 35 | 88 | 155 | 949 | 950 | 951 | 951 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954
G2a.056 | I/C | Number of Filtration and disinfection asset interventions | Nr. | O_OM1_M5 | MA033, MA046, MA093, MA094 |  | 0 | 99 | 189 | 464 | 643 | 643 | 644 | 650 | 655 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656
G2a.057 | I/C | Number of WTW Instrumentation interventions | Nr. | O_OM1_M6 | MA042, MA043, MA046, MA095 |  | 0 | 34 | 74 | 491 | 521 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525
G2a.058 | I/C | Number of treated water storage or secondary disinfection asset interventions | Nr. | O_OM2_M1 | MA037, MA046, MA096 |  | 0 | 24 | 91 | 156 | 230 | 233 | 234 | 234 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235
G2a.059 | I/C | Number of sample point interventions | Nr. | O_OM2_M2 | MA081 |  | 0 | 3 | 8 | 14 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G2a.060 | I/C | Number of treated water storage by-pass interventions | Nr. | O_OM6_M | MA037 |  | 0 | 7 | 9 | 18 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
G2a.061 | I/C | Number ATOM water asset interventions | Nr. | O_OM9_M | MA068 |  | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2a.062 | I/C | Number of property asset interventions | Nr. | O_PE1_M | MA029 |  | 0 | 0 | 5 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2a.063 | I/C | Length of trunk main interventions | m | O_SA1_M1 | MA001, MA025 |  | 0 | 4850 | 5220 | 5220 | 5220 | 5220 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007
G2a.064 | I/C | Length of trunk main cathodic protection system interventions | m | O_SA1_M2 | MA025 |  | 0 | 101 | 214 | 409 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659
G2a.065 | I/C | Number of raw water intake interventions | Nr. | O_SA2_M | MA025 |  | 0 | 5 | 6 | 12 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2a.066 | I/C | Number of treated water pump interventions | Nr. | O_SA3_M1 | MA015, MA058 |  | 0 | 13 | 32 | 56 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82
G2a.067 | I/C | Number of raw water pump interventions | Nr. | O_SA3_M2 | MA046, MA058 |  | 0 | 3 | 13 | 18 | 29 | 33 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34
G2a.068 | I/C | Length of raw water mains interventions | m | O_SA4_M | MA025 |  | 0 | 724 | 766 | 1120 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216
G2a.069 | I/C | Length of aqueducts or tunnel interventions | m | O_SA5_M | MA025 |  | 0 | 0 | 0 | 27600 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602
G2a.070 | I/C | Length of new or enhanced distribution mains | m | O_SA6_E | MA015, MA037 |  | 0 | 0 | 0 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870
G2a.071 | I/C | Length of distribution mains interventions | m | O_SA6_M2 | _SR15, MA001, MA015, MA037, MA058 |  | 0 | 24382 | 34646 | 65353 | 94386 | 94386 | 94386 | 94386 | 107166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166
G2a.072 | I/C | Number of properties with persistent low pressure resolved | Nr. | O_SA7_E | MA070 |  | 0 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2a.073 | I/C | Number of borehole interventions | Nr. | O_SA8_M | MA033, MA080, MA094 |  | 0 | 1 | 9 | 22 | 60 | 60 | 60 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65
G2a.074 | I/C | Number of scientific equipment instruments replaced | Nr. | O_SC1_M | MA053 |  | 0 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114
G2a.075 | I/C | Length of critical sewers interventions | m | O_SN1_M1 | MA002, MA014 |  | 0 | 500 | 1310 | 2004 | 2478 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717
G2a.076 | I/C | Number of wastewater Network Motor Control Centre interventions | Nr. | O_SN1_M11 | MA011, MA023 |  | 0 | 6 | 6 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2a.077 | I/C | Number of sites with wastewater pipebridge interventions | Nr. | O_SN1_M12 | MA003 |  | 0 | 1 | 4 | 13 | 22 | 22 | 22 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33
G2a.078 | I/C | Number of screw pumps interventions | Nr. | O_SN1_M13 | MA023, MA036 |  | 0 | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2a.079 | I/C | Number of sites with sewage pumping station interventions | Nr. | O_SN1_M14 | MA017, MA023 |  | 0 | 197 | 383 | 608 | 805 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806
G2a.080 | I/C | Number of storm tank interventions | Nr. | O_SN1_M16 | MA017, MA062 |  | 0 | 3 | 5 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2a.081 | I/C | Number of wastewater property operational building interventions | Nr. | O_SN1_M18 | MA096 |  | 0 | 1 | 9 | 18 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
G2a.082 | I/C | Length of wastewater pumping main interventions | m | O_SN1_M2 | MA012 |  | 0 | 676 | 680 | 1063 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144
G2a.083 | I/C | Length of sea outfalls replaced or maintained | m | O_SN1_M3 | MA035, MA043 |  | 0 | 4 | 571 | 582 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586
G2a.084 | I/C | Length of non-critical sewer interventions | m | O_SN1_M4 | MA003, MA014, MA039 |  | 1 | 2427 | 4066 | 5918 | 6611 | 10219 | 10219 | 10219 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404
G2a.085 | I/C | Number of street furniture interventions | Nr. | O_SN1_M5 | MA018 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.086 | I/C | Number of sites with sewer structures APNRV intervention | Nr. | O_SN1_M7 | MA062 |  | 0 | 2 | 9 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2a.087 | I/C | Number of Combined Storm Overflow (CSO) screen interventions | Nr. | O_SN1_M8 | MA039 |  | 0 | 4 | 14 | 23 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27
G2a.088 | I/C | Number of Transformation initiatives implemented | Nr. | O_TF1_E | MA_proj_app |  | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2a.089 | I/C | Number of sites with emergency planning equipment interventions | Nr. | O_WR1_M | MA098 |  | 0 | 0 | 0 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2a.090 | I/C | Number of strategic network valve interventions | Nr. | O_WR2_M | MA060, MA094 |  | 0 | 0 | 6 | 14 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
G2a.091 | I/C | Number of water hydraulic models maintained | Nr. | O_WR4_M | MA054 |  | 0 | 0 | 1 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59
G2a.092 | I/C | Number of sites with security fencing or gate interventions - wastewater | Nr. | O_WW1_M1 | MA044, MA096 |  | 0 | 7 | 7 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2a.093 | I/C | Number of WWTW odour equipment asset interventions | Nr. | O_WW1_M10 | _SR15, MA012, MA017, MA043, MA049 |  | 0 | 6 | 15 | 24 | 27 | 27 | 27 | 27 | 27 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2a.094 | I/C | Number of WWTW primary treatment asset interventions | Nr. | O_WW1_M11 | MA013, MA017, MA042, MA043 |  | 0 | 38 | 103 | 164 | 203 | 205 | 205 | 205 | 205 | 206 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208
G2a.095 | I/C | Number of redundant or abandoned assets interventions - WWTW | Nr. | O_WW1_M12 | MA096 |  | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2a.096 | I/C | Number of WWTW secondary treatment asset interventions | Nr. | O_WW1_M13 | MA017, MA042, MA043, MA057 |  | 0 | 172 | 342 | 532 | 671 | 677 | 678 | 679 | 679 | 686 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690
G2a.097 | I/C | Number of site welfare facilities interventions - WWTW | Nr. | O_WW1_M14 | MA096 |  | 0 | 5 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2a.098 | I/C | Number of WWTW sites with temporary process unit interventions | Nr. | O_WW1_M15 | MA021 |  | 0 | 3 | 4 | 6 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2a.099 | I/C | Number of WWTW treatment ancillaries asset interventions | Nr. | O_WW1_M16 | MA015, MA042, MA043, MA057 |  | 0 | 143 | 336 | 637 | 1264 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265
G2a.100 | I/C | Number of high voltage system interventions | Nr. | O_WW1_M17 | MA091 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.101 | I/C | Number of WWTW statutory maintenance asset interventions | Nr. | O_WW1_M18 | MA068 |  | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2a.102 | I/C | Number of fixed wire electrical system asset interventions | Nr. | O_WW1_M2 | MA068 |  | 0 | 0 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338
G2a.103 | I/C | Number of WWTW Motor Control Centre interventions | Nr. | O_WW1_M3 | MA011, MA017 |  | 0 | 2 | 9 | 11 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2a.104 | I/C | Number of wastewater SCADA interventions | Nr. | O_WW1_M4 | MA013, MA023 |  | 0 | 16 | 20 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23
G2a.105 | I/C | Number of screw pumps interventions | Nr. | O_WW1_M5 | MA036 |  | 0 | 8 | 20 | 29 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
G2a.106 | I/C | Number of watewater telemetry interventions | Nr. | O_WW1_M6 | MA044 |  | 0 | 165 | 210 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222
G2a.107 | I/C | Number of wastewater property operational building interventions | Nr. | O_WW1_M7 | MA096 |  | 0 | 51 | 280 | 337 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367
G2a.108 | I/C | Number of WWTW inlet works asset interventions | Nr. | O_WW1_M9 | MA017, MA023, MA042, MA094 |  | 0 | 75 | 164 | 324 | 463 | 467 | 467 | 467 | 467 | 469 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471
Supporting Sustainable Economic Growth
G2a.109 | I/C | Number of Asset Inspections completed | Nr. | O_AI1_M | MA087 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2a.110 | I/C | Number of WWTW sites requiring RRR activities to support Part 4 growth | Nr. | O_ED1_M | MA026 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.111 | I/C | Increase in Part 4 capacity to meet local growth requirements | PE | O_ED3_G | MA026 |  | 0 | 151 | 2745 | 2745 | 3699 | 8905 | 21932 | 21932 | 21932 | 21932 | 21932 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898
G2a.112 | I/C | Additional Capacity enabled from strategic wastewater network reinforcement | PE | O_ED4_G | MA032 |  | 0 | 0 | 0 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259
G2a.113 | I/C | Length of new or enhanced distribution mains | m | O_SA6_E | MA087 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2a.114 | I/C | Additional Capacity enabled from strategic water network reinforcement | PE | O_WR10_G1 | MA032 |  | 0 | 0 | 0 | 1320 | 12765 | 12765 | 12765 | 12765 | 12765 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665
G2a.115 | I/C | Number of resilience improvements at rural supply hubs to provide capacity for new demand | Nr. | O_WR8_G3 | MA087 |  | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2a.116 | I/C | Number of tanker fill points installed | Nr. | O_WR8_G4 | MA087 |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.117 | I/C | Number of service relocations - water mains | Nr. | O_WR9_G1 | MA065 |  | 0 | 1 | 1077 | 7983 | 7986 | 7986 | 7986 | 7986 | 7986 | 9186 | 9186 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187
Prepared by: …………………………………………….. | [5 empty] | Date: ……………………
Checked by: …………………………………………….. | [5 empty] | Date: ……………………
Authorised by:

## G2b
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2022
SECTION G: INVESTMENT MONITORING
Table G2b: Completion Investment
Line Ref | Field Type | Output Description | Output Units | Output Code | Management Approach Reference(s) |  | Pre-2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Total
[8 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
2015-21 outputs remaining that were planned to complete in the 2021-27 period - Planned
G2b.1 | I/C | Number of water treatment works improved | No. | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2b.2 | I/C | Number of zones made compliant with iron & manganese standards | No. | 2 |  |  | 3 | 6 | 6 | 7 | 16 | 16 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2b.3 | I/C | Improvements to reliability of drinking water (catchments and treatment) | No. | 3 |  |  | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8
G2b.4 | I/C | Improvements to reliability of drinking water (networks and storage) | No. | 4 |  |  | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2b.5 | I/C | Distribution mains cleaned (km) | km | 5 |  |  | 0 | 0 | 2323.845 | 2323.845 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405
G2b.6 | I/C | Number of water quality etc studies to inform future periods | No. | 6 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2b.7 | I/C | 2010-15 outputs planned to complete in the 2015-21 period -DW | No. | 7 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2b.8 | I/C | Water supply resilience strategy and improvements made | No. | 8 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2b.9 | I/C | Number of zones with improved security of supply (SOSI) | No. | 9 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2b.10 | I/C | Number of security measures and improvements to the infrastructure of critical reservoirs | No. | 10 |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2b.11 | I/C | Number of WWTWs improved to meet UWWTD | No. | 11 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2b.12 | I/C | Number of waste water networks improved to meet UWWTD | No. | 12 |  |  | 0 | 3 | 6 | 6 | 7 | 10 | 10 | 10 | 10 | 10 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2b.13 | I/C | Number of improvements required to meet UWWTD - Glasgow completion | No. | 13 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2b.14 | I/C | Number of improvements required to meet the Water Framework Directive | No. | 14 |  |  | 0 | 0 | 1 | 2 | 4 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2b.15 | I/C | Studies to inform requirements under the revised Bathing Waters Directive | No. | 15 |  |  | 0 | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2b.16 | I/C | Number of environmental studies to inform future periods | No. | 16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2b.17 | I/C | Number of improvements required by the Compliance Assessment Scheme; odour reduction and sludge management | No. | 17 |  |  | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2b.18 | I/C | 2010-15 outputs planned to complete in the 2015-21 period - WW | No. | 18 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-21 completion outputs remaining - Delayed
G2b.19 | I/C | Number of water treatment works improved | No. | 1 |  |  | 3 | 4 | 4 | 4 | 4 | 5 | 6 | 6 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11
G2b.20 | I/C | Number of zones made compliant with iron & manganese standards | No. | 2 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2b.21 | I/C | Improvements to reliability of drinking water (catchments and treatment) | No. | 3 |  |  | 3 | 6 | 7 | 8 | 9 | 11 | 12 | 12 | 14 | 16 | 16 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2b.22 | I/C | Improvements to reliability of drinking water (networks and storage) | No. | 4 |  |  | 2 | 11 | 12 | 12 | 13 | 14 | 15 | 15 | 15 | 15 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2b.23 | I/C | Distribution mains cleaned (km) | km | 5 |  |  | 48.4 | 48.4 | 289.38 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633
G2b.24 | I/C | Number of water quality etc studies to inform future periods | No. | 6 |  |  | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2b.25 | I/C | 2010-15 outputs planned to complete in the 2015-21 period -DW | No. | 7 |  |  | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2b.26 | I/C | Water supply resilience strategy and improvements made | No. | 8 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2b.27 | I/C | Number of zones with improved security of supply (SOSI) | No. | 9 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2b.28 | I/C | Number of security measures and improvements to the infrastructure of critical reservoirs | No. | 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2b.29 | I/C | Number of WWTWs improved to meet UWWTD | No. | 11 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2b.30 | I/C | Number of waste water networks improved to meet UWWTD | No. | 12 |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2b.31 | I/C | Number of improvements required to meet UWWTD - Glasgow completion | No. | 13 |  |  | 3 | 4 | 9 | 9 | 11 | 11 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2b.32 | I/C | Number of improvements required to meet the Water Framework Directive | No. | 14 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 10 | 13 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2b.33 | I/C | Studies to inform requirements under the revised Bathing Waters Directive | No. | 15 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2b.34 | I/C | Number of environmental studies to inform future periods | No. | 16 |  |  | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2b.35 | I/C | Number of improvements required by the Compliance Assessment Scheme; odour reduction and sludge management | No. | 17 |  |  | 2 | 2 | 2 | 2 | 2 | 13 | 14 | 22 | 28 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
G2b.36 | I/C | 2010-15 outputs planned to complete in the 2015-21 period - WW | No. | 18 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | SR15 Completion projects | Units
G2b.37 | I/C | SR10 projects remaining (Q&S3b) | Nr |  |  |  | 19 | 15 | 10 | 8 | 6 | 6 | 4 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2b.38 | I/C | SR15 projects remaining (Q&SIV) | Nr |  |  |  | 124 | 94 | 73 | 67 | 55 | 45 | 36 | 28 | 21 | 15 | 11 | 9 | 6 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
G2b.39 | I/C | 2015-21 projects remaining that were planned to complete in the 2021-27 period - Planned | Nr |  |  |  | 57 | 49 | 33 | 30 | 22 | 18 | 16 | 11 | 9 | 8 | 6 | 5 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2b.40 | I/C | 2015-21 completion projects remaining - Delayed | Nr |  |  |  | 86 | 60 | 50 | 45 | 39 | 33 | 24 | 20 | 15 | 10 | 7 | 6 | 4 | 4 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Prepared by: …………………………………………….. | [5 empty] | Date: ……………………
Checked by: …………………………………………….. | [5 empty] | Date: ……………………
Authorised by:

## G2c
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2022
SECTION G: INVESTMENT MONITORING
Table G2c: Outputs by Milestone
Asset Maintenance | [7 empty] | Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.0001 | I | No outputs identified for this ministerial objective |  | - |  | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0002 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0003 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0004 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0005 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0006 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0007 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0008 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Circular Economy |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.0009 | I | No outputs identified for this ministerial objective |  | - |  | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0010 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0011 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0012 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0013 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0014 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0015 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0016 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Climate Change, Adaptation and Mitigation |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.0017 | I | Number of renewable energy asset interventions | Nr. | O_SE9_M | MA056 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0018 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0019 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0020 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0021 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0022 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0023 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0024 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drinking Water |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.0025 | I | Number of Asset Inspections completed | Nr. | O_AI1_M | IR 18, MA006 | Baseline | G90 - Delivery Approval | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0026 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0027 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0028 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0029 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0030 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0031 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0032 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0033 | I | Number of sites where new phosphate monitoring equipment has been provided | Nr. | O_LD1_E3 | MA041 | Baseline | G90 - Delivery Approval | 0 | 0 | 4 | 4 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27
G2c.0034 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0035 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0036 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0037 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 4 | 4 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27
G2c.0038 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 4 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27
G2c.0039 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 4 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27
G2c.0040 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 4 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27
G2c.0041 | I | Number of lead communication pipes replaced | Nr. | O_LD2_E | MA041 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0042 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0043 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0044 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0045 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0046 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0047 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0048 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0049 | I | Number of WTW sites with auto-shutdown risk control interventions | Nr. | O_OM4_E | MA006 | Baseline | G90 - Delivery Approval | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0050 | I | [5 empty] | SOS - Start On Site | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0051 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0052 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0053 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0054 | I | [5 empty] | SOS - Start On Site | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0055 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0056 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0057 | I | Number of WTW sites with improved organics removal | Nr. | O_OM5_E | MA006 | Baseline | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0058 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0059 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0060 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0061 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0062 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0063 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0064 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0065 | I | Number of sites with emergency planning equipment interventions | Nr. | O_WR1_M | MA087 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0066 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0067 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0068 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0069 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0070 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0071 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0072 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0073 | I | Number of Water Supply Zones with improved resilience | Nr. | O_WR6_E | MA087 | Baseline | G90 - Delivery Approval | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0074 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0075 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0076 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0077 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0078 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0079 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0080 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0081 | I | Number of WTW with increased capacity | Nr. | O_WR8_G1 | MA006 | Baseline | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0082 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0083 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0084 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0085 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0086 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0087 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0088 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Environment |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.0089 | I | Number of Asset Inspections completed | Nr. | O_AI1_M | MA063 | Baseline | G90 - Delivery Approval | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0090 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0091 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0092 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0093 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0094 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0095 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0096 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0097 | I | Number of Combined Storm Overflow (CSO) screen interventions | Nr. | O_SN1_M8 | MA005 | Baseline | G90 - Delivery Approval | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0098 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0099 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0100 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0101 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0102 | I | [5 empty] | SOS - Start On Site | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0103 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0104 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0105 | I | Number of unsatisfactory intermittent discharges (UID) improved or removed | Nr. | O_SN2_E | IR 18, MA005 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0106 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0107 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0108 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0109 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0110 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0111 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0112 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0113 | I | Number of WWTW continuous discharges improved or removed | Nr. | O_WW2_E | MA084 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0114 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0115 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0116 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0117 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0118 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0119 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0120 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0121 | I | Number of studies complete | Nr. | O_WW3_E | MA076 | Baseline | G90 - Delivery Approval | 289 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291
G2c.0122 | I | [5 empty] | SOS - Start On Site | 289 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290
G2c.0123 | I | [5 empty] | G100 - Acceptance | 0 | 27 | 114 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290
G2c.0124 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290 | 290
G2c.0125 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 289 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291
G2c.0126 | I | [5 empty] | SOS - Start On Site | 289 | 290 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291
G2c.0127 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 27 | 191 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291
G2c.0128 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 115 | 290 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291
Flooding and Surface Water Management |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.0129 | I | No outputs identified for this ministerial objective |  | - |  | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0130 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0131 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0132 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0133 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0134 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0135 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0136 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Private Finance Initiative Funded Projects |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.0137 | I | No outputs identified for this ministerial objective |  | - |  | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0138 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0139 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0140 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0141 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0142 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0143 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0144 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Security & Resilience |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.0145 | I | Number of digital systems improved | Nr. | O_DI1_M | MA066 | Baseline | G90 - Delivery Approval | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0146 | I | [5 empty] | SOS - Start On Site | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0147 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0148 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0149 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0150 | I | [5 empty] | SOS - Start On Site | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0151 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0152 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0153 | I | Number of sites with water security interventions | Nr. | O_HS1_M10 | MA089 | Baseline | G90 - Delivery Approval | 7 | 10 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.0154 | I | [5 empty] | SOS - Start On Site | 4 | 6 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0155 | I | [5 empty] | G100 - Acceptance | 0 | 4 | 6 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0156 | I | [5 empty] | G110 - Financial Closure | 0 | 4 | 6 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0157 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 7 | 10 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.0158 | I | [5 empty] | SOS - Start On Site | 7 | 10 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.0159 | I | [5 empty] | G100 - Acceptance | 0 | 4 | 9 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.0160 | I | [5 empty] | G110 - Financial Closure | 0 | 4 | 9 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
Standards of service |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.0161 | I | Number of WTW sludge handling asset interventions | Nr. | O_AD1_M | MA033, MA052, MA094 | Baseline | G90 - Delivery Approval | 77 | 111 | 128 | 156 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163
G2c.0162 | I | [5 empty] | SOS - Start On Site | 35 | 61 | 81 | 94 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98
G2c.0163 | I | [5 empty] | G100 - Acceptance | 0 | 33 | 59 | 74 | 88 | 96 | 96 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98
G2c.0164 | I | [5 empty] | G110 - Financial Closure | 0 | 33 | 59 | 74 | 88 | 91 | 95 | 96 | 96 | 96 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98
G2c.0165 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 77 | 111 | 128 | 156 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163
G2c.0166 | I | [5 empty] | SOS - Start On Site | 72 | 106 | 124 | 156 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163
G2c.0167 | I | [5 empty] | G100 - Acceptance | 0 | 40 | 85 | 127 | 161 | 161 | 161 | 161 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163
G2c.0168 | I | [5 empty] | G110 - Financial Closure | 0 | 39 | 84 | 122 | 156 | 156 | 160 | 161 | 161 | 161 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163
G2c.0169 | I | Number of leakage management equipment interventions | Nr. | O_AD5_M | MA073 | Baseline | G90 - Delivery Approval | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0170 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0171 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0172 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0173 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0174 | I | [5 empty] | SOS - Start On Site | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0175 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0176 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 1 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0177 | I | Number of Asset Inspections completed | Nr. | O_AI1_M | _SR15, MA002, MA004, MA011, MA012, MA014, MA015, MA016, MA017, MA022, MA023, MA025, MA033, MA035, MA037, MA039, MA042, MA043, MA046, MA052, MA054, MA057, MA058, MA091, MA092, MA094, MA096 | Baseline | G90 - Delivery Approval | 1358 | 1369 | 1375 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376
G2c.0178 | I | [5 empty] | SOS - Start On Site | 1319 | 1328 | 1330 | 1333 | 1335 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337
G2c.0179 | I | [5 empty] | G100 - Acceptance | 0 | 23 | 74 | 1275 | 1333 | 1335 | 1336 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337
G2c.0180 | I | [5 empty] | G110 - Financial Closure | 0 | 21 | 59 | 73 | 1269 | 1278 | 1283 | 1335 | 1336 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337 | 1337
G2c.0181 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1358 | 1369 | 1375 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376
G2c.0182 | I | [5 empty] | SOS - Start On Site | 1345 | 1360 | 1370 | 1373 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376
G2c.0183 | I | [5 empty] | G100 - Acceptance | 0 | 16 | 88 | 1308 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376
G2c.0184 | I | [5 empty] | G110 - Financial Closure | 0 | 12 | 33 | 51 | 1260 | 1306 | 1369 | 1372 | 1374 | 1375 | 1375 | 1375 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376 | 1376
G2c.0185 | I | Number of sludge treatment centre asset interventions | Nr. | O_BR1_M | MA024, MA043 | Baseline | G90 - Delivery Approval | 69 | 113 | 146 | 181 | 187 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188
G2c.0186 | I | [5 empty] | SOS - Start On Site | 54 | 88 | 107 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124
G2c.0187 | I | [5 empty] | G100 - Acceptance | 0 | 52 | 87 | 107 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124
G2c.0188 | I | [5 empty] | G110 - Financial Closure | 0 | 48 | 83 | 102 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124
G2c.0189 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 69 | 113 | 146 | 181 | 187 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188
G2c.0190 | I | [5 empty] | SOS - Start On Site | 69 | 113 | 145 | 180 | 187 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188
G2c.0191 | I | [5 empty] | G100 - Acceptance | 0 | 38 | 77 | 121 | 187 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188
G2c.0192 | I | [5 empty] | G110 - Financial Closure | 0 | 34 | 71 | 120 | 187 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188
G2c.0193 | I | Length of water mains replaced or refurbished | m | O_DC2_E | MA058 | Baseline | G90 - Delivery Approval | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256
G2c.0194 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0195 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0196 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0197 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256
G2c.0198 | I | [5 empty] | SOS - Start On Site | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256
G2c.0199 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256
G2c.0200 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256 | 1256
G2c.0201 | I | Length of water mains cleaned | m | O_DC2_M1 | _SR15, MA016 | Baseline | G90 - Delivery Approval | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939
G2c.0202 | I | [5 empty] | SOS - Start On Site | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939
G2c.0203 | I | [5 empty] | G100 - Acceptance | 0 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939
G2c.0204 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939
G2c.0205 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939
G2c.0206 | I | [5 empty] | SOS - Start On Site | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939
G2c.0207 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939
G2c.0208 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939 | 449939
G2c.0209 | I | Length of water mains replaced or refurbished | m | O_DC2_M2 | MA016 | Baseline | G90 - Delivery Approval | 1 | 2 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257
G2c.0210 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 1 | 2 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
G2c.0211 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 2 | 2 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
G2c.0212 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
G2c.0213 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 2 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257
G2c.0214 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 1 | 2 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257
G2c.0215 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257
G2c.0216 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257 | 257
G2c.0217 | I | Number of digital systems improved | Nr. | O_DI1_M | MA066 | Baseline | G90 - Delivery Approval | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0218 | I | [5 empty] | SOS - Start On Site | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0219 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0220 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 3 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0221 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0222 | I | [5 empty] | SOS - Start On Site | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0223 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 2 | 4 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0224 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 1 | 3 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0225 | I | Number of properties removed from internal flooding at risk register. | Nr. | O_FR1_F1 | _SR15, MA020 | Baseline | G90 - Delivery Approval | 68 | 193 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194
G2c.0226 | I | [5 empty] | SOS - Start On Site | 50 | 65 | 66 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192
G2c.0227 | I | [5 empty] | G100 - Acceptance | 0 | 8 | 8 | 25 | 42 | 180 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192
G2c.0228 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1 | 9 | 20 | 152 | 167 | 180 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192
G2c.0229 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 68 | 193 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194
G2c.0230 | I | [5 empty] | SOS - Start On Site | 52 | 66 | 193 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194
G2c.0231 | I | [5 empty] | G100 - Acceptance | 0 | 10 | 11 | 149 | 166 | 178 | 182 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194
G2c.0232 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 14 | 31 | 39 | 56 | 68 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194
G2c.0233 | I | Number of properties with temporary internal flood prevention measures | Nr. | O_FR1_F2 | MA020 | Baseline | G90 - Delivery Approval | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.0234 | I | [5 empty] | SOS - Start On Site | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.0235 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.0236 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.0237 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.0238 | I | [5 empty] | SOS - Start On Site | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.0239 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.0240 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.0241 | I | Number of properties removed from external flooding at risk register. | Nr. | O_FR2_F | _SR15, IR 18, MA020 | Baseline | G90 - Delivery Approval | 53 | 53 | 53 | 53 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
G2c.0242 | I | [5 empty] | SOS - Start On Site | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0243 | I | [5 empty] | G100 - Acceptance | 0 | 2 | 2 | 10 | 10 | 10 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0244 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 2 | 2 | 2 | 2 | 10 | 10 | 10 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0245 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 53 | 53 | 53 | 53 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
G2c.0246 | I | [5 empty] | SOS - Start On Site | 53 | 53 | 53 | 53 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
G2c.0247 | I | [5 empty] | G100 - Acceptance | 0 | 8 | 10 | 19 | 49 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
G2c.0248 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 19 | 22 | 49 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
G2c.0249 | I | Number of Flood risk management (Section 16) model assessments | Nr. | O_FR3_F | IR 18, MA020 | Baseline | G90 - Delivery Approval | 0 | 0 | 1 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0250 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0251 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0252 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0253 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 1 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0254 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 1 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0255 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0256 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0257 | I | Number of reservoir Interests of Safety interventions | Nr. | O_HS1_M1 | MA004 | Baseline | G90 - Delivery Approval | 109 | 117 | 126 | 127 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128
G2c.0258 | I | [5 empty] | SOS - Start On Site | 17 | 25 | 35 | 39 | 40 | 40 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
G2c.0259 | I | [5 empty] | G100 - Acceptance | 0 | 6 | 12 | 22 | 34 | 37 | 40 | 40 | 40 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
G2c.0260 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 7 | 12 | 16 | 27 | 34 | 39 | 40 | 40 | 40 | 41 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
G2c.0261 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 109 | 117 | 126 | 127 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128
G2c.0262 | I | [5 empty] | SOS - Start On Site | 84 | 101 | 119 | 124 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128
G2c.0263 | I | [5 empty] | G100 - Acceptance | 0 | 15 | 35 | 77 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128
G2c.0264 | I | [5 empty] | G110 - Financial Closure | 0 | 7 | 13 | 22 | 83 | 95 | 110 | 127 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128
G2c.0265 | I | Number of sites with standby power equipment interventions | Nr. | O_HS1_M11 | MA092 | Baseline | G90 - Delivery Approval | 38 | 42 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51
G2c.0266 | I | [5 empty] | SOS - Start On Site | 36 | 38 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
G2c.0267 | I | [5 empty] | G100 - Acceptance | 14 | 32 | 33 | 41 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
G2c.0268 | I | [5 empty] | G110 - Financial Closure | 14 | 17 | 33 | 37 | 37 | 37 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
G2c.0269 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 38 | 42 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51
G2c.0270 | I | [5 empty] | SOS - Start On Site | 37 | 42 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51
G2c.0271 | I | [5 empty] | G100 - Acceptance | 0 | 16 | 22 | 32 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51
G2c.0272 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 22 | 28 | 50 | 50 | 50 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51
G2c.0273 | I | Number of water sites with telemetry interventions | Nr. | O_HS1_M12 | MA022, MA033, MA044, MA046 | Baseline | G90 - Delivery Approval | 224 | 231 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238
G2c.0274 | I | [5 empty] | SOS - Start On Site | 209 | 213 | 224 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225
G2c.0275 | I | [5 empty] | G100 - Acceptance | 0 | 208 | 212 | 216 | 224 | 224 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225
G2c.0276 | I | [5 empty] | G110 - Financial Closure | 0 | 4 | 210 | 216 | 216 | 224 | 224 | 224 | 224 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225
G2c.0277 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 224 | 231 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238
G2c.0278 | I | [5 empty] | SOS - Start On Site | 214 | 229 | 237 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238
G2c.0279 | I | [5 empty] | G100 - Acceptance | 0 | 5 | 10 | 231 | 236 | 236 | 236 | 236 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238
G2c.0280 | I | [5 empty] | G110 - Financial Closure | 0 | 5 | 9 | 21 | 228 | 235 | 235 | 236 | 236 | 236 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238
G2c.0281 | I | Number of water property operational buildings interventions | Nr. | O_HS1_M13 | MA096 | Baseline | G90 - Delivery Approval | 238 | 301 | 343 | 344 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346
G2c.0282 | I | [5 empty] | SOS - Start On Site | 60 | 89 | 110 | 113 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116
G2c.0283 | I | [5 empty] | G100 - Acceptance | 0 | 57 | 88 | 107 | 113 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116
G2c.0284 | I | [5 empty] | G110 - Financial Closure | 0 | 53 | 87 | 107 | 109 | 110 | 112 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116
G2c.0285 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 238 | 301 | 343 | 344 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346
G2c.0286 | I | [5 empty] | SOS - Start On Site | 225 | 287 | 337 | 341 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346
G2c.0287 | I | [5 empty] | G100 - Acceptance | 0 | 50 | 228 | 305 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346
G2c.0288 | I | [5 empty] | G110 - Financial Closure | 0 | 45 | 105 | 177 | 207 | 327 | 332 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346 | 346
G2c.0289 | I | Number of raw water storage asset interventions | Nr. | O_HS1_M2 | MA074 | Baseline | G90 - Delivery Approval | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0290 | I | [5 empty] | SOS - Start On Site | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0291 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0292 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0293 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0294 | I | [5 empty] | SOS - Start On Site | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0295 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0296 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0297 | I | Number of water pipe bridge interventions | Nr. | O_HS1_M3 | MA025 | Baseline | G90 - Delivery Approval | 306 | 307 | 307 | 311 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312
G2c.0298 | I | [5 empty] | SOS - Start On Site | 1 | 3 | 3 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.0299 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.0300 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 3 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.0301 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 306 | 307 | 307 | 311 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312
G2c.0302 | I | [5 empty] | SOS - Start On Site | 304 | 305 | 307 | 311 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312
G2c.0303 | I | [5 empty] | G100 - Acceptance | 0 | 101 | 102 | 304 | 311 | 311 | 311 | 311 | 311 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312
G2c.0304 | I | [5 empty] | G110 - Financial Closure | 0 | 101 | 101 | 301 | 308 | 309 | 311 | 311 | 311 | 311 | 311 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312
G2c.0305 | I | Number of fixed wire electrical system or statutory maintenance asset interventions | Nr. | O_HS1_M4 | MA068 | Baseline | G90 - Delivery Approval | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412
G2c.0306 | I | [5 empty] | SOS - Start On Site | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589
G2c.0307 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589
G2c.0308 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 1 | 1 | 1 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589 | 589
G2c.0309 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412
G2c.0310 | I | [5 empty] | SOS - Start On Site | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412
G2c.0311 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412
G2c.0312 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1 | 1 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412 | 1412
G2c.0313 | I | Number of SCADA, HMI, PLC asset interventions | Nr. | O_HS1_M5 | MA022, MA033, MA046 | Baseline | G90 - Delivery Approval | 36 | 54 | 58 | 79 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83
G2c.0314 | I | [5 empty] | SOS - Start On Site | 12 | 29 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33
G2c.0315 | I | [5 empty] | G100 - Acceptance | 0 | 9 | 23 | 27 | 28 | 29 | 31 | 31 | 31 | 32 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33
G2c.0316 | I | [5 empty] | G110 - Financial Closure | 0 | 8 | 23 | 26 | 26 | 26 | 28 | 28 | 29 | 31 | 31 | 31 | 32 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33
G2c.0317 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 36 | 54 | 58 | 79 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83
G2c.0318 | I | [5 empty] | SOS - Start On Site | 34 | 54 | 58 | 78 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83
G2c.0319 | I | [5 empty] | G100 - Acceptance | 0 | 6 | 31 | 64 | 76 | 77 | 77 | 78 | 81 | 82 | 82 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83
G2c.0320 | I | [5 empty] | G110 - Financial Closure | 0 | 3 | 17 | 31 | 75 | 75 | 75 | 77 | 77 | 80 | 81 | 82 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 83
G2c.0321 | I | Number of WTW Chemical Storage and Dosing Vessel interventions | Nr. | O_HS1_M6 | MA037, MA046, MA094 | Baseline | G90 - Delivery Approval | 131 | 131 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132
G2c.0322 | I | [5 empty] | SOS - Start On Site | 5 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0323 | I | [5 empty] | G100 - Acceptance | 0 | 4 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0324 | I | [5 empty] | G110 - Financial Closure | 0 | 4 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0325 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 131 | 131 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132
G2c.0326 | I | [5 empty] | SOS - Start On Site | 128 | 130 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132
G2c.0327 | I | [5 empty] | G100 - Acceptance | 0 | 6 | 14 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132
G2c.0328 | I | [5 empty] | G110 - Financial Closure | 0 | 6 | 9 | 13 | 130 | 131 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132
G2c.0329 | I | Number of street furniture interventions | Nr. | O_HS1_M7 | MA018 | Baseline | G90 - Delivery Approval | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535
G2c.0330 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0331 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0332 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0333 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535
G2c.0334 | I | [5 empty] | SOS - Start On Site | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535
G2c.0335 | I | [5 empty] | G100 - Acceptance | 0 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535
G2c.0336 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535 | 6535
G2c.0337 | I | Number of high voltage system interventions | Nr. | O_HS1_M8 | MA091, MA094 | Baseline | G90 - Delivery Approval | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0338 | I | [5 empty] | SOS - Start On Site | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0339 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0340 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0341 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0342 | I | [5 empty] | SOS - Start On Site | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0343 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0344 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0345 | I | Number of water sites with Motor Control Centre interventions | Nr. | O_HS1_M9 | MA082 | Baseline | G90 - Delivery Approval | 3 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0346 | I | [5 empty] | SOS - Start On Site | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0347 | I | [5 empty] | G100 - Acceptance | 0 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0348 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0349 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 3 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0350 | I | [5 empty] | SOS - Start On Site | 3 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0351 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 2 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0352 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 2 | 4 | 4 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0353 | I | Number of sites with water security enhancements | Nr. | O_HS2_E | MA089 | Baseline | G90 - Delivery Approval | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66
G2c.0354 | I | [5 empty] | SOS - Start On Site | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66
G2c.0355 | I | [5 empty] | G100 - Acceptance | 0 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66
G2c.0356 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66
G2c.0357 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66
G2c.0358 | I | [5 empty] | SOS - Start On Site | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66
G2c.0359 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66
G2c.0360 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 1 | 35 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66
G2c.0361 | I | Number of sites with reservoir drawdown enhancements | Nr. | O_HS3_E | MA004 | Baseline | G90 - Delivery Approval | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0362 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0363 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0364 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0365 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0366 | I | [5 empty] | SOS - Start On Site | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0367 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0368 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0369 | I | Number of Innovation pilot programmes undertaken | Nr. | O_IN1_M | _SR15 | Baseline | G90 - Delivery Approval | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
G2c.0370 | I | [5 empty] | SOS - Start On Site | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
G2c.0371 | I | [5 empty] | G100 - Acceptance | 0 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
G2c.0372 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
G2c.0373 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
G2c.0374 | I | [5 empty] | SOS - Start On Site | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
G2c.0375 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 20 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
G2c.0376 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
G2c.0377 | I | Number of Phosphate Equipment asset interventions | Nr. | O_LD1_M1 | MA046, MA094 | Baseline | G90 - Delivery Approval | 0 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0378 | I | [5 empty] | SOS - Start On Site | 0 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0379 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0380 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0381 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0382 | I | [5 empty] | SOS - Start On Site | 0 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0383 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0384 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0385 | I | Number of WTW Instrumentation interventions | Nr. | O_LD1_M2 | MA095 | Baseline | G90 - Delivery Approval | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0386 | I | [5 empty] | SOS - Start On Site | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0387 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0388 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0389 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0390 | I | [5 empty] | SOS - Start On Site | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0391 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0392 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0393 | I | Number of lead communication pipes replaced | Nr. | O_LD2_E | _SR15, MA025, MA096 | Baseline | G90 - Delivery Approval | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422
G2c.0394 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0395 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0396 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0397 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422
G2c.0398 | I | [5 empty] | SOS - Start On Site | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422
G2c.0399 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 2 | 8380 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422
G2c.0400 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 2 | 8380 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422 | 8422
G2c.0401 | I | Number of vehicle or plant item interventions | Nr. | O_LV1_M | MA071 | Baseline | G90 - Delivery Approval | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174
G2c.0402 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0403 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0404 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0405 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174
G2c.0406 | I | [5 empty] | SOS - Start On Site | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174
G2c.0407 | I | [5 empty] | G100 - Acceptance | 0 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174
G2c.0408 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174
G2c.0409 | I | Number of WTW membranes replaced | Nr. | O_OM1_M1 | MA033 | Baseline | G90 - Delivery Approval | 13 | 14 | 17 | 27 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
G2c.0410 | I | [5 empty] | SOS - Start On Site | 2 | 4 | 6 | 13 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2c.0411 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 4 | 6 | 13 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2c.0412 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 4 | 6 | 13 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2c.0413 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 13 | 14 | 17 | 27 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
G2c.0414 | I | [5 empty] | SOS - Start On Site | 12 | 14 | 17 | 27 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
G2c.0415 | I | [5 empty] | G100 - Acceptance | 0 | 2 | 3 | 8 | 24 | 24 | 24 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
G2c.0416 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 2 | 6 | 24 | 24 | 24 | 24 | 24 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
G2c.0417 | I | Number of WTW sand filters with media replaced | Nr. | O_OM1_M2 | MA033, MA094 | Baseline | G90 - Delivery Approval | 38 | 42 | 49 | 50 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57
G2c.0418 | I | [5 empty] | SOS - Start On Site | 23 | 23 | 29 | 30 | 30 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
G2c.0419 | I | [5 empty] | G100 - Acceptance | 0 | 4 | 14 | 20 | 20 | 20 | 30 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
G2c.0420 | I | [5 empty] | G110 - Financial Closure | 0 | 4 | 5 | 19 | 19 | 20 | 20 | 20 | 20 | 22 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
G2c.0421 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 38 | 42 | 49 | 50 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57
G2c.0422 | I | [5 empty] | SOS - Start On Site | 35 | 39 | 49 | 50 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57
G2c.0423 | I | [5 empty] | G100 - Acceptance | 0 | 2 | 11 | 30 | 46 | 46 | 56 | 56 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57
G2c.0424 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 9 | 22 | 45 | 45 | 46 | 46 | 56 | 56 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57
G2c.0425 | I | Number of WTW Granular Activated Carbon (GAC) filters with media replaced | Nr. | O_OM1_M3 | MA033 | Baseline | G90 - Delivery Approval | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53
G2c.0426 | I | [5 empty] | SOS - Start On Site | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53
G2c.0427 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53
G2c.0428 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 52 | 52 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53
G2c.0429 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53
G2c.0430 | I | [5 empty] | SOS - Start On Site | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53
G2c.0431 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53
G2c.0432 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 52 | 52 | 52 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53
G2c.0433 | I | Number of WTW chemical storage and dosing interventions | Nr. | O_OM1_M4 | MA033, MA046 | Baseline | G90 - Delivery Approval | 785 | 818 | 852 | 887 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954
G2c.0434 | I | [5 empty] | SOS - Start On Site | 728 | 761 | 787 | 814 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819
G2c.0435 | I | [5 empty] | G100 - Acceptance | 685 | 721 | 754 | 781 | 812 | 817 | 818 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819
G2c.0436 | I | [5 empty] | G110 - Financial Closure | 685 | 720 | 748 | 776 | 802 | 814 | 815 | 817 | 817 | 818 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819 | 819
G2c.0437 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 785 | 818 | 852 | 887 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954
G2c.0438 | I | [5 empty] | SOS - Start On Site | 776 | 812 | 850 | 887 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954
G2c.0439 | I | [5 empty] | G100 - Acceptance | 0 | 35 | 88 | 155 | 949 | 950 | 951 | 951 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954
G2c.0440 | I | [5 empty] | G110 - Financial Closure | 0 | 34 | 79 | 146 | 918 | 943 | 946 | 950 | 951 | 952 | 953 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954 | 954
G2c.0441 | I | Number of Filtration and disinfection asset interventions | Nr. | O_OM1_M5 | MA033, MA046, MA093, MA094 | Baseline | G90 - Delivery Approval | 198 | 293 | 510 | 638 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656
G2c.0442 | I | [5 empty] | SOS - Start On Site | 80 | 142 | 236 | 348 | 363 | 363 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366
G2c.0443 | I | [5 empty] | G100 - Acceptance | 0 | 74 | 138 | 246 | 348 | 360 | 362 | 362 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366
G2c.0444 | I | [5 empty] | G110 - Financial Closure | 0 | 74 | 138 | 245 | 346 | 358 | 359 | 360 | 361 | 362 | 362 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366 | 366
G2c.0445 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 198 | 293 | 510 | 638 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656
G2c.0446 | I | [5 empty] | SOS - Start On Site | 195 | 290 | 505 | 638 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656
G2c.0447 | I | [5 empty] | G100 - Acceptance | 0 | 99 | 189 | 464 | 643 | 643 | 644 | 650 | 655 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656
G2c.0448 | I | [5 empty] | G110 - Financial Closure | 0 | 99 | 189 | 461 | 636 | 636 | 636 | 644 | 644 | 651 | 655 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656 | 656
G2c.0449 | I | Number of WTW Instrumentation interventions | Nr. | O_OM1_M6 | MA042, MA043, MA046, MA095 | Baseline | G90 - Delivery Approval | 367 | 389 | 505 | 505 | 521 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525
G2c.0450 | I | [5 empty] | SOS - Start On Site | 313 | 332 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444
G2c.0451 | I | [5 empty] | G100 - Acceptance | 0 | 311 | 332 | 443 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444
G2c.0452 | I | [5 empty] | G110 - Financial Closure | 0 | 311 | 331 | 441 | 443 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444
G2c.0453 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 367 | 389 | 505 | 505 | 521 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525
G2c.0454 | I | [5 empty] | SOS - Start On Site | 365 | 388 | 505 | 505 | 521 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525
G2c.0455 | I | [5 empty] | G100 - Acceptance | 0 | 34 | 74 | 491 | 521 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525
G2c.0456 | I | [5 empty] | G110 - Financial Closure | 0 | 34 | 69 | 485 | 520 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525 | 525
G2c.0457 | I | Number of treated water storage or secondary disinfection asset interventions | Nr. | O_OM2_M1 | MA037, MA046, MA096 | Baseline | G90 - Delivery Approval | 173 | 193 | 201 | 224 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235
G2c.0458 | I | [5 empty] | SOS - Start On Site | 53 | 75 | 83 | 109 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120
G2c.0459 | I | [5 empty] | G100 - Acceptance | 0 | 31 | 48 | 64 | 100 | 119 | 119 | 119 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120
G2c.0460 | I | [5 empty] | G110 - Financial Closure | 0 | 28 | 43 | 54 | 88 | 98 | 104 | 114 | 119 | 119 | 119 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120
G2c.0461 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 173 | 193 | 201 | 224 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235
G2c.0462 | I | [5 empty] | SOS - Start On Site | 152 | 180 | 196 | 221 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235
G2c.0463 | I | [5 empty] | G100 - Acceptance | 0 | 24 | 91 | 156 | 230 | 233 | 234 | 234 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235
G2c.0464 | I | [5 empty] | G110 - Financial Closure | 0 | 20 | 42 | 84 | 164 | 183 | 213 | 233 | 233 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235
G2c.0465 | I | Number of sample point interventions | Nr. | O_OM2_M2 | MA081 | Baseline | G90 - Delivery Approval | 8 | 14 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G2c.0466 | I | [5 empty] | SOS - Start On Site | 4 | 6 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
G2c.0467 | I | [5 empty] | G100 - Acceptance | 0 | 4 | 7 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
G2c.0468 | I | [5 empty] | G110 - Financial Closure | 0 | 3 | 7 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
G2c.0469 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 8 | 14 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G2c.0470 | I | [5 empty] | SOS - Start On Site | 7 | 12 | 18 | 18 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G2c.0471 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 8 | 14 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G2c.0472 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 5 | 12 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G2c.0473 | I | Number of treated water storage by-pass interventions | Nr. | O_OM6_M | MA037 | Baseline | G90 - Delivery Approval | 22 | 23 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
G2c.0474 | I | [5 empty] | SOS - Start On Site | 12 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0475 | I | [5 empty] | G100 - Acceptance | 0 | 10 | 11 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0476 | I | [5 empty] | G110 - Financial Closure | 0 | 3 | 10 | 10 | 12 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0477 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 22 | 23 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
G2c.0478 | I | [5 empty] | SOS - Start On Site | 22 | 23 | 23 | 23 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
G2c.0479 | I | [5 empty] | G100 - Acceptance | 0 | 7 | 9 | 18 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
G2c.0480 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 1 | 8 | 15 | 18 | 23 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
G2c.0481 | I | Number ATOM water asset interventions | Nr. | O_OM9_M | MA068 | Baseline | G90 - Delivery Approval | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0482 | I | [5 empty] | SOS - Start On Site | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0483 | I | [5 empty] | G100 - Acceptance | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0484 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0485 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0486 | I | [5 empty] | SOS - Start On Site | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0487 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0488 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0489 | I | Number of property asset interventions | Nr. | O_PE1_M | MA029 | Baseline | G90 - Delivery Approval | 5 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0490 | I | [5 empty] | SOS - Start On Site | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0491 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0492 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0493 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 5 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0494 | I | [5 empty] | SOS - Start On Site | 5 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0495 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 5 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0496 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 2 | 4 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0497 | I | Length of trunk main interventions | m | O_SA1_M1 | MA001, MA025 | Baseline | G90 - Delivery Approval | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007
G2c.0498 | I | [5 empty] | SOS - Start On Site | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047
G2c.0499 | I | [5 empty] | G100 - Acceptance | 0 | 1260 | 1260 | 1260 | 1260 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047
G2c.0500 | I | [5 empty] | G110 - Financial Closure | 0 | 370 | 370 | 370 | 1260 | 1260 | 1260 | 1260 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047 | 5047
G2c.0501 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007
G2c.0502 | I | [5 empty] | SOS - Start On Site | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007
G2c.0503 | I | [5 empty] | G100 - Acceptance | 0 | 4850 | 5220 | 5220 | 5220 | 5220 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007
G2c.0504 | I | [5 empty] | G110 - Financial Closure | 0 | 3960 | 5220 | 5220 | 5220 | 5220 | 5220 | 5220 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007 | 9007
G2c.0505 | I | Length of trunk main cathodic protection system interventions | m | O_SA1_M2 | MA025 | Baseline | G90 - Delivery Approval | 247 | 247 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659
G2c.0506 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261
G2c.0507 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 161 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261
G2c.0508 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 161 | 161 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261
G2c.0509 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 247 | 247 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659
G2c.0510 | I | [5 empty] | SOS - Start On Site | 147 | 247 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659
G2c.0511 | I | [5 empty] | G100 - Acceptance | 0 | 101 | 214 | 409 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659
G2c.0512 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 101 | 408 | 658 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659 | 659
G2c.0513 | I | Number of raw water intake interventions | Nr. | O_SA2_M | MA025 | Baseline | G90 - Delivery Approval | 7 | 10 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0514 | I | [5 empty] | SOS - Start On Site | 3 | 4 | 7 | 7 | 7 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0515 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 5 | 6 | 7 | 7 | 7 | 7 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0516 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 5 | 6 | 6 | 7 | 7 | 7 | 7 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0517 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 7 | 10 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0518 | I | [5 empty] | SOS - Start On Site | 6 | 8 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0519 | I | [5 empty] | G100 - Acceptance | 0 | 5 | 6 | 12 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0520 | I | [5 empty] | G110 - Financial Closure | 0 | 5 | 5 | 10 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0521 | I | Number of treated water pump interventions | Nr. | O_SA3_M1 | MA015, MA058 | Baseline | G90 - Delivery Approval | 41 | 55 | 68 | 81 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82
G2c.0522 | I | [5 empty] | SOS - Start On Site | 20 | 32 | 43 | 51 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52
G2c.0523 | I | [5 empty] | G100 - Acceptance | 0 | 17 | 32 | 41 | 51 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52
G2c.0524 | I | [5 empty] | G110 - Financial Closure | 0 | 17 | 29 | 38 | 48 | 51 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52
G2c.0525 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 41 | 55 | 68 | 81 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82
G2c.0526 | I | [5 empty] | SOS - Start On Site | 38 | 53 | 67 | 81 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82
G2c.0527 | I | [5 empty] | G100 - Acceptance | 0 | 13 | 32 | 56 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82
G2c.0528 | I | [5 empty] | G110 - Financial Closure | 0 | 13 | 29 | 52 | 77 | 78 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82
G2c.0529 | I | Number of raw water pump interventions | Nr. | O_SA3_M2 | MA046, MA058 | Baseline | G90 - Delivery Approval | 22 | 25 | 31 | 33 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34
G2c.0530 | I | [5 empty] | SOS - Start On Site | 15 | 15 | 19 | 20 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21
G2c.0531 | I | [5 empty] | G100 - Acceptance | 0 | 15 | 15 | 18 | 20 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21
G2c.0532 | I | [5 empty] | G110 - Financial Closure | 0 | 11 | 11 | 14 | 19 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21
G2c.0533 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 22 | 25 | 31 | 33 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34
G2c.0534 | I | [5 empty] | SOS - Start On Site | 21 | 25 | 31 | 33 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34
G2c.0535 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 13 | 18 | 29 | 33 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34
G2c.0536 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 11 | 16 | 26 | 26 | 31 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34
G2c.0537 | I | Length of raw water mains interventions | m | O_SA4_M | MA025 | Baseline | G90 - Delivery Approval | 726 | 1107 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216
G2c.0538 | I | [5 empty] | SOS - Start On Site | 0 | 382 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425
G2c.0539 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 421 | 424 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425
G2c.0540 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 381 | 384 | 424 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425
G2c.0541 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 726 | 1107 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216
G2c.0542 | I | [5 empty] | SOS - Start On Site | 725 | 1107 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216
G2c.0543 | I | [5 empty] | G100 - Acceptance | 0 | 724 | 766 | 1120 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216
G2c.0544 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 2 | 355 | 1176 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216 | 1216
G2c.0545 | I | Length of aqueducts or tunnel interventions | m | O_SA5_M | MA025 | Baseline | G90 - Delivery Approval | 27600 | 27600 | 27601 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602
G2c.0546 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0547 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0548 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0549 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 27600 | 27600 | 27601 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602
G2c.0550 | I | [5 empty] | SOS - Start On Site | 27600 | 27600 | 27600 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602
G2c.0551 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 27600 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602
G2c.0552 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 27601 | 27601 | 27601 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602 | 27602
G2c.0553 | I | Length of new or enhanced distribution mains | m | O_SA6_E | MA015, MA037 | Baseline | G90 - Delivery Approval | 1500 | 1500 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870
G2c.0554 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370
G2c.0555 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370
G2c.0556 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370
G2c.0557 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1500 | 1500 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870
G2c.0558 | I | [5 empty] | SOS - Start On Site | 1500 | 1500 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870
G2c.0559 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870
G2c.0560 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 370 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870
G2c.0561 | I | Length of distribution mains interventions | m | O_SA6_M2 | _SR15, MA001, MA015, MA037, MA058 | Baseline | G90 - Delivery Approval | 106455 | 110019 | 113165 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166
G2c.0562 | I | [5 empty] | SOS - Start On Site | 88419 | 98635 | 100965 | 102950 | 103010 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160
G2c.0563 | I | [5 empty] | G100 - Acceptance | 0 | 35644 | 41932 | 61083 | 68990 | 84169 | 90230 | 103010 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160
G2c.0564 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 1739 | 32229 | 41967 | 52725 | 65188 | 70606 | 84230 | 90380 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160 | 103160
G2c.0565 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 106455 | 110019 | 113165 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166
G2c.0566 | I | [5 empty] | SOS - Start On Site | 100898 | 105115 | 109542 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166
G2c.0567 | I | [5 empty] | G100 - Acceptance | 0 | 24382 | 34646 | 65353 | 94386 | 94386 | 94386 | 94386 | 107166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166
G2c.0568 | I | [5 empty] | G110 - Financial Closure | 0 | 2054 | 5874 | 30929 | 65642 | 68083 | 90356 | 94386 | 94386 | 94386 | 107166 | 107166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166 | 113166
G2c.0569 | I | Number of properties with persistent low pressure resolved | Nr. | O_SA7_E | MA070 | Baseline | G90 - Delivery Approval | 0 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.0570 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.0571 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.0572 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.0573 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.0574 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.0575 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.0576 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.0577 | I | Number of borehole interventions | Nr. | O_SA8_M | MA033, MA080, MA094 | Baseline | G90 - Delivery Approval | 30 | 44 | 53 | 58 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65
G2c.0578 | I | [5 empty] | SOS - Start On Site | 20 | 25 | 29 | 36 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39
G2c.0579 | I | [5 empty] | G100 - Acceptance | 0 | 12 | 16 | 33 | 36 | 37 | 37 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39
G2c.0580 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 16 | 21 | 25 | 37 | 37 | 37 | 37 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39
G2c.0581 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 30 | 44 | 53 | 58 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65
G2c.0582 | I | [5 empty] | SOS - Start On Site | 26 | 37 | 48 | 58 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65
G2c.0583 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 9 | 22 | 60 | 60 | 60 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65
G2c.0584 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 6 | 11 | 39 | 46 | 49 | 60 | 60 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65
G2c.0585 | I | Number of scientific equipment instruments replaced | Nr. | O_SC1_M | MA053 | Baseline | G90 - Delivery Approval | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114
G2c.0586 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0587 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0588 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0589 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114
G2c.0590 | I | [5 empty] | SOS - Start On Site | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114
G2c.0591 | I | [5 empty] | G100 - Acceptance | 0 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114
G2c.0592 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114
G2c.0593 | I | Length of critical sewers interventions | m | O_SN1_M1 | MA002, MA014 | Baseline | G90 - Delivery Approval | 4647 | 4660 | 4716 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717
G2c.0594 | I | [5 empty] | SOS - Start On Site | 2118 | 2129 | 2132 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135
G2c.0595 | I | [5 empty] | G100 - Acceptance | 0 | 500 | 886 | 2132 | 2134 | 2134 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135
G2c.0596 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 11 | 889 | 889 | 889 | 2132 | 2132 | 2133 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135 | 2135
G2c.0597 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 4647 | 4660 | 4716 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717
G2c.0598 | I | [5 empty] | SOS - Start On Site | 3651 | 4659 | 4714 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717
G2c.0599 | I | [5 empty] | G100 - Acceptance | 0 | 500 | 1310 | 2004 | 2478 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717
G2c.0600 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 7 | 15 | 517 | 2425 | 2426 | 4665 | 4665 | 4667 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717 | 4717
G2c.0601 | I | Number of wastewater Network Motor Control Centre interventions | Nr. | O_SN1_M11 | MA011, MA023 | Baseline | G90 - Delivery Approval | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0602 | I | [5 empty] | SOS - Start On Site | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0603 | I | [5 empty] | G100 - Acceptance | 0 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0604 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0605 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0606 | I | [5 empty] | SOS - Start On Site | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0607 | I | [5 empty] | G100 - Acceptance | 0 | 6 | 6 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0608 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 6 | 6 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0609 | I | Number of sites with wastewater pipebridge interventions | Nr. | O_SN1_M12 | MA003 | Baseline | G90 - Delivery Approval | 29 | 29 | 32 | 32 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33
G2c.0610 | I | [5 empty] | SOS - Start On Site | 6 | 7 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2c.0611 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 5 | 14 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2c.0612 | I | [5 empty] | G110 - Financial Closure | 0 | 3 | 3 | 4 | 4 | 6 | 8 | 8 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2c.0613 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 29 | 29 | 32 | 32 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33
G2c.0614 | I | [5 empty] | SOS - Start On Site | 20 | 21 | 32 | 32 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33
G2c.0615 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 4 | 13 | 22 | 22 | 22 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33
G2c.0616 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 2 | 3 | 9 | 14 | 14 | 14 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33
G2c.0617 | I | Number of screw pumps interventions | Nr. | O_SN1_M13 | MA023, MA036 | Baseline | G90 - Delivery Approval | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0618 | I | [5 empty] | SOS - Start On Site | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0619 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0620 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0621 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0622 | I | [5 empty] | SOS - Start On Site | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0623 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0624 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0625 | I | Number of sites with sewage pumping station interventions | Nr. | O_SN1_M14 | MA017, MA023 | Baseline | G90 - Delivery Approval | 356 | 541 | 671 | 778 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806
G2c.0626 | I | [5 empty] | SOS - Start On Site | 261 | 383 | 474 | 547 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566
G2c.0627 | I | [5 empty] | G100 - Acceptance | 0 | 249 | 379 | 484 | 546 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566
G2c.0628 | I | [5 empty] | G110 - Financial Closure | 0 | 246 | 372 | 473 | 536 | 557 | 562 | 564 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566
G2c.0629 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 356 | 541 | 671 | 778 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806
G2c.0630 | I | [5 empty] | SOS - Start On Site | 351 | 536 | 669 | 778 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806
G2c.0631 | I | [5 empty] | G100 - Acceptance | 0 | 197 | 383 | 608 | 805 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806 | 806
G2c.0632 | I | [5 empty] | G110 - Financial Closure | 0 | 189 | 373 | 600 | 785 | 789 | 793 | 797 | 800 | 805 | 805 | 805 | 805 | 805 | 805 | 805 | 805 | 805 | 805 | 805 | 805 | 805 | 805 | 805 | 805 | 806
G2c.0633 | I | Number of storm tank interventions | Nr. | O_SN1_M16 | MA017, MA062 | Baseline | G90 - Delivery Approval | 6 | 10 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.0634 | I | [5 empty] | SOS - Start On Site | 2 | 6 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0635 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 4 | 6 | 7 | 7 | 7 | 7 | 7 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0636 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 4 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0637 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 6 | 10 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.0638 | I | [5 empty] | SOS - Start On Site | 6 | 10 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.0639 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 5 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.0640 | I | [5 empty] | G110 - Financial Closure | 0 | 3 | 5 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.0641 | I | Number of wastewater property operational building interventions | Nr. | O_SN1_M18 | MA096 | Baseline | G90 - Delivery Approval | 6 | 16 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
G2c.0642 | I | [5 empty] | SOS - Start On Site | 0 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0643 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0644 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0645 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 6 | 16 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
G2c.0646 | I | [5 empty] | SOS - Start On Site | 6 | 16 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
G2c.0647 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 9 | 18 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
G2c.0648 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 9 | 18 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
G2c.0649 | I | Length of wastewater pumping main interventions | m | O_SN1_M2 | MA012 | Baseline | G90 - Delivery Approval | 1058 | 1061 | 1063 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144
G2c.0650 | I | [5 empty] | SOS - Start On Site | 657 | 1039 | 1040 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121
G2c.0651 | I | [5 empty] | G100 - Acceptance | 0 | 201 | 658 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121
G2c.0652 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 203 | 206 | 587 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121
G2c.0653 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1058 | 1061 | 1063 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144
G2c.0654 | I | [5 empty] | SOS - Start On Site | 678 | 1060 | 1062 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144
G2c.0655 | I | [5 empty] | G100 - Acceptance | 0 | 676 | 680 | 1063 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144
G2c.0656 | I | [5 empty] | G110 - Financial Closure | 0 | 203 | 225 | 227 | 680 | 1062 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144 | 1144
G2c.0657 | I | Length of sea outfalls replaced or maintained | m | O_SN1_M3 | MA035, MA043 | Baseline | G90 - Delivery Approval | 580 | 585 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586
G2c.0658 | I | [5 empty] | SOS - Start On Site | 567 | 567 | 570 | 570 | 570 | 570 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580
G2c.0659 | I | [5 empty] | G100 - Acceptance | 0 | 566 | 566 | 567 | 570 | 570 | 570 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580
G2c.0660 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 566 | 567 | 568 | 568 | 568 | 570 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580 | 580
G2c.0661 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 580 | 585 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586
G2c.0662 | I | [5 empty] | SOS - Start On Site | 568 | 573 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586
G2c.0663 | I | [5 empty] | G100 - Acceptance | 0 | 4 | 571 | 582 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586
G2c.0664 | I | [5 empty] | G110 - Financial Closure | 0 | 4 | 6 | 7 | 21 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586 | 586
G2c.0665 | I | Length of non-critical sewer interventions | m | O_SN1_M4 | MA003, MA014, MA039 | Baseline | G90 - Delivery Approval | 9092 | 9777 | 10290 | 10399 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404
G2c.0666 | I | [5 empty] | SOS - Start On Site | 6693 | 6730 | 6923 | 6996 | 7001 | 7003 | 7003 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263
G2c.0667 | I | [5 empty] | G100 - Acceptance | 0 | 2133 | 5536 | 6692 | 6808 | 6998 | 7000 | 7002 | 7003 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263
G2c.0668 | I | [5 empty] | G110 - Financial Closure | 0 | 5 | 71 | 676 | 2517 | 5894 | 6744 | 6815 | 7002 | 7002 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263 | 7263
G2c.0669 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 9092 | 9777 | 10290 | 10399 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404
G2c.0670 | I | [5 empty] | SOS - Start On Site | 9087 | 9169 | 10025 | 10397 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404
G2c.0671 | I | [5 empty] | G100 - Acceptance | 1 | 2427 | 4066 | 5918 | 6611 | 10219 | 10219 | 10219 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404
G2c.0672 | I | [5 empty] | G110 - Financial Closure | 1 | 1798 | 2068 | 2552 | 4632 | 6110 | 9858 | 10190 | 10216 | 10217 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404 | 10404
G2c.0673 | I | Number of street furniture interventions | Nr. | O_SN1_M5 | MA018 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0674 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0675 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0676 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0677 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0678 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0679 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0680 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0681 | I | Number of sites with sewer structures APNRV intervention | Nr. | O_SN1_M7 | MA062 | Baseline | G90 - Delivery Approval | 2 | 8 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.0682 | I | [5 empty] | SOS - Start On Site | 0 | 5 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0683 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 5 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0684 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0685 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 2 | 8 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.0686 | I | [5 empty] | SOS - Start On Site | 2 | 7 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.0687 | I | [5 empty] | G100 - Acceptance | 0 | 2 | 9 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.0688 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 8 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.0689 | I | Number of Combined Storm Overflow (CSO) screen interventions | Nr. | O_SN1_M8 | MA039 | Baseline | G90 - Delivery Approval | 12 | 17 | 24 | 26 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27
G2c.0690 | I | [5 empty] | SOS - Start On Site | 4 | 7 | 7 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0691 | I | [5 empty] | G100 - Acceptance | 0 | 4 | 7 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0692 | I | [5 empty] | G110 - Financial Closure | 0 | 4 | 7 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0693 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 12 | 17 | 24 | 26 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27
G2c.0694 | I | [5 empty] | SOS - Start On Site | 12 | 16 | 24 | 26 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27
G2c.0695 | I | [5 empty] | G100 - Acceptance | 0 | 4 | 14 | 23 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27
G2c.0696 | I | [5 empty] | G110 - Financial Closure | 0 | 3 | 13 | 21 | 25 | 25 | 26 | 26 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27
G2c.0697 | I | Number of Transformation initiatives implemented | Nr. | O_TF1_E | MA_proj_app | Baseline | G90 - Delivery Approval | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0698 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0699 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0700 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0701 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0702 | I | [5 empty] | SOS - Start On Site | 0 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0703 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0704 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0705 | I | Number of sites with emergency planning equipment interventions | Nr. | O_WR1_M | MA098 | Baseline | G90 - Delivery Approval | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0706 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0707 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0708 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0709 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0710 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0711 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0712 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0713 | I | Number of strategic network valve interventions | Nr. | O_WR2_M | MA060, MA094 | Baseline | G90 - Delivery Approval | 9 | 17 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
G2c.0714 | I | [5 empty] | SOS - Start On Site | 1 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0715 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 5 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0716 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0717 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 9 | 17 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
G2c.0718 | I | [5 empty] | SOS - Start On Site | 9 | 17 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
G2c.0719 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 6 | 14 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
G2c.0720 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 6 | 14 | 16 | 16 | 16 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
G2c.0721 | I | Number of water hydraulic models maintained | Nr. | O_WR4_M | MA054 | Baseline | G90 - Delivery Approval | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59
G2c.0722 | I | [5 empty] | SOS - Start On Site | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59
G2c.0723 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59
G2c.0724 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 1 | 1 | 1 | 1 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59
G2c.0725 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59
G2c.0726 | I | [5 empty] | SOS - Start On Site | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59
G2c.0727 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59
G2c.0728 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1 | 1 | 1 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59
G2c.0729 | I | Number of sites with security fencing or gate interventions - wastewater | Nr. | O_WW1_M1 | MA044, MA096 | Baseline | G90 - Delivery Approval | 8 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.0730 | I | [5 empty] | SOS - Start On Site | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.0731 | I | [5 empty] | G100 - Acceptance | 0 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.0732 | I | [5 empty] | G110 - Financial Closure | 0 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.0733 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 8 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.0734 | I | [5 empty] | SOS - Start On Site | 8 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.0735 | I | [5 empty] | G100 - Acceptance | 0 | 7 | 7 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.0736 | I | [5 empty] | G110 - Financial Closure | 0 | 7 | 7 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.0737 | I | Number of WWTW odour equipment asset interventions | Nr. | O_WW1_M10 | _SR15, MA012, MA017, MA043, MA049 | Baseline | G90 - Delivery Approval | 10 | 21 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.0738 | I | [5 empty] | SOS - Start On Site | 3 | 5 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
G2c.0739 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 6 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
G2c.0740 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 6 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
G2c.0741 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 10 | 21 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.0742 | I | [5 empty] | SOS - Start On Site | 10 | 21 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.0743 | I | [5 empty] | G100 - Acceptance | 0 | 6 | 15 | 24 | 27 | 27 | 27 | 27 | 27 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.0744 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 9 | 23 | 26 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.0745 | I | Number of WWTW primary treatment asset interventions | Nr. | O_WW1_M11 | MA013, MA017, MA042, MA043 | Baseline | G90 - Delivery Approval | 62 | 138 | 173 | 201 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208
G2c.0746 | I | [5 empty] | SOS - Start On Site | 44 | 98 | 118 | 134 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137
G2c.0747 | I | [5 empty] | G100 - Acceptance | 0 | 41 | 95 | 114 | 132 | 135 | 136 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137
G2c.0748 | I | [5 empty] | G110 - Financial Closure | 0 | 38 | 92 | 113 | 129 | 132 | 132 | 135 | 135 | 136 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137 | 137
G2c.0749 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 62 | 138 | 173 | 201 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208
G2c.0750 | I | [5 empty] | SOS - Start On Site | 62 | 136 | 173 | 201 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208
G2c.0751 | I | [5 empty] | G100 - Acceptance | 0 | 38 | 103 | 164 | 203 | 205 | 205 | 205 | 205 | 206 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208
G2c.0752 | I | [5 empty] | G110 - Financial Closure | 0 | 35 | 98 | 162 | 202 | 202 | 204 | 204 | 204 | 205 | 205 | 206 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208
G2c.0753 | I | Number of redundant or abandoned assets interventions - WWTW | Nr. | O_WW1_M12 | MA096 | Baseline | G90 - Delivery Approval | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0754 | I | [5 empty] | SOS - Start On Site | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0755 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0756 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0757 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0758 | I | [5 empty] | SOS - Start On Site | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0759 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0760 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0761 | I | Number of WWTW secondary treatment asset interventions | Nr. | O_WW1_M13 | MA017, MA042, MA043, MA057 | Baseline | G90 - Delivery Approval | 325 | 457 | 577 | 675 | 689 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690
G2c.0762 | I | [5 empty] | SOS - Start On Site | 215 | 281 | 370 | 423 | 430 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431
G2c.0763 | I | [5 empty] | G100 - Acceptance | 0 | 201 | 265 | 365 | 421 | 428 | 429 | 430 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431
G2c.0764 | I | [5 empty] | G110 - Financial Closure | 0 | 198 | 256 | 348 | 402 | 414 | 425 | 427 | 428 | 430 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431 | 431
G2c.0765 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 325 | 457 | 577 | 675 | 689 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690
G2c.0766 | I | [5 empty] | SOS - Start On Site | 315 | 451 | 576 | 674 | 689 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690
G2c.0767 | I | [5 empty] | G100 - Acceptance | 0 | 172 | 342 | 532 | 671 | 677 | 678 | 679 | 679 | 686 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690
G2c.0768 | I | [5 empty] | G110 - Financial Closure | 0 | 166 | 331 | 511 | 652 | 655 | 671 | 675 | 677 | 679 | 679 | 686 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690 | 690
G2c.0769 | I | Number of site welfare facilities interventions - WWTW | Nr. | O_WW1_M14 | MA096 | Baseline | G90 - Delivery Approval | 7 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0770 | I | [5 empty] | SOS - Start On Site | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0771 | I | [5 empty] | G100 - Acceptance | 0 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0772 | I | [5 empty] | G110 - Financial Closure | 0 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0773 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 7 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0774 | I | [5 empty] | SOS - Start On Site | 7 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0775 | I | [5 empty] | G100 - Acceptance | 0 | 5 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0776 | I | [5 empty] | G110 - Financial Closure | 0 | 5 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0777 | I | Number of WWTW sites with temporary process unit interventions | Nr. | O_WW1_M15 | MA021 | Baseline | G90 - Delivery Approval | 10 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2c.0778 | I | [5 empty] | SOS - Start On Site | 10 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2c.0779 | I | [5 empty] | G100 - Acceptance | 0 | 9 | 10 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2c.0780 | I | [5 empty] | G110 - Financial Closure | 0 | 9 | 10 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2c.0781 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 10 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2c.0782 | I | [5 empty] | SOS - Start On Site | 10 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2c.0783 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 4 | 6 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2c.0784 | I | [5 empty] | G110 - Financial Closure | 0 | 3 | 4 | 6 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2c.0785 | I | Number of WWTW treatment ancillaries asset interventions | Nr. | O_WW1_M16 | MA015, MA042, MA043, MA057 | Baseline | G90 - Delivery Approval | 454 | 675 | 884 | 1219 | 1264 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265
G2c.0786 | I | [5 empty] | SOS - Start On Site | 375 | 534 | 709 | 1011 | 1052 | 1053 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054
G2c.0787 | I | [5 empty] | G100 - Acceptance | 0 | 150 | 305 | 491 | 1020 | 1052 | 1052 | 1053 | 1053 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054
G2c.0788 | I | [5 empty] | G110 - Financial Closure | 0 | 149 | 304 | 489 | 782 | 814 | 1040 | 1051 | 1052 | 1052 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054 | 1054
G2c.0789 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 454 | 675 | 884 | 1219 | 1264 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265
G2c.0790 | I | [5 empty] | SOS - Start On Site | 449 | 662 | 882 | 1219 | 1264 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265
G2c.0791 | I | [5 empty] | G100 - Acceptance | 0 | 143 | 336 | 637 | 1264 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265
G2c.0792 | I | [5 empty] | G110 - Financial Closure | 0 | 140 | 333 | 631 | 1022 | 1025 | 1252 | 1262 | 1262 | 1262 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265 | 1265
G2c.0793 | I | Number of high voltage system interventions | Nr. | O_WW1_M17 | MA091 | Baseline | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0794 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0795 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0796 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0797 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0798 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0799 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0800 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0801 | I | Number of WWTW statutory maintenance asset interventions | Nr. | O_WW1_M18 | MA068 | Baseline | G90 - Delivery Approval | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0802 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0803 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0804 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0805 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0806 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0807 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0808 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0809 | I | Number of fixed wire electrical system asset interventions | Nr. | O_WW1_M2 | MA068 | Baseline | G90 - Delivery Approval | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338
G2c.0810 | I | [5 empty] | SOS - Start On Site | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773
G2c.0811 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773
G2c.0812 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773 | 1773
G2c.0813 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338
G2c.0814 | I | [5 empty] | SOS - Start On Site | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338
G2c.0815 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338
G2c.0816 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338 | 3338
G2c.0817 | I | Number of WWTW Motor Control Centre interventions | Nr. | O_WW1_M3 | MA011, MA017 | Baseline | G90 - Delivery Approval | 6 | 9 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.0818 | I | [5 empty] | SOS - Start On Site | 2 | 5 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0819 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 5 | 7 | 7 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0820 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 4 | 7 | 7 | 7 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0821 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 6 | 9 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.0822 | I | [5 empty] | SOS - Start On Site | 4 | 9 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.0823 | I | [5 empty] | G100 - Acceptance | 0 | 2 | 9 | 11 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.0824 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 9 | 11 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.0825 | I | Number of wastewater SCADA interventions | Nr. | O_WW1_M4 | MA013, MA023 | Baseline | G90 - Delivery Approval | 17 | 21 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23
G2c.0826 | I | [5 empty] | SOS - Start On Site | 2 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0827 | I | [5 empty] | G100 - Acceptance | 0 | 2 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0828 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0829 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 17 | 21 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23
G2c.0830 | I | [5 empty] | SOS - Start On Site | 17 | 21 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23
G2c.0831 | I | [5 empty] | G100 - Acceptance | 0 | 16 | 20 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23
G2c.0832 | I | [5 empty] | G110 - Financial Closure | 0 | 3 | 7 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23
G2c.0833 | I | Number of screw pumps interventions | Nr. | O_WW1_M5 | MA036 | Baseline | G90 - Delivery Approval | 21 | 32 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
G2c.0834 | I | [5 empty] | SOS - Start On Site | 14 | 26 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29
G2c.0835 | I | [5 empty] | G100 - Acceptance | 0 | 12 | 22 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29
G2c.0836 | I | [5 empty] | G110 - Financial Closure | 0 | 10 | 19 | 23 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29
G2c.0837 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 21 | 32 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
G2c.0838 | I | [5 empty] | SOS - Start On Site | 18 | 32 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
G2c.0839 | I | [5 empty] | G100 - Acceptance | 0 | 8 | 20 | 29 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
G2c.0840 | I | [5 empty] | G110 - Financial Closure | 0 | 4 | 17 | 26 | 31 | 33 | 35 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
G2c.0841 | I | Number of watewater telemetry interventions | Nr. | O_WW1_M6 | MA044 | Baseline | G90 - Delivery Approval | 214 | 216 | 221 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222
G2c.0842 | I | [5 empty] | SOS - Start On Site | 213 | 215 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219
G2c.0843 | I | [5 empty] | G100 - Acceptance | 0 | 212 | 215 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219
G2c.0844 | I | [5 empty] | G110 - Financial Closure | 0 | 150 | 214 | 218 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219
G2c.0845 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 214 | 216 | 221 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222
G2c.0846 | I | [5 empty] | SOS - Start On Site | 214 | 216 | 221 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222
G2c.0847 | I | [5 empty] | G100 - Acceptance | 0 | 165 | 210 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222
G2c.0848 | I | [5 empty] | G110 - Financial Closure | 0 | 103 | 209 | 221 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222
G2c.0849 | I | Number of wastewater property operational building interventions | Nr. | O_WW1_M7 | MA096 | Baseline | G90 - Delivery Approval | 268 | 336 | 362 | 366 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367
G2c.0850 | I | [5 empty] | SOS - Start On Site | 69 | 104 | 122 | 124 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125
G2c.0851 | I | [5 empty] | G100 - Acceptance | 0 | 62 | 98 | 121 | 122 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125
G2c.0852 | I | [5 empty] | G110 - Financial Closure | 0 | 62 | 96 | 110 | 119 | 120 | 124 | 124 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125
G2c.0853 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 268 | 336 | 362 | 366 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367
G2c.0854 | I | [5 empty] | SOS - Start On Site | 264 | 330 | 359 | 363 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367
G2c.0855 | I | [5 empty] | G100 - Acceptance | 0 | 51 | 280 | 337 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367
G2c.0856 | I | [5 empty] | G110 - Financial Closure | 0 | 50 | 118 | 166 | 195 | 363 | 363 | 365 | 366 | 366 | 366 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367 | 367
G2c.0857 | I | Number of WWTW inlet works asset interventions | Nr. | O_WW1_M9 | MA017, MA023, MA042, MA094 | Baseline | G90 - Delivery Approval | 146 | 234 | 376 | 450 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471
G2c.0858 | I | [5 empty] | SOS - Start On Site | 62 | 97 | 170 | 199 | 202 | 202 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203
G2c.0859 | I | [5 empty] | G100 - Acceptance | 0 | 46 | 93 | 171 | 198 | 202 | 202 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203
G2c.0860 | I | [5 empty] | G110 - Financial Closure | 0 | 39 | 80 | 155 | 184 | 190 | 202 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203
G2c.0861 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 146 | 234 | 376 | 450 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471
G2c.0862 | I | [5 empty] | SOS - Start On Site | 142 | 233 | 376 | 450 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471
G2c.0863 | I | [5 empty] | G100 - Acceptance | 0 | 75 | 164 | 324 | 463 | 467 | 467 | 467 | 467 | 469 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471
G2c.0864 | I | [5 empty] | G110 - Financial Closure | 0 | 71 | 159 | 308 | 452 | 452 | 463 | 466 | 466 | 467 | 467 | 469 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471 | 471
Supporting Sustainable Economic Growth |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.0865 | I | Number of Asset Inspections completed | Nr. | O_AI1_M | MA087 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0866 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0867 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0868 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0869 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0870 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0871 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0872 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0873 | I | Number of WWTW sites requiring RRR activities to support Part 4 growth | Nr. | O_ED1_M | MA026 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0874 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0875 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0876 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0877 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0878 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0879 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0880 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0881 | I | Increase in Part 4 capacity to meet local growth requirements | PE | O_ED3_G | MA026 | Baseline | G90 - Delivery Approval | 22842 | 22842 | 22842 | 22842 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898
G2c.0882 | I | [5 empty] | SOS - Start On Site | 21469 | 21876 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842
G2c.0883 | I | [5 empty] | G100 - Acceptance | 0 | 151 | 2745 | 7339 | 10284 | 11602 | 21876 | 21876 | 21876 | 21876 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842
G2c.0884 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 151 | 2745 | 7339 | 10284 | 11602 | 21876 | 21876 | 21876 | 21876 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842 | 22842
G2c.0885 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 22842 | 22842 | 22842 | 22842 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898
G2c.0886 | I | [5 empty] | SOS - Start On Site | 21469 | 21876 | 21876 | 21876 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898
G2c.0887 | I | [5 empty] | G100 - Acceptance | 0 | 151 | 2745 | 2745 | 3699 | 8905 | 21932 | 21932 | 21932 | 21932 | 21932 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898
G2c.0888 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 151 | 2745 | 2745 | 4015 | 9011 | 20982 | 21932 | 21932 | 21932 | 21932 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898 | 22898
G2c.0889 | I | Additional Capacity enabled from strategic wastewater network reinforcement | PE | O_ED4_G | MA032 | Baseline | G90 - Delivery Approval | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259
G2c.0890 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0891 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0892 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0893 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259
G2c.0894 | I | [5 empty] | SOS - Start On Site | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259
G2c.0895 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259
G2c.0896 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259 | 1259
G2c.0897 | I | Length of new or enhanced distribution mains | m | O_SA6_E | MA087 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0898 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0899 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0900 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0901 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0902 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0903 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0904 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0905 | I | Additional Capacity enabled from strategic water network reinforcement | PE | O_WR10_G1 | MA032 | Baseline | G90 - Delivery Approval | 14759 | 14759 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665
G2c.0906 | I | [5 empty] | SOS - Start On Site | 11249 | 14149 | 14149 | 14149 | 14149 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055
G2c.0907 | I | [5 empty] | G100 - Acceptance | 0 | 1320 | 2649 | 10149 | 11249 | 14149 | 14149 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055
G2c.0908 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 1320 | 1320 | 8820 | 8820 | 12626 | 13726 | 13726 | 13726 | 13726 | 13726 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055 | 15055
G2c.0909 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 14759 | 14759 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665
G2c.0910 | I | [5 empty] | SOS - Start On Site | 11859 | 14759 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665
G2c.0911 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1320 | 12765 | 12765 | 12765 | 12765 | 12765 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665
G2c.0912 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 2226 | 2836 | 10336 | 12765 | 12765 | 12765 | 12765 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665 | 15665
G2c.0913 | I | Number of resilience improvements at rural supply hubs to provide capacity for new demand | Nr. | O_WR8_G3 | MA087 | Baseline | G90 - Delivery Approval | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0914 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0915 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0916 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0917 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0918 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0919 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0920 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0921 | I | Number of tanker fill points installed | Nr. | O_WR8_G4 | MA087 | Baseline | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0922 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0923 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0924 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0925 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0926 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0927 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0928 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0929 | I | Number of service relocations - water mains | Nr. | O_WR9_G1 | MA065 | Baseline | G90 - Delivery Approval | 9185 | 9186 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187
G2c.0930 | I | [5 empty] | SOS - Start On Site | 9184 | 9184 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186
G2c.0931 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1077 | 5092 | 7984 | 7985 | 9185 | 9185 | 9185 | 9185 | 9185 | 9185 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186
G2c.0932 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1078 | 1078 | 1078 | 5093 | 7985 | 7985 | 7985 | 9185 | 9185 | 9185 | 9185 | 9185 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186 | 9186
G2c.0933 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 9185 | 9186 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187
G2c.0934 | I | [5 empty] | SOS - Start On Site | 9184 | 9184 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187
G2c.0935 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1077 | 7983 | 7986 | 7986 | 7986 | 7986 | 7986 | 9186 | 9186 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187
G2c.0936 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1076 | 7985 | 7986 | 7986 | 7986 | 7986 | 7986 | 9186 | 9186 | 9186 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187 | 9187
2010-15 outputs remaining that were planned to complete in the 2021-27 period - Planned - SR10 |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.0937 | I | Number of water treatment works improved | No. | 1 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0938 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0939 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0940 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0941 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0942 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0943 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0944 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0945 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0946 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0947 | I | Number of zones made compliant with iron & manganese standards | No. | 2 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0948 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0949 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0950 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0951 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0952 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0953 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0954 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0955 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0956 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0957 | I | Improvements to reliability of drinking water (catchments and treatment) | No. | 3 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0958 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0959 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0960 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0961 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0962 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0963 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0964 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0965 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0966 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0967 | I | Improvements to reliability of drinking water (networks and storage) | No. | 4 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0968 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0969 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0970 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0971 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0972 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0973 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0974 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0975 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0976 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0977 | I | Distribution mains cleaned (km) | km | 5 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0978 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0979 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0980 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0981 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0982 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0983 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0984 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0985 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0986 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0987 | I | Number of water quality etc studies to inform future periods | No. | 6 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0988 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0989 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0990 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0991 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0992 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0993 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0994 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0995 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0996 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0997 | I | 2010-15 outputs planned to complete in the 2015-21 period -DW | No. | 7 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0998 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0999 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1000 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1001 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1002 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1003 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1004 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1005 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1006 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1007 | I | Water supply resilience strategy and improvements made | No. | 8 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1008 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1009 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1010 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1011 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1012 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1013 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1014 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1015 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1016 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1017 | I | Number of zones with improved security of supply (SOSI) | No. | 9 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1018 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1019 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1020 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1021 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1022 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1023 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1024 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1025 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1026 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1027 | I | Number of security measures and improvements to the infrastructure of critical reservoirs | No. | 10 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1028 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1029 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1030 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1031 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1032 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1033 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1034 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1035 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1036 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1037 | I | Number of WWTWs improved to meet UWWTD | No. | 11 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1038 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1039 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1040 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1041 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1042 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1043 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1044 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1045 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1046 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1047 | I | Number of waste water networks improved to meet UWWTD | No. | 12 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1048 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1049 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1050 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1051 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1052 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1053 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1054 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1055 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1056 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1057 | I | Number of improvements required to meet UWWTD - Glasgow completion | No. | 13 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1058 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1059 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1060 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1061 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1062 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1063 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1064 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1065 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1066 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1067 | I | Number of improvements required to meet the Water Framework Directive | No. | 14 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1068 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1069 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1070 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1071 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1072 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1073 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1074 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1075 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1076 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1077 | I | Studies to inform requirements under the revised Bathing Waters Directive | No. | 15 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1078 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1079 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1080 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1081 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1082 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1083 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1084 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1085 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1086 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1087 | I | Number of environmental studies to inform future periods | No. | 16 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1088 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1089 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1090 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1091 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1092 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1093 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1094 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1095 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1096 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1097 | I | Number of improvements required by the Compliance Assessment Scheme; odour reduction and sludge management | No. | 17 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1098 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1099 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1100 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1101 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1102 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1103 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1104 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1105 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1106 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1107 | I | 2010-15 outputs planned to complete in the 2015-21 period - WW | No. | 18 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1108 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1109 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1110 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1111 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1112 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1113 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1114 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1115 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1116 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010-15 completion outputs remaining - Delayed - SR10 |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.1117 | I | Number of water treatment works improved | No. | 1 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1118 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1119 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1120 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1121 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1122 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1123 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1124 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1125 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1126 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1127 | I | Number of zones made compliant with iron & manganese standards | No. | 2 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1128 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1129 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1130 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1131 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1132 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1133 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1134 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1135 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1136 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1137 | I | Improvements to reliability of drinking water (catchments and treatment) | No. | 3 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1138 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1139 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1140 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1141 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1142 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1143 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1144 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1145 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1146 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1147 | I | Improvements to reliability of drinking water (networks and storage) | No. | 4 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1148 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1149 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1150 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1151 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1152 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1153 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1154 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1155 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1156 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1157 | I | Distribution mains cleaned (km) | km | 5 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1158 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1159 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1160 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1161 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1162 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1163 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1164 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1165 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1166 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1167 | I | Number of water quality etc studies to inform future periods | No. | 6 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1168 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1169 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1170 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1171 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1172 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1173 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1174 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1175 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1176 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1177 | I | 2010-15 outputs planned to complete in the 2015-21 period -DW | No. | 7 |  | Committed List Baseline | MS1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1178 | I | [5 empty] | MS2 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1179 | I | [5 empty] | MS3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1180 | I | [5 empty] | MS4 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1181 | I | [5 empty] | MS5 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1182 | I |  |  |  |  | Forecast Actual | MS1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1183 | I | [5 empty] | MS2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1184 | I | [5 empty] | MS3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1185 | I | [5 empty] | MS4 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1186 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1187 | I | Water supply resilience strategy and improvements made | No. | 8 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1188 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1189 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1190 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1191 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1192 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1193 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1194 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1195 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1196 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1197 | I | Number of zones with improved security of supply (SOSI) | No. | 9 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1198 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1199 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1200 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1201 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1202 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1203 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1204 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1205 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1206 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1207 | I | Number of security measures and improvements to the infrastructure of critical reservoirs | No. | 10 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1208 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1209 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1210 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1211 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1212 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1213 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1214 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1215 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1216 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1217 | I | Number of WWTWs improved to meet UWWTD | No. | 11 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1218 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1219 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1220 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1221 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1222 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1223 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1224 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1225 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1226 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1227 | I | Number of waste water networks improved to meet UWWTD | No. | 12 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1228 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1229 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1230 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1231 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1232 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1233 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1234 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1235 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1236 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1237 | I | Number of improvements required to meet UWWTD - Glasgow completion | No. | 13 |  | Committed List Baseline | MS1 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.1238 | I | [5 empty] | MS2 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.1239 | I | [5 empty] | MS3 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.1240 | I | [5 empty] | MS4 | 3 | 3 | 11 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.1241 | I | [5 empty] | MS5 | 0 | 2 | 2 | 10 | 12 | 12 | 12 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.1242 | I |  |  |  |  | Forecast Actual | MS1 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.1243 | I | [5 empty] | MS2 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.1244 | I | [5 empty] | MS3 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.1245 | I | [5 empty] | MS4 | 3 | 4 | 9 | 9 | 11 | 11 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.1246 | I | [5 empty] | MS5 | 0 | 0 | 3 | 3 | 3 | 7 | 10 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 14
G2c.1247 | I | Number of improvements required to meet the Water Framework Directive | No. | 14 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1248 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1249 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1250 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1251 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1252 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1253 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1254 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1255 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1256 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1257 | I | Studies to inform requirements under the revised Bathing Waters Directive | No. | 15 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1258 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1259 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1260 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1261 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1262 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1263 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1264 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1265 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1266 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1267 | I | Number of environmental studies to inform future periods | No. | 16 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1268 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1269 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1270 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1271 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1272 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1273 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1274 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1275 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1276 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1277 | I | Number of improvements required by the Compliance Assessment Scheme; odour reduction and sludge management | No. | 17 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1278 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1279 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1280 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1281 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1282 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1283 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1284 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1285 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1286 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1287 | I | 2010-15 outputs planned to complete in the 2015-21 period - WW | No. | 18 |  | Committed List Baseline | MS1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1288 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1289 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1290 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1291 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1292 | I |  |  |  |  | Forecast Actual | MS1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1293 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1294 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1295 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1296 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2015-21 outputs remaining that were planned to complete in the 2021-27 period - Planned - SR15 |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.1297 | I | Number of water treatment works improved | No. | 1 |  | Committed List Baseline | MS1 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.1298 | I | [5 empty] | MS2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.1299 | I | [5 empty] | MS3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.1300 | I | [5 empty] | MS4 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.1301 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.1302 | I |  |  |  |  | Forecast Actual | MS1 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.1303 | I | [5 empty] | MS2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.1304 | I | [5 empty] | MS3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.1305 | I | [5 empty] | MS4 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.1306 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.1307 | I | Number of zones made compliant with iron & manganese standards | No. | 2 |  | Committed List Baseline | MS1 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1308 | I | [5 empty] | MS2 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1309 | I | [5 empty] | MS3 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1310 | I | [5 empty] | MS4 | 3 | 6 | 7 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1311 | I | [5 empty] | MS5 | 0 | 3 | 6 | 15 | 15 | 16 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1312 | I |  |  |  |  | Forecast Actual | MS1 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1313 | I | [5 empty] | MS2 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1314 | I | [5 empty] | MS3 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1315 | I | [5 empty] | MS4 | 3 | 6 | 6 | 7 | 16 | 16 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1316 | I | [5 empty] | MS5 | 0 | 3 | 3 | 3 | 6 | 7 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1317 | I | Improvements to reliability of drinking water (catchments and treatment) | No. | 3 |  | Committed List Baseline | MS1 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1318 | I | [5 empty] | MS2 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.1319 | I | [5 empty] | MS3 | 6 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1320 | I | [5 empty] | MS4 | 1 | 1 | 2 | 4 | 4 | 5 | 6 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1321 | I | [5 empty] | MS5 | 0 | 1 | 1 | 3 | 4 | 4 | 5 | 6 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1322 | I |  |  |  |  | Forecast Actual | MS1 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1323 | I | [5 empty] | MS2 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1324 | I | [5 empty] | MS3 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1325 | I | [5 empty] | MS4 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8
G2c.1326 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 5 | 5 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8
G2c.1327 | I | Improvements to reliability of drinking water (networks and storage) | No. | 4 |  | Committed List Baseline | MS1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1328 | I | [5 empty] | MS2 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1329 | I | [5 empty] | MS3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1330 | I | [5 empty] | MS4 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1331 | I | [5 empty] | MS5 | 0 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1332 | I |  |  |  |  | Forecast Actual | MS1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1333 | I | [5 empty] | MS2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1334 | I | [5 empty] | MS3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1335 | I | [5 empty] | MS4 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1336 | I | [5 empty] | MS5 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1337 | I | Distribution mains cleaned (km) | km | 5 |  | Committed List Baseline | MS1 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405
G2c.1338 | I | [5 empty] | MS2 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405
G2c.1339 | I | [5 empty] | MS3 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405
G2c.1340 | I | [5 empty] | MS4 | 0 | 149.578 | 2057.299 | 2057.299 | 2057.299 | 2057.299 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405
G2c.1341 | I | [5 empty] | MS5 | 0 | 0 | 149.578 | 161.138 | 161.138 | 161.138 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405
G2c.1342 | I |  |  |  |  | Forecast Actual | MS1 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405
G2c.1343 | I | [5 empty] | MS2 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405
G2c.1344 | I | [5 empty] | MS3 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405
G2c.1345 | I | [5 empty] | MS4 | 0 | 0 | 2323.845 | 2323.845 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405
G2c.1346 | I | [5 empty] | MS5 | 0 | 0 | 149.578 | 149.578 | 505.877 | 505.877 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405
G2c.1347 | I | Number of water quality etc studies to inform future periods | No. | 6 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1348 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1349 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1350 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1351 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1352 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1353 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1354 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1355 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1356 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1357 | I | 2010-15 outputs planned to complete in the 2015-21 period -DW | No. | 7 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1358 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1359 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1360 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1361 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1362 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1363 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1364 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1365 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1366 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1367 | I | Water supply resilience strategy and improvements made | No. | 8 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1368 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1369 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1370 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1371 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1372 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1373 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1374 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1375 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1376 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1377 | I | Number of zones with improved security of supply (SOSI) | No. | 9 |  | Committed List Baseline | MS1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1378 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1379 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1380 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1381 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1382 | I |  |  |  |  | Forecast Actual | MS1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1383 | I | [5 empty] | MS2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1384 | I | [5 empty] | MS3 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1385 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1386 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1387 | I | Number of security measures and improvements to the infrastructure of critical reservoirs | No. | 10 |  | Committed List Baseline | MS1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1388 | I | [5 empty] | MS2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1389 | I | [5 empty] | MS3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1390 | I | [5 empty] | MS4 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1391 | I | [5 empty] | MS5 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1392 | I |  |  |  |  | Forecast Actual | MS1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1393 | I | [5 empty] | MS2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1394 | I | [5 empty] | MS3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1395 | I | [5 empty] | MS4 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1396 | I | [5 empty] | MS5 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1397 | I | Number of WWTWs improved to meet UWWTD | No. | 11 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1398 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1399 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1400 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1401 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1402 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1403 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1404 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1405 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1406 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1407 | I | Number of waste water networks improved to meet UWWTD | No. | 12 |  | Committed List Baseline | MS1 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.1408 | I | [5 empty] | MS2 | 10 | 10 | 10 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.1409 | I | [5 empty] | MS3 | 10 | 10 | 10 | 10 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.1410 | I | [5 empty] | MS4 | 0 | 3 | 6 | 6 | 9 | 10 | 10 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.1411 | I | [5 empty] | MS5 | 0 | 0 | 3 | 6 | 6 | 6 | 10 | 10 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.1412 | I |  |  |  |  | Forecast Actual | MS1 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.1413 | I | [5 empty] | MS2 | 10 | 10 | 10 | 10 | 10 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.1414 | I | [5 empty] | MS3 | 10 | 10 | 10 | 10 | 10 | 10 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.1415 | I | [5 empty] | MS4 | 0 | 3 | 6 | 6 | 7 | 10 | 10 | 10 | 10 | 10 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.1416 | I | [5 empty] | MS5 | 0 | 0 | 0 | 1 | 4 | 7 | 10 | 10 | 10 | 10 | 10 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2c.1417 | I | Number of improvements required to meet UWWTD - Glasgow completion | No. | 13 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1418 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1419 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1420 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1421 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1422 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1423 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1424 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1425 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1426 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1427 | I | Number of improvements required to meet the Water Framework Directive | No. | 14 |  | Committed List Baseline | MS1 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.1428 | I | [5 empty] | MS2 | 4 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.1429 | I | [5 empty] | MS3 | 3 | 4 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1430 | I | [5 empty] | MS4 | 0 | 1 | 2 | 4 | 5 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1431 | I | [5 empty] | MS5 | 0 | 1 | 1 | 2 | 4 | 5 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1432 | I |  |  |  |  | Forecast Actual | MS1 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1433 | I | [5 empty] | MS2 | 4 | 4 | 4 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1434 | I | [5 empty] | MS3 | 3 | 3 | 4 | 4 | 6 | 6 | 6 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1435 | I | [5 empty] | MS4 | 0 | 0 | 1 | 2 | 4 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1436 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 2 | 4 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1437 | I | Studies to inform requirements under the revised Bathing Waters Directive | No. | 15 |  | Committed List Baseline | MS1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1438 | I | [5 empty] | MS2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1439 | I | [5 empty] | MS3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1440 | I | [5 empty] | MS4 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1441 | I | [5 empty] | MS5 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1442 | I |  |  |  |  | Forecast Actual | MS1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1443 | I | [5 empty] | MS2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1444 | I | [5 empty] | MS3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1445 | I | [5 empty] | MS4 | 0 | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1446 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1447 | I | Number of environmental studies to inform future periods | No. | 16 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1448 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1449 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1450 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1451 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1452 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1453 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1454 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1455 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1456 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1457 | I | Number of improvements required by the Compliance Assessment Scheme; odour reduction and sludge management | No. | 17 |  | Committed List Baseline | MS1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1458 | I | [5 empty] | MS2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1459 | I | [5 empty] | MS3 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1460 | I | [5 empty] | MS4 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1461 | I | [5 empty] | MS5 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1462 | I |  |  |  |  | Forecast Actual | MS1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1463 | I | [5 empty] | MS2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1464 | I | [5 empty] | MS3 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1465 | I | [5 empty] | MS4 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1466 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1467 | I | 2010-15 outputs planned to complete in the 2015-21 period - WW | No. | 18 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1468 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1469 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1470 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1471 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1472 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1473 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1474 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1475 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1476 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-21 completion outputs remaining - Delayed - SR15 |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.1477 | I | Number of water treatment works improved | No. | 1 |  | Committed List Baseline | MS1 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
G2c.1478 | I | [5 empty] | MS2 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
G2c.1479 | I | [5 empty] | MS3 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.1480 | I | [5 empty] | MS4 | 3 | 4 | 5 | 6 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.1481 | I | [5 empty] | MS5 | 0 | 0 | 1 | 3 | 3 | 6 | 7 | 8 | 8 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.1482 | I |  |  |  |  | Forecast Actual | MS1 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.1483 | I | [5 empty] | MS2 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.1484 | I | [5 empty] | MS3 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.1485 | I | [5 empty] | MS4 | 3 | 4 | 4 | 4 | 4 | 5 | 6 | 6 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11
G2c.1486 | I | [5 empty] | MS5 | 0 | 0 | 1 | 1 | 2 | 2 | 4 | 4 | 4 | 8 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11
G2c.1487 | I | Number of zones made compliant with iron & manganese standards | No. | 2 |  | Committed List Baseline | MS1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1488 | I | [5 empty] | MS2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1489 | I | [5 empty] | MS3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1490 | I | [5 empty] | MS4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1491 | I | [5 empty] | MS5 | 0 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1492 | I |  |  |  |  | Forecast Actual | MS1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1493 | I | [5 empty] | MS2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1494 | I | [5 empty] | MS3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1495 | I | [5 empty] | MS4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1496 | I | [5 empty] | MS5 | 0 | 0 | 0 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1497 | I | Improvements to reliability of drinking water (catchments and treatment) | No. | 3 |  | Committed List Baseline | MS1 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1498 | I | [5 empty] | MS2 | 16 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1499 | I | [5 empty] | MS3 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1500 | I | [5 empty] | MS4 | 3 | 6 | 7 | 11 | 14 | 14 | 15 | 15 | 16 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1501 | I | [5 empty] | MS5 | 0 | 3 | 5 | 6 | 11 | 13 | 14 | 14 | 15 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1502 | I |  |  |  |  | Forecast Actual | MS1 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1503 | I | [5 empty] | MS2 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1504 | I | [5 empty] | MS3 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1505 | I | [5 empty] | MS4 | 3 | 6 | 7 | 8 | 9 | 11 | 12 | 12 | 14 | 16 | 16 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1506 | I | [5 empty] | MS5 | 0 | 1 | 2 | 3 | 6 | 8 | 9 | 11 | 12 | 13 | 16 | 16 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1507 | I | Improvements to reliability of drinking water (networks and storage) | No. | 4 |  | Committed List Baseline | MS1 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
G2c.1508 | I | [5 empty] | MS2 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
G2c.1509 | I | [5 empty] | MS3 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2c.1510 | I | [5 empty] | MS4 | 2 | 11 | 14 | 14 | 15 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2c.1511 | I | [5 empty] | MS5 | 0 | 9 | 12 | 14 | 14 | 15 | 15 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2c.1512 | I |  |  |  |  | Forecast Actual | MS1 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2c.1513 | I | [5 empty] | MS2 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2c.1514 | I | [5 empty] | MS3 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2c.1515 | I | [5 empty] | MS4 | 2 | 11 | 12 | 12 | 13 | 14 | 15 | 15 | 15 | 15 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2c.1516 | I | [5 empty] | MS5 | 0 | 7 | 8 | 10 | 13 | 13 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2c.1517 | I | Distribution mains cleaned (km) | km | 5 |  | Committed List Baseline | MS1 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633
G2c.1518 | I | [5 empty] | MS2 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633
G2c.1519 | I | [5 empty] | MS3 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633
G2c.1520 | I | [5 empty] | MS4 | 48.4 | 114.18 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633
G2c.1521 | I | [5 empty] | MS5 | 0 | 48.4 | 48.4 | 48.4 | 114.18 | 289.38 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633
G2c.1522 | I |  |  |  |  | Forecast Actual | MS1 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633
G2c.1523 | I | [5 empty] | MS2 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633
G2c.1524 | I | [5 empty] | MS3 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633
G2c.1525 | I | [5 empty] | MS4 | 48.4 | 48.4 | 289.38 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633
G2c.1526 | I | [5 empty] | MS5 | 0 | 0 | 65.78 | 183.433 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633
G2c.1527 | I | Number of water quality etc studies to inform future periods | No. | 6 |  | Committed List Baseline | MS1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1528 | I | [5 empty] | MS2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1529 | I | [5 empty] | MS3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1530 | I | [5 empty] | MS4 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1531 | I | [5 empty] | MS5 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1532 | I |  |  |  |  | Forecast Actual | MS1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1533 | I | [5 empty] | MS2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1534 | I | [5 empty] | MS3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1535 | I | [5 empty] | MS4 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1536 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1537 | I | 2010-15 outputs planned to complete in the 2015-21 period -DW | No. | 7 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1538 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1539 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1540 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1541 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1542 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1543 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1544 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1545 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1546 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1547 | I | Water supply resilience strategy and improvements made | No. | 8 |  | Committed List Baseline | MS1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1548 | I | [5 empty] | MS2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1549 | I | [5 empty] | MS3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1550 | I | [5 empty] | MS4 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1551 | I | [5 empty] | MS5 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1552 | I |  |  |  |  | Forecast Actual | MS1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1553 | I | [5 empty] | MS2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1554 | I | [5 empty] | MS3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1555 | I | [5 empty] | MS4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1556 | I | [5 empty] | MS5 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1557 | I | Number of zones with improved security of supply (SOSI) | No. | 9 |  | Committed List Baseline | MS1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1558 | I | [5 empty] | MS2 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1559 | I | [5 empty] | MS3 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1560 | I | [5 empty] | MS4 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1561 | I | [5 empty] | MS5 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1562 | I |  |  |  |  | Forecast Actual | MS1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1563 | I | [5 empty] | MS2 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1564 | I | [5 empty] | MS3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1565 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1566 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1567 | I | Number of security measures and improvements to the infrastructure of critical reservoirs | No. | 10 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1568 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1569 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1570 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1571 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1572 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1573 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1574 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1575 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1576 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1577 | I | Number of WWTWs improved to meet UWWTD | No. | 11 |  | Committed List Baseline | MS1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1578 | I | [5 empty] | MS2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1579 | I | [5 empty] | MS3 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1580 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1581 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1582 | I |  |  |  |  | Forecast Actual | MS1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1583 | I | [5 empty] | MS2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1584 | I | [5 empty] | MS3 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1585 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1586 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1587 | I | Number of waste water networks improved to meet UWWTD | No. | 12 |  | Committed List Baseline | MS1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1588 | I | [5 empty] | MS2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1589 | I | [5 empty] | MS3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1590 | I | [5 empty] | MS4 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1591 | I | [5 empty] | MS5 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1592 | I |  |  |  |  | Forecast Actual | MS1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1593 | I | [5 empty] | MS2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1594 | I | [5 empty] | MS3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1595 | I | [5 empty] | MS4 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1596 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1597 | I | Number of improvements required to meet UWWTD - Glasgow completion | No. | 13 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1598 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1599 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1600 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1601 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1602 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1603 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1604 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1605 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1606 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1607 | I | Number of improvements required to meet the Water Framework Directive | No. | 14 |  | Committed List Baseline | MS1 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1608 | I | [5 empty] | MS2 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1609 | I | [5 empty] | MS3 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1610 | I | [5 empty] | MS4 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 13 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1611 | I | [5 empty] | MS5 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 10 | 13 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1612 | I |  |  |  |  | Forecast Actual | MS1 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1613 | I | [5 empty] | MS2 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1614 | I | [5 empty] | MS3 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1615 | I | [5 empty] | MS4 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 10 | 13 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1616 | I | [5 empty] | MS5 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 10 | 10 | 13 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.1617 | I | Studies to inform requirements under the revised Bathing Waters Directive | No. | 15 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1618 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1619 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1620 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1621 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1622 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1623 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1624 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1625 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1626 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1627 | I | Number of environmental studies to inform future periods | No. | 16 |  | Committed List Baseline | MS1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1628 | I | [5 empty] | MS2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1629 | I | [5 empty] | MS3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1630 | I | [5 empty] | MS4 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1631 | I | [5 empty] | MS5 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1632 | I |  |  |  |  | Forecast Actual | MS1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1633 | I | [5 empty] | MS2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1634 | I | [5 empty] | MS3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1635 | I | [5 empty] | MS4 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1636 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1637 | I | Number of improvements required by the Compliance Assessment Scheme; odour reduction and sludge management | No. | 17 |  | Committed List Baseline | MS1 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
G2c.1638 | I | [5 empty] | MS2 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
G2c.1639 | I | [5 empty] | MS3 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
G2c.1640 | I | [5 empty] | MS4 | 2 | 2 | 30 | 39 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
G2c.1641 | I | [5 empty] | MS5 | 0 | 2 | 2 | 30 | 39 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
G2c.1642 | I |  |  |  |  | Forecast Actual | MS1 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
G2c.1643 | I | [5 empty] | MS2 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
G2c.1644 | I | [5 empty] | MS3 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
G2c.1645 | I | [5 empty] | MS4 | 2 | 2 | 2 | 2 | 2 | 13 | 14 | 22 | 28 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
G2c.1646 | I | [5 empty] | MS5 | 0 | 0 | 1 | 1 | 2 | 3 | 13 | 22 | 28 | 28 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
G2c.1647 | I | 2010-15 outputs planned to complete in the 2015-21 period - WW | No. | 18 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1648 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1649 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1650 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1651 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1652 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1653 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1654 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1655 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1656 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prepared by: …………………………………………….. |  | 5: Date: ……………………
Checked by: …………………………………………….. |  | 5: Date: ……………………
Authorised by:

## G3
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2022
Table G3: Number of needs or projects by milestone
Standards of Service |  |  |  |  | Confirmed on Committed List | [23 empty] | Non Named (Programmes and Projects within programmes | [23 empty] | Pre Committed List Named | [23 empty] | Confirmed in Committed List + Pre Committed Named + Non Named
[5 empty] | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
G3.1 | I | 2: Baseline; 3: Gate 30 - Project Creation | 136 | 290 | 389 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 11 | 49 | 76 | 108 | 117 | 124 | 124 | 124 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 147 | 339 | 465 | 547 | 556 | 563 | 563 | 563 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566
G3.2 | I | 3: Gate 50 - Options Confirmed | 12 | 19 | 23 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 5 | 21 | 40 | 63 | 83 | 105 | 136 | 150 | 162 | 168 | 171 | 175 | 177 | 178 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 17 | 40 | 63 | 87 | 107 | 129 | 160 | 174 | 186 | 192 | 195 | 199 | 201 | 202 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203
G3.3 | I | 3: Gate 70 - Option Selection | 50 | 66 | 77 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 5 | 24 | 47 | 57 | 85 | 121 | 153 | 187 | 201 | 215 | 219 | 222 | 226 | 229 | 231 | 231 | 232 | 232 | 232 | 232 | 232 | 232 | 232 | 233 | 55 | 90 | 124 | 137 | 165 | 201 | 233 | 267 | 281 | 295 | 299 | 302 | 306 | 309 | 311 | 311 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 313
G3.4 | I | 3: Gate 80 - Project Approval | 61 | 93 | 110 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 1 | 3 | 9 | 12 | 36 | 70 | 103 | 127 | 144 | 160 | 181 | 207 | 229 | 242 | 253 | 258 | 262 | 262 | 264 | 266 | 266 | 267 | 267 | 268 | 62 | 96 | 119 | 140 | 164 | 198 | 231 | 255 | 272 | 288 | 309 | 335 | 357 | 370 | 381 | 386 | 390 | 390 | 392 | 394 | 394 | 395 | 395 | 396
G3.5 | I |  |  | Gate 90 - Delivery Approval | 4 | 17 | 27 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 1025 | 2191 | 3637 | 5104 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 0 | 0 | 0 | 0 | 27 | 59 | 91 | 120 | 138 | 151 | 167 | 178 | 185 | 223 | 243 | 255 | 262 | 265 | 267 | 268 | 272 | 274 | 274 | 275 | 1029 | 2208 | 3664 | 5148 | 5176 | 5208 | 5240 | 5269 | 5287 | 5300 | 5316 | 5327 | 5334 | 5372 | 5392 | 5404 | 5411 | 5414 | 5416 | 5417 | 5421 | 5423 | 5423 | 5424
G3.6 | I |  |  | SOS - Start on Site | 12 | 21 | 36 | 44 | 52 | 57 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 1009 | 2130 | 3628 | 5149 | 5279 | 5388 | 5410 | 5421 | 5425 | 5428 | 5429 | 5430 | 5430 | 5432 | 5432 | 5432 | 5433 | 5433 | 5433 | 5433 | 5433 | 5433 | 5433 | 5434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021 | 2151 | 3664 | 5193 | 5331 | 5445 | 5469 | 5480 | 5484 | 5487 | 5488 | 5489 | 5489 | 5491 | 5491 | 5491 | 5492 | 5492 | 5492 | 5492 | 5492 | 5492 | 5492 | 5493
G3.7 | I |  |  | G100 - Project Acceptance | 43 | 84 | 113 | 136 | 155 | 173 | 188 | 195 | 201 | 212 | 217 | 220 | 223 | 224 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 1542 | 2559 | 3750 | 5187 | 6647 | 6807 | 6941 | 7053 | 7135 | 7150 | 7158 | 7169 | 7172 | 7176 | 7177 | 7180 | 7180 | 7183 | 7183 | 7184 | 7184 | 7184 | 7185 | 7209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1585 | 2643 | 3863 | 5323 | 6802 | 6980 | 7129 | 7248 | 7336 | 7362 | 7375 | 7389 | 7395 | 7400 | 7403 | 7406 | 7406 | 7409 | 7409 | 7410 | 7410 | 7410 | 7411 | 7435
G3.8 | I |  |  | G110 - Financial Closure | 4 | 4 | 30 | 62 | 95 | 129 | 159 | 179 | 199 | 214 | 220 | 230 | 237 | 242 | 245 | 248 | 249 | 251 | 251 | 251 | 251 | 251 | 251 | 251 | 1476 | 2475 | 3665 | 5047 | 6498 | 6635 | 6804 | 6947 | 7074 | 7154 | 7208 | 7229 | 7248 | 7256 | 7259 | 7261 | 7264 | 7264 | 7267 | 7267 | 7268 | 7268 | 7269 | 7290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1480 | 2479 | 3695 | 5109 | 6593 | 6764 | 6963 | 7126 | 7273 | 7368 | 7428 | 7459 | 7485 | 7498 | 7504 | 7509 | 7513 | 7515 | 7518 | 7518 | 7519 | 7519 | 7520 | 7541
G3.9 | I | 2: Forecast Actual; 3: Gate 30 - Project Creation | 136 | 290 | 389 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 439 | 11 | 49 | 76 | 108 | 117 | 124 | 124 | 124 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 147 | 339 | 465 | 547 | 556 | 563 | 563 | 563 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566 | 566
G3.10 | I | 3: Gate 50 - Options Confirmed | 12 | 19 | 23 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 5 | 21 | 40 | 63 | 83 | 105 | 136 | 150 | 162 | 168 | 171 | 175 | 177 | 178 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 179 | 17 | 40 | 63 | 87 | 107 | 129 | 160 | 174 | 186 | 192 | 195 | 199 | 201 | 202 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203
G3.11 | I | 3: Gate 70 - Option Selection | 50 | 66 | 77 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 5 | 24 | 47 | 57 | 85 | 121 | 153 | 187 | 201 | 215 | 219 | 222 | 226 | 229 | 231 | 231 | 232 | 232 | 232 | 232 | 232 | 232 | 232 | 233 | 55 | 90 | 124 | 137 | 165 | 201 | 233 | 267 | 281 | 295 | 299 | 302 | 306 | 309 | 311 | 311 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 313
G3.12 | I | 3: Gate 80 - Project Approval | 61 | 93 | 110 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 1 | 3 | 9 | 12 | 36 | 70 | 103 | 127 | 144 | 160 | 181 | 207 | 229 | 242 | 253 | 258 | 262 | 262 | 264 | 266 | 266 | 267 | 267 | 268 | 62 | 96 | 119 | 140 | 164 | 198 | 231 | 255 | 272 | 288 | 309 | 335 | 357 | 370 | 381 | 386 | 390 | 390 | 392 | 394 | 394 | 395 | 395 | 396
G3.13 | I |  |  | Gate 90 - Delivery Approval | 4 | 17 | 27 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 1025 | 2191 | 3637 | 5104 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 5105 | 0 | 0 | 0 | 0 | 27 | 59 | 91 | 120 | 138 | 151 | 167 | 178 | 185 | 223 | 243 | 255 | 262 | 265 | 267 | 268 | 272 | 274 | 274 | 275 | 1029 | 2208 | 3664 | 5148 | 5176 | 5208 | 5240 | 5269 | 5287 | 5300 | 5316 | 5327 | 5334 | 5372 | 5392 | 5404 | 5411 | 5414 | 5416 | 5417 | 5421 | 5423 | 5423 | 5424
G3.14 | I |  |  | SOS - Start on Site | 4 | 13 | 26 | 40 | 45 | 50 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 1024 | 2129 | 3585 | 5098 | 5176 | 5287 | 5346 | 5356 | 5390 | 5392 | 5392 | 5393 | 5394 | 5395 | 5395 | 5395 | 5395 | 5396 | 5396 | 5396 | 5396 | 5396 | 5396 | 5397 | 0 | 0 | 0 | 0 | 13 | 35 | 57 | 97 | 122 | 139 | 148 | 169 | 178 | 190 | 221 | 242 | 253 | 261 | 265 | 267 | 268 | 272 | 274 | 275 | 1028 | 2142 | 3611 | 5138 | 5234 | 5372 | 5454 | 5504 | 5563 | 5582 | 5591 | 5613 | 5623 | 5636 | 5667 | 5688 | 5699 | 5708 | 5712 | 5714 | 5715 | 5719 | 5721 | 5723
G3.15 | I |  |  | G100 - Project Acceptance | 25 | 56 | 77 | 103 | 125 | 150 | 160 | 181 | 197 | 206 | 209 | 212 | 213 | 215 | 215 | 215 | 215 | 215 | 215 | 215 | 215 | 215 | 215 | 215 | 627 | 1540 | 2684 | 3796 | 5641 | 5797 | 6795 | 6926 | 7075 | 7111 | 7147 | 7157 | 7163 | 7177 | 7178 | 7183 | 7184 | 7186 | 7186 | 7187 | 7187 | 7187 | 7188 | 7213 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 20 | 40 | 56 | 79 | 104 | 122 | 134 | 143 | 153 | 157 | 177 | 194 | 208 | 223 | 235 | 245 | 652 | 1596 | 2761 | 3899 | 5766 | 5947 | 6957 | 7112 | 7292 | 7357 | 7412 | 7448 | 7480 | 7514 | 7527 | 7541 | 7552 | 7558 | 7578 | 7596 | 7610 | 7625 | 7638 | 7673
G3.16 | I |  |  | G110 - Financial Closure | 3 | 11 | 39 | 94 | 121 | 142 | 171 | 187 | 200 | 217 | 230 | 242 | 246 | 247 | 250 | 251 | 251 | 251 | 251 | 251 | 251 | 251 | 251 | 251 | 606 | 1423 | 2549 | 3637 | 5454 | 5559 | 6595 | 6728 | 6887 | 7027 | 7117 | 7181 | 7213 | 7236 | 7260 | 7261 | 7266 | 7267 | 7270 | 7270 | 7271 | 7271 | 7271 | 7294 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 5 | 13 | 31 | 49 | 64 | 83 | 101 | 121 | 137 | 148 | 155 | 167 | 191 | 204 | 213 | 231 | 609 | 1434 | 2588 | 3731 | 5575 | 5701 | 6767 | 6917 | 7092 | 7257 | 7378 | 7472 | 7523 | 7566 | 7611 | 7633 | 7654 | 7666 | 7676 | 7688 | 7713 | 7726 | 7735 | 7776
G3.17 | I |  |  | Needs from Gate 30 onwards put on hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.18 | I |  |  | Needs from Gate 30 onwards that do not require an intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Asset Maintenance |  | 4: Confirmed on Committed List | Non Named (Programmes and Projects within programmes | [23 empty] | Pre Committed List Named | [23 empty] | Confirmed in Committed List + Pre Committed Named + Non Named
|  | 4: 2021-22; 8: 2022-23; 12: 2023-24; 16: 2024-25; 20: 2025-26; 24: 2026-27 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
G3.19 | I | 2: Baseline; 3: Gate 30 - Project Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.20 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.21 | I | 3: Gate 70 - Option Selection | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G3.22 | I | 3: Gate 80 - Project Approval | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G3.23 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.24 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.25 | I |  |  | G100 - Project Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.26 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.27 | I | 2: Forecast Actual; 3: Gate 30 - Project Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.28 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.29 | I | 3: Gate 70 - Option Selection | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G3.30 | I | 3: Gate 80 - Project Approval | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G3.31 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.32 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.33 | I |  |  | G100 - Project Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.34 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.35 | I |  |  | Needs from Gate 30 onwards put on hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.36 | I |  |  | Needs from Gate 30 onwards that do not require an intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Supporting Sustainable Economic Growth |  | 4: Confirmed on Committed List | Non Named (Programmes and Projects within programmes | [23 empty] | Pre Committed List Named | [23 empty] | Confirmed in Committed List + Pre Committed Named + Non Named
|  | 4: 2021-22; 8: 2022-23; 12: 2023-24; 16: 2024-25; 20: 2025-26; 24: 2026-27 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
G3.37 | I | 2: Baseline; 3: Gate 30 - Project Creation | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 6 | 14 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 3 | 11 | 19 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23
G3.38 | I | 3: Gate 50 - Options Confirmed | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 3 | 13 | 20 | 24 | 26 | 35 | 44 | 49 | 50 | 53 | 59 | 62 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 0 | 5 | 15 | 22 | 26 | 28 | 37 | 46 | 51 | 52 | 55 | 61 | 64 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66
G3.39 | I | 3: Gate 70 - Option Selection | 3 | 11 | 13 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 2 | 2 | 13 | 14 | 23 | 30 | 37 | 40 | 46 | 56 | 58 | 64 | 65 | 70 | 73 | 74 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 5 | 13 | 26 | 29 | 38 | 45 | 52 | 55 | 61 | 71 | 73 | 79 | 80 | 85 | 88 | 89 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
G3.40 | I | 3: Gate 80 - Project Approval | 5 | 14 | 24 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 1 | 1 | 1 | 4 | 8 | 16 | 30 | 37 | 43 | 48 | 52 | 54 | 61 | 73 | 78 | 82 | 84 | 86 | 89 | 91 | 92 | 92 | 92 | 92 | 6 | 15 | 25 | 32 | 36 | 44 | 58 | 65 | 71 | 76 | 80 | 82 | 89 | 101 | 106 | 110 | 112 | 114 | 117 | 119 | 120 | 120 | 120 | 120
G3.41 | I |  |  | Gate 90 - Delivery Approval | 0 | 2 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 6 | 19 | 27 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 0 | 0 | 0 | 0 | 5 | 14 | 25 | 32 | 42 | 47 | 49 | 52 | 55 | 61 | 64 | 67 | 78 | 85 | 87 | 90 | 92 | 96 | 99 | 99 | 6 | 21 | 30 | 38 | 43 | 52 | 63 | 70 | 80 | 85 | 87 | 90 | 93 | 99 | 102 | 105 | 116 | 123 | 125 | 128 | 130 | 134 | 137 | 137
G3.42 | I |  |  | SOS - Start on Site | 2 | 4 | 5 | 5 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 17 | 20 | 29 | 35 | 36 | 37 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 21 | 25 | 34 | 41 | 42 | 43 | 44 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
G3.43 | I |  |  | G100 - Project Acceptance | 4 | 8 | 12 | 21 | 24 | 28 | 28 | 30 | 32 | 34 | 34 | 35 | 36 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 9 | 11 | 16 | 22 | 29 | 36 | 44 | 47 | 52 | 55 | 56 | 56 | 56 | 56 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 58 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 19 | 28 | 43 | 53 | 64 | 72 | 77 | 84 | 89 | 90 | 91 | 92 | 94 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 96 | 97
G3.44 | I |  |  | G110 - Financial Closure | 0 | 0 | 2 | 6 | 8 | 12 | 19 | 23 | 27 | 28 | 30 | 32 | 35 | 36 | 37 | 38 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 8 | 12 | 16 | 20 | 27 | 30 | 35 | 45 | 51 | 54 | 56 | 60 | 60 | 61 | 62 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 64 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 12 | 18 | 26 | 35 | 42 | 54 | 68 | 78 | 82 | 86 | 92 | 95 | 97 | 99 | 101 | 103 | 103 | 103 | 103 | 103 | 103 | 104 | 105
G3.45 | I | 2: Forecast Actual; 3: Gate 30 - Project Creation | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 6 | 14 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 3 | 11 | 19 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23
G3.46 | I | 3: Gate 50 - Options Confirmed | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 3 | 13 | 20 | 24 | 26 | 35 | 44 | 49 | 50 | 53 | 59 | 62 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 0 | 5 | 15 | 22 | 26 | 28 | 37 | 46 | 51 | 52 | 55 | 61 | 64 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66
G3.47 | I | 3: Gate 70 - Option Selection | 3 | 11 | 13 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 2 | 2 | 13 | 14 | 23 | 30 | 37 | 40 | 46 | 56 | 58 | 64 | 65 | 70 | 73 | 74 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 5 | 13 | 26 | 29 | 38 | 45 | 52 | 55 | 61 | 71 | 73 | 79 | 80 | 85 | 88 | 89 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
G3.48 | I | 3: Gate 80 - Project Approval | 5 | 14 | 24 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 1 | 1 | 1 | 4 | 8 | 16 | 30 | 37 | 43 | 48 | 52 | 54 | 61 | 73 | 78 | 82 | 84 | 86 | 89 | 91 | 92 | 92 | 92 | 92 | 6 | 15 | 25 | 32 | 36 | 44 | 58 | 65 | 71 | 76 | 80 | 82 | 89 | 101 | 106 | 110 | 112 | 114 | 117 | 119 | 120 | 120 | 120 | 120
G3.49 | I |  |  | Gate 90 - Delivery Approval | 0 | 2 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 6 | 19 | 27 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 0 | 0 | 0 | 0 | 5 | 14 | 25 | 32 | 42 | 47 | 49 | 52 | 55 | 61 | 64 | 67 | 78 | 85 | 87 | 90 | 92 | 96 | 99 | 99 | 6 | 21 | 30 | 38 | 43 | 52 | 63 | 70 | 80 | 85 | 87 | 90 | 93 | 99 | 102 | 105 | 116 | 123 | 125 | 128 | 130 | 134 | 137 | 137
G3.50 | I |  |  | SOS - Start on Site | 2 | 3 | 5 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 18 | 21 | 30 | 35 | 36 | 37 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 0 | 0 | 0 | 0 | 3 | 6 | 13 | 25 | 32 | 36 | 47 | 49 | 52 | 55 | 60 | 64 | 66 | 78 | 85 | 85 | 90 | 92 | 96 | 98 | 6 | 21 | 26 | 36 | 45 | 49 | 57 | 70 | 77 | 81 | 92 | 94 | 97 | 100 | 105 | 109 | 111 | 123 | 130 | 130 | 135 | 137 | 141 | 143
G3.51 | I |  |  | G100 - Project Acceptance | 1 | 3 | 6 | 13 | 17 | 23 | 24 | 24 | 29 | 29 | 31 | 32 | 35 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 3 | 7 | 10 | 14 | 25 | 28 | 41 | 45 | 50 | 54 | 56 | 56 | 56 | 56 | 57 | 57 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8 | 13 | 15 | 26 | 29 | 37 | 39 | 42 | 45 | 53 | 56 | 61 | 68 | 77 | 81 | 4 | 10 | 16 | 27 | 42 | 51 | 65 | 70 | 80 | 91 | 100 | 103 | 117 | 121 | 130 | 132 | 136 | 139 | 147 | 150 | 155 | 162 | 171 | 176
G3.52 | I |  |  | G110 - Financial Closure | 0 | 1 | 3 | 10 | 10 | 16 | 22 | 26 | 27 | 29 | 32 | 33 | 36 | 38 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 2 | 7 | 10 | 15 | 24 | 28 | 33 | 44 | 50 | 53 | 57 | 61 | 61 | 61 | 62 | 62 | 62 | 63 | 63 | 63 | 63 | 63 | 63 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 9 | 13 | 20 | 27 | 32 | 36 | 38 | 44 | 46 | 55 | 59 | 63 | 73 | 2 | 8 | 13 | 25 | 34 | 44 | 55 | 70 | 78 | 83 | 93 | 103 | 110 | 119 | 129 | 134 | 138 | 141 | 147 | 149 | 158 | 162 | 166 | 178
G3.53 | I |  |  | Needs from Gate 30 onwards put on hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.54 | I |  |  | Needs from Gate 30 onwards that do not require an intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Circular Economy |  | 4: Confirmed on Committed List | Non Named (Programmes and Projects within programmes | [23 empty] | Pre Committed List Named | [23 empty] | Confirmed in Committed List + Pre Committed Named + Non Named
|  | 4: 2021-22; 8: 2022-23; 12: 2023-24; 16: 2024-25; 20: 2025-26; 24: 2026-27 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
G3.55 | I | 2: Baseline; 3: Gate 30 - Project Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.56 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.57 | I | 3: Gate 70 - Option Selection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.58 | I | 3: Gate 80 - Project Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.59 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.60 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.61 | I |  |  | G100 - Project Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.62 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.63 | I | 2: Forecast Actual; 3: Gate 30 - Project Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.64 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.65 | I | 3: Gate 70 - Option Selection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.66 | I | 3: Gate 80 - Project Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.67 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.68 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.69 | I |  |  | G100 - Project Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.70 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.71 | I |  |  | Needs from Gate 30 onwards put on hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.72 | I |  |  | Needs from Gate 30 onwards that do not require an intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drinking Water |  | 4: Confirmed on Committed List | Non Named (Programmes and Projects within programmes | [23 empty] | Pre Committed List Named | [23 empty] | Confirmed in Committed List + Pre Committed Named + Non Named
|  | 4: 2021-22; 8: 2022-23; 12: 2023-24; 16: 2024-25; 20: 2025-26; 24: 2026-27 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
G3.73 | I | 2: Baseline; 3: Gate 30 - Project Creation | 6 | 7 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 3 | 5 | 16 | 29 | 30 | 31 | 31 | 31 | 31 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 9 | 12 | 25 | 39 | 40 | 41 | 41 | 41 | 41 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
G3.74 | I | 3: Gate 50 - Options Confirmed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 8 | 15 | 20 | 36 | 42 | 46 | 50 | 52 | 52 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 2 | 2 | 7 | 9 | 16 | 21 | 37 | 43 | 47 | 51 | 53 | 53 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
G3.75 | I | 3: Gate 70 - Option Selection | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 9 | 13 | 23 | 31 | 40 | 44 | 48 | 52 | 53 | 54 | 54 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 2 | 3 | 3 | 4 | 10 | 14 | 24 | 32 | 41 | 45 | 49 | 53 | 54 | 55 | 55 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56
G3.76 | I | 3: Gate 80 - Project Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 3 | 3 | 6 | 8 | 10 | 12 | 15 | 28 | 38 | 44 | 47 | 49 | 55 | 55 | 56 | 56 | 57 | 57 | 57 | 57 | 1 | 1 | 1 | 1 | 4 | 4 | 7 | 9 | 11 | 13 | 16 | 29 | 39 | 45 | 48 | 50 | 56 | 56 | 57 | 57 | 58 | 58 | 58 | 58
G3.77 | I |  |  | Gate 90 - Delivery Approval | 2 | 2 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 8 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 1 | 3 | 4 | 5 | 9 | 10 | 10 | 12 | 13 | 26 | 34 | 38 | 40 | 41 | 47 | 47 | 48 | 48 | 48 | 48 | 8 | 10 | 13 | 17 | 18 | 20 | 21 | 22 | 26 | 27 | 27 | 29 | 30 | 43 | 51 | 55 | 57 | 58 | 64 | 64 | 65 | 65 | 65 | 65
G3.78 | I |  |  | SOS - Start on Site | 2 | 3 | 3 | 4 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 1 | 8 | 14 | 16 | 23 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 11 | 17 | 20 | 29 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
G3.79 | I |  |  | G100 - Project Acceptance | 5 | 7 | 9 | 11 | 14 | 15 | 16 | 20 | 23 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 8 | 10 | 18 | 22 | 25 | 27 | 35 | 36 | 37 | 39 | 39 | 39 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 17 | 27 | 33 | 39 | 42 | 51 | 56 | 60 | 63 | 63 | 63 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 67
G3.80 | I |  |  | G110 - Financial Closure | 1 | 1 | 4 | 9 | 12 | 14 | 16 | 17 | 18 | 21 | 26 | 28 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 3 | 8 | 15 | 18 | 22 | 24 | 29 | 30 | 36 | 38 | 40 | 40 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9 | 19 | 27 | 34 | 38 | 45 | 47 | 54 | 59 | 66 | 68 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 73
G3.81 | I | 2: Forecast Actual; 3: Gate 30 - Project Creation | 6 | 7 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 3 | 5 | 16 | 29 | 30 | 31 | 31 | 31 | 31 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 9 | 12 | 25 | 39 | 40 | 41 | 41 | 41 | 41 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
G3.82 | I | 3: Gate 50 - Options Confirmed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 8 | 15 | 20 | 36 | 42 | 46 | 50 | 52 | 52 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 2 | 2 | 7 | 9 | 16 | 21 | 37 | 43 | 47 | 51 | 53 | 53 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
G3.83 | I | 3: Gate 70 - Option Selection | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 9 | 13 | 23 | 31 | 40 | 44 | 48 | 52 | 53 | 54 | 54 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 2 | 3 | 3 | 4 | 10 | 14 | 24 | 32 | 41 | 45 | 49 | 53 | 54 | 55 | 55 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56
G3.84 | I | 3: Gate 80 - Project Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 3 | 3 | 6 | 8 | 10 | 12 | 15 | 28 | 38 | 44 | 47 | 49 | 55 | 55 | 56 | 56 | 57 | 57 | 57 | 57 | 1 | 1 | 1 | 1 | 4 | 4 | 7 | 9 | 11 | 13 | 16 | 29 | 39 | 45 | 48 | 50 | 56 | 56 | 57 | 57 | 58 | 58 | 58 | 58
G3.85 | I |  |  | Gate 90 - Delivery Approval | 2 | 2 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 8 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 1 | 3 | 4 | 5 | 9 | 10 | 10 | 12 | 13 | 26 | 34 | 38 | 40 | 41 | 47 | 47 | 48 | 48 | 48 | 48 | 8 | 10 | 13 | 17 | 18 | 20 | 21 | 22 | 26 | 27 | 27 | 29 | 30 | 43 | 51 | 55 | 57 | 58 | 64 | 64 | 65 | 65 | 65 | 65
G3.86 | I |  |  | SOS - Start on Site | 2 | 4 | 4 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 1 | 7 | 14 | 16 | 19 | 24 | 24 | 24 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 1 | 3 | 3 | 4 | 4 | 7 | 9 | 10 | 12 | 14 | 26 | 33 | 38 | 39 | 40 | 45 | 47 | 48 | 48 | 48 | 3 | 11 | 18 | 22 | 26 | 34 | 34 | 35 | 36 | 39 | 41 | 42 | 44 | 46 | 58 | 65 | 70 | 71 | 72 | 77 | 79 | 80 | 80 | 80
G3.87 | I |  |  | G100 - Project Acceptance | 0 | 2 | 4 | 6 | 8 | 10 | 14 | 16 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 4 | 6 | 11 | 13 | 17 | 20 | 27 | 30 | 34 | 36 | 38 | 38 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 4 | 4 | 5 | 5 | 6 | 8 | 12 | 15 | 19 | 27 | 30 | 4 | 8 | 15 | 19 | 25 | 30 | 42 | 47 | 55 | 57 | 60 | 60 | 62 | 63 | 63 | 64 | 64 | 65 | 67 | 71 | 74 | 78 | 86 | 93
G3.88 | I |  |  | G110 - Financial Closure | 0 | 4 | 7 | 11 | 14 | 14 | 17 | 19 | 22 | 25 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 1 | 3 | 10 | 12 | 13 | 15 | 19 | 22 | 30 | 31 | 37 | 38 | 39 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 4 | 5 | 5 | 7 | 10 | 14 | 16 | 23 | 1 | 7 | 17 | 23 | 27 | 29 | 36 | 41 | 53 | 57 | 65 | 67 | 69 | 70 | 70 | 71 | 72 | 73 | 73 | 75 | 78 | 82 | 84 | 95
G3.89 | I |  |  | Needs from Gate 30 onwards put on hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.90 | I |  |  | Needs from Gate 30 onwards that do not require an intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Environment |  | 4: Confirmed on Committed List | Non Named (Programmes and Projects within programmes | [23 empty] | Pre Committed List Named | [23 empty] | Confirmed in Committed List + Pre Committed Named + Non Named
|  | 4: 2021-22; 8: 2022-23; 12: 2023-24; 16: 2024-25; 20: 2025-26; 24: 2026-27 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
G3.91 | I | 2: Baseline; 3: Gate 30 - Project Creation | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G3.92 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 5 | 7 | 16 | 17 | 17 | 17 | 17 | 17 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 5 | 7 | 16 | 17 | 17 | 17 | 17 | 17 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G3.93 | I | 3: Gate 70 - Option Selection | 3 | 4 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 5 | 10 | 16 | 17 | 17 | 17 | 17 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 3 | 4 | 5 | 7 | 7 | 8 | 8 | 9 | 11 | 12 | 17 | 23 | 24 | 24 | 24 | 24 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27
G3.94 | I | 3: Gate 80 - Project Approval | 3 | 4 | 10 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 5 | 7 | 12 | 12 | 15 | 18 | 18 | 18 | 18 | 18 | 21 | 21 | 21 | 4 | 5 | 11 | 15 | 15 | 15 | 16 | 16 | 17 | 17 | 17 | 19 | 21 | 26 | 26 | 29 | 32 | 32 | 32 | 32 | 32 | 35 | 35 | 35
G3.95 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 14 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 3 | 4 | 4 | 6 | 8 | 12 | 12 | 13 | 13 | 17 | 18 | 18 | 19 | 19 | 19 | 20 | 4 | 6 | 14 | 20 | 20 | 22 | 22 | 22 | 23 | 24 | 24 | 26 | 28 | 32 | 32 | 33 | 33 | 37 | 38 | 38 | 39 | 39 | 39 | 40
G3.96 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 15 | 24 | 27 | 29 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 15 | 24 | 27 | 30 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
G3.97 | I |  |  | G100 - Project Acceptance | 0 | 7 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 13 | 18 | 25 | 27 | 36 | 37 | 38 | 40 | 40 | 42 | 42 | 42 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 20 | 26 | 33 | 36 | 45 | 46 | 47 | 49 | 49 | 52 | 52 | 52 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53
G3.98 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 1 | 8 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 8 | 8 | 10 | 13 | 24 | 25 | 30 | 33 | 39 | 41 | 42 | 42 | 44 | 44 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 10 | 14 | 32 | 34 | 39 | 43 | 49 | 51 | 52 | 52 | 54 | 55 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56
G3.99 | I | 2: Forecast Actual; 3: Gate 30 - Project Creation | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G3.100 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 5 | 7 | 16 | 17 | 17 | 17 | 17 | 17 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 5 | 7 | 16 | 17 | 17 | 17 | 17 | 17 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G3.101 | I | 3: Gate 70 - Option Selection | 3 | 4 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 5 | 10 | 16 | 17 | 17 | 17 | 17 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 3 | 4 | 5 | 7 | 7 | 8 | 8 | 9 | 11 | 12 | 17 | 23 | 24 | 24 | 24 | 24 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27
G3.102 | I | 3: Gate 80 - Project Approval | 3 | 4 | 10 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 5 | 7 | 12 | 12 | 15 | 18 | 18 | 18 | 18 | 18 | 21 | 21 | 21 | 4 | 5 | 11 | 15 | 15 | 15 | 16 | 16 | 17 | 17 | 17 | 19 | 21 | 26 | 26 | 29 | 32 | 32 | 32 | 32 | 32 | 35 | 35 | 35
G3.103 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 14 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 3 | 4 | 4 | 6 | 8 | 12 | 12 | 13 | 13 | 17 | 18 | 18 | 19 | 19 | 19 | 20 | 4 | 6 | 14 | 20 | 20 | 22 | 22 | 22 | 23 | 24 | 24 | 26 | 28 | 32 | 32 | 33 | 33 | 37 | 38 | 38 | 39 | 39 | 39 | 40
G3.104 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 9 | 12 | 22 | 25 | 29 | 31 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 4 | 5 | 6 | 11 | 12 | 12 | 13 | 13 | 17 | 18 | 18 | 19 | 19 | 19 | 9 | 12 | 22 | 26 | 30 | 32 | 35 | 35 | 36 | 36 | 37 | 38 | 39 | 44 | 45 | 45 | 46 | 46 | 50 | 51 | 51 | 52 | 52 | 52
G3.105 | I |  |  | G100 - Project Acceptance | 0 | 2 | 2 | 4 | 6 | 6 | 7 | 8 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 10 | 14 | 18 | 23 | 31 | 38 | 39 | 41 | 41 | 43 | 43 | 43 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 8 | 12 | 12 | 15 | 16 | 7 | 12 | 16 | 22 | 29 | 37 | 45 | 47 | 51 | 52 | 54 | 55 | 56 | 57 | 57 | 58 | 58 | 58 | 59 | 62 | 66 | 66 | 69 | 70
G3.106 | I |  |  | G110 - Financial Closure | 0 | 0 | 1 | 4 | 5 | 7 | 7 | 8 | 9 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 2 | 3 | 6 | 9 | 14 | 19 | 25 | 33 | 36 | 42 | 43 | 43 | 45 | 45 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 7 | 12 | 12 | 15 | 2 | 3 | 7 | 13 | 19 | 26 | 32 | 41 | 46 | 53 | 55 | 55 | 58 | 58 | 60 | 60 | 60 | 61 | 61 | 61 | 64 | 69 | 69 | 72
G3.107 | I |  |  | Needs from Gate 30 onwards put on hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.108 | I |  |  | Needs from Gate 30 onwards that do not require an intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooding and Surface Water Management |  | 4: Confirmed on Committed List | Non Named (Programmes and Projects within programmes | [23 empty] | Pre Committed List Named | [23 empty] | Confirmed in Committed List + Pre Committed Named + Non Named
|  | 4: 2021-22; 8: 2022-23; 12: 2023-24; 16: 2024-25; 20: 2025-26; 24: 2026-27 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
G3.109 | I | 2: Baseline; 3: Gate 30 - Project Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.110 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.111 | I | 3: Gate 70 - Option Selection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.112 | I | 3: Gate 80 - Project Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.113 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.114 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.115 | I |  |  | G100 - Project Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.116 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.117 | I | 2: Forecast Actual; 3: Gate 30 - Project Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.118 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.119 | I | 3: Gate 70 - Option Selection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.120 | I | 3: Gate 80 - Project Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.121 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.122 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.123 | I |  |  | G100 - Project Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.124 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.125 | I |  |  | Needs from Gate 30 onwards put on hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.126 | I |  |  | Needs from Gate 30 onwards that do not require an intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Security & Resilience |  | 4: Confirmed on Committed List | Non Named (Programmes and Projects within programmes | [23 empty] | Pre Committed List Named | [23 empty] | Confirmed in Committed List + Pre Committed Named + Non Named
|  | 4: 2021-22; 8: 2022-23; 12: 2023-24; 16: 2024-25; 20: 2025-26; 24: 2026-27 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
G3.127 | I | 2: Baseline; 3: Gate 30 - Project Creation | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 2 | 3 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 2 | 7 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
G3.128 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.129 | I | 3: Gate 70 - Option Selection | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 3 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G3.130 | I | 3: Gate 80 - Project Approval | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 4 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 2 | 3 | 6 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
G3.131 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 5 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 1 | 3 | 4 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 5 | 5 | 9 | 10 | 12 | 13 | 14 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G3.132 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 6 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 6 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
G3.133 | I |  |  | G100 - Project Acceptance | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 9 | 12 | 12 | 12 | 13 | 14 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 14 | 17 | 17 | 17 | 18 | 19 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21
G3.134 | I |  |  | G110 - Financial Closure | 0 | 0 | 1 | 1 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 9 | 12 | 12 | 12 | 12 | 12 | 13 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 9 | 13 | 13 | 18 | 18 | 18 | 19 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
G3.135 | I | 2: Forecast Actual; 3: Gate 30 - Project Creation | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 2 | 3 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 2 | 7 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
G3.136 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.137 | I | 3: Gate 70 - Option Selection | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 3 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G3.138 | I | 3: Gate 80 - Project Approval | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 4 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 2 | 3 | 6 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
G3.139 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 5 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 1 | 3 | 4 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 5 | 5 | 9 | 10 | 12 | 13 | 14 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G3.140 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 6 | 8 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 1 | 3 | 4 | 4 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 5 | 6 | 8 | 10 | 12 | 14 | 14 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G3.141 | I |  |  | G100 - Project Acceptance | 0 | 0 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 7 | 11 | 12 | 12 | 13 | 13 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 4 | 5 | 5 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 2 | 7 | 14 | 16 | 17 | 18 | 18 | 22 | 23 | 24 | 25 | 26 | 26 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 29
G3.142 | I |  |  | G110 - Financial Closure | 1 | 1 | 1 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 7 | 10 | 12 | 12 | 12 | 12 | 12 | 14 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 4 | 5 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 3 | 8 | 11 | 17 | 18 | 18 | 18 | 19 | 22 | 25 | 25 | 26 | 27 | 27 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29
G3.143 | I |  |  | Needs from Gate 30 onwards put on hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.144 | I |  |  | Needs from Gate 30 onwards that do not require an intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Climate Change, Adaptation and Mitigation |  | 4: Confirmed on Committed List | Non Named (Programmes and Projects within programmes | [23 empty] | Pre Committed List Named | [23 empty] | Confirmed in Committed List + Pre Committed Named + Non Named
|  | 4: 2021-22; 8: 2022-23; 12: 2023-24; 16: 2024-25; 20: 2025-26; 24: 2026-27 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
G3.145 | I | 2: Baseline; 3: Gate 30 - Project Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.146 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.147 | I | 3: Gate 70 - Option Selection | 2 | 4 | 11 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 0 | 3 | 4 | 4 | 4 | 4 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 2 | 7 | 15 | 17 | 17 | 17 | 18 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G3.148 | I | 3: Gate 80 - Project Approval | 2 | 4 | 5 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 4 | 4 | 5 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 2 | 4 | 5 | 14 | 14 | 14 | 14 | 14 | 16 | 16 | 16 | 16 | 17 | 17 | 18 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G3.149 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 7 | 9 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 6 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 7 | 9 | 17 | 17 | 18 | 19 | 19 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 23 | 24 | 25 | 25 | 25 | 25 | 25 | 25 | 25
G3.150 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 4 | 13 | 14 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 4 | 13 | 14 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G3.151 | I |  |  | G100 - Project Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 6 | 7 | 9 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 6 | 7 | 9 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 23
G3.152 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 4 | 6 | 7 | 10 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 4 | 6 | 7 | 10 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G3.153 | I | 2: Forecast Actual; 3: Gate 30 - Project Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.154 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.155 | I | 3: Gate 70 - Option Selection | 2 | 4 | 11 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 0 | 3 | 4 | 4 | 4 | 4 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 2 | 7 | 15 | 17 | 17 | 17 | 18 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G3.156 | I | 3: Gate 80 - Project Approval | 2 | 4 | 5 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 4 | 4 | 5 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 2 | 4 | 5 | 14 | 14 | 14 | 14 | 14 | 16 | 16 | 16 | 16 | 17 | 17 | 18 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G3.157 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 7 | 9 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 6 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 7 | 9 | 17 | 17 | 18 | 19 | 19 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 23 | 24 | 25 | 25 | 25 | 25 | 25 | 25 | 25
G3.158 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 6 | 15 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 5 | 6 | 6 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 3 | 6 | 6 | 15 | 16 | 16 | 16 | 19 | 19 | 21 | 21 | 21 | 21 | 21 | 22 | 23 | 23 | 24 | 25 | 25 | 25 | 25 | 25 | 25
G3.159 | I |  |  | G100 - Project Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 6 | 7 | 9 | 9 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 4 | 4 | 4 | 4 | 4 | 5 | 0 | 0 | 1 | 1 | 6 | 7 | 9 | 9 | 10 | 11 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 15 | 16 | 16 | 16 | 16 | 16 | 26
G3.160 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 8 | 9 | 9 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 1 | 4 | 8 | 9 | 9 | 10 | 10 | 11 | 12 | 13 | 13 | 13 | 13 | 14 | 14 | 16 | 16 | 16 | 16 | 16
G3.161 | I |  |  | Needs from Gate 30 onwards put on hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.162 | I |  |  | Needs from Gate 30 onwards that do not require an intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Private Finance Initiative Funded Projects |  | 4: Confirmed on Committed List | Non Named (Programmes and Projects within programmes | [23 empty] | Pre Committed List Named | [23 empty] | Confirmed in Committed List + Pre Committed Named + Non Named
|  | 4: 2021-22; 8: 2022-23; 12: 2023-24; 16: 2024-25; 20: 2025-26; 24: 2026-27 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
G3.163 | I | 2: Baseline; 3: Gate 30 - Project Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.164 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.165 | I | 3: Gate 70 - Option Selection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.166 | I | 3: Gate 80 - Project Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.167 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.168 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.169 | I |  |  | G100 - Project Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.170 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.171 | I | 2: Forecast Actual; 3: Gate 30 - Project Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.172 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.173 | I | 3: Gate 70 - Option Selection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.174 | I | 3: Gate 80 - Project Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.175 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.176 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.177 | I |  |  | G100 - Project Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.178 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.179 | I |  |  | Needs from Gate 30 onwards put on hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.180 | I |  |  | Needs from Gate 30 onwards that do not require an intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SR10 Completion Projects |  | 4: Confirmed on Committed List
[5 empty] | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
G3.181 | I |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.182 | I |  |  | MS2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.183 | I |  |  | MS3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.184 | I |  |  | MS4 | 14 | 6 | 4 | 4 | 4 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.185 | I |  |  | MS5 | 17 | 16 | 7 | 5 | 5 | 5 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.186 | I |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.187 | I |  |  | MS2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.188 | I |  |  | MS3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.189 | I |  |  | MS4 | 15 | 10 | 8 | 6 | 6 | 4 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.190 | I |  |  | MS5 | 19 | 16 | 16 | 14 | 10 | 7 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
SR15 Completion Projects |  | 4: Confirmed on Committed List
[5 empty] | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
G3.191 | I |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.192 | I |  |  | MS2 | 10 | 7 | 6 | 4 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.193 | I |  |  | MS3 | 18 | 12 | 10 | 8 | 6 | 4 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.194 | I |  |  | MS4 | 90 | 60 | 44 | 33 | 25 | 18 | 15 | 10 | 6 | 4 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.195 | I |  |  | MS5 | 107 | 96 | 73 | 60 | 47 | 27 | 21 | 16 | 11 | 6 | 4 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.196 | I |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.197 | I |  |  | MS2 | 16 | 16 | 13 | 9 | 6 | 5 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.198 | I |  |  | MS3 | 19 | 17 | 16 | 11 | 9 | 6 | 5 | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.199 | I |  |  | MS4 | 94 | 73 | 67 | 55 | 45 | 36 | 28 | 21 | 15 | 11 | 9 | 6 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
G3.200 | I |  |  | MS5 | 120 | 113 | 104 | 78 | 66 | 46 | 37 | 30 | 26 | 18 | 14 | 11 | 7 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
SR21 Total |  | 4: Confirmed on Committed List | Non Named (Programmes and Projects within programmes | [23 empty] | Pre Committed List Named | [23 empty] | Confirmed in Committed List + Minimum expectation
|  | 4: 2021-22; 8: 2022-23; 12: 2023-24; 16: 2024-25; 20: 2025-26; 24: 2026-27 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
G3.201 | I |  | Baseline | Gate 30 - Project Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 302 | 407 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 20 | 66 | 113 | 167 | 177 | 186 | 186 | 186 | 195 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 163 | 368 | 520 | 626 | 636 | 645 | 645 | 645 | 654 | 655 | 655 | 655 | 655 | 655 | 655 | 655 | 655 | 655 | 655 | 655 | 655 | 655 | 655 | 655
G3.202 | I |  |  | Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 22 | 27 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 7 | 26 | 60 | 95 | 126 | 156 | 213 | 243 | 265 | 278 | 296 | 307 | 313 | 316 | 317 | 317 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 20 | 48 | 87 | 124 | 155 | 185 | 242 | 272 | 294 | 307 | 325 | 336 | 342 | 345 | 346 | 346 | 349 | 349 | 349 | 349 | 349 | 349 | 349 | 349
G3.203 | I |  |  | Gate 70 - Option Selection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 88 | 110 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 8 | 31 | 68 | 83 | 126 | 174 | 224 | 272 | 303 | 332 | 348 | 367 | 374 | 383 | 388 | 390 | 395 | 395 | 395 | 395 | 395 | 395 | 395 | 396 | 69 | 119 | 178 | 203 | 246 | 294 | 344 | 392 | 423 | 452 | 468 | 487 | 494 | 503 | 508 | 510 | 515 | 515 | 515 | 515 | 515 | 515 | 515 | 516
G3.204 | I |  |  | Gate 80 - Project Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 118 | 153 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 3 | 5 | 12 | 19 | 53 | 97 | 149 | 182 | 210 | 233 | 261 | 304 | 346 | 382 | 403 | 418 | 434 | 436 | 442 | 446 | 448 | 452 | 452 | 453 | 77 | 123 | 165 | 207 | 241 | 285 | 337 | 370 | 398 | 421 | 449 | 492 | 534 | 570 | 591 | 606 | 622 | 624 | 630 | 634 | 636 | 640 | 640 | 641
G3.205 | I |  |  | Gate 90 - Delivery Approval | 6 | 21 | 33 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 1051 | 2239 | 3705 | 5198 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 0 | 0 | 0 | 0 | 34 | 82 | 128 | 166 | 203 | 223 | 241 | 259 | 272 | 334 | 365 | 386 | 408 | 424 | 435 | 439 | 447 | 453 | 456 | 458 | 1057 | 2260 | 3738 | 5252 | 5287 | 5335 | 5381 | 5419 | 5456 | 5476 | 5494 | 5512 | 5525 | 5587 | 5618 | 5639 | 5661 | 5677 | 5688 | 5692 | 5700 | 5706 | 5709 | 5711
G3.206 | I |  |  | SOS - Start on Site | 16 | 28 | 44 | 53 | 65 | 71 | 73 | 73 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 1024 | 2181 | 3699 | 5245 | 5393 | 5507 | 5531 | 5543 | 5547 | 5550 | 5551 | 5552 | 5552 | 5554 | 5554 | 5554 | 5555 | 5555 | 5555 | 5555 | 5555 | 5555 | 5555 | 5556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1040 | 2209 | 3743 | 5298 | 5458 | 5578 | 5604 | 5616 | 5621 | 5624 | 5625 | 5626 | 5626 | 5628 | 5628 | 5628 | 5629 | 5629 | 5629 | 5629 | 5629 | 5629 | 5629 | 5630
G3.207 | I |  |  | G100 - Project Acceptance | 52 | 111 | 147 | 181 | 207 | 230 | 246 | 259 | 270 | 284 | 290 | 294 | 298 | 301 | 303 | 303 | 303 | 303 | 303 | 303 | 303 | 303 | 303 | 303 | 1578 | 2604 | 3817 | 5271 | 6746 | 6926 | 7080 | 7203 | 7295 | 7316 | 7327 | 7339 | 7343 | 7348 | 7350 | 7353 | 7353 | 7356 | 7356 | 7357 | 7357 | 7357 | 7359 | 7396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1630 | 2715 | 3964 | 5452 | 6953 | 7156 | 7326 | 7462 | 7565 | 7600 | 7617 | 7633 | 7641 | 7649 | 7653 | 7656 | 7656 | 7659 | 7659 | 7660 | 7660 | 7660 | 7662 | 7699
G3.208 | I |  |  | G110 - Financial Closure | 5 | 5 | 37 | 79 | 129 | 170 | 209 | 235 | 260 | 279 | 292 | 306 | 317 | 324 | 328 | 332 | 335 | 337 | 337 | 337 | 337 | 337 | 337 | 337 | 1501 | 2514 | 3721 | 5113 | 6587 | 6732 | 6917 | 7078 | 7229 | 7319 | 7378 | 7403 | 7426 | 7435 | 7440 | 7443 | 7446 | 7446 | 7449 | 7449 | 7450 | 7450 | 7452 | 7477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1506 | 2519 | 3758 | 5192 | 6716 | 6902 | 7126 | 7313 | 7489 | 7598 | 7670 | 7709 | 7743 | 7759 | 7768 | 7775 | 7781 | 7783 | 7786 | 7786 | 7787 | 7787 | 7789 | 7814
G3.209 | I |  | Forecast Actual | Gate 30 - Project Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 302 | 407 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 459 | 20 | 66 | 113 | 167 | 177 | 186 | 186 | 186 | 195 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 163 | 368 | 520 | 626 | 636 | 645 | 645 | 645 | 654 | 655 | 655 | 655 | 655 | 655 | 655 | 655 | 655 | 655 | 655 | 655 | 655 | 655 | 655 | 655
G3.210 | I |  |  | Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 22 | 27 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 7 | 26 | 60 | 95 | 126 | 156 | 213 | 243 | 265 | 278 | 296 | 307 | 313 | 316 | 317 | 317 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 20 | 48 | 87 | 124 | 155 | 185 | 242 | 272 | 294 | 307 | 325 | 336 | 342 | 345 | 346 | 346 | 349 | 349 | 349 | 349 | 349 | 349 | 349 | 349
G3.211 | I |  |  | Gate 70 - Option Selection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 88 | 110 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 8 | 31 | 68 | 83 | 126 | 174 | 224 | 272 | 303 | 332 | 348 | 367 | 374 | 383 | 388 | 390 | 395 | 395 | 395 | 395 | 395 | 395 | 395 | 396 | 69 | 119 | 178 | 203 | 246 | 294 | 344 | 392 | 423 | 452 | 468 | 487 | 494 | 503 | 508 | 510 | 515 | 515 | 515 | 515 | 515 | 515 | 515 | 516
G3.212 | I |  |  | Gate 80 - Project Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 118 | 153 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 3 | 5 | 12 | 19 | 53 | 97 | 149 | 182 | 210 | 233 | 261 | 304 | 346 | 382 | 403 | 418 | 434 | 436 | 442 | 446 | 448 | 452 | 452 | 453 | 77 | 123 | 165 | 207 | 241 | 285 | 337 | 370 | 398 | 421 | 449 | 492 | 534 | 570 | 591 | 606 | 622 | 624 | 630 | 634 | 636 | 640 | 640 | 641
G3.213 | I |  |  | Gate 90 - Delivery Approval | 6 | 21 | 33 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 1051 | 2239 | 3705 | 5198 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 5199 | 0 | 0 | 0 | 0 | 34 | 82 | 128 | 166 | 203 | 223 | 241 | 259 | 272 | 334 | 365 | 386 | 408 | 424 | 435 | 439 | 447 | 453 | 456 | 458 | 1057 | 2260 | 3738 | 5252 | 5287 | 5335 | 5381 | 5419 | 5456 | 5476 | 5494 | 5512 | 5525 | 5587 | 5618 | 5639 | 5661 | 5677 | 5688 | 5692 | 5700 | 5706 | 5709 | 5711
G3.214 | I |  |  | SOS - Start on Site | 8 | 20 | 35 | 53 | 59 | 65 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 1045 | 2180 | 3657 | 5195 | 5287 | 5406 | 5468 | 5480 | 5515 | 5517 | 5517 | 5518 | 5519 | 5520 | 5520 | 5520 | 5520 | 5521 | 5521 | 5521 | 5521 | 5521 | 5521 | 5522 | 0 | 0 | 0 | 0 | 18 | 47 | 79 | 134 | 170 | 196 | 219 | 244 | 259 | 281 | 331 | 364 | 383 | 406 | 423 | 431 | 439 | 447 | 453 | 456 | 1053 | 2200 | 3692 | 5248 | 5364 | 5518 | 5613 | 5680 | 5751 | 5779 | 5802 | 5828 | 5844 | 5867 | 5917 | 5950 | 5969 | 5993 | 6010 | 6018 | 6026 | 6034 | 6040 | 6044
G3.215 | I |  |  | G100 - Project Acceptance | 26 | 63 | 92 | 130 | 161 | 194 | 210 | 234 | 260 | 270 | 275 | 279 | 283 | 286 | 286 | 286 | 286 | 286 | 286 | 286 | 286 | 286 | 286 | 286 | 643 | 1570 | 2731 | 3854 | 5724 | 5896 | 6923 | 7064 | 7228 | 7272 | 7314 | 7324 | 7331 | 7346 | 7348 | 7353 | 7355 | 7358 | 7358 | 7359 | 7359 | 7359 | 7360 | 7399 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 9 | 25 | 53 | 77 | 104 | 143 | 166 | 187 | 200 | 213 | 222 | 254 | 281 | 307 | 333 | 365 | 385 | 669 | 1633 | 2823 | 3984 | 5885 | 6090 | 7136 | 7307 | 7513 | 7595 | 7666 | 7707 | 7757 | 7798 | 7821 | 7839 | 7854 | 7866 | 7898 | 7926 | 7952 | 7978 | 8011 | 8070
G3.216 | I |  |  | G110 - Financial Closure | 4 | 17 | 51 | 124 | 156 | 185 | 223 | 246 | 264 | 287 | 306 | 320 | 327 | 330 | 335 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 613 | 1443 | 2585 | 3685 | 5518 | 5637 | 6692 | 6848 | 7028 | 7181 | 7283 | 7353 | 7388 | 7412 | 7438 | 7439 | 7444 | 7447 | 7450 | 7450 | 7451 | 7451 | 7451 | 7480 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 10 | 19 | 40 | 64 | 87 | 114 | 142 | 168 | 189 | 204 | 217 | 235 | 274 | 300 | 315 | 353 | 617 | 1460 | 2636 | 3809 | 5674 | 5822 | 6916 | 7097 | 7302 | 7487 | 7629 | 7737 | 7802 | 7856 | 7915 | 7943 | 7969 | 7987 | 8003 | 8021 | 8061 | 8087 | 8102 | 8169
G3.217 | I |  |  | Needs from Gate 30 onwards put on hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.218 | I |  |  | Needs from Gate 30 onwards that do not require an intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prepared by: …………………………………………….. |  | 2: Date: ……………………
Checked by: …………………………………………….. |  | 2: Date: ……………………
Authorised by:

## G4a
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2022
SECTION G: INVESTMENT MONITORING
Table G4a: Summary IPOD by Ministerial Objective
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Line Ref | Ministerial Objective | Type | Gate | Pre 21-22 | 2021-22-Q1 | 2021-22-Q2 | 2021-22-Q3 | 2021-22-Q4 | 2021-22-Q1 | 2022-23-Q2 | 2022-23-Q3 | 2022-23-Q4 | 2023-24-Q1 | 2023-24-Q2 | 2023-24-Q3 | 2023-24-Q4 | 2024-25-Q1 | 2024-25-Q2 | 2024-25-Q3 | 2024-25-Q4 | 2025-26-Q1 | 2025-26-Q2 | 2025-26-Q3 | 2025-26-Q4 | 2026-27-Q1 | 2026-27-Q2 | 2026-27-Q3 | 2026-27-Q4 | Post 2026-27
G4a.01 | Standards of Service | Committed List Baseline | SOS - Start On Site | 0 | 12 | 21 | 36 | 44 | 52 | 57 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59
G4a.02 |  |  | G100 - Acceptance | 0 | 43 | 84 | 113 | 136 | 155 | 173 | 188 | 195 | 201 | 212 | 217 | 220 | 223 | 224 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 226
G4a.03 |  |  | G110 - Financial Closure | 0 | 4 | 4 | 30 | 62 | 95 | 129 | 159 | 179 | 199 | 214 | 220 | 230 | 237 | 242 | 245 | 248 | 249 | 251 | 251 | 251 | 251 | 251 | 251 | 251 | 251
G4a.04 |  |  | Total | 0 | 59 | 109 | 179 | 242 | 302 | 359 | 406 | 433 | 459 | 485 | 496 | 509 | 519 | 525 | 530 | 533 | 534 | 536 | 536 | 536 | 536 | 536 | 536 | 536 | 536
G4a.05 |  | Forecast Actual | SOS - Start On Site | 8 | 12 | 21 | 34 | 48 | 53 | 58 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59
G4a.06 |  |  | G100 - Acceptance | 11 | 36 | 67 | 88 | 114 | 136 | 161 | 171 | 192 | 208 | 217 | 220 | 223 | 224 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 226 | 226
G4a.07 |  |  | G110 - Financial Closure | 0 | 3 | 11 | 39 | 94 | 121 | 142 | 171 | 187 | 200 | 217 | 230 | 242 | 246 | 247 | 250 | 251 | 251 | 251 | 251 | 251 | 251 | 251 | 251 | 251 | 251
G4a.08 |  |  | Total | 19 | 51 | 99 | 161 | 256 | 310 | 361 | 401 | 438 | 467 | 493 | 509 | 524 | 529 | 532 | 535 | 536 | 536 | 536 | 536 | 536 | 536 | 536 | 536 | 536 | 536
G4a.09 | Asset Maintenance | Committed List Baseline | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.10 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.11 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.12 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.13 |  | Forecast Actual | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.14 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.15 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.16 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.17 | Supporting Sustainable Economic Growth | Committed List Baseline | SOS - Start On Site | 0 | 2 | 4 | 5 | 5 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G4a.18 |  |  | G100 - Acceptance | 0 | 4 | 8 | 12 | 21 | 24 | 28 | 28 | 30 | 32 | 34 | 34 | 35 | 36 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38
G4a.19 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 2 | 6 | 8 | 12 | 19 | 23 | 27 | 28 | 30 | 32 | 35 | 36 | 37 | 38 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
G4a.20 |  |  | Total | 0 | 6 | 12 | 19 | 32 | 38 | 46 | 53 | 59 | 66 | 69 | 71 | 74 | 78 | 81 | 82 | 83 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85
G4a.21 |  | Forecast Actual | SOS - Start On Site | 0 | 2 | 3 | 5 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G4a.22 |  |  | G100 - Acceptance | 2 | 3 | 5 | 8 | 15 | 19 | 25 | 26 | 26 | 31 | 31 | 33 | 34 | 37 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38
G4a.23 |  |  | G110 - Financial Closure | 0 | 0 | 1 | 3 | 10 | 10 | 16 | 22 | 26 | 27 | 29 | 32 | 33 | 36 | 38 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
G4a.24 |  |  | Total | 2 | 5 | 9 | 16 | 31 | 36 | 48 | 55 | 59 | 65 | 67 | 72 | 74 | 80 | 83 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85
G4a.25 | Circular Economy | Committed List Baseline | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.26 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.27 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.28 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.29 |  | Forecast Actual | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.30 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.31 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.32 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.33 | Drinking Water | Committed List Baseline | SOS - Start On Site | 0 | 2 | 3 | 3 | 4 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G4a.34 |  |  | G100 - Acceptance | 0 | 5 | 7 | 9 | 11 | 14 | 15 | 16 | 20 | 23 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
G4a.35 |  |  | G110 - Financial Closure | 0 | 1 | 1 | 4 | 9 | 12 | 14 | 16 | 17 | 18 | 21 | 26 | 28 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29
G4a.36 |  |  | Total | 0 | 8 | 11 | 16 | 24 | 32 | 36 | 39 | 44 | 48 | 52 | 57 | 59 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60
G4a.37 |  | Forecast Actual | SOS - Start On Site | 0 | 2 | 4 | 4 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G4a.38 |  |  | G100 - Acceptance | 3 | 3 | 5 | 7 | 9 | 11 | 13 | 17 | 19 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 24
G4a.39 |  |  | G110 - Financial Closure | 0 | 0 | 4 | 7 | 11 | 14 | 14 | 17 | 19 | 22 | 25 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 29
G4a.40 |  |  | Total | 3 | 5 | 13 | 18 | 26 | 31 | 34 | 41 | 45 | 52 | 55 | 57 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 60
G4a.41 | Environment | Committed List Baseline | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G4a.42 |  |  | G100 - Acceptance | 0 | 0 | 7 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
G4a.43 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 1 | 8 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G4a.44 |  |  | Total | 0 | 0 | 7 | 8 | 9 | 18 | 19 | 19 | 20 | 20 | 20 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
G4a.45 |  | Forecast Actual | SOS - Start On Site | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G4a.46 |  |  | G100 - Acceptance | 0 | 0 | 2 | 2 | 4 | 6 | 6 | 7 | 8 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
G4a.47 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 1 | 4 | 5 | 7 | 7 | 8 | 9 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G4a.48 |  |  | Total | 0 | 0 | 2 | 3 | 9 | 12 | 14 | 15 | 17 | 19 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
G4a.49 | Flooding and Surface Water Management | Committed List Baseline | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.50 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.51 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.52 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.53 |  | Forecast Actual | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.54 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.55 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.56 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.57 | Security & Resilience | Committed List Baseline | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.58 |  |  | G100 - Acceptance | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G4a.59 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 1 | 1 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G4a.60 |  |  | Total | 0 | 0 | 5 | 6 | 6 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G4a.61 |  | Forecast Actual | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.62 |  |  | G100 - Acceptance | 0 | 0 | 0 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G4a.63 |  |  | G110 - Financial Closure | 0 | 1 | 1 | 1 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G4a.64 |  |  | Total | 0 | 1 | 1 | 4 | 9 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G4a.65 | Climate Change, Adaptation and Mitigation | Committed List Baseline | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.66 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.67 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.68 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.69 |  | Forecast Actual | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.70 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.71 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.72 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.73 | Private Finance Initiative Funded Projects | Committed List Baseline | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.74 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.75 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.76 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.77 |  | Forecast Actual | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.78 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.79 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.80 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.81 | Long Term Water Sector Vision | Committed List Baseline | SOS - Start On Site | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G4a.82 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G4a.83 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G4a.84 |  |  | Total | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3
G4a.85 |  | Forecast Actual | SOS - Start On Site | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G4a.86 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G4a.87 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G4a.88 |  |  | Total | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3
Prepared by: …………………………………………….. |  | 2: Date: ……………………
Checked by: …………………………………………….. |  | 2: Date: ……………………
Authorised by:

## G4b
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2022
SECTION G: INVESTMENT MONITORING
Table G4b: Summary IPOD by Portfolio
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Line Ref | Portfolio | Type | Gate | Pre 21-22 | 2021-22-Q1 | 2021-22-Q2 | 2021-22-Q3 | 2021-22-Q4 | 2021-22-Q1 | 2022-23-Q2 | 2022-23-Q3 | 2022-23-Q4 | 2023-24-Q1 | 2023-24-Q2 | 2023-24-Q3 | 2023-24-Q4 | 2024-25-Q1 | 2024-25-Q2 | 2024-25-Q3 | 2024-25-Q4 | 2025-26-Q1 | 2025-26-Q2 | 2025-26-Q3 | 2025-26-Q4 | 2026-27-Q1 | 2026-27-Q2 | 2026-27-Q3 | 2026-27-Q4 | Post 2026-27
G4b.01 | CE&FS | Committed List Baseline | SOS - Start On Site | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G4b.02 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G4b.03 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G4b.04 |  |  | Total | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3
G4b.05 |  | Forecast Actual | SOS - Start On Site | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G4b.06 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G4b.07 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G4b.08 |  |  | Total | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3
G4b.09 | Water | Committed List Baseline | SOS - Start On Site | 0 | 11 | 15 | 25 | 31 | 40 | 44 | 45 | 45 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46
G4b.10 |  |  | G100 - Acceptance | 0 | 27 | 48 | 64 | 80 | 93 | 104 | 114 | 123 | 131 | 142 | 147 | 151 | 153 | 155 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157
G4b.11 |  |  | G110 - Financial Closure | 0 | 5 | 5 | 28 | 47 | 64 | 81 | 102 | 115 | 127 | 140 | 150 | 161 | 168 | 174 | 178 | 180 | 182 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184
G4b.12 |  |  | Total | 0 | 43 | 68 | 117 | 158 | 197 | 229 | 261 | 283 | 304 | 328 | 343 | 358 | 367 | 375 | 381 | 383 | 385 | 387 | 387 | 387 | 387 | 387 | 387 | 387 | 387
G4b.13 |  | Forecast Actual | SOS - Start On Site | 7 | 11 | 16 | 26 | 36 | 41 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46
G4b.14 |  |  | G100 - Acceptance | 5 | 16 | 36 | 53 | 70 | 79 | 92 | 100 | 118 | 138 | 145 | 149 | 151 | 154 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 156 | 157
G4b.15 |  |  | G110 - Financial Closure | 0 | 2 | 12 | 29 | 68 | 83 | 91 | 108 | 118 | 129 | 146 | 159 | 171 | 176 | 178 | 182 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 184
G4b.16 |  |  | Total | 12 | 29 | 64 | 108 | 174 | 203 | 229 | 254 | 282 | 313 | 337 | 354 | 368 | 376 | 380 | 384 | 385 | 385 | 385 | 385 | 385 | 385 | 385 | 385 | 385 | 387
G4b.17 | Wastewater | Committed List Baseline | SOS - Start On Site | 0 | 4 | 11 | 16 | 18 | 21 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23
G4b.18 |  |  | G100 - Acceptance | 0 | 21 | 51 | 71 | 88 | 101 | 112 | 117 | 121 | 124 | 127 | 128 | 128 | 129 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130
G4b.19 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 8 | 27 | 53 | 76 | 93 | 106 | 117 | 123 | 126 | 129 | 133 | 134 | 134 | 135 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136
G4b.20 |  |  | Total | 0 | 25 | 62 | 95 | 133 | 175 | 210 | 233 | 250 | 264 | 273 | 277 | 280 | 285 | 287 | 287 | 288 | 289 | 289 | 289 | 289 | 289 | 289 | 289 | 289 | 289
G4b.21 |  | Forecast Actual | SOS - Start On Site | 0 | 3 | 9 | 13 | 20 | 21 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23
G4b.22 |  |  | G100 - Acceptance | 11 | 25 | 41 | 48 | 65 | 84 | 102 | 110 | 116 | 122 | 125 | 126 | 128 | 129 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130
G4b.23 |  |  | G110 - Financial Closure | 0 | 0 | 3 | 18 | 46 | 60 | 79 | 98 | 111 | 118 | 124 | 130 | 132 | 134 | 135 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136
G4b.24 |  |  | Total | 11 | 28 | 53 | 79 | 131 | 165 | 203 | 231 | 250 | 263 | 272 | 279 | 283 | 286 | 288 | 289 | 289 | 289 | 289 | 289 | 289 | 289 | 289 | 289 | 289 | 289
G4b.25 | Support Services | Committed List Baseline | SOS - Start On Site | 0 | 1 | 2 | 3 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G4b.26 |  |  | G100 - Acceptance | 0 | 4 | 12 | 12 | 13 | 13 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
G4b.27 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 1 | 5 | 12 | 13 | 14 | 14 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G4b.28 |  |  | Total | 0 | 5 | 14 | 16 | 22 | 29 | 32 | 34 | 34 | 36 | 36 | 36 | 36 | 37 | 37 | 37 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38
G4b.29 |  | Forecast Actual | SOS - Start On Site | 1 | 2 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G4b.30 |  |  | G100 - Acceptance | 0 | 1 | 2 | 7 | 11 | 14 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
G4b.31 |  |  | G110 - Financial Closure | 0 | 2 | 2 | 4 | 10 | 13 | 15 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G4b.32 |  |  | Total | 1 | 5 | 7 | 15 | 26 | 32 | 36 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38
G4b.33 | Total | Committed List Baseline | SOS - Start On Site | 0 | 17 | 29 | 45 | 54 | 66 | 72 | 74 | 74 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75
G4b.34 |  |  | G100 - Acceptance | 0 | 52 | 111 | 147 | 181 | 207 | 230 | 246 | 259 | 270 | 284 | 290 | 294 | 298 | 301 | 303 | 303 | 303 | 303 | 303 | 303 | 303 | 303 | 303 | 303 | 304
G4b.35 |  |  | G110 - Financial Closure | 0 | 5 | 5 | 37 | 79 | 129 | 170 | 209 | 235 | 260 | 279 | 292 | 306 | 317 | 324 | 328 | 332 | 335 | 337 | 337 | 337 | 337 | 337 | 337 | 337 | 338
G4b.36 |  |  | Total | 0 | 74 | 145 | 229 | 314 | 402 | 472 | 529 | 568 | 605 | 638 | 657 | 675 | 690 | 700 | 706 | 710 | 713 | 715 | 715 | 715 | 715 | 715 | 715 | 715 | 717
G4b.37 |  | Forecast Actual | SOS - Start On Site | 8 | 17 | 29 | 44 | 62 | 68 | 74 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75
G4b.38 |  |  | G100 - Acceptance | 16 | 42 | 79 | 108 | 146 | 177 | 210 | 226 | 250 | 276 | 286 | 291 | 295 | 299 | 302 | 302 | 302 | 302 | 302 | 302 | 302 | 302 | 302 | 302 | 302 | 304
G4b.39 |  |  | G110 - Financial Closure | 0 | 4 | 17 | 51 | 124 | 156 | 185 | 223 | 246 | 264 | 287 | 306 | 320 | 327 | 330 | 335 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 338
G4b.40 |  |  | Total | 24 | 63 | 125 | 203 | 332 | 401 | 469 | 524 | 571 | 615 | 648 | 672 | 690 | 701 | 707 | 712 | 713 | 713 | 713 | 713 | 713 | 713 | 713 | 713 | 713 | 717
Prepared by: …………………………………………….. |  | 2: Date: ……………………
Checked by: …………………………………………….. |  | 2: Date: ……………………
Authorised by:

## G4c
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2022
SECTION G: INVESTMENT MONITORING
Table G4c: Detail IPOD
GATE ID | PROJECT ID | PORTFOLIO | GATE | GATE NAME | BASELINE DATE | FORECAST DATE | BASELINE MONTH | FORECAST MONTH | BASELINE QUARTER | FORECAST QUARTER
SOS403716 | 403716 | Wastewater | SOS | Start on Site | 2022-07-11 | 2022-07-11 | 2022_23_P04 | 2022_23_P04 | 2022_23_Q2 | 2022_23_Q2
SOS403923 | 403923 | Wastewater | SOS | Start on Site | 2021-04-06 | 2021-06-15 | 2021_22_P01 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
SOS403782 | 403782 | Wastewater | SOS | Start on Site | 2021-12-20 | 2021-12-06 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
SOS403967 | 403967 | Wastewater | SOS | Start on Site | 2021-08-09 | 2021-07-29 | 2021_22_P05 | 2021_22_P04 | 2021_22_Q2 | 2021_22_Q2
SOS500046 | 500046 | Water | SOS | Start on Site | 2023-05-11 | 2021-12-21 | 2023_24_P02 | 2021_22_P09 | 2023_24_Q1 | 2021_22_Q3
SOS403995 | 403995 | Water | SOS | Start on Site | 2022-03-15 | 2022-03-15 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
SOS404026 | 404026 | Wastewater | SOS | Start on Site | 2021-08-09 | 2022-03-31 | 2021_22_P05 | 2021_22_P12 | 2021_22_Q2 | 2021_22_Q4
SOS500229 | 500229 | Wastewater | SOS | Start on Site | 2021-07-30 | 2022-03-31 | 2021_22_P04 | 2021_22_P12 | 2021_22_Q2 | 2021_22_Q4
SOS500654 | 500654 | Wastewater | SOS | Start on Site | 2021-05-10 | 2021-09-30 | 2021_22_P02 | 2021_22_P06 | 2021_22_Q1 | 2021_22_Q2
SOS500661 | 500661 | Wastewater | SOS | Start on Site | 2021-08-09 | 2021-08-20 | 2021_22_P05 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2
SOS500681 | 500681 | Wastewater | SOS | Start on Site | 2021-08-03 | 2021-09-27 | 2021_22_P05 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
SOS500682 | 500682 | Wastewater | SOS | Start on Site | 2021-09-20 | 2021-09-20 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
SOS500755 | 500755 | Water | SOS | Start on Site | 2021-09-01 | 2021-08-02 | 2021_22_P06 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2
SOS500892 | 500892 | Water | SOS | Start on Site | 2021-06-02 | 2021-04-26 | 2021_22_P03 | 2021_22_P01 | 2021_22_Q1 | 2021_22_Q1
SOS501379 | 501379 | Water | SOS | Start on Site | 2021-04-01 | 2021-03-22 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
SOS501512 | 501512 | Wastewater | SOS | Start on Site | 2022-10-11 | 2022-10-11 | 2022_23_P07 | 2022_23_P07 | 2022_23_Q3 | 2022_23_Q3
SOS502282 | 502282 | Water | SOS | Start on Site | 2022-09-12 | 2022-09-12 | 2022_23_P06 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2
SOS502212 | 502212 | Wastewater | SOS | Start on Site | 2022-04-04 | 2022-03-30 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
SOS502342 | 502342 | Wastewater | SOS | Start on Site | 2021-07-05 | 2021-07-05 | 2021_22_P04 | 2021_22_P04 | 2021_22_Q2 | 2021_22_Q2
SOS502383 | 502383 | Water | SOS | Start on Site | 2021-04-14 | 2021-03-08 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
SOS502563 | 502563 | Water | SOS | Start on Site | 2021-07-20 | 2021-07-05 | 2021_22_P04 | 2021_22_P04 | 2021_22_Q2 | 2021_22_Q2
SOS502652 | 502652 | Water | SOS | Start on Site | 2022-02-21 | 2022-02-21 | 2021_22_P11 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4
SOS502827 | 502827 | Wastewater | SOS | Start on Site | 2021-05-18 | 2021-05-31 | 2021_22_P02 | 2021_22_P02 | 2021_22_Q1 | 2021_22_Q1
SOS502853 | 502853 | Water | SOS | Start on Site | 2021-10-22 | 2021-10-22 | 2021_22_P07 | 2021_22_P07 | 2021_22_Q3 | 2021_22_Q3
SOS502895 | 502895 | Wastewater | SOS | Start on Site | 2021-11-18 | 2021-11-18 | 2021_22_P08 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
SOS502857 | 502857 | Water | SOS | Start on Site | 2022-05-19 | 2022-05-19 | 2022_23_P02 | 2022_23_P02 | 2022_23_Q1 | 2022_23_Q1
SOS502958 | 502958 | Wastewater | SOS | Start on Site | 2021-10-18 | 2021-10-18 | 2021_22_P07 | 2021_22_P07 | 2021_22_Q3 | 2021_22_Q3
SOS503050 | 503050 | Water | SOS | Start on Site | 2021-08-04 | 2021-08-30 | 2021_22_P05 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2
SOS503162 | 503162 | Water | SOS | Start on Site | 2021-10-05 | 2021-12-14 | 2021_22_P07 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
SOS503230 | 503230 | Wastewater | SOS | Start on Site | 2022-04-11 | 2022-03-31 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
SOS503234 | 503234 | Water | SOS | Start on Site | 2021-06-21 | 2021-06-01 | 2021_22_P03 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
SOS503336 | 503336 | Water | SOS | Start on Site | 2021-08-02 | 2021-08-04 | 2021_22_P05 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2
SOS503408 | 503408 | Water | SOS | Start on Site | 2022-02-28 | 2022-02-28 | 2021_22_P11 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4
SOS503412 | 503412 | Water | SOS | Start on Site | 2021-04-21 | 2021-03-23 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
SOS503413 | 503413 | Water | SOS | Start on Site | 2021-04-21 | 2021-03-24 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
SOS503421 | 503421 | Water | SOS | Start on Site | 2022-04-18 | 2021-09-13 | 2022_23_P01 | 2021_22_P06 | 2022_23_Q1 | 2021_22_Q2
SOS503441 | 503441 | Wastewater | SOS | Start on Site | 2022-02-28 | 2022-03-28 | 2021_22_P11 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
SOS503571 | 503571 | Wastewater | SOS | Start on Site | 2021-06-10 | 2021-06-10 | 2021_22_P03 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
SOS503678 | 503678 | Water | SOS | Start on Site | 2022-03-11 | 2022-03-28 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
SOS503686 | 503686 | Water | SOS | Start on Site | 2022-04-04 | 2022-03-11 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
SOS503716 | 503716 | Water | SOS | Start on Site | 2021-06-14 | 2021-05-11 | 2021_22_P03 | 2021_22_P02 | 2021_22_Q1 | 2021_22_Q1
SOS503730 | 503730 | Water | SOS | Start on Site | 2022-11-16 | 2022-02-14 | 2022_23_P08 | 2021_22_P11 | 2022_23_Q3 | 2021_22_Q4
SOS503731 | 503731 | Water | SOS | Start on Site | 2021-04-01 | 2021-03-31 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
SOS503761 | 503761 | Water | SOS | Start on Site | 2021-05-25 | 2021-06-22 | 2021_22_P02 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
SOS504995 | 504995 | Water | SOS | Start on Site | 2022-09-05 | 2022-09-05 | 2022_23_P06 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2
SOS505053 | 505053 | Wastewater | SOS | Start on Site | 2022-05-23 | 2022-05-23 | 2022_23_P02 | 2022_23_P02 | 2022_23_Q1 | 2022_23_Q1
SOS505447 | 505447 | Water | SOS | Start on Site | 2021-12-01 | 2021-11-29 | 2021_22_P09 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
SOS505504 | 505504 | Water | SOS | Start on Site | 2021-11-29 | 2022-08-01 | 2021_22_P08 | 2022_23_P05 | 2021_22_Q3 | 2022_23_Q2
SOS505641 | 505641 | Wastewater | SOS | Start on Site | 2022-01-06 | 2022-01-06 | 2021_22_P10 | 2021_22_P10 | 2021_22_Q4 | 2021_22_Q4
SOS505693 | 505693 | Water | SOS | Start on Site | 2021-11-08 | 2021-11-22 | 2021_22_P08 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
SOS506029 | 506029 | Water | SOS | Start on Site | 2022-08-31 | 2022-08-31 | 2022_23_P05 | 2022_23_P05 | 2022_23_Q2 | 2022_23_Q2
SOS506032 | 506032 | Water | SOS | Start on Site | 2022-09-30 | 2022-09-30 | 2022_23_P06 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2
SOS506228 | 506228 | Water | SOS | Start on Site | 2021-10-11 | 2021-11-22 | 2021_22_P07 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
SOS506232 | 506232 | Water | SOS | Start on Site | 2021-10-11 | 2021-10-11 | 2021_22_P07 | 2021_22_P07 | 2021_22_Q3 | 2021_22_Q3
SOS506234 | 506234 | Water | SOS | Start on Site | 2021-10-26 | 2021-10-26 | 2021_22_P07 | 2021_22_P07 | 2021_22_Q3 | 2021_22_Q3
SOS506608 | 506608 | Water | SOS | Start on Site | 2022-06-10 | 2022-06-10 | 2022_23_P03 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1
SOS506684 | 506684 | Water | SOS | Start on Site | 2021-04-05 | 2021-03-23 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
SOS506779 | 506779 | Water | SOS | Start on Site | 2021-10-11 | 2021-11-01 | 2021_22_P07 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
SOS507057 | 507057 | Water | SOS | Start on Site | 2022-05-30 | 2022-05-30 | 2022_23_P02 | 2022_23_P02 | 2022_23_Q1 | 2022_23_Q1
SOS507186 | 507186 | Water | SOS | Start on Site | 2022-01-10 | 2022-01-24 | 2021_22_P10 | 2021_22_P10 | 2021_22_Q4 | 2021_22_Q4
SOS507189 | 507189 | Water | SOS | Start on Site | 2022-03-30 | 2022-03-31 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
SOS507933 | 507933 | Wastewater | SOS | Start on Site | 2021-10-22 | 2021-11-19 | 2021_22_P07 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
SOS508109 | 508109 | Support Services | SOS | Start on Site | 2021-04-19 | 2021-03-24 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
SOS508601 | 508601 | Wastewater | SOS | Start on Site | 2021-11-02 | 2022-01-10 | 2021_22_P08 | 2021_22_P10 | 2021_22_Q3 | 2021_22_Q4
SOS509283 | 509283 | Water | SOS | Start on Site | 2021-04-12 | 2021-02-15 | 2021_22_P01 | 2020_21_P11 | 2021_22_Q1 | 2020_21_Q4
SOS510727 | 510727 | Support Services | SOS | Start on Site | 2021-12-13 | 2021-11-09 | 2021_22_P09 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
SOS511344 | 511344 | Support Services | SOS | Start on Site | 2022-08-24 | 2021-04-30 | 2022_23_P05 | 2021_22_P01 | 2022_23_Q2 | 2021_22_Q1
SOS512600 | 512600 | Water | SOS | Start on Site | 2022-04-04 | 2022-04-11 | 2022_23_P01 | 2022_23_P01 | 2022_23_Q1 | 2022_23_Q1
SOS512711 | 512711 | Water | SOS | Start on Site | 2022-06-29 | 2022-03-31 | 2022_23_P03 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
SOS512749 | 512749 | Water | SOS | Start on Site | 2022-05-25 | 2022-06-08 | 2022_23_P02 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1
SOS513312 | 513312 | CE&FS | SOS | Start on Site | 2021-06-22 | 2021-06-21 | 2021_22_P03 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
SOS513461 | 513461 | Support Services | SOS | Start on Site | 2022-03-21 | 2022-01-26 | 2021_22_P12 | 2021_22_P10 | 2021_22_Q4 | 2021_22_Q4
SOS513832 | 513832 | Support Services | SOS | Start on Site | 2021-08-17 | 2021-08-23 | 2021_22_P05 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2
SOS513923 | 513923 | Water | SOS | Start on Site | 2021-11-15 | 2021-11-25 | 2021_22_P08 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
SOS515505 | 515505 | Water | SOS | Start on Site | 2022-04-11 | 2022-03-31 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G100046172 | 046172 | Water | G100 | Gate 100 | 2021-09-01 | 2021-10-05 | 2021_22_P06 | 2021_22_P07 | 2021_22_Q2 | 2021_22_Q3
G100400324 | 400324 | Water | G100 | Gate 100 | 2023-04-14 | 2023-04-14 | 2023_24_P01 | 2023_24_P01 | 2023_24_Q1 | 2023_24_Q1
G100401687 | 401687 | Wastewater | G100 | Gate 100 | 2021-09-21 | 2021-09-21 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100401668 | 401668 | Wastewater | G100 | Gate 100 | 2021-09-20 | 2022-07-21 | 2021_22_P06 | 2022_23_P04 | 2021_22_Q2 | 2022_23_Q2
G100401685 | 401685 | Wastewater | G100 | Gate 100 | 2021-09-20 | 2021-09-21 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100401705 | 401705 | Wastewater | G100 | Gate 100 | 2021-10-24 | 2022-09-19 | 2021_22_P07 | 2022_23_P06 | 2021_22_Q3 | 2022_23_Q2
G100401795 | 401795 | Wastewater | G100 | Gate 100 | 2021-07-06 | 2021-06-28 | 2021_22_P04 | 2021_22_P03 | 2021_22_Q2 | 2021_22_Q1
G100402197 | 402197 | Wastewater | G100 | Gate 100 | 2021-05-11 | 2021-04-30 | 2021_22_P02 | 2021_22_P01 | 2021_22_Q1 | 2021_22_Q1
G100402949 | 402949 | Wastewater | G100 | Gate 100 | 2022-10-21 | 2022-07-21 | 2022_23_P07 | 2022_23_P04 | 2022_23_Q3 | 2022_23_Q2
G100403098 | 403098 | Wastewater | G100 | Gate 100 | 2021-12-01 | 2022-03-24 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G100403100 | 403100 | Wastewater | G100 | Gate 100 | 2021-08-21 | 2021-09-24 | 2021_22_P05 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100403101 | 403101 | Wastewater | G100 | Gate 100 | 2021-08-24 | 2021-09-21 | 2021_22_P05 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100403102 | 403102 | Wastewater | G100 | Gate 100 | 2021-08-24 | 2021-09-21 | 2021_22_P05 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100403103 | 403103 | Wastewater | G100 | Gate 100 | 2021-09-26 | 2021-03-31 | 2021_22_P06 | 2020_21_P12 | 2021_22_Q2 | 2020_21_Q4
G100403104 | 403104 | Wastewater | G100 | Gate 100 | 2021-09-01 | 2022-03-30 | 2021_22_P06 | 2021_22_P12 | 2021_22_Q2 | 2021_22_Q4
G100403106 | 403106 | Wastewater | G100 | Gate 100 | 2023-01-31 | 2022-10-31 | 2022_23_P10 | 2022_23_P07 | 2022_23_Q4 | 2022_23_Q3
G100403090 | 403090 | Water | G100 | Gate 100 | 2021-06-30 | 2021-05-31 | 2021_22_P03 | 2021_22_P02 | 2021_22_Q1 | 2021_22_Q1
G100403238 | 403238 | Wastewater | G100 | Gate 100 | 2021-08-16 | 2021-09-21 | 2021_22_P05 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100403127 | 403127 | Water | G100 | Gate 100 | 2022-01-31 | 2023-02-09 | 2021_22_P10 | 2022_23_P11 | 2021_22_Q4 | 2022_23_Q4
G100403321 | 403321 | Wastewater | G100 | Gate 100 | 2022-08-27 | 2022-06-22 | 2022_23_P05 | 2022_23_P03 | 2022_23_Q2 | 2022_23_Q1
G100403532 | 403532 | Water | G100 | Gate 100 | 2021-10-01 | 2022-01-21 | 2021_22_P07 | 2021_22_P10 | 2021_22_Q3 | 2021_22_Q4
G100403716 | 403716 | Wastewater | G100 | Gate 100 | 2023-02-22 | 2022-11-24 | 2022_23_P11 | 2022_23_P08 | 2022_23_Q4 | 2022_23_Q3
G100403658 | 403658 | Water | G100 | Gate 100 | 2022-09-30 | 2023-05-26 | 2022_23_P06 | 2023_24_P02 | 2022_23_Q2 | 2023_24_Q1
G100403923 | 403923 | Wastewater | G100 | Gate 100 | 2022-06-30 | 2022-10-14 | 2022_23_P03 | 2022_23_P07 | 2022_23_Q1 | 2022_23_Q3
G100403781 | 403781 | Wastewater | G100 | Gate 100 | 2021-09-16 | 2021-07-20 | 2021_22_P06 | 2021_22_P04 | 2021_22_Q2 | 2021_22_Q2
G100403782 | 403782 | Wastewater | G100 | Gate 100 | 2023-05-01 | 2023-04-21 | 2023_24_P02 | 2023_24_P01 | 2023_24_Q1 | 2023_24_Q1
G100403902 | 403902 | Wastewater | G100 | Gate 100 | 2021-11-22 | 2022-05-10 | 2021_22_P08 | 2022_23_P02 | 2021_22_Q3 | 2022_23_Q1
G100404082 | 404082 | Water | G100 | Gate 100 | 2021-09-10 | 2021-04-26 | 2021_22_P06 | 2021_22_P01 | 2021_22_Q2 | 2021_22_Q1
G100403934 | 403934 | Wastewater | G100 | Gate 100 | 2022-07-04 | 2022-05-31 | 2022_23_P04 | 2022_23_P02 | 2022_23_Q2 | 2022_23_Q1
G100500060 | 500060 | Water | G100 | Gate 100 | 2021-05-12 | 2021-04-01 | 2021_22_P02 | 2021_22_P01 | 2021_22_Q1 | 2021_22_Q1
G100403967 | 403967 | Wastewater | G100 | Gate 100 | 2024-09-09 | 2024-07-30 | 2024_25_P06 | 2024_25_P04 | 2024_25_Q2 | 2024_25_Q2
G100403991 | 403991 | Water | G100 | Gate 100 | 2023-01-30 | 2023-04-10 | 2022_23_P10 | 2023_24_P01 | 2022_23_Q4 | 2023_24_Q1
G100403943 | 403943 | Wastewater | G100 | Gate 100 | 2021-11-18 | 2022-07-11 | 2021_22_P08 | 2022_23_P04 | 2021_22_Q3 | 2022_23_Q2
G100403939 | 403939 | Wastewater | G100 | Gate 100 | 2022-05-05 | 2022-09-13 | 2022_23_P02 | 2022_23_P06 | 2022_23_Q1 | 2022_23_Q2
G100403994 | 403994 | Water | G100 | Gate 100 | 2022-02-25 | 2022-07-13 | 2021_22_P11 | 2022_23_P04 | 2021_22_Q4 | 2022_23_Q2
G100500046 | 500046 | Water | G100 | Gate 100 | 2024-08-18 | 2022-03-10 | 2024_25_P05 | 2021_22_P12 | 2024_25_Q2 | 2021_22_Q4
G100404007 | 404007 | Wastewater | G100 | Gate 100 | 2022-02-18 | 2021-09-30 | 2021_22_P11 | 2021_22_P06 | 2021_22_Q4 | 2021_22_Q2
G100404003 | 404003 | Water | G100 | Gate 100 | 2021-04-01 | 2021-11-19 | 2021_22_P01 | 2021_22_P08 | 2021_22_Q1 | 2021_22_Q3
G100403995 | 403995 | Water | G100 | Gate 100 | 2024-10-17 | 2024-07-19 | 2024_25_P07 | 2024_25_P04 | 2024_25_Q3 | 2024_25_Q2
G100403986 | 403986 | Water | G100 | Gate 100 | 2023-04-14 | 2023-06-02 | 2023_24_P01 | 2023_24_P03 | 2023_24_Q1 | 2023_24_Q1
G100404093 | 404093 | Water | G100 | Gate 100 | 2023-08-23 | 2023-10-12 | 2023_24_P05 | 2023_24_P07 | 2023_24_Q2 | 2023_24_Q3
G100404026 | 404026 | Wastewater | G100 | Gate 100 | 2022-06-20 | 2023-05-09 | 2022_23_P03 | 2023_24_P02 | 2022_23_Q1 | 2023_24_Q1
G100404069 | 404069 | Wastewater | G100 | Gate 100 | 2021-04-30 | 2021-03-24 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100500017 | 500017 | Wastewater | G100 | Gate 100 | 2022-02-21 | 2022-03-30 | 2021_22_P11 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G100500052 | 500052 | Wastewater | G100 | Gate 100 | 2022-07-30 | 2022-09-23 | 2022_23_P04 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2
G100404134 | 404134 | Water | G100 | Gate 100 | 2021-06-17 | 2021-10-01 | 2021_22_P03 | 2021_22_P07 | 2021_22_Q1 | 2021_22_Q3
G100404135 | 404135 | Water | G100 | Gate 100 | 2023-01-27 | 2023-09-15 | 2022_23_P10 | 2023_24_P06 | 2022_23_Q4 | 2023_24_Q2
G100500068 | 500068 | Wastewater | G100 | Gate 100 | 2021-06-23 | 2021-06-29 | 2021_22_P03 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100500040 | 500040 | Water | G100 | Gate 100 | 2021-04-30 | 2021-07-30 | 2021_22_P01 | 2021_22_P04 | 2021_22_Q1 | 2021_22_Q2
G100500047 | 500047 | Water | G100 | Gate 100 | 2022-10-07 | 2022-08-29 | 2022_23_P07 | 2022_23_P05 | 2022_23_Q3 | 2022_23_Q2
G100500207 | 500207 | Water | G100 | Gate 100 | 2021-06-01 | 2021-10-21 | 2021_22_P03 | 2021_22_P07 | 2021_22_Q1 | 2021_22_Q3
G100500246 | 500246 | Water | G100 | Gate 100 | 2021-10-22 | 2022-10-10 | 2021_22_P07 | 2022_23_P07 | 2021_22_Q3 | 2022_23_Q3
G100500218 | 500218 | Water | G100 | Gate 100 | 2022-02-15 | 2021-12-21 | 2021_22_P11 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3
G100500233 | 500233 | Wastewater | G100 | Gate 100 | 2022-01-14 | 2022-05-05 | 2021_22_P10 | 2022_23_P02 | 2021_22_Q4 | 2022_23_Q1
G100500235 | 500235 | Wastewater | G100 | Gate 100 | 2022-06-03 | 2022-05-12 | 2022_23_P03 | 2022_23_P02 | 2022_23_Q1 | 2022_23_Q1
G100500245 | 500245 | Water | G100 | Gate 100 | 2022-08-17 | 2023-01-27 | 2022_23_P05 | 2022_23_P10 | 2022_23_Q2 | 2022_23_Q4
G100500299 | 500299 | Wastewater | G100 | Gate 100 | 2021-10-20 | 2021-08-31 | 2021_22_P07 | 2021_22_P05 | 2021_22_Q3 | 2021_22_Q2
G100500302 | 500302 | Wastewater | G100 | Gate 100 | 2022-06-30 | 2022-07-21 | 2022_23_P03 | 2022_23_P04 | 2022_23_Q1 | 2022_23_Q2
G100500229 | 500229 | Wastewater | G100 | Gate 100 | 2023-07-28 | 2023-12-22 | 2023_24_P04 | 2023_24_P09 | 2023_24_Q2 | 2023_24_Q3
G100500496 | 500496 | Wastewater | G100 | Gate 100 | 2021-05-30 | 2021-03-26 | 2021_22_P02 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100500509 | 500509 | Water | G100 | Gate 100 | 2021-08-24 | 2022-10-25 | 2021_22_P05 | 2022_23_P07 | 2021_22_Q2 | 2022_23_Q3
G100500523 | 500523 | Water | G100 | Gate 100 | 2023-09-20 | 2024-03-25 | 2023_24_P06 | 2023_24_P12 | 2023_24_Q2 | 2023_24_Q4
G100500573 | 500573 | Water | G100 | Gate 100 | 2022-06-28 | 2022-05-27 | 2022_23_P03 | 2022_23_P02 | 2022_23_Q1 | 2022_23_Q1
G100500575 | 500575 | Water | G100 | Gate 100 | 2022-08-22 | 2023-03-02 | 2022_23_P05 | 2022_23_P12 | 2022_23_Q2 | 2022_23_Q4
G100500579 | 500579 | Wastewater | G100 | Gate 100 | 2022-03-31 | 2022-11-17 | 2021_22_P12 | 2022_23_P08 | 2021_22_Q4 | 2022_23_Q3
G100500580 | 500580 | Wastewater | G100 | Gate 100 | 2022-10-30 | 2022-09-22 | 2022_23_P07 | 2022_23_P06 | 2022_23_Q3 | 2022_23_Q2
G100500652 | 500652 | Wastewater | G100 | Gate 100 | 2021-11-09 | 2022-03-17 | 2021_22_P08 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G100500654 | 500654 | Wastewater | G100 | Gate 100 | 2022-01-29 | 2022-08-31 | 2021_22_P10 | 2022_23_P05 | 2021_22_Q4 | 2022_23_Q2
G100500655 | 500655 | Wastewater | G100 | Gate 100 | 2022-03-28 | 2021-10-29 | 2021_22_P12 | 2021_22_P07 | 2021_22_Q4 | 2021_22_Q3
G100500661 | 500661 | Wastewater | G100 | Gate 100 | 2022-09-22 | 2022-08-26 | 2022_23_P06 | 2022_23_P05 | 2022_23_Q2 | 2022_23_Q2
G100500662 | 500662 | Wastewater | G100 | Gate 100 | 2021-11-24 | 2022-01-26 | 2021_22_P08 | 2021_22_P10 | 2021_22_Q3 | 2021_22_Q4
G100500665 | 500665 | Wastewater | G100 | Gate 100 | 2022-01-16 | 2021-11-24 | 2021_22_P10 | 2021_22_P08 | 2021_22_Q4 | 2021_22_Q3
G100500681 | 500681 | Wastewater | G100 | Gate 100 | 2022-09-14 | 2023-01-26 | 2022_23_P06 | 2022_23_P10 | 2022_23_Q2 | 2022_23_Q4
G100500682 | 500682 | Wastewater | G100 | Gate 100 | 2022-09-07 | 2022-09-30 | 2022_23_P06 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2
G100500687 | 500687 | Wastewater | G100 | Gate 100 | 2021-09-24 | 2021-07-29 | 2021_22_P06 | 2021_22_P04 | 2021_22_Q2 | 2021_22_Q2
G100500694 | 500694 | Wastewater | G100 | Gate 100 | 2021-11-22 | 2022-05-19 | 2021_22_P08 | 2022_23_P02 | 2021_22_Q3 | 2022_23_Q1
G100500695 | 500695 | Wastewater | G100 | Gate 100 | 2021-04-02 | 2021-03-22 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100500707 | 500707 | Wastewater | G100 | Gate 100 | 2021-07-14 | 2021-06-14 | 2021_22_P04 | 2021_22_P03 | 2021_22_Q2 | 2021_22_Q1
G100500709 | 500709 | Water | G100 | Gate 100 | 2021-10-11 | 2022-06-24 | 2021_22_P07 | 2022_23_P03 | 2021_22_Q3 | 2022_23_Q1
G100500755 | 500755 | Water | G100 | Gate 100 | 2023-11-13 | 2023-04-19 | 2023_24_P08 | 2023_24_P01 | 2023_24_Q3 | 2023_24_Q1
G100500784 | 500784 | Wastewater | G100 | Gate 100 | 2021-04-23 | 2021-06-15 | 2021_22_P01 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100500742 | 500742 | Water | G100 | Gate 100 | 2021-04-30 | 2021-07-14 | 2021_22_P01 | 2021_22_P04 | 2021_22_Q1 | 2021_22_Q2
G100500771 | 500771 | Water | G100 | Gate 100 | 2021-06-14 | 2021-12-21 | 2021_22_P03 | 2021_22_P09 | 2021_22_Q1 | 2021_22_Q3
G100500723 | 500723 | Wastewater | G100 | Gate 100 | 2022-01-14 | 2022-01-26 | 2021_22_P10 | 2021_22_P10 | 2021_22_Q4 | 2021_22_Q4
G100500892 | 500892 | Water | G100 | Gate 100 | 2022-06-27 | 2023-04-19 | 2022_23_P03 | 2023_24_P01 | 2022_23_Q1 | 2023_24_Q1
G100500896 | 500896 | Water | G100 | Gate 100 | 2022-11-07 | 2023-03-14 | 2022_23_P08 | 2022_23_P12 | 2022_23_Q3 | 2022_23_Q4
G100500918 | 500918 | Water | G100 | Gate 100 | 2022-05-31 | 2022-08-17 | 2022_23_P02 | 2022_23_P05 | 2022_23_Q1 | 2022_23_Q2
G100500947 | 500947 | Support Services | G100 | Gate 100 | 2021-06-16 | 2022-03-03 | 2021_22_P03 | 2021_22_P12 | 2021_22_Q1 | 2021_22_Q4
G100500958 | 500958 | Water | G100 | Gate 100 | 2021-07-08 | 2022-01-13 | 2021_22_P04 | 2021_22_P10 | 2021_22_Q2 | 2021_22_Q4
G100501001 | 501001 | Water | G100 | Gate 100 | 2023-02-16 | 2023-08-08 | 2022_23_P11 | 2023_24_P05 | 2022_23_Q4 | 2023_24_Q2
G100501019 | 501019 | Wastewater | G100 | Gate 100 | 2021-05-29 | 2021-03-12 | 2021_22_P02 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100501021 | 501021 | Wastewater | G100 | Gate 100 | 2022-03-31 | 2022-09-14 | 2021_22_P12 | 2022_23_P06 | 2021_22_Q4 | 2022_23_Q2
G100501040 | 501040 | Water | G100 | Gate 100 | 2021-05-31 | 2021-06-30 | 2021_22_P02 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100501070 | 501070 | Water | G100 | Gate 100 | 2021-10-22 | 2027-04-01 | 2021_22_P07 | 2027_28_P01 | 2021_22_Q3 | 2027_28_Q1
G100501091 | 501091 | Water | G100 | Gate 100 | 2022-01-12 | 2021-08-23 | 2021_22_P10 | 2021_22_P05 | 2021_22_Q4 | 2021_22_Q2
G100501144 | 501144 | Water | G100 | Gate 100 | 2022-01-21 | 2022-02-21 | 2021_22_P10 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4
G100501146 | 501146 | Water | G100 | Gate 100 | 2021-04-30 | 2021-06-11 | 2021_22_P01 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100501151 | 501151 | Wastewater | G100 | Gate 100 | 2021-05-25 | 2021-06-28 | 2021_22_P02 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100501153 | 501153 | Wastewater | G100 | Gate 100 | 2021-09-28 | 2022-04-28 | 2021_22_P06 | 2022_23_P01 | 2021_22_Q2 | 2022_23_Q1
G100501156 | 501156 | Wastewater | G100 | Gate 100 | 2021-10-11 | 2022-03-31 | 2021_22_P07 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G100501388 | 501388 | Water | G100 | Gate 100 | 2022-01-31 | 2022-07-12 | 2021_22_P10 | 2022_23_P04 | 2021_22_Q4 | 2022_23_Q2
G100501390 | 501390 | Water | G100 | Gate 100 | 2022-11-10 | 2023-03-31 | 2022_23_P08 | 2022_23_P12 | 2022_23_Q3 | 2022_23_Q4
G100501200 | 501200 | Water | G100 | Gate 100 | 2022-04-25 | 2022-06-10 | 2022_23_P01 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1
G100501216 | 501216 | Water | G100 | Gate 100 | 2021-11-18 | 2022-03-22 | 2021_22_P08 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G100501217 | 501217 | Water | G100 | Gate 100 | 2021-08-31 | 2022-04-29 | 2021_22_P05 | 2022_23_P01 | 2021_22_Q2 | 2022_23_Q1
G100501158 | 501158 | Wastewater | G100 | Gate 100 | 2021-06-03 | 2022-03-01 | 2021_22_P03 | 2021_22_P12 | 2021_22_Q1 | 2021_22_Q4
G100501159 | 501159 | Wastewater | G100 | Gate 100 | 2023-06-20 | 2023-07-14 | 2023_24_P03 | 2023_24_P04 | 2023_24_Q1 | 2023_24_Q2
G100501165 | 501165 | Wastewater | G100 | Gate 100 | 2021-06-16 | 2021-03-30 | 2021_22_P03 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100501168 | 501168 | Wastewater | G100 | Gate 100 | 2022-05-30 | 2022-04-01 | 2022_23_P02 | 2022_23_P01 | 2022_23_Q1 | 2022_23_Q1
G100501169 | 501169 | Wastewater | G100 | Gate 100 | 2021-04-01 | 2021-05-10 | 2021_22_P01 | 2021_22_P02 | 2021_22_Q1 | 2021_22_Q1
G100501232 | 501232 | Water | G100 | Gate 100 | 2022-02-02 | 2023-01-18 | 2021_22_P11 | 2022_23_P10 | 2021_22_Q4 | 2022_23_Q4
G100501233 | 501233 | Water | G100 | Gate 100 | 2021-07-30 | 2021-05-17 | 2021_22_P04 | 2021_22_P02 | 2021_22_Q2 | 2021_22_Q1
G100501379 | 501379 | Water | G100 | Gate 100 | 2022-09-29 | 2023-01-23 | 2022_23_P06 | 2022_23_P10 | 2022_23_Q2 | 2022_23_Q4
G100501243 | 501243 | Water | G100 | Gate 100 | 2023-02-01 | 2023-03-29 | 2022_23_P11 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4
G100501259 | 501259 | Water | G100 | Gate 100 | 2021-06-15 | 2021-07-19 | 2021_22_P03 | 2021_22_P04 | 2021_22_Q1 | 2021_22_Q2
G100501290 | 501290 | Wastewater | G100 | Gate 100 | 2022-07-30 | 2022-08-31 | 2022_23_P04 | 2022_23_P05 | 2022_23_Q2 | 2022_23_Q2
G100501218 | 501218 | Water | G100 | Gate 100 | 2021-08-27 | 2021-11-17 | 2021_22_P05 | 2021_22_P08 | 2021_22_Q2 | 2021_22_Q3
G100501219 | 501219 | Water | G100 | Gate 100 | 2021-07-01 | 2021-07-29 | 2021_22_P04 | 2021_22_P04 | 2021_22_Q2 | 2021_22_Q2
G100501488 | 501488 | Wastewater | G100 | Gate 100 | 2022-03-30 | 2022-03-28 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G100501499 | 501499 | Wastewater | G100 | Gate 100 | 2022-02-21 | 2022-04-08 | 2021_22_P11 | 2022_23_P01 | 2021_22_Q4 | 2022_23_Q1
G100501500 | 501500 | Wastewater | G100 | Gate 100 | 2021-05-30 | 2021-03-31 | 2021_22_P02 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100501352 | 501352 | Wastewater | G100 | Gate 100 | 2021-12-09 | 2022-03-29 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G100501393 | 501393 | Water | G100 | Gate 100 | 2022-05-30 | 2022-11-15 | 2022_23_P02 | 2022_23_P08 | 2022_23_Q1 | 2022_23_Q3
G100501402 | 501402 | Water | G100 | Gate 100 | 2021-05-07 | 2021-03-31 | 2021_22_P02 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100501418 | 501418 | Water | G100 | Gate 100 | 2021-12-03 | 2022-05-31 | 2021_22_P09 | 2022_23_P02 | 2021_22_Q3 | 2022_23_Q1
G100501421 | 501421 | Water | G100 | Gate 100 | 2021-04-01 | 2021-06-11 | 2021_22_P01 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100501579 | 501579 | Wastewater | G100 | Gate 100 | 2022-12-30 | 2023-05-12 | 2022_23_P09 | 2023_24_P02 | 2022_23_Q3 | 2023_24_Q1
G100501592 | 501592 | Wastewater | G100 | Gate 100 | 2021-05-30 | 2021-05-20 | 2021_22_P02 | 2021_22_P02 | 2021_22_Q1 | 2021_22_Q1
G100501593 | 501593 | Wastewater | G100 | Gate 100 | 2021-04-01 | 2021-04-01 | 2021_22_P01 | 2021_22_P01 | 2021_22_Q1 | 2021_22_Q1
G100501632 | 501632 | Support Services | G100 | Gate 100 | 2021-05-07 | 2021-06-02 | 2021_22_P02 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100501635 | 501635 | Water | G100 | Gate 100 | 2021-06-30 | 2021-06-21 | 2021_22_P03 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100501436 | 501436 | Water | G100 | Gate 100 | 2021-04-28 | 2021-06-18 | 2021_22_P01 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100501554 | 501554 | Water | G100 | Gate 100 | 2022-11-10 | 2022-08-10 | 2022_23_P08 | 2022_23_P05 | 2022_23_Q3 | 2022_23_Q2
G100501599 | 501599 | Wastewater | G100 | Gate 100 | 2021-06-30 | 2022-04-22 | 2021_22_P03 | 2022_23_P01 | 2021_22_Q1 | 2022_23_Q1
G100501600 | 501600 | Water | G100 | Gate 100 | 2021-07-12 | 2021-09-24 | 2021_22_P04 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100501639 | 501639 | Support Services | G100 | Gate 100 | 2021-06-15 | 2021-09-06 | 2021_22_P03 | 2021_22_P06 | 2021_22_Q1 | 2021_22_Q2
G100501512 | 501512 | Wastewater | G100 | Gate 100 | 2024-04-25 | 2024-01-26 | 2024_25_P01 | 2023_24_P10 | 2024_25_Q1 | 2023_24_Q4
G100501518 | 501518 | Wastewater | G100 | Gate 100 | 2021-09-30 | 2021-12-20 | 2021_22_P06 | 2021_22_P09 | 2021_22_Q2 | 2021_22_Q3
G100501666 | 501666 | Water | G100 | Gate 100 | 2021-06-25 | 2022-04-21 | 2021_22_P03 | 2022_23_P01 | 2021_22_Q1 | 2022_23_Q1
G100501683 | 501683 | Wastewater | G100 | Gate 100 | 2021-11-30 | 2022-08-10 | 2021_22_P08 | 2022_23_P05 | 2021_22_Q3 | 2022_23_Q2
G100501720 | 501720 | Wastewater | G100 | Gate 100 | 2021-08-30 | 2021-06-28 | 2021_22_P05 | 2021_22_P03 | 2021_22_Q2 | 2021_22_Q1
G100501739 | 501739 | Wastewater | G100 | Gate 100 | 2021-07-22 | 2022-05-05 | 2021_22_P04 | 2022_23_P02 | 2021_22_Q2 | 2022_23_Q1
G100501898 | 501898 | Support Services | G100 | Gate 100 | 2021-09-29 | 2022-04-25 | 2021_22_P06 | 2022_23_P01 | 2021_22_Q2 | 2022_23_Q1
G100501818 | 501818 | Support Services | G100 | Gate 100 | 2021-07-28 | 2021-11-30 | 2021_22_P04 | 2021_22_P08 | 2021_22_Q2 | 2021_22_Q3
G100501829 | 501829 | Wastewater | G100 | Gate 100 | 2021-12-11 | 2022-06-14 | 2021_22_P09 | 2022_23_P03 | 2021_22_Q3 | 2022_23_Q1
G100502132 | 502132 | Water | G100 | Gate 100 | 2023-01-20 | 2023-04-13 | 2022_23_P10 | 2023_24_P01 | 2022_23_Q4 | 2023_24_Q1
G100502246 | 502246 | Water | G100 | Gate 100 | 2021-07-12 | 2021-12-20 | 2021_22_P04 | 2021_22_P09 | 2021_22_Q2 | 2021_22_Q3
G100502267 | 502267 | Wastewater | G100 | Gate 100 | 2021-04-22 | 2021-03-22 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100502268 | 502268 | Wastewater | G100 | Gate 100 | 2022-04-14 | 2023-01-31 | 2022_23_P01 | 2022_23_P10 | 2022_23_Q1 | 2022_23_Q4
G100502269 | 502269 | Wastewater | G100 | Gate 100 | 2021-04-12 | 2021-03-22 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100502282 | 502282 | Water | G100 | Gate 100 | 2023-09-14 | 2023-06-16 | 2023_24_P06 | 2023_24_P03 | 2023_24_Q2 | 2023_24_Q1
G100502212 | 502212 | Wastewater | G100 | Gate 100 | 2023-10-24 | 2023-07-26 | 2023_24_P07 | 2023_24_P04 | 2023_24_Q3 | 2023_24_Q2
G100502231 | 502231 | Wastewater | G100 | Gate 100 | 2021-04-02 | 2021-03-22 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100502329 | 502329 | Water | G100 | Gate 100 | 2021-08-09 | 2021-08-24 | 2021_22_P05 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2
G100502280 | 502280 | Wastewater | G100 | Gate 100 | 2022-03-07 | 2022-08-19 | 2021_22_P12 | 2022_23_P05 | 2021_22_Q4 | 2022_23_Q2
G100502281 | 502281 | Wastewater | G100 | Gate 100 | 2021-11-19 | 2022-04-15 | 2021_22_P08 | 2022_23_P01 | 2021_22_Q3 | 2022_23_Q1
G100502342 | 502342 | Wastewater | G100 | Gate 100 | 2022-07-07 | 2022-06-01 | 2022_23_P04 | 2022_23_P03 | 2022_23_Q2 | 2022_23_Q1
G100502380 | 502380 | Water | G100 | Gate 100 | 2021-04-01 | 2021-08-17 | 2021_22_P01 | 2021_22_P05 | 2021_22_Q1 | 2021_22_Q2
G100502382 | 502382 | Water | G100 | Gate 100 | 2021-10-29 | 2022-03-24 | 2021_22_P07 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G100502383 | 502383 | Water | G100 | Gate 100 | 2021-12-20 | 2022-01-31 | 2021_22_P09 | 2021_22_P10 | 2021_22_Q3 | 2021_22_Q4
G100502584 | 502584 | Wastewater | G100 | Gate 100 | 2021-04-01 | 2021-03-24 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100502392 | 502392 | Water | G100 | Gate 100 | 2022-03-01 | 2022-03-22 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G100502578 | 502578 | Wastewater | G100 | Gate 100 | 2022-04-27 | 2022-03-31 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G100502412 | 502412 | Water | G100 | Gate 100 | 2021-06-25 | 2021-08-03 | 2021_22_P03 | 2021_22_P05 | 2021_22_Q1 | 2021_22_Q2
G100502648 | 502648 | Water | G100 | Gate 100 | 2022-06-01 | 2022-10-21 | 2022_23_P03 | 2022_23_P07 | 2022_23_Q1 | 2022_23_Q3
G100502649 | 502649 | Water | G100 | Gate 100 | 2023-01-30 | 2023-04-28 | 2022_23_P10 | 2023_24_P01 | 2022_23_Q4 | 2023_24_Q1
G100502650 | 502650 | Water | G100 | Gate 100 | 2022-06-16 | 2022-09-08 | 2022_23_P03 | 2022_23_P06 | 2022_23_Q1 | 2022_23_Q2
G100502563 | 502563 | Water | G100 | Gate 100 | 2022-01-18 | 2021-12-16 | 2021_22_P10 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3
G100502743 | 502743 | Wastewater | G100 | Gate 100 | 2022-06-13 | 2022-05-06 | 2022_23_P03 | 2022_23_P02 | 2022_23_Q1 | 2022_23_Q1
G100502765 | 502765 | Wastewater | G100 | Gate 100 | 2021-10-26 | 2021-09-21 | 2021_22_P07 | 2021_22_P06 | 2021_22_Q3 | 2021_22_Q2
G100502740 | 502740 | Wastewater | G100 | Gate 100 | 2021-08-27 | 2021-06-02 | 2021_22_P05 | 2021_22_P03 | 2021_22_Q2 | 2021_22_Q1
G100502741 | 502741 | Wastewater | G100 | Gate 100 | 2021-07-22 | 2021-06-02 | 2021_22_P04 | 2021_22_P03 | 2021_22_Q2 | 2021_22_Q1
G100502742 | 502742 | Wastewater | G100 | Gate 100 | 2021-10-14 | 2021-08-24 | 2021_22_P07 | 2021_22_P05 | 2021_22_Q3 | 2021_22_Q2
G100502605 | 502605 | Water | G100 | Gate 100 | 2021-09-30 | 2021-09-30 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100502651 | 502651 | Water | G100 | Gate 100 | 2022-07-19 | 2022-12-14 | 2022_23_P04 | 2022_23_P09 | 2022_23_Q2 | 2022_23_Q3
G100502652 | 502652 | Water | G100 | Gate 100 | 2023-01-19 | 2022-10-21 | 2022_23_P10 | 2022_23_P07 | 2022_23_Q4 | 2022_23_Q3
G100502600 | 502600 | Water | G100 | Gate 100 | 2022-01-10 | 2023-01-11 | 2021_22_P10 | 2022_23_P10 | 2021_22_Q4 | 2022_23_Q4
G100502827 | 502827 | Wastewater | G100 | Gate 100 | 2022-01-13 | 2022-03-30 | 2021_22_P10 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G100502808 | 502808 | Water | G100 | Gate 100 | 2021-11-02 | 2021-12-01 | 2021_22_P08 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
G100502747 | 502747 | Wastewater | G100 | Gate 100 | 2021-09-30 | 2021-09-21 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100502748 | 502748 | Wastewater | G100 | Gate 100 | 2022-07-24 | 2022-01-27 | 2022_23_P04 | 2021_22_P10 | 2022_23_Q2 | 2021_22_Q4
G100502749 | 502749 | Wastewater | G100 | Gate 100 | 2022-05-10 | 2022-04-28 | 2022_23_P02 | 2022_23_P01 | 2022_23_Q1 | 2022_23_Q1
G100502772 | 502772 | Water | G100 | Gate 100 | 2021-05-11 | 2021-03-31 | 2021_22_P02 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100502853 | 502853 | Water | G100 | Gate 100 | 2022-10-26 | 2022-07-28 | 2022_23_P07 | 2022_23_P04 | 2022_23_Q3 | 2022_23_Q2
G100502895 | 502895 | Wastewater | G100 | Gate 100 | 2022-09-18 | 2022-09-23 | 2022_23_P06 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2
G100502896 | 502896 | Water | G100 | Gate 100 | 2021-10-12 | 2021-11-29 | 2021_22_P07 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
G100502780 | 502780 | Wastewater | G100 | Gate 100 | 2021-06-11 | 2021-06-28 | 2021_22_P03 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100502783 | 502783 | Water | G100 | Gate 100 | 2022-06-23 | 2023-06-15 | 2022_23_P03 | 2023_24_P03 | 2022_23_Q1 | 2023_24_Q1
G100502857 | 502857 | Water | G100 | Gate 100 | 2023-06-20 | 2023-03-22 | 2023_24_P03 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4
G100502866 | 502866 | Wastewater | G100 | Gate 100 | 2022-01-14 | 2022-02-17 | 2021_22_P10 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4
G100502867 | 502867 | Water | G100 | Gate 100 | 2022-01-14 | 2021-12-08 | 2021_22_P10 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3
G100502934 | 502934 | Wastewater | G100 | Gate 100 | 2021-10-03 | 2021-11-22 | 2021_22_P07 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
G100502940 | 502940 | Water | G100 | Gate 100 | 2021-10-04 | 2022-09-16 | 2021_22_P07 | 2022_23_P06 | 2021_22_Q3 | 2022_23_Q2
G100502943 | 502943 | Wastewater | G100 | Gate 100 | 2021-09-06 | 2022-05-30 | 2021_22_P06 | 2022_23_P02 | 2021_22_Q2 | 2022_23_Q1
G100502944 | 502944 | Wastewater | G100 | Gate 100 | 2021-09-06 | 2023-01-18 | 2021_22_P06 | 2022_23_P10 | 2021_22_Q2 | 2022_23_Q4
G100502945 | 502945 | Wastewater | G100 | Gate 100 | 2021-09-29 | 2023-05-26 | 2021_22_P06 | 2023_24_P02 | 2021_22_Q2 | 2023_24_Q1
G100502946 | 502946 | Wastewater | G100 | Gate 100 | 2021-12-03 | 2022-10-14 | 2021_22_P09 | 2022_23_P07 | 2021_22_Q3 | 2022_23_Q3
G100502947 | 502947 | Wastewater | G100 | Gate 100 | 2021-07-26 | 2021-09-29 | 2021_22_P04 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100502949 | 502949 | Wastewater | G100 | Gate 100 | 2022-03-01 | 2024-02-19 | 2021_22_P12 | 2023_24_P11 | 2021_22_Q4 | 2023_24_Q4
G100502958 | 502958 | Wastewater | G100 | Gate 100 | 2023-01-03 | 2023-03-24 | 2022_23_P10 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4
G100503045 | 503045 | Wastewater | G100 | Gate 100 | 2021-07-02 | 2021-08-26 | 2021_22_P04 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2
G100503050 | 503050 | Water | G100 | Gate 100 | 2022-08-25 | 2022-10-12 | 2022_23_P05 | 2022_23_P07 | 2022_23_Q2 | 2022_23_Q3
G100503072 | 503072 | Water | G100 | Gate 100 | 2022-09-30 | 2022-09-15 | 2022_23_P06 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2
G100503119 | 503119 | Support Services | G100 | Gate 100 | 2021-07-28 | 2021-11-25 | 2021_22_P04 | 2021_22_P08 | 2021_22_Q2 | 2021_22_Q3
G100503120 | 503120 | Support Services | G100 | Gate 100 | 2021-07-28 | 2021-12-22 | 2021_22_P04 | 2021_22_P09 | 2021_22_Q2 | 2021_22_Q3
G100503121 | 503121 | Support Services | G100 | Gate 100 | 2021-07-28 | 2022-01-20 | 2021_22_P04 | 2021_22_P10 | 2021_22_Q2 | 2021_22_Q4
G100503177 | 503177 | Wastewater | G100 | Gate 100 | 2021-11-17 | 2021-10-26 | 2021_22_P08 | 2021_22_P07 | 2021_22_Q3 | 2021_22_Q3
G100503094 | 503094 | Water | G100 | Gate 100 | 2021-04-01 | 2021-03-31 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100503110 | 503110 | Water | G100 | Gate 100 | 2023-05-27 | 2023-04-21 | 2023_24_P02 | 2023_24_P01 | 2023_24_Q1 | 2023_24_Q1
G100503162 | 503162 | Water | G100 | Gate 100 | 2022-08-09 | 2023-03-24 | 2022_23_P05 | 2022_23_P12 | 2022_23_Q2 | 2022_23_Q4
G100503200 | 503200 | Water | G100 | Gate 100 | 2021-06-17 | 2021-09-03 | 2021_22_P03 | 2021_22_P06 | 2021_22_Q1 | 2021_22_Q2
G100503229 | 503229 | Wastewater | G100 | Gate 100 | 2021-12-10 | 2021-12-20 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
G100503230 | 503230 | Wastewater | G100 | Gate 100 | 2023-06-20 | 2023-03-22 | 2023_24_P03 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4
G100503234 | 503234 | Water | G100 | Gate 100 | 2021-12-20 | 2021-12-06 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
G100503235 | 503235 | Water | G100 | Gate 100 | 2022-11-30 | 2023-02-27 | 2022_23_P08 | 2022_23_P11 | 2022_23_Q3 | 2022_23_Q4
G100503236 | 503236 | Water | G100 | Gate 100 | 2021-04-06 | 2021-03-31 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100503239 | 503239 | Water | G100 | Gate 100 | 2021-09-01 | 2022-03-25 | 2021_22_P06 | 2021_22_P12 | 2021_22_Q2 | 2021_22_Q4
G100503249 | 503249 | Water | G100 | Gate 100 | 2021-04-21 | 2022-03-10 | 2021_22_P01 | 2021_22_P12 | 2021_22_Q1 | 2021_22_Q4
G100503256 | 503256 | Water | G100 | Gate 100 | 2021-06-29 | 2021-07-29 | 2021_22_P03 | 2021_22_P04 | 2021_22_Q1 | 2021_22_Q2
G100503257 | 503257 | Water | G100 | Gate 100 | 2021-04-30 | 2021-03-31 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100503250 | 503250 | Water | G100 | Gate 100 | 2021-07-30 | 2021-07-29 | 2021_22_P04 | 2021_22_P04 | 2021_22_Q2 | 2021_22_Q2
G100503194 | 503194 | Water | G100 | Gate 100 | 2021-04-27 | 2021-06-30 | 2021_22_P01 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100503195 | 503195 | Water | G100 | Gate 100 | 2022-08-30 | 2021-09-30 | 2022_23_P05 | 2021_22_P06 | 2022_23_Q2 | 2021_22_Q2
G100503197 | 503197 | Water | G100 | Gate 100 | 2021-09-30 | 2021-09-30 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100503198 | 503198 | Water | G100 | Gate 100 | 2021-09-30 | 2021-09-30 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100503199 | 503199 | Water | G100 | Gate 100 | 2021-09-30 | 2021-09-30 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100503269 | 503269 | Wastewater | G100 | Gate 100 | 2022-05-18 | 2022-08-12 | 2022_23_P02 | 2022_23_P05 | 2022_23_Q1 | 2022_23_Q2
G100503291 | 503291 | Support Services | G100 | Gate 100 | 2021-07-28 | 2022-04-05 | 2021_22_P04 | 2022_23_P01 | 2021_22_Q2 | 2022_23_Q1
G100503336 | 503336 | Water | G100 | Gate 100 | 2022-11-01 | 2023-03-30 | 2022_23_P08 | 2022_23_P12 | 2022_23_Q3 | 2022_23_Q4
G100503362 | 503362 | Wastewater | G100 | Gate 100 | 2021-09-01 | 2022-10-03 | 2021_22_P06 | 2022_23_P07 | 2021_22_Q2 | 2022_23_Q3
G100503393 | 503393 | Wastewater | G100 | Gate 100 | 2021-11-03 | 2022-01-17 | 2021_22_P08 | 2021_22_P10 | 2021_22_Q3 | 2021_22_Q4
G100503408 | 503408 | Water | G100 | Gate 100 | 2022-11-30 | 2022-09-01 | 2022_23_P08 | 2022_23_P06 | 2022_23_Q3 | 2022_23_Q2
G100503412 | 503412 | Water | G100 | Gate 100 | 2021-09-30 | 2021-09-30 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100503413 | 503413 | Water | G100 | Gate 100 | 2021-09-30 | 2021-09-21 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100503415 | 503415 | Wastewater | G100 | Gate 100 | 2022-04-22 | 2023-03-23 | 2022_23_P01 | 2022_23_P12 | 2022_23_Q1 | 2022_23_Q4
G100503418 | 503418 | Wastewater | G100 | Gate 100 | 2021-09-30 | 2021-10-12 | 2021_22_P06 | 2021_22_P07 | 2021_22_Q2 | 2021_22_Q3
G100503421 | 503421 | Water | G100 | Gate 100 | 2023-04-05 | 2022-08-12 | 2023_24_P01 | 2022_23_P05 | 2023_24_Q1 | 2022_23_Q2
G100503434 | 503434 | Water | G100 | Gate 100 | 2022-03-31 | 2022-05-19 | 2021_22_P12 | 2022_23_P02 | 2021_22_Q4 | 2022_23_Q1
G100503441 | 503441 | Wastewater | G100 | Gate 100 | 2023-08-20 | 2023-05-22 | 2023_24_P05 | 2023_24_P02 | 2023_24_Q2 | 2023_24_Q1
G100503543 | 503543 | Wastewater | G100 | Gate 100 | 2021-09-21 | 2022-03-30 | 2021_22_P06 | 2021_22_P12 | 2021_22_Q2 | 2021_22_Q4
G100503545 | 503545 | Wastewater | G100 | Gate 100 | 2021-09-21 | 2022-02-16 | 2021_22_P06 | 2021_22_P11 | 2021_22_Q2 | 2021_22_Q4
G100503546 | 503546 | Wastewater | G100 | Gate 100 | 2021-09-21 | 2021-08-24 | 2021_22_P06 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2
G100503562 | 503562 | Water | G100 | Gate 100 | 2021-09-10 | 2022-01-31 | 2021_22_P06 | 2021_22_P10 | 2021_22_Q2 | 2021_22_Q4
G100503564 | 503564 | Wastewater | G100 | Gate 100 | 2022-02-03 | 2022-09-28 | 2021_22_P11 | 2022_23_P06 | 2021_22_Q4 | 2022_23_Q2
G100503571 | 503571 | Wastewater | G100 | Gate 100 | 2022-03-31 | 2022-10-03 | 2021_22_P12 | 2022_23_P07 | 2021_22_Q4 | 2022_23_Q3
G100503587 | 503587 | Water | G100 | Gate 100 | 2021-10-30 | 2022-05-06 | 2021_22_P07 | 2022_23_P02 | 2021_22_Q3 | 2022_23_Q1
G100503595 | 503595 | Water | G100 | Gate 100 | 2022-03-29 | 2023-06-21 | 2021_22_P12 | 2023_24_P03 | 2021_22_Q4 | 2023_24_Q1
G100503617 | 503617 | Water | G100 | Gate 100 | 2022-03-17 | 2022-03-28 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G100503630 | 503630 | Water | G100 | Gate 100 | 2021-09-30 | 2021-09-30 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100503631 | 503631 | Water | G100 | Gate 100 | 2022-01-27 | 2022-03-24 | 2021_22_P10 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G100503632 | 503632 | Water | G100 | Gate 100 | 2022-07-05 | 2022-09-30 | 2022_23_P04 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2
G100503678 | 503678 | Water | G100 | Gate 100 | 2024-01-16 | 2023-10-18 | 2023_24_P10 | 2023_24_P07 | 2023_24_Q4 | 2023_24_Q3
G100503686 | 503686 | Water | G100 | Gate 100 | 2023-08-31 | 2023-04-06 | 2023_24_P05 | 2023_24_P01 | 2023_24_Q2 | 2023_24_Q1
G100503701 | 503701 | Wastewater | G100 | Gate 100 | 2021-05-14 | 2021-05-28 | 2021_22_P02 | 2021_22_P02 | 2021_22_Q1 | 2021_22_Q1
G100503716 | 503716 | Water | G100 | Gate 100 | 2022-04-30 | 2021-12-02 | 2022_23_P01 | 2021_22_P09 | 2022_23_Q1 | 2021_22_Q3
G100503726 | 503726 | Water | G100 | Gate 100 | 2021-10-06 | 2021-11-29 | 2021_22_P07 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
G100503727 | 503727 | Water | G100 | Gate 100 | 2022-02-15 | 2022-01-31 | 2021_22_P11 | 2021_22_P10 | 2021_22_Q4 | 2021_22_Q4
G100503728 | 503728 | Water | G100 | Gate 100 | 2021-06-30 | 2021-06-09 | 2021_22_P03 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100503730 | 503730 | Water | G100 | Gate 100 | 2023-10-26 | 2023-07-28 | 2023_24_P07 | 2023_24_P04 | 2023_24_Q3 | 2023_24_Q2
G100503731 | 503731 | Water | G100 | Gate 100 | 2022-08-23 | 2023-05-30 | 2022_23_P05 | 2023_24_P02 | 2022_23_Q2 | 2023_24_Q1
G100503733 | 503733 | Water | G100 | Gate 100 | 2022-05-31 | 2022-03-14 | 2022_23_P02 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G100503761 | 503761 | Water | G100 | Gate 100 | 2023-06-19 | 2023-03-17 | 2023_24_P03 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4
G100503860 | 503860 | Wastewater | G100 | Gate 100 | 2022-07-28 | 2022-06-20 | 2022_23_P04 | 2022_23_P03 | 2022_23_Q2 | 2022_23_Q1
G100504434 | 504434 | Water | G100 | Gate 100 | 2021-11-18 | 2021-11-29 | 2021_22_P08 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
G100504995 | 504995 | Water | G100 | Gate 100 | 2024-10-24 | 2024-07-26 | 2024_25_P07 | 2024_25_P04 | 2024_25_Q3 | 2024_25_Q2
G100505032 | 505032 | Water | G100 | Gate 100 | 2021-12-10 | 2022-03-18 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G100505053 | 505053 | Wastewater | G100 | Gate 100 | 2023-08-02 | 2023-08-04 | 2023_24_P05 | 2023_24_P05 | 2023_24_Q2 | 2023_24_Q2
G100505384 | 505384 | Water | G100 | Gate 100 | 2024-01-19 | 2023-12-15 | 2023_24_P10 | 2023_24_P09 | 2023_24_Q4 | 2023_24_Q3
G100505447 | 505447 | Water | G100 | Gate 100 | 2023-06-11 | 2023-06-13 | 2023_24_P03 | 2023_24_P03 | 2023_24_Q1 | 2023_24_Q1
G100505504 | 505504 | Water | G100 | Gate 100 | 2022-12-05 | 2023-01-16 | 2022_23_P09 | 2022_23_P10 | 2022_23_Q3 | 2022_23_Q4
G100505641 | 505641 | Wastewater | G100 | Gate 100 | 2022-12-14 | 2023-04-12 | 2022_23_P09 | 2023_24_P01 | 2022_23_Q3 | 2023_24_Q1
G100505693 | 505693 | Water | G100 | Gate 100 | 2024-02-26 | 2023-06-08 | 2023_24_P11 | 2023_24_P03 | 2023_24_Q4 | 2023_24_Q1
G100506029 | 506029 | Water | G100 | Gate 100 | 2024-06-19 | 2024-03-21 | 2024_25_P03 | 2023_24_P12 | 2024_25_Q1 | 2023_24_Q4
G100506032 | 506032 | Water | G100 | Gate 100 | 2024-07-29 | 2024-04-30 | 2024_25_P04 | 2024_25_P01 | 2024_25_Q2 | 2024_25_Q1
G100506228 | 506228 | Water | G100 | Gate 100 | 2023-07-02 | 2023-05-26 | 2023_24_P04 | 2023_24_P02 | 2023_24_Q2 | 2023_24_Q1
G100506232 | 506232 | Water | G100 | Gate 100 | 2023-07-02 | 2023-01-27 | 2023_24_P04 | 2022_23_P10 | 2023_24_Q2 | 2022_23_Q4
G100506234 | 506234 | Water | G100 | Gate 100 | 2023-07-02 | 2022-07-22 | 2023_24_P04 | 2022_23_P04 | 2023_24_Q2 | 2022_23_Q2
G100506608 | 506608 | Water | G100 | Gate 100 | 2023-04-26 | 2023-01-26 | 2023_24_P01 | 2022_23_P10 | 2023_24_Q1 | 2022_23_Q4
G100506684 | 506684 | Water | G100 | Gate 100 | 2023-03-24 | 2023-01-13 | 2022_23_P12 | 2022_23_P10 | 2022_23_Q4 | 2022_23_Q4
G100506779 | 506779 | Water | G100 | Gate 100 | 2024-01-18 | 2023-10-20 | 2023_24_P10 | 2023_24_P07 | 2023_24_Q4 | 2023_24_Q3
G100506864 | 506864 | Water | G100 | Gate 100 | 2023-03-01 | 2024-06-20 | 2022_23_P12 | 2024_25_P03 | 2022_23_Q4 | 2024_25_Q1
G100506865 | 506865 | Wastewater | G100 | Gate 100 | 2023-03-01 | 2024-06-20 | 2022_23_P12 | 2024_25_P03 | 2022_23_Q4 | 2024_25_Q1
G100506896 | 506896 | Support Services | G100 | Gate 100 | 2021-09-30 | 2022-01-18 | 2021_22_P06 | 2021_22_P10 | 2021_22_Q2 | 2021_22_Q4
G100507057 | 507057 | Water | G100 | Gate 100 | 2023-12-17 | 2023-09-18 | 2023_24_P09 | 2023_24_P06 | 2023_24_Q3 | 2023_24_Q2
G100507173 | 507173 | Support Services | G100 | Gate 100 | 2021-08-02 | 2021-12-21 | 2021_22_P05 | 2021_22_P09 | 2021_22_Q2 | 2021_22_Q3
G100507186 | 507186 | Water | G100 | Gate 100 | 2023-07-16 | 2023-04-17 | 2023_24_P04 | 2023_24_P01 | 2023_24_Q2 | 2023_24_Q1
G100507189 | 507189 | Water | G100 | Gate 100 | 2023-12-18 | 2023-09-19 | 2023_24_P09 | 2023_24_P06 | 2023_24_Q3 | 2023_24_Q2
G100507455 | 507455 | Water | G100 | Gate 100 | 2024-04-30 | 2024-04-30 | 2024_25_P01 | 2024_25_P01 | 2024_25_Q1 | 2024_25_Q1
G100507813 | 507813 | Water | G100 | Gate 100 | 2022-04-25 | 2022-03-31 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G100507860 | 507860 | Water | G100 | Gate 100 | 2022-05-15 | 2021-12-15 | 2022_23_P02 | 2021_22_P09 | 2022_23_Q1 | 2021_22_Q3
G100507933 | 507933 | Wastewater | G100 | Gate 100 | 2022-11-16 | 2022-11-24 | 2022_23_P08 | 2022_23_P08 | 2022_23_Q3 | 2022_23_Q3
G100508109 | 508109 | Support Services | G100 | Gate 100 | 2021-05-14 | 2021-12-07 | 2021_22_P02 | 2021_22_P09 | 2021_22_Q1 | 2021_22_Q3
G100508601 | 508601 | Wastewater | G100 | Gate 100 | 2022-06-12 | 2022-06-17 | 2022_23_P03 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1
G100509283 | 509283 | Water | G100 | Gate 100 | 2022-06-04 | 2022-06-03 | 2022_23_P03 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1
G100510727 | 510727 | Support Services | G100 | Gate 100 | 2022-11-04 | 2022-06-07 | 2022_23_P08 | 2022_23_P03 | 2022_23_Q3 | 2022_23_Q1
G100511344 | 511344 | Support Services | G100 | Gate 100 | 2024-04-17 | 2022-07-29 | 2024_25_P01 | 2022_23_P04 | 2024_25_Q1 | 2022_23_Q2
G100512600 | 512600 | Water | G100 | Gate 100 | 2023-08-24 | 2023-05-26 | 2023_24_P05 | 2023_24_P02 | 2023_24_Q2 | 2023_24_Q1
G100512711 | 512711 | Water | G100 | Gate 100 | 2023-09-10 | 2023-06-12 | 2023_24_P06 | 2023_24_P03 | 2023_24_Q2 | 2023_24_Q1
G100512749 | 512749 | Water | G100 | Gate 100 | 2023-11-30 | 2023-09-01 | 2023_24_P08 | 2023_24_P06 | 2023_24_Q3 | 2023_24_Q2
G100513312 | 513312 | CE&FS | G100 | Gate 100 | 2027-09-16 | 2027-06-18 | 2027_28_P06 | 2027_28_P03 | 2027_28_Q2 | 2027_28_Q1
G100513461 | 513461 | Support Services | G100 | Gate 100 | 2022-08-21 | 2022-07-15 | 2022_23_P05 | 2022_23_P04 | 2022_23_Q2 | 2022_23_Q2
G100513832 | 513832 | Support Services | G100 | Gate 100 | 2022-03-31 | 2022-03-28 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G100513923 | 513923 | Water | G100 | Gate 100 | 2023-07-02 | 2023-07-03 | 2023_24_P04 | 2023_24_P04 | 2023_24_Q2 | 2023_24_Q2
G100515505 | 515505 | Water | G100 | Gate 100 | 2022-10-19 | 2022-10-07 | 2022_23_P07 | 2022_23_P07 | 2022_23_Q3 | 2022_23_Q3
G110046172 | 046172 | Water | G110 | Gate 110 | 2022-06-02 | 2022-06-29 | 2022_23_P03 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1
G110400324 | 400324 | Water | G110 | Gate 110 | 2024-01-13 | 2023-09-06 | 2023_24_P10 | 2023_24_P06 | 2023_24_Q4 | 2023_24_Q2
G110401687 | 401687 | Wastewater | G110 | Gate 110 | 2022-06-22 | 2022-11-02 | 2022_23_P03 | 2022_23_P08 | 2022_23_Q1 | 2022_23_Q3
G110401668 | 401668 | Wastewater | G110 | Gate 110 | 2022-06-21 | 2022-12-14 | 2022_23_P03 | 2022_23_P09 | 2022_23_Q1 | 2022_23_Q3
G110401685 | 401685 | Wastewater | G110 | Gate 110 | 2022-06-21 | 2022-11-02 | 2022_23_P03 | 2022_23_P08 | 2022_23_Q1 | 2022_23_Q3
G110401705 | 401705 | Wastewater | G110 | Gate 110 | 2022-07-25 | 2023-01-25 | 2022_23_P04 | 2022_23_P10 | 2022_23_Q2 | 2022_23_Q4
G110401795 | 401795 | Wastewater | G110 | Gate 110 | 2022-04-06 | 2022-02-15 | 2022_23_P01 | 2021_22_P11 | 2022_23_Q1 | 2021_22_Q4
G110402197 | 402197 | Wastewater | G110 | Gate 110 | 2022-02-09 | 2022-02-01 | 2021_22_P11 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4
G110402949 | 402949 | Wastewater | G110 | Gate 110 | 2023-07-22 | 2022-09-21 | 2023_24_P04 | 2022_23_P06 | 2023_24_Q2 | 2022_23_Q2
G110403097 | 403097 | Wastewater | G110 | Gate 110 | 2021-11-26 | 2021-12-09 | 2021_22_P08 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
G110403098 | 403098 | Wastewater | G110 | Gate 110 | 2022-09-01 | 2022-07-27 | 2022_23_P06 | 2022_23_P04 | 2022_23_Q2 | 2022_23_Q2
G110403100 | 403100 | Wastewater | G110 | Gate 110 | 2022-05-22 | 2022-03-30 | 2022_23_P02 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110403101 | 403101 | Wastewater | G110 | Gate 110 | 2022-05-25 | 2022-06-15 | 2022_23_P02 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1
G110403102 | 403102 | Wastewater | G110 | Gate 110 | 2022-05-25 | 2022-06-15 | 2022_23_P02 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1
G110403103 | 403103 | Wastewater | G110 | Gate 110 | 2022-06-27 | 2021-08-25 | 2022_23_P03 | 2021_22_P05 | 2022_23_Q1 | 2021_22_Q2
G110403104 | 403104 | Wastewater | G110 | Gate 110 | 2022-06-02 | 2022-06-15 | 2022_23_P03 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1
G110403106 | 403106 | Wastewater | G110 | Gate 110 | 2023-11-01 | 2023-01-25 | 2023_24_P08 | 2022_23_P10 | 2023_24_Q3 | 2022_23_Q4
G110403090 | 403090 | Water | G110 | Gate 110 | 2022-03-31 | 2022-04-06 | 2021_22_P12 | 2022_23_P01 | 2021_22_Q4 | 2022_23_Q1
G110403238 | 403238 | Wastewater | G110 | Gate 110 | 2022-05-17 | 2022-06-01 | 2022_23_P02 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1
G110403127 | 403127 | Water | G110 | Gate 110 | 2023-05-17 | 2023-07-12 | 2023_24_P02 | 2023_24_P04 | 2023_24_Q1 | 2023_24_Q2
G110403146 | 403146 | Water | G110 | Gate 110 | 2021-06-16 | 2021-07-01 | 2021_22_P03 | 2021_22_P04 | 2021_22_Q1 | 2021_22_Q2
G110403321 | 403321 | Wastewater | G110 | Gate 110 | 2023-05-28 | 2022-10-19 | 2023_24_P02 | 2022_23_P07 | 2023_24_Q1 | 2022_23_Q3
G110403532 | 403532 | Water | G110 | Gate 110 | 2022-07-02 | 2022-03-30 | 2022_23_P04 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4
G110403605 | 403605 | Water | G110 | Gate 110 | 2021-11-29 | 2022-01-27 | 2021_22_P08 | 2021_22_P10 | 2021_22_Q3 | 2021_22_Q4
G110403716 | 403716 | Wastewater | G110 | Gate 110 | 2023-11-19 | 2023-06-14 | 2023_24_P08 | 2023_24_P03 | 2023_24_Q3 | 2023_24_Q1
G110403658 | 403658 | Water | G110 | Gate 110 | 2023-07-01 | 2023-09-06 | 2023_24_P04 | 2023_24_P06 | 2023_24_Q2 | 2023_24_Q2
G110403923 | 403923 | Wastewater | G110 | Gate 110 | 2023-03-31 | 2023-02-22 | 2022_23_P12 | 2022_23_P11 | 2022_23_Q4 | 2022_23_Q4
G110403781 | 403781 | Wastewater | G110 | Gate 110 | 2022-06-17 | 2022-01-18 | 2022_23_P03 | 2021_22_P10 | 2022_23_Q1 | 2021_22_Q4
G110403782 | 403782 | Wastewater | G110 | Gate 110 | 2024-01-26 | 2023-10-04 | 2023_24_P10 | 2023_24_P07 | 2023_24_Q4 | 2023_24_Q3
G110403902 | 403902 | Wastewater | G110 | Gate 110 | 2022-08-23 | 2022-10-24 | 2022_23_P05 | 2022_23_P07 | 2022_23_Q2 | 2022_23_Q3
G110403917 | 403917 | Water | G110 | Gate 110 | 2022-06-29 | 2022-03-31 | 2022_23_P03 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110404082 | 404082 | Water | G110 | Gate 110 | 2022-06-11 | 2021-11-10 | 2022_23_P03 | 2021_22_P08 | 2022_23_Q1 | 2021_22_Q3
G110403934 | 403934 | Wastewater | G110 | Gate 110 | 2023-04-04 | 2022-10-05 | 2023_24_P01 | 2022_23_P07 | 2023_24_Q1 | 2022_23_Q3
G110500060 | 500060 | Water | G110 | Gate 110 | 2022-02-23 | 2021-11-26 | 2021_22_P11 | 2021_22_P08 | 2021_22_Q4 | 2021_22_Q3
G110403967 | 403967 | Wastewater | G110 | Gate 110 | 2025-06-06 | 2024-12-16 | 2025_26_P03 | 2024_25_P09 | 2025_26_Q1 | 2024_25_Q3
G110403968 | 403968 | Wastewater | G110 | Gate 110 | 2021-12-30 | 2022-03-28 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G110403991 | 403991 | Water | G110 | Gate 110 | 2023-10-31 | 2023-10-04 | 2023_24_P07 | 2023_24_P07 | 2023_24_Q3 | 2023_24_Q3
G110403943 | 403943 | Wastewater | G110 | Gate 110 | 2022-08-19 | 2023-01-11 | 2022_23_P05 | 2022_23_P10 | 2022_23_Q2 | 2022_23_Q4
G110403939 | 403939 | Wastewater | G110 | Gate 110 | 2023-02-03 | 2023-02-22 | 2022_23_P11 | 2022_23_P11 | 2022_23_Q4 | 2022_23_Q4
G110403994 | 403994 | Water | G110 | Gate 110 | 2022-11-26 | 2022-12-14 | 2022_23_P08 | 2022_23_P09 | 2022_23_Q3 | 2022_23_Q3
G110500046 | 500046 | Water | G110 | Gate 110 | 2025-05-15 | 2024-10-16 | 2025_26_P02 | 2024_25_P07 | 2025_26_Q1 | 2024_25_Q3
G110404007 | 404007 | Wastewater | G110 | Gate 110 | 2022-11-19 | 2022-02-08 | 2022_23_P08 | 2021_22_P11 | 2022_23_Q3 | 2021_22_Q4
G110404003 | 404003 | Water | G110 | Gate 110 | 2021-12-31 | 2022-09-07 | 2021_22_P09 | 2022_23_P06 | 2021_22_Q3 | 2022_23_Q2
G110403995 | 403995 | Water | G110 | Gate 110 | 2025-07-14 | 2024-11-27 | 2025_26_P04 | 2024_25_P08 | 2025_26_Q2 | 2024_25_Q3
G110403986 | 403986 | Water | G110 | Gate 110 | 2024-01-13 | 2023-11-01 | 2023_24_P10 | 2023_24_P08 | 2023_24_Q4 | 2023_24_Q3
G110404093 | 404093 | Water | G110 | Gate 110 | 2024-05-23 | 2024-03-20 | 2024_25_P02 | 2023_24_P12 | 2024_25_Q1 | 2023_24_Q4
G110404026 | 404026 | Wastewater | G110 | Gate 110 | 2023-04-22 | 2023-09-06 | 2023_24_P01 | 2023_24_P06 | 2023_24_Q1 | 2023_24_Q2
G110404069 | 404069 | Wastewater | G110 | Gate 110 | 2022-01-29 | 2021-11-09 | 2021_22_P10 | 2021_22_P08 | 2021_22_Q4 | 2021_22_Q3
G110500017 | 500017 | Wastewater | G110 | Gate 110 | 2022-11-22 | 2022-07-27 | 2022_23_P08 | 2022_23_P04 | 2022_23_Q3 | 2022_23_Q2
G110500052 | 500052 | Wastewater | G110 | Gate 110 | 2023-04-30 | 2023-04-19 | 2023_24_P01 | 2023_24_P01 | 2023_24_Q1 | 2023_24_Q1
G110500190 | 500190 | Water | G110 | Gate 110 | 2021-12-07 | 2022-03-24 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G110404134 | 404134 | Water | G110 | Gate 110 | 2022-03-18 | 2022-03-31 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G110404135 | 404135 | Water | G110 | Gate 110 | 2023-10-28 | 2024-01-24 | 2023_24_P07 | 2023_24_P10 | 2023_24_Q3 | 2023_24_Q4
G110500068 | 500068 | Wastewater | G110 | Gate 110 | 2022-03-24 | 2021-12-21 | 2021_22_P12 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3
G110500040 | 500040 | Water | G110 | Gate 110 | 2022-01-29 | 2021-12-16 | 2021_22_P10 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3
G110500047 | 500047 | Water | G110 | Gate 110 | 2023-07-08 | 2023-01-26 | 2023_24_P04 | 2022_23_P10 | 2023_24_Q2 | 2022_23_Q4
G110500030 | 500030 | Water | G110 | Gate 110 | 2021-12-30 | 2022-03-10 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G110500154 | 500154 | Wastewater | G110 | Gate 110 | 2021-10-29 | 2021-09-24 | 2021_22_P07 | 2021_22_P06 | 2021_22_Q3 | 2021_22_Q2
G110500206 | 500206 | Water | G110 | Gate 110 | 2021-05-05 | 2021-12-16 | 2021_22_P02 | 2021_22_P09 | 2021_22_Q1 | 2021_22_Q3
G110500207 | 500207 | Water | G110 | Gate 110 | 2022-09-21 | 2022-04-20 | 2022_23_P06 | 2022_23_P01 | 2022_23_Q2 | 2022_23_Q1
G110500211 | 500211 | Water | G110 | Gate 110 | 2021-10-20 | 2022-03-31 | 2021_22_P07 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G110500246 | 500246 | Water | G110 | Gate 110 | 2022-07-23 | 2023-04-05 | 2022_23_P04 | 2023_24_P01 | 2022_23_Q2 | 2023_24_Q1
G110500218 | 500218 | Water | G110 | Gate 110 | 2022-11-16 | 2022-04-01 | 2022_23_P08 | 2022_23_P01 | 2022_23_Q3 | 2022_23_Q1
G110500233 | 500233 | Wastewater | G110 | Gate 110 | 2022-10-15 | 2022-07-27 | 2022_23_P07 | 2022_23_P04 | 2022_23_Q3 | 2022_23_Q2
G110500244 | 500244 | Water | G110 | Gate 110 | 2021-11-19 | 2021-07-30 | 2021_22_P08 | 2021_22_P04 | 2021_22_Q3 | 2021_22_Q2
G110500235 | 500235 | Wastewater | G110 | Gate 110 | 2023-03-04 | 2022-09-07 | 2022_23_P12 | 2022_23_P06 | 2022_23_Q4 | 2022_23_Q2
G110500241 | 500241 | Water | G110 | Gate 110 | 2021-10-26 | 2021-12-21 | 2021_22_P07 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
G110500245 | 500245 | Water | G110 | Gate 110 | 2023-05-18 | 2023-10-12 | 2023_24_P02 | 2023_24_P07 | 2023_24_Q1 | 2023_24_Q3
G110500299 | 500299 | Wastewater | G110 | Gate 110 | 2022-07-21 | 2022-02-11 | 2022_23_P04 | 2021_22_P11 | 2022_23_Q2 | 2021_22_Q4
G110500302 | 500302 | Wastewater | G110 | Gate 110 | 2023-03-31 | 2022-11-16 | 2022_23_P12 | 2022_23_P08 | 2022_23_Q4 | 2022_23_Q3
G110500229 | 500229 | Wastewater | G110 | Gate 110 | 2024-04-27 | 2024-05-21 | 2024_25_P01 | 2024_25_P02 | 2024_25_Q1 | 2024_25_Q1
G110500496 | 500496 | Wastewater | G110 | Gate 110 | 2022-02-28 | 2022-03-30 | 2021_22_P11 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G110500509 | 500509 | Water | G110 | Gate 110 | 2022-05-25 | 2023-04-19 | 2022_23_P02 | 2023_24_P01 | 2022_23_Q1 | 2023_24_Q1
G110500523 | 500523 | Water | G110 | Gate 110 | 2024-06-20 | 2024-09-18 | 2024_25_P03 | 2024_25_P06 | 2024_25_Q1 | 2024_25_Q2
G110500573 | 500573 | Water | G110 | Gate 110 | 2023-03-29 | 2022-11-02 | 2022_23_P12 | 2022_23_P08 | 2022_23_Q4 | 2022_23_Q3
G110500575 | 500575 | Water | G110 | Gate 110 | 2023-05-23 | 2023-07-26 | 2023_24_P02 | 2023_24_P04 | 2023_24_Q1 | 2023_24_Q2
G110500579 | 500579 | Wastewater | G110 | Gate 110 | 2022-12-30 | 2023-04-19 | 2022_23_P09 | 2023_24_P01 | 2022_23_Q3 | 2023_24_Q1
G110500580 | 500580 | Wastewater | G110 | Gate 110 | 2023-07-31 | 2023-03-22 | 2023_24_P04 | 2022_23_P12 | 2023_24_Q2 | 2022_23_Q4
G110500652 | 500652 | Wastewater | G110 | Gate 110 | 2022-08-10 | 2022-06-01 | 2022_23_P05 | 2022_23_P03 | 2022_23_Q2 | 2022_23_Q1
G110500654 | 500654 | Wastewater | G110 | Gate 110 | 2022-10-30 | 2022-12-28 | 2022_23_P07 | 2022_23_P09 | 2022_23_Q3 | 2022_23_Q3
G110500655 | 500655 | Wastewater | G110 | Gate 110 | 2022-12-27 | 2022-03-30 | 2022_23_P09 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4
G110500661 | 500661 | Wastewater | G110 | Gate 110 | 2023-06-19 | 2022-12-28 | 2023_24_P03 | 2022_23_P09 | 2023_24_Q1 | 2022_23_Q3
G110500662 | 500662 | Wastewater | G110 | Gate 110 | 2022-08-25 | 2022-04-20 | 2022_23_P05 | 2022_23_P01 | 2022_23_Q2 | 2022_23_Q1
G110500665 | 500665 | Wastewater | G110 | Gate 110 | 2022-10-17 | 2022-03-30 | 2022_23_P07 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4
G110500681 | 500681 | Wastewater | G110 | Gate 110 | 2023-06-14 | 2023-05-31 | 2023_24_P03 | 2023_24_P02 | 2023_24_Q1 | 2023_24_Q1
G110500682 | 500682 | Wastewater | G110 | Gate 110 | 2023-06-04 | 2023-02-08 | 2023_24_P03 | 2022_23_P11 | 2023_24_Q1 | 2022_23_Q4
G110500687 | 500687 | Wastewater | G110 | Gate 110 | 2022-06-25 | 2022-03-30 | 2022_23_P03 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110500694 | 500694 | Wastewater | G110 | Gate 110 | 2022-08-23 | 2022-10-19 | 2022_23_P05 | 2022_23_P07 | 2022_23_Q2 | 2022_23_Q3
G110500695 | 500695 | Wastewater | G110 | Gate 110 | 2022-01-01 | 2021-10-22 | 2021_22_P10 | 2021_22_P07 | 2021_22_Q4 | 2021_22_Q3
G110500707 | 500707 | Wastewater | G110 | Gate 110 | 2022-04-14 | 2021-12-22 | 2022_23_P01 | 2021_22_P09 | 2022_23_Q1 | 2021_22_Q3
G110500709 | 500709 | Water | G110 | Gate 110 | 2022-07-12 | 2022-11-02 | 2022_23_P04 | 2022_23_P08 | 2022_23_Q2 | 2022_23_Q3
G110500843 | 500843 | Water | G110 | Gate 110 | 2021-12-30 | 2021-11-19 | 2021_22_P09 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
G110500755 | 500755 | Water | G110 | Gate 110 | 2024-08-23 | 2023-09-20 | 2024_25_P05 | 2023_24_P06 | 2024_25_Q2 | 2023_24_Q2
G110500784 | 500784 | Wastewater | G110 | Gate 110 | 2022-01-22 | 2021-11-24 | 2021_22_P10 | 2021_22_P08 | 2021_22_Q4 | 2021_22_Q3
G110500742 | 500742 | Water | G110 | Gate 110 | 2022-01-29 | 2022-05-18 | 2021_22_P10 | 2022_23_P02 | 2021_22_Q4 | 2022_23_Q1
G110500771 | 500771 | Water | G110 | Gate 110 | 2022-03-15 | 2022-03-24 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G110500723 | 500723 | Wastewater | G110 | Gate 110 | 2022-10-15 | 2022-08-10 | 2022_23_P07 | 2022_23_P05 | 2022_23_Q3 | 2022_23_Q2
G110500892 | 500892 | Water | G110 | Gate 110 | 2023-03-28 | 2023-10-04 | 2022_23_P12 | 2023_24_P07 | 2022_23_Q4 | 2023_24_Q3
G110500896 | 500896 | Water | G110 | Gate 110 | 2023-08-08 | 2023-08-11 | 2023_24_P05 | 2023_24_P05 | 2023_24_Q2 | 2023_24_Q2
G110500899 | 500899 | Water | G110 | Gate 110 | 2021-12-17 | 2022-03-29 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G110500918 | 500918 | Water | G110 | Gate 110 | 2023-03-01 | 2023-01-25 | 2022_23_P12 | 2022_23_P10 | 2022_23_Q4 | 2022_23_Q4
G110500947 | 500947 | Support Services | G110 | Gate 110 | 2022-03-17 | 2022-07-27 | 2021_22_P12 | 2022_23_P04 | 2021_22_Q4 | 2022_23_Q2
G110500958 | 500958 | Water | G110 | Gate 110 | 2022-04-08 | 2022-03-29 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110501001 | 501001 | Water | G110 | Gate 110 | 2023-11-17 | 2024-02-07 | 2023_24_P08 | 2023_24_P11 | 2023_24_Q3 | 2023_24_Q4
G110501019 | 501019 | Wastewater | G110 | Gate 110 | 2022-02-27 | 2021-12-22 | 2021_22_P11 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3
G110501021 | 501021 | Wastewater | G110 | Gate 110 | 2022-12-30 | 2023-02-14 | 2022_23_P09 | 2022_23_P11 | 2022_23_Q3 | 2022_23_Q4
G110501040 | 501040 | Water | G110 | Gate 110 | 2022-03-01 | 2022-02-28 | 2021_22_P12 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4
G110501070 | 501070 | Water | G110 | Gate 110 | 2022-07-23 | 2027-07-21 | 2022_23_P04 | 2027_28_P04 | 2022_23_Q2 | 2027_28_Q2
G110501091 | 501091 | Water | G110 | Gate 110 | 2022-10-13 | 2022-03-31 | 2022_23_P07 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4
G110501092 | 501092 | Water | G110 | Gate 110 | 2021-11-18 | 2022-03-31 | 2021_22_P08 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G110501144 | 501144 | Water | G110 | Gate 110 | 2022-10-22 | 2022-04-20 | 2022_23_P07 | 2022_23_P01 | 2022_23_Q3 | 2022_23_Q1
G110501146 | 501146 | Water | G110 | Gate 110 | 2022-01-29 | 2021-07-30 | 2021_22_P10 | 2021_22_P04 | 2021_22_Q4 | 2021_22_Q2
G110501151 | 501151 | Wastewater | G110 | Gate 110 | 2022-02-23 | 2021-12-22 | 2021_22_P11 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3
G110501152 | 501152 | Wastewater | G110 | Gate 110 | 2021-12-30 | 2022-03-16 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G110501153 | 501153 | Wastewater | G110 | Gate 110 | 2022-06-29 | 2022-10-19 | 2022_23_P03 | 2022_23_P07 | 2022_23_Q1 | 2022_23_Q3
G110501156 | 501156 | Wastewater | G110 | Gate 110 | 2022-07-12 | 2022-08-24 | 2022_23_P04 | 2022_23_P05 | 2022_23_Q2 | 2022_23_Q2
G110501388 | 501388 | Water | G110 | Gate 110 | 2022-11-01 | 2022-11-30 | 2022_23_P08 | 2022_23_P08 | 2022_23_Q3 | 2022_23_Q3
G110501390 | 501390 | Water | G110 | Gate 110 | 2023-08-11 | 2023-07-26 | 2023_24_P05 | 2023_24_P04 | 2023_24_Q2 | 2023_24_Q2
G110501200 | 501200 | Water | G110 | Gate 110 | 2023-01-24 | 2022-12-14 | 2022_23_P10 | 2022_23_P09 | 2022_23_Q4 | 2022_23_Q3
G110501203 | 501203 | Water | G110 | Gate 110 | 2021-12-11 | 2021-07-30 | 2021_22_P09 | 2021_22_P04 | 2021_22_Q3 | 2021_22_Q2
G110501216 | 501216 | Water | G110 | Gate 110 | 2022-08-19 | 2022-10-19 | 2022_23_P05 | 2022_23_P07 | 2022_23_Q2 | 2022_23_Q3
G110501217 | 501217 | Water | G110 | Gate 110 | 2022-06-01 | 2022-08-10 | 2022_23_P03 | 2022_23_P05 | 2022_23_Q1 | 2022_23_Q2
G110501158 | 501158 | Wastewater | G110 | Gate 110 | 2022-03-04 | 2022-04-01 | 2021_22_P12 | 2022_23_P01 | 2021_22_Q4 | 2022_23_Q1
G110501159 | 501159 | Wastewater | G110 | Gate 110 | 2024-03-20 | 2024-01-10 | 2023_24_P12 | 2023_24_P10 | 2023_24_Q4 | 2023_24_Q4
G110501165 | 501165 | Wastewater | G110 | Gate 110 | 2022-03-17 | 2022-02-28 | 2021_22_P12 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4
G110501168 | 501168 | Wastewater | G110 | Gate 110 | 2023-02-28 | 2022-09-07 | 2022_23_P11 | 2022_23_P06 | 2022_23_Q4 | 2022_23_Q2
G110501169 | 501169 | Wastewater | G110 | Gate 110 | 2021-12-31 | 2021-11-15 | 2021_22_P09 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
G110501232 | 501232 | Water | G110 | Gate 110 | 2022-11-03 | 2023-07-12 | 2022_23_P08 | 2023_24_P04 | 2022_23_Q3 | 2023_24_Q2
G110501233 | 501233 | Water | G110 | Gate 110 | 2022-04-30 | 2021-10-29 | 2022_23_P01 | 2021_22_P07 | 2022_23_Q1 | 2021_22_Q3
G110501227 | 501227 | Water | G110 | Gate 110 | 2022-05-18 | 2021-06-29 | 2022_23_P02 | 2021_22_P03 | 2022_23_Q1 | 2021_22_Q1
G110501379 | 501379 | Water | G110 | Gate 110 | 2023-06-30 | 2023-06-14 | 2023_24_P03 | 2023_24_P03 | 2023_24_Q1 | 2023_24_Q1
G110501243 | 501243 | Water | G110 | Gate 110 | 2023-11-02 | 2023-08-23 | 2023_24_P08 | 2023_24_P05 | 2023_24_Q3 | 2023_24_Q2
G110501258 | 501258 | Water | G110 | Gate 110 | 2021-12-24 | 2021-11-12 | 2021_22_P09 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
G110501259 | 501259 | Water | G110 | Gate 110 | 2022-04-06 | 2022-03-30 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110501290 | 501290 | Wastewater | G110 | Gate 110 | 2023-04-30 | 2023-02-08 | 2023_24_P01 | 2022_23_P11 | 2023_24_Q1 | 2022_23_Q4
G110501218 | 501218 | Water | G110 | Gate 110 | 2022-05-28 | 2022-10-05 | 2022_23_P02 | 2022_23_P07 | 2022_23_Q1 | 2022_23_Q3
G110501219 | 501219 | Water | G110 | Gate 110 | 2022-04-01 | 2022-01-20 | 2022_23_P01 | 2021_22_P10 | 2022_23_Q1 | 2021_22_Q4
G110501488 | 501488 | Wastewater | G110 | Gate 110 | 2022-12-29 | 2022-07-27 | 2022_23_P09 | 2022_23_P04 | 2022_23_Q3 | 2022_23_Q2
G110501499 | 501499 | Wastewater | G110 | Gate 110 | 2022-11-22 | 2022-08-10 | 2022_23_P08 | 2022_23_P05 | 2022_23_Q3 | 2022_23_Q2
G110501500 | 501500 | Wastewater | G110 | Gate 110 | 2022-02-28 | 2022-02-28 | 2021_22_P11 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4
G110501352 | 501352 | Wastewater | G110 | Gate 110 | 2022-09-09 | 2022-07-27 | 2022_23_P06 | 2022_23_P04 | 2022_23_Q2 | 2022_23_Q2
G110501393 | 501393 | Water | G110 | Gate 110 | 2023-02-28 | 2023-05-03 | 2022_23_P11 | 2023_24_P02 | 2022_23_Q4 | 2023_24_Q1
G110501402 | 501402 | Water | G110 | Gate 110 | 2022-02-05 | 2021-11-12 | 2021_22_P11 | 2021_22_P08 | 2021_22_Q4 | 2021_22_Q3
G110501418 | 501418 | Water | G110 | Gate 110 | 2022-09-03 | 2022-09-21 | 2022_23_P06 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2
G110501421 | 501421 | Water | G110 | Gate 110 | 2021-12-31 | 2021-12-21 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
G110501579 | 501579 | Wastewater | G110 | Gate 110 | 2023-09-30 | 2023-11-01 | 2023_24_P06 | 2023_24_P08 | 2023_24_Q2 | 2023_24_Q3
G110501592 | 501592 | Wastewater | G110 | Gate 110 | 2022-02-28 | 2022-03-16 | 2021_22_P11 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G110501593 | 501593 | Wastewater | G110 | Gate 110 | 2021-12-31 | 2021-12-22 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
G110501632 | 501632 | Support Services | G110 | Gate 110 | 2022-02-05 | 2021-06-30 | 2021_22_P11 | 2021_22_P03 | 2021_22_Q4 | 2021_22_Q1
G110501635 | 501635 | Water | G110 | Gate 110 | 2022-03-31 | 2021-08-31 | 2021_22_P12 | 2021_22_P05 | 2021_22_Q4 | 2021_22_Q2
G110501436 | 501436 | Water | G110 | Gate 110 | 2022-01-27 | 2022-03-23 | 2021_22_P10 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G110501554 | 501554 | Water | G110 | Gate 110 | 2023-08-11 | 2023-01-11 | 2023_24_P05 | 2022_23_P10 | 2023_24_Q2 | 2022_23_Q4
G110501573 | 501573 | Water | G110 | Gate 110 | 2021-12-25 | 2021-06-10 | 2021_22_P09 | 2021_22_P03 | 2021_22_Q3 | 2021_22_Q1
G110501574 | 501574 | Water | G110 | Gate 110 | 2021-06-16 | 2022-03-24 | 2021_22_P03 | 2021_22_P12 | 2021_22_Q1 | 2021_22_Q4
G110501599 | 501599 | Wastewater | G110 | Gate 110 | 2022-03-31 | 2022-07-27 | 2021_22_P12 | 2022_23_P04 | 2021_22_Q4 | 2022_23_Q2
G110501600 | 501600 | Water | G110 | Gate 110 | 2022-04-12 | 2022-02-24 | 2022_23_P01 | 2021_22_P11 | 2022_23_Q1 | 2021_22_Q4
G110501639 | 501639 | Support Services | G110 | Gate 110 | 2022-03-16 | 2021-11-29 | 2021_22_P12 | 2021_22_P08 | 2021_22_Q4 | 2021_22_Q3
G110501642 | 501642 | Water | G110 | Gate 110 | 2021-12-30 | 2021-10-28 | 2021_22_P09 | 2021_22_P07 | 2021_22_Q3 | 2021_22_Q3
G110501512 | 501512 | Wastewater | G110 | Gate 110 | 2025-01-20 | 2024-04-17 | 2024_25_P10 | 2024_25_P01 | 2024_25_Q4 | 2024_25_Q1
G110501518 | 501518 | Wastewater | G110 | Gate 110 | 2022-07-01 | 2022-03-31 | 2022_23_P04 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4
G110501666 | 501666 | Water | G110 | Gate 110 | 2022-03-26 | 2022-09-08 | 2021_22_P12 | 2022_23_P06 | 2021_22_Q4 | 2022_23_Q2
G110501683 | 501683 | Wastewater | G110 | Gate 110 | 2022-08-31 | 2022-12-14 | 2022_23_P05 | 2022_23_P09 | 2022_23_Q2 | 2022_23_Q3
G110501720 | 501720 | Wastewater | G110 | Gate 110 | 2022-05-31 | 2022-02-28 | 2022_23_P02 | 2021_22_P11 | 2022_23_Q1 | 2021_22_Q4
G110501739 | 501739 | Wastewater | G110 | Gate 110 | 2022-04-22 | 2022-09-07 | 2022_23_P01 | 2022_23_P06 | 2022_23_Q1 | 2022_23_Q2
G110501898 | 501898 | Support Services | G110 | Gate 110 | 2022-06-30 | 2022-06-29 | 2022_23_P03 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1
G110501818 | 501818 | Support Services | G110 | Gate 110 | 2022-04-28 | 2021-12-21 | 2022_23_P01 | 2021_22_P09 | 2022_23_Q1 | 2021_22_Q3
G110501829 | 501829 | Wastewater | G110 | Gate 110 | 2022-09-11 | 2022-10-05 | 2022_23_P06 | 2022_23_P07 | 2022_23_Q2 | 2022_23_Q3
G110502132 | 502132 | Water | G110 | Gate 110 | 2023-10-21 | 2023-09-20 | 2023_24_P07 | 2023_24_P06 | 2023_24_Q3 | 2023_24_Q2
G110502246 | 502246 | Water | G110 | Gate 110 | 2022-04-12 | 2022-06-15 | 2022_23_P01 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1
G110502267 | 502267 | Wastewater | G110 | Gate 110 | 2022-01-21 | 2022-01-27 | 2021_22_P10 | 2021_22_P10 | 2021_22_Q4 | 2021_22_Q4
G110502268 | 502268 | Wastewater | G110 | Gate 110 | 2023-01-13 | 2023-07-12 | 2022_23_P10 | 2023_24_P04 | 2022_23_Q4 | 2023_24_Q2
G110502269 | 502269 | Wastewater | G110 | Gate 110 | 2022-01-11 | 2022-01-27 | 2021_22_P10 | 2021_22_P10 | 2021_22_Q4 | 2021_22_Q4
G110502282 | 502282 | Water | G110 | Gate 110 | 2024-06-10 | 2023-09-20 | 2024_25_P03 | 2023_24_P06 | 2024_25_Q1 | 2023_24_Q2
G110502212 | 502212 | Wastewater | G110 | Gate 110 | 2024-07-20 | 2023-11-01 | 2024_25_P04 | 2023_24_P08 | 2024_25_Q2 | 2023_24_Q3
G110502231 | 502231 | Wastewater | G110 | Gate 110 | 2022-01-01 | 2021-12-21 | 2021_22_P10 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3
G110502329 | 502329 | Water | G110 | Gate 110 | 2022-05-10 | 2022-02-25 | 2022_23_P02 | 2021_22_P11 | 2022_23_Q1 | 2021_22_Q4
G110502280 | 502280 | Wastewater | G110 | Gate 110 | 2022-12-06 | 2022-11-30 | 2022_23_P09 | 2022_23_P08 | 2022_23_Q3 | 2022_23_Q3
G110502281 | 502281 | Wastewater | G110 | Gate 110 | 2022-08-20 | 2022-06-15 | 2022_23_P05 | 2022_23_P03 | 2022_23_Q2 | 2022_23_Q1
G110502342 | 502342 | Wastewater | G110 | Gate 110 | 2022-11-22 | 2022-10-05 | 2022_23_P08 | 2022_23_P07 | 2022_23_Q3 | 2022_23_Q3
G110502380 | 502380 | Water | G110 | Gate 110 | 2021-12-31 | 2022-06-15 | 2021_22_P09 | 2022_23_P03 | 2021_22_Q3 | 2022_23_Q1
G110502382 | 502382 | Water | G110 | Gate 110 | 2022-07-30 | 2022-09-07 | 2022_23_P04 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2
G110502383 | 502383 | Water | G110 | Gate 110 | 2022-09-20 | 2022-07-13 | 2022_23_P06 | 2022_23_P04 | 2022_23_Q2 | 2022_23_Q2
G110502584 | 502584 | Wastewater | G110 | Gate 110 | 2021-12-31 | 2021-12-16 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
G110502392 | 502392 | Water | G110 | Gate 110 | 2023-06-14 | 2022-11-30 | 2023_24_P03 | 2022_23_P08 | 2023_24_Q1 | 2022_23_Q3
G110502578 | 502578 | Wastewater | G110 | Gate 110 | 2023-01-26 | 2022-06-29 | 2022_23_P10 | 2022_23_P03 | 2022_23_Q4 | 2022_23_Q1
G110502412 | 502412 | Water | G110 | Gate 110 | 2022-03-26 | 2022-06-29 | 2021_22_P12 | 2022_23_P03 | 2021_22_Q4 | 2022_23_Q1
G110502648 | 502648 | Water | G110 | Gate 110 | 2023-08-23 | 2023-04-19 | 2023_24_P05 | 2023_24_P01 | 2023_24_Q2 | 2023_24_Q1
G110502649 | 502649 | Water | G110 | Gate 110 | 2023-10-31 | 2023-10-04 | 2023_24_P07 | 2023_24_P07 | 2023_24_Q3 | 2023_24_Q3
G110502650 | 502650 | Water | G110 | Gate 110 | 2023-09-20 | 2023-03-08 | 2023_24_P06 | 2022_23_P12 | 2023_24_Q2 | 2022_23_Q4
G110502563 | 502563 | Water | G110 | Gate 110 | 2022-10-19 | 2022-06-15 | 2022_23_P07 | 2022_23_P03 | 2022_23_Q3 | 2022_23_Q1
G110502743 | 502743 | Wastewater | G110 | Gate 110 | 2023-03-14 | 2022-09-07 | 2022_23_P12 | 2022_23_P06 | 2022_23_Q4 | 2022_23_Q2
G110502765 | 502765 | Wastewater | G110 | Gate 110 | 2022-07-27 | 2022-05-04 | 2022_23_P04 | 2022_23_P02 | 2022_23_Q2 | 2022_23_Q1
G110502740 | 502740 | Wastewater | G110 | Gate 110 | 2022-05-28 | 2021-12-21 | 2022_23_P02 | 2021_22_P09 | 2022_23_Q1 | 2021_22_Q3
G110502741 | 502741 | Wastewater | G110 | Gate 110 | 2022-04-22 | 2022-03-24 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110502742 | 502742 | Wastewater | G110 | Gate 110 | 2022-07-15 | 2022-03-29 | 2022_23_P04 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4
G110502605 | 502605 | Water | G110 | Gate 110 | 2022-07-01 | 2022-05-04 | 2022_23_P04 | 2022_23_P02 | 2022_23_Q2 | 2022_23_Q1
G110502606 | 502606 | Water | G110 | Gate 110 | 2021-05-19 | 2021-10-28 | 2021_22_P02 | 2021_22_P07 | 2021_22_Q1 | 2021_22_Q3
G110502651 | 502651 | Water | G110 | Gate 110 | 2023-04-19 | 2023-05-17 | 2023_24_P01 | 2023_24_P02 | 2023_24_Q1 | 2023_24_Q1
G110502652 | 502652 | Water | G110 | Gate 110 | 2023-10-16 | 2023-01-25 | 2023_24_P07 | 2022_23_P10 | 2023_24_Q3 | 2022_23_Q4
G110502600 | 502600 | Water | G110 | Gate 110 | 2022-10-11 | 2023-08-23 | 2022_23_P07 | 2023_24_P05 | 2022_23_Q3 | 2023_24_Q2
G110502792 | 502792 | Support Services | G110 | Gate 110 | 2021-12-01 | 2021-04-13 | 2021_22_P09 | 2021_22_P01 | 2021_22_Q3 | 2021_22_Q1
G110502827 | 502827 | Wastewater | G110 | Gate 110 | 2022-10-14 | 2022-09-21 | 2022_23_P07 | 2022_23_P06 | 2022_23_Q3 | 2022_23_Q2
G110502808 | 502808 | Water | G110 | Gate 110 | 2022-08-03 | 2022-02-10 | 2022_23_P05 | 2021_22_P11 | 2022_23_Q2 | 2021_22_Q4
G110502747 | 502747 | Wastewater | G110 | Gate 110 | 2022-07-01 | 2022-05-04 | 2022_23_P04 | 2022_23_P02 | 2022_23_Q2 | 2022_23_Q1
G110502748 | 502748 | Wastewater | G110 | Gate 110 | 2023-04-24 | 2022-06-01 | 2023_24_P01 | 2022_23_P03 | 2023_24_Q1 | 2022_23_Q1
G110502749 | 502749 | Wastewater | G110 | Gate 110 | 2023-02-08 | 2022-08-24 | 2022_23_P11 | 2022_23_P05 | 2022_23_Q4 | 2022_23_Q2
G110502772 | 502772 | Water | G110 | Gate 110 | 2022-02-09 | 2021-12-03 | 2021_22_P11 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3
G110502853 | 502853 | Water | G110 | Gate 110 | 2023-07-23 | 2023-01-11 | 2023_24_P04 | 2022_23_P10 | 2023_24_Q2 | 2022_23_Q4
G110502895 | 502895 | Wastewater | G110 | Gate 110 | 2023-06-15 | 2023-01-25 | 2023_24_P03 | 2022_23_P10 | 2023_24_Q1 | 2022_23_Q4
G110502896 | 502896 | Water | G110 | Gate 110 | 2022-07-13 | 2022-03-30 | 2022_23_P04 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4
G110502780 | 502780 | Wastewater | G110 | Gate 110 | 2022-03-12 | 2022-03-24 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G110502783 | 502783 | Water | G110 | Gate 110 | 2023-03-24 | 2023-11-15 | 2022_23_P12 | 2023_24_P08 | 2022_23_Q4 | 2023_24_Q3
G110502857 | 502857 | Water | G110 | Gate 110 | 2024-03-16 | 2023-09-06 | 2023_24_P12 | 2023_24_P06 | 2023_24_Q4 | 2023_24_Q2
G110502866 | 502866 | Wastewater | G110 | Gate 110 | 2022-10-15 | 2022-08-10 | 2022_23_P07 | 2022_23_P05 | 2022_23_Q3 | 2022_23_Q2
G110502867 | 502867 | Water | G110 | Gate 110 | 2022-10-15 | 2022-03-31 | 2022_23_P07 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4
G110502934 | 502934 | Wastewater | G110 | Gate 110 | 2022-07-04 | 2022-03-24 | 2022_23_P04 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4
G110502940 | 502940 | Water | G110 | Gate 110 | 2023-01-11 | 2023-03-22 | 2022_23_P10 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4
G110502943 | 502943 | Wastewater | G110 | Gate 110 | 2022-06-07 | 2022-09-21 | 2022_23_P03 | 2022_23_P06 | 2022_23_Q1 | 2022_23_Q2
G110502944 | 502944 | Wastewater | G110 | Gate 110 | 2022-06-07 | 2023-05-03 | 2022_23_P03 | 2023_24_P02 | 2022_23_Q1 | 2023_24_Q1
G110502945 | 502945 | Wastewater | G110 | Gate 110 | 2022-06-30 | 2023-09-20 | 2022_23_P03 | 2023_24_P06 | 2022_23_Q1 | 2023_24_Q2
G110502946 | 502946 | Wastewater | G110 | Gate 110 | 2022-09-03 | 2023-01-25 | 2022_23_P06 | 2022_23_P10 | 2022_23_Q2 | 2022_23_Q4
G110502947 | 502947 | Wastewater | G110 | Gate 110 | 2022-04-26 | 2022-03-23 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110502949 | 502949 | Wastewater | G110 | Gate 110 | 2023-03-08 | 2024-03-06 | 2022_23_P12 | 2023_24_P12 | 2022_23_Q4 | 2023_24_Q4
G110502958 | 502958 | Wastewater | G110 | Gate 110 | 2023-09-30 | 2023-09-06 | 2023_24_P06 | 2023_24_P06 | 2023_24_Q2 | 2023_24_Q2
G110503037 | 503037 | Water | G110 | Gate 110 | 2021-12-30 | 2021-09-13 | 2021_22_P09 | 2021_22_P06 | 2021_22_Q3 | 2021_22_Q2
G110503045 | 503045 | Wastewater | G110 | Gate 110 | 2022-04-02 | 2022-02-01 | 2022_23_P01 | 2021_22_P11 | 2022_23_Q1 | 2021_22_Q4
G110503050 | 503050 | Water | G110 | Gate 110 | 2023-05-22 | 2023-04-05 | 2023_24_P02 | 2023_24_P01 | 2023_24_Q1 | 2023_24_Q1
G110503072 | 503072 | Water | G110 | Gate 110 | 2023-07-01 | 2023-03-08 | 2023_24_P04 | 2022_23_P12 | 2023_24_Q2 | 2022_23_Q4
G110503083 | 503083 | Wastewater | G110 | Gate 110 | 2022-03-15 | 2022-03-24 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G110503119 | 503119 | Support Services | G110 | Gate 110 | 2022-04-28 | 2022-03-11 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110503120 | 503120 | Support Services | G110 | Gate 110 | 2022-04-28 | 2022-03-31 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110503121 | 503121 | Support Services | G110 | Gate 110 | 2022-04-28 | 2022-03-11 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110503170 | 503170 | Water | G110 | Gate 110 | 2021-06-30 | 2022-03-31 | 2021_22_P03 | 2021_22_P12 | 2021_22_Q1 | 2021_22_Q4
G110503177 | 503177 | Wastewater | G110 | Gate 110 | 2022-08-18 | 2022-03-29 | 2022_23_P05 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4
G110503094 | 503094 | Water | G110 | Gate 110 | 2021-12-31 | 2022-01-20 | 2021_22_P09 | 2021_22_P10 | 2021_22_Q3 | 2021_22_Q4
G110503106 | 503106 | Water | G110 | Gate 110 | 2021-12-23 | 2021-09-28 | 2021_22_P09 | 2021_22_P06 | 2021_22_Q3 | 2021_22_Q2
G110503110 | 503110 | Water | G110 | Gate 110 | 2024-02-25 | 2024-01-24 | 2023_24_P11 | 2023_24_P10 | 2023_24_Q4 | 2023_24_Q4
G110503162 | 503162 | Water | G110 | Gate 110 | 2023-05-10 | 2023-09-20 | 2023_24_P02 | 2023_24_P06 | 2023_24_Q1 | 2023_24_Q2
G110503200 | 503200 | Water | G110 | Gate 110 | 2022-04-20 | 2021-12-23 | 2022_23_P01 | 2021_22_P09 | 2022_23_Q1 | 2021_22_Q3
G110503229 | 503229 | Wastewater | G110 | Gate 110 | 2022-09-10 | 2022-09-21 | 2022_23_P06 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2
G110503230 | 503230 | Wastewater | G110 | Gate 110 | 2024-03-16 | 2023-07-12 | 2023_24_P12 | 2023_24_P04 | 2023_24_Q4 | 2023_24_Q2
G110503234 | 503234 | Water | G110 | Gate 110 | 2022-09-20 | 2022-03-18 | 2022_23_P06 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4
G110503235 | 503235 | Water | G110 | Gate 110 | 2023-08-31 | 2023-08-23 | 2023_24_P05 | 2023_24_P05 | 2023_24_Q2 | 2023_24_Q2
G110503236 | 503236 | Water | G110 | Gate 110 | 2022-01-05 | 2021-08-30 | 2021_22_P10 | 2021_22_P05 | 2021_22_Q4 | 2021_22_Q2
G110503237 | 503237 | Water | G110 | Gate 110 | 2021-12-29 | 2021-12-17 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
G110503239 | 503239 | Water | G110 | Gate 110 | 2024-07-10 | 2022-10-19 | 2024_25_P04 | 2022_23_P07 | 2024_25_Q2 | 2022_23_Q3
G110503243 | 503243 | Water | G110 | Gate 110 | 2021-12-16 | 2021-09-13 | 2021_22_P09 | 2021_22_P06 | 2021_22_Q3 | 2021_22_Q2
G110503248 | 503248 | Water | G110 | Gate 110 | 2021-12-29 | 2022-06-01 | 2021_22_P09 | 2022_23_P03 | 2021_22_Q3 | 2022_23_Q1
G110503249 | 503249 | Water | G110 | Gate 110 | 2022-01-20 | 2022-06-15 | 2021_22_P10 | 2022_23_P03 | 2021_22_Q4 | 2022_23_Q1
G110503256 | 503256 | Water | G110 | Gate 110 | 2022-04-06 | 2022-03-30 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110503257 | 503257 | Water | G110 | Gate 110 | 2022-10-19 | 2022-03-31 | 2022_23_P07 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4
G110503250 | 503250 | Water | G110 | Gate 110 | 2023-01-25 | 2023-01-25 | 2022_23_P10 | 2022_23_P10 | 2022_23_Q4 | 2022_23_Q4
G110503193 | 503193 | Water | G110 | Gate 110 | 2021-12-01 | 2021-12-15 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
G110503194 | 503194 | Water | G110 | Gate 110 | 2022-01-26 | 2022-02-28 | 2021_22_P10 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4
G110503195 | 503195 | Water | G110 | Gate 110 | 2023-05-31 | 2022-03-30 | 2023_24_P02 | 2021_22_P12 | 2023_24_Q1 | 2021_22_Q4
G110503197 | 503197 | Water | G110 | Gate 110 | 2022-10-19 | 2022-03-31 | 2022_23_P07 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4
G110503198 | 503198 | Water | G110 | Gate 110 | 2022-10-19 | 2022-03-30 | 2022_23_P07 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4
G110503199 | 503199 | Water | G110 | Gate 110 | 2022-10-19 | 2022-03-30 | 2022_23_P07 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4
G110503266 | 503266 | Water | G110 | Gate 110 | 2022-02-28 | 2021-09-21 | 2021_22_P11 | 2021_22_P06 | 2021_22_Q4 | 2021_22_Q2
G110503269 | 503269 | Wastewater | G110 | Gate 110 | 2023-02-16 | 2023-03-08 | 2022_23_P11 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4
G110503291 | 503291 | Support Services | G110 | Gate 110 | 2022-04-28 | 2022-05-18 | 2022_23_P01 | 2022_23_P02 | 2022_23_Q1 | 2022_23_Q1
G110503336 | 503336 | Water | G110 | Gate 110 | 2023-06-14 | 2023-11-15 | 2023_24_P03 | 2023_24_P08 | 2023_24_Q1 | 2023_24_Q3
G110503362 | 503362 | Wastewater | G110 | Gate 110 | 2024-06-12 | 2022-10-19 | 2024_25_P03 | 2022_23_P07 | 2024_25_Q1 | 2022_23_Q3
G110503393 | 503393 | Wastewater | G110 | Gate 110 | 2022-08-04 | 2023-04-19 | 2022_23_P05 | 2023_24_P01 | 2022_23_Q2 | 2023_24_Q1
G110503408 | 503408 | Water | G110 | Gate 110 | 2023-08-27 | 2023-03-08 | 2023_24_P05 | 2022_23_P12 | 2023_24_Q2 | 2022_23_Q4
G110503412 | 503412 | Water | G110 | Gate 110 | 2022-12-28 | 2022-03-30 | 2022_23_P09 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4
G110503413 | 503413 | Water | G110 | Gate 110 | 2022-12-28 | 2022-03-30 | 2022_23_P09 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4
G110503415 | 503415 | Wastewater | G110 | Gate 110 | 2023-01-21 | 2023-09-06 | 2022_23_P10 | 2023_24_P06 | 2022_23_Q4 | 2023_24_Q2
G110503418 | 503418 | Wastewater | G110 | Gate 110 | 2022-07-01 | 2022-06-29 | 2022_23_P04 | 2022_23_P03 | 2022_23_Q2 | 2022_23_Q1
G110503421 | 503421 | Water | G110 | Gate 110 | 2023-12-31 | 2022-12-14 | 2023_24_P09 | 2022_23_P09 | 2023_24_Q3 | 2022_23_Q3
G110503424 | 503424 | Wastewater | G110 | Gate 110 | 2021-12-18 | 2021-11-26 | 2021_22_P09 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
G110503434 | 503434 | Water | G110 | Gate 110 | 2022-12-30 | 2022-10-19 | 2022_23_P09 | 2022_23_P07 | 2022_23_Q3 | 2022_23_Q3
G110503441 | 503441 | Wastewater | G110 | Gate 110 | 2024-05-16 | 2023-11-29 | 2024_25_P02 | 2023_24_P08 | 2024_25_Q1 | 2023_24_Q3
G110503543 | 503543 | Wastewater | G110 | Gate 110 | 2022-06-22 | 2022-05-18 | 2022_23_P03 | 2022_23_P02 | 2022_23_Q1 | 2022_23_Q1
G110503545 | 503545 | Wastewater | G110 | Gate 110 | 2022-06-22 | 2022-03-29 | 2022_23_P03 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110503546 | 503546 | Wastewater | G110 | Gate 110 | 2022-06-22 | 2021-12-22 | 2022_23_P03 | 2021_22_P09 | 2022_23_Q1 | 2021_22_Q3
G110503562 | 503562 | Water | G110 | Gate 110 | 2022-06-11 | 2022-03-24 | 2022_23_P03 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110503564 | 503564 | Wastewater | G110 | Gate 110 | 2022-11-04 | 2022-11-30 | 2022_23_P08 | 2022_23_P08 | 2022_23_Q3 | 2022_23_Q3
G110503571 | 503571 | Wastewater | G110 | Gate 110 | 2022-12-30 | 2023-02-08 | 2022_23_P09 | 2022_23_P11 | 2022_23_Q3 | 2022_23_Q4
G110503587 | 503587 | Water | G110 | Gate 110 | 2022-07-31 | 2022-11-16 | 2022_23_P04 | 2022_23_P08 | 2022_23_Q2 | 2022_23_Q3
G110503595 | 503595 | Water | G110 | Gate 110 | 2022-12-28 | 2023-12-13 | 2022_23_P09 | 2023_24_P09 | 2022_23_Q3 | 2023_24_Q3
G110503617 | 503617 | Water | G110 | Gate 110 | 2022-12-16 | 2022-11-02 | 2022_23_P09 | 2022_23_P08 | 2022_23_Q3 | 2022_23_Q3
G110503630 | 503630 | Water | G110 | Gate 110 | 2022-10-19 | 2022-10-19 | 2022_23_P07 | 2022_23_P07 | 2022_23_Q3 | 2022_23_Q3
G110503631 | 503631 | Water | G110 | Gate 110 | 2022-10-28 | 2022-11-30 | 2022_23_P07 | 2022_23_P08 | 2022_23_Q3 | 2022_23_Q3
G110503632 | 503632 | Water | G110 | Gate 110 | 2023-04-05 | 2023-04-19 | 2023_24_P01 | 2023_24_P01 | 2023_24_Q1 | 2023_24_Q1
G110503678 | 503678 | Water | G110 | Gate 110 | 2024-10-12 | 2024-04-03 | 2024_25_P07 | 2024_25_P01 | 2024_25_Q3 | 2024_25_Q1
G110503686 | 503686 | Water | G110 | Gate 110 | 2024-05-27 | 2023-09-06 | 2024_25_P02 | 2023_24_P06 | 2024_25_Q1 | 2023_24_Q2
G110503701 | 503701 | Wastewater | G110 | Gate 110 | 2022-02-12 | 2021-08-27 | 2021_22_P11 | 2021_22_P05 | 2021_22_Q4 | 2021_22_Q2
G110503716 | 503716 | Water | G110 | Gate 110 | 2023-01-29 | 2022-06-01 | 2022_23_P10 | 2022_23_P03 | 2022_23_Q4 | 2022_23_Q1
G110503726 | 503726 | Water | G110 | Gate 110 | 2022-07-07 | 2022-03-30 | 2022_23_P04 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4
G110503727 | 503727 | Water | G110 | Gate 110 | 2022-11-16 | 2022-03-31 | 2022_23_P08 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4
G110503728 | 503728 | Water | G110 | Gate 110 | 2022-03-31 | 2021-12-23 | 2021_22_P12 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3
G110503730 | 503730 | Water | G110 | Gate 110 | 2024-07-22 | 2024-01-24 | 2024_25_P04 | 2023_24_P10 | 2024_25_Q2 | 2023_24_Q4
G110503731 | 503731 | Water | G110 | Gate 110 | 2023-05-24 | 2024-01-24 | 2023_24_P02 | 2023_24_P10 | 2023_24_Q1 | 2023_24_Q4
G110503733 | 503733 | Water | G110 | Gate 110 | 2023-03-01 | 2022-03-31 | 2022_23_P12 | 2021_22_P12 | 2022_23_Q4 | 2021_22_Q4
G110503761 | 503761 | Water | G110 | Gate 110 | 2024-03-20 | 2023-10-04 | 2023_24_P12 | 2023_24_P07 | 2023_24_Q4 | 2023_24_Q3
G110503860 | 503860 | Wastewater | G110 | Gate 110 | 2023-04-28 | 2022-10-19 | 2023_24_P01 | 2022_23_P07 | 2023_24_Q1 | 2022_23_Q3
G110504434 | 504434 | Water | G110 | Gate 110 | 2022-08-19 | 2022-03-29 | 2022_23_P05 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4
G110504995 | 504995 | Water | G110 | Gate 110 | 2025-07-21 | 2024-11-27 | 2025_26_P04 | 2024_25_P08 | 2025_26_Q2 | 2024_25_Q3
G110505032 | 505032 | Water | G110 | Gate 110 | 2022-09-10 | 2022-07-27 | 2022_23_P06 | 2022_23_P04 | 2022_23_Q2 | 2022_23_Q2
G110505053 | 505053 | Wastewater | G110 | Gate 110 | 2024-04-28 | 2023-11-29 | 2024_25_P01 | 2023_24_P08 | 2024_25_Q1 | 2023_24_Q3
G110505384 | 505384 | Water | G110 | Gate 110 | 2024-10-19 | 2024-05-15 | 2024_25_P07 | 2024_25_P02 | 2024_25_Q3 | 2024_25_Q1
G110505447 | 505447 | Water | G110 | Gate 110 | 2024-03-07 | 2024-02-21 | 2023_24_P12 | 2023_24_P11 | 2023_24_Q4 | 2023_24_Q4
G110505504 | 505504 | Water | G110 | Gate 110 | 2023-09-01 | 2023-10-18 | 2023_24_P06 | 2023_24_P07 | 2023_24_Q2 | 2023_24_Q3
G110505641 | 505641 | Wastewater | G110 | Gate 110 | 2023-09-10 | 2023-10-04 | 2023_24_P06 | 2023_24_P07 | 2023_24_Q2 | 2023_24_Q3
G110505693 | 505693 | Water | G110 | Gate 110 | 2024-11-22 | 2024-02-21 | 2024_25_P08 | 2023_24_P11 | 2024_25_Q3 | 2023_24_Q4
G110506029 | 506029 | Water | G110 | Gate 110 | 2025-03-16 | 2024-12-11 | 2024_25_P12 | 2024_25_P09 | 2024_25_Q4 | 2024_25_Q3
G110506032 | 506032 | Water | G110 | Gate 110 | 2025-04-25 | 2025-01-22 | 2025_26_P01 | 2024_25_P10 | 2025_26_Q1 | 2024_25_Q4
G110506228 | 506228 | Water | G110 | Gate 110 | 2024-03-28 | 2023-09-20 | 2023_24_P12 | 2023_24_P06 | 2023_24_Q4 | 2023_24_Q2
G110506232 | 506232 | Water | G110 | Gate 110 | 2024-03-28 | 2023-05-31 | 2023_24_P12 | 2023_24_P02 | 2023_24_Q4 | 2023_24_Q1
G110506234 | 506234 | Water | G110 | Gate 110 | 2024-03-28 | 2022-11-16 | 2023_24_P12 | 2022_23_P08 | 2023_24_Q4 | 2022_23_Q3
G110506608 | 506608 | Water | G110 | Gate 110 | 2024-01-21 | 2023-10-04 | 2023_24_P10 | 2023_24_P07 | 2023_24_Q4 | 2023_24_Q3
G110506684 | 506684 | Water | G110 | Gate 110 | 2023-12-23 | 2023-05-31 | 2023_24_P09 | 2023_24_P02 | 2023_24_Q3 | 2023_24_Q1
G110506779 | 506779 | Water | G110 | Gate 110 | 2024-10-14 | 2024-01-24 | 2024_25_P07 | 2023_24_P10 | 2024_25_Q3 | 2023_24_Q4
G110506864 | 506864 | Water | G110 | Gate 110 | 2023-11-30 | 2024-08-14 | 2023_24_P08 | 2024_25_P05 | 2023_24_Q3 | 2024_25_Q2
G110506865 | 506865 | Wastewater | G110 | Gate 110 | 2023-11-30 | 2024-08-14 | 2023_24_P08 | 2024_25_P05 | 2023_24_Q3 | 2024_25_Q2
G110506896 | 506896 | Support Services | G110 | Gate 110 | 2022-07-01 | 2022-03-10 | 2022_23_P04 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4
G110507057 | 507057 | Water | G110 | Gate 110 | 2024-09-12 | 2024-06-26 | 2024_25_P06 | 2024_25_P03 | 2024_25_Q2 | 2024_25_Q1
G110507173 | 507173 | Support Services | G110 | Gate 110 | 2022-05-03 | 2022-02-01 | 2022_23_P02 | 2021_22_P11 | 2022_23_Q1 | 2021_22_Q4
G110507186 | 507186 | Water | G110 | Gate 110 | 2024-04-11 | 2024-01-10 | 2024_25_P01 | 2023_24_P10 | 2024_25_Q1 | 2023_24_Q4
G110507189 | 507189 | Water | G110 | Gate 110 | 2024-09-13 | 2024-06-26 | 2024_25_P06 | 2024_25_P03 | 2024_25_Q2 | 2024_25_Q1
G110507455 | 507455 | Water | G110 | Gate 110 | 2025-01-29 | 2024-06-26 | 2024_25_P10 | 2024_25_P03 | 2024_25_Q4 | 2024_25_Q1
G110507813 | 507813 | Water | G110 | Gate 110 | 2023-01-24 | 2022-07-27 | 2022_23_P10 | 2022_23_P04 | 2022_23_Q4 | 2022_23_Q2
G110507860 | 507860 | Water | G110 | Gate 110 | 2023-02-13 | 2022-05-18 | 2022_23_P11 | 2022_23_P02 | 2022_23_Q4 | 2022_23_Q1
G110507933 | 507933 | Wastewater | G110 | Gate 110 | 2023-08-13 | 2023-04-05 | 2023_24_P05 | 2023_24_P01 | 2023_24_Q2 | 2023_24_Q1
G110508109 | 508109 | Support Services | G110 | Gate 110 | 2022-02-12 | 2022-02-10 | 2021_22_P11 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4
G110508601 | 508601 | Wastewater | G110 | Gate 110 | 2023-03-09 | 2022-11-30 | 2022_23_P12 | 2022_23_P08 | 2022_23_Q4 | 2022_23_Q3
G110509283 | 509283 | Water | G110 | Gate 110 | 2023-03-05 | 2022-10-05 | 2022_23_P12 | 2022_23_P07 | 2022_23_Q4 | 2022_23_Q3
G110510727 | 510727 | Support Services | G110 | Gate 110 | 2023-04-03 | 2022-09-07 | 2023_24_P01 | 2022_23_P06 | 2023_24_Q1 | 2022_23_Q2
G110511344 | 511344 | Support Services | G110 | Gate 110 | 2025-01-16 | 2022-11-30 | 2024_25_P10 | 2022_23_P08 | 2024_25_Q4 | 2022_23_Q3
G110512600 | 512600 | Water | G110 | Gate 110 | 2024-05-20 | 2023-10-04 | 2024_25_P02 | 2023_24_P07 | 2024_25_Q1 | 2023_24_Q3
G110512711 | 512711 | Water | G110 | Gate 110 | 2024-06-06 | 2024-02-21 | 2024_25_P03 | 2023_24_P11 | 2024_25_Q1 | 2023_24_Q4
G110512749 | 512749 | Water | G110 | Gate 110 | 2024-08-26 | 2024-03-20 | 2024_25_P05 | 2023_24_P12 | 2024_25_Q2 | 2023_24_Q4
G110513312 | 513312 | CE&FS | G110 | Gate 110 | 2028-06-12 | 2027-09-15 | 2028_29_P03 | 2027_28_P06 | 2028_29_Q1 | 2027_28_Q2
G110513461 | 513461 | Support Services | G110 | Gate 110 | 2023-05-18 | 2022-10-05 | 2023_24_P02 | 2022_23_P07 | 2023_24_Q1 | 2022_23_Q3
G110513832 | 513832 | Support Services | G110 | Gate 110 | 2022-12-26 | 2022-06-29 | 2022_23_P09 | 2022_23_P03 | 2022_23_Q3 | 2022_23_Q1
G110513923 | 513923 | Water | G110 | Gate 110 | 2024-03-28 | 2023-11-01 | 2023_24_P12 | 2023_24_P08 | 2023_24_Q4 | 2023_24_Q3
G110515505 | 515505 | Water | G110 | Gate 110 | 2023-07-16 | 2023-04-05 | 2023_24_P04 | 2023_24_P01 | 2023_24_Q2 | 2023_24_Q1

## G5
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2022
SECTION G: INVESTMENT MONITORING
Table G5: Growth
|  |  |  | Actual and Forecast | [5 empty] | Confidence Grades
Line | Description | Units | Field | Report Year | Forecast Year | Forecast Year | Forecast Year | Forecast Year | Forecast Year | Report Year | Forecast Year | Forecast Year | Forecast Year | Forecast Year | Forecast Year
Ref. |  |  | Type
|  |  |  | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27
Growth expenditure (gross)
G5.1 | Expenditure for Reasonable Cost Contributions - household - water | £m | I | 9.8776 | 6.9178 | 6.9178 | 6.9178 | 6.9178 | 6.9178 | A1 | A1 | A1 | A1 | A1 | A1
G5.2 | Expenditure for Reasonable Cost Contributions - non-household - water | £m | I | -0.047478 | 0.019349 | 0.021137 | 0.021137 | 0.021137 | 0.021137 | A1 | A1 | A1 | A1 | A1 | A1
G5.3 | Total expenditure on Reasonable Cost Contributions - water | £m | C | 9.8301 | 6.9371 | 6.9389 | 6.9389 | 6.9389 | 6.9389
G5.4 | Expenditure for Reasonable Cost Contributions - household - wastewater | £m | I | 14.734 | 11.205 | 11.205 | 16.3108 | 11.205 | 11.205 | A1 | A1 | A1 | A1 | A1 | A1
G5.5 | Expenditure for Reasonable Cost Contributions - non-household - wastewater | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1
G5.6 | Total expenditure on Reasonable Cost Contributions - wastewater | £m | C | 14.734 | 11.205 | 11.205 | 16.3108 | 11.205 | 11.205
G5.7 | Total expenditure on Reasonable Cost Contributions - water and wastewater | £m | C | 24.5642 | 18.1421 | 18.1439 | 23.2497 | 18.1439 | 18.1439
G5.8 | Expenditure on Part 3 Strategic Capacity - water | £m | I | 9.7634 | 19.9589 | 19.7553 | 14.4175 | 10.0238 | 1.2777 | A1 | A1 | A1 | A1 | A1 | A1
G5.9 | Expenditure on Part 3 Strategic Capacity - wastewater | £m | I | 3.3062 | 8.9976 | 17.9669 | 11.313 | 1.3207 | 0.72934 | A1 | A1 | A1 | A1 | A1 | A1
G5.10 | Total expenditure on Part 3 Strategic Capacity - water and wastewater | £m | C | 13.0696 | 28.9564 | 37.7222 | 25.7305 | 11.3445 | 2.007
G5.11 | Expenditure on Part 4 assets - water | £m | I | 3.9131 | 4.3567 | 3.6547 | 1.8961 | 1.8872 | 1.2134 | A1 | A1 | A1 | A1 | A1 | A1
G5.12 | Expenditure on Part 4 assets - wastewater | £m | I | 35.6998 | 37.2542 | 57.9506 | 53.6003 | 77.2952 | 71.688 | A1 | A1 | A1 | A1 | A1 | A1
G5.13 | Total expenditure on Part 4 assets - water and wastewater | £m | C | 39.6129 | 41.6109 | 61.6053 | 55.4964 | 79.1824 | 72.9013
G5.14 | Total gross expenditure on growth - (RCC + Part 3 strategic capacity + Part 4) | £m | C | 77.2467 | 88.7095 | 117.4714 | 104.4766 | 108.6707 | 93.0522
Service Relocations
G5.15 | Service Relocations Water | £m | I | 3.5695 | 8.7764 | 4.3547 | 1.2936 | 0.91067 | 0.91067 | A1 | A1 | A1 | A1 | A1 | A1
G5.16 | Service Relocations Wastewater | £m | I | 0.77459 | 1.7983 | 1.6604 | 0.69517 | 0.51825 | 0.51825 | A1 | A1 | A1 | A1 | A1 | A1
G5.17 | Service Relocations Water Contributions | £m | I | -6.745 | -5.8595 | -5.8595 | -5.8595 | -5.8595 | -5.8595 | A1 | B1 | B1 | B1 | B1 | B1
G5.18 | Service Relocations Wastewater Contributions | £m | I | -3.4747 | -3.0185 | -3.0185 | -3.0185 | -3.0185 | -3.0185 | A1 | B1 | B1 | B1 | B1 | B1
G5.19 | Net Service Relocations | £m | C | -5.8756 | 1.6967 | -2.8629 | -6.8892 | -7.4491 | -7.4491
Gross Growth expenditure
G5.19a | Total gross expenditure on growth and service relocations | £m | C | 71.3711 | 90.4062 | 114.6085 | 97.5873 | 101.2217 | 85.6032
G5.19b | Total gross expenditure on growth and service relocations (excluding reasonable cost contributions) | £m | C | 46.8069 | 72.264 | 96.4646 | 74.3376 | 83.0778 | 67.4593
Growth income (Infrastructure charge)
G5.20 | Water household infrastructure charge income | £m | I | 9.7321 | 9.3232 | 9.4071 | 9.4917 | 9.5772 | 9.6634 | A1 | A1 | A1 | A1 | A1 | A1
G5.21 | Water non-household infrastructure charge income | £m | I | 0.23477 | 0.1746 | 0.17617 | 0.17775 | 0.17935 | 0.18097 | A1 | A1 | A1 | A1 | A1 | A1
G5.22 | Wastewater household infrastructure charge income | £m | I | 9.0469 | 8.857 | 8.9367 | 9.0171 | 9.0983 | 9.1802 | A1 | A1 | A1 | A1 | A1 | A1
G5.23 | Wastewater non-household infrastructure charge income | £m | I | 0.017365 | 0.049582 | 0.050029 | 0.050479 | 0.050933 | 0.051391 | A1 | A1 | A1 | A1 | A1 | A1
G5.24 | Total infrastructure charge income | £m | C | 19.0311 | 18.4043 | 18.57 | 18.7371 | 18.9057 | 19.0759
Growth expenditure (net of income)
G5.25 | Total net growth expenditure | £m | C | 52.34 | 72.0018 | 96.0385 | 78.8502 | 82.3159 | 66.5273
G5.26 | Total net growth expenditure (excluding reasonable cost contributions) | £m | C | 27.7758 | 53.8597 | 77.8946 | 55.6005 | 64.172 | 48.3834
Growth - properties and populations
G5.27 | Number of new household properties connected to the water network | Nr | I | 23172 | 22198 | 22397.782 | 22599.362 | 22802.7563 | 23007.9811 | A1 | A1 | A1 | A1 | A1 | A1
G5.28 | Number of new non-household properties connected to the water network | Nr | I | 559 | 415.708 | 419.4494 | 423.2244 | 427.0334 | 430.8767 | A1 | A1 | A1 | A1 | A1 | A1
G5.29 | Total number of new properties connected to the water network | Nr | C | 23731 | 22613.708 | 22817.2314 | 23022.5865 | 23229.7897 | 23438.8578
G5.30 | Number of new household properties connected to the wastewater network | Nr | I | 21540 | 21088.1 | 21277.8929 | 21469.3939 | 21662.6185 | 21857.582 | A1 | A1 | A1 | A1 | A1 | A1
G5.31 | Number of new non-household properties connected to the wastewater network | Nr | I | 41 | 118.053 | 119.1155 | 120.1875 | 121.2692 | 122.3606 | A1 | A1 | A1 | A1 | A1 | A1
G5.32 | Total number of new properties connected to the wastewater network | Nr | C | 21581 | 21206.153 | 21397.0084 | 21589.5815 | 21783.8877 | 21979.9427
G5.33 | Number of new household properties receiving reasonable cost contributions - water | Nr | I | 28296 | 26836.1878 | 27077.7135 | 27321.4129 | 27567.3056 | 27815.4114 | A1 | A1 | A1 | A1 | A1 | A1
G5.34 | Number of new non-household properties receiving reasonable cost contributions - water | Nr | I | 12 | 502.5686 | 507.0917 | 511.6556 | 516.2605 | 520.9068 | A1 | A1 | A1 | A1 | A1 | A1
G5.35 | Total number of properties receiving reasonable cost contributions - water Part 2 | Nr | C | 28308 | 27338.7564 | 27584.8052 | 27833.0685 | 28083.5661 | 28336.3182
G5.36 | Number of new household properties receiving reasonable cost contributions - wastewater | Nr | I | 14580 | 8791.7671 | 8870.893 | 8950.731 | 9031.2876 | 9112.5692 | A1 | A1 | A1 | A1 | A1 | A1
G5.37 | Number of new non-household properties receiving reasonable cost contributions - wastewater | Nr | I | 95 | 49.2171 | 49.66 | 50.107 | 50.5579 | 51.0129 | A1 | A1 | A1 | A1 | A1 | A1
G5.38 | Total number of properties receiving reasonable cost contributions - wastewater Part 2 | Nr | C | 14675 | 8840.9842 | 8920.553 | 9000.838 | 9081.8455 | 9163.5821
G5.39 | Number of household property infrastructure charge payments - water | Nr | I | 23172 | 22198 | 22397.782 | 22599.362 | 22802.7563 | 23007.9811 | A1 | A1 | A1 | A1 | A1 | A1
G5.40 | Number of non-household property infrastructure charge payments - water | Nr | I | 559 | 415.708 | 419.4494 | 423.2244 | 427.0334 | 430.8767 | A1 | A1 | A1 | A1 | A1 | A1
G5.41 | Total number of infrastructure charge payments - water | Nr | C | 23731 | 22613.708 | 22817.2314 | 23022.5865 | 23229.7897 | 23438.8578
G5.42 | Number of household property infrastructure charge payments - wastewater | Nr | I | 21540 | 21088.1 | 21277.8929 | 21469.3939 | 21662.6185 | 21857.582 | A1 | A1 | A1 | A1 | A1 | A1
G5.43 | Number of non-household property infrastructure charge payments - wastewater | Nr | I | 41 | 118.053 | 119.1155 | 120.1875 | 121.2692 | 122.3606 | A1 | A1 | A1 | A1 | A1 | A1
G5.44 | Total number of property infrastructure charge - wastewater | Nr | C | 21581 | 21206.153 | 21397.0084 | 21589.5815 | 21783.8877 | 21979.9427
G5.45 | Additional population equivalent served from new Part 4 investment - water | Pe | I | 0 | 0 | 0 | 0 | 0 | 0 | B1 | B1 | B1 | B1 | B1 | B1
G5.46 | Additional population equivalent served from new Part 4 investment - wastewater | Pe | I | 3699 | 21932 | 22898 | 22898 | 22898 | 22898 | B1 | B1 | B1 | B1 | B1 | B1
Prepared by: …………………………………….……………………………….. |  |  | Date: ……………………
Checked by: …………………………….………………………………………….. |  |  | Date: ……………………
Authorised by: …………………………….…………………………………………..

## G7
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2022
SECTION G: INVESTMENT MONITORING
Table G7: Repair, Refurbishment and Asset Replacement - Disaggregation by Management Approach
Line Ref. | Description | Units | Field Type | Management Approaches included within the Group | Actual Year 2017-18 | Actual Year 2018-19 | Actual Year 2019-20 | Actual Year 2020-21 | Actual year 2021-22 | Forecast year 2022-23 | Forecast year 2023-24 | Forecast year 2024-25 | Forecast year 2025-26 | Forecast year 2026-27 | Total for SR21-27
|  |  |  | 1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
CPI inflation assumption
G7.001 | Cost inflation (RPI until 2021 and CPI from 2021/22; financial year average) | % | I |  |  | 3.06% | 2.588% | 1.213% | 3.98% | 11.5% | 8.5% | 1.5% | 1% | 1.5%
G7.002 | Inflation index (2017/18 base year) | Nr. | I/C |  | 1 | 1.0306 | 1.0573 | 1.0701 | 1.1127 | 1.2406 | 1.3461 | 1.3663 | 1.38 | 1.4007
| Management approach group 1 (Projected outturn prices) |  |  | Bioresource
G7.003 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | MA024 |  |  |  |  | 3.8944 | 4.3423 | 4.7114 | 4.782 | 4.8299 | 4.9023 | 27.4623
G7.004 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.005 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 4.8217 | 5.3761 | 5.8331 | 5.9206 | 5.9798 | 6.0695 | 34.0009
G7.006 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0.77591 | 0.26566 | 1.2749 | 3.8818 | 3.9595 | 4.0387 | 14.1964
G7.007 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0.20597 | 0.65214 | 1.2873 | 1.2407 | 2.1417 | 1.2128 | 6.7406
G7.008 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 2.2291 | 3.0519 | 1.8246 | 2.3179 | 3.7097 | 2.3066 | 15.4398
| Management approach group 2 (Projected outturn prices) |  |  | Common Asset groups
G7.009 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | MA011, MA013, MA018, MA022, MA044, MA068, MA082, MA089, MA091, MA092, MA096 |  |  |  |  | 30.7963 | 34.3379 | 37.2566 | 37.8154 | 38.1936 | 38.7665 | 217.1663
G7.010 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.011 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 59.9258 | 66.8173 | 72.4968 | 73.5842 | 74.3201 | 75.4349 | 422.579
G7.012 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 24.683 | 51.0516 | 51.9951 | 17.8361 | 18.2744 | 17.6884 | 181.5285
G7.013 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 2.8818 | 5.0029 | 6.2288 | 9.9352 | 10.802 | 4.1008 | 38.9514
G7.014 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 14.9738 | 25.6469 | 59.6098 | 66.9633 | 99.5088 | 64.7276 | 331.4302
| Management approach group 3 (Projected outturn prices) |  |  | Customer & Community
G7.015 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | _MA_proj_app_CEFS, MA_proj_app |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.016 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.017 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.018 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.019 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.020 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Management approach group 4 (Projected outturn prices) |  |  | Environmental improvement
G7.021 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | IR 18, MA005, MA076, MA084, MA085, PA |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.022 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.023 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.024 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.025 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0.0013359 | -0.0013276 | 0 | 0 | 0 | 0 | 8.3239e-06
G7.026 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0.00030254 | 0.0022401 | 0 | 0 | 0 | 0 | 0.0025426
| Management approach group 5 (Projected outturn prices) |  |  | Flourishing Scotland
G7.027 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | _MA_proj_app_CEFS, MA102, MA103, PA |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.028 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.029 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.030 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.031 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.032 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Management approach group 6 (Projected outturn prices) |  |  | Managing Flood Risk
G7.033 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | IR 18, MA020 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.034 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.035 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.036 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.037 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0.065708 | 0.010022 | 0.017335 | 0.097414 | 0.074058 | 0.037983 | 0.30252
G7.038 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Management approach group 7 (Projected outturn prices) |  |  | Net Zero
G7.039 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | _MA_proj_app_CEFS, _MA_proj_app_WW, MA027, MA056, MA077, PA |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.040 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.041 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 1.5746 | 1.7557 | 1.9049 | 1.9335 | 1.9528 | 1.9821 | 11.1036
G7.042 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0.0070051 | 0 | 0 | 0 | 0 | 0 | 0.0070051
G7.043 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | -0.0013044 | 0 | 0 | 0 | 0 | 0 | -0.0013044
G7.044 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0.844 | 2.0069 | 2.874 | 0.37032 | 0.35236 | 0.35865 | 6.8063
| Management approach group 8 (Projected outturn prices) |  |  | Other Services
G7.045 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | MA029, MA034, MA048, MA053, MA054, MA066, MA071, PA |  |  |  |  | 0.18545 | 0.20677 | 0.22435 | 0.22772 | 0.22999 | 0.23344 | 1.3077
G7.046 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.047 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 72.9341 | 81.3215 | 88.2338 | 89.5573 | 90.4529 | 91.8097 | 514.3094
G7.048 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0.02811 | 0.08022 | 0.13591 | 0.13863 | 0.14141 | 0.14423 | 0.66852
G7.049 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 8.1297 | 11.1131 | 15.1319 | 15.8153 | 6.8273 | 2.7711 | 59.7884
G7.050 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 38.2485 | 74.0325 | 89.0006 | 93.5438 | 53.6598 | 38.99 | 387.4753
| Management approach group 8 (Projected outturn prices) |  |  | Overheads
G7.051 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | SR21_Prog_Over |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.052 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.053 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.054 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 6.7062e-05 | 0 | 2.4e-07 | 2.4e-07 | 2.4e-07 | 2.4e-07 | 6.8022e-05
G7.055 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | -1.1466 | -0.18576 | -0.24277 | 1.5196 | 0 | 0 | -0.05551
G7.056 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0.49212 | -0.068374 | 0.012182 | -0.00049656 | -0.00049656 | -0.00049656 | 0.43444
| Management approach group 9 (Projected outturn prices) |  |  | PFI
G7.057 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | _MA_proj_app_WW, PA |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.058 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.059 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.060 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.061 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.062 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0.27546 | 0.66319 | 0.056405 | 0 | 0 | 0 | 0.99506
| Management approach group 10 (Projected outturn prices) |  |  | RCC
G7.063 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | RCC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.064 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.065 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.066 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.067 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.068 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Management approach group 11 (Projected outturn prices) |  |  | Resilience & Growth
G7.069 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | IR 18, MA026, MA032, MA065, MA087, PA |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.070 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.071 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 4.0137 | 4.4753 | 4.8557 | 4.9285 | 4.9778 | 5.0524 | 28.3033
G7.072 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0.00067821 | 0.02 | 0 | 0 | 0 | 0 | 0.020678
G7.073 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0.078456 | 0.23923 | 0.26462 | 1.5205 | 1.9986 | 4.3979 | 8.4994
G7.074 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0.77846 | 0.51883 | 0.77007 | 0.19979 | 0.0087371 | 0.0014185 | 2.2773
| Management approach group 12 (Projected outturn prices) |  |  | sludge treatment
G7.075 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | _MA_proj_app_WW, PA |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.076 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.077 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.078 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.079 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.080 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0.35669 | 0.10837 | 0.21464 | 0.16532 | 6.1341 | 14.5726 | 21.5517
| Management approach group 13 (Projected outturn prices) |  |  | SR15
G7.081 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | _SR15, IR 18 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.082 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.083 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.084 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.085 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.086 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Management approach group 14 (Projected outturn prices) |  |  | Transformation
G7.087 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | MA_proj_app, MA104 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.088 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.089 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 60.0757 | 66.9844 | 72.6781 | 73.7682 | 74.5059 | 75.6235 | 423.6359
G7.090 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.091 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.092 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0 | 30.7575 | 12.5784 | 6.7216 | 6.856 | 6.9932 | 63.9066
| Management approach group 15 (Projected outturn prices) |  |  | Water Quality
G7.093 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | _MA_proj_app_W, IR 18, MA006, MA016, MA028, MA033, MA037, MA046, MA052, MA081, MA093, MA094, MA095, MA100 |  |  |  |  | 50.5442 | 56.3568 | 61.1471 | 62.0643 | 62.685 | 63.6252 | 356.4227
G7.094 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.095 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 72.2022 | 80.5054 | 87.3484 | 88.6586 | 89.5452 | 90.8884 | 509.1483
G7.096 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 18.8921 | 18.5089 | 24.6864 | 30.7273 | 31.9749 | 31.8557 | 156.6452
G7.097 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 26.6611 | 35.214 | 32.5261 | 27.0164 | 27.7247 | 8.4977 | 157.64
G7.098 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 64.695 | 59.3991 | 47.4306 | 69.6056 | 78.0855 | 54.3857 | 373.6016
| Management approach group 16 (Projected outturn prices) |  |  | Water Quality (lead)
G7.099 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | IR 18, MA041 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.100 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.101 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 0.23156 | 0.25819 | 0.28013 | 0.28434 | 0.28718 | 0.29149 | 1.6329
G7.102 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.103 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.104 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0 | 0.023416 | 0.1957 | 0.19962 | 0.20361 | 0.20768 | 0.83003
| Management approach group 17 (Projected outturn prices) |  |  | water resources
G7.105 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | _MA_proj_app_W, IR 18, MA063 |  |  |  |  | 0.18545 | 0.20677 | 0.22435 | 0.22772 | 0.22999 | 0.23344 | 1.3077
G7.106 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.107 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 0.31472 | 0.35091 | 0.38074 | 0.38645 | 0.39031 | 0.39617 | 2.2193
G7.108 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0.020039 | 0.04072 | 0.20382 | 0.20789 | 0.21205 | 0.21629 | 0.90081
G7.109 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0.00095652 | 0.10555 | 0.13 | 0 | 0 | 0 | 0.23651
G7.110 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0.51709 | 0.26603 | 0.51808 | 0.51759 | 0.52729 | 0.53719 | 2.8833
| Management approach group 18 (Projected outturn prices) |  |  | Water Supply
G7.111 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | MA001, MA004, MA015, MA025, MA058, MA060, MA070, MA073, MA074, MA080, MA098, MA099, PA |  |  |  |  | 42.8979 | 47.8312 | 51.8968 | 52.6753 | 53.202 | 54.0001 | 302.5032
G7.112 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.113 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 152.674 | 170.2315 | 184.7011 | 187.4717 | 189.3464 | 192.1866 | 1076.6111
G7.114 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 55.6089 | 59.4565 | 60.6692 | 23.6165 | 27.8965 | 21.3411 | 248.5887
G7.115 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 22.2635 | 38.4596 | 24.8654 | 18.8871 | 16.7573 | 10.0176 | 131.2506
G7.116 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 34.5899 | 67.5278 | 71.8756 | 44.2085 | 44.1835 | 37.42 | 299.8052
| Management approach group 19 (Projected outturn prices) |  |  | WW Collection
G7.117 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | _MA_proj_app_WW, IR 18, MA002, MA003, MA012, MA014, MA023, MA039, MA062 |  |  |  |  | 33.0618 | 36.8639 | 39.9973 | 40.5972 | 41.0032 | 41.6183 | 233.1416
G7.118 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.119 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 64.4922 | 71.9088 | 78.0211 | 79.1914 | 79.9833 | 81.183 | 454.7797
G7.120 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 36.0011 | 32.3567 | 38.973 | 24.6476 | 27.0041 | 28.3479 | 187.3303
G7.121 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 22.9496 | 17.6527 | 16.9313 | 9.8113 | 5.6954 | 3.6747 | 76.715
G7.122 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 14.2911 | 18.8947 | 31.0196 | 44.3296 | 54.7696 | 50.4995 | 213.8041
| Management approach group 20 (Projected outturn prices) |  |  | WW Treatment
G7.123 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | MA017, MA021, MA035, MA036, MA042, MA043, MA049, MA057 |  |  |  |  | 19.3829 | 21.6119 | 23.4489 | 23.8007 | 24.0387 | 24.3993 | 136.6824
G7.124 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.125 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 70.6123 | 78.7327 | 85.425 | 86.7063 | 87.5734 | 88.887 | 497.9366
G7.126 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 15.5825 | 18.2939 | 15.2738 | 9.1133 | 10.8477 | 10.7879 | 79.8991
G7.127 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 12.56 | 10.9212 | 5.0715 | 7.474 | 9.1384 | 2.8898 | 48.0549
G7.128 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 45.2179 | 51.544 | 46.8253 | 50.042 | 65.9508 | 61.6768 | 321.2569
Totals across all management approaches (Projected outturn prices)
G7.129 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | £m | C | [5 empty] | 180.9484 | 201.7574 | 218.9068 | 222.1904 | 224.4123 | 227.7785 | 1275.9939
G7.130 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | £m | C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.131 | Projected expenditure for Tier 2 replacement from the original management approaches | £m | C | [5 empty] | 563.8724 | 628.7178 | 682.1588 | 692.3912 | 699.3151 | 709.8048 | 3976.26
G7.132 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | £m | C | [5 empty] | 151.5994 | 180.074 | 193.2121 | 110.1692 | 120.3105 | 114.4201 | 869.7853
G7.133 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | £m | C | [5 empty] | 94.6502 | 119.1834 | 102.2116 | 93.3177 | 81.1593 | 37.6003 | 528.1225
G7.134 | Latest forecast expenditure for Tier 2 replacement | £m | C | [5 empty] | 217.5095 | 334.3749 | 364.8056 | 379.1844 | 413.9495 | 332.6764 | 2042.5003
Totals across all management approaches (2017/18 prices; CPI based)
G7.135 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | £m | C | [5 empty] | 162.6225 | 162.6225 | 162.6225 | 162.6225 | 162.6225 | 162.6225 | 975.735
G7.136 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | £m | C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.137 | Projected expenditure for Tier 2 replacement from the original management approaches | £m | C | [5 empty] | 506.7652 | 506.7652 | 506.7652 | 506.7652 | 506.7652 | 506.7652 | 3040.5914
G7.138 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | £m | C | [5 empty] | 136.2459 | 145.145 | 143.5343 | 80.6335 | 87.1841 | 81.6903 | 674.4331
G7.139 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | £m | C | [5 empty] | 85.0643 | 96.0654 | 75.9314 | 68.2998 | 58.8129 | 26.8447 | 411.0185
G7.140 | Latest forecast expenditure for Tier 2 replacement | £m | C | [5 empty] | 195.4808 | 269.5161 | 271.0085 | 277.5273 | 299.9724 | 237.5143 | 1551.0195
Prepared by: …………………………………………….. |  |  | Date: ……………………
Checked by: …………………………………………….. |  |  | Date: ……………………
Authorised by:
Check
G7.141 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | £m | C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
G7.142 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | £m | C | bar: 5 to 11
G7.143 | Projected expenditure for Tier 2 replacement from the original management approaches | £m | C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
G7.144 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | £m | C | [5 empty] | 151.5994 | 180.074 | 193.2121 | 110.1692 | 120.3105 | 114.4201
G7.145 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | £m | C | [5 empty] | 94.6502 | 119.1834 | 102.2116 | 93.3177 | 81.1593 | 37.6003
G7.146 | Latest forecast expenditure for Tier 2 replacement | £m | C | [5 empty] | 217.5095 | 334.3749 | 364.8056 | 379.1844 | 413.9495 | 332.6764

## G8
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2022
SECTION G: INVESTMENT MONITORING
Table G8: Investment and Capital Price Inflation
Line | Description | Units | Field | Actual Year 2017-18 | Actual Year 2018-19 | Actual Year 2019-20 | Actual Year 2020-21 | Actual Year 2021-22 | Forecast Year 2022-23 | Forecast Year 2023-24 | Forecast Year 2024-25 | Forecast Year 2025-26 | Forecast Year 2026-27 | Total SR21
Ref. |  |  | Type
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Inflation assumptions
G8.1 | Capital price inflation | % | I |  | 3.06% | 2.588% | 1.213% | 5.98% | 13.8% | 10.2% | 1.8% | 1% | 1.5%
G8.2 | Capital price inflation factor | Nr. | I/C | 1 | 1.0306 | 1.0573 | 1.0701 | 1.1341 | 1.2906 | 1.4222 | 1.4478 | 1.4623 | 1.4843
G8.3 | Cost inflation (RPI until 2021 and CPI from 2021/22; financial year average) | % | I |  | 3.06% | 2.588% | 1.213% | 3.98% | 11.5% | 8.5% | 1.5% | 1% | 1.5%
G8.4 | Inflation index (2017/18 base year) | Nr. | I/C | 1 | 1.0306 | 1.0573 | 1.0701 | 1.1127 | 1.2406 | 1.3461 | 1.3663 | 1.38 | 1.4007
Repair and refurbishment (Tier 1a) and Tier 2 Investment
G8.5 | Repair and refurbishment (Tier 1a) and Tier 2 investment pre-efficiency (2017/18 prices) | £m | I |  |  |  |  | 578.8151 | 580.9103 | 471.5113 | 321.1475 | 371.027 | 230.3095
G8.6 | Repair and refurbishment (Tier 1a) and Tier 2 investment pre-efficiency (projected outturn prices based on capital price inflation) | £m | C |  |  |  |  | 656.4294 | 749.7207 | 670.6009 | 464.9694 | 542.5587 | 341.8371
G8.7 | Efficiency (projected outturn prices) | £m | I | bar: 4 to 9
G8.8 | Repair and refurbishment (Tier 1a) and Tier 2 investment post-efficiency (projected outturn prices) | £m | C |  |  |  |  | 656.4294 | 749.7207 | 670.6009 | 464.9694 | 542.5587 | 341.8371
G8.9 | Repair and refurbishment (Tier 1a) and Tier 2 investment post-efficiency (2017/18 prices; CPI based) | £m | C |  |  |  |  | 589.9483 | 604.2972 | 498.1791 | 340.3138 | 393.1702 | 244.0546 | 2669.9632
Completion investment
G8.10 | Completion investment post-efficiency (projected outturn prices) | £m | I |  |  |  |  | 117.9891 | 58.4025 | 26.0148 | 29.6452 | 1.9611 | 10.1673
G8.11 | Completion investment post-efficiency (2017/18 prices; CPI based) | £m | C |  |  |  |  | 106.0395 | 47.0742 | 19.326 | 21.6975 | 1.4211 | 7.2589 | 202.8172
Expenditure Totals (Gross)
G8.12 | Total Investment (projected outturn prices) | £m | C |  |  |  |  | 774.4184 | 808.1232 | 696.6157 | 494.6145 | 544.5197 | 352.0043
G8.13 | Total Investment (2017/18 prices) | £m | C |  |  |  |  | 695.9878 | 651.3714 | 517.5051 | 362.0113 | 394.5913 | 251.3135 | 2872.7804
Prepared by: …………………………………………….. |  |  | Date: ……………………
Checked by: …………………………………………….. |  |  | Date: ……………………
Authorised by: