## G1 - Summary
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2024
SECTION G: INVESTMENT MONITORING
Table G1: Summary - Investment
|  |  |  | Actual and Forecast | [8 empty] | Confidence Grades
Line Ref. | Description | Units | Field Type | Actual Pre | Actual Year | Actual Year | Report Year | Forecast Year | Forecast Year | Forecast Year | Forecast Post | SR21 Total | Actual Pre | Actual Year | Actual Year | Report Year | Forecast Year | Forecast Year | Forecast Year | Forecast Post
|  |  |  | 2021-22 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2026-27 |  | 2021-22 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2026-27
1 | Inspections and testing
G1.01 | Inspections and testing - Water | £m | I | 6.845 | 11.6265 | 15.8472 | 16.9729 | 22.3777 | 27.4447 | 12.8537 | 4.6203 | 107.1226 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.02 | Inspections and testing - Wastewater | £m | I | 6.527 | 13.1877 | 14.2334 | 19.5335 | 19.9207 | 33.8666 | 11.5285 | 7.7448 | 112.2703 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.03 | Inspections and testing - Foul sewage only | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.04 | Inspections and testing - Surface water only | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.05 | Inspections and testing - General | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.06 | Total Inspections and testing | £m | C | 13.372 | 24.8142 | 30.0806 | 36.5063 | 42.2984 | 61.3113 | 24.3821 | 12.3651 | 219.3929
2 | Repair
G1.07 | Repair - Water | £m | I | 205.8484 | 104.1426 | 137.0265 | 185.0115 | 146.1671 | 120.7474 | 140.9428 | 60.1361 | 834.0379 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.08 | Repair - Wastewater | £m | I | 92.9813 | 76.4524 | 100.2638 | 119.6349 | 103.1347 | 89.8186 | 93.1138 | 19.4793 | 582.4183 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.09 | Repair - Foul sewage only | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.10 | Repair - Surface water only | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.11 | Repair - General | £m | I | -1.6199 | 1.8161 | 2.3685 | 0.14328 | 2.5699 | 2.0262 | 1.2788 | 0.12422 | 10.2028 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.12 | Total Repair | £m | C | 297.2097 | 182.4111 | 239.6588 | 304.7897 | 251.8717 | 212.5922 | 235.3354 | 79.7396 | 1426.659
3 | Refurbishment
G1.13 | Refurbishment - Water | £m | I | 87.7723 | 16.598 | 22.3759 | 33.181 | 50.9194 | 51.7178 | 46.2714 | 32.758 | 221.0635 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.14 | Refurbishment - Wastewater | £m | I | 41.6032 | 15.0474 | 21.4566 | 39.912 | 50.4102 | 50.3991 | 31.4762 | 10.4991 | 208.7016 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.15 | Refurbishment - Foul sewage only | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.16 | Refurbishment - Surface water only | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.17 | Refurbishment - General | £m | I | 0.6547 | 0.71987 | 0.97102 | 1.6774 | 4.8328 | 3.1274 | 1.1198 | 0 | 12.4483 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.18 | Total Refurbishment | £m | C | 130.0302 | 32.3653 | 44.8035 | 74.7704 | 106.1624 | 105.2443 | 78.8674 | 43.2572 | 442.2133
4 | Asset Replacement
G1.19 | Water services | £m | I | 410.815 | 116.4837 | 130.2855 | 162.9424 | 131.4123 | 159.4963 | 123.7871 | 159.8648 | 824.4074 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.20 | Wastewater services | £m | I | 287.7203 | 71.1104 | 76.0269 | 123.9452 | 68.9117 | 81.9249 | 127.6428 | 270.9233 | 549.5619 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.21 | Foul sewage only services | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.22 | Surface water only services | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.23 | General services | £m | I | 134.9298 | 32.8995 | 46.8942 | 12.4774 | 126.4987 | 97.992 | 76.8324 | 0.90876 | 393.5942 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.24 | Total Asset Replacement | £m | C | 833.4651 | 220.4935 | 253.2067 | 299.365 | 326.8228 | 339.4132 | 328.2623 | 431.6968 | 1767.5635
5 | Growth
G1.25 | Strategic capacity - water (Part 4) | £m | BF / I | 10.8837 | 0.96259 | 0.62125 | 1.2888 | 9.7487 | 9.8694 | 5.8744 | 0.024539 | 28.3651 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.26 | Strategic capacity - wastewater (Part 4) | £m | BF / I | 90.239 | 35.0858 | 45.9955 | 43.4599 | 16.7687 | 46.0758 | 40.8236 | 182.8005 | 228.2093 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.27 | Strategic water network capacity (Part 3) | £m | BF / I | 25.1491 | 10.1519 | 16.0706 | 13.1753 | 8.5799 | 4.3372 | 3.7288 | 39.69 | 56.0437 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.28 | Strategic wastewater network capacity (Part 3) | £m | BF / I | 11.6389 | 1.9824 | 3.7966 | 9.9095 | 16.4788 | 26.5409 | 22.1249 | 30.2626 | 80.8332 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.29 | Strategic foul sewerage network capacity (Part 3) | £m | BF / I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.30 | Strategic SWD network capacity (Part 3) | £m | BF / I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.31 | Service relocations (water and wastewater) | £m | I |  | 4.2824 | 3.7149 | 4.2115 | 23.1116 | 15.591 | 10.7568 |  | 61.6683 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.32 | Total Growth | £m | C | 137.9107 | 52.465 | 70.199 | 72.045 | 74.6877 | 102.4143 | 83.3085 | 252.7776 | 455.1195
6 | Enhancement
G1.33 | Water Quality | £m | BF / I | 77.3503 | 65.729 | 52.0554 | 58.6639 | 45.4556 | 51.0605 | 131.4053 | 657.8201 | 404.3696 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.34 | Water Environment | £m | BF / I | 34.125 | 13.9866 | 10.3681 | 21.7719 | 37.4496 | 84.6821 | 146.2204 | 356.0514 | 314.4788 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.35 | Climate Change Mitigation | £m | BF / I | 4.3095 | 3.2921 | 6.8078 | 15.1946 | 31.9665 | 27.0511 | 10.1326 | 8.2857 | 94.4447 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.36 | Circular Economy | £m | BF / I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.37 | Water Continuity | £m | BF / I | 13.1689 | 2.46 | 3.7384 | 8.0545 | 27.616 | 23.9646 | 18.3215 | 164.3223 | 84.155 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.38 | Managing Quantity of Flows | £m | BF / I | 62.9488 | 23.1885 | 28.0178 | 27.3452 | 21.9333 | 28.3045 | 35.3019 | 163.9774 | 164.0912 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.39 | Other Enhancements | £m | BF / I | 22.817 | 34.5982 | 79.8245 | 56.2258 | 85.0472 | 75.7892 | 56.419 | 109.2657 | 387.9039 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.40 | Total Enhancement | £m | C | 214.7194 | 143.2543 | 180.8121 | 187.256 | 249.4682 | 290.8519 | 397.8007 | 1459.7226 | 1449.4432
7 | Completion Programme
G1.41 | SR10 Completion | £m | I | 522.5936 | 7.1052 | 0.54794 | 12.7921 | 6.595 | 12.6754 | 7.2436 | 4.1302 | 46.9593 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.42 | SR15 Completion - Enhancement | £m | I | 493.5067 | 72.9584 | 32.5338 | 13.3645 | 16.1384 | 17.7125 | 2.4595 | 3.2853 | 155.1671 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.43 | SR15 Completion - Growth | £m | I | 22.2466 | 6.1342 | 5.2917 | 4.8497 | -8.4173 | 0 | 0 | 0 | 7.8583 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.44 | SR15 Completion - Asset Maintenance | £m | I | 132.2281 | 32.0903 | 21.9219 | 19.0077 | 4.3727 | 2.7848 | 0.094 | 0 | 80.2714 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.45 | Total Completion Programme | £m | C | 1170.575 | 118.2881 | 60.2952 | 50.014 | 18.6888 | 33.1727 | 9.7972 | 7.4156 | 290.2561
8 | Grants and Contributions
G1.46 | Grants for infrastructure assets | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.47 | Grants for non-infrastructure assets | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.48 | Contributions to infrastructure assets | £m | I | 0 | 10.2197 | 3.3754 | 2.9927 | 6.711 | 6.711 | 6.711 | 0 | 36.7208 | A1 | A1 | A1 | A1 | B1 | B1 | B1 | B1
G1.49 | Contributions to non-infrastructure assets | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.50 | Total capital contributions (excluding infrastructure charge contributions) | £m | C | 0 | 10.2197 | 3.3754 | 2.9927 | 6.711 | 6.711 | 6.711 | 0 | 36.7208
9 | Expenditure Totals
G1.51 | Inspections and testing | £m | C | 13.372 | 24.8142 | 30.0806 | 36.5063 | 42.2984 | 61.3113 | 24.3821 | 12.3651 | 219.3929
G1.52 | Repair | £m | C | 297.2097 | 182.4111 | 239.6588 | 304.7897 | 251.8717 | 212.5922 | 235.3354 | 79.7396 | 1426.659
G1.53 | Refurbishment | £m | C | 130.0302 | 32.3653 | 44.8035 | 74.7704 | 106.1624 | 105.2443 | 78.8674 | 43.2572 | 442.2133
G1.54 | Asset Replacement | £m | C | 833.4651 | 220.4935 | 253.2067 | 299.365 | 326.8228 | 339.4132 | 328.2623 | 431.6968 | 1767.5635
G1.55 | Growth | £m | C | 137.9107 | 52.465 | 70.199 | 72.045 | 74.6877 | 102.4143 | 83.3085 | 252.7776 | 455.1195
G1.56 | Enhancement | £m | C | 214.7194 | 143.2543 | 180.8121 | 187.256 | 249.4682 | 290.8519 | 397.8007 | 1459.7226 | 1449.4432
G1.57 | Completion Programme | £m | C | 1170.575 | 118.2881 | 60.2952 | 50.014 | 18.6888 | 33.1727 | 9.7972 | 7.4156 | 290.2561
G1.58 | Gross Investment | £m | C | 2797.2822 | 774.0915 | 879.0559 | 1024.7464 | 1070 | 1145 | 1157.7537 | 2286.9745 | 6050.6475
G1.59 | Total capital contributions (excluding infrastructure charge contributions) | £m | C | 0 | 10.2197 | 3.3754 | 2.9927 | 6.711 | 6.711 | 6.711 | 0 | 36.7208
G1.60 | Net Investment | £m | C | 2797.2822 | 763.8718 | 875.6805 | 1021.7537 | 1063.289 | 1138.289 | 1151.0427 | 2286.9745 | 6013.9267
G1.61 | Total Asset Additions | £m | C | 1523.2051 | 314.0074 | 311.3063 | 309.315 | 342.8447 | 426.439 | 490.9065 | 1719.9157 | 2194.8188
10 | Risk and Overhead Investment Breakdown
G1.62 | Direct costs | £m | I | [8 empty] | 5513.4189 | [7 empty] | A1
G1.63 | Project overheads allocated to projects | £m | I | [8 empty] | 429.2135 | [7 empty] | A1
G1.64 | Risk allowance | £m | I | [8 empty] | 108.0152 | [7 empty] | A1
G1.65 | Gross Investment | £m | C | [8 empty] | 6050.6475
11 | Primary Purpose Investment Breakdown
G1.66 | Water | £m | I | 1538.6694 | 410.6411 | 435.3787 | 530.1182 | 480.7154 | 499.8428 | 489.3589 | 1337.3215 | 2846.0551 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.67 | Wastewater (combined) | £m | I | 1094.4069 | 297.649 | 340.943 | 435.8049 | 373.1525 | 467.5625 | 544.7196 | 908.3067 | 2459.8314 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.68 | Foul sewage only | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.69 | Surface water only | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.70 | General | £m | I | 164.2059 | 65.8015 | 102.7343 | 58.8233 | 216.1321 | 177.5947 | 123.6751 | 41.3462 | 744.7609 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.71 | Gross Investment | £m | C | 2797.2822 | 774.0915 | 879.0559 | 1024.7464 | 1070 | 1145 | 1157.7537 | 2286.9745 | 6050.6475
12 | Planned and Responsive Repair & Refurbishment
G1.72 | Responsive repair and refurbishment investment previously expensed as operating expenditure ('Tier 1') | £m | I | 19.434 | 53 | 58.0953 | 61.3893 | 62.8626 | 64.497 | 65.787 | 0 | 365.6311 | B1 | B1 | B1 | B1 | B1 | B1 | B1 | B1
G1.73 | Remaining responsive repair and refurbishment investment ('Tier 1') | £m | I | 282.7254 | 97.5756 | 131.4042 | 167.9606 | 172.8049 | 173.3231 | 188.6917 | 83.8943 | 931.76 | B1 | B1 | B1 | B1 | B1 | B1 | B1 | B1
G1.74 | Planned repair and refurbishment investment ('Tier 2') | £m | I | 125.0805 | 64.2008 | 94.9629 | 150.2102 | 122.3667 | 80.0165 | 59.7241 | 39.1025 | 571.4812 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.75 | Total Repair and Refurbishment | £m | C | 427.2399 | 214.7764 | 284.4623 | 379.5601 | 358.0342 | 317.8366 | 314.2028 | 122.9968 | 1868.8723
13 | Tier Investment Breakdown
G1.76 | Tier 1a | £m | I | 308.9292 | 152.5446 | 191.339 | 235.8439 | 250 | 265.2 | 264.5827 | 85.2411 | 1359.5101 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.77 | Tier 2 - Pre Committed List | £m | I | 523.1094 | 28.0566 | 40.309 | 87.2362 | 298.9345 | 613.4853 | 738.1238 | 2165.1184 | 1806.1455 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.78 | Tier 2 - Committed List | £m | I | 1965.2436 | 593.4903 | 647.408 | 701.6664 | 521.0655 | 266.3147 | 155.0472 | 36.6149 | 2884.992 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.79 | Gross Investment | £m | C | 2797.2822 | 774.0915 | 879.0559 | 1024.7464 | 1070 | 1145 | 1157.7537 | 2286.9745 | 6050.6475
G1.80 | Tier 2 Investment for comparison to FD | £m | C | 1648.2857 | 367.9885 | 402.8938 | 456.5325 | 458.5004 | 499.7444 | 543.9195 | 1759.0182 | 2729.5792
14 | Comparison to Historical Investment Baseline
G1.81 | Water Reasonable Cost Contributions | £m | I | 62.177 | 10.0979 | 10.2697 | 8.0712 | 12.7899 | 11.3799 | 11.6702 | 3.5565 | 64.2787 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.82 | Wastewater Reasonable Cost Contributions | £m | I | 112.5827 | 14.7932 | 22.8942 | 25.0349 | 28.6111 | 21.4337 | 26.7185 | 0 | 139.4856 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.83 | Total Investment including Reasonable Cost Contributions | £m | C | 2972.0418 | 798.9826 | 912.2198 | 1057.8525 | 1111.401 | 1177.8137 | 1196.1423 | 2290.531 | 6254.4119
G1.84 | Infrastructure charge contributions for infrastructure assets | £m | I | 0 | 11.4288 | 17.0209 | 18.5 | 18.604 | 18.604 | 18.604 | 0 | 102.7617 | A1 | A1 | A1 | A1 | B1 | B1 | B1 | B1
G1.85 | Total capital contributions (excluding infrastructure charge contributions) | £m | C | 0 | 10.2197 | 3.3754 | 2.9927 | 6.711 | 6.711 | 6.711 | 0 | 36.7208 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.86 | Net Capital Investment | £m | C | 2972.0418 | 777.3341 | 891.8235 | 1036.3598 | 1086.086 | 1152.4987 | 1170.8273 | 2290.531 | 6114.9294
Prepared by: ……………………………………………...….. |  | Date: 07/10/2024
Checked by: ……………………………………………...….. |  | Date: 07/10/2024
Authorised by: …...........……………………...……............ |  | Date: 07/10/2024

## G2 - Replacement
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2024
SECTION G: INVESTMENT MONITORING
Table G2: Summary - Replacement | [36 empty] | Forecast based on IPS24.1 in AR24 | [6 empty] | Forecast based on IPS24.1 in AR24 |  |  |  | Forecast based on IPS24.1 in AR24
[5 empty] | Block A: Asset information | [8 empty] | Block B: Investment consistent with asset management policies | [5 empty] | Block C: Investment baseline (Investment Planning Scenario 23.2) | [12 empty] | Block D: Actual to date and updated forecast
Line ref. | Service | Functional activity | Asset category | Sub asset category | Asset units | Asset value (2017-18 prices) | CG | Asset stock | CG | Assumed asset life | CG | Annual run-rate (no.) for replacement | Annual run-rate (£) for replacement (2017-18 prices) | Projected expenditure from 2021-22 to 2026-27 (2017-18 prices) | Projected expenditure from 2027-28 to 2032-33 (2017-18 prices) | Projected expenditure from 2033-34 to 2038-39 (2017-18 prices) | Projected expenditure from 2039-40 to 2044-45 (2017-18 prices) | Projected expenditure from 2045-46 to 2050-51 (2017-18 prices) |  | Projected expenditure in investment baseline pre 2021-22 (2017-18 prices) | Projected expenditure in investment baseline in 2021-22 (2017-18 prices) | Projected expenditure in investment baseline in 2022-23 (2017-18 prices) | Projected expenditure in investment baseline in 2023-24 (2017-18 prices) | Projected expenditure in investment baseline in 2024-25 (2017-18 prices) | Projected expenditure in investment baseline in 2025-26 (2017-18 prices) | Projected expenditure in investment baseline in 2026-27 (2017-18 prices) | Projected expenditure from 2021-22 to 2026-27 (2017-18 prices) | Projected expenditure from 2027-28 to 2032-33 (2017-18 prices) | Projected expenditure from 2033-34 to 2038-39 (2017-18 prices) | Projected expenditure from 2039-40 to 2044-45 (2017-18 prices) | Projected expenditure from 2045-46 to 2050-51 (2017-18 prices) | Surplus/deficit relative to high-level asset replacement work (£) | Actual number of replacement interventions pre 2021-22 | Actual number of replacement interventions in 2021-22 | Actual number of replacement interventions in 2022-23 | Actual number of replacement interventions in 2023-24 | Projected number of replacement interventions in 2024-25 | Projected number of replacement interventions in 2025-26 | Projected number of replacement interventions in 2026-27 | Actual expenditure pre 2021-22 (2017-18 prices) | Actual expenditure in 2021-22 (2017-18 prices) | Actual expenditure in 2022-23 (2017-18 prices) | Actual expenditure in 2023-24 (2017-18 prices) | Projected expenditure in 2024-25 (2017-18 prices) | Projected expenditure in 2025-26 (2017-18 prices) | Projected expenditure in 2026-27 (2017-18 prices) | Projected expenditure from 2021-22 to 2026-27 (2017-18 prices) | Projected expenditure from 2027-28 to 2032-33 (2017-18 prices) | Projected expenditure from 2033-34 to 2038-39 (2017-18 prices) | Projected expenditure from 2039-40 to 2044-45 (2017-18 prices) | Projected expenditure from 2045-46 to 2050-51 (2017-18 prices) | Surplus/deficit relative to high-level asset replacement work (£)
[6 empty] | £m |  | nr |  | nr |  | nr | £m | £m | £m | £m | £m | £m |  | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | nr | nr | nr | nr | nr | nr | nr | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m
[6 empty] | 1 |  | 2 |  | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43
G2.01 | Water | Source | Raw Water Pumping | Civils | nr | 50.6163 | B4 | 417 | A3 | 80 | A3 |  | 0.6327 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -3.7962 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -3.7962
G2.02 |  |  | Raw Water Pumping | MEICA | nr | 35.7978 | B4 | 616 | A3 | 20 | A2 |  | 1.7899 | [6 empty] | 0 | 0.11083 | 0.25018 | 1.0923 | 0.36025 | 0.4806 | 0.53423 | 2.8284 | 0.26942 | 0 | 0 |  | -7.911 | [7 empty] | 0.21732 | 0.10679 | 0.25116 | 0.8248 | 0.44395 | -0.072266 | -0.03816 | 1.5163 | 0.0012061 | 0 | 0 |  | -9.2231
G2.03 |  |  | Raw Water Pumping | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.04 |  |  | Raw Water Pumping | Total |  | 86.4141 | B4 | [5 empty] | 2.4226 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.11083 | 0.25018 | 1.0923 | 0.36025 | 0.4806 | 0.53423 | 2.8284 | 0.26942 | 0 | 0 | 0 | -11.7072 | [7 empty] | 0.21732 | 0.10679 | 0.25116 | 0.8248 | 0.44395 | -0.072266 | -0.03816 | 1.5163 | 0.0012061 | 0 | 0 | 0 | -13.0193
G2.05 |  |  | Raw Water Mains | Raw water mains | km | 2102.5801 | B2 | 1678.821 | B2 | 115 | B3 | 14.5984 | 18.2833 | [6 empty] | 0 | 1.5389 | 0.14776 | 0.75635 | 0.07205 | 0 | 0.018708 | 2.5338 | 0.13015 | 0 | 0 |  | -107.1661 | 0 | 450 | 4267 | 0 | 12 | 3 | 1 | 0.71643 | 1.5389 | 0.14776 | 0.55848 | 0.35643 | 0.38867 | 0.092473 | 3.0827 | 0.44956 | 0 | 0 |  | -106.6171
G2.06 |  |  | Raw Water Mains | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.07 |  |  | Raw Water Mains | Total | km | 2102.5801 | B2 | 1678.821 | B2 | 115 | B3 |  | 18.2833 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1.5389 | 0.14776 | 0.75635 | 0.07205 | 0 | 0.018708 | 2.5338 | 0.13015 | 0 | 0 | 0 | -107.1661 | [7 empty] | 0.71643 | 1.5389 | 0.14776 | 0.55848 | 0.35643 | 0.38867 | 0.092473 | 3.0827 | 0.44956 | 0 | 0 | 0 | -106.6171
G2.08 |  |  | Infinite-Life Assets | Dams and impounding reservoirs | nr | 1579.3618 | C4 | 199 | C4 |  |  |  | 0 | [6 empty] | 0 | 2.891 | 1.4895 | 3.3415 | 1.9362 | 1.6025 | 3.2878 | 14.5485 | 0.53279 | 0 | 0 |  | 14.5485 | [7 empty] | 6.1679 | 2.1386 | 3.5949 | 8.2102 | 7.0566 | 11.0818 | 10.6069 | 42.689 | 8.8942 | 0 | 0 |  | 42.689
G2.09 |  |  | Infinite-Life Assets | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0.31804 | 0.38269 | 0.081414 | 0.22321 | 0.58892 | 0.95578 | 2.5501 | 0.5667 | 0 | 0 |  | 2.5501 | [7 empty] | 0 | 0.31804 | 0.38295 | 0.19681 | 0.32236 | 0.13856 | 0.52294 | 1.8817 | 0.77606 | 0 | 0 |  | 1.8817
G2.10 |  |  | Infinite-Life Assets | Raw water storage (Civils) | [8 empty] | 0 | [6 empty] | 0 | 0.00015334 | 0.00056596 | 0.0052687 | 0 | 0 | 0 | 0.005988 | 0 | 0 | 0 |  | 0.005988 | [7 empty] | 0.02123 | 0.00015334 | 0.00056595 | 0.037452 | 0.0051368 | 0 | 0 | 0.043308 | 0 | 0 | 0 |  | 0.043308
G2.11 |  |  | Infinite-Life Assets | Aqueduct | km | 2102.5801 | B2 | 1678.821 | B2 |  |  |  | 0 | [6 empty] | 0 | 0.00045273 | 0.052782 | -1.4463 | -0.8428 | 1.6143 | 1.856 | 1.2345 | 2.7964 | 0 | 0 |  | 1.2345 | [7 empty] | 0.01669 | 0.00045272 | 0.052781 | 0.20197 | -0.46567 | 1.595 | 3.1283 | 4.5128 | 2.8302 | 0 | 0 |  | 4.5128
G2.12 |  |  | Infinite-Life Assets | Raw water intakes (Gravity) | nr | 25.9001 | C5 | 263 | C5 |  |  |  | 0 | [6 empty] | 0 | 0.71994 | 0.53467 | 1.3825 | 1.0674 | 0.92485 | 1.0076 | 5.637 | 0.28152 | 0 | 0 |  | 5.637 | [7 empty] | 0.8924 | 0.71993 | 0.52977 | 0.81683 | 2.0659 | 1.0708 | 0.36716 | 5.5704 | 0.28275 | 0 | 0 |  | 5.5704
G2.13 |  |  | Infinite-Life Assets | Catchment | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0.0048345 | 0.0032426 | 0.022279 | 0.026131 | 0.056487 | 0 | 0 | 0 |  | 0.056487 | [7 empty] | 0 | 0 | 0 | 0 | 0.025241 | 0.018829 | 0.012416 | 0.056486 | 0 | 0 | 0 |  | 0.056486
G2.14 |  |  | Infinite-Life Assets | Total |  | 3707.842 | C4 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3.9296 | 2.4602 | 3.3692 | 2.3873 | 4.7529 | 7.1334 | 24.0326 | 4.1774 | 0 | 0 | 0 | 24.0326 | [7 empty] | 7.0983 | 3.1772 | 4.561 | 9.4632 | 9.0095 | 13.905 | 14.6377 | 54.7536 | 12.7832 | 0 | 0 | 0 | 54.7536
G2.15 |  |  | Ground Water Sources (Pumped) | Civils | nr | 9.8642 | B4 | 247 | A3 | 80 | A3 |  | 0.1233 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -0.73982 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -0.73982
G2.16 |  |  | Ground Water Sources (Pumped) | MEICA | nr | 14.0521 | B4 | 309 | A3 | 20 | A2 |  | 0.7026 | [6 empty] | 0 | 0.619 | 0.5682 | 0.45516 | 0.55637 | 0.40493 | 0.32371 | 2.9274 | 0.0031039 | 0 | 0 |  | -1.2882 | [7 empty] | 2.2795 | 0.47991 | 0.36925 | 1.1268 | 1.0152 | 0.82639 | 0.88108 | 4.6987 | 0.26391 | 0 | 0 |  | 0.48306
G2.17 |  |  | Ground Water Sources (Pumped) | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.18 |  |  | Ground Water Sources (Pumped) | Total |  | 23.9163 | B4 | [5 empty] | 0.82591 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.619 | 0.5682 | 0.45516 | 0.55637 | 0.40493 | 0.32371 | 2.9274 | 0.0031039 | 0 | 0 | 0 | -2.0281 | [7 empty] | 2.2795 | 0.47991 | 0.36925 | 1.1268 | 1.0152 | 0.82639 | 0.88108 | 4.6987 | 0.26391 | 0 | 0 | 0 | -0.25676
G2.19 |  | Water Treatment Works | Water Treatment Works (Civils) | Civils | nr | 1603.6435 | C4 | 6712 | A2 | 80 | A3 |  | 20.0455 | [6 empty] | 0 | 3.9143 | 1.8253 | 2.5087 | 0.87437 | 0.3326 | 0.40506 | 9.8603 | 0.88525 | 0 | 0 |  | -110.413 | [7 empty] | 8.4251 | 1.4864 | 0.97042 | 3.0389 | -0.44929 | -1.4758 | -0.85321 | 2.7175 | 2.2707 | 0.0011359 | 0 |  | -117.5558
G2.20 |  |  | Water Treatment Works (Civils) | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.21 |  |  | Water Treatment Works (Civils) | Total | nr | 1603.6435 | C4 | 6712 | A2 | 80 | A3 |  | 20.0455 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3.9143 | 1.8253 | 2.5087 | 0.87437 | 0.3326 | 0.40506 | 9.8603 | 0.88525 | 0 | 0 | 0 | -110.413 | [7 empty] | 8.4251 | 1.4864 | 0.97042 | 3.0389 | -0.44929 | -1.4758 | -0.85321 | 2.7175 | 2.2707 | 0.0011359 | 0 | 0 | -117.5558
G2.22 |  |  | Water Treatment Works (MEICA) | MEICA | nr | 1596.4242 | C4 | 7580 | A2 | 20 | A2 |  | 79.8212 | [6 empty] | 0 | 39.545 | 34.5661 | 32.213 | 32.9216 | 35.6767 | 45.1501 | 220.0726 | 21.5047 | 0 | 0 |  | -258.8547 | [7 empty] | 183.2201 | 45.3643 | 38.0464 | 39.9577 | 39.9869 | 40.1201 | 31.3487 | 234.8242 | 49.1363 | 0.0015418 | 0 |  | -244.1031
G2.23 |  |  | Water Treatment Works (MEICA) | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0.033108 | 0.065302 | 0.67697 | 0.84432 | 2.5309 | 4.9111 | 9.0616 | 0.068638 | 0 | 0 |  | 9.0616 | [7 empty] | 0.11541 | 0.042704 | 0.080744 | 0.055622 | 3.4101 | 3.0631 | 3.3899 | 10.0422 | 0.090106 | 0 | 0 |  | 10.0422
G2.24 |  |  | Water Treatment Works (MEICA) | Filtration | [8 empty] | 0 | [6 empty] | 0 | 15.2294 | 9.2116 | 5.5046 | 4.046 | 8.2781 | 0.37801 | 42.6477 | 1.3146 | 0 | 0 |  | 42.6477 | [7 empty] | 41.6551 | 9.819 | 5.2027 | 6.6506 | 14.5245 | 9.4969 | 5.1371 | 50.8308 | 8.7033 | 0.025558 | 0 |  | 50.8308
G2.25 |  |  | Water Treatment Works (MEICA) | Security | [8 empty] | 0 | [6 empty] | 0 | -0.064659 | 0 | 0 | 0 | 0 | 0 | -0.064659 | 0 | 0 | 0 |  | -0.064659 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.26 |  |  | Water Treatment Works (MEICA) | Total | nr | 1596.4242 | C4 | 7580 | A2 | 20 | A2 |  | 79.8212 | 0 | 0 | 0 | 0 | 0 |  | 0 | 54.7429 | 43.843 | 38.3946 | 37.8119 | 46.4856 | 50.4392 | 271.7173 | 22.8879 | 0 | 0 | 0 | -207.21 | [7 empty] | 224.9905 | 55.2261 | 43.3298 | 46.6639 | 57.9216 | 52.6801 | 39.8757 | 295.6972 | 57.9297 | 0.027099 | 0 | 0 | -183.23
G2.27 |  | Distribution | Treated Water Pumping | Civils | nr | 70.5206 | B4 | 1850 | A3 | 80 | A3 |  | 0.88151 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -5.289 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -5.289
G2.28 |  |  | Treated Water Pumping | MEICA | nr | 135.9626 | B4 | 3086 | A3 | 20 | A2 |  | 6.7981 | [6 empty] | 0 | 4.6068 | 2.9213 | 3.4182 | 2.2377 | 2.3364 | 2.7065 | 18.2269 | 1.1486 | 0 | 0 |  | -22.5618 | [7 empty] | 17.5665 | 4.3231 | 2.8519 | 3.7751 | 1.9917 | 2.9835 | 4.3076 | 20.233 | 3.361 | 0 | 0 |  | -20.5558
G2.29 |  |  | Treated Water Pumping | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.30 |  |  | Treated Water Pumping | Total |  | 206.5 | B4 | [5 empty] | 7.6796 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4.6068 | 2.9213 | 3.4182 | 2.2377 | 2.3364 | 2.7065 | 18.2269 | 1.1486 | 0 | 0 | 0 | -27.8509 | [7 empty] | 17.5665 | 4.3231 | 2.8519 | 3.7751 | 1.9917 | 2.9835 | 4.3076 | 20.233 | 3.361 | 0 | 0 | 0 | -25.8449
G2.31 |  |  | Treated Water Storage | Civils | nr | 1769.7241 | B4 | 4624 | A2 | 80 | A3 |  | 22.1216 | [6 empty] | 0 | 9.3047 | 6.1933 | 5.2454 | 6.7627 | 6.4503 | 11.2492 | 45.2056 | 5.5202 | 0 | 0 |  | -87.5237 | [7 empty] | 57.1186 | 10.8395 | 6.9401 | 6.3092 | 4.1551 | 9.5179 | 10.644 | 48.4058 | 21.0264 | 0.37713 | 0 |  | -84.3235
G2.32 |  |  | Treated Water Storage | MEICA | nr | 344.538 | B4 | 8193 | A2 | 20 | A2 |  | 17.2269 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -103.3614 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -103.3614
G2.33 |  |  | Treated Water Storage | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.34 |  |  | Treated Water Storage | Total |  | 2114.2621 | B4 | [5 empty] | 39.3485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.3047 | 6.1933 | 5.2454 | 6.7627 | 6.4503 | 11.2492 | 45.2056 | 5.5202 | 0 | 0 | 0 | -190.8851 | [7 empty] | 57.1186 | 10.8395 | 6.9401 | 6.3092 | 4.1551 | 9.5179 | 10.644 | 48.4058 | 21.0264 | 0.37713 | 0 | 0 | -187.6849
G2.35 |  |  | Water Mains | Water trunk mains <300mm | km | 198.9268 | B4 | 476.085 | A2 | 105 | A3 | 4.5341 | 1.8945 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -11.3672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -11.3672
G2.36 |  |  | Water Mains | Water trunk mains >300mm | km | 3597.6888 | B4 | 5164.143 | A2 | 115 | A3 | 44.9056 | 31.2843 | [6 empty] | 0 | 1.7986 | 1.8103 | 1.2263 | 0.74174 | 0.028044 | 0.032235 | 5.6372 | 0 | 0 | 0 |  | -182.0683 | 0 | 410 | 5101 | 38 | 56 | 3 | 681.3 | 2.3109 | 1.7986 | 1.8103 | 0.71158 | 0.30028 | 0.7046 | 0.9198 | 6.2452 | 0.16811 | 0 | 0 |  | -181.4604
G2.37 |  |  | Water Mains | Water trunk mains asbestos cement | km | 123.5198 | B4 | 245.183 | A2 | 90 | A3 | 2.7243 | 1.3724 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -8.2347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -8.2347
G2.38 |  |  | Water Mains | Water distribution mains <300mm | km | 7724.9582 | B4 | 37894.099 | A2 | 105 | A3 | 360.8962 | 73.571 | [6 empty] | 0 | 23.1676 | 37.0206 | 43.569 | 55.8863 | 29.357 | 19.69 | 208.6905 | 0.11932 | 0 | 0 |  | -232.7357 | 0 | 66668 | 88856.88 | 115135.03 | 133840.09 | 1129739.23 | 269054.83 | 53.0501 | 22.1808 | 37.4495 | 40.2179 | 8.5735 | 31.3242 | 15.4433 | 155.1893 | 8.1216 | 0 | 0 |  | -286.2369
G2.39 |  |  | Water Mains | Water distribution mains >300mm | km | 21.7098 | B4 | 36.599 | A2 | 115 | A3 | 0.31825 | 0.18878 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -1.1327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -1.1327
G2.40 |  |  | Water Mains | Water distribution mains asbestos cement | km | 872.4314 | B4 | 5408.321 | A2 | 90 | A3 | 60.0925 | 9.6937 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -58.1621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -58.1621
G2.41 |  |  | Water Mains | Ironworks | [7 empty] | 0 | 0 | [6 empty] | 0 | 0 | 0.011605 | -0.0017501 | -0.003285 | -0.003285 | -0.003285 | 1.9379e-10 | 0 | 0 | 0 |  | 1.9379e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.011605 | 0.02021 | -0.010908 | -0.0094365 | -0.0040484 | 0.0074229 | 0 | 0 | 0 |  | 0.0074229
G2.42 |  |  | Water Mains | Communication pipes | nr | 2258.9956 | C4 | 1852973 | B4 |  |  | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.43 |  |  | Water Mains | Sub sea pipes | [7 empty] | 0 | 0 | [6 empty] | 0 | 0 | 0.00092045 | 0.11699 | 0.23673 | 0.45739 | 0.57773 | 1.3898 | 0 | 0 | 0 |  | 1.3898 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0.0058094 | 0.72656 | 0.42016 | 0.18926 | 0.10835 | 1.4501 | 0 | 0 | 0 |  | 1.4501
G2.44 |  |  | Water Mains | Pipe bridges | [7 empty] | 0 | 0 | [6 empty] | 0 | 0.027589 | 0.21091 | 1.1441 | 0.22756 | 0.087133 | 0.00057649 | 1.6978 | 0.0041394 | 0 | 0 |  | 1.6978 | 0 | 3 | 8 | 25 | 32 | 2 | 52 | 0.016689 | 0.025803 | 0.21091 | 0.99796 | 1.0331 | 0.41085 | 0.1015 | 2.7801 | 0.00073389 | 0 | 0 |  | 2.7801
G2.45 |  |  | Water Mains | Water network ancillaries | [7 empty] | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.46 |  |  | Water Mains | Leakage and consumption reduction measures | [7 empty] | 0 | 0 | [6 empty] | 0 | 2.2389 | 2.9369 | 2.8408 | 0.79248 | 0.78318 | 1.2253 | 10.8175 | 0.26872 | 0 | 0 |  | 10.8175 | 0 | 9 | 378 | 75 | 9674 | 8260 | 2 | 1.923 | 2.046 | 2.6304 | 5.2 | 3.1982 | -0.1374 | 0.18068 | 13.1179 | 0.35951 | 0 | 0 |  | 13.1179
G2.47 |  |  | Water Mains | Total |  | 14798.2305 | B4 |  |  |  |  | 473.4709 | 118.0047 | 0 | 0 | 0 | 0 | 0 |  | 0 | 27.2327 | 41.9912 | 48.8953 | 57.8815 | 30.7095 | 21.5225 | 228.2328 | 0.39218 | 0 | 0 | 0 | -479.7955 | 0 | 67090 | 94343.88 | 115275.03 | 143602.09 | 1138005.23 | 269790.13 | 57.3007 | 26.0512 | 42.1186 | 47.8742 | 13.5143 | 32.4821 | 16.7496 | 178.79 | 8.65 | 0 | 0 | 0 | -529.2383
G2.48 |  |  | Water Meters | Water meters | nr | 119.5518 | B4 | 138074 | A3 | 10 | B3 | 13807.4 | 11.9552 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -71.7311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -71.7311
G2.49 |  |  | Water Meters | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.50 |  |  | Water Meters | Total | nr | 119.5518 | B4 | 138074 | A3 | 10 | B3 |  | 11.9552 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -71.7311 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -71.7311
G2.51 | Foul sewage & surface water shared assets | Collection | Pumped Combined Rising Mains | Pumped combined rising mains | km | 487.9817 | B4 | 1136.062 | A4 | 38 | B3 | 29.8964 | 12.8416 | [6 empty] | 0 | 2.8422 | 1.0946 | 5.583 | 2.0882 | 2.42 | 5.0881 | 19.1161 | 0.1791 | 0 | 0 |  | -57.9337 | 0 | 834 | 4083 | 1843 | 2275 | 2500 | 0 | 7.4414 | 2.8422 | 1.0946 | 3.8259 | 3.7156 | 2.1805 | 4.246 | 17.9048 | 14.1566 | 0 | 0 |  | -59.145
G2.52 |  |  | Pumped Combined Rising Mains | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0.018507 | 0.14236 | 0.63438 | 0.38367 | 0.71285 | 0.92929 | 2.8211 | 0 | 0 | 0 |  | 2.8211 | [7 empty] | 0 | 0.018507 | 0.14236 | 0.37016 | -0.089277 | -0.082681 | -0.035471 | 0.3236 | 0 | 0 | 0 |  | 0.3236
G2.53 |  |  | Pumped Combined Rising Mains | Total | km | 487.9817 | B4 | 1136.062 | A4 | 38 | B3 |  | 12.8416 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2.8607 | 1.237 | 6.2173 | 2.4719 | 3.1328 | 6.0174 | 21.9371 | 0.1791 | 0 | 0 | 0 | -55.1126 | [7 empty] | 7.4414 | 2.8607 | 1.237 | 4.1961 | 3.6263 | 2.0978 | 4.2105 | 18.2284 | 14.1566 | 0 | 0 | 0 | -58.8214
G2.54 |  |  | Combined Sewer Overflow | Civils | nr | 686.7578 | B4 | 4083 | A3 | 80 | A3 |  | 8.5845 | [6 empty] | 0 | 0.24973 | 0.18094 | 1.9502 | 1.6783 | 2.4078 | 2.9347 | 9.4017 | 0.0016907 | 0 | 0 |  | -42.1051 | [7 empty] | 7.2928 | 0.29211 | 0.20322 | 1.1357 | -0.5155 | -0.44067 | 2.9449 | 3.6197 | 5.0074 | 0 | 0 |  | -47.8871
G2.55 |  |  | Combined Sewer Overflow | MEICA | nr | 195.2074 | B4 | 1124 | A3 | 20 | A2 |  | 9.7604 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -58.5622 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -58.5622
G2.56 |  |  | Combined Sewer Overflow | Total |  | 881.9652 | B4 | [5 empty] | 18.3448 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.24973 | 0.18094 | 1.9502 | 1.6783 | 2.4078 | 2.9347 | 9.4017 | 0.0016907 | 0 | 0 | 0 | -100.6673 | [7 empty] | 7.2928 | 0.29211 | 0.20322 | 1.1357 | -0.5155 | -0.44067 | 2.9449 | 3.6197 | 5.0074 | 0 | 0 | 0 | -106.4493
G2.57 |  |  | Sewage Pumping Stations (Combined) | Civils | nr | 608.6749 | B4 | 7015 | A3 | 80 | A3 |  | 7.6084 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -45.6506 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -45.6506
G2.58 |  |  | Sewage Pumping Stations (Combined) | MEICA | nr | 426.9671 | B4 | 9847 | A3 | 20 | A2 |  | 21.3484 | [6 empty] | 0 | 7.123 | 8.1256 | 11.4018 | 13.8853 | 17.3796 | 25.8349 | 83.7502 | 8.6161 | 0 | 0 |  | -44.3399 | [7 empty] | 44.0558 | 7.0898 | 8.1045 | 14.6847 | 16.4588 | 6.4971 | 12.3496 | 65.1844 | 27.0551 | 0.01988 | 0 |  | -62.9057
G2.59 |  |  | Sewage Pumping Stations (Combined) | Total |  | 1035.6419 | B4 | [5 empty] | 28.9568 | 0 | 0 | 0 | 0 | 0 |  | 0 | 7.123 | 8.1256 | 11.4018 | 13.8853 | 17.3796 | 25.8349 | 83.7502 | 8.6161 | 0 | 0 | 0 | -89.9905 | [7 empty] | 44.0558 | 7.0898 | 8.1045 | 14.6847 | 16.4588 | 6.4971 | 12.3496 | 65.1844 | 27.0551 | 0.01988 | 0 | 0 | -108.5564
G2.60 |  |  | Other Sewage Structures (Combined) | Sewer structures | [8 empty] | 0 | [6 empty] | 0 | 0.17935 | 0.19135 | 0.29304 | 0.014771 | 0 | 0 | 0.67851 | 0 | 0 | 0 |  | 0.67851 | [7 empty] | 0.24591 | 0.18158 | 0.20347 | 0.49253 | 0.1819 | 0.032166 | 0.047493 | 1.1391 | 0.0083621 | 0 | 0 |  | 1.1391
G2.61 |  |  | Other Sewage Structures (Combined) | Pipe bridges | [7 empty] | 0 | 0 | [6 empty] | 0 | 1.0155 | 0.62207 | -0.29032 | 1.5272 | -0.064366 | 1.5711 | 4.3811 | 0.034335 | 0 | 0 |  | 4.3811 | 0 | 5 | 1 | 3 | 1 | 6 | 14 | 4.7908 | 1.1183 | 1.0435 | 1.2367 | -4.6595 | -2.7732 | -1.5432 | -5.5774 | 0.80054 | 0 | 0 |  | -5.5774
G2.62 |  |  | Other Sewage Structures (Combined) | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0.045977 | 0.039639 | 1.415 | 1.7999 | 4.7414 | 8.1276 | 16.1695 | 0 | 0 | 0 |  | 16.1695 | [7 empty] | 0.014501 | 0.045976 | 0.039639 | 0.054527 | 0.12483 | 0.087478 | 0.064591 | 0.41704 | 0 | 0 | 0 |  | 0.41704
G2.63 |  |  | Other Sewage Structures (Combined) | Total |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1.2408 | 0.85306 | 1.4177 | 3.3418 | 4.6771 | 9.6987 | 21.2291 | 0.034335 | 0 | 0 | 0 | 21.2291 | [7 empty] | 5.0512 | 1.3459 | 1.2866 | 1.7838 | -4.3528 | -2.6536 | -1.4311 | -4.0212 | 0.8089 | 0 | 0 | 0 | -4.0212
G2.64 |  |  | Infinite-Life Assets (Combined) | Sewers (combined) | km | 43515.1 | B4 | 38002.1 | B2 |  |  | 0 | 0 | [6 empty] | 0 | 6.3581 | 5.6013 | 5.2234 | 6.3047 | 5.6868 | 4.6709 | 33.8451 | 0.40711 | 0 | 0 |  | 33.8451 | 0 | 1607 | 4878.01 | 3753.5 | 501 | 2352 | 4257 | 17.3321 | 6.2603 | 4.8162 | 7.1719 | -3.3297 | 1.2496 | 4.6016 | 20.7698 | 6.0962 | 0 | 0 |  | 20.7698
G2.65 |  |  | Infinite-Life Assets (Combined) | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 2.0802 | 1.5517 | 1.0233 | 4.6552 | 0 | 0 | 0 |  | 4.6552
G2.66 |  |  | Infinite-Life Assets (Combined) | Total | km | 43515.1 | B4 | 38002.1 | B2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 6.3581 | 5.6013 | 5.2234 | 6.3047 | 5.6868 | 4.6709 | 33.8451 | 0.40711 | 0 | 0 | 0 | 33.8451 | [7 empty] | 17.3321 | 6.2603 | 4.8162 | 7.1719 | -1.2495 | 2.8014 | 5.6248 | 25.425 | 6.0962 | 0 | 0 | 0 | 25.425
G2.67 |  | Wastewater Treatment Works | Wastewater Treatment Works (Combined) (Civils) | Civils | nr | 2792.6367 | B4 | 14790 | A2 | 80 | A3 |  | 34.908 | [6 empty] | 0 | 32.1883 | 26.5925 | 21.3416 | 24.235 | 23.7904 | 38.1805 | 166.3284 | 21.7956 | 0 | 0 |  | -43.1194 | [7 empty] | 120.7418 | 32.648 | 27.355 | 41.027 | 5.3523 | 12.9617 | 28.8205 | 148.1645 | 83.7751 | 0.069578 | 0 |  | -61.2832
G2.68 |  |  | Wastewater Treatment Works (Combined) (Civils) | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.69 |  |  | Wastewater Treatment Works (Combined) (Civils) | Total | nr | 2792.6367 | B4 | 14790 | A2 | 80 | A3 |  | 34.908 | 0 | 0 | 0 | 0 | 0 |  | 0 | 32.1883 | 26.5925 | 21.3416 | 24.235 | 23.7904 | 38.1805 | 166.3284 | 21.7956 | 0 | 0 | 0 | -43.1194 | [7 empty] | 120.7418 | 32.648 | 27.355 | 41.027 | 5.3523 | 12.9617 | 28.8205 | 148.1645 | 83.7751 | 0.069578 | 0 | 0 | -61.2832
G2.70 |  |  | Wastewater Treatment Works (Combined) (MEICA) | MEICA | nr | 1715.5987 | B4 | 15289 | A2 | 20 | A2 |  | 85.7799 | [6 empty] | 0 | 12.3773 | 16.7701 | 23.0177 | 26.2339 | 34.4641 | 40.0546 | 152.9176 | 3.9863 | 0 | 0 |  | -361.762 | [7 empty] | 61.5556 | 12.2172 | 17.4369 | 23.7995 | 27.1176 | 27.1863 | 27.3425 | 135.1001 | 30.6783 | 0 | 0 |  | -379.5795
G2.71 |  |  | Wastewater Treatment Works (Combined) (MEICA) | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.72 |  |  | Wastewater Treatment Works (Combined) (MEICA) | Total | nr | 1715.5987 | B4 | 15289 | A2 | 20 | A2 |  | 85.7799 | 0 | 0 | 0 | 0 | 0 |  | 0 | 12.3773 | 16.7701 | 23.0177 | 26.2339 | 34.4641 | 40.0546 | 152.9176 | 3.9863 | 0 | 0 | 0 | -361.762 | [7 empty] | 61.5556 | 12.2172 | 17.4369 | 23.7995 | 27.1176 | 27.1863 | 27.3425 | 135.1001 | 30.6783 | 0 | 0 | 0 | -379.5795
G2.73 |  |  | Cess and Septic Tanks (Combined) (Civils) | Civils | nr | 137.8349 | C4 | 2518 | A2 | 80 | A3 |  | 1.7229 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -10.3376 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -10.3376
G2.74 |  |  | Cess and Septic Tanks (Combined) (Civils) | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.75 |  |  | Cess and Septic Tanks (Combined) (Civils) | Total | nr | 137.8349 | C4 | 2518 | A2 | 80 | A3 |  | 1.7229 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10.3376 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10.3376
G2.76 |  |  | Cess and Septic Tanks (Combined) (MEICA) | MEICA | nr | 10.2064 | C4 | 1297 | A2 | 20 | A2 |  | 0.51032 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -3.0619 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -3.0619
G2.77 |  |  | Cess and Septic Tanks (Combined) (MEICA) | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.78 |  |  | Cess and Septic Tanks (Combined) (MEICA) | Total | nr | 10.2064 | C4 | 1297 | A2 | 80 | A2 |  | 0.51032 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3.0619 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3.0619
G2.79 |  |  | Sludge Treatment Centres (Combined) | Civils | nr | 177.2678 | B4 | 348 | A2 | 80 | A3 |  | 2.2158 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -13.2951 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -13.2951
G2.80 |  |  | Sludge Treatment Centres (Combined) | MEICA | nr | 151.53 | B4 | 412 | A2 | 20 | A2 |  | 7.5765 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -45.459 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -45.459
G2.81 |  |  | Sludge Treatment Centres (Combined) | Total |  | 328.7977 | B4 | [5 empty] | 9.7923 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -58.7541 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -58.7541
G2.82 |  | Discharge | Outfalls from Treatment (Combined) | Long and short sea outfalls (combined) | nr | 489.6059 | B4 | 1096 | B2 | 105 | A3 |  | 4.6629 | [6 empty] | 0 | 0.14372 | 0.32605 | 0.26687 | 1.191 | 2.7016 | 2.8715 | 7.5008 | 0.78229 | 0 | 0 |  | -20.4767 | [7 empty] | 4.4929 | 0.14372 | 0.32605 | 0.31607 | 0.82516 | 2.317 | 3.0731 | 7.0011 | 5.8475 | 0 | 0 |  | -20.9764
G2.83 |  |  | Outfalls from Treatment (Combined) | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.84 |  |  | Outfalls from Treatment (Combined) | Total | nr | 489.6059 | B4 | 1096 | B2 | 105 | A3 |  | 4.6629 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.14372 | 0.32605 | 0.26687 | 1.191 | 2.7016 | 2.8715 | 7.5008 | 0.78229 | 0 | 0 | 0 | -20.4767 | [7 empty] | 4.4929 | 0.14372 | 0.32605 | 0.31607 | 0.82516 | 2.317 | 3.0731 | 7.0011 | 5.8475 | 0 | 0 | 0 | -20.9764
G2.85 | Foul sewage only | Collection | Sewage and Sludge Pumping Mains (Foul Only) | Pumped foul only rising mains | km | 78.2669 | B4 | 300.2 | A4 | 38 | B3 | 7.9 | 2.0597 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -12.3579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -12.3579
G2.86 |  |  | Sewage and Sludge Pumping Mains (Foul Only) | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.87 |  |  | Sewage and Sludge Pumping Mains (Foul Only) | Total | km | 78.2669 | B4 | 300.2 | A4 | 38 | B3 |  | 2.0597 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12.3579 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12.3579
G2.88 |  |  | Emergency Outfalls (Foul Only) | Civils | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.89 |  |  | Emergency Outfalls (Foul Only) | MEICA | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.90 |  |  | Emergency Outfalls (Foul Only) | Total |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2.91 |  |  | Sewage Pumping Stations (Foul Only) | Civils | nr | 139.09 | B4 | 3213 | A3 | 80 | A3 |  | 1.7386 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -10.4317 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -10.4317
G2.92 |  |  | Sewage Pumping Stations (Foul Only) | MEICA | nr | 143.2442 | B4 | 4717 | A3 | 20 | A2 |  | 7.1622 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -42.9733 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -42.9733
G2.93 |  |  | Sewage Pumping Stations (Foul Only) | Total |  | 282.3342 | B4 | [5 empty] | 8.9008 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -53.405 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -53.405
G2.94 |  |  | Other Sewage Structures (Foul Only) | Sewer structures | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.95 |  |  | Other Sewage Structures (Foul Only) | Pipe bridges | [7 empty] | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.96 |  |  | Other Sewage Structures (Foul Only) | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.97 |  |  | Other Sewage Structures (Foul Only) | Total |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2.98 |  |  | Infinite-Life Assets (Foul Only) | Sewers (foul only) | km | 7084.4 | B4 | 7666.1 | B2 |  |  | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.99 |  |  | Infinite-Life Assets (Foul Only) | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.100 |  |  | Infinite-Life Assets (Foul Only) | Total | km | 7084.4 | B4 | 7666.1 | B2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2.101 |  | Wastewater Treatment Works | Wastewater Treatment Works (Foul Only) (Civils) | Civils | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.102 |  |  | Wastewater Treatment Works (Foul Only) (Civils) | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.103 |  |  | Wastewater Treatment Works (Foul Only) (Civils) | Total |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2.104 |  |  | Wastewater Treatment Works (Foul Only) (MEICA) | MEICA | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.105 |  |  | Wastewater Treatment Works (Foul Only) (MEICA) | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.106 |  |  | Wastewater Treatment Works (Foul Only) (MEICA) | Total |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2.107 |  |  | Cess and Septic Tanks (Foul Only) (Civils) | Civils | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.108 |  |  | Cess and Septic Tanks (Foul Only) (Civils) | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.109 |  |  | Cess and Septic Tanks (Foul Only) (Civils) | Total |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2.110 |  |  | Cess and Septic Tanks (Foul Only) (MEICA) | MEICA | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.111 |  |  | Cess and Septic Tanks (Foul Only) (MEICA) | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.112 |  |  | Cess and Septic Tanks (Foul Only) (MEICA) | Total |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2.113 |  |  | Sludge Treatment Centres (Foul Only) | Civils | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.114 |  |  | Sludge Treatment Centres (Foul Only) | MEICA | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.115 |  |  | Sludge Treatment Centres (Foul Only) | Total |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2.116 |  | Discharge | Outfalls from Treatment (Foul Only) | Long and short sea outfalls (foul only) | nr | 0.38002 | B4 | 5 | B2 | 105 | A3 |  | 0.0036192 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -0.021715 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -0.021715
G2.117 |  |  | Outfalls from Treatment (Foul Only) | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.118 |  |  | Outfalls from Treatment (Foul Only) | Total | nr | 0.38002 | B4 | 5 | B2 | 105 | A3 |  | 0.0036192 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.021715 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.021715
G2.119 | Surface water only | Collection | Sewage and Sludge Pumping Mains (Surface Water Only) | Pumped surface water only rising mains | km | 3.499 | B3 | 6.2 | A4 | 38 | B3 | 0.16316 | 0.092079 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -0.55247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -0.55247
G2.120 |  |  | Sewage and Sludge Pumping Mains (Surface Water Only) | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.121 |  |  | Sewage and Sludge Pumping Mains (Surface Water Only) | Total | km | 3.499 | B3 | 6.2 | A4 | 38 | B3 |  | 0.092079 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.55247 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.55247
G2.122 |  |  | Emergency Outfalls (Surface Water Only) | Civils | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.123 |  |  | Emergency Outfalls (Surface Water Only) | MEICA | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.124 |  |  | Emergency Outfalls (Surface Water Only) | Total |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2.125 |  |  | Surface Water Pumping Stations | Civils | nr | 20.241 | B4 | 198 | A3 | 80 | A3 |  | 0.25301 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -1.5181 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -1.5181
G2.126 |  |  | Surface Water Pumping Stations | MEICA | nr | 11.5094 | B4 | 262 | A3 | 20 | A2 |  | 0.57547 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -3.4528 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -3.4528
G2.127 |  |  | Surface Water Pumping Stations | Total |  | 31.7504 | B4 | [5 empty] | 0.82848 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4.9709 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4.9709
G2.128 |  |  | Other Surface Water Structures | Surface water structures | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.129 |  |  | Other Surface Water Structures | Pipe bridges | [7 empty] | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.130 |  |  | Other Surface Water Structures | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.131 |  |  | Other Surface Water Structures | Total |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2.132 |  |  | Infinite-Life Assets (Surface Water Only) | Surface water pipes | km | 10561.9 | B4 | 9021.4 | B2 |  |  | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.133 |  |  | Infinite-Life Assets (Surface Water Only) | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.134 |  |  | Infinite-Life Assets (Surface Water Only) | Total | km | 10561.9 | B4 | 9021.4 | B2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2.135 |  | Wastewater Treatment Works | Surface Water Storage and Treatment (Nature-Based) | SUDS | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0.0089682 | 0.024711 | 0 | 0 | 0.033679 | 0 | 0 | 0 |  | 0.033679
G2.136 |  |  | Surface Water Storage and Treatment (Nature-Based) | Wetlands | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.137 |  |  | Surface Water Storage and Treatment (Nature-Based) | Reed beds | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.138 |  |  | Surface Water Storage and Treatment (Nature-Based) | Swales | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.139 |  |  | Surface Water Storage and Treatment (Nature-Based) | Rain gardens | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.140 |  |  | Surface Water Storage and Treatment (Nature-Based) | Total |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0.0089682 | 0.024711 | 0 | 0 | 0.033679 | 0 | 0 | 0 | 0 | 0.033679
G2.141 |  |  | Surface Water Storage and Treatment (MEICA) | MEICA | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.142 |  |  | Sludge Treatment Centres (Surface Water Only) | Civils | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.143 |  |  | Sludge Treatment Centres (Surface Water Only) | MEICA | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.144 |  |  | Sludge Treatment Centres (Surface Water Only) | Total |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2.145 |  | Discharge | Outfalls from Treatment (Surface Water Only) | Long and short sea outfalls (surface water only) | nr | 13.7015 | B4 | 142 | B2 | 105 | A3 |  | 0.13049 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -0.78294 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -0.78294
G2.146 |  |  | Outfalls from Treatment (Surface Water Only) | Ancillaries | [8 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.147 |  |  | Outfalls from Treatment (Surface Water Only) | Total | nr | 13.7015 | B4 | 142 | B2 | 105 | A3 |  | 0.13049 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.78294 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.78294
G2.148 | Shared | Business Services | Support Services | Vehicles | nr | 79.56 | B3 | 2559 | A2 | 5 | A3 |  | 15.912 | [6 empty] | 0 | 7.6999 | 11.1548 | 18.1315 | 17.8457 | 13.3032 | 9.4971 | 77.6322 | 0 | 0 | 0 |  | -17.8398 | [7 empty] | 5.6942 | 7.6998 | 11.1547 | 15.4495 | 18.5301 | 12.7614 | 12.0356 | 77.6312 | 0.0033622 | 0 | 0 |  | -17.8408
G2.149 |  |  | Support Services | Digital | nr | 4.571 | B2 | 4632 | A2 | 3 | A2 |  | 1.5237 | [6 empty] | 0 | 28.5678 | 37.4573 | 44.6058 | 38.2703 | 29.4044 | 32.2038 | 210.5096 | 0 | 0 | 0 |  | 201.3676 | [7 empty] | 79.0539 | 30.3714 | 37.741 | 37.7763 | 53.6603 | 43.5348 | 8.6108 | 211.6945 | 0 | 0 | 0 |  | 202.5525
G2.150 |  |  | Support Services | Facilities and estates | nr | 71.94 | C4 | 77 | B2 | 60 | A2 |  | 1.199 | [6 empty] | 0 | 0.97962 | 1.2495 | 2.5607 | 1.4137 | 1.3749 | 1.7081 | 9.2866 | 0.00019652 | 0 | 0 |  | 2.0926 | [7 empty] | 19.7627 | 1.8866 | 0.91673 | 1.1349 | 1.6635 | 0.64836 | 0.10919 | 6.3593 | 0.0012921 | 0 | 0 |  | -0.83475
G2.151 |  |  | Support Services | Renewable energy | [8 empty] | 0 | [6 empty] | 0 | 0.75854 | 0.79188 | 2.8793 | 1.035 | 0.0015739 | 0.0015739 | 5.4678 | 0.00067338 | 0 | 0 |  | 5.4678 | [7 empty] | 0.61371 | 0.66599 | 0.69692 | 1.9329 | 2.3278 | 1.8981 | 0.94594 | 8.4677 | 0.0052004 | 0 | 0 |  | 8.4677
G2.152 |  |  | Support Services | Scientific services | [8 empty] | 0 | [6 empty] | 0 | 0.57202 | 0.79315 | 0.61176 | 1.1807 | 0.65049 | 0.76304 | 4.5711 | 0 | 0 | 0 |  | 4.5711 | [7 empty] | 3.7609 | 0.52656 | 0.79314 | 0.5838 | 0.78695 | 0.63517 | 1.2 | 4.5256 | 0 | 0 | 0 |  | 4.5256
G2.153 |  |  | Support Services | Customer meters | [8 empty] | 0 | [6 empty] | 0 | 1.9659 | 3.9452 | 3.3077 | 0.3198 | 0.59417 | 0.77459 | 10.9075 | 0 | 0 | 0 |  | 10.9075 | [7 empty] | 7.7276 | 1.9659 | 3.9452 | 3.4343 | 7.0729 | 3.3077 | 2.1812 | 21.9072 | 0 | 0 | 0 |  | 21.9072
G2.154 |  |  | Support Services | Transformation | [8 empty] | 0 | [6 empty] | 0 | 24.0392 | 43.0341 | 29.8892 | 17.29 | 2.1254 | 1.4385 | 117.8164 | 0.29641 | 0 | 0 |  | 117.8164 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
G2.155 |  |  | Support Services | Other | nr | 15.67 | C4 | 35 | B3 | 60 | A3 |  | 0.26117 | [6 empty] | 0 | -8.4917 | -8.5313 | 10.8706 | 7.1858 | 8.6368 | 10.9631 | 20.6334 | 2.6494 | 0 | 0 |  | 19.0664 | [7 empty] | 17.7229 | -11.5407 | -11.822 | -44.4644 | 22.6651 | 16.0118 | 34.4502 | 5.3 | 3.369 | 0.0099398 | 0 |  | 3.733
G2.156 |  |  | Support Services | Total | nr | 171.741 | C4 | 7303 | A2 |  |  |  | 18.8958 | 0 | 0 | 0 | 0 | 0 |  | 0 | 56.0914 | 89.8948 | 112.8567 | 84.541 | 56.091 | 57.3498 | 456.8247 | 2.9467 | 0 | 0 | 0 | 343.4497 | [7 empty] | 134.3359 | 31.5756 | 43.4257 | 15.8474 | 106.7067 | 78.7974 | 59.5328 | 335.8856 | 3.3789 | 0.0099398 | 0 | 0 | 222.5106
G2.157 | Total | Total | Total | Total |  | 96010.9 | B4 | [5 empty] | 526.8172 | 0 | 0 | 0 | 0 | 0 |  | 0 | 224.6326 | 249.7819 | 287.8286 | 272.827 | 242.2841 | 281.9455 | 1559.2998 | 74.1632 | 0 | 0 | 0 | -1601.6035 | [7 empty] | 778.0125 | 197.6623 | 205.7312 | 229.6057 | 241.9522 | 240.8001 | 228.7645 | 1344.516 | 283.5395 | 0.50476 | 0 | 0 | -1816.3873
|  |  |  | Caclulated check on totals | [15 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE | TRUE |  |  | 31: FALSE; 32: FALSE; 33: FALSE; 34: FALSE; 35: FALSE; 36: FALSE; 37: FALSE; 39: FALSE; 40: TRUE; 41: TRUE
Prepared by: ……………………………………………...….. |  |  |  | Date: 07/10/2024
Checked by: ……………………………………………...….. |  |  |  | Date: 07/10/2024
Authorised by: …...........……………………...……............ |  |  |  | Date: 07/10/2024

## G3 - Repair
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2024
SECTION G: INVESTMENT MONITORING
Table G3: Summary - Repair | [33 empty] | Forecast based on IPS24.1 in AR24 | [6 empty] | Forecast based on IPS24.1 in AR24 |  |  |  | Forecast based on IPS24.1 in AR24
[5 empty] | Block A: Asset information | [6 empty] | Block B: Investment consistent with asset management policies | [5 empty] | Block C: Investment baseline (Investment Planning Scenario 23.2) | [11 empty] | Block D: Actual to date and updated forecast
Line ref. | Service | Functional activity | Asset category | Sub asset category | Asset units | Asset value (2017-18 prices) | CG | Asset stock | CG | Assumed asset life | CG | Projected expenditure from 2021-22 to 2026-27 (2017-18 prices) | Projected expenditure from 2027-28 to 2032-33 (2017-18 prices) | Projected expenditure from 2033-34 to 2038-39 (2017-18 prices) | Projected expenditure from 2039-40 to 2044-45 (2017-18 prices) | Projected expenditure from 2045-46 to 2050-51 (2017-18 prices) |  | Projected expenditure in investment baseline pre 2021-22 (2017-18 prices) | Projected expenditure in investment baseline in 2021-22 (2017-18 prices) | Projected expenditure in investment baseline in 2022-23 (2017-18 prices) | Projected expenditure in investment baseline in 2023-24 (2017-18 prices) | Projected expenditure in investment baseline in 2024-25 (2017-18 prices) | Projected expenditure in investment baseline in 2025-26 (2017-18 prices) | Projected expenditure in investment baseline in 2026-27 (2017-18 prices) | Projected expenditure from 2021-22 to 2026-27 (2017-18 prices) | Projected expenditure from 2027-28 to 2032-33 (2017-18 prices) | Projected expenditure from 2033-34 to 2038-39 (2017-18 prices) | Projected expenditure from 2039-40 to 2044-45 (2017-18 prices) | Projected expenditure from 2045-46 to 2050-51 (2017-18 prices) | Actual number of replacement interventions pre 2021-22 | Actual number of replacement interventions in 2021-22 | Actual number of replacement interventions in 2022-23 | Actual number of replacement interventions in 2023-24 | Projected number of replacement interventions in 2024-25 | Projected number of replacement interventions in 2025-26 | Projected number of replacement interventions in 2026-27 | Actual expenditure pre 2021-22 (2017-18 prices) | Actual expenditure in 2021-22 (2017-18 prices) | Actual expenditure in 2022-23 (2017-18 prices) | Actual expenditure in 2023-24 (2017-18 prices) | Projected expenditure in 2024-25 (2017-18 prices) | Projected expenditure in 2025-26 (2017-18 prices) | Projected expenditure in 2026-27 (2017-18 prices) | Projected expenditure from 2021-22 to 2026-27 (2017-18 prices) | Projected expenditure from 2027-28 to 2032-33 (2017-18 prices) | Projected expenditure from 2033-34 to 2038-39 (2017-18 prices) | Projected expenditure from 2039-40 to 2044-45 (2017-18 prices) | Projected expenditure from 2045-46 to 2050-51 (2017-18 prices)
[6 empty] | £m |  | nr |  | nr |  | £m | £m | £m | £m | £m |  | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | nr | nr | nr | nr | nr | nr | nr | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m
[6 empty] | 1 |  | 2 |  | 3 |  | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
G3.01 | Water | Source | Raw Water Pumping | Civils | nr | 50.6163 | B4 | 417 | A3 | 80 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.02 |  |  | Raw Water Pumping | MEICA | nr | 35.7978 | B4 | 616 | A3 | 20 | A2 | [6 empty] | 0 | 0.16757 | 0.12464 | 0.61147 | 0.69509 | 0.697 | 0.52153 | 2.8173 | 0 | 0 | 0 |  | 28: 0.030342; 29: 0.16757; 30: 0.12463; 31: 0.078355; 32: 0.44638; 33: 0.54052; 34: 0.76481; 35: 2.1223; 36: 0.0011207; 37: 0; 38: 0
G3.03 |  |  | Raw Water Pumping | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.04 |  |  | Raw Water Pumping | Total |  | 86.4141 | B4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.16757 | 0.12464 | 0.61147 | 0.69509 | 0.697 | 0.52153 | 2.8173 | 0 | 0 | 0 | 0 | [7 empty] | 0.030342 | 0.16757 | 0.12463 | 0.078355 | 0.44638 | 0.54052 | 0.76481 | 2.1223 | 0.0011207 | 0 | 0 | 0
G3.05 |  |  | Raw Water Mains | Raw water mains | km | 2102.5801 | B2 | 1678.821 | B2 | 115 | B3 | [6 empty] | 0 | 0.1909 | 0.29706 | 2.7608 | 2.4131 | 1.7186 | 1.1854 | 8.5658 | 1.9258 | 0 | 0 |  | 0 | 765 | 2393 | 1 | 1242 | 9531 | 1 | 0.2264 | 0.19089 | 0.4798 | 2.8038 | 2.3074 | 1.1117 | 0.44587 | 7.3395 | 0.21608 | 0 | 0
G3.06 |  |  | Raw Water Mains | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.07 |  |  | Raw Water Mains | Total | km | 2102.5801 | B2 | 1678.821 | B2 | 115 | B3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.1909 | 0.29706 | 2.7608 | 2.4131 | 1.7186 | 1.1854 | 8.5658 | 1.9258 | 0 | 0 | 0 | [7 empty] | 0.2264 | 0.19089 | 0.4798 | 2.8038 | 2.3074 | 1.1117 | 0.44587 | 7.3395 | 0.21608 | 0 | 0 | 0
G3.08 |  |  | Infinite-Life Assets | Dams and impounding reservoirs | nr | 1579.3618 | C4 | 199 | C4 | [8 empty] | 0 | 8.8911 | 17.6468 | 10.2982 | 9.8903 | 11.3361 | 2.8233 | 60.8858 | 1.0942 | 0 | 0 |  | 28: 23.7177; 29: 7.9799; 30: 15.7907; 31: 16.9561; 32: -1.935; 33: -0.68572; 34: 9.4162; 35: 47.5221; 36: 11.5844; 37: 0.029855; 38: 0
G3.09 |  |  | Infinite-Life Assets | Ancillaries | [13 empty] | 0 | 0.0094533 | 0 | 0.015906 | 0 | 0 | 0 | 0.025359 | 0 | 0 | 0 |  | 28: 0.0084385; 29: 0.0094532; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0.0094532; 36: 0; 37: 0; 38: 0
G3.10 |  |  | Infinite-Life Assets | Raw water storage (Civils) | [13 empty] | 0 | 0 | 0.0065062 | 0.24868 | 0.29237 | 0.29452 | 0.26045 | 1.1025 | 0 | 0 | 0 |  | 28: 0; 29: 0.10122; 30: 0.27712; 31: 1.4494; 32: 0.11873; 33: 0.10097; 34: 0.085734; 35: 2.1332; 36: 0; 37: 0; 38: 0
G3.11 |  |  | Infinite-Life Assets | Aqueduct | km | 2102.5801 | B2 | 1678.821 | B2 | [8 empty] | 0 | 2.6166 | 1.1567 | 6.5954 | 5.4257 | 6.3566 | 5.2034 | 27.3543 | 4.2508 | 0 | 0 |  | 28: 18.9042; 29: 2.6166; 30: 1.2174; 31: 2.6698; 32: 2.4921; 33: 6.5562; 34: 7.6273; 35: 23.1793; 36: 3.0639; 37: 0; 38: 0
G3.12 |  |  | Infinite-Life Assets | Raw water intakes (Gravity) | nr | 25.9001 | C5 | 263 | C5 | [8 empty] | 0 | 0.82802 | 0.40024 | 0.76761 | 1.1621 | 0.69755 | 0.51081 | 4.3663 | 0 | 0 | 0 |  | 28: 0.29799; 29: 0.82801; 30: 0.39619; 31: 0.49546; 32: 0.80182; 33: 0.56405; 34: 0.57203; 35: 3.6576; 36: 0.33146; 37: 0; 38: 0
G3.13 |  |  | Infinite-Life Assets | Catchment | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.14 |  |  | Infinite-Life Assets | Total |  | 3707.842 | C4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 12.3452 | 19.2103 | 17.9257 | 16.7704 | 18.6848 | 8.798 | 93.7344 | 5.345 | 0 | 0 | 0 | [7 empty] | 42.9283 | 11.5351 | 17.6814 | 21.5708 | 1.4776 | 6.5355 | 17.7012 | 76.5016 | 14.9798 | 0.029855 | 0 | 0
G3.15 |  |  | Ground Water Sources (Pumped) | Civils | nr | 9.8642 | B4 | 247 | A3 | 80 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.16 |  |  | Ground Water Sources (Pumped) | MEICA | nr | 14.0521 | B4 | 309 | A3 | 20 | A2 | [6 empty] | 0 | 0.24038 | 0.16897 | 0.016401 | 0 | 0 | 0 | 0.42575 | 0 | 0 | 0 |  | 28: 1.6623; 29: 0.24038; 30: 0.16897; 31: 0.14141; 32: 0.12196; 33: 0.011558; 34: 0; 35: 0.68427; 36: 0; 37: 0; 38: 0
G3.17 |  |  | Ground Water Sources (Pumped) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.18 |  |  | Ground Water Sources (Pumped) | Total |  | 23.9163 | B4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.24038 | 0.16897 | 0.016401 | 0 | 0 | 0 | 0.42575 | 0 | 0 | 0 | 0 | [7 empty] | 1.6623 | 0.24038 | 0.16897 | 0.14141 | 0.12196 | 0.011558 | 0 | 0.68427 | 0 | 0 | 0 | 0
G3.19 |  | Water Treatment Works | Water Treatment Works (Civils) | Civils | nr | 1603.6435 | C4 | 6712 | A2 | 80 | A3 | [6 empty] | 0 | 0.77425 | 0.95468 | 5.238 | 3.9414 | 4.0122 | 5.7147 | 20.6352 | 0 | 0 | 0 |  | 28: 2.6187; 29: 0.77424; 30: 0.95467; 31: 2.627; 32: 0.82898; 33: 4.7257; 34: 4.7514; 35: 14.662; 36: 0.90508; 37: 0; 38: 0
G3.20 |  |  | Water Treatment Works (Civils) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.21 |  |  | Water Treatment Works (Civils) | Total | nr | 1603.6435 | C4 | 6712 | A2 | 80 | A3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.77425 | 0.95468 | 5.238 | 3.9414 | 4.0122 | 5.7147 | 20.6352 | 0 | 0 | 0 | 0 | [7 empty] | 2.6187 | 0.77424 | 0.95467 | 2.627 | 0.82898 | 4.7257 | 4.7514 | 14.662 | 0.90508 | 0 | 0 | 0
G3.22 |  |  | Water Treatment Works (MEICA) | MEICA | nr | 1596.4242 | C4 | 7580 | A2 | 20 | A2 | [6 empty] | 0 | 13.6314 | 16.1554 | 29.0955 | 18.4517 | 18.88 | 13.5426 | 109.7566 | 0.097076 | 0 | 0 |  | 28: 12.1515; 29: 13.6631; 30: 16.4211; 31: 16.043; 32: 19.5304; 33: 19.2286; 34: 21.9669; 35: 106.8532; 36: 2.5479; 37: 0.00020427; 38: 0
G3.23 |  |  | Water Treatment Works (MEICA) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.24 |  |  | Water Treatment Works (MEICA) | Filtration | [13 empty] | 0 | 0.041149 | 0.59913 | 0.46748 | 2.2042 | 2.6665 | 5.7514 | 11.7299 | 0.33818 | 0 | 0 |  | 28: 0.00082532; 29: 0.041148; 30: 0.67021; 31: 1.0095; 32: 2.049; 33: 2.0113; 34: 2.3735; 35: 8.1546; 36: 0; 37: 0; 38: 0
G3.25 |  |  | Water Treatment Works (MEICA) | Security | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.26 |  |  | Water Treatment Works (MEICA) | Total | nr | 1596.4242 | C4 | 7580 | A2 | 20 | A2 | 0 | 0 | 0 | 0 | 0 |  | 0 | 13.6725 | 16.7545 | 29.5629 | 20.6559 | 21.5465 | 19.294 | 121.4864 | 0.43526 | 0 | 0 | 0 | [7 empty] | 12.1523 | 13.7043 | 17.0913 | 17.0526 | 21.5794 | 21.2398 | 24.3405 | 115.0078 | 2.5479 | 0.00020427 | 0 | 0
G3.27 |  | Distribution | Treated Water Pumping | Civils | nr | 70.5206 | B4 | 1850 | A3 | 80 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.28 |  |  | Treated Water Pumping | MEICA | nr | 135.9626 | B4 | 3086 | A3 | 20 | A2 | [6 empty] | 0 | 0.24918 | 1.32 | 2.9507 | 2.9298 | 3.0261 | 2.3138 | 12.7895 | 0.12256 | 0 | 0 |  | 28: 1.3855; 29: 0.24918; 30: 1.32; 31: 1.5264; 32: 2.2614; 33: 1.949; 34: 2.6657; 35: 9.9716; 36: 0.74333; 37: 0; 38: 0
G3.29 |  |  | Treated Water Pumping | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.30 |  |  | Treated Water Pumping | Total |  | 206.5 | B4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.24918 | 1.32 | 2.9507 | 2.9298 | 3.0261 | 2.3138 | 12.7895 | 0.12256 | 0 | 0 | 0 | [7 empty] | 1.3855 | 0.24918 | 1.32 | 1.5264 | 2.2614 | 1.949 | 2.6657 | 9.9716 | 0.74333 | 0 | 0 | 0
G3.31 |  |  | Treated Water Storage | Civils | nr | 1769.7241 | B4 | 4624 | A2 | 80 | A3 | [6 empty] | 0 | 4.4399 | 1.4833 | 2.1383 | 2.1295 | 0.89119 | 0.64819 | 11.7303 | 3.6627 | 0 | 0 |  | 28: 4.4874; 29: 18.144; 30: 20.8184; 31: 41.9163; 32: 33.2061; 33: 6.8656; 34: -0.21999; 35: 120.7303; 36: 5.701; 37: 0; 38: 0
G3.32 |  |  | Treated Water Storage | MEICA | nr | 344.538 | B4 | 8193 | A2 | 20 | A2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.33 |  |  | Treated Water Storage | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.34 |  |  | Treated Water Storage | Total |  | 2114.2621 | B4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4399 | 1.4833 | 2.1383 | 2.1295 | 0.89119 | 0.64819 | 11.7303 | 3.6627 | 0 | 0 | 0 | [7 empty] | 4.4874 | 18.144 | 20.8184 | 41.9163 | 33.2061 | 6.8656 | -0.21999 | 120.7303 | 5.701 | 0 | 0 | 0
G3.35 |  |  | Water Mains | Water trunk mains <300mm | km | 198.9268 | B4 | 476.085 | A2 | 105 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.36 |  |  | Water Mains | Water trunk mains >300mm | km | 3597.6888 | B4 | 5164.143 | A2 | 115 | A3 | [6 empty] | 0 | 0.88406 | 1.5504 | 4.3389 | 4.3736 | 6.4123 | 2.9478 | 20.507 | 5.7374 | 0 | 0 |  | 0 | 73764 | 4735 | 238.5 | 101 | 110 | 5595.01 | 23.9224 | 0.88424 | 1.9939 | 2.7948 | 3.4169 | 4.6748 | 2.3041 | 16.0687 | 3.2928 | 0 | 0
G3.37 |  |  | Water Mains | Water trunk mains asbestos cement | km | 123.5198 | B4 | 245.183 | A2 | 90 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.38 |  |  | Water Mains | Water distribution mains <300mm | km | 7724.9582 | B4 | 37894.099 | A2 | 105 | A3 | [6 empty] | 0 | 37.4325 | 35.615 | 5.7218 | 35.364 | 34.7787 | 83.4676 | 232.3796 | 0.02359 | 0 | 0 |  | 0 | 2373779 | 2226577.9 | 1709852 | 10528 | 908572.1 | 0 | 46.9755 | 39.7988 | 37.653 | 38.8629 | 29.8001 | 29.2902 | 32.8132 | 208.2181 | 10.446 | 0 | 0
G3.39 |  |  | Water Mains | Water distribution mains >300mm | km | 21.7098 | B4 | 36.599 | A2 | 115 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.40 |  |  | Water Mains | Water distribution mains asbestos cement | km | 872.4314 | B4 | 5408.321 | A2 | 90 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.41 |  |  | Water Mains | Ironworks | [13 empty] | 0 | 4.7284 | 8.6916 | 9.6907 | 6.3908 | 1.4905 | 1.1153 | 32.1074 | 0 | 0 | 0 |  | 0 | 6535 | 5 | 5 | 1 | 0 | 10340 | 4.5207 | 4.6791 | 5.5716 | 5.1677 | 6.5827 | 6.7169 | 3.3817 | 32.0996 | 0 | 0 | 0
G3.42 |  |  | Water Mains | Communication pipes | nr | 2258.9956 | C4 | 1852973 | B4 | [8 empty] | 0 | 0.10909 | 0.077953 | 0.25972 | 0.4618 | -0.45411 | -0.45446 | -1.2516e-10 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1836 | 0.10909 | 0.077952 | 0.32394 | -0.077221 | -0.43545 | 0.001696 | 2.7709e-11 | 0.00039539 | 0 | 0
G3.43 |  |  | Water Mains | Sub sea pipes | [13 empty] | 0 | 7.3633e-05 | 0.001204 | 0.00015189 | -2.9597e-11 | 0 | 0 | 0.0014295 | 0.0033404 | 0 | 0 |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0.051198 | 7.3632e-05 | 0 | 0 | -4.9088e-05 | -2.4544e-05 | 0 | 5.9075e-11 | 0 | 0 | 0
G3.44 |  |  | Water Mains | Pipe bridges | [13 empty] | 0 | 0.51539 | 0.57381 | 0.73541 | 2.3639 | 2.8438 | 0.57132 | 7.6037 | 1.2749 | 0 | 0 |  | 0 | 305 | 3 | 15 | 8 | 433 | 10 | 7.7943 | 0.52451 | 0.57907 | 1.4643 | -1.4198 | -0.57479 | 4.1919 | 4.7651 | 0.91051 | 0 | 0
G3.45 |  |  | Water Mains | Water network ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.46 |  |  | Water Mains | Leakage and consumption reduction measures | [13 empty] | 0 | 3.8174 | 4.8698 | 6.3435 | 7.5602 | 10.084 | 4.1268 | 36.8016 | 0 | 0 | 0 |  | 0 | 11 | 8 | 9 | 19 | 5991 | 1 | 40.9862 | 3.6546 | 6.1801 | 6.7845 | 9.9419 | 6.1621 | 8.4923 | 41.2155 | 0.65949 | 0 | 0
G3.47 |  |  | Water Mains | Total |  | 14798.2305 | B4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 47.4869 | 51.3797 | 27.0902 | 56.5143 | 55.1552 | 91.7744 | 329.4007 | 7.0392 | 0 | 0 | 0 | 0 | 2454395 | 2231328.9 | 1710119.5 | 10657 | 915106.1 | 15946.01 | 124.434 | 49.6503 | 52.0556 | 55.3981 | 48.2444 | 45.8338 | 51.1849 | 302.3671 | 15.3093 | 0 | 0 | 0
G3.48 |  |  | Water Meters | Water meters | nr | 119.5518 | B4 | 138074 | A3 | 10 | B3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.49 |  |  | Water Meters | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.50 |  |  | Water Meters | Total | nr | 119.5518 | B4 | 138074 | A3 | 10 | B3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.51 | Foul sewage & surface water shared assets | Collection | Pumped Combined Rising Mains | Pumped combined rising mains | km | 487.9817 | B4 | 1136.062 | A4 | 38 | B3 | [6 empty] | 0 | 0.70948 | 1.5393 | 0.96036 | 0.014853 | -0.15011 | -0.17008 | 2.9038 | 0 | 0 | 0 |  | 0 | 108 | 15 | 27 | 1034 | 3 | 1 | 4.1004 | 0.70948 | 1.5393 | 3.3148 | 0.64299 | -0.09929 | 0.23487 | 6.3421 | 0 | 0 | 0
G3.52 |  |  | Pumped Combined Rising Mains | Ancillaries | [13 empty] | 0 | 0 | 0 | 0.21168 | 0.25064 | 0.25132 | 0.18806 | 0.9017 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0.0021056; 31: 0.0092288; 32: 0.3056; 33: 0.31679; 34: 0.38992; 35: 1.0236; 36: 0; 37: 0; 38: 0
G3.53 |  |  | Pumped Combined Rising Mains | Total | km | 487.9817 | B4 | 1136.062 | A4 | 38 | B3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.70948 | 1.5393 | 1.172 | 0.26549 | 0.10121 | 0.017977 | 3.8055 | 0 | 0 | 0 | 0 | [7 empty] | 4.1004 | 0.70948 | 1.5414 | 3.324 | 0.94859 | 0.2175 | 0.62479 | 7.3658 | 0 | 0 | 0 | 0
G3.54 |  |  | Combined Sewer Overflow | Civils | nr | 686.7578 | B4 | 4083 | A3 | 80 | A3 | [6 empty] | 0 | 0.13398 | 0.15034 | 1.0143 | 0.81546 | 0.81732 | 0.60192 | 3.5334 | 0.0001066 | 0 | 0 |  | 28: 1.1012; 29: 0.13397; 30: 0.15034; 31: 0.39868; 32: 0.76505; 33: 0.65624; 34: 0.73534; 35: 2.8396; 36: 0.50537; 37: 0; 38: 0
G3.55 |  |  | Combined Sewer Overflow | MEICA | nr | 195.2074 | B4 | 1124 | A3 | 20 | A2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.56 |  |  | Combined Sewer Overflow | Total |  | 881.9652 | B4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.13398 | 0.15034 | 1.0143 | 0.81546 | 0.81732 | 0.60192 | 3.5334 | 0.0001066 | 0 | 0 | 0 | [7 empty] | 1.1012 | 0.13397 | 0.15034 | 0.39868 | 0.76505 | 0.65624 | 0.73534 | 2.8396 | 0.50537 | 0 | 0 | 0
G3.57 |  |  | Sewage Pumping Stations (Combined) | Civils | nr | 608.6749 | B4 | 7015 | A3 | 80 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.58 |  |  | Sewage Pumping Stations (Combined) | MEICA | nr | 426.9671 | B4 | 9847 | A3 | 20 | A2 | [6 empty] | 0 | 5.4898 | 9.0963 | 6.7783 | 10.5982 | 16.7484 | 7.1223 | 55.8333 | 0.060134 | 0 | 0 |  | 28: 1.1871; 29: 5.4897; 30: 9.0962; 31: 11.2808; 32: 9.2636; 33: 8.0942; 34: 7.4356; 35: 50.6601; 36: 1.041; 37: 0; 38: 0
G3.59 |  |  | Sewage Pumping Stations (Combined) | Total |  | 1035.6419 | B4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 5.4898 | 9.0963 | 6.7783 | 10.5982 | 16.7484 | 7.1223 | 55.8333 | 0.060134 | 0 | 0 | 0 | [7 empty] | 1.1871 | 5.4897 | 9.0962 | 11.2808 | 9.2636 | 8.0942 | 7.4356 | 50.6601 | 1.041 | 0 | 0 | 0
G3.60 |  |  | Other Sewage Structures (Combined) | Sewer structures | [13 empty] | 0 | 0.088829 | 0.19109 | 0.29841 | 0.25973 | 0.26165 | 0.18791 | 1.2876 | 0 | 0 | 0 |  | 28: 3.4952; 29: 0.088828; 30: 0.19109; 31: 0.058119; 32: 0.030172; 33: 0.070469; 34: 0.046727; 35: 0.4854; 36: 0; 37: 0; 38: 0
G3.61 |  |  | Other Sewage Structures (Combined) | Pipe bridges | [13 empty] | 0 | 4.638 | 3.6703 | 2.2484 | -0.88705 | -1.3412 | -1.601 | 6.7275 | 0.023464 | 0 | 0 |  | 0 | 16 | 9 | 1 | 11 | 5 | 0 | 8.9593 | 2.4205 | 2.3419 | 4.1019 | 3.4043 | 1.9475 | 3.3307 | 17.5467 | 1.2242 | 0 | 0
G3.62 |  |  | Other Sewage Structures (Combined) | Ancillaries | [13 empty] | 0 | 4.6803 | 5.5649 | 1.7548 | 1.6865 | -3.2175 | -3.2225 | 7.2465 | 0 | 0 | 0 |  | 28: 4.559; 29: 4.6802; 30: 5.5649; 31: 5.165; 32: 3.006; 33: 4.035; 34: 0.54748; 35: 22.9987; 36: 0; 37: 0; 38: 0
G3.63 |  |  | Other Sewage Structures (Combined) | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 9.4071 | 9.4263 | 4.3016 | 1.0592 | -4.297 | -4.6355 | 15.2616 | 0.023464 | 0 | 0 | 0 | [7 empty] | 17.0134 | 7.1895 | 8.0979 | 9.325 | 6.4405 | 6.053 | 3.9249 | 41.0307 | 1.2242 | 0 | 0 | 0
G3.64 |  |  | Infinite-Life Assets (Combined) | Sewers (combined) | km | 43515.1 | B4 | 38002.1 | B2 | [8 empty] | 0 | 33.2726 | 29.2902 | 29.4246 | 21.7756 | 27.825 | 12.6882 | 154.2763 | 0.30257 | 0 | 0 |  | 2 | 7661 | 5859.5 | 7260.5 | 2205 | 1845 | 3007 | 43.9163 | 33.2563 | 29.3188 | 37.2125 | 25.1161 | 21.2209 | 24.3693 | 170.4939 | 5.8156 | 0 | 0
G3.65 |  |  | Infinite-Life Assets (Combined) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0.75772 | 0.89716 | 0.89962 | 0.67314 | 3.2276 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0.48147; 33: 0.53866; 34: 0.77985; 35: 1.8; 36: 0; 37: 0; 38: 0
G3.66 |  |  | Infinite-Life Assets (Combined) | Total | km | 43515.1 | B4 | 38002.1 | B2 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 33.2726 | 29.2902 | 30.1824 | 22.6728 | 28.7246 | 13.3614 | 157.5039 | 0.30257 | 0 | 0 | 0 | [7 empty] | 43.9163 | 33.2563 | 29.3188 | 37.2125 | 25.5976 | 21.7596 | 25.1492 | 172.2939 | 5.8156 | 0 | 0 | 0
G3.67 |  | Wastewater Treatment Works | Wastewater Treatment Works (Combined) (Civils) | Civils | nr | 2792.6367 | B4 | 14790 | A2 | 80 | A3 | [6 empty] | 0 | 14.7601 | 19.4189 | 17.3092 | 16.7215 | 24.4219 | 11.2507 | 103.8823 | 0.28438 | 0 | 0 |  | 28: 11.2311; 29: 14.7636; 30: 19.4838; 31: 19.4898; 32: 20.9135; 33: 14.6102; 34: 15.6966; 35: 104.9576; 36: 2.1291; 37: 0; 38: 0
G3.68 |  |  | Wastewater Treatment Works (Combined) (Civils) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.69 |  |  | Wastewater Treatment Works (Combined) (Civils) | Total | nr | 2792.6367 | B4 | 14790 | A2 | 80 | A3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 14.7601 | 19.4189 | 17.3092 | 16.7215 | 24.4219 | 11.2507 | 103.8823 | 0.28438 | 0 | 0 | 0 | [7 empty] | 11.2311 | 14.7636 | 19.4838 | 19.4898 | 20.9135 | 14.6102 | 15.6966 | 104.9576 | 2.1291 | 0 | 0 | 0
G3.70 |  |  | Wastewater Treatment Works (Combined) (MEICA) | MEICA | nr | 1715.5987 | B4 | 15289 | A2 | 20 | A2 | [6 empty] | 0 | 6.5483 | 13.4735 | 13.9121 | 9.0105 | 8.9856 | 8.4771 | 60.4072 | 0.38547 | 0 | 0 |  | 28: 7.0114; 29: 6.5482; 30: 13.4735; 31: 10.1082; 32: 12.7639; 33: 13.8121; 34: 13.3839; 35: 70.0898; 36: 2.369; 37: 0; 38: 0
G3.71 |  |  | Wastewater Treatment Works (Combined) (MEICA) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.72 |  |  | Wastewater Treatment Works (Combined) (MEICA) | Total | nr | 1715.5987 | B4 | 15289 | A2 | 20 | A2 | 0 | 0 | 0 | 0 | 0 |  | 0 | 6.5483 | 13.4735 | 13.9121 | 9.0105 | 8.9856 | 8.4771 | 60.4072 | 0.38547 | 0 | 0 | 0 | [7 empty] | 7.0114 | 6.5482 | 13.4735 | 10.1082 | 12.7639 | 13.8121 | 13.3839 | 70.0898 | 2.369 | 0 | 0 | 0
G3.73 |  |  | Cess and Septic Tanks (Combined) (Civils) | Civils | nr | 137.8349 | C4 | 2518 | A2 | 80 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.74 |  |  | Cess and Septic Tanks (Combined) (Civils) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.75 |  |  | Cess and Septic Tanks (Combined) (Civils) | Total | nr | 137.8349 | C4 | 2518 | A2 | 80 | A3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.76 |  |  | Cess and Septic Tanks (Combined) (MEICA) | MEICA | nr | 10.2064 | C4 | 1297 | A2 | 20 | A2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.77 |  |  | Cess and Septic Tanks (Combined) (MEICA) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.78 |  |  | Cess and Septic Tanks (Combined) (MEICA) | Total | nr | 10.2064 | C4 | 1297 | A2 | 80 | A2 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.79 |  |  | Sludge Treatment Centres (Combined) | Civils | nr | 177.2678 | B4 | 348 | A2 | 80 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.80 |  |  | Sludge Treatment Centres (Combined) | MEICA | nr | 151.53 | B4 | 412 | A2 | 20 | A2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.81 |  |  | Sludge Treatment Centres (Combined) | Total |  | 328.7977 | B4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.82 |  | Discharge | Outfalls from Treatment (Combined) | Long and short sea outfalls (combined) | nr | 489.6059 | B4 | 1096 | B2 | 105 | A3 | [6 empty] | 0 | 0.26874 | 0.23466 | 0.32583 | 0.26677 | 0.19497 | 0.17278 | 1.4637 | 0 | 0 | 0 |  | 28: 0.87456; 29: 0.26874; 30: 0.23465; 31: 0.46131; 32: 0.27637; 33: 0.34373; 34: 0.10779; 35: 1.6926; 36: 0.014328; 37: 0; 38: 0
G3.83 |  |  | Outfalls from Treatment (Combined) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.84 |  |  | Outfalls from Treatment (Combined) | Total | nr | 489.6059 | B4 | 1096 | B2 | 105 | A3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.26874 | 0.23466 | 0.32583 | 0.26677 | 0.19497 | 0.17278 | 1.4637 | 0 | 0 | 0 | 0 | [7 empty] | 0.87456 | 0.26874 | 0.23465 | 0.46131 | 0.27637 | 0.34373 | 0.10779 | 1.6926 | 0.014328 | 0 | 0 | 0
G3.85 | Foul sewage only | Collection | Sewage and Sludge Pumping Mains (Foul Only) | Pumped foul only rising mains | km | 78.2669 | B4 | 300.2 | A4 | 38 | B3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.86 |  |  | Sewage and Sludge Pumping Mains (Foul Only) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.87 |  |  | Sewage and Sludge Pumping Mains (Foul Only) | Total | km | 78.2669 | B4 | 300.2 | A4 | 38 | B3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.88 |  |  | Emergency Outfalls (Foul Only) | Civils | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.89 |  |  | Emergency Outfalls (Foul Only) | MEICA | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.90 |  |  | Emergency Outfalls (Foul Only) | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.91 |  |  | Sewage Pumping Stations (Foul Only) | Civils | nr | 139.09 | B4 | 3213 | A3 | 80 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.92 |  |  | Sewage Pumping Stations (Foul Only) | MEICA | nr | 143.2442 | B4 | 4717 | A3 | 20 | A2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.93 |  |  | Sewage Pumping Stations (Foul Only) | Total |  | 282.3342 | B4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.94 |  |  | Other Sewage Structures (Foul Only) | Sewer structures | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.95 |  |  | Other Sewage Structures (Foul Only) | Pipe bridges | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.96 |  |  | Other Sewage Structures (Foul Only) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.97 |  |  | Other Sewage Structures (Foul Only) | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.98 |  |  | Infinite-Life Assets (Foul Only) | Sewers (foul only) | km | 7084.4 | B4 | 7666.1 | B2 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.99 |  |  | Infinite-Life Assets (Foul Only) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.100 |  |  | Infinite-Life Assets (Foul Only) | Total | km | 7084.4 | B4 | 7666.1 | B2 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.101 |  | Wastewater Treatment Works | Wastewater Treatment Works (Foul Only) (Civils) | Civils | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.102 |  |  | Wastewater Treatment Works (Foul Only) (Civils) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.103 |  |  | Wastewater Treatment Works (Foul Only) (Civils) | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.104 |  |  | Wastewater Treatment Works (Foul Only) (MEICA) | MEICA | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.105 |  |  | Wastewater Treatment Works (Foul Only) (MEICA) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.106 |  |  | Wastewater Treatment Works (Foul Only) (MEICA) | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.107 |  |  | Cess and Septic Tanks (Foul Only) (Civils) | Civils | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.108 |  |  | Cess and Septic Tanks (Foul Only) (Civils) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.109 |  |  | Cess and Septic Tanks (Foul Only) (Civils) | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.110 |  |  | Cess and Septic Tanks (Foul Only) (MEICA) | MEICA | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.111 |  |  | Cess and Septic Tanks (Foul Only) (MEICA) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.112 |  |  | Cess and Septic Tanks (Foul Only) (MEICA) | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.113 |  |  | Sludge Treatment Centres (Foul Only) | Civils | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.114 |  |  | Sludge Treatment Centres (Foul Only) | MEICA | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.115 |  |  | Sludge Treatment Centres (Foul Only) | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.116 |  | Discharge | Outfalls from Treatment (Foul Only) | Long and short sea outfalls (foul only) | nr | 0.38002 | B4 | 5 | B2 | 105 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.117 |  |  | Outfalls from Treatment (Foul Only) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.118 |  |  | Outfalls from Treatment (Foul Only) | Total | nr | 0.38002 | B4 | 5 | B2 | 105 | A3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.119 | Surface water only | Collection | Sewage and Sludge Pumping Mains (Surface Water Only) | Pumped surface water only rising mains | km | 3.499 | B3 | 6.2 | A4 | 38 | B3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.120 |  |  | Sewage and Sludge Pumping Mains (Surface Water Only) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.121 |  |  | Sewage and Sludge Pumping Mains (Surface Water Only) | Total | km | 3.499 | B3 | 6.2 | A4 | 38 | B3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.122 |  |  | Emergency Outfalls (Surface Water Only) | Civils | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.123 |  |  | Emergency Outfalls (Surface Water Only) | MEICA | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.124 |  |  | Emergency Outfalls (Surface Water Only) | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.125 |  |  | Surface Water Pumping Stations | Civils | nr | 20.241 | B4 | 198 | A3 | 80 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.126 |  |  | Surface Water Pumping Stations | MEICA | nr | 11.5094 | B4 | 262 | A3 | 20 | A2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.127 |  |  | Surface Water Pumping Stations | Total |  | 31.7504 | B4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.128 |  |  | Other Surface Water Structures | Surface water structures | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.129 |  |  | Other Surface Water Structures | Pipe bridges | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.130 |  |  | Other Surface Water Structures | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.131 |  |  | Other Surface Water Structures | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.132 |  |  | Infinite-Life Assets (Surface Water Only) | Surface water pipes | km | 10561.9 | B4 | 9021.4 | B2 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.133 |  |  | Infinite-Life Assets (Surface Water Only) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.134 |  |  | Infinite-Life Assets (Surface Water Only) | Total | km | 10561.9 | B4 | 9021.4 | B2 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.135 |  | Wastewater Treatment Works | Surface Water Storage and Treatment (Nature-Based) | SUDS | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0.01431; 32: 0.004448; 33: 0; 34: 0; 35: 0.018758; 36: 0; 37: 0; 38: 0
G3.136 |  |  | Surface Water Storage and Treatment (Nature-Based) | Wetlands | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.137 |  |  | Surface Water Storage and Treatment (Nature-Based) | Reed beds | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.138 |  |  | Surface Water Storage and Treatment (Nature-Based) | Swales | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.139 |  |  | Surface Water Storage and Treatment (Nature-Based) | Rain gardens | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.140 |  |  | Surface Water Storage and Treatment (Nature-Based) | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0.01431 | 0.004448 | 0 | 0 | 0.018758 | 0 | 0 | 0 | 0
G3.141 |  |  | Surface Water Storage and Treatment (MEICA) | MEICA | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.142 |  |  | Sludge Treatment Centres (Surface Water Only) | Civils | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.143 |  |  | Sludge Treatment Centres (Surface Water Only) | MEICA | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.144 |  |  | Sludge Treatment Centres (Surface Water Only) | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.145 |  | Discharge | Outfalls from Treatment (Surface Water Only) | Long and short sea outfalls (surface water only) | nr | 13.7015 | B4 | 142 | B2 | 105 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.146 |  |  | Outfalls from Treatment (Surface Water Only) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.147 |  |  | Outfalls from Treatment (Surface Water Only) | Total | nr | 13.7015 | B4 | 142 | B2 | 105 | A3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.148 | Shared | Business Services | Support Services | Vehicles | nr | 79.56 | B3 | 2559 | A2 | 5 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.149 |  |  | Support Services | Digital | nr | 4.571 | B2 | 4632 | A2 | 3 | A2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0.3392; 30: 0.90524; 31: 0.80822; 32: 0.34161; 33: 0.0084164; 34: 0; 35: 2.4027; 36: 0; 37: 0; 38: 0
G3.150 |  |  | Support Services | Facilities and estates | nr | 71.94 | C4 | 77 | B2 | 60 | A2 | [6 empty] | 0 | 1.2602 | 1.316 | 1.5844 | 0.95287 | 0.13168 | 0.074185 | 5.3193 | 0 | 0 | 0 |  | 28: 1.3341; 29: 1.4723; 30: 1.4029; 31: 1.7346; 32: 1.3519; 33: 1.1997; 34: 0.15204; 35: 7.3134; 36: 0; 37: 0; 38: 0
G3.151 |  |  | Support Services | Renewable energy | [13 empty] | 0 | 0.0062957 | -2.3728e-17 | -0.0015739 | -0.0015739 | -0.0015739 | -0.0015739 | -5.1063e-11 | 0 | 0 | 0 |  | 28: 0.097141; 29: 0.0062956; 30: 0; 31: 0; 32: -0.0041971; 33: -0.0020985; 34: 0; 35: 5.4846e-11; 36: 0; 37: 0; 38: 0
G3.152 |  |  | Support Services | Scientific services | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.153 |  |  | Support Services | Customer meters | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.154 |  |  | Support Services | Transformation | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G3.155 |  |  | Support Services | Other | nr | 15.67 | C4 | 35 | B3 | 60 | A3 | [6 empty] | 0 | -0.89617 | 1.2725 | -0.10049 | -0.15683 | 6.1068e-05 | 6.1033e-05 | 0.11915 | 0 | 0 | 0 |  | 28: -0.051789; 29: -0.89616; 30: 1.3001; 31: -1.7429; 32: 0.93817; 33: 0.80123; 34: 0.85672; 35: 1.2572; 36: 0.083527; 37: 0; 38: 0
G3.156 |  |  | Support Services | Total | nr | 171.741 | C4 | 7303 | A2 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.37029 | 2.5885 | 1.4823 | 0.79446 | 0.13017 | 0.072672 | 5.4384 | 0 | 0 | 0 | 0 | [7 empty] | 1.3795 | 0.92161 | 3.6082 | 0.79996 | 2.6275 | 2.0072 | 1.0088 | 10.9733 | 0.083527 | 0 | 0 | 0
G2.157 | Total | Total | Total | Total |  | 96010.9 | B4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 150.5272 | 176.9112 | 164.7726 | 168.2538 | 181.5588 | 166.6913 | 1008.7148 | 19.5867 | 0 | 0 | 0 | [7 empty] | 277.7402 | 163.9371 | 195.6996 | 235.5293 | 190.0747 | 156.3669 | 169.701 | 1111.3086 | 53.5856 | 0.030059 | 0 | 0
|  |  |  | Caclulated check on totals | [13 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE | TRUE |  | 28: TRUE; 29: TRUE; 30: TRUE; 31: TRUE; 32: TRUE; 33: TRUE; 34: TRUE; 36: TRUE; 37: TRUE; 38: TRUE
Prepared by: ……………………………………………...….. |  |  |  | Date: 07/10/2024
Checked by: ……………………………………………...….. |  |  |  | Date: 07/10/2024
Authorised by: …...........……………………...……............ |  |  |  | Date: 07/10/2024

## G4 - Refurbishment
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2024
SECTION G: INVESTMENT MONITORING
Table G4: Summary - Refurbishment | [33 empty] | Forecast based on IPS24.1 in AR24 | [6 empty] | Forecast based on IPS24.1 in AR24 |  |  |  | Forecast based on IPS24.1 in AR24
[5 empty] | Block A: Asset information | [6 empty] | Block B: Investment consistent with asset management policies | [5 empty] | Block C: Investment baseline (Investment Planning Scenario 23.2) | [11 empty] | Block D: Actual to date and updated forecast
Line ref. | Service | Functional activity | Asset category | Sub asset category | Asset units | Asset value (2017-18 prices) | CG | Asset stock | CG | Assumed asset life | CG | Projected expenditure from 2021-22 to 2026-27 (2017-18 prices) | Projected expenditure from 2027-28 to 2032-33 (2017-18 prices) | Projected expenditure from 2033-34 to 2038-39 (2017-18 prices) | Projected expenditure from 2039-40 to 2044-45 (2017-18 prices) | Projected expenditure from 2045-46 to 2050-51 (2017-18 prices) |  | Projected expenditure in investment baseline pre 2021-22 (2017-18 prices) | Projected expenditure in investment baseline in 2021-22 (2017-18 prices) | Projected expenditure in investment baseline in 2022-23 (2017-18 prices) | Projected expenditure in investment baseline in 2023-24 (2017-18 prices) | Projected expenditure in investment baseline in 2024-25 (2017-18 prices) | Projected expenditure in investment baseline in 2025-26 (2017-18 prices) | Projected expenditure in investment baseline in 2026-27 (2017-18 prices) | Projected expenditure from 2021-22 to 2026-27 (2017-18 prices) | Projected expenditure from 2027-28 to 2032-33 (2017-18 prices) | Projected expenditure from 2033-34 to 2038-39 (2017-18 prices) | Projected expenditure from 2039-40 to 2044-45 (2017-18 prices) | Projected expenditure from 2045-46 to 2050-51 (2017-18 prices) | Actual number of replacement interventions pre 2021-22 | Actual number of replacement interventions in 2021-22 | Actual number of replacement interventions in 2022-23 | Actual number of replacement interventions in 2023-24 | Projected number of replacement interventions in 2024-25 | Projected number of replacement interventions in 2025-26 | Projected number of replacement interventions in 2026-27 | Actual expenditure pre 2021-22 (2017-18 prices) | Actual expenditure in 2021-22 (2017-18 prices) | Actual expenditure in 2022-23 (2017-18 prices) | Actual expenditure in 2023-24 (2017-18 prices) | Projected expenditure in 2024-25 (2017-18 prices) | Projected expenditure in 2025-26 (2017-18 prices) | Projected expenditure in 2026-27 (2017-18 prices) | Projected expenditure from 2021-22 to 2026-27 (2017-18 prices) | Projected expenditure from 2027-28 to 2032-33 (2017-18 prices) | Projected expenditure from 2033-34 to 2038-39 (2017-18 prices) | Projected expenditure from 2039-40 to 2044-45 (2017-18 prices) | Projected expenditure from 2045-46 to 2050-51 (2017-18 prices)
[6 empty] | £m |  | nr |  | nr |  | £m | £m | £m | £m | £m |  | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | nr | nr | nr | nr | nr | nr | nr | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m
[6 empty] | 1 |  | 2 |  | 3 |  | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
G4.01 | Water | Source | Raw Water Pumping | Civils | nr | 50.6163 | B4 | 417 | A3 | 80 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.02 |  |  | Raw Water Pumping | MEICA | nr | 35.7978 | B4 | 616 | A3 | 20 | A2 | [6 empty] | 0 | 0.10448 | 0.018857 | 0.12114 | 0 | 0 | 0 | 0.24447 | 0 | 0 | 0 |  | 28: 0.052771; 29: 0.10852; 30: 0.01782; 31: 0.10495; 32: 0.10676; 33: 0; 34: 0; 35: 0.33805; 36: 0; 37: 0; 38: 0
G4.03 |  |  | Raw Water Pumping | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.04 |  |  | Raw Water Pumping | Total |  | 86.4141 | B4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.10448 | 0.018857 | 0.12114 | 0 | 0 | 0 | 0.24447 | 0 | 0 | 0 | 0 | [7 empty] | 0.052771 | 0.10852 | 0.01782 | 0.10495 | 0.10676 | 0 | 0 | 0.33805 | 0 | 0 | 0 | 0
G4.05 |  |  | Raw Water Mains | Raw water mains | km | 2102.5801 | B2 | 1678.821 | B2 | 115 | B3 | [6 empty] | 0 | 0.036911 | 0.22762 | 0.15202 | 0.15641 | 0.051642 | 0 | 0.6246 | 0 | 0 | 0 |  | 0 | 0 | 3 | 0 | 11 | 1 | 0 | 0 | 0.036731 | 0.069998 | 0.011365 | 0.11729 | 0.0066827 | 0 | 0.24206 | 0 | 0 | 0
G4.06 |  |  | Raw Water Mains | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.07 |  |  | Raw Water Mains | Total | km | 2102.5801 | B2 | 1678.821 | B2 | 115 | B3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.036911 | 0.22762 | 0.15202 | 0.15641 | 0.051642 | 0 | 0.6246 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0.036731 | 0.069998 | 0.011365 | 0.11729 | 0.0066827 | 0 | 0.24206 | 0 | 0 | 0 | 0
G4.08 |  |  | Infinite-Life Assets | Dams and impounding reservoirs | nr | 1579.3618 | C4 | 199 | C4 | [8 empty] | 0 | 0.40161 | 0.37166 | 0.84181 | 0.27835 | 0.71896 | 0.013233 | 2.6256 | 0 | 0 | 0 |  | 28: 1.9023; 29: 0.94732; 30: 0.53766; 31: 0.96411; 32: 5.0961; 33: 5.1639; 34: 2.2518; 35: 14.9609; 36: 0.16442; 37: 0; 38: 0
G4.09 |  |  | Infinite-Life Assets | Ancillaries | [13 empty] | 0 | 0.0090632 | 0 | 0.069661 | 0.0076408 | 0 | 0 | 0.086365 | 0 | 0 | 0 |  | 28: 0.012096; 29: 0.0090631; 30: 0; 31: 0.029737; 32: 0; 33: 0; 34: 0; 35: 0.0388; 36: 0; 37: 0; 38: 0
G4.10 |  |  | Infinite-Life Assets | Raw water storage (Civils) | [13 empty] | 0 | 0.2015 | 0.41008 | 0.55355 | 0.29811 | 0.35036 | 0.048522 | 1.8621 | 0.0021019 | 0 | 0 |  | 28: 0.014013; 29: 0.1004; 30: 0.1855; 31: 0.10093; 32: 0.15567; 33: 0.21375; 34: 0.0050724; 35: 0.76131; 36: 0.0020339; 37: 0; 38: 0
G4.11 |  |  | Infinite-Life Assets | Aqueduct | km | 2102.5801 | B2 | 1678.821 | B2 | [8 empty] | 0 | 0.063742 | 0.1062 | 0.066561 | 0.46504 | 0.026366 | 0 | 0.72791 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.12 |  |  | Infinite-Life Assets | Raw water intakes (Gravity) | nr | 25.9001 | C5 | 263 | C5 | [8 empty] | 0 | 0.1097 | 0.22648 | 0.80087 | 0.21911 | 0.0068597 | 0 | 1.363 | 0 | 0 | 0 |  | 28: 0.081231; 29: 0.10988; 30: 0.22725; 31: 0.7348; 32: 0.72682; 33: 0.23989; 34: 0.10217; 35: 2.1408; 36: 0.028819; 37: 0; 38: 0
G4.13 |  |  | Infinite-Life Assets | Catchment | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.14 |  |  | Infinite-Life Assets | Total |  | 3707.842 | C4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.78562 | 1.1144 | 2.3325 | 1.2683 | 1.1025 | 0.061755 | 6.6651 | 0.0021019 | 0 | 0 | 0 | [7 empty] | 2.0097 | 1.1667 | 0.9504 | 1.8296 | 5.9786 | 5.6175 | 2.359 | 17.9018 | 0.19527 | 0 | 0 | 0
G4.15 |  |  | Ground Water Sources (Pumped) | Civils | nr | 9.8642 | B4 | 247 | A3 | 80 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.16 |  |  | Ground Water Sources (Pumped) | MEICA | nr | 14.0521 | B4 | 309 | A3 | 20 | A2 | [6 empty] | 0 | 0.33538 | 0.18308 | 0.28717 | 0.063197 | 0.072959 | 0.090734 | 1.0325 | 0.0016534 | 0 | 0 |  | 28: 0.0059628; 29: 0.33538; 30: 0.18308; 31: 0.55631; 32: 0.20483; 33: 0.1321; 34: 0.026368; 35: 1.4381; 36: 0.014997; 37: 0; 38: 0
G4.17 |  |  | Ground Water Sources (Pumped) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.18 |  |  | Ground Water Sources (Pumped) | Total |  | 23.9163 | B4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.33538 | 0.18308 | 0.28717 | 0.063197 | 0.072959 | 0.090734 | 1.0325 | 0.0016534 | 0 | 0 | 0 | [7 empty] | 0.0059628 | 0.33538 | 0.18308 | 0.55631 | 0.20483 | 0.1321 | 0.026368 | 1.4381 | 0.014997 | 0 | 0 | 0
G4.19 |  | Water Treatment Works | Water Treatment Works (Civils) | Civils | nr | 1603.6435 | C4 | 6712 | A2 | 80 | A3 | [6 empty] | 0 | 1.8465 | 2.0239 | 0.8134 | 0.59665 | 1.1391 | 1.0239 | 7.4435 | 1.9879 | 0 | 0 |  | 28: 7.1407; 29: 1.8423; 30: 2.0167; 31: 1.2284; 32: 0.39699; 33: 0.37487; 34: 0.11077; 35: 5.97; 36: 0.015417; 37: 0; 38: 0
G4.20 |  |  | Water Treatment Works (Civils) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.21 |  |  | Water Treatment Works (Civils) | Total | nr | 1603.6435 | C4 | 6712 | A2 | 80 | A3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1.8465 | 2.0239 | 0.8134 | 0.59665 | 1.1391 | 1.0239 | 7.4435 | 1.9879 | 0 | 0 | 0 | [7 empty] | 7.1407 | 1.8423 | 2.0167 | 1.2284 | 0.39699 | 0.37487 | 0.11077 | 5.97 | 0.015417 | 0 | 0 | 0
G4.22 |  |  | Water Treatment Works (MEICA) | MEICA | nr | 1596.4242 | C4 | 7580 | A2 | 20 | A2 | [6 empty] | 0 | 4.7839 | 5.2879 | 6.5198 | 8.1182 | 13.4992 | 9.0044 | 47.2134 | 2.6917 | 0 | 0 |  | 28: 27.0455; 29: 4.8262; 30: 5.3456; 31: 8.9508; 32: 13.8294; 33: 13.7193; 34: 14.2874; 35: 60.9587; 36: 11.8095; 37: 0; 38: 0
G4.23 |  |  | Water Treatment Works (MEICA) | Ancillaries | [13 empty] | 0 | 0.25904 | 0.18015 | 0.18499 | 0.12857 | 0.84431 | 0.95412 | 2.5512 | 0.085641 | 0 | 0 |  | 28: 0.016816; 29: 0.25904; 30: 0.18015; 31: 0.14322; 32: 0.062941; 33: 0.12986; 34: 0.79523; 35: 1.5704; 36: 0.94871; 37: 0; 38: 0
G4.24 |  |  | Water Treatment Works (MEICA) | Filtration | [13 empty] | 0 | 0.97909 | 6.0891 | 4.7158 | 5.5934 | 15.7341 | 14.4942 | 47.6056 | 0.35178 | 0 | 0 |  | 28: 7.4229; 29: 0.97928; 30: 6.0179; 31: 5.3917; 32: 8.1246; 33: 0.6343; 34: 1.3366; 35: 22.4843; 36: 0.0056622; 37: 0; 38: 0
G4.25 |  |  | Water Treatment Works (MEICA) | Security | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.26 |  |  | Water Treatment Works (MEICA) | Total | nr | 1596.4242 | C4 | 7580 | A2 | 20 | A2 | 0 | 0 | 0 | 0 | 0 |  | 0 | 6.022 | 11.5571 | 11.4207 | 13.8401 | 30.0776 | 24.4527 | 97.3703 | 3.1291 | 0 | 0 | 0 | [7 empty] | 34.4852 | 6.0646 | 11.5437 | 14.4856 | 22.0169 | 14.4834 | 16.4192 | 85.0134 | 12.7638 | 0 | 0 | 0
G4.27 |  | Distribution | Treated Water Pumping | Civils | nr | 70.5206 | B4 | 1850 | A3 | 80 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.28 |  |  | Treated Water Pumping | MEICA | nr | 135.9626 | B4 | 3086 | A3 | 20 | A2 | [6 empty] | 0 | 0.24127 | 0.1636 | 0.59009 | 1.1076 | 3.5417 | 3.3547 | 8.9989 | 3.3295 | 0 | 0 |  | 28: 0.91209; 29: 0.24127; 30: 0.1636; 31: 0.24086; 32: 1.3349; 33: 3.4498; 34: 4.0433; 35: 9.4738; 36: 4.6636; 37: 0; 38: 0
G4.29 |  |  | Treated Water Pumping | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.30 |  |  | Treated Water Pumping | Total |  | 206.5 | B4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.24127 | 0.1636 | 0.59009 | 1.1076 | 3.5417 | 3.3547 | 8.9989 | 3.3295 | 0 | 0 | 0 | [7 empty] | 0.91209 | 0.24127 | 0.1636 | 0.24086 | 1.3349 | 3.4498 | 4.0433 | 9.4738 | 4.6636 | 0 | 0 | 0
G4.31 |  |  | Treated Water Storage | Civils | nr | 1769.7241 | B4 | 4624 | A2 | 80 | A3 | [6 empty] | 0 | 16.9648 | 21.3284 | 21.6303 | 16.4826 | 7.4585 | 13.3595 | 97.2243 | 1.4946 | 0 | 0 |  | 28: 13.7285; 29: 3.2186; 30: 1.9684; 31: 3.2105; 32: 2.8226; 33: 9.0566; 34: 4.8626; 35: 25.1393; 36: 3.9364; 37: 0; 38: 0
G4.32 |  |  | Treated Water Storage | MEICA | nr | 344.538 | B4 | 8193 | A2 | 20 | A2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.33 |  |  | Treated Water Storage | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.34 |  |  | Treated Water Storage | Total |  | 2114.2621 | B4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.9648 | 21.3284 | 21.6303 | 16.4826 | 7.4585 | 13.3595 | 97.2243 | 1.4946 | 0 | 0 | 0 | [7 empty] | 13.7285 | 3.2186 | 1.9684 | 3.2105 | 2.8226 | 9.0566 | 4.8626 | 25.1393 | 3.9364 | 0 | 0 | 0
G4.35 |  |  | Water Mains | Water trunk mains <300mm | km | 198.9268 | B4 | 476.085 | A2 | 105 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.36 |  |  | Water Mains | Water trunk mains >300mm | km | 3597.6888 | B4 | 5164.143 | A2 | 115 | A3 | [6 empty] | 0 | 0.66766 | 0.33594 | 0.24493 | 0.4894 | 0.088499 | 0 | 1.8264 | 0 | 0 | 0 |  | 0 | 33 | 1 | 0 | 0 | 60 | 0 | 0.077163 | 0.66765 | 0.022239 | 0.0094455 | 0 | 0.2731 | 0.21662 | 1.1891 | 0.086571 | 0 | 0
G4.37 |  |  | Water Mains | Water trunk mains asbestos cement | km | 123.5198 | B4 | 245.183 | A2 | 90 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.38 |  |  | Water Mains | Water distribution mains <300mm | km | 7724.9582 | B4 | 37894.099 | A2 | 105 | A3 | [6 empty] | 0 | 1.0948 | 0.94915 | 6.0543 | 5.9491 | 5.3771 | 4.7494 | 24.1738 | 2.5697e-05 | 0 | 0 |  | 0 | 1 | 2516 | 70 | 190000 | 178587 | 479020 | 6.6689 | 0.18731 | 0.087324 | 1.4342 | 3.4842 | 2.2472 | 2.8509 | 10.2911 | 0.0006084 | 0 | 0
G4.39 |  |  | Water Mains | Water distribution mains >300mm | km | 21.7098 | B4 | 36.599 | A2 | 115 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.40 |  |  | Water Mains | Water distribution mains asbestos cement | km | 872.4314 | B4 | 5408.321 | A2 | 90 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.41 |  |  | Water Mains | Ironworks | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.42 |  |  | Water Mains | Communication pipes | nr | 2258.9956 | C4 | 1852973 | B4 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.43 |  |  | Water Mains | Sub sea pipes | [13 empty] | 0 | 0 | 0.012205 | 0.08185 | 0.014751 | 0 | 0 | 0.10881 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0.012205 | 0.03763 | 0 | 0 | 0 | 0.049835 | 0 | 0 | 0
G4.44 |  |  | Water Mains | Pipe bridges | [13 empty] | 0 | 0.12105 | 0.75573 | 2.0063 | 1.7346 | 1.5527 | 0.93434 | 7.1047 | 0.62942 | 0 | 0 |  | 0 | 2 | 286 | 240 | 6 | 2 | 165 | 3.6912 | 0.51239 | 0.87653 | 2.2369 | 1.5594 | 2.0116 | 1.7696 | 8.9664 | 0.12388 | 0 | 0
G4.45 |  |  | Water Mains | Water network ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.46 |  |  | Water Mains | Leakage and consumption reduction measures | [13 empty] | 0 | 0.33712 | 0.17072 | 0.28329 | 0.24708 | 0.77277 | 1.3047 | 3.1156 | 0 | 0 | 0 |  | 0 | 5 | 4 | 4 | 10 | 5023 | 269 | 13.2493 | 0.52352 | 0.35787 | 0.25512 | 0.40377 | 0.38681 | 0.70804 | 2.6351 | 0.227 | 0 | 0
G4.47 |  |  | Water Mains | Total |  | 14798.2305 | B4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 2.2206 | 2.2237 | 8.6707 | 8.4349 | 7.7911 | 6.9884 | 36.3295 | 0.62944 | 0 | 0 | 0 | 0 | 41 | 2807 | 315 | 190016 | 183672 | 479454 | 23.6865 | 1.8909 | 1.3562 | 3.9733 | 5.4474 | 4.9188 | 5.5451 | 23.1316 | 0.43806 | 0 | 0 | 0
G4.48 |  |  | Water Meters | Water meters | nr | 119.5518 | B4 | 138074 | A3 | 10 | B3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.49 |  |  | Water Meters | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.50 |  |  | Water Meters | Total | nr | 119.5518 | B4 | 138074 | A3 | 10 | B3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.51 | Foul sewage & surface water shared assets | Collection | Pumped Combined Rising Mains | Pumped combined rising mains | km | 487.9817 | B4 | 1136.062 | A4 | 38 | B3 | [6 empty] | 0 | 0.035006 | 0.00057867 | 0 | 0 | 0 | 0 | 0.035585 | 0 | 0 | 0 |  | 0 | 1 | 0 | 4 | 840 | 0 | 0 | 0.018929 | 0.035006 | 0.00057866 | 2.3297 | 3.1884 | 0.019049 | 0 | 5.5728 | 0 | 0 | 0
G4.52 |  |  | Pumped Combined Rising Mains | Ancillaries | [13 empty] | 0 | 0 | 0.0021056 | 0.00063527 | 0 | 0.056649 | 0.065114 | 0.1245 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.53 |  |  | Pumped Combined Rising Mains | Total | km | 487.9817 | B4 | 1136.062 | A4 | 38 | B3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.035006 | 0.0026843 | 0.00063527 | 0 | 0.056649 | 0.065114 | 0.16009 | 0 | 0 | 0 | 0 | [7 empty] | 0.018929 | 0.035006 | 0.00057866 | 2.3297 | 3.1884 | 0.019049 | 0 | 5.5728 | 0 | 0 | 0 | 0
G4.54 |  |  | Combined Sewer Overflow | Civils | nr | 686.7578 | B4 | 4083 | A3 | 80 | A3 | [6 empty] | 0 | 0.0083395 | 0.023155 | 0.058629 | 0 | 0 | 0 | 0.090123 | 0 | 0 | 0 |  | 28: 0.017355; 29: 0.0083394; 30: 0.023155; 31: 0.15233; 32: 0.09953; 33: 0; 34: 0; 35: 0.28335; 36: 0; 37: 0; 38: 0
G4.55 |  |  | Combined Sewer Overflow | MEICA | nr | 195.2074 | B4 | 1124 | A3 | 20 | A2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.56 |  |  | Combined Sewer Overflow | Total |  | 881.9652 | B4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.0083395 | 0.023155 | 0.058629 | 0 | 0 | 0 | 0.090123 | 0 | 0 | 0 | 0 | [7 empty] | 0.017355 | 0.0083394 | 0.023155 | 0.15233 | 0.09953 | 0 | 0 | 0.28335 | 0 | 0 | 0 | 0
G4.57 |  |  | Sewage Pumping Stations (Combined) | Civils | nr | 608.6749 | B4 | 7015 | A3 | 80 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.58 |  |  | Sewage Pumping Stations (Combined) | MEICA | nr | 426.9671 | B4 | 9847 | A3 | 20 | A2 | [6 empty] | 0 | 1.6798 | 1.9592 | 4.158 | 2.9336 | 0.47752 | 0.35249 | 11.5606 | 0.24398 | 0 | 0 |  | 28: 5.7716; 29: 1.691; 30: 2.0204; 31: 6.1619; 32: 9.285; 33: 8.0604; 34: 3.7744; 35: 30.9932; 36: 0.028314; 37: 0; 38: 0
G4.59 |  |  | Sewage Pumping Stations (Combined) | Total |  | 1035.6419 | B4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 1.6798 | 1.9592 | 4.158 | 2.9336 | 0.47752 | 0.35249 | 11.5606 | 0.24398 | 0 | 0 | 0 | [7 empty] | 5.7716 | 1.691 | 2.0204 | 6.1619 | 9.285 | 8.0604 | 3.7744 | 30.9932 | 0.028314 | 0 | 0 | 0
G4.60 |  |  | Other Sewage Structures (Combined) | Sewer structures | [13 empty] | 0 | 0.019571 | -0.021105 | 0 | 0 | 0 | 0 | -0.0015347 | 0 | 0 | 0 |  | 28: 1.6343; 29: 0.01957; 30: -0.021105; 31: 0.30237; 32: 0; 33: 0; 34: 0; 35: 0.30084; 36: 0; 37: 0; 38: 0
G4.61 |  |  | Other Sewage Structures (Combined) | Pipe bridges | [13 empty] | 0 | 1.5982 | 0.51505 | 0.30343 | 2.8008 | 1.4056 | 0.029866 | 6.6529 | 0.01547 | 0 | 0 |  | 0 | 1 | 14 | 0 | 0 | 4 | 8 | 4.5326 | 3.3435 | 1.3236 | 0.46905 | 1.6021 | 3.9882 | 0.95023 | 11.6767 | -0.22758 | 0 | 0
G4.62 |  |  | Other Sewage Structures (Combined) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.63 |  |  | Other Sewage Structures (Combined) | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 1.6177 | 0.49394 | 0.30343 | 2.8008 | 1.4056 | 0.029866 | 6.6513 | 0.01547 | 0 | 0 | 0 | [7 empty] | 6.1669 | 3.3631 | 1.3025 | 0.77142 | 1.6021 | 3.9882 | 0.95023 | 11.9776 | -0.22758 | 0 | 0 | 0
G4.64 |  |  | Infinite-Life Assets (Combined) | Sewers (combined) | km | 43515.1 | B4 | 38002.1 | B2 | [8 empty] | 0 | 0.75613 | 2.1741 | 3.0947 | 4.7902 | 3.0915 | 1.678 | 15.5848 | 0.29388 | 0 | 0 |  | 0 | 96 | 1566.5 | 98 | 2385.2 | 2723 | 5362 | 9.0552 | 0.75612 | 1.5533 | 1.7568 | 3.8137 | 5.1782 | 5.5527 | 18.6109 | 2.2611 | 0 | 0
G4.65 |  |  | Infinite-Life Assets (Combined) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.66 |  |  | Infinite-Life Assets (Combined) | Total | km | 43515.1 | B4 | 38002.1 | B2 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.75613 | 2.1741 | 3.0947 | 4.7902 | 3.0915 | 1.678 | 15.5848 | 0.29388 | 0 | 0 | 0 | [7 empty] | 9.0552 | 0.75612 | 1.5533 | 1.7568 | 3.8137 | 5.1782 | 5.5527 | 18.6109 | 2.2611 | 0 | 0 | 0
G4.67 |  | Wastewater Treatment Works | Wastewater Treatment Works (Combined) (Civils) | Civils | nr | 2792.6367 | B4 | 14790 | A2 | 80 | A3 | [6 empty] | 0 | 6.3112 | 8.925 | 11.8774 | 7.8151 | 7.7378 | 6.6944 | 49.3608 | 2.5283 | 0 | 0 |  | 28: 15.2309; 29: 6.3156; 30: 8.9723; 31: 15.9731; 32: 17.797; 33: 15.4902; 34: 11.2736; 35: 75.8217; 36: 4.7483; 37: 0; 38: 0
G4.68 |  |  | Wastewater Treatment Works (Combined) (Civils) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.69 |  |  | Wastewater Treatment Works (Combined) (Civils) | Total | nr | 2792.6367 | B4 | 14790 | A2 | 80 | A3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 6.3112 | 8.925 | 11.8774 | 7.8151 | 7.7378 | 6.6944 | 49.3608 | 2.5283 | 0 | 0 | 0 | [7 empty] | 15.2309 | 6.3156 | 8.9723 | 15.9731 | 17.797 | 15.4902 | 11.2736 | 75.8217 | 4.7483 | 0 | 0 | 0
G4.70 |  |  | Wastewater Treatment Works (Combined) (MEICA) | MEICA | nr | 1715.5987 | B4 | 15289 | A2 | 20 | A2 | [6 empty] | 0 | 1.3325 | 3.7111 | 3.6021 | 4.0984 | 2.3517 | 0.83385 | 15.9296 | 0.37125 | 0 | 0 |  | 28: 2.616; 29: 1.3178; 30: 3.5406; 31: 3.4054; 32: 1.8197; 33: 2.8432; 34: 1.092; 35: 14.0188; 36: 0.2386; 37: 0; 38: 0
G4.71 |  |  | Wastewater Treatment Works (Combined) (MEICA) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.72 |  |  | Wastewater Treatment Works (Combined) (MEICA) | Total | nr | 1715.5987 | B4 | 15289 | A2 | 20 | A2 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1.3325 | 3.7111 | 3.6021 | 4.0984 | 2.3517 | 0.83385 | 15.9296 | 0.37125 | 0 | 0 | 0 | [7 empty] | 2.616 | 1.3178 | 3.5406 | 3.4054 | 1.8197 | 2.8432 | 1.092 | 14.0188 | 0.2386 | 0 | 0 | 0
G4.73 |  |  | Cess and Septic Tanks (Combined) (Civils) | Civils | nr | 137.8349 | C4 | 2518 | A2 | 80 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.74 |  |  | Cess and Septic Tanks (Combined) (Civils) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.75 |  |  | Cess and Septic Tanks (Combined) (Civils) | Total | nr | 137.8349 | C4 | 2518 | A2 | 80 | A3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.76 |  |  | Cess and Septic Tanks (Combined) (MEICA) | MEICA | nr | 10.2064 | C4 | 1297 | A2 | 20 | A2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.77 |  |  | Cess and Septic Tanks (Combined) (MEICA) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.78 |  |  | Cess and Septic Tanks (Combined) (MEICA) | Total | nr | 10.2064 | C4 | 1297 | A2 | 80 | A2 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.79 |  |  | Sludge Treatment Centres (Combined) | Civils | nr | 177.2678 | B4 | 348 | A2 | 80 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.80 |  |  | Sludge Treatment Centres (Combined) | MEICA | nr | 151.53 | B4 | 412 | A2 | 20 | A2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.81 |  |  | Sludge Treatment Centres (Combined) | Total |  | 328.7977 | B4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.82 |  | Discharge | Outfalls from Treatment (Combined) | Long and short sea outfalls (combined) | nr | 489.6059 | B4 | 1096 | B2 | 105 | A3 | [6 empty] | 0 | 0.035717 | 0.10736 | 0.47893 | 1.3676 | 0.33749 | 0.0075892 | 2.3347 | 0.0054099 | 0 | 0 |  | 28: 0; 29: 0.035717; 30: 0.10736; 31: 0.27869; 32: 0.42776; 33: 1.4311; 34: 0.021087; 35: 2.3017; 36: 0.0094764; 37: 0; 38: 0
G4.83 |  |  | Outfalls from Treatment (Combined) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.84 |  |  | Outfalls from Treatment (Combined) | Total | nr | 489.6059 | B4 | 1096 | B2 | 105 | A3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.035717 | 0.10736 | 0.47893 | 1.3676 | 0.33749 | 0.0075892 | 2.3347 | 0.0054099 | 0 | 0 | 0 | [7 empty] | 0 | 0.035717 | 0.10736 | 0.27869 | 0.42776 | 1.4311 | 0.021087 | 2.3017 | 0.0094764 | 0 | 0 | 0
G4.85 | Foul sewage only | Collection | Sewage and Sludge Pumping Mains (Foul Only) | Pumped foul only rising mains | km | 78.2669 | B4 | 300.2 | A4 | 38 | B3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.86 |  |  | Sewage and Sludge Pumping Mains (Foul Only) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.87 |  |  | Sewage and Sludge Pumping Mains (Foul Only) | Total | km | 78.2669 | B4 | 300.2 | A4 | 38 | B3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.88 |  |  | Emergency Outfalls (Foul Only) | Civils | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.89 |  |  | Emergency Outfalls (Foul Only) | MEICA | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.90 |  |  | Emergency Outfalls (Foul Only) | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.91 |  |  | Sewage Pumping Stations (Foul Only) | Civils | nr | 139.09 | B4 | 3213 | A3 | 80 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.92 |  |  | Sewage Pumping Stations (Foul Only) | MEICA | nr | 143.2442 | B4 | 4717 | A3 | 20 | A2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.93 |  |  | Sewage Pumping Stations (Foul Only) | Total |  | 282.3342 | B4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.94 |  |  | Other Sewage Structures (Foul Only) | Sewer structures | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.95 |  |  | Other Sewage Structures (Foul Only) | Pipe bridges | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.96 |  |  | Other Sewage Structures (Foul Only) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.97 |  |  | Other Sewage Structures (Foul Only) | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.98 |  |  | Infinite-Life Assets (Foul Only) | Sewers (foul only) | km | 7084.4 | B4 | 7666.1 | B2 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.99 |  |  | Infinite-Life Assets (Foul Only) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.100 |  |  | Infinite-Life Assets (Foul Only) | Total | km | 7084.4 | B4 | 7666.1 | B2 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.101 |  | Wastewater Treatment Works | Wastewater Treatment Works (Foul Only) (Civils) | Civils | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.102 |  |  | Wastewater Treatment Works (Foul Only) (Civils) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.103 |  |  | Wastewater Treatment Works (Foul Only) (Civils) | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.104 |  |  | Wastewater Treatment Works (Foul Only) (MEICA) | MEICA | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.105 |  |  | Wastewater Treatment Works (Foul Only) (MEICA) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.106 |  |  | Wastewater Treatment Works (Foul Only) (MEICA) | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.107 |  |  | Cess and Septic Tanks (Foul Only) (Civils) | Civils | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.108 |  |  | Cess and Septic Tanks (Foul Only) (Civils) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.109 |  |  | Cess and Septic Tanks (Foul Only) (Civils) | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.110 |  |  | Cess and Septic Tanks (Foul Only) (MEICA) | MEICA | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.111 |  |  | Cess and Septic Tanks (Foul Only) (MEICA) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.112 |  |  | Cess and Septic Tanks (Foul Only) (MEICA) | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.113 |  |  | Sludge Treatment Centres (Foul Only) | Civils | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.114 |  |  | Sludge Treatment Centres (Foul Only) | MEICA | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.115 |  |  | Sludge Treatment Centres (Foul Only) | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.116 |  | Discharge | Outfalls from Treatment (Foul Only) | Long and short sea outfalls (foul only) | nr | 0.38002 | B4 | 5 | B2 | 105 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.117 |  |  | Outfalls from Treatment (Foul Only) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.118 |  |  | Outfalls from Treatment (Foul Only) | Total | nr | 0.38002 | B4 | 5 | B2 | 105 | A3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.119 | Surface water only | Collection | Sewage and Sludge Pumping Mains (Surface Water Only) | Pumped surface water only rising mains | km | 3.499 | B3 | 6.2 | A4 | 38 | B3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.120 |  |  | Sewage and Sludge Pumping Mains (Surface Water Only) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.121 |  |  | Sewage and Sludge Pumping Mains (Surface Water Only) | Total | km | 3.499 | B3 | 6.2 | A4 | 38 | B3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.122 |  |  | Emergency Outfalls (Surface Water Only) | Civils | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.123 |  |  | Emergency Outfalls (Surface Water Only) | MEICA | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.124 |  |  | Emergency Outfalls (Surface Water Only) | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.125 |  |  | Surface Water Pumping Stations | Civils | nr | 20.241 | B4 | 198 | A3 | 80 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.126 |  |  | Surface Water Pumping Stations | MEICA | nr | 11.5094 | B4 | 262 | A3 | 20 | A2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.127 |  |  | Surface Water Pumping Stations | Total |  | 31.7504 | B4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.128 |  |  | Other Surface Water Structures | Surface water structures | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.129 |  |  | Other Surface Water Structures | Pipe bridges | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.130 |  |  | Other Surface Water Structures | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.131 |  |  | Other Surface Water Structures | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.132 |  |  | Infinite-Life Assets (Surface Water Only) | Surface water pipes | km | 10561.9 | B4 | 9021.4 | B2 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.133 |  |  | Infinite-Life Assets (Surface Water Only) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.134 |  |  | Infinite-Life Assets (Surface Water Only) | Total | km | 10561.9 | B4 | 9021.4 | B2 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.135 |  | Wastewater Treatment Works | Surface Water Storage and Treatment (Nature-Based) | SUDS | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0.01261; 32: 0; 33: 0; 34: 0; 35: 0.01261; 36: 0; 37: 0; 38: 0
G4.136 |  |  | Surface Water Storage and Treatment (Nature-Based) | Wetlands | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.137 |  |  | Surface Water Storage and Treatment (Nature-Based) | Reed beds | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.138 |  |  | Surface Water Storage and Treatment (Nature-Based) | Swales | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.139 |  |  | Surface Water Storage and Treatment (Nature-Based) | Rain gardens | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.140 |  |  | Surface Water Storage and Treatment (Nature-Based) | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0.01261 | 0 | 0 | 0 | 0.01261 | 0 | 0 | 0 | 0
G4.141 |  |  | Surface Water Storage and Treatment (MEICA) | MEICA | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.142 |  |  | Sludge Treatment Centres (Surface Water Only) | Civils | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.143 |  |  | Sludge Treatment Centres (Surface Water Only) | MEICA | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.144 |  |  | Sludge Treatment Centres (Surface Water Only) | Total |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.145 |  | Discharge | Outfalls from Treatment (Surface Water Only) | Long and short sea outfalls (surface water only) | nr | 13.7015 | B4 | 142 | B2 | 105 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.146 |  |  | Outfalls from Treatment (Surface Water Only) | Ancillaries | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.147 |  |  | Outfalls from Treatment (Surface Water Only) | Total | nr | 13.7015 | B4 | 142 | B2 | 105 | A3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4.148 | Shared | Business Services | Support Services | Vehicles | nr | 79.56 | B3 | 2559 | A2 | 5 | A3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.149 |  |  | Support Services | Digital | nr | 4.571 | B2 | 4632 | A2 | 3 | A2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.150 |  |  | Support Services | Facilities and estates | nr | 71.94 | C4 | 77 | B2 | 60 | A2 | [6 empty] | 0 | 0.77564 | 0.91896 | 1.596 | 0.81649 | 2.1637 | 3.624 | 9.8948 | 0 | 0 | 0 |  | 28: 0.00097692; 29: 0.6603; 30: 0.79465; 31: 1.2962; 32: 3.6471; 33: 2.3003; 34: 0.80749; 35: 9.506; 36: 0; 37: 0; 38: 0
G4.151 |  |  | Support Services | Renewable energy | [13 empty] | 0 | -0.0011723 | 0 | 0 | 0 | 0 | 0 | -0.0011723 | 0 | 0 | 0 |  | 28: 0.61182; 29: -0.0011723; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: -0.0011723; 36: 0; 37: 0; 38: 0
G4.152 |  |  | Support Services | Scientific services | [13 empty] | 0 | 0.69402 | 0.8724 | 2.0013 | 7.8431 | 8.631 | 11.7957 | 31.8375 | 3.423 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.153 |  |  | Support Services | Customer meters | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.154 |  |  | Support Services | Transformation | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28: 0; 29: 0; 30: 0; 31: 0; 32: 0; 33: 0; 34: 0; 35: 0; 36: 0; 37: 0; 38: 0
G4.155 |  |  | Support Services | Other | nr | 15.67 | C4 | 35 | B3 | 60 | A3 | [6 empty] | 0 | 0.00080513 | 0.028321 | 0.21001 | 0.44607 | 0.080849 | 0.00096077 | 0.76701 | 0 | 0 | 0 |  | 28: 0.0010816; 29: 0.00080512; 30: 0.00073919; 31: 0.00035982; 32: 0.0087521; 33: 0.059395; 34: 0.033423; 35: 0.10347; 36: 0.0016964; 37: 0; 38: 0
G4.156 |  |  | Support Services | Total | nr | 171.741 | C4 | 7303 | A2 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 1.4693 | 1.8197 | 3.8073 | 9.1056 | 10.8756 | 15.4207 | 42.4982 | 3.423 | 0 | 0 | 0 | [7 empty] | 0.61387 | 0.65994 | 0.79539 | 1.2966 | 3.6558 | 2.3597 | 0.84092 | 9.6083 | 0.0016964 | 0 | 0 | 0
G4.157 | Total | Total | Total | Total |  | 96010.9 | B4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 41.8033 | 58.057 | 73.399 | 74.8612 | 77.569 | 74.4137 | 400.1032 | 17.4556 | 0 | 0 | 0 | [7 empty] | 121.5122 | 29.0874 | 36.5855 | 57.7796 | 80.1153 | 77.4098 | 56.8715 | 337.8491 | 29.0875 | 0 | 0 | 0
|  |  |  | Caclulated check on totals | [13 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE | TRUE |  | 28: TRUE; 29: TRUE; 30: TRUE; 31: TRUE; 32: TRUE; 33: TRUE; 34: TRUE; 36: TRUE; 37: TRUE; 38: TRUE
Prepared by: ……………………………………………...….. |  |  |  | Date: 07/10/2024
Checked by: ……………………………………………...….. |  |  |  | Date: 07/10/2024
Authorised by: …...........……………………...……............ |  |  |  | Date: 07/10/2024

## G5a - Enh & Growth
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2024
SECTION G: INVESTMENT MONITORING
Table G5a: Summary - Enhancement and Growth |  |  |  |  | Based on IPS23.2 in this AR24 and subsequent returns | [36 empty] | Forecast based on IPS24.1 in AR24 | [10 empty] | Forecast based on IPS24.1 in AR24 | [10 empty] | Forecast based on IPS24.1 in AR24
|  |  |  | Block A: Driver | Block B: Baseline outputs | [10 empty] | Block C: Baseline expenditure in the year (2017-18 price base) | [10 empty] | Block D: Baseline expenditure in the year (outturn prices) | [10 empty] | Block E: Actual and forecast outputs | [10 empty] | Block F: Actual and forecast expenditure in the year (2017-18 price base) | [10 empty] | Block G: Actual and forecast expenditure in the year (outturn prices)
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 53 | 54 | 55 | 56
Line Ref. | Description of output category | Units | Field Type | Driver | [33 empty] | Actual | Actual Year | Actual Year | Report Year | Forecast Year | Forecast Year | Forecast Year | Forecast Year | Forecast Year | Forecast Year | Forecast Year | Actual | Actual Year | Actual Year | Report Year | Forecast Year | Forecast Year | Forecast Year | Forecast Years | Forecast Years | Forecast Years | Forecast Years | Actual | Actual Year | Actual Year | Report Year | Forecast Year | Forecast Year | Forecast Year | Forecast Years | Forecast Years | Forecast Years | Forecast Years
[5 empty] | Pre 2021-22 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-33 | 2033-39 | 2039-45 | 2045-51 | Pre 2021-22 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-33 | 2033-39 | 2039-45 | 2045-51 | Pre 2021-22 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-33 | 2033-39 | 2039-45 | 2045-51 | Pre 2021-22 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-33 | 2033-39 | 2039-45 | 2045-51 | Pre 2021-22 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-33 | 2033-39 | 2039-45 | 2045-51 | Pre 2021-22 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-33 | 2033-39 | 2039-45 | 2045-51
[16 empty] | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | nr | nr | nr | nr | nr | nr | nr | nr | nr | nr | nr | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | bar: Block B: Baseline outputs 2 to Block B: Baseline outputs 12
Growth
G5a.01 | Increase in strategic capacity at water Part 4 assets | Number | I / BF |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.68555 | 0.29825 | 1.9055 | 1.0975 | 5.0046 | 4.9292 | 0.88015 | 0 | 0 | 0 | 0 | 0.76281 | 0.36524 | 2.4658 | 1.4543 | 6.8042 | 6.8356 | 1.3089 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.1707 | 0.8651 | 0.5073 | 0.99593 | 7.3568 | 7.2592 | 4.2361 | 0.016501 | 0 | 0 | 0 | 10.8837 | 0.96259 | 0.62125 | 1.2888 | 9.7487 | 9.8694 | 5.8744 | 0.024539 | 0 | 0 | 0
G5a.02 | Increase in strategic capacity at wastewater Part 4 assets |  | I / BF | [12 empty] | 0 | 32.7782 | 39.2591 | 6.2915 | 31.6282 | 24.2331 | 19.4107 | 69.8444 | 0 | 0 | 0 | 0 | 36.472 | 48.0778 | 8.1417 | 41.9111 | 32.9467 | 26.9181 | 103.8683 | 0 | 0 | 0 | [11 empty] | 84.3277 | 31.5324 | 37.5588 | 33.5841 | 12.6544 | 33.8899 | 29.438 | 122.8051 | 0.10281 | 0 | 0 | 90.239 | 35.0858 | 45.9955 | 43.4599 | 16.7687 | 46.0758 | 40.8236 | 182.6283 | 0.17219 | 0 | 0
G5a.03 | Increase in strategic capacity at water Part 3 assets |  | I / BF |  | 0 | 10759 | 3256 | 16768 | 42132 | 32000 | 10001 | 0 | 0 | 0 | 0 | 0 | 9.9923 | 14.4179 | 8.9031 | 8.1459 | 3.323 | 2.477e-11 | 0.67371 | 0 | 0 | 0 | 0 | 11.1183 | 17.6566 | 11.5212 | 10.7944 | 4.5179 | 3.4351e-11 | 1.0019 | 0 | 0 | 0 | 0 | 11665 | 3256 | 11026 | 21072 | 2174 | 35133 | 0 | 0 | 0 | 0 | 23.5016 | 9.1237 | 13.1229 | 10.1813 | 6.4748 | 3.1901 | 2.6888 | 26.6884 | 0.00035045 | 0 | 0 | 25.1491 | 10.1519 | 16.0706 | 13.1753 | 8.5799 | 4.3372 | 3.7288 | 39.6894 | 0.00058692 | 0 | 0
G5a.04 | Increase in strategic capacity at wastewater Part 3 assets |  | I / BF |  | 0 | 906 | 0 | 107 | 36289 | 59440 | 31810 | 0 | 0 | 0 | 0 | 0 | 0.85069 | 2.5132 | 7.5031 | 18.4639 | 24.5643 | 6.5567 | 1.545 | 0 | 0 | 0 | 0 | 0.94655 | 3.0777 | 9.7095 | 24.4668 | 33.397 | 9.0926 | 2.2977 | 0 | 0 | 0 | 0 | 1259 | 0 | 21101 | 10708 | 11243 | 0 | 0 | 0 | 0 | 0 | 10.8765 | 1.7816 | 3.1002 | 7.6577 | 12.4357 | 19.5215 | 15.9543 | 20.3495 | 0 | 0 | 0 | 11.6389 | 1.9824 | 3.7966 | 9.9095 | 16.4788 | 26.5409 | 22.1249 | 30.2626 | 0 | 0 | 0
G5a.05 | Increase in strategic capacity at foul sewerage Part 3 assets |  | I / BF | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G5a.06 | Increase in strategic capacity at surface water Part 3 assets |  | I / BF | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enhancements - Water Quality
G5a.07 | Chemicals & Compounds |  | I / BF | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G5a.08 | Discolouration |  | I / BF | [12 empty] | 0 | 3.3724 | 3.7587 | 0.40183 | 0.43779 | -0.98542 | -1.3212 | 0 | 0 | 0 | 0 | 0 | 3.7524 | 4.603 | 0.51999 | 0.58013 | -1.3397 | -1.8322 | 0 | 0 | 0 | 0 | [11 empty] | 0.84222 | 3.44 | 3.6866 | 2.2658 | 2.4537 | 1.3124 | 0.40093 | 2.0421 | 0 | 0 | 0 | 0.90126 | 3.8276 | 4.5147 | 2.9321 | 3.2515 | 1.7843 | 0.55599 | 3.0369 | 0 | 0 | 0
G5a.09 | Lead |  | I / BF | [12 empty] | 0 | 2.5151 | 6.0101 | 4.5496 | 3.9326 | 5.3822 | 9.2529 | 4.0039 | 0 | 0 | 0 | 0 | 2.7985 | 7.3601 | 5.8875 | 5.2112 | 7.3174 | 12.8316 | 5.9544 | 0 | 0 | 0 | [11 empty] | 0.82626 | 2.0738 | 3.402 | 3.1814 | 7.8438 | 6.3866 | 4.2622 | 0.06479 | 0 | 0 | 0 | 0.88419 | 2.3075 | 4.1662 | 4.1169 | 10.3939 | 8.6831 | 5.9106 | 0.096352 | 0 | 0 | 0
G5a.10 | Microbiology |  | I / BF | [12 empty] | 0 | 21.4543 | 8.9228 | 3.8625 | 19.9163 | 13.1822 | 7.1535 | 11.5219 | 0 | 0 | 0 | 0 | 23.872 | 10.927 | 4.9984 | 26.3914 | 17.9222 | 9.9202 | 17.1347 | 0 | 0 | 0 | [11 empty] | 30.5068 | 21.5725 | 9.1246 | 7.2385 | 4.0666 | 2.4579 | 8.8039 | 37.9352 | 0.018664 | 0 | 0 | 32.6453 | 24.0035 | 11.1742 | 9.3671 | 5.3888 | 3.3417 | 12.209 | 56.415 | 0.031258 | 0 | 0
G5a.11 | Organics & DBPs |  | I / BF | [12 empty] | 0 | 31.5279 | 23.5 | 16.8827 | 13.0131 | 24.9868 | 57.7039 | 153.8258 | 0 | 0 | 0 | 0 | 35.0808 | 28.7787 | 21.8473 | 17.244 | 33.9714 | 80.0217 | 228.7604 | 0 | 0 | 0 | [11 empty] | 40.1079 | 31.9859 | 26.294 | 32.6474 | 19.9388 | 27.3994 | 81.2897 | 401.7764 | 0.4437 | 0 | 0 | 42.9195 | 35.5904 | 32.2003 | 42.2478 | 26.4214 | 37.2514 | 112.7297 | 597.4976 | 0.74309 | 0 | 0
G5a.12 | Taste & Odour |  | I / BF | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G5a.13 | Enhancements - Water Quality total expenditure | £m | C | [12 empty] | 0 | 58.8696 | 42.1915 | 25.6968 | 37.2998 | 42.5657 | 72.789 | 169.3517 | 0 | 0 | 0 | 0 | 65.5036 | 51.6688 | 33.2532 | 49.4267 | 57.8712 | 100.9412 | 251.8495 | 0 | 0 | 0 | [11 empty] | 72.2832 | 59.0721 | 42.5072 | 45.3331 | 34.303 | 37.5563 | 94.7568 | 441.8185 | 0.46236 | 0 | 0 | 77.3503 | 65.729 | 52.0554 | 58.6639 | 45.4556 | 51.0605 | 131.4053 | 657.0458 | 0.77434 | 0 | 0
Enhancements - Water Environment
G5a.14 | Network Discharges |  | I / BF | [12 empty] | 0 | 4.8735 | 3.1182 | 11.4642 | 19.7402 | 42.2228 | 54.236 | 6.8526 | 0 | 0 | 0 | 0 | 5.4227 | 3.8187 | 14.8353 | 26.1582 | 57.405 | 75.2126 | 10.1908 | 0 | 0 | 0 | [11 empty] | 12.397 | 4.893 | 2.8102 | 11.4408 | 12.6533 | 25.628 | 63.2281 | 33.5149 | 0 | 0 | 0 | 13.266 | 5.4444 | 3.4414 | 14.8051 | 16.7672 | 34.8432 | 87.6824 | 49.8414 | 0 | 0 | 0
G5a.15 | Network Improvements |  | I / BF | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G5a.16 | Regulatory Abstraction and Impoundment | Number | I / BF |  | 0 | 3 | 5 | 1 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 3.3931 | 0.68494 | 0.64855 | 0.89515 | 2.013 | 2.952 | 1.3629 | 0 | 0 | 0 | 0 | 3.7755 | 0.83879 | 0.83927 | 1.1862 | 2.7369 | 4.0938 | 2.0268 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 8.2722 | 3.3851 | 0.67776 | 0.11733 | 2.2398 | 2.0053 | 2.1613 | 2.2137 | 0 | 0 | 0 | 8.852 | 3.7666 | 0.83001 | 0.15183 | 2.9681 | 2.7264 | 2.9973 | 3.2921 | 0 | 0 | 0
G5a.17 | Resource Recovery |  | I / BF | [12 empty] | 0 | 0.38955 | 0.19035 | 1.5122 | 2.0599 | 4.8616 | 9.7407 | 24.0078 | 0 | 0 | 0 | 0 | 0.43345 | 0.2331 | 1.9568 | 2.7296 | 6.6097 | 13.508 | 35.703 | 0 | 0 | 0 | [11 empty] | 0 | 0.38955 | 0.19035 | 0.25495 | 4.6656 | 11.0145 | -0.76087 | 178.3689 | 0 | 0 | 0 | 0 | 0.43344 | 0.2331 | 0.32992 | 6.1824 | 14.975 | -1.0551 | 265.2594 | 0 | 0 | 0
G5a.18 | Treatment Discharges | Number | I / BF |  | 0 | 1 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4771 | 0.61662 | 11.619 | 23.4056 | 29.8881 | 20.4581 | 84.9537 | 0 | 0 | 0 | 0 | 1.6436 | 0.75513 | 15.0358 | 31.0153 | 40.6351 | 28.3706 | 126.338 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 7 | 2 | 6 | 0 | 0 | 0 | 0 | 6.478 | 1.6314 | 0.7327 | 1.0441 | 2.8158 | 19.0186 | 37.1212 | 24.7612 | 0.00071652 | 0 | 0 | 6.9321 | 1.8152 | 0.89729 | 1.3512 | 3.7313 | 25.8571 | 51.4784 | 36.8234 | 0.0012 | 0 | 0
G5a.19 | Treatment Improvements |  | I / BF | [12 empty] | 0 | 2.2759 | 4.0551 | 1.5843 | 2.6995 | 2.5844 | 1.1913 | 0.01639 | 0 | 0 | 0 | 0 | 2.5324 | 4.966 | 2.0502 | 3.5771 | 3.5137 | 1.652 | 0.024375 | 0 | 0 | 0 | [11 empty] | 4.7425 | 2.2711 | 4.0554 | 3.9673 | 5.8867 | 4.6194 | 3.6902 | 0.56082 | 0 | 0 | 0 | 5.0749 | 2.527 | 4.9663 | 5.1339 | 7.8006 | 6.2804 | 5.1174 | 0.83401 | 0 | 0 | 0
G5a.20 | Enhancements - Water Environment total expenditure | £m | C | [12 empty] | 0 | 12.4092 | 8.6652 | 26.8282 | 48.8003 | 81.57 | 88.5781 | 117.1934 | 0 | 0 | 0 | 0 | 13.8075 | 10.6117 | 34.7174 | 64.6663 | 110.9003 | 122.837 | 174.2829 | 0 | 0 | 0 | [11 empty] | 31.8896 | 12.5701 | 8.4664 | 16.8245 | 28.2613 | 62.2858 | 105.4399 | 239.4195 | 0.00071652 | 0 | 0 | 34.125 | 13.9866 | 10.3681 | 21.7719 | 37.4496 | 84.6821 | 146.2204 | 356.0502 | 0.0012 | 0 | 0
Enhancements - Climate Change Mitigation
G5a.21 | Carbon Capture |  | I / BF | [12 empty] | 0 | 0.018208 | 0.48747 | 1.9129 | 1.9653 | 1.6489 | 1.2586 | 0.42149 | 0 | 0 | 0 | 0 | 0.02026 | 0.59697 | 2.4754 | 2.6042 | 2.2419 | 1.7454 | 0.62681 | 0 | 0 | 0 | [11 empty] | 0 | 0.17113 | 1.4923 | 1.7344 | 3.2608 | 2.0767 | 1.1744 | 2.3442 | 0 | 0 | 0 | 0 | 0.19041 | 1.8275 | 2.2444 | 4.321 | 2.8234 | 1.6285 | 3.4861 | 0 | 0 | 0
G5a.22 | Investment Emissions |  | I / BF | [12 empty] | 0 | 0 | 0 | 0.0094186 | 0.008777 | 0.014402 | 0.016213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.012188 | 0.011631 | 0.01958 | 0.022484 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0.021811 | 0.01627 | 0.010729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.028902 | 0.02212 | 0.014878 | 0 | 0 | 0 | 0
G5a.23 | Operational Emissions |  | I / BF | [12 empty] | 0 | 2.7948 | 4.2374 | 13.7307 | 13.7414 | 12.531 | 14.5934 | 1.074 | 0 | 0 | 0 | 0 | 3.1098 | 5.1892 | 17.7684 | 18.209 | 17.0368 | 20.2377 | 1.5973 | 0 | 0 | 0 | [11 empty] | 4.0272 | 2.7875 | 4.0668 | 10.0074 | 20.8408 | 17.8038 | 6.1216 | 3.2274 | 0 | 0 | 0 | 4.3095 | 3.1017 | 4.9803 | 12.9502 | 27.6166 | 24.2056 | 8.4892 | 4.7996 | 0 | 0 | 0
G5a.24 | Enhancements - Climate Change Mitigation total expenditure | £m | C | [12 empty] | 0 | 2.813 | 4.7249 | 15.653 | 15.7154 | 14.1943 | 15.8683 | 1.4955 | 0 | 0 | 0 | 0 | 3.13 | 5.7862 | 20.256 | 20.8248 | 19.2983 | 22.0055 | 2.2241 | 0 | 0 | 0 | [11 empty] | 4.0272 | 2.9587 | 5.5591 | 11.7418 | 24.1235 | 19.8967 | 7.3067 | 5.5715 | 0 | 0 | 0 | 4.3095 | 3.2921 | 6.8078 | 15.1946 | 31.9665 | 27.0511 | 10.1326 | 8.2857 | 0 | 0 | 0
Enhancements - Circular Economy
G5a.25 | Circular Economy |  | I / BF | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G5a.26 | Enhancements - Circular Economy total expenditure | £m | C | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enhancements - Water Continuity
G5a.27 | Interruption to Supply |  | I / BF | [12 empty] | 0 | 0.0060218 | 0.018876 | 0.4523 | 0.45188 | 0.93819 | 0.89715 | 0 | 0 | 0 | 0 | 0 | 0.0067004 | 0.023116 | 0.58531 | 0.59879 | 1.2755 | 1.2441 | 0 | 0 | 0 | 0 | [11 empty] | 0.036326 | 0.0060217 | 0.018876 | 0 | 1.2241 | 0.91316 | 0.60217 | 0 | 0 | 0 | 0 | 0.038872 | 0.0067003 | 0.023116 | 0 | 1.6221 | 1.2415 | 0.83507 | 0 | 0 | 0 | 0
G5a.28 | Pressure |  | I / BF | [12 empty] | 0 | 0.22358 | 0.69457 | 1.1933 | 0.5236 | 0.12919 | 0.10577 | -0.00079075 | 0 | 0 | 0 | 0 | 0.24878 | 0.85058 | 1.5442 | 0.69383 | 0.17564 | 0.14668 | -0.001176 | 0 | 0 | 0 | [11 empty] | 0.1021 | 0.22919 | 0.69875 | 2.1514 | -0.065202 | -0.12819 | -0.016054 | 0.050199 | 0 | 0 | 0 | 0.10926 | 0.25501 | 0.8557 | 2.7841 | -0.0864 | -0.17429 | -0.022264 | 0.074653 | 0 | 0 | 0
G5a.29 | Resistance to Threat |  | I / BF | [12 empty] | 0 | 0.56563 | 1.2405 | 2.795 | 5.874 | 7.1343 | 9.4309 | 17.7701 | 0 | 0 | 0 | 0 | 0.62938 | 1.5191 | 3.617 | 7.7837 | 9.6996 | 13.0785 | 26.4266 | 0 | 0 | 0 | [11 empty] | 5.2228 | 0.44303 | 0.71071 | 2.6818 | 18.0273 | 14.0971 | 10.8356 | 10.2328 | 0.038142 | 0 | 0 | 5.5889 | 0.49296 | 0.87036 | 3.4704 | 23.8883 | 19.166 | 15.0264 | 15.2177 | 0.063879 | 0 | 0
G5a.30 | Water Availability |  | I / BF | [12 empty] | 0 | 1.3866 | 1.5282 | -0.58003 | 2.9877 | 2.6299 | 2.2143 | 3.1295 | 0 | 0 | 0 | 0 | 1.5428 | 1.8715 | -0.75059 | 3.959 | 3.5755 | 3.0707 | 4.654 | 0 | 0 | 0 | [11 empty] | 6.945 | 1.5326 | 1.6244 | 1.391 | 1.6542 | 2.7445 | 1.79 | 100.1648 | 0.004265 | 0 | 0 | 7.4319 | 1.7053 | 1.9892 | 1.8 | 2.1919 | 3.7313 | 2.4823 | 148.959 | 0.0071429 | 0 | 0
G5a.31 | Water Transfer |  | I / BF | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G5a.32 | Enhancements - Water Continuity total expenditure | £m | C | [12 empty] | 0 | 2.1818 | 3.4822 | 3.8606 | 9.8371 | 10.8316 | 12.6481 | 20.8988 | 0 | 0 | 0 | 0 | 2.4277 | 4.2643 | 4.9958 | 13.0353 | 14.7263 | 17.54 | 31.0794 | 0 | 0 | 0 | [11 empty] | 12.3062 | 2.2109 | 3.0527 | 6.2242 | 20.8404 | 17.6265 | 13.2117 | 110.4478 | 0.042407 | 0 | 0 | 13.1689 | 2.46 | 3.7384 | 8.0545 | 27.616 | 23.9646 | 18.3215 | 164.2513 | 0.071022 | 0 | 0
Wastewater – Managing Quantity of Flows
G5a.33 | Chronic Issues on the Waste Network | Number | I / BF |  | 0 | 191 | 44 | 19 | 54 | 44 | 49 | 0 | 0 | 0 | 0 | 0 | 17.9331 | 16.4191 | 4.8915 | 7.3304 | 17.6833 | 22.4125 | 5.3645 | 0 | 0 | 0 | 0 | 19.954 | 20.1073 | 6.3299 | 9.7136 | 24.0417 | 31.0809 | 7.9778 | 0 | 0 | 0 | 0 | 70 | 42 | 27 | 36 | 40 | 33 | 0 | 0 | 0 | 0 | 48.7782 | 18.2365 | 17.8267 | 14.9219 | 15.516 | 16.2796 | 23.3602 | 80.3682 | 0 | 0 | 0 | 52.1975 | 20.2916 | 21.8311 | 19.3098 | 20.5606 | 22.1334 | 32.3951 | 119.5188 | 0 | 0 | 0
G5a.34 | Long-Term Planning of the Drainage Service |  | I / BF | [12 empty] | 0 | 3.0726 | 6.7414 | 2.4611 | 3.0073 | 2.5884 | 4.3654 | 7.0374 | 0 | 0 | 0 | 0 | 3.4189 | 8.2557 | 3.1848 | 3.9851 | 3.5191 | 6.0538 | 10.4656 | 0 | 0 | 0 | [11 empty] | 10.0469 | 2.6035 | 5.0519 | 6.2094 | 1.0359 | 4.539 | 2.0962 | 29.8954 | 0 | 0 | 0 | 10.7512 | 2.8969 | 6.1867 | 8.0353 | 1.3727 | 6.1712 | 2.9069 | 44.4586 | 0 | 0 | 0
G5a.35 | Enhancements - Managing Quantity of Flows total expenditure | £m | C | [12 empty] | 0 | 21.0058 | 23.1605 | 7.3526 | 10.3377 | 20.2717 | 26.7779 | 12.4019 | 0 | 0 | 0 | 0 | 23.3729 | 28.363 | 9.5148 | 13.6987 | 27.5608 | 37.1346 | 18.4433 | 0 | 0 | 0 | [11 empty] | 58.8251 | 20.84 | 22.8787 | 21.1312 | 16.552 | 20.8187 | 25.4563 | 110.2636 | 0 | 0 | 0 | 62.9488 | 23.1885 | 28.0178 | 27.3452 | 21.9333 | 28.3045 | 35.3019 | 163.9774 | 0 | 0 | 0
Enhancements - Other
G5a.36 | Business Intelligence | Number | I / BF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32372 | 0.37965 | 0.61747 | 0.76046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41891 | 0.50308 | 0.83949 | 1.0546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1 | 0 | 0 | 0 | 0 | 0 | 0.1004 | 0.39681 | 0.063474 | 1.1257 | 0.71808 | 0.47532 | 0.0026976 | 0 | 0 | 0 | 0 | 0.11171 | 0.48595 | 0.082139 | 1.4917 | 0.97628 | 0.65916 | 0.0040116 | 0 | 0 | 0
G5a.37 | Customer & Community Experience |  | I / BF | [12 empty] | 0 | 0.66022 | 0.63013 | 1.0846 | 0.28452 | 0.40626 | 0.34273 | 0 | 0 | 0 | 0 | 0 | 0.73462 | 0.77167 | 1.4036 | 0.37702 | 0.55234 | 0.47528 | 0 | 0 | 0 | 0 | [11 empty] | 0.24946 | 1.2355 | 0.8674 | 2.4362 | 2.4917 | 1.3573 | 1.1004 | 0.0001681 | 0 | 0 | 0 | 0.26695 | 1.3748 | 1.0622 | 3.1526 | 3.3019 | 1.8453 | 1.526 | 0.00024999 | 0 | 0 | 0
G5a.38 | Enhance Scotland's Environment |  | I / BF | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G5a.39 | Innovation (inc. Chair) | Number | I / BF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.097785 | 0.17874 | 0.32457 | 0.42185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12654 | 0.23685 | 0.44127 | 0.585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1.8737 | 2.3098 | 2.3636 | 3.3473 | 1.7304 | 1.1583 | 0.0050311 | 0 | 0 | 0 | 0 | 2.0848 | 2.8286 | 3.0586 | 4.4355 | 2.3526 | 1.6063 | 0.007482 | 0 | 0 | 0
G5a.40 | Other areas |  | I / BF | [12 empty] | 0 | 4.7824 | 1.8063 | 13.5585 | 12.471 | 48.3101 | 58.5809 | 5.4752 | 0 | 0 | 0 | 0 | 5.3213 | 2.2121 | 17.5456 | 16.5256 | 65.6811 | 81.238 | 8.1424 | 0 | 0 | 0 | [11 empty] | 20.852 | 27.569 | 45.1045 | 29.8216 | 49.4584 | 45.955 | 25.9426 | 31.5799 | 0 | 0 | 0 | 22.3137 | 30.6758 | 55.2362 | 38.591 | 65.5383 | 62.4792 | 35.9763 | 46.9638 | 0 | 0 | 0
G5a.41 | PFI returns |  | I / BF | [12 empty] | 0 | 0.32314 | 16.5085 | 6.2857 | 3.8156 | 7.9003 | 19.5005 | 9.6855 | 0 | 0 | 0 | 0 | 0.35955 | 20.2167 | 8.1341 | 5.0561 | 10.741 | 27.0426 | 14.4037 | 0 | 0 | 0 | [11 empty] | 0.22087 | 0.31558 | 16.5042 | 8.7643 | 7.7577 | 5.984 | 12.0073 | 30.0867 | 10.4774 | 0 | 0 | 0.23636 | 0.35114 | 20.2115 | 11.3415 | 10.2798 | 8.1357 | 16.6513 | 44.7431 | 17.5471 | 0 | 0
G5a.42 | Service Relocation |  | I / BF | [12 empty] | 0 | 3.8487 | 3.0336 | 5.0678 | 7.6966 | 12.6044 | 14.5518 | 0.61256 | 0 | 0 | 0 | 0 | 4.2824 | 3.715 | 6.558 | 10.1989 | 17.1366 | 20.1799 | 0.91097 | 0 | 0 | 0 | [11 empty] | 38.7644 | 3.8487 | 3.0335 | 3.2545 | 17.4412 | 11.4676 | 7.7568 | 0.93213 | 0 | 0 | 0 | 41.4818 | 4.2824 | 3.7149 | 4.2115 | 23.1116 | 15.591 | 10.7568 | 1.3862 | 0 | 0 | 0
G5a.43 | Enhancements - Other total expenditure | £m | C | [12 empty] | 0 | 9.6145 | 21.9785 | 26.4181 | 24.826 | 70.163 | 94.1583 | 15.7733 | 0 | 0 | 0 | 0 | 10.6979 | 26.9154 | 34.1867 | 32.8975 | 95.3917 | 130.5754 | 23.4571 | 0 | 0 | 0 | [11 empty] | 60.0867 | 34.9428 | 68.2163 | 46.7036 | 81.6219 | 67.2124 | 48.4407 | 62.6067 | 10.4774 | 0 | 0 | 64.2988 | 38.8805 | 83.5394 | 60.4373 | 108.1589 | 91.3802 | 67.1758 | 93.1048 | 17.5471 | 0 | 0
Totals
G5a.44 | Total growth expenditure | £m | C | [12 empty] | 0 | 44.3067 | 56.4885 | 24.6033 | 59.3355 | 57.1251 | 30.8966 | 72.9433 | 0 | 0 | 0 | 0 | 49.2996 | 69.1773 | 31.8382 | 78.6266 | 77.6658 | 42.8463 | 108.4768 | 0 | 0 | 0 | [11 empty] | 128.8765 | 43.3029 | 54.2892 | 52.419 | 38.9218 | 63.8607 | 52.3172 | 169.8595 | 0.10316 | 0 | 0 | 137.9107 | 48.1826 | 66.484 | 67.8335 | 51.5761 | 86.8233 | 72.5517 | 252.6048 | 0.17277 | 0 | 0
G5a.45 | Total enhancement expenditure | £m | C | [12 empty] | 0 | 106.8939 | 104.2028 | 105.8094 | 146.8164 | 239.5963 | 310.8198 | 337.1146 | 0 | 0 | 0 | 0 | 118.9397 | 127.6095 | 136.9239 | 194.5494 | 325.7487 | 431.0339 | 501.3364 | 0 | 0 | 0 | [11 empty] | 239.4181 | 132.5946 | 150.6803 | 147.9584 | 205.702 | 225.3964 | 294.612 | 970.1277 | 10.9828 | 0 | 0 | 256.2012 | 147.5367 | 184.527 | 191.4674 | 272.5798 | 306.4429 | 408.5576 | 1442.7152 | 18.3936 | 0 | 0
| Caclulated check on totals | [14 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | [22 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
Prepared by: ……………………………………………...….. |  | Date: 07/10/2024
Checked by: ……………………………………………...….. |  | Date: 07/10/2024
Authorised by: …...........……………………...……............ |  | Date: 07/10/2024

## G5b - Outputs
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2024
SECTION G: INVESTMENT MONITORING
Table G5b: Summary - Outputs | [6 empty] | Based on IPS23.2 in this AR24 and subsequent returns | [36 empty] | Forecast based on IPS24.1 in AR24 | [10 empty] | Forecast based on IPS24.1 in AR24 | [10 empty] | Forecast based on IPS24.1 in AR24
[6 empty] | Block A: Driver | Block B: Baseline outputs | [10 empty] | Block C: Baseline expenditure in the year (2017-18 price base) | [10 empty] | Block D: Baseline expenditure in the year (outturn prices) | [10 empty] | Block E: Actual and forecast outputs | [10 empty] | Block F: Actual and forecast expenditure in the year (2017-18 price base) | [10 empty] | Block G: Actual and forecast expenditure in the year (outturn prices)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67
Line Ref. | Description of output category | Description of output | Output code | Units | Field Type | Driver | [33 empty] | Actual | Actual Year | Actual Year | Report Year | Forecast Year | Forecast Year | Forecast Year | Forecast Year | Forecast Year | Forecast Year | Forecast Year | Actual | Actual Year | Actual Year | Report Year | Forecast Year | Forecast Year | Forecast Year | Forecast Years | Forecast Years | Forecast Years | Forecast Years | Actual | Actual Year | Actual Year | Report Year | Forecast Year | Forecast Year | Forecast Year | Forecast Years | Forecast Years | Forecast Years | Forecast Years
[7 empty] | Pre 2021-22 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-33 | 2033-39 | 2039-45 | 2045-51 | Pre 2021-22 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-33 | 2033-39 | 2039-45 | 2045-51 | Pre 2021-22 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-33 | 2033-39 | 2039-45 | 2045-51 | Pre 2021-22 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-33 | 2033-39 | 2039-45 | 2045-51 | Pre 2021-22 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-33 | 2033-39 | 2039-45 | 2045-51 | Pre 2021-22 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-33 | 2033-39 | 2039-45 | 2045-51
[18 empty] | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | nr | nr | nr | nr | nr | nr | nr | nr | nr | nr | nr | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | bar: Block B: Baseline outputs 2 to Block B: Baseline outputs 12
Growth
G5b.01 | Increase in strategic capacity at water Part 4 assets | Number of WTW with increased capacity | O_WR8_G1 | Number | I / BF | Bonnycraig WTW capacity increase (linked to WQ core programme); Torra WTW capacity increase (linked to WQ Programme and Islay Strategy); Aviemore WTW capacity increase; Inverness & Nairn Growth & Resilience - Interim Controls; Increase the availability of water to meet strategic growth requirements - Water. | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0.68555 | 0.29825 | 1.9055 | 1.0975 | 5.0046 | 4.9292 | 0.88015 | 0 | 0 | 0 | 0 | 0.76281 | 0.36524 | 2.4658 | 1.4543 | 6.8042 | 6.8356 | 1.3089 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | 10.1707 | 0.8651 | 0.5073 | 0.99593 | 7.3568 | 7.2592 | 4.2361 | 0.016501 | 0 | 0 | 0 | 10.8837 | 0.96259 | 0.62125 | 1.2888 | 9.7487 | 9.8694 | 5.8744 | 0.024539 | 0 | 0 | 0
G5b.02 | Increase in strategic capacity at wastewater Part 4 assets | Number of WWTW sites requiring RRR activities to support Part 4 Growth | O_ED1_M | Number | I / BF | When development occurs in a catchment, it may be necessary to accelerate to refurbishment or replacement cycles support growth requirements | 0 | 1 | 1 | 1 | 1 | 0 | 2 | [5 empty] | 0.45683 | 0.5948 | 2.1026 | 4.6828 | 6.6075 | 8.4963 | 3.6045 | 0 | 0 | 0 | 0 | 0.50831 | 0.72841 | 2.721 | 6.2053 | 8.9834 | 11.7824 | 5.3604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G5b.03 | Increase in strategic capacity at wastewater Part 4 assets | Increase in Part 4 capacity to meet strategic growth requirements | O_ED2_G | PE | I / BF | North Berwick, and Bertha Park (Perth), East Stirlingshire | 0 | 0 | 0 | 0 | 0 | 25476 | 0 | [5 empty] | 1.597 | 2.4332 | 2.9345 | 19.4854 | 17.6256 | 10.9144 | 32.1931 | 0 | 0 | 0 | 0 | 1.7769 | 2.9797 | 3.7974 | 25.8205 | 23.9633 | 15.1357 | 47.8756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8760 | 30000 |  |  |  |  | 1.7487 | 1.1389 | 1.8849 | 9.31 | 8.6696 | 19.2887 | 14.6973 | 53.1376 | 0.10238 | 0 | 0 | 1.8713 | 1.2673 | 2.3083 | 12.0477 | 11.4882 | 26.2243 | 20.3816 | 79.023 | 0.17147 | 0 | 0
G5b.04 | Increase in strategic capacity at wastewater Part 4 assets | Increase in Part 4 capacity to meet local growth requirements | O_ED3_G | PE | I / BF | Confirmed development in catchments which require investment | 0 | 3699 | 18088.11 | 112078.17 | 23104 | 9017 | 10535 | [5 empty] | 30.7244 | 36.2312 | 1.2544 | 7.46 | -2.4336e-11 | 1.2292e-11 | 34.0468 | 0 | 0 | 0 | 0 | 34.1867 | 44.3696 | 1.6233 | 9.8854 | -3.3087e-11 | 1.7047e-11 | 50.6323 | 0 | 0 | 0 | 0 | 1391 | 15673 | 4171 | 18000 | 3938 | 2912 |  |  |  |  | 82.579 | 30.3935 | 35.6739 | 24.2741 | 3.9849 | 14.6013 | 14.7408 | 69.6675 | 0.00042991 | 0 | 0 | 88.3677 | 33.8185 | 43.6873 | 31.4122 | 5.2804 | 19.8515 | 20.442 | 103.6053 | 0.00072 | 0 | 0
G5b.05 | Increase in strategic capacity at water Part 3 assets | Additional Capacity enabled from strategic water network reinforcement | O_WR10_G1 | PE | I / BF | Reinvestment of the receipts from the Infrastructure Charge to create or restore capacity in the general network - Water | 0 | 10759 | 3256 | 16768 | 42132 | 32000 | 10001 | [5 empty] | 9.9923 | 14.4179 | 8.9031 | 8.1459 | 3.323 | 2.477e-11 | 0.67371 | 0 | 0 | 0 | 0 | 11.1183 | 17.6566 | 11.5212 | 10.7944 | 4.5179 | 3.4351e-11 | 1.0019 | 0 | 0 | 0 | 0 | 11665 | 3256 | 11026 | 21072 | 2174 | 35133 |  |  |  |  | 23.5016 | 9.1237 | 13.1229 | 10.1813 | 6.4748 | 3.1901 | 2.6888 | 26.6884 | 0.00035045 | 0 | 0 | 25.1491 | 10.1519 | 16.0706 | 13.1753 | 8.5799 | 4.3372 | 3.7288 | 39.6894 | 0.00058692 | 0 | 0
G5b.06 | Increase in strategic capacity at wastewater Part 3 assets | Additional Capacity enabled from strategic wastewater network reinforcement | O_ED4_G | PE | I / BF | Reinvestment of the receipts from the Infrastructure Charge to create or restore capacity in the general network - Waste | 0 | 906 | 0 | 107 | 36289 | 59440 | 31810 | [5 empty] | 0.85069 | 2.5132 | 7.5031 | 18.4639 | 24.5643 | 6.5567 | 1.545 | 0 | 0 | 0 | 0 | 0.94655 | 3.0777 | 9.7095 | 24.4668 | 33.397 | 9.0926 | 2.2977 | 0 | 0 | 0 | 0 | 1259 | 0 | 21101 | 10708 | 11243 | 0 |  |  |  |  | 10.8765 | 1.7816 | 3.1002 | 7.6577 | 12.4357 | 19.5215 | 15.9543 | 20.3495 | 0 | 0 | 0 | 11.6389 | 1.9824 | 3.7966 | 9.9095 | 16.4788 | 26.5409 | 22.1249 | 30.2626 | 0 | 0 | 0
G5b.07 | Increase in strategic capacity at foul sewerage Part 3 assets |  |  |  | I / BF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G5b.08 | Increase in strategic capacity at surface water Part 3 assets |  |  |  | I / BF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enhancements - Water Quality
G5b.09 | Chemicals & Compounds |  |  |  | I / BF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G5b.10 | Discolouration | Length of water main replaced or refurbished | O_DC2_E | Metres | I / BF | Maintenance activities on water mains where cleaning does not resolve the need. | 0 | 0 | 7432 | 4051 | 2747 | 1400 | 0 | [5 empty] | 3.3724 | 3.7587 | 0.40183 | 0.43779 | -0.98542 | -1.3212 | 0 | 0 | 0 | 0 | 0 | 3.7524 | 4.603 | 0.51999 | 0.58013 | -1.3397 | -1.8322 | 0 | 0 | 0 | 0 | 0 | 1513 | 9228 | 22972.12 | 516 | 6333 | 5235 |  |  |  |  | 0.84222 | 3.44 | 3.6866 | 2.2658 | 2.4537 | 1.3124 | 0.40093 | 2.0421 | 0 | 0 | 0 | 0.90126 | 3.8276 | 4.5147 | 2.9321 | 3.2515 | 1.7843 | 0.55599 | 3.0369 | 0 | 0 | 0
G5b.11 | Lead | Number of WTW sites with phosphate equipment dosing optimised | O_LD1_E1 | Number | I / BF | Increased phosphate dose - move to 1mg/l to 1.5 mg/l | 0 | 0 | 1 | 0 | 0 | 0 | 0 | [5 empty] | 0.066992 | 0.58808 | 0.49334 | 0.48618 | 0.48289 | 0.4748 | 0.88307 | 0 | 0 | 0 | 0 | 0.074541 | 0.72018 | 0.63841 | 0.64424 | 0.65653 | 0.65844 | 1.3133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0.066991 | 0.58807 | -0.61412 | -0.018308 | -0.015839 | -0.0067952 | 0 | 0 | 0 | 0 | 0 | 0.07454 | 0.72017 | -0.79471 | -0.024261 | -0.021535 | -0.0094234 | 0 | 0 | 0 | 0
G5b.12 | Lead | Number of interventions developed | O_LD1_E2 | Number | I / BF | Investigate and develop options for Fife Boreholes. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0.0051749 | 0.0063696 | 0.0075843 | 0.007689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0066966 | 0.0084405 | 0.010311 | 0.010663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0.011984 | 0.0089392 | 0.0058948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01588 | 0.012154 | 0.0081748 | 0 | 0 | 0 | 0
G5b.13 | Lead | Number of sites where new phosphate monitoring equipment has been provided | O_LD1_E3 | Number | I / BF | Phosphate Monitors at WTWs | 0 | 21 | 0 | 12 | 32 | 2 | 0 | [5 empty] | 0.043546 | 0.43641 | 0.78073 | 0.23931 | -3.9451e-11 | -6.5694e-12 | 0.0005147 | 0 | 0 | 0 | 0 | 0.048453 | 0.53444 | 1.0103 | 0.31712 | -5.3636e-11 | -9.1102e-12 | 0.00076543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G5b.14 | Lead | Number of lead communication pipes replaced | O_LD2_E | Number | I / BF | 3,700 pipes assumed, when sampled will exceed 10 microgram/l.; Option to replace 800 pipes assumed will exceed 5 microgram/l.; 3,100 pipes assumed when customer request or opportunistically encountered.; IR18 Completion | 0 | 0 | 1580 | 0 | 0 | 0 | 363 | [5 empty] | 2.2545 | 4.7305 | 2.0527 | 1.9771 | 3.9554 | 7.5513 | 3.1201 | 0 | 0 | 0 | 0 | 2.5085 | 5.7931 | 2.6564 | 2.6199 | 5.3777 | 10.4719 | 4.64 | 0 | 0 | 0 | 0 | 8422 | 0 | 0 | 1 | 927 | 223 |  |  |  |  | 0.36428 | 1.8509 | 2.1845 | 3.3093 | 6.3197 | 4.9239 | 3.9331 | 0.005245 | 0 | 0 | 0 | 0.38981 | 2.0594 | 2.6752 | 4.2825 | 8.3744 | 6.6944 | 5.4542 | 0.0078 | 0 | 0 | 0
G5b.15 | Lead | Number of properties with lead sampling and risk assessment completed | O_LD4_E | Number | I / BF | Sample around 20,000 additional properties and develop analytical model to assess risk in all properties | 0 | 0 | 0 | 1 | 1 | 0 | 0 | [5 empty] | 0.15004 | 0.20191 | 0.94852 | 0.9847 | 0.93625 | 1.2191 | 0.00027271 | 0 | 0 | 0 | 0 | 0.16694 | 0.24727 | 1.2274 | 1.3048 | 1.2729 | 1.6906 | 0.00040556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4700 | 0 | 0 |  |  |  |  | 0.46199 | 0.15595 | 0.57631 | 0.45628 | 0.94504 | 1.3634 | 0.34344 | 0.059545 | 0 | 0 | 0 | 0.49437 | 0.17352 | 0.70576 | 0.59045 | 1.2523 | 1.8537 | 0.47628 | 0.088552 | 0 | 0 | 0
G5b.16 | Lead | Number of Water Safety Zones covered by customer awareness campaigns | O_LD5_E | Number | I / BF | Develop the first 2 years of customer awareness campaign | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0.053154 | 0.26913 | 0.23892 | -3.1431e-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.065094 | 0.34827 | 0.3166 | -4.2733e-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0.053154 | 0.029883 | 0.58535 | 0.10623 | -0.013424 | 0 | 0 | 0 | 0 | 0 | 0 | 0.065093 | 0.03867 | 0.77567 | 0.14443 | -0.018616 | 0 | 0 | 0 | 0
G5b.18 | Microbiology | Number of WTW sites with auto-shutdown risk control interventions | O_OM4_E | Number | I / BF | Develop solutions at 21 sites (auto shutdown / run to waste) | 0 | 3 | 1 | 0 | 3 | 3 | 7 | [5 empty] | 0.11718 | 0.96363 | 0.40307 | 14.9311 | 11.3578 | 5.891 | 4.2825 | 0 | 0 | 0 | 0 | 0.13039 | 1.1801 | 0.5216 | 19.7855 | 15.4417 | 8.1695 | 6.3686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | 0.081546 | 0.12715 | 1.0365 | 0.60928 | 0.0089411 | 0.060745 | 3.7211 | 25.1088 | 0.018322 | 0 | 0 | 0.087263 | 0.14148 | 1.2693 | 0.78844 | 0.011848 | 0.082587 | 5.1603 | 37.3403 | 0.030685 | 0 | 0
G5b.19 | Microbiology | Number of WTW sites made compliant with standards | O_OM3_E | Number | I / BF | Develop solutions at 4 sites (Filter improvements); Develop solutions at 16 sites (Disinfection imporvements) | 0 | 0 | 0 | 1 | 3 | 1 | 2 | [5 empty] | 17.9752 | 6.1447 | 2.2756 | 1.0486 | 0.055934 | 0.29455 | 4.8656 | 0 | 0 | 0 | 0 | 20.0008 | 7.5249 | 2.9447 | 1.3895 | 0.076046 | 0.40847 | 7.2358 | 0 | 0 | 0 | 0 | 82 | 6 | 0 | 29 | 23 | 0 |  |  |  |  | 28.2896 | 18.1057 | 6.2737 | 4.1771 | 2.9583 | 1.0826 | 2.0966 | 9.9301 | 0.00034172 | 0 | 0 | 30.2727 | 20.146 | 7.6829 | 5.4055 | 3.9201 | 1.4719 | 2.9074 | 14.7674 | 0.0005723 | 0 | 0
G5b.20 | Microbiology | Numberof treated water storage operability (by-pass) interventions | O_OM6_E | Number | I / BF | Assess 50-100 tanks to determine if new bypass arrangements are required to enable future inspection/repair work. | 0 | 0 | 6 | 1 | 3 | 3 | 57 | [5 empty] | 3.3619 | 1.8145 | 1.1839 | 3.9367 | 1.7685 | 0.96788 | 2.3739 | 0 | 0 | 0 | 0 | 3.7408 | 2.222 | 1.5321 | 5.2165 | 2.4044 | 1.3422 | 3.5303 | 0 | 0 | 0 | 0 | 17 | 16 | 17 | 69 | 8 | 68 |  |  |  |  | 2.1356 | 3.3396 | 1.8144 | 2.4521 | 1.0994 | 1.3145 | 2.9863 | 2.8964 | 0 | 0 | 0 | 2.2853 | 3.7159 | 2.222 | 3.1732 | 1.4568 | 1.7872 | 4.1413 | 4.3073 | 0 | 0 | 0
G5b.21 | Organics & DBPs | Number of sites with enhanced metals removal | O_DC1_E | Number | I / BF | Systems Approach (Core WTW Programme) | 0 | 0 | 1 | 0 | 0 | 1 | 0 | [5 empty] | 0.24664 | 0.15024 | -0.038521 | -0.044904 | -0.045412 | -0.1341 | 0.00037858 | 0 | 0 | 0 | 0 | 0.27444 | 0.18399 | -0.049849 | -0.059503 | -0.061741 | -0.18596 | 0.000563 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 0.058995 | 0.24664 | 0.15024 | 0.034951 | 0.12406 | -0.019299 | -0.0026506 | 0.00052062 | 0 | 0 | 0 | 0.063131 | 0.27443 | 0.18399 | 0.045228 | 0.1644 | -0.026239 | -0.0036757 | 0.00077424 | 0 | 0 | 0
G5b.22 | Organics & DBPs | Number of WTW sites made compliant with standards | O_OM3_E | Number | I / BF | Improve Water Treatment Works (WTWs) with persistent non-trivial fails (Group 1) (committed / enforced).; Improve Water Treatment Works (WTWs) with persistent non-trivial fails (Group 2); Improve Water Treatment Works (WTWs) with persistent non-trivial fails (Group 3); Chlorine Contact Tank Management | 0 | 0 | 5 | 7 | 150 | 7 | 8 | [5 empty] | 20.7193 | 17.4882 | 13.0082 | 10.743 | 22.0786 | 51.5794 | 152.2428 | 0 | 0 | 0 | 0 | 23.0541 | 21.4165 | 16.8334 | 14.2358 | 30.0175 | 71.5285 | 226.4063 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 |  |  |  |  | 15.1669 | 20.8239 | 17.7641 | 28.4734 | 16.4782 | 26.031 | 79.8436 | 401.3643 | 0.4437 | 0 | 0 | 16.2301 | 23.1706 | 21.7544 | 36.8463 | 21.8356 | 35.391 | 110.7243 | 596.8847 | 0.74309 | 0 | 0
G5b.23 | Organics & DBPs | Number of WTW sites with improved organics removal | O_OM5_E | Number | I / BF | Develop solutions for 13 sites in addition to the Core Programme (Organics trent to fail) | 0 | 1 | 0 | 1 | 0 | 0 | 0 | [5 empty] | 6.9393 | 3.45 | 0.57557 | -0.75231 | -0.80217 | -0.80477 | 0 | 0 | 0 | 0 | 0 | 7.7213 | 4.225 | 0.74482 | -0.99691 | -1.0906 | -1.116 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 |  |  |  |  | 14.4851 | 6.9183 | 3.4305 | 1.6364 | 5.3811 | 3.5944 | 2.3446 | 0 | 0 | 0 | 0 | 15.5005 | 7.6979 | 4.2011 | 2.1176 | 7.1306 | 4.8868 | 3.2514 | 0 | 0 | 0 | 0
G5b.24 | Organics & DBPs | Number of single supply standard products developed | O_OM7_E | Number | I / BF | Develop standard product through IR18 study for 32-59 non-compliant single supplies.; Construct and pilot standard product. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | [5 empty] | 0.28305 | 0.16276 | 0.6685 | 0.19172 | 0.021383 | 0.014807 | 0.0016262 | 0 | 0 | 0 | 0 | 0.31495 | 0.19932 | 0.86509 | 0.25406 | 0.029071 | 0.020534 | 0.0024184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | 0.25055 | 0.28305 | 0.16276 | 0.030139 | 0.0087854 | 0.0076883 | -0.006654 | 0.0012815 | 0 | 0 | 0 | 0.26812 | 0.31495 | 0.19932 | 0.039001 | 0.011642 | 0.010453 | -0.0092275 | 0.0019057 | 0 | 0 | 0
G5b.25 | Organics & DBPs | Number of raw water supplies with improved water quality | O_OM9_E | Number | I / BF | Raw Water Supplies � Improve Water Quality | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0.044685 | 0.033333 | 0.021981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.059213 | 0.045319 | 0.030482 | 0 | 0 | 0 | 0
G5b.26 | Organics & DBPs | Number of IR18 project completed | O_IR18 | Number | I / BF | IR18 Completion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 3.3396 | 2.2488 | 2.669 | 2.8756 | 3.7344 | 7.0485 | 1.581 | 0 | 0 | 0 | 0 | 3.716 | 2.754 | 3.4539 | 3.8105 | 5.0772 | 9.7746 | 2.3511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 10.1464 | 3.7139 | 4.7864 | 2.4725 | -2.098 | -2.2478 | -0.91118 | 0.41035 | 0 | 0 | 0 | 10.8576 | 4.1325 | 5.8615 | 3.1996 | -2.7802 | -3.056 | -1.2636 | 0.61025 | 0 | 0 | 0
G5b.27 | Taste & Odour |  |  |  | I / BF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G5b.28 | Enhancements - Water Quality total expenditure |  |  | £m | C | [12 empty] | 0 | 58.8696 | 42.1915 | 25.6968 | 37.2998 | 42.5657 | 72.789 | 169.3517 | 0 | 0 | 0 | 0 | 65.5036 | 51.6688 | 33.2532 | 49.4267 | 57.8712 | 100.9412 | 251.8495 | 0 | 0 | 0 | [11 empty] | 72.2832 | 59.0721 | 42.5072 | 45.3331 | 34.303 | 37.5563 | 94.7568 | 441.8185 | 0.46236 | 0 | 0 | 77.3503 | 65.729 | 52.0554 | 58.6639 | 45.4556 | 51.0605 | 131.4053 | 657.0458 | 0.77434 | 0 | 0
Enhancements - Water Environment
G5b.29 | Network Discharges | Number of catchments with intelligent network technology | O_NI1_E1 | Number | I / BF | Increase network intelligence - Roll out intelligent network technology in [5] priority catchments. Help move from reactive to proactive approach | 0 | 0 | 0 | 1 | 12 | 0 | 0 | [5 empty] | 0.76102 | 1.2853 | 3.7634 | 4.0268 | 3.2065 | 5.5294 | 0 | 0 | 0 | 0 | 0 | 0.84678 | 1.5741 | 4.87 | 5.336 | 4.3594 | 7.668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  |  |  |  | 1.1599 | 0.76101 | 0.95696 | 0.5429 | 7.532 | 5.3716 | 3.4077 | 0 | 0 | 0 | 0 | 1.2412 | 0.84676 | 1.1719 | 0.70255 | 9.9808 | 7.3031 | 4.7257 | 0 | 0 | 0 | 0
G5b.30 | Network Discharges | Number of Event Duration Monitors (EDM) deployed | O_NI1_E2 | Number | I / BF | Deploy Event Duration Monitors (EDM) at locations within 5km of designated waters | 0 | 0 | 1 | 31 | 0 | 0 | 0 | [5 empty] | 0.49808 | 0.24024 | 0.3141 | 0.36965 | 0.93327 | 1.2397 | 0.25366 | 0 | 0 | 0 | 0 | 0.55421 | 0.2942 | 0.40647 | 0.48983 | 1.2688 | 1.7191 | 0.37722 | 0 | 0 | 0 | 0 | 0 | 20 | 30 | 0 | 1030 | 0 |  |  |  |  | 0.18568 | 0.5134 | 0.24889 | 4.5317 | -0.36398 | -1.1329 | -0.20216 | 0.86784 | 0 | 0 | 0 | 0.1987 | 0.57125 | 0.30479 | 5.8643 | -0.48232 | -1.5403 | -0.28034 | 1.2906 | 0 | 0 | 0
G5b.31 | Network Discharges | Number of unsatisfactory intermittent discharges (UID) improved or removed for aesthetics | O_SN2_E1 | Number | I / BF | Reduce the risk of environmental pollution from CSOs - Develop solutions to priority UIDs (catchments to be agreed with SEPA) for aesthetics | 0 | 0 | 3 | 4 | 1 | 9 | 15 | [5 empty] | 3.6144 | 1.458 | 3.5075 | 7.6912 | 15.5643 | 31.0266 | 6.5989 | 0 | 0 | 0 | 0 | 4.0217 | 1.7855 | 4.5389 | 10.1918 | 21.1608 | 43.0265 | 9.8135 | 0 | 0 | 0 | 0 | 4 | 1 | 3 | 4 | 7 | 22 |  |  |  |  | 10.9618 | 3.556 | 1.3295 | 3.6779 | 4.0455 | 13.6182 | 43.7338 | 23.8554 | 0 | 0 | 0 | 11.7302 | 3.9568 | 1.6282 | 4.7594 | 5.3608 | 18.515 | 60.6485 | 35.4763 | 0 | 0 | 0
G5b.32 | Network Discharges | Number of unsatisfactory intermittent discharges (UID) improved or removed for water quality | O_SN2_E2 | Number | I / BF | Reduce the risk of environmental pollution from CSOs - Develop solutions to priority UIDs (catchments to be agreed with SEPA) for water quality | 0 | 0 | 0 | 0 | 2 | 0 | 0 | [5 empty] | 0 | 0.13463 | 3.8792 | 7.6526 | 22.5188 | 16.4404 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16487 | 5.0199 | 10.1406 | 30.616 | 22.799 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 10 |  |  |  |  | 0.089557 | 0.062541 | 0.27479 | 2.6883 | 1.4398 | 7.7711 | 16.2887 | 8.7917 | 0 | 0 | 0 | 0.095835 | 0.069588 | 0.33651 | 3.4788 | 1.9079 | 10.5654 | 22.5886 | 13.0745 | 0 | 0 | 0
G5b.33 | Network Improvements |  |  |  | I / BF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G5b.34 | Regulatory Abstraction and Impoundment | Number of sites with Water Framework Directive improvements | O_AD6_E | Number | I / BF | River Loy Redundant Weir (Fort William) - removal of redundant weir - barrier to 5.7km of waterbody studied in IR18; Auchengaich Dam, Belmore - provision of compensation arrangements on dam to prevent burn drying out and fish kill; Support compliance with changes to CAR Licence conditions to meet RBMP3 commitments; Reduce impact of water supply infrastructure, abstractions and compensation releases on surface waters | 0 | 0 | 0 | 0 | 0 | 1 | 1 | [5 empty] | 0.71308 | 0.39623 | -0.20349 | 0.15947 | 0.82878 | 0.62624 | 0 | 0 | 0 | 0 | 0 | 0.79344 | 0.48523 | -0.26332 | 0.21131 | 1.1268 | 0.86845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  |  | 0.93191 | 0.71307 | 0.39622 | 0.016834 | 0.26404 | 0.42339 | 0.70671 | 1.0519 | 0 | 0 | 0 | 0.99724 | 0.79343 | 0.48522 | 0.021784 | 0.34989 | 0.57563 | 0.98004 | 1.5643 | 0 | 0 | 0
G5b.35 | Regulatory Abstraction and Impoundment | Number of sites with reservoir drawdown enhancements | O_HS3_E | Number | I / BF | Develop solutions for 11 named sites required by 2022 and delivery of solutions at 8 sites | 0 | 3 | 5 | 1 | 1 | 2 | 2 | [5 empty] | 2.6801 | 0.28871 | 0.85204 | 0.73568 | 1.1843 | 2.3258 | 1.3629 | 0 | 0 | 0 | 0 | 2.9821 | 0.35356 | 1.1026 | 0.97487 | 1.6101 | 3.2253 | 2.0268 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 2 | 0 |  |  |  |  | 7.3402 | 2.672 | 0.28154 | 0.1005 | 1.9758 | 1.5819 | 1.4546 | 1.1618 | 0 | 0 | 0 | 7.8548 | 2.9732 | 0.34478 | 0.13005 | 2.6182 | 2.1508 | 2.0172 | 1.7278 | 0 | 0 | 0
G5b.36 | Resource Recovery | Increase in renewable energy generated | O_LC2_E1 | GWh / Annum | I / BF | Maximise energy generation and maximise value at Kinneil Kerse sludge treatment centre; Develop plans to generate energy and maximise value at Daldowie Sludge Treatment Centre post PFI contract | 0 | 0 | 0 | 1 | 0 | 0 | 0 | [5 empty] | 0.38955 | 0.19035 | 1.5122 | 2.0599 | 4.8616 | 9.7407 | 24.0078 | 0 | 0 | 0 | 0 | 0.43345 | 0.2331 | 1.9568 | 2.7296 | 6.6097 | 13.508 | 35.703 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | 0 | 0.38955 | 0.19035 | 0.25495 | 4.6656 | 11.0145 | -0.76087 | 178.3689 | 0 | 0 | 0 | 0 | 0.43344 | 0.2331 | 0.32992 | 6.1824 | 14.975 | -1.0551 | 265.2594 | 0 | 0 | 0
G5b.37 | Treatment Discharges | Number of WWTW continuous discharges improved or removed | O_WW2_E | Number | I / BF | Phosphorus, BOD and ammonia impact to be reduced at WwTWs where impact has been confirmed. These form part of draft RBMP3 objectives; Improve Bathing Water at Ayr South | 0 | 1 | 0 | 0 | 7 | 0 | 0 | [5 empty] | 1.4771 | 0.61662 | 11.619 | 23.4056 | 29.8881 | 20.4581 | 84.9537 | 0 | 0 | 0 | 0 | 1.6436 | 0.75513 | 15.0358 | 31.0153 | 40.6351 | 28.3706 | 126.338 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 7 | 2 | 6 |  |  |  |  | 6.478 | 1.6314 | 0.7327 | 1.0441 | 2.8158 | 19.0186 | 37.1212 | 24.7612 | 0.00071652 | 0 | 0 | 6.9321 | 1.8152 | 0.89729 | 1.3512 | 3.7313 | 25.8571 | 51.4784 | 36.8234 | 0.0012 | 0 | 0
G5b.38 | Treatment Improvements | Number of WWTW sites with Environmental Pollution risk reduced | O_BR2_E | Number | I / BF | Cupar WwTW - Bank stability monitoring to monitor environmental pollution risk; Cupar WwTW - Remove environmental risk associated with legacy sludge storage areas; Reduce risk of malodour at Seafield WwTW | 0 | 0 | 1 | 0 | 0 | 0 | 1 | [5 empty] | 0.69061 | 1.2514 | 0.85082 | 2.4642 | 2.1944 | 0.67909 | 0.01069 | 0 | 0 | 0 | 0 | 0.76844 | 1.5325 | 1.101 | 3.2653 | 2.9834 | 0.94174 | 0.015898 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 |  |  |  |  | 0.12511 | 0.69061 | 1.2514 | 1.2475 | 3.3156 | 3.8625 | 3.6627 | 0.54311 | 0 | 0 | 0 | 0.13388 | 0.76843 | 1.5324 | 1.6143 | 4.3936 | 5.2513 | 5.0794 | 0.80768 | 0 | 0 | 0
G5b.39 | Treatment Improvements | Number of studies complete | O_WW3_E | Number | I / BF | Study to understand the impact of waste water discharges on the water environment | 0 | 291 | 2 | 5 | 1 | 0 | 1 | [5 empty] | 1.2614 | 0.58033 | 0.19666 | 0.036479 | 0.035293 | 0.058813 | 0.0056999 | 0 | 0 | 0 | 0 | 1.4035 | 0.71069 | 0.25449 | 0.048339 | 0.047983 | 0.081559 | 0.0084766 | 0 | 0 | 0 | 0 | 293 | 13 | 141 | 19 | 257 | 0.01 |  |  |  |  | 2.4031 | 1.2511 | 0.58032 | 0.26938 | 0.021172 | 0.067941 | -0.020934 | 0.0080692 | 0 | 0 | 0 | 2.5716 | 1.392 | 0.71068 | 0.3486 | 0.028055 | 0.09237 | -0.029031 | 0.012 | 0 | 0 | 0
G5b.40 | Treatment Improvements | Number of studies complete | O_WW4_E | Number | I / BF | Confirm requirements under the Priority Substances Directive - Define the investigation programme and work with SEPA on control of pollution at source; Trial new treatment technology to meet End of Pipe standards - Deliver pilot / demonstrator scale innovative / traditional technology to determine effectiveness of removal rates | 0 | 0 | 0 | 1 | 0 | 0 | 0 | [5 empty] | 0.074615 | 0.31616 | 0.055872 | 0.013502 | 0.014955 | 0.015393 | 0 | 0 | 0 | 0 | 0 | 0.083023 | 0.38718 | 0.072302 | 0.017891 | 0.020332 | 0.021346 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | 0.041857 | 0.074614 | 0.31616 | 0.15021 | 0.029219 | -0.059038 | -0.020676 | 0 | 0 | 0 | 0 | 0.044791 | 0.083022 | 0.38718 | 0.19439 | 0.038719 | -0.080266 | -0.028673 | 0 | 0 | 0 | 0
G5b.41 | Treatment Improvements | Number of studies complete | O_WW5_E | Number | I / BF | Understand level of treatment resilience as a result of climate change and other plausible hazards | 0 | 0 | 0 | 2 | 0 | 0 | 0 | [5 empty] | 0.0025264 | 0.10814 | 0.087189 | 0.012131 | 0.018006 | 0.018505 | 0 | 0 | 0 | 0 | 0 | 0.0028111 | 0.13243 | 0.11283 | 0.016076 | 0.02448 | 0.025662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 |  |  |  |  | 0 | 0.0080641 | 0.10846 | 0.083727 | 0.037787 | 0.0082042 | 0.00024739 | 0 | 0 | 0 | 0 | 0 | 0.0089728 | 0.13282 | 0.10835 | 0.050073 | 0.011154 | 0.00034307 | 0 | 0 | 0 | 0
G5b.42 | Treatment Improvements | Number of IR18 projects completed | O_IR18 | Number | I / BF | IR18 completion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0.24674 | 1.7991 | 1.4238 | 3.109 | -0.12476 | 0.0056865 | 0 | 0 | 0 | 0 | 0 | 0.27454 | 2.2032 | 1.8425 | 4.1198 | -0.16962 | 0.0078858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2.1724 | 0.24674 | 1.7991 | 1.5547 | 2.4659 | 0.72711 | 0.060427 | 0.0096412 | 0 | 0 | 0 | 2.3246 | 0.27454 | 2.2032 | 2.0118 | 3.2676 | 0.98856 | 0.083798 | 0.014338 | 0 | 0 | 0
G5b.43 | Treatment Improvements | Number of WWTW continuous discharges improved or removed | O_WW2_E2 | Number | I / BF | Provision of appropriate equipment and analysis to demonstrate pass forward flow (PFF) spill compliance at WWTW and that flow is maintained during the event duration. These form part of draft RBMP3 objectives | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | -1.0301 | -2.9358 | 0.44653 | 0.41378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.333 | -3.8903 | 0.60709 | 0.57382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0.66183 | 0.01705 | 0.012719 | 0.0083873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85645 | 0.022594 | 0.017292 | 0.011631 | 0 | 0 | 0 | 0
G5b.44 | Enhancements - Water Environment total expenditure |  |  | £m | C | [12 empty] | 0 | 12.4092 | 8.6652 | 26.8282 | 48.8003 | 81.57 | 88.5781 | 117.1934 | 0 | 0 | 0 | 0 | 13.8075 | 10.6117 | 34.7174 | 64.6663 | 110.9003 | 122.837 | 174.2829 | 0 | 0 | 0 | [11 empty] | 31.8896 | 12.5701 | 8.4664 | 16.8245 | 28.2613 | 62.2858 | 105.4399 | 239.4195 | 0.00071652 | 0 | 0 | 34.125 | 13.9866 | 10.3681 | 21.7719 | 37.4496 | 84.6821 | 146.2204 | 356.0502 | 0.0012 | 0 | 0
Enhancements - Climate Change Mitigation
G5b.45 | Carbon Capture | Number of peatland catchment assessments | O_OM8_E | Number | I / BF | Assess peatland restoration options at all 20 catchments. | 0 | 0 | 0 | 3 | 3 | 1 | 2 | [5 empty] | 0.015161 | 0.11014 | 0.6759 | 1.5562 | 0.45651 | 0.34301 | 0 | 0 | 0 | 0 | 0 | 0.01687 | 0.13489 | 0.87465 | 2.0622 | 0.62066 | 0.47567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 8 |  |  |  |  | 0 | 0.012172 | 0.071903 | 0.54383 | 1.2314 | 0.58945 | 0.70817 | 0.3674 | 0 | 0 | 0 | 0 | 0.013544 | 0.088054 | 0.70375 | 1.6317 | 0.80141 | 0.98206 | 0.54637 | 0 | 0 | 0
G5b.46 | Carbon Capture | Number of carbon capture sites established or supported | O_SE8_E | Number | I / BF | Net Zero Emissions - Understanding and Increasing Carbon Capture and Storage in Scottish Water s Landholdings. | 0 | 0 | 0 | 0 | 1 | 0 | 1 | [5 empty] | 0.0030471 | 0.37732 | 1.237 | 0.40905 | 1.1924 | 0.91559 | 0.42149 | 0 | 0 | 0 | 0 | 0.0033904 | 0.46208 | 1.6007 | 0.54205 | 1.6212 | 1.2697 | 0.62681 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 2 | 3 | 0 |  |  |  |  | 0 | 0.15896 | 1.4204 | 1.1905 | 2.0295 | 1.4872 | 0.46618 | 1.9768 | 0 | 0 | 0 | 0 | 0.17687 | 1.7394 | 1.5406 | 2.6893 | 2.022 | 0.64649 | 2.9397 | 0 | 0 | 0
G5b.47 | Investment Emissions | Number of low carbon construction trials | O_SE2_E3 | Number | I / BF | Net Zero Emissions - Trial low carbon construction materials and construction techniques to reduce the emission intensity of investment. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0.0094186 | 0.008777 | 0.014402 | 0.016213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.012188 | 0.011631 | 0.01958 | 0.022484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0.021811 | 0.01627 | 0.010729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.028902 | 0.02212 | 0.014878 | 0 | 0 | 0 | 0
G5b.48 | Operational Emissions | Number of industrial Emissions Directive compliance action plans | O_BR3_E | Number | I / BF | Creation of IED Compliance Action Plans (Industrial Emissions Directive) | 0 | 0 | 9 | 0 | 0 | 0 | 0 | [5 empty] | 0.058655 | 0.095232 | 0.41005 | 0.52961 | 0.86583 | 1.1088 | 0 | 0 | 0 | 0 | 0 | 0.065264 | 0.11662 | 0.53064 | 0.7018 | 1.1772 | 1.5376 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 |  |  |  |  | 0.44071 | 0.058654 | 0.095231 | -1.6228e-07 | 1.3022 | 0.97141 | 0.64059 | 0 | 0 | 0 | 0 | 0.4716 | 0.065264 | 0.11662 | -2.1e-07 | 1.7256 | 1.3207 | 0.88834 | 0 | 0 | 0 | 0
G5b.49 | Operational Emissions | Number of sludge treatment centres achieving compliance with industrial Emissions Directive | O_BR3_E2 | Number | I / BF | Industrial Emissions Directive (IED) compliance for existing Sludge Treatment Centres | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0.26259 | 0.53135 | 0.98723 | 1.287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33981 | 0.7041 | 1.3422 | 1.7848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 1.371 | 1.0227 | 0.67441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8167 | 1.3904 | 0.93525 | 0 | 0 | 0 | 0
G5b.50 | Operational Emissions | Reduction in energy usage through improved energy efficiency | O_LC1_E | GWh / Annum | I / BF | Improve aeration real time control capability to generate benefits in energy efficiency and reduced risk of non-compliance; Develop energy efficient technology strategies; Improve Energy Efficiency at Existing Operational Sites (Water Assets); Net Zero Emissions - Understanding, measuring, managing, and reducing the impact of wastewater process emissions. | 0 | 1 | 0 | 0 | 2 | 0 | 0.41965 | [5 empty] | 2.2598 | 1.897 | 2.8235 | 1.4904 | 1.6906 | 3.0274 | 1.0487 | 0 | 0 | 0 | 0 | 2.5144 | 2.3231 | 3.6537 | 1.975 | 2.2985 | 4.1983 | 1.5596 | 0 | 0 | 0 | 0 | 1 | 0 | 9.69 | 7.98 | 13.15 | 4.5697 |  |  |  |  | 3.0251 | 2.2597 | 1.7937 | 3.4078 | 3.0235 | 1.6491 | 1.0546 | 0.23266 | 0 | 0 | 0 | 3.2371 | 2.5144 | 2.1967 | 4.41 | 4.0065 | 2.2421 | 1.4624 | 0.346 | 0 | 0 | 0
G5b.51 | Operational Emissions | Number of Climate Change Audits | O_SE2_E1 | Number | I / BF | Sustainability auditing / review of Scottish Water assets and estates to support future action and inform future investment planning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0.10749 | 0.10016 | 0.16436 | 0.18503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1391 | 0.13273 | 0.22345 | 0.25659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0.24891 | 0.18568 | 0.12244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32984 | 0.25244 | 0.1698 | 0 | 0 | 0 | 0
G5b.52 | Operational Emissions | Number of sites assessed for renewable energy generation | O_SE2_E2 | Number | I / BF | Host renewable energy generation at SW assets | 0 | 0 | 1 | 10.4 | 12.3 | 17 | 1 | [5 empty] | 0.4305 | 2.1895 | 9.6184 | 10.5489 | 7.9054 | 7.8618 | 0.025346 | 0 | 0 | 0 | 0 | 0.47901 | 2.6813 | 12.4468 | 13.9786 | 10.748 | 10.9024 | 0.037693 | 0 | 0 | 0 | 106 | 0 | 0 | 0 | 1 | 3 | 1 |  |  |  |  | 0 | 0.42324 | 2.1222 | 6.4991 | 13.5585 | 12.9689 | 2.9822 | 2.9947 | 0 | 0 | 0 | 0 | 0.47093 | 2.5989 | 8.4103 | 17.9666 | 17.6321 | 4.1356 | 4.4536 | 0 | 0 | 0
G5b.53 | Operational Emissions | Number of property assets with reduced emissions | O_PE1_E | Number | I / BF | Net Zero Emissions - Reduce the emission intensity associated with the provision of heat and energy in our buildings and estates. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0.076523 | 0.076491 | 0.15881 | 0.15186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.099025 | 0.10136 | 0.21592 | 0.2106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0.2072 | 0.15456 | 0.10192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27456 | 0.21014 | 0.14134 | 0 | 0 | 0 | 0
G5b.54 | Operational Emissions | Number of Climate Change studies | O_SE3_E | Number | I / BF | Identifying technologies and pilot work across water and waste water assets. Company-wide waste / resource audit review to embed circularity across SW. Progressing at scale outcomes from Sustainable Growth Agreement | 0 | 0 | 0 | 2 | 0 | 0 | 0 | [5 empty] | 0.045919 | 0.055704 | 0.43221 | 0.4644 | 0.75872 | 0.97162 | 0 | 0 | 0 | 0 | 0 | 0.051094 | 0.068216 | 0.5593 | 0.61539 | 1.0315 | 1.3474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 |  |  |  |  | 0.56146 | 0.045919 | 0.055703 | 0.10044 | 1.1295 | 0.85148 | 0.5455 | 0 | 0 | 0 | 0 | 0.60082 | 0.051093 | 0.068216 | 0.12998 | 1.4967 | 1.1576 | 0.75648 | 0 | 0 | 0 | 0
G5b.55 | Enhancements - Climate Change Mitigation total expenditure |  |  | £m | C | [12 empty] | 0 | 2.813 | 4.7249 | 15.653 | 15.7154 | 14.1943 | 15.8683 | 1.4955 | 0 | 0 | 0 | 0 | 3.13 | 5.7862 | 20.256 | 20.8248 | 19.2983 | 22.0055 | 2.2241 | 0 | 0 | 0 | [11 empty] | 4.0272 | 2.9587 | 5.5591 | 11.7418 | 24.1235 | 19.8967 | 7.3067 | 5.5715 | 0 | 0 | 0 | 4.3095 | 3.2921 | 6.8078 | 15.1946 | 31.9665 | 27.0511 | 10.1326 | 8.2857 | 0 | 0 | 0
Enhancements - Circular Economy
G5b.56 | Circular Economy |  |  |  | I / BF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G5b.57 | Enhancements - Circular Economy total expenditure |  |  | £m | C | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enhancements - Water Continuity
G5b.58 | Interruption to Supply | Number of plans to improve customer experience | O_SA12_E | Number | I / BF | Develop plans and interventions for repeat asset failures. | 0 | 0 | 1 | 0 | 0 | 0 | 0 | [5 empty] | 0.0060218 | 0.018876 | 0.4523 | 0.45188 | 0.93819 | 0.89715 | 0 | 0 | 0 | 0 | 0 | 0.0067004 | 0.023116 | 0.58531 | 0.59879 | 1.2755 | 1.2441 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | 0.036326 | 0.0060217 | 0.018876 | 0 | 1.2241 | 0.91316 | 0.60217 | 0 | 0 | 0 | 0 | 0.038872 | 0.0067003 | 0.023116 | 0 | 1.6221 | 1.2415 | 0.83507 | 0 | 0 | 0 | 0
G5b.59 | Pressure | Number of properties where persistent low pressure is resolved | O_SA7_E | Number | I / BF | Resolve properties confirmed with persistent low pressure | 0 | 7 | 5 | 25.4 | 33 | 3 | 0 | [5 empty] | 0.22358 | 0.69457 | 1.1933 | 0.5236 | 0.12919 | 0.10577 | -0.00079075 | 0 | 0 | 0 | 0 | 0.24878 | 0.85058 | 1.5442 | 0.69383 | 0.17564 | 0.14668 | -0.001176 | 0 | 0 | 0 | 0 | 7 | 5 | 56 | 22 | 3 | 0 |  |  |  |  | 0.1021 | 0.22919 | 0.69875 | 2.1514 | -0.065202 | -0.12819 | -0.016054 | 0.050199 | 0 | 0 | 0 | 0.10926 | 0.25501 | 0.8557 | 2.7841 | -0.0864 | -0.17429 | -0.022264 | 0.074653 | 0 | 0 | 0
G5b.60 | Resistance to Threat | Number of interventions to reduce risk of flooding from mains | O_HS4_E | Number | I / BF | Liberton trunk mains (Glencorse System) - based on burst control or diversion solution; Assynt trunk main Maryburgh - Diversion of high pressure trunk mains; Assess high priority risks of flooding and options to mitigate where they have not occurred | 0 | 0 | 0 | 1 | 1 | 0 | 1 | [5 empty] | 0.17172 | 0.1329 | 0.12008 | 1.7005 | 0.078888 | 0.82968 | 8.2945 | 0 | 0 | 0 | 0 | 0.19107 | 0.16275 | 0.15539 | 2.2533 | 0.10725 | 1.1506 | 12.3351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | 0.16334 | 0.11787 | -0.043161 | 0.011594 | 0.92983 | 0.97693 | 1.0406 | 9.0998 | 0.038142 | 0 | 0 | 0.17479 | 0.13115 | -0.052856 | 0.015004 | 1.2321 | 1.3282 | 1.4431 | 13.5327 | 0.063879 | 0 | 0
G5b.61 | Resistance to Threat | Length of new or enhanced distribution mains | O_SA6_E | Metres | I / BF | Enhancing network supply capability. | 0 | 0 | 0 | 0 | 0 | 3450 | 0 | [5 empty] | 0.027993 | 0.12675 | 0.33369 | -4.9876e-11 | 4.8092e-11 | 4.6475e-11 | 0 | 0 | 0 | 0 | 0 | 0.031148 | 0.15522 | 0.43182 | -6.6092e-11 | 6.5384e-11 | 6.4449e-11 | 0 | 0 | 0 | 0 | 0 | 1870 | 0 | 0 | 0 | 0 | 3450 |  |  |  |  | 1.4831 | 0.05719 | 0.12674 | 0.86792 | -0.0028747 | -0.4109 | -0.14966 | 0.19316 | 0 | 0 | 0 | 1.5871 | 0.063635 | 0.15521 | 1.1231 | -0.0038093 | -0.55864 | -0.20754 | 0.28725 | 0 | 0 | 0
G5b.62 | Resistance to Threat | Number of WTW's with capacity restored | O_WR7_E | Number | I / BF | Mannofield to Turriff network link; Eela Water clarifier hydraulic restriction | 0 | 0 | 1 | 2 | 0 | 0 | 0 | [5 empty] | 0.26789 | 0.80743 | 1.0284 | 2.6664 | 3.9083 | 5.32 | 7.9034 | 0 | 0 | 0 | 0 | 0.29808 | 0.9888 | 1.3308 | 3.5332 | 5.3136 | 7.3776 | 11.7534 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | 0.050798 | 0.16323 | 0.5286 | 1.4504 | 14.3596 | 11.4639 | 8.0321 | 0.92689 | 0 | 0 | 0 | 0.054359 | 0.18162 | 0.64734 | 1.877 | 19.0282 | 15.586 | 11.1387 | 1.3784 | 0 | 0 | 0
G5b.63 | Resistance to Threat | Number of Resilience Improvements | O_WR11_E | Number | I / BF | Dundee drought resilience - leading from IR18 development study; Moray Coast resilience - leading from IR18 development study; Resilience - Blairlinnans & Milngavie Connectivity. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0.20828 | 0.39986 | 0.7278 | 0.94054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26953 | 0.52986 | 0.9895 | 1.3043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  |  | 0.29583 | 0.049529 | 0.084649 | 0.21385 | 1.0906 | 0.96722 | -0.12937 | 0.012967 | 0 | 0 | 0 | 0.31657 | 0.05511 | 0.10366 | 0.27673 | 1.4452 | 1.315 | -0.17941 | 0.019284 | 0 | 0 | 0
G5b.64 | Resistance to Threat | Number of sites with emergency planning equipment installed | O_WR1_E1 | Number | I / BF | Increase capability to respond | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0.10166 | 0.083996 | 0.083961 | 0.94861 | 0.58279 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1245 | 0.1087 | 0.11126 | 1.2897 | 0.8082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G5b.65 | Resistance to Threat | Number of sites with standby power equipment installed | O_WR1_E2 | Number | I / BF | Provision of New Standby Power | 0 | 0 | 0 | 1 | 0 | 0 | 0 | [5 empty] | 0.042817 | 0.057861 | 0.075822 | 0.05602 | 0.06944 | 0.076634 | 0 | 0 | 0 | 0 | 0 | 0.047642 | 0.070858 | 0.098118 | 0.074234 | 0.094408 | 0.10627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G5b.66 | Resistance to Threat | Number of sites with black start capability improved | O_WR3_E | Number | I / BF | Improvements to communication systems, and backup generation - (Guidance awaited from Government) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0.18385 | 0.18378 | 0.38156 | 0.36487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23792 | 0.24353 | 0.51876 | 0.50599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0.49782 | 0.37135 | 0.24488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65967 | 0.50488 | 0.33959 | 0 | 0 | 0 | 0
G5b.67 | Resistance to Threat | Number of sites with water security enhancements | O_HS2_E | Number | I / BF | Physical Security - dams and intakes, control rooms, wash water return (assessed for deliver / integration with core programme sites) | 0 | 65 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0.055216 | 0.013881 | 0.7609 | 0.78353 | 1.0197 | 1.3164 | 1.5722 | 0 | 0 | 0 | 0 | 0.061438 | 0.016999 | 0.98465 | 1.0383 | 1.3863 | 1.8256 | 2.3381 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 33 | 0 |  |  |  |  | 3.2297 | 0.055215 | 0.013881 | 0.13799 | 1.1523 | 0.72857 | 1.797 | 0 | 0 | 0 | 0 | 3.4561 | 0.061437 | 0.016999 | 0.17856 | 1.5269 | 0.99054 | 2.492 | 0 | 0 | 0 | 0
G5b.68 | Water Availability | Number of Water Supply Zones with improved resilience | O_WR6_E | Number | I / BF | Resilience to drought for Afton supplies; Resilience to drought for Turret supplies; Improve resilience of water supply systems to enable them to provide continuous water supplies | 0 | 2 | 2 | 4 | 10 | 1 | 6 | [5 empty] | 0.89899 | 1.0117 | -1.6797 | 1.6122 | 0.30938 | 0.40751 | 3.1127 | 0 | 0 | 0 | 0 | 1.0003 | 1.2389 | -2.1736 | 2.1364 | 0.42062 | 0.56512 | 4.629 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 4 | 3 | 1 |  |  |  |  | 2.7679 | 0.86293 | 0.80512 | 0.88553 | -0.83848 | 0.30873 | 0.53627 | 99.191 | 0.004265 | 0 | 0 | 2.9619 | 0.96017 | 0.98597 | 1.1459 | -1.1111 | 0.41974 | 0.74368 | 147.5109 | 0.0071429 | 0 | 0
G5b.69 | Water Availability | Number of resilience improvements via Water Efficiency campaigns | O_WR8_G2 | Number | I / BF | Water efficiency campaign | 0 | 0 | 0 | 4 | 1 | 0 | 0 | [5 empty] | 0.031695 | 0.45576 | 0.29557 | 0.28805 | 0.5976 | 0.57146 | 0 | 0 | 0 | 0 | 0 | 0.035266 | 0.55814 | 0.38248 | 0.3817 | 0.81248 | 0.79248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | 0 | 0.020935 | 0.45488 | 0.0007564 | 0.78821 | 0.58778 | 0.38754 | 0 | 0 | 0 | 0 | 0 | 0.023294 | 0.55706 | 0.00097882 | 1.0445 | 0.79913 | 0.53743 | 0 | 0 | 0 | 0
G5b.70 | Water Availability | Number of resilience improvements at rural supply hubs to provide capacity for new demand | O_WR8_G3 | Number | I / BF | Rural supply hub | 0 | 2 | 1 | 0 | 2 | 1116 | 0 | [5 empty] | 0.32725 | 0.01423 | 0.51332 | 0.79748 | 1.1705 | 0.70592 | 0.00088704 | 0 | 0 | 0 | 0 | 0.36413 | 0.017426 | 0.66427 | 1.0568 | 1.5914 | 0.97894 | 0.0013191 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 |  |  |  |  | 4.1761 | 0.32725 | 0.01423 | 0.15391 | 1.4287 | 0.96689 | 0.63773 | 0.88213 | 0 | 0 | 0 | 4.4689 | 0.36413 | 0.017426 | 0.19916 | 1.8932 | 1.3146 | 0.88438 | 1.3119 | 0 | 0 | 0
G5b.71 | Water Availability | Number of education campaigns targeted at reducing water wastage in households | O_SA11_E | Number | I / BF | Working in partnership with other bodies to provide customers with the tools and knowledge they require to reduce water waste | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0.098907 | 0.062924 | 0.046441 | 0.045723 | 0.045394 | 0.044582 | 0.015905 | 0 | 0 | 0 | 0 | 0.11005 | 0.077059 | 0.060097 | 0.060589 | 0.061716 | 0.061825 | 0.023653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0.29179 | 0.36649 | 0.33398 | 0.009704 | -0.082643 | -0.0052642 | 0.091617 | 0 | 0 | 0 | 0 | 0.32468 | 0.44882 | 0.4322 | 0.012859 | -0.11236 | -0.0073001 | 0.13625 | 0 | 0 | 0
G5b.72 | Water Availability | Number of tanker fill points installed | O_WR8_G4 | Number | I / BF | Tankers and tanker fill points to meet peak capacity at small WTW | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0.029714 | -0.016372 | 0.2443 | 0.2442 | 0.507 | 0.48482 | 0 | 0 | 0 | 0 | 0 | 0.033062 | -0.02005 | 0.31613 | 0.32359 | 0.68931 | 0.67233 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0.0010153 | 0.029713 | -0.016372 | 0.016805 | 0.26604 | 0.96374 | 0.23372 | 0 | 0 | 0 | 0 | 0.0010865 | 0.033062 | -0.02005 | 0.021746 | 0.35253 | 1.3103 | 0.32411 | 0 | 0 | 0 | 0
G5b.73 | Water Transfer |  |  |  | I / BF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G5b.74 | Enhancements - Water Continuity total expenditure |  |  | £m | C | [12 empty] | 0 | 2.1818 | 3.4822 | 3.8606 | 9.8371 | 10.8316 | 12.6481 | 20.8988 | 0 | 0 | 0 | 0 | 2.4277 | 4.2643 | 4.9958 | 13.0353 | 14.7263 | 17.54 | 31.0794 | 0 | 0 | 0 | [11 empty] | 12.3062 | 2.2109 | 3.0527 | 6.2242 | 20.8404 | 17.6265 | 13.2117 | 110.4478 | 0.042407 | 0 | 0 | 13.1689 | 2.46 | 3.7384 | 8.0545 | 27.616 | 23.9646 | 18.3215 | 164.2513 | 0.071022 | 0 | 0
Wastewater – Managing Quantity of Flows
G5b.75 | Chronic Issues on the Waste Network | Number of properties removed from internal flooding at risk register | O_FR1_F1 | Number | I / BF | To reduce flood risk to customers impacted by repeat high consequence internal sewer flooding where not disproportionately expensive | 0 | 163 | 44 | 19 | 54 | 44 | 49 | [5 empty] | 17.1777 | 15.0257 | 3.3161 | 5.423 | 14.6373 | 18.9821 | 4.6037 | 0 | 0 | 0 | 0 | 19.1134 | 18.4009 | 4.2913 | 7.1862 | 19.9005 | 26.3238 | 6.8463 | 0 | 0 | 0 | 0 | 42 | 42 | 27 | 35 | 39 | 33 |  |  |  |  | 47.8577 | 17.4884 | 16.543 | 13.0602 | 14.6577 | 15.7535 | 23.1579 | 80.1244 | 0 | 0 | 0 | 51.2125 | 19.4592 | 20.2589 | 16.9007 | 19.4232 | 21.4181 | 32.1146 | 119.1561 | 0 | 0 | 0
G5b.76 | Chronic Issues on the Waste Network | Number of properties with temporary internal flood prevention measures | O_FR1_F2 | Number | I / BF | Provide protection to customers from the risk of flooding whilst permanent solutions are being identified and implemented | 0 | 28 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0.44089 | 1.0616 | 0.74314 | 1.2398 | 1.7339 | 2.1134 | 0.76085 | 0 | 0 | 0 | 0 | 0.49058 | 1.3 | 0.96166 | 1.6428 | 2.3574 | 2.9309 | 1.1315 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | 0.58219 | 0.43349 | 0.95193 | 1.5267 | 0.4495 | 0.38621 | 0.18487 | 0.24388 | 0 | 0 | 0 | 0.623 | 0.48234 | 1.1658 | 1.9756 | 0.59564 | 0.52508 | 0.25637 | 0.36268 | 0 | 0 | 0
G5b.77 | Chronic Issues on the Waste Network | Number of catchments with network monitoring Food Service Establishment roll outs | O_FR6_E | Number | I / BF | Enhanced response to reduce likelihood of repeat pollution incidents - Wider Food Service Establishment (FSE) roll out (following St Andrews trial) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0.078377 | 0.10123 | 0.16549 | 0.21193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10143 | 0.13414 | 0.225 | 0.2939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | 0 | 0 | 0 | 0.10721 | 0.34824 | 0.095308 | 0.0062627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13874 | 0.46147 | 0.12958 | 0.0086849 | 0 | 0 | 0 | 0
G5b.78 | Chronic Issues on the Waste Network | Number of customer flooding response process improvements | O_FR5_F1 | Number | I / BF | Enhanced approach to customer journey in the event of internal and external sewer flooding incidents; Maintain customer response approach in event of internal and external sewer flooding incidents; Minimise sewer blockages (flooding and environmental pollution incidents) through engagement with customers; Develop enhanced response for sewer flooding (response kits and flood guards) including specialised clean up for agricultural land | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | -3.5051e-07 | -0.00019073 | 0.56332 | 0.56445 | 1.1441 | 1.1024 | 0 | 0 | 0 | 0 | 0 | -3.9001e-07 | -0.00023357 | 0.72897 | 0.74796 | 1.5555 | 1.5288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0.33836 | -3.505e-07 | -0.00019073 | 0 | 0.065517 | 0.048873 | 0.032229 | 0 | 0 | 0 | 0 | 0.36208 | -3.9e-07 | -0.00023357 | 0 | 0.086818 | 0.066446 | 0.044694 | 0 | 0 | 0 | 0
G5b.79 | Chronic Issues on the Waste Network | Number of education campaigns targeted at customers in sewer choke hot spot areas | O_FR5_F2 | Number | I / BF | Education campaigns targeted at customers in sewer choke hot spot areas | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0.31456 | 0.33205 | 0.19055 | 0.0019244 | 0.0024279 | 0.0025906 | 0 | 0 | 0 | 0 | 0 | 0.35 | 0.40663 | 0.24658 | 0.0025501 | 0.0033009 | 0.0035926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0.31455 | 0.33204 | 0.22777 | -0.0049295 | -0.0042647 | -0.021093 | 0 | 0 | 0 | 0 | 0 | 0.35 | 0.40663 | 0.29475 | -0.0065322 | -0.0057982 | -0.029251 | 0 | 0 | 0 | 0
G5b.80 | Long-Term Planning of the Drainage Service | Number of flood risk management (Section 16) models | O_FR3_F | Number | I / BF | Provide fit for purpose models required as minimum legislative requirement under Flood Risk Management Act | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 0.42425 | 0.25625 | 0.17368 | 6.927e-12 | 0.13964 | 0.12553 | 1.1483 | 0 | 0 | 0 | 0 | 0.47206 | 0.31381 | 0.22475 | 9.1791e-12 | 0.18985 | 0.17409 | 1.7076 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 1.7097 | 0.42424 | 0.25625 | 0.070561 | 0.12349 | 0.7003 | 0.74448 | 1.1595 | 0 | 0 | 0 | 1.8295 | 0.47205 | 0.3138 | 0.09131 | 0.16364 | 0.95211 | 1.0324 | 1.7243 | 0 | 0 | 0
G5b.81 | Long-Term Planning of the Drainage Service | Number of properties removed from external flooding at risk register | O_FR2_F | Number | I / BF | To reduce flood risk to customers impacted by repeat high consequence external sewer flooding where not disproportionately expensive; Reduce and remove storm water in the sewer network in areas to address high priority risk areas of sewer flooding | 0 | 5 | 0 | 36 | 28 | 111 | 76 | [5 empty] | 2.6484 | 6.4851 | 2.1501 | 2.8299 | 2.1587 | 3.8684 | 5.8891 | 0 | 0 | 0 | 0 | 2.9468 | 7.9419 | 2.7823 | 3.75 | 2.9349 | 5.3646 | 8.7579 | 0 | 0 | 0 | 0 | 49 | 5 | 17 | 44 | 7 | 88 |  |  |  |  | 8.3373 | 2.1793 | 4.7957 | 6.1388 | 0.47623 | 3.5133 | 1.1371 | 28.7359 | 0 | 0 | 0 | 8.9217 | 2.4248 | 5.8729 | 7.944 | 0.63106 | 4.7767 | 1.5769 | 42.7343 | 0 | 0 | 0
G5b.82 | Long-Term Planning of the Drainage Service | Number of surface water management planning schemes | O_FR4_F | Number | I / BF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0.13736 | 0.1774 | 0.29003 | 0.37141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17775 | 0.23508 | 0.39431 | 0.51505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0.43621 | 0.32539 | 0.21458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57803 | 0.4424 | 0.29757 | 0 | 0 | 0 | 0
G5b.83 | Enhancements - Managing Quantity of Flows total expenditure |  |  | £m | C | [12 empty] | 0 | 21.0058 | 23.1605 | 7.3526 | 10.3377 | 20.2717 | 26.7779 | 12.4019 | 0 | 0 | 0 | 0 | 23.3729 | 28.363 | 9.5148 | 13.6987 | 27.5608 | 37.1346 | 18.4433 | 0 | 0 | 0 | [11 empty] | 58.8251 | 20.84 | 22.8787 | 21.1312 | 16.552 | 20.8187 | 25.4563 | 110.2636 | 0 | 0 | 0 | 62.9488 | 23.1885 | 28.0178 | 27.3452 | 21.9333 | 28.3045 | 35.3019 | 163.9774 | 0 | 0 | 0
Enhancements - Other
G5b.84 | Business Intelligence | Number of Climate Change studies | O_SE1_E | Number | I / BF | Further develop our understanding of the implications of climate change. Update the Scottish Water risk assessment work/ tools (UKCP18) following the latest projections from Met Office | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0.091643 | 0.085399 | 0.14013 | 0.15775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11859 | 0.11316 | 0.19051 | 0.21876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | 0 | 0.031609 | 0.23918 | 0.13194 | 0.23461 | 0.15859 | 0.10458 | 0 | 0 | 0 | 0 | 0 | 0.035171 | 0.2929 | 0.17074 | 0.31089 | 0.21561 | 0.14503 | 0 | 0 | 0 | 0
G5b.85 | Business Intelligence | Number of Climate Change Audits | O_SE4_E | Number | I / BF | Sustainability auditing/review of SW assets and estates to support future action and inform future investment planning. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0.00052668 | 0.0005277 | 0.00053038 | 0.00053108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00068156 | 0.00069926 | 0.0007211 | 0.00073648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  |  |  |  | 0 | 0.06879 | 0.15764 | -0.068465 | 0.17425 | 0.024748 | 0.018114 | 0.0026976 | 0 | 0 | 0 | 0 | 0.076542 | 0.19305 | -0.088598 | 0.2309 | 0.033646 | 0.025121 | 0.0040116 | 0 | 0 | 0
G5b.86 | Business Intelligence | Number of demonstrators / catchment trials deployed | O_SE5_E | Number | I / BF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0.21005 | 0.2713 | 0.44353 | 0.56798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27182 | 0.3595 | 0.60301 | 0.78765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0.66708 | 0.49761 | 0.32814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88396 | 0.67654 | 0.45506 | 0 | 0 | 0 | 0
G5b.87 | Business Intelligence | Number of environmental sustainability communication initiatives | O_SE6_E | Number | I / BF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0.021498 | 0.022423 | 0.033281 | 0.034205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.027819 | 0.029714 | 0.045248 | 0.047434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0.049782 | 0.037135 | 0.024488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.065967 | 0.050488 | 0.03396 | 0 | 0 | 0 | 0
G5b.88 | Customer & Community Experience | Number of plans to improve customer experience | O_CE1_E1 | Number | I / BF | Provision to develop plans for extending and/or tailoring market research programme to support the outcomes for SR21; Develop plan and programme to introduce more automated self-service to improve the speed and quality of response for customers. Develop plan and programme to enable customers to track the progress of their enquiry. Develop plan to introduce AI tools where; Co-create tailored support plans. Develop specifically trained and trusted employees. Develop a priority service register. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0.081197 | 0.11397 | 0.16105 | 0.068815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10507 | 0.15102 | 0.21895 | 0.095431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  |  | 0 | 0.31402 | 0.067029 | 0.23658 | 0.30684 | 0.26048 | 0.17317 | 0 | 0 | 0 | 0 | 0 | 0.34941 | 0.082086 | 0.30615 | 0.4066 | 0.35414 | 0.24015 | 0 | 0 | 0 | 0
G5b.89 | Customer & Community Experience | Number of process improvements to support improved response to priority service customers | O_CE1_E2 | Number | I / BF | Improve response to priority service customer groups during an incident | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0.08647 | 0.080579 | 0.13222 | 0.14885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1119 | 0.10678 | 0.17976 | 0.20642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0.066083 | 0.027993 | 0.032191 | 0.23315 | 0.15234 | 0.32558 | 0 | 0 | 0 | 0 | 0 | 0.073529 | 0.034281 | 0.041658 | 0.30895 | 0.20711 | 0.45151 | 0 | 0 | 0 | 0
G5b.90 | Customer & Community Experience | Number of sites enabled for community access | O_CR3_E | Number | I / BF | Opening up our assets (where appropriate) to the community for leisure purposes and by taking the necessary steps to ensure we facilitate peoples enjoyment of the natural environment. STUDY: 6 pilot sites, vistor surveys and signage refresh for each site.; Mugdock and Craigmaddie Reservoirs: Refreshed Strategic Approach | 0 | 0 | 0 | 0 | 1 | 0 | 0 | [5 empty] | 0.17419 | 0.064588 | 0.41248 | 0.093425 | 0.11645 | 0.12852 | 0 | 0 | 0 | 0 | 0 | 0.19382 | 0.079096 | 0.53378 | 0.1238 | 0.15833 | 0.17823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  |  |  |  | 0.22587 | 0.28951 | 0.21542 | 1.8287 | 1.7449 | 0.9802 | 0.617 | 0.0001681 | 0 | 0 | 0 | 0.2417 | 0.32213 | 0.26381 | 2.3665 | 2.3122 | 1.3327 | 0.85563 | 0.00024999 | 0 | 0 | 0
G5b.91 | Customer & Community Experience | Number of new top-up-from-the-tap points | O_CR5_E | Number | I / BF | Continue our Top up Taps programme, installing a network of taps across the country and prevent the use of single-use plastic bottles | 0 | 0 | 0 | 50 | 0 | 0 | 0 | [5 empty] | 0.48604 | 0.56554 | 0.50792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.54081 | 0.69258 | 0.65728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 |  |  |  |  | 0 | 0.48603 | 0.56553 | 0.33872 | 0.21263 | -0.030392 | -0.013039 | 0 | 0 | 0 | 0 | 0 | 0.5408 | 0.69257 | 0.43832 | 0.28176 | -0.041321 | -0.018082 | 0 | 0 | 0 | 0
G5b.92 | Customer & Community Experience | Number of private water supplies investigated | O_CR7_E | Number | I / BF | Investigate the reliability of private water supplies - Aberdeenshire, Moray & Angus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | -0.0034543 | -0.0034543 | -0.0034543 | -0.0034543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.0044701 | -0.0045774 | -0.0046964 | -0.0047903 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | 0.023596 | 0.07988 | -0.0085786 | 0 | -0.0057971 | -0.0053417 | -0.0022917 | 0 | 0 | 0 | 0 | 0.02525 | 0.088882 | -0.010506 | 0 | -0.0076819 | -0.0072625 | -0.003178 | 0 | 0 | 0 | 0
G5b.93 | Enhance Scotland's Environment |  |  |  | I / BF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G5b.94 | Innovation (inc. Chair) | Number of innovation pilot programmes undertaken | O_IN1_E | Number | I / BF | Innovation; Build water research and development capacity in Scotland s Universities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0.097785 | 0.17874 | 0.32457 | 0.42185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12654 | 0.23685 | 0.44127 | 0.585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 |  |  |  |  | 0 | 1.8737 | 2.3098 | 2.3636 | 3.3473 | 1.7304 | 1.1583 | 0.0050311 | 0 | 0 | 0 | 0 | 2.0848 | 2.8286 | 3.0586 | 4.4355 | 2.3526 | 1.6063 | 0.007482 | 0 | 0 | 0
G5b.95 | Other areas | Number of WTW sites with Legacy Sludge Issues resolved | O_AD3_E | Number | I / BF | Develop alternative sludge disposal route options for WTW on Orkney to allow cessation of operations at Big Breck and Westray land fill sites; Big Breck - Develop options to close and restore the site; Westray - Develop options to close and restore the site; Loch Eck - Develop options to restore / remove sludge in line with IR18 study scopes agreed with SEPA; Invercannie - Develop options to close sludge storage and restore land in line with IR18 study scopes agreed with SEPA; Loch Eck - Develop compliant run to waste facilities; Bareagle - maintain current capability - Develop options to extend lease for site | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 0.43383 | 0.27706 | 1.3001 | 2.388 | 2.649 | 2.4156 | 5.4752 | 0 | 0 | 0 | 0 | 0.48271 | 0.3393 | 1.6824 | 3.1644 | 3.6015 | 3.3498 | 8.1424 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | 3.944 | 0.43382 | 0.27706 | 0.63238 | 2.8502 | 2.3306 | 2.9395 | 6.087 | 0 | 0 | 0 | 4.2204 | 0.48271 | 0.3393 | 0.81835 | 3.7769 | 3.1686 | 4.0764 | 9.0523 | 0 | 0 | 0
G5b.96 | Other areas | Number of sites with catchment management safety interventions | O_HS5_M | Number | I / BF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G5b.97 | Other areas | Number of Lighthouse projects delivered | O_IC1_E | Number | I / BF | Ringfenced value fixed by FD (Lighthouse projects - Craigleith, River Almond, St Marys) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 2.1177 | 2.7316 | 7.3019 | 12.5918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7404 | 3.6197 | 9.9274 | 17.4618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 2 | 3 |  |  |  |  | 0 | 0 | 0.10319 | 0.51376 | 4.4279 | 4.6893 | 3.0086 | 1.6631 | 0 | 0 | 0 | 0 | 0 | 0.12637 | 0.66483 | 5.8675 | 6.3754 | 4.1722 | 2.4733 | 0 | 0 | 0
G5b.98 | Other areas | Number of Transformation initiatives implemented | O_TF1_E | Number | I / BF | Strategic & Enabling; Transformation of Scottish Water (DEVELOP) QE funded - Overall Tier 2 benefit; Transforming How We Serve; Transformation PoC, PoV & Pilots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 8.2278 | 7.0242 | 37.8509 | 43.0315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.6473 | 9.308 | 51.461 | 59.6746 | 0 | 0 | 0 | 0 | 0 | 2 | 16 | 24 | 24 | 7 | 10 |  |  |  |  | 9.2038 | 23.6312 | 42.3681 | 26.0578 | 39.6562 | 34.7999 | 15.71 | 0.56995 | 0 | 0 | 0 | 9.849 | 26.2942 | 51.8851 | 33.7204 | 52.5493 | 47.313 | 21.7861 | 0.8476 | 0 | 0 | 0
G5b.99 | Other areas | Number of digital transformation interventions | O_DI1_M | Number | I / BF | Risk and Security | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 1.584 | 0.045444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7625 | 0.055651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G5b.100 | Other areas | Number of plans to improve customer experience | O_DC4_E | Number | I / BF | Develop plans and interventions for customers side to address dissatisfaction with core products (e.g. taste and odour). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0.0087459 | 0.050215 | 0.20723 | 0.18897 | 0.31007 | 0.34907 | 0 | 0 | 0 | 0 | 0 | 0.0097315 | 0.061495 | 0.26817 | 0.25041 | 0.42156 | 0.48408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0.001033 | 0.0087458 | 0.050215 | 0 | 0.47398 | 0.35033 | 0.23102 | 0 | 0 | 0 | 0 | 0.0011054 | 0.0097314 | 0.061494 | 0 | 0.62808 | 0.4763 | 0.32037 | 0 | 0 | 0 | 0
G5b.101 | Other areas | Number of properties with meter installations for first time registered non domestic premises | O_MR2_G | Number | I / BF | Meter installation for all first time registered non domestic premises as per policy and provides meters for domestic occupants | 0 | 0 | 5050 | 0 | 0 | 0 | 0 | [5 empty] | 2.7558 | 1.4336 | 1.7057 | 0.13815 | 0.19825 | 0.19304 | 0 | 0 | 0 | 0 | 0 | 3.0664 | 1.7556 | 2.2073 | 0.18306 | 0.26953 | 0.2677 | 0 | 0 | 0 | 0 | 0 | 0 | 16444 | 0 | 0 | 6563 | 0 |  |  |  |  | 7.6368 | 2.7558 | 1.4336 | 1.2466 | 0.89125 | 0.058601 | 0.038644 | 0 | 0 | 0 | 0 | 8.1722 | 3.0663 | 1.7556 | 1.6132 | 1.181 | 0.079673 | 0.05359 | 0 | 0 | 0 | 0
G5b.102 | Other areas | Number of domestic smart meters installed | O_SA13_E | Number | I / BF | Deliver a domestic smart metering pilot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0.8937 | 0.66666 | 0.43962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1843 | 0.90637 | 0.60965 | 0 | 0 | 0 | 0
G5b.102a | Other areas | Number of scientific services facilities upgraded | O_JH1_E | Number | I / BF | Continue provision of an accredited laboratory service | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | 0.066299 | 0.73947 | 0.87238 | 1.371 | 0.2651 | 3.0597 | 3.5752 | 23.2598 | 0 | 0 | 0 | 0.070946 | 0.8228 | 1.0683 | 1.7742 | 0.35129 | 4.1599 | 4.9579 | 34.5906 | 0 | 0 | 0
G5b.103 | PFI returns | Number of Private Finance Initiative (PFI) sites returned to Scottish Water | O_PF1_E | Number | I / BF | Highland PFI Includes transition to Scottish Water ownership and contractual obligation of fair market value payment; Manage the expiry of the Daldowie Private Finance Initiative contract; Highland PFI - Sludge; Dalmuir PFI Post concession work; PFI other returns initial work (Almond valley, Tay project, Moray Coast, Ayrshire) | 0 | 0 | 0 | 2 | 0 | 0 | 1 | [5 empty] | 0.32314 | 16.5082 | 5.9492 | 3.2384 | 7.0367 | 14.9813 | 9.6855 | 0 | 0 | 0 | 0 | 0.35955 | 20.2164 | 7.6987 | 4.2912 | 9.567 | 20.7755 | 14.4037 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 |  |  |  |  | 0.21903 | 0.31482 | 16.5036 | 8.7106 | 6.5255 | 5.0623 | 7.9196 | 22.8016 | 0 | 0 | 0 | 0.23439 | 0.3503 | 20.2107 | 11.272 | 8.6471 | 6.8825 | 10.9827 | 33.9092 | 0 | 0 | 0
G5b.104 | PFI returns | Number of approved plans for PFI Contracts transitioned to Scottish Water | O_PF2_E | Number | I / BF | Dalmuir PFI Determine an appropriate plan to support transition to Scottish Water ownership and operation and contract completion payments at both sites | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 0 | 0.00027784 | 0.33651 | 0.5772 | 0.86355 | 4.5192 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00034025 | 0.43547 | 0.76486 | 1.1741 | 6.2671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | 0.0018392 | 0.00075569 | 0.00068058 | 0.053715 | 1.2322 | 0.92176 | 4.0876 | 7.2851 | 10.4774 | 0 | 0 | 0.0019682 | 0.00084084 | 0.00083346 | 0.069511 | 1.6327 | 1.2532 | 5.6686 | 10.8339 | 17.5471 | 0 | 0
G5b.105 | Service Relocation | Number of service relocations - waste | O_ED5_G | Number | I / BF | Scottish Waters statutory contribution towards the relocation and integration of Scottish Water assets associated with large infrastructure schemes - waste | 0 | 1 | 0 | 2 | 4 | 0 | 0 | [5 empty] | 0.69556 | 0.27381 | 0.67645 | 2.1609 | 0.47933 | 0.47171 | 0.22255 | 0 | 0 | 0 | 0 | 0.77395 | 0.33532 | 0.87537 | 2.8635 | 0.65168 | 0.65415 | 0.33096 | 0 | 0 | 0 | 0 | 8 | 0 | 5 | 3 | 0 | 0 |  |  |  |  | 7.6335 | 0.69555 | 0.27507 | 0.2224 | 2.4934 | 0.56267 | 0.50863 | 0.191 | 0 | 0 | 0 | 8.1686 | 0.77394 | 0.33686 | 0.2878 | 3.3041 | 0.76499 | 0.70535 | 0.28405 | 0 | 0 | 0
G5b.106 | Service Relocation | Length of service relocations - water mains | O_WR9_G1 | km | I / BF | Scottish Water�s statutory contribution towards the relocation and integration of Scottish Water assets associated with large infrastructure schemes | 0 | 0 | 1129 | 48 | 2 | 0 | 6 | [5 empty] | 3.1532 | 2.7598 | 4.3913 | 5.5356 | 12.125 | 14.0801 | 0.39001 | 0 | 0 | 0 | 0 | 3.5085 | 3.3797 | 5.6826 | 7.3354 | 16.4849 | 19.5258 | 0.58 | 0 | 0 | 0 | 0 | 7973 | 126 | 2329.5 | 524 | 4115 | 1598 |  |  |  |  | 31.131 | 3.1531 | 2.7585 | 3.0321 | 14.9477 | 10.9049 | 7.2481 | 0.74112 | 0 | 0 | 0 | 33.3132 | 3.5084 | 3.3781 | 3.9237 | 19.8075 | 14.826 | 10.0515 | 1.1022 | 0 | 0 | 0
G5b.107 | Enhancements - Other total expenditure |  |  | £m | C | [12 empty] | 0 | 9.6145 | 21.9785 | 26.4181 | 24.826 | 70.163 | 94.1583 | 15.7733 | 0 | 0 | 0 | 0 | 10.6979 | 26.9154 | 34.1867 | 32.8975 | 95.3917 | 130.5754 | 23.4571 | 0 | 0 | 0 | [11 empty] | 60.0867 | 34.9428 | 68.2163 | 46.7036 | 81.6219 | 67.2124 | 48.4407 | 62.6067 | 10.4774 | 0 | 0 | 64.2988 | 38.8805 | 83.5394 | 60.4373 | 108.1589 | 91.3802 | 67.1758 | 93.1048 | 17.5471 | 0 | 0
Totals
G5b.108 | Total growth expenditure |  |  | £m | C | [12 empty] | 0 | 44.3067 | 56.4885 | 24.6033 | 59.3355 | 57.1251 | 30.8966 | 72.9433 | 0 | 0 | 0 | 0 | 49.2996 | 69.1773 | 31.8382 | 78.6266 | 77.6658 | 42.8463 | 108.4768 | 0 | 0 | 0 | [11 empty] | 128.8765 | 43.3029 | 54.2892 | 52.419 | 38.9218 | 63.8607 | 52.3172 | 169.8595 | 0.10316 | 0 | 0 | 137.9107 | 48.1826 | 66.484 | 67.8335 | 51.5761 | 86.8233 | 72.5517 | 252.6048 | 0.17277 | 0 | 0
G5b.109 | Total enhancement expenditure |  |  | £m | C | [12 empty] | 0 | 106.8939 | 104.2028 | 105.8094 | 146.8164 | 239.5963 | 310.8198 | 337.1146 | 0 | 0 | 0 | 0 | 118.9397 | 127.6095 | 136.9239 | 194.5494 | 325.7487 | 431.0339 | 501.3364 | 0 | 0 | 0 | [11 empty] | 239.4181 | 132.5946 | 150.6803 | 147.9584 | 205.702 | 225.3964 | 294.612 | 970.1277 | 10.9828 | 0 | 0 | 256.2012 | 147.5367 | 184.527 | 191.4674 | 272.5798 | 306.4429 | 408.5576 | 1442.7152 | 18.3936 | 0 | 0
| Caclulated check on totals | [16 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | [11 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
[18 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | [11 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
Prepared by: ……………………………………………...….. |  |  | Date: 07/10/2024
Checked by: ……………………………………………...….. |  |  | Date: 07/10/2024
Authorised by: …...........……………………...……............ |  |  | Date: 07/10/2024

## G7 - Completion
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2024
SECTION G: INVESTMENT MONITORING
Table G7: Completion Investment
Line Ref | Field Type | Output Description | Output Units | Output Code | Pre-2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Total
[6 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 |  | 2015-21 outputs remaining that were planned to complete in the 2021-27 period - Planned
G7.1 | I/C | Number of water treatment works improved | nr | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G7.2 | I/C | Number of zones made compliant with iron & manganese standards | nr | 2 | 3 | 6 | 6 | 7 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G7.3 | I/C | Improvements to reliability of drinking water (catchments and treatment) | nr | 3 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 5 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G7.4 | I/C | Improvements to reliability of drinking water (networks and storage) | nr | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G7.5 | I/C | Distribution mains cleaned (km) | nr | 5 | 0 | 0 | 2323.845 | 2323.845 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405
G7.6 | I/C | Number of water quality etc studies to inform future periods | nr | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.7 | I/C | 2010-15 outputs planned to complete in the 2015-21 period -DW | nr | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.8 | I/C | Water supply resilience strategy and improvements made | nr | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.9 | I/C | Number of zones with improved security of supply (SOSI) | nr | 9 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G7.10 | I/C | Number of security measures and improvements to the infrastructure of critical reservoirs | nr | 10 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G7.11 | I/C | Number of WWTWs improved to meet UWWTD | nr | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.12 | I/C | Number of waste water networks improved to meet UWWTD | nr | 12 | 0 | 3 | 6 | 6 | 7 | 7 | 7 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G7.13 | I/C | Number of improvements required to meet UWWTD - Glasgow completion | nr | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.14 | I/C | Number of improvements required to meet the Water Framework Directive | nr | 14 | 0 | 0 | 1 | 2 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8
G7.15 | I/C | Studies to inform requirements under the revised Bathing Waters Directive | nr | 15 | 0 | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G7.16 | I/C | Number of environmental studies to inform future periods | nr | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.17 | I/C | Number of improvements required by the Compliance Assessment Scheme; odour reduction and sludge management | nr | 17 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G7.18 | I/C | 2010-15 outputs planned to complete in the 2015-21 period - WW | nr | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | 2015-21 completion outputs remaining - Delayed
G7.19 | I/C | Number of water treatment works improved | nr | 1 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G7.20 | I/C | Number of zones made compliant with iron & manganese standards | nr | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G7.21 | I/C | Improvements to reliability of drinking water (catchments and treatment) | nr | 3 | 3 | 6 | 7 | 8 | 9 | 9 | 9 | 10 | 10 | 11 | 11 | 12 | 13 | 13 | 15 | 16 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18
G7.22 | I/C | Improvements to reliability of drinking water (networks and storage) | nr | 4 | 2 | 11 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 17 | 17 | 17 | 17 | 17 | 17
G7.23 | I/C | Distribution mains cleaned (km) | nr | 5 | 48.4 | 48.4 | 289.38 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633
G7.24 | I/C | Number of water quality etc studies to inform future periods | nr | 6 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G7.25 | I/C | 2010-15 outputs planned to complete in the 2015-21 period -DW | nr | 7 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G7.26 | I/C | Water supply resilience strategy and improvements made | nr | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G7.27 | I/C | Number of zones with improved security of supply (SOSI) | nr | 9 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G7.28 | I/C | Number of security measures and improvements to the infrastructure of critical reservoirs | nr | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.29 | I/C | Number of WWTWs improved to meet UWWTD | nr | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G7.30 | I/C | Number of waste water networks improved to meet UWWTD | nr | 12 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G7.31 | I/C | Number of improvements required to meet UWWTD - Glasgow completion | nr | 13 | 3 | 4 | 9 | 9 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G7.32 | I/C | Number of improvements required to meet the Water Framework Directive | nr | 14 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 10 | 10 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G7.33 | I/C | Studies to inform requirements under the revised Bathing Waters Directive | nr | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.34 | I/C | Number of environmental studies to inform future periods | nr | 16 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G7.35 | I/C | Number of improvements required by the Compliance Assessment Scheme; odour reduction and sludge management | nr | 17 | 2 | 2 | 2 | 2 | 2 | 13 | 13 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 40
G7.36 | I/C | 2010-15 outputs planned to complete in the 2015-21 period - WW | nr | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
3 |  | SR15 Completion projects | Units
G7.37 | I/C | SR10 projects remaining (Q&S3b) | nr |  | 19 | 15 | 10 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G7.38 | I/C | SR15 projects remaining (Q&SIV) | nr |  | 124 | 94 | 73 | 67 | 55 | 52 | 48 | 40 | 35 | 32 | 29 | 28 | 25 | 22 | 18 | 13 | 10 | 7 | 7 | 4 | 1 | 1 | 1 | 1 | 1
G7.39 | I/C | 2015-21 projects remaining that were planned to complete in the 2021-27 period - Planned | nr |  | 57 | 49 | 33 | 30 | 22 | 21 | 19 | 16 | 14 | 13 | 11 | 11 | 9 | 7 | 6 | 4 | 4 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0
G7.40 | I/C | 2015-21 completion projects remaining - Delayed | nr |  | 86 | 60 | 50 | 45 | 39 | 37 | 35 | 30 | 27 | 25 | 24 | 23 | 22 | 20 | 15 | 12 | 8 | 7 | 6 | 4 | 2 | 2 | 2 | 2 | 2
Prepared by: …………………………………………….. |  |  | Date: 07/10/2024
Checked by: …………………………………………….. |  |  | Date: 07/10/2024
Authorised by: …...........……………………...……............ |  |  | Date: 07/10/2024

## G8a - IPOD by MO
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2024
SECTION G: INVESTMENT MONITORING
Table G8a: Summary IPOD by Ministerial Objective
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Line Ref | Ministerial Objective | Type | Gate | Pre 21-22 | 2021-22-Q1 | 2021-22-Q2 | 2021-22-Q3 | 2021-22-Q4 | 2021-22-Q1 | 2022-23-Q2 | 2022-23-Q3 | 2022-23-Q4 | 2023-24-Q1 | 2023-24-Q2 | 2023-24-Q3 | 2023-24-Q4 | 2024-25-Q1 | 2024-25-Q2 | 2024-25-Q3 | 2024-25-Q4 | 2025-26-Q1 | 2025-26-Q2 | 2025-26-Q3 | 2025-26-Q4 | 2026-27-Q1 | 2026-27-Q2 | 2026-27-Q3 | 2026-27-Q4 | Post 2026-27
G8a.01 | Standards of Service | Committed List Baseline | SOS - Start On Site | 0 | 13 | 23 | 38 | 46 | 58 | 74 | 89 | 107 | 124 | 144 | 168 | 184 | 198 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205
G8a.02 |  |  | G100 - Acceptance | 0 | 47 | 90 | 121 | 147 | 167 | 186 | 201 | 210 | 218 | 234 | 247 | 267 | 284 | 301 | 321 | 337 | 351 | 366 | 370 | 378 | 381 | 382 | 382 | 384 | 386
G8a.03 |  |  | G110 - Financial Closure | 0 | 4 | 4 | 33 | 69 | 105 | 141 | 174 | 195 | 215 | 231 | 239 | 251 | 265 | 280 | 296 | 317 | 332 | 351 | 366 | 381 | 396 | 400 | 408 | 410 | 415
G8a.04 |  |  | Total | 0 | 64 | 117 | 192 | 262 | 330 | 401 | 464 | 512 | 557 | 609 | 654 | 702 | 747 | 786 | 822 | 859 | 888 | 922 | 941 | 964 | 982 | 987 | 995 | 999 | 1006
G8a.05 |  | Forecast Actual | SOS - Start On Site | 8 | 13 | 23 | 37 | 52 | 62 | 77 | 90 | 115 | 132 | 152 | 172 | 188 | 198 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205
G8a.06 |  |  | G100 - Acceptance | 13 | 38 | 71 | 96 | 124 | 131 | 146 | 165 | 197 | 207 | 222 | 239 | 261 | 276 | 298 | 323 | 336 | 358 | 364 | 377 | 380 | 380 | 383 | 384 | 385 | 386
G8a.07 |  |  | G110 - Financial Closure | 0 | 4 | 16 | 46 | 104 | 117 | 131 | 149 | 197 | 202 | 217 | 229 | 266 | 274 | 295 | 310 | 334 | 356 | 373 | 389 | 398 | 407 | 408 | 411 | 413 | 415
G8a.08 |  |  | Total | 21 | 55 | 110 | 179 | 280 | 310 | 354 | 404 | 509 | 541 | 591 | 640 | 715 | 748 | 798 | 838 | 875 | 919 | 942 | 971 | 983 | 992 | 996 | 1000 | 1003 | 1006
G8a.09 | Asset Maintenance | Committed List Baseline | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.10 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.11 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.12 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.13 |  | Forecast Actual | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.14 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.15 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.16 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.17 | Supporting Sustainable Economic Growth | Committed List Baseline | SOS - Start On Site | 0 | 2 | 4 | 5 | 6 | 7 | 8 | 11 | 13 | 14 | 17 | 18 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G8a.18 |  |  | G100 - Acceptance | 0 | 4 | 8 | 11 | 19 | 22 | 25 | 25 | 27 | 28 | 31 | 32 | 33 | 36 | 40 | 41 | 42 | 42 | 43 | 44 | 44 | 45 | 45 | 46 | 46 | 46
G8a.19 |  |  | G110 - Financial Closure | 0 | 1 | 1 | 2 | 6 | 8 | 11 | 17 | 21 | 25 | 25 | 27 | 28 | 32 | 34 | 35 | 38 | 42 | 43 | 44 | 44 | 45 | 46 | 46 | 47 | 48
G8a.20 |  |  | Total | 0 | 7 | 13 | 18 | 31 | 37 | 44 | 53 | 61 | 67 | 73 | 77 | 80 | 88 | 94 | 96 | 100 | 104 | 106 | 108 | 108 | 110 | 111 | 112 | 113 | 114
G8a.21 |  | Forecast Actual | SOS - Start On Site | 0 | 2 | 3 | 4 | 6 | 8 | 10 | 12 | 13 | 15 | 17 | 18 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G8a.22 |  |  | G100 - Acceptance | 2 | 3 | 5 | 6 | 12 | 13 | 14 | 16 | 19 | 21 | 24 | 25 | 31 | 34 | 36 | 39 | 40 | 42 | 43 | 44 | 44 | 44 | 46 | 46 | 46 | 46
G8a.23 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 3 | 8 | 8 | 10 | 13 | 17 | 18 | 20 | 23 | 27 | 29 | 34 | 37 | 39 | 42 | 42 | 43 | 44 | 45 | 46 | 46 | 47 | 48
G8a.24 |  |  | Total | 2 | 5 | 8 | 13 | 26 | 29 | 34 | 41 | 49 | 54 | 61 | 66 | 78 | 83 | 90 | 96 | 99 | 104 | 105 | 107 | 108 | 109 | 112 | 112 | 113 | 114
G8a.25 | Circular Economy | Committed List Baseline | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.26 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.27 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.28 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.29 |  | Forecast Actual | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.30 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.31 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.32 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.33 | Drinking Water | Committed List Baseline | SOS - Start On Site | 0 | 1 | 1 | 1 | 1 | 4 | 5 | 6 | 11 | 13 | 15 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G8a.34 |  |  | G100 - Acceptance | 0 | 0 | 1 | 2 | 2 | 4 | 5 | 7 | 9 | 12 | 12 | 14 | 15 | 17 | 20 | 21 | 22 | 22 | 23 | 23 | 24 | 24 | 24 | 24 | 24 | 25
G8a.35 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 3 | 4 | 8 | 11 | 13 | 13 | 15 | 17 | 18 | 21 | 22 | 23 | 23 | 24 | 24 | 25 | 25 | 26
G8a.36 |  |  | Total | 0 | 1 | 2 | 3 | 4 | 10 | 13 | 16 | 23 | 29 | 35 | 41 | 45 | 47 | 52 | 55 | 57 | 60 | 62 | 63 | 64 | 65 | 65 | 66 | 66 | 68
G8a.37 |  | Forecast Actual | SOS - Start On Site | 0 | 1 | 2 | 2 | 3 | 4 | 5 | 7 | 11 | 13 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G8a.38 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 4 | 5 | 8 | 10 | 13 | 16 | 19 | 22 | 22 | 23 | 23 | 24 | 24 | 24 | 24 | 24 | 24 | 25
G8a.39 |  |  | G110 - Financial Closure | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 8 | 10 | 11 | 14 | 19 | 21 | 23 | 23 | 24 | 24 | 25 | 25 | 25 | 25 | 26
G8a.40 |  |  | Total | 0 | 1 | 3 | 3 | 6 | 7 | 8 | 10 | 17 | 20 | 27 | 34 | 40 | 44 | 50 | 58 | 60 | 63 | 63 | 65 | 65 | 66 | 66 | 66 | 66 | 68
G8a.41 | Environment | Committed List Baseline | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G8a.42 |  |  | G100 - Acceptance | 0 | 1 | 7 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G8a.43 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 2 | 3 | 9 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14
G8a.44 |  |  | Total | 0 | 1 | 7 | 10 | 11 | 18 | 19 | 19 | 21 | 21 | 22 | 23 | 24 | 24 | 26 | 26 | 26 | 27 | 28 | 28 | 28 | 29 | 29 | 29 | 29 | 29
G8a.45 |  | Forecast Actual | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G8a.46 |  |  | G100 - Acceptance | 1 | 1 | 3 | 3 | 5 | 6 | 6 | 8 | 8 | 8 | 8 | 9 | 10 | 10 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G8a.47 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 1 | 6 | 7 | 7 | 8 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G8a.48 |  |  | Total | 1 | 1 | 3 | 4 | 11 | 13 | 13 | 16 | 19 | 20 | 20 | 21 | 25 | 25 | 26 | 27 | 28 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29
G8a.49 | Flooding and Surface Water Management | Committed List Baseline | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.50 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.51 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.52 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.53 |  | Forecast Actual | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.54 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.55 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.56 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.57 | Security & Resilience | Committed List Baseline | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 4 | 4 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G8a.58 |  |  | G100 - Acceptance | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 7 | 7 | 8 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 12 | 12
G8a.59 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 7 | 7 | 8 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 12
G8a.60 |  |  | Total | 0 | 0 | 5 | 5 | 5 | 10 | 11 | 11 | 13 | 14 | 14 | 18 | 19 | 22 | 23 | 24 | 26 | 27 | 27 | 28 | 28 | 29 | 29 | 29 | 30 | 31
G8a.61 |  | Forecast Actual | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 4 | 4 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G8a.62 |  |  | G100 - Acceptance | 0 | 0 | 0 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 7 | 8 | 8 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12
G8a.63 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 4 | 5 | 5 | 5 | 5 | 5 | 7 | 7 | 8 | 8 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 12 | 12 | 12
G8a.64 |  |  | Total | 0 | 0 | 0 | 3 | 8 | 10 | 10 | 11 | 13 | 14 | 18 | 21 | 22 | 24 | 26 | 27 | 27 | 28 | 28 | 29 | 29 | 29 | 30 | 31 | 31 | 31
G8a.65 | Climate Change, Adaptation and Mitigation | Committed List Baseline | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 5 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G8a.66 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 3 | 3 | 4 | 5 | 6 | 7 | 7 | 7 | 7 | 7 | 7
G8a.67 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 3 | 3 | 4 | 6 | 6 | 7 | 7 | 7
G8a.68 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 6 | 7 | 10 | 11 | 11 | 13 | 15 | 16 | 18 | 20 | 20 | 21 | 21 | 21
G8a.69 |  | Forecast Actual | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 3 | 5 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G8a.70 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 4 | 5 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G8a.71 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 3 | 4 | 5 | 6 | 6 | 7 | 7 | 7 | 7 | 7
G8a.72 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 3 | 7 | 9 | 12 | 13 | 14 | 16 | 18 | 20 | 20 | 21 | 21 | 21 | 21 | 21
G8a.73 | Private Finance Initiative Funded Projects | Committed List Baseline | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.74 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.75 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.76 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.77 |  | Forecast Actual | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.78 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.79 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.80 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G8a.81 | Long Term Water Sector Vision | Committed List Baseline | SOS - Start On Site | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G8a.82 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
G8a.83 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
G8a.84 |  |  | Total | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 6
G8a.85 |  | Forecast Actual | SOS - Start On Site | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G8a.86 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
G8a.87 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
G8a.88 |  |  | Total | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 6
G8a.89 | Total | Committed List Baseline | SOS - Start On Site | 0 | 17 | 29 | 45 | 54 | 70 | 89 | 108 | 137 | 158 | 186 | 215 | 236 | 253 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261
G8a.90 |  |  | G100 - Acceptance | 0 | 52 | 111 | 147 | 181 | 207 | 230 | 247 | 260 | 272 | 291 | 311 | 333 | 356 | 383 | 407 | 426 | 441 | 460 | 467 | 477 | 481 | 482 | 483 | 486 | 490
G8a.91 |  |  | G110 - Financial Closure | 0 | 5 | 5 | 37 | 79 | 129 | 170 | 209 | 235 | 260 | 280 | 293 | 309 | 328 | 349 | 369 | 395 | 420 | 443 | 460 | 476 | 497 | 502 | 512 | 515 | 524
G8a.92 |  |  | Total | 0 | 74 | 145 | 229 | 314 | 406 | 489 | 564 | 632 | 690 | 757 | 819 | 878 | 937 | 993 | 1037 | 1082 | 1122 | 1164 | 1188 | 1214 | 1239 | 1245 | 1256 | 1262 | 1275
G8a.93 |  | Forecast Actual | SOS - Start On Site | 8 | 17 | 29 | 44 | 62 | 75 | 93 | 112 | 145 | 168 | 195 | 219 | 241 | 253 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261 | 261
G8a.94 |  |  | G100 - Acceptance | 16 | 42 | 79 | 108 | 146 | 156 | 172 | 195 | 233 | 246 | 269 | 291 | 324 | 347 | 378 | 409 | 425 | 452 | 460 | 476 | 479 | 479 | 485 | 486 | 487 | 490
G8a.95 |  |  | G110 - Financial Closure | 0 | 4 | 17 | 51 | 124 | 139 | 155 | 177 | 231 | 237 | 257 | 277 | 324 | 335 | 366 | 392 | 421 | 450 | 468 | 488 | 498 | 510 | 512 | 516 | 519 | 524
G8a.96 |  |  | Total | 24 | 63 | 125 | 203 | 332 | 370 | 420 | 484 | 609 | 651 | 721 | 787 | 889 | 935 | 1005 | 1062 | 1107 | 1163 | 1189 | 1225 | 1238 | 1250 | 1258 | 1263 | 1267 | 1275
Prepared by: …………………………………………….. |  | 3: Date: 07/10/2024
Checked by: …………………………………………….. |  | 3: Date: 07/10/2024
Authorised by: …...........……………………...……............ |  | 3: Date: 07/10/2024

## G8b IPOD detail
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2024
SECTION G: INVESTMENT MONITORING
Table G8b: Detail IPOD
1 | 2 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
GATE ID | PROJECT ID | PORTFOLIO | GATE | GATE NAME | BASELINE DATE | FORECAST DATE | BASELINE MONTH | FORECAST MONTH | BASELINE QUARTER | FORECAST QUARTER | MINISTERIAL OBJECTIVE
SOS403716 | 403716 | Wastewater | SOS | Start on Site | 2022-07-11 | 2022-07-11 | 2022_23_P04 | 2022_23_P04 | 2022_23_Q2 | 2022_23_Q2 | Standards of service
SOS404026 | 404026 | Wastewater | SOS | Start on Site | 2021-08-09 | 2022-03-31 | 2021_22_P05 | 2021_22_P12 | 2021_22_Q2 | 2021_22_Q4 | Standards of service
SOS500046 | 500046 | Water | SOS | Start on Site | 2023-05-11 | 2021-12-21 | 2023_24_P02 | 2021_22_P09 | 2023_24_Q1 | 2021_22_Q3 | Standards of service
SOS403995 | 403995 | Water | SOS | Start on Site | 2022-03-15 | 2022-03-15 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
SOS403967 | 403967 | Wastewater | SOS | Start on Site | 2021-08-09 | 2021-07-29 | 2021_22_P05 | 2021_22_P04 | 2021_22_Q2 | 2021_22_Q2 | Supporting Sustainable Economic Growth
SOS403782 | 403782 | Wastewater | SOS | Start on Site | 2021-12-20 | 2021-12-06 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3 | Supporting Sustainable Economic Growth
SOS403923 | 403923 | Wastewater | SOS | Start on Site | 2021-04-06 | 2021-06-15 | 2021_22_P01 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1 | Standards of service
SOS404132 | 404132 | Water | SOS | Start on Site | 2023-05-23 | 2023-03-06 | 2023_24_P02 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4 | Standards of service
SOS500681 | 500681 | Wastewater | SOS | Start on Site | 2021-08-03 | 2021-09-27 | 2021_22_P05 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
SOS500229 | 500229 | Wastewater | SOS | Start on Site | 2021-07-30 | 2022-03-31 | 2021_22_P04 | 2021_22_P12 | 2021_22_Q2 | 2021_22_Q4 | Supporting Sustainable Economic Growth
SOS500576 | 500576 | Wastewater | SOS | Start on Site | 2023-03-31 | 2023-03-31 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4 | Standards of service
SOS500892 | 500892 | Water | SOS | Start on Site | 2021-06-02 | 2021-04-26 | 2021_22_P03 | 2021_22_P01 | 2021_22_Q1 | 2021_22_Q1 | Supporting Sustainable Economic Growth
SOS500682 | 500682 | Wastewater | SOS | Start on Site | 2021-09-20 | 2021-09-20 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
SOS500755 | 500755 | Water | SOS | Start on Site | 2021-09-01 | 2021-08-02 | 2021_22_P06 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
SOS500661 | 500661 | Wastewater | SOS | Start on Site | 2021-08-09 | 2021-08-20 | 2021_22_P05 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
SOS501211 | 501211 | Water | SOS | Start on Site | 2024-02-05 | 2023-12-29 | 2023_24_P11 | 2023_24_P09 | 2023_24_Q4 | 2023_24_Q3 | Standards of service
SOS500654 | 500654 | Wastewater | SOS | Start on Site | 2021-05-10 | 2021-09-30 | 2021_22_P02 | 2021_22_P06 | 2021_22_Q1 | 2021_22_Q2 | Standards of service
SOS500729 | 500729 | Wastewater | SOS | Start on Site | 2023-09-25 | 2023-03-28 | 2023_24_P06 | 2022_23_P12 | 2023_24_Q2 | 2022_23_Q4 | Standards of service
SOS500724 | 500724 | Wastewater | SOS | Start on Site | 2023-02-03 | 2023-02-20 | 2022_23_P11 | 2022_23_P11 | 2022_23_Q4 | 2022_23_Q4 | Supporting Sustainable Economic Growth
SOS500731 | 500731 | Wastewater | SOS | Start on Site | 2022-12-05 | 2022-05-31 | 2022_23_P09 | 2022_23_P02 | 2022_23_Q3 | 2022_23_Q1 | Supporting Sustainable Economic Growth
SOS501017 | 501017 | Wastewater | SOS | Start on Site | 2022-08-22 | 2022-08-22 | 2022_23_P05 | 2022_23_P05 | 2022_23_Q2 | 2022_23_Q2 | Standards of service
SOS500893 | 500893 | Water | SOS | Start on Site | 2022-09-26 | 2022-10-17 | 2022_23_P06 | 2022_23_P07 | 2022_23_Q2 | 2022_23_Q3 | Standards of service
SOS501512 | 501512 | Wastewater | SOS | Start on Site | 2022-10-11 | 2022-12-05 | 2022_23_P07 | 2022_23_P09 | 2022_23_Q3 | 2022_23_Q3 | Standards of service
SOS501379 | 501379 | Water | SOS | Start on Site | 2021-04-01 | 2021-03-22 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4 | Standards of service
SOS501670 | 501670 | Water | SOS | Start on Site | 2023-07-03 | 2023-07-03 | 2023_24_P04 | 2023_24_P04 | 2023_24_Q2 | 2023_24_Q2 | Standards of service
SOS501731 | 501731 | Water | SOS | Start on Site | 2022-09-01 | 2022-06-30 | 2022_23_P06 | 2022_23_P03 | 2022_23_Q2 | 2022_23_Q1 | Standards of service
SOS501703 | 501703 | Wastewater | SOS | Start on Site | 2023-02-14 | 2023-02-06 | 2022_23_P11 | 2022_23_P11 | 2022_23_Q4 | 2022_23_Q4 | Standards of service
SOS502243 | 502243 | Water | SOS | Start on Site | 2022-09-01 | 2022-08-15 | 2022_23_P06 | 2022_23_P05 | 2022_23_Q2 | 2022_23_Q2 | Standards of service
SOS502332 | 502332 | Wastewater | SOS | Start on Site | 2022-10-06 | 2022-10-19 | 2022_23_P07 | 2022_23_P07 | 2022_23_Q3 | 2022_23_Q3 | Supporting Sustainable Economic Growth
SOS502212 | 502212 | Wastewater | SOS | Start on Site | 2022-04-04 | 2022-03-30 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4 | Standards of service
SOS502220 | 502220 | Wastewater | SOS | Start on Site | 2023-07-17 | 2023-04-01 | 2023_24_P04 | 2023_24_P01 | 2023_24_Q2 | 2023_24_Q1 | Standards of service
SOS502282 | 502282 | Water | SOS | Start on Site | 2022-09-12 | 2022-06-06 | 2022_23_P06 | 2022_23_P03 | 2022_23_Q2 | 2022_23_Q1 | Standards of service
SOS502425 | 502425 | Wastewater | SOS | Start on Site | 2023-12-04 | 2023-04-01 | 2023_24_P09 | 2023_24_P01 | 2023_24_Q3 | 2023_24_Q1 | Standards of service
SOS502375 | 502375 | Wastewater | SOS | Start on Site | 2022-09-22 | 2022-06-06 | 2022_23_P06 | 2022_23_P03 | 2022_23_Q2 | 2022_23_Q1 | Standards of service
SOS502342 | 502342 | Wastewater | SOS | Start on Site | 2021-07-05 | 2021-07-05 | 2021_22_P04 | 2021_22_P04 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
SOS502895 | 502895 | Wastewater | SOS | Start on Site | 2021-11-18 | 2021-11-18 | 2021_22_P08 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
SOS502868 | 502868 | Wastewater | SOS | Start on Site | 2024-02-20 | 2024-02-20 | 2023_24_P11 | 2023_24_P11 | 2023_24_Q4 | 2023_24_Q4 | Standards of service
SOS502355 | 502355 | Wastewater | SOS | Start on Site | 2023-11-24 | 2023-11-24 | 2023_24_P08 | 2023_24_P08 | 2023_24_Q3 | 2023_24_Q3 | Standards of service
SOS502652 | 502652 | Water | SOS | Start on Site | 2022-02-21 | 2022-02-21 | 2021_22_P11 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
SOS502369 | 502369 | Water | SOS | Start on Site | 2023-09-04 | 2023-09-04 | 2023_24_P06 | 2023_24_P06 | 2023_24_Q2 | 2023_24_Q2 | Drinking Water
SOS502827 | 502827 | Wastewater | SOS | Start on Site | 2021-05-18 | 2021-05-31 | 2021_22_P02 | 2021_22_P02 | 2021_22_Q1 | 2021_22_Q1 | Supporting Sustainable Economic Growth
SOS502766 | 502766 | Wastewater | SOS | Start on Site | 2023-06-30 | 2023-06-30 | 2023_24_P03 | 2023_24_P03 | 2023_24_Q1 | 2023_24_Q1 | Supporting Sustainable Economic Growth
SOS502383 | 502383 | Water | SOS | Start on Site | 2021-04-14 | 2021-03-08 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4 | Standards of service
SOS502958 | 502958 | Wastewater | SOS | Start on Site | 2021-10-18 | 2021-10-18 | 2021_22_P07 | 2021_22_P07 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
SOS502791 | 502791 | Water | SOS | Start on Site | 2023-09-04 | 2023-07-31 | 2023_24_P06 | 2023_24_P04 | 2023_24_Q2 | 2023_24_Q2 | Standards of service
SOS502563 | 502563 | Water | SOS | Start on Site | 2021-07-20 | 2021-07-05 | 2021_22_P04 | 2021_22_P04 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
SOS502859 | 502859 | Water | SOS | Start on Site | 2024-02-05 | 2024-02-05 | 2023_24_P11 | 2023_24_P11 | 2023_24_Q4 | 2023_24_Q4 | Standards of service
SOS502358 | 502358 | Water | SOS | Start on Site | 2022-08-29 | 2022-09-30 | 2022_23_P05 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2 | Supporting Sustainable Economic Growth
SOS502883 | 502883 | Wastewater | SOS | Start on Site | 2024-05-24 | 2024-05-24 | 2024_25_P02 | 2024_25_P02 | 2024_25_Q1 | 2024_25_Q1 | Standards of service
SOS502689 | 502689 | Wastewater | SOS | Start on Site | 2024-07-22 | 2024-07-22 | 2024_25_P04 | 2024_25_P04 | 2024_25_Q2 | 2024_25_Q2 | Standards of service
SOS502955 | 502955 | Wastewater | SOS | Start on Site | 2023-07-10 | 2023-01-09 | 2023_24_P04 | 2022_23_P10 | 2023_24_Q2 | 2022_23_Q4 | Standards of service
SOS502853 | 502853 | Water | SOS | Start on Site | 2021-10-22 | 2021-10-22 | 2021_22_P07 | 2021_22_P07 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
SOS503050 | 503050 | Water | SOS | Start on Site | 2021-08-04 | 2021-08-30 | 2021_22_P05 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
SOS502746 | 502746 | Wastewater | SOS | Start on Site | 2023-06-19 | 2023-03-13 | 2023_24_P03 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4 | Standards of service
SOS502877 | 502877 | Wastewater | SOS | Start on Site | 2024-02-12 | 2024-02-26 | 2023_24_P11 | 2023_24_P11 | 2023_24_Q4 | 2023_24_Q4 | Standards of service
SOS502857 | 502857 | Water | SOS | Start on Site | 2022-05-19 | 2022-05-19 | 2022_23_P02 | 2022_23_P02 | 2022_23_Q1 | 2022_23_Q1 | Standards of service
SOS503132 | 503132 | Wastewater | SOS | Start on Site | 2024-07-15 | 2024-08-19 | 2024_25_P04 | 2024_25_P05 | 2024_25_Q2 | 2024_25_Q2 | Standards of service
SOS503234 | 503234 | Water | SOS | Start on Site | 2021-06-21 | 2021-06-01 | 2021_22_P03 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1 | Standards of service
SOS503162 | 503162 | Water | SOS | Start on Site | 2021-10-05 | 2021-12-14 | 2021_22_P07 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
SOS503056 | 503056 | Water | SOS | Start on Site | 2023-10-02 | 2023-09-12 | 2023_24_P07 | 2023_24_P06 | 2023_24_Q3 | 2023_24_Q2 | Standards of service
SOS503092 | 503092 | Water | SOS | Start on Site | 2023-07-03 | 2023-06-12 | 2023_24_P04 | 2023_24_P03 | 2023_24_Q2 | 2023_24_Q1 | Standards of service
SOS503480 | 503480 | Water | SOS | Start on Site | 2023-07-10 | 2023-07-10 | 2023_24_P04 | 2023_24_P04 | 2023_24_Q2 | 2023_24_Q2 | Standards of service
SOS503230 | 503230 | Wastewater | SOS | Start on Site | 2022-04-11 | 2022-03-31 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4 | Standards of service
SOS503336 | 503336 | Water | SOS | Start on Site | 2021-08-02 | 2021-08-04 | 2021_22_P05 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
SOS503525 | 503525 | CE&FS | SOS | Start on Site | 2024-07-09 | 2024-07-09 | 2024_25_P04 | 2024_25_P04 | 2024_25_Q2 | 2024_25_Q2 | Standards of service
SOS503441 | 503441 | Wastewater | SOS | Start on Site | 2022-02-28 | 2022-03-28 | 2021_22_P11 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4 | Supporting Sustainable Economic Growth
SOS503408 | 503408 | Water | SOS | Start on Site | 2022-02-28 | 2022-02-28 | 2021_22_P11 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
SOS503238 | 503238 | Water | SOS | Start on Site | 2024-06-17 | 2024-06-17 | 2024_25_P03 | 2024_25_P03 | 2024_25_Q1 | 2024_25_Q1 | Standards of service
SOS503412 | 503412 | Water | SOS | Start on Site | 2021-04-21 | 2021-03-23 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4 | Standards of service
SOS503413 | 503413 | Water | SOS | Start on Site | 2021-04-21 | 2021-03-24 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4 | Standards of service
SOS503571 | 503571 | Wastewater | SOS | Start on Site | 2021-06-10 | 2021-06-10 | 2021_22_P03 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1 | Standards of service
SOS503421 | 503421 | Water | SOS | Start on Site | 2022-04-18 | 2021-09-13 | 2022_23_P01 | 2021_22_P06 | 2022_23_Q1 | 2021_22_Q2 | Drinking Water
SOS503594 | 503594 | Wastewater | SOS | Start on Site | 2022-11-22 | 2022-08-30 | 2022_23_P08 | 2022_23_P05 | 2022_23_Q3 | 2022_23_Q2 | Standards of service
SOS503628 | 503628 | Water | SOS | Start on Site | 2022-11-14 | 2022-11-21 | 2022_23_P08 | 2022_23_P08 | 2022_23_Q3 | 2022_23_Q3 | Drinking Water
SOS503638 | 503638 | Wastewater | SOS | Start on Site | 2023-03-02 | 2023-03-27 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4 | Standards of service
SOS503613 | 503613 | Water | SOS | Start on Site | 2023-01-09 | 2023-01-09 | 2022_23_P10 | 2022_23_P10 | 2022_23_Q4 | 2022_23_Q4 | Standards of service
SOS503656 | 503656 | Wastewater | SOS | Start on Site | 2024-02-02 | 2023-12-04 | 2023_24_P11 | 2023_24_P09 | 2023_24_Q4 | 2023_24_Q3 | Standards of service
SOS503678 | 503678 | Water | SOS | Start on Site | 2022-03-11 | 2022-03-28 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
SOS503680 | 503680 | Water | SOS | Start on Site | 2023-06-27 | 2023-05-31 | 2023_24_P03 | 2023_24_P02 | 2023_24_Q1 | 2023_24_Q1 | Standards of service
SOS503681 | 503681 | Water | SOS | Start on Site | 2024-06-19 | 2024-06-19 | 2024_25_P03 | 2024_25_P03 | 2024_25_Q1 | 2024_25_Q1 | Standards of service
SOS503686 | 503686 | Water | SOS | Start on Site | 2022-04-04 | 2022-03-11 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4 | Standards of service
SOS503714 | 503714 | Water | SOS | Start on Site | 2022-12-06 | 2023-02-16 | 2022_23_P09 | 2022_23_P11 | 2022_23_Q3 | 2022_23_Q4 | Standards of service
SOS503716 | 503716 | Water | SOS | Start on Site | 2021-06-14 | 2021-05-11 | 2021_22_P03 | 2021_22_P02 | 2021_22_Q1 | 2021_22_Q1 | Standards of service
SOS503730 | 503730 | Water | SOS | Start on Site | 2022-11-16 | 2022-02-14 | 2022_23_P08 | 2021_22_P11 | 2022_23_Q3 | 2021_22_Q4 | Standards of service
SOS503731 | 503731 | Water | SOS | Start on Site | 2021-04-01 | 2021-03-31 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4 | Standards of service
SOS503732 | 503732 | Water | SOS | Start on Site | 2022-12-12 | 2022-12-21 | 2022_23_P09 | 2022_23_P09 | 2022_23_Q3 | 2022_23_Q3 | Standards of service
SOS503753 | 503753 | Wastewater | SOS | Start on Site | 2024-05-27 | 2024-05-27 | 2024_25_P02 | 2024_25_P02 | 2024_25_Q1 | 2024_25_Q1 | Standards of service
SOS503761 | 503761 | Water | SOS | Start on Site | 2021-05-25 | 2021-06-22 | 2021_22_P02 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1 | Drinking Water
SOS503699 | 503699 | Water | SOS | Start on Site | 2024-03-28 | 2024-03-29 | 2023_24_P12 | 2023_24_P12 | 2023_24_Q4 | 2023_24_Q4 | Standards of service
SOS504068 | 504068 | Water | SOS | Start on Site | 2023-11-10 | 2023-11-10 | 2023_24_P08 | 2023_24_P08 | 2023_24_Q3 | 2023_24_Q3 | Standards of service
SOS504203 | 504203 | Water | SOS | Start on Site | 2024-06-24 | 2024-06-24 | 2024_25_P03 | 2024_25_P03 | 2024_25_Q1 | 2024_25_Q1 | Standards of service
SOS504391 | 504391 | Water | SOS | Start on Site | 2023-10-11 | 2023-09-29 | 2023_24_P07 | 2023_24_P06 | 2023_24_Q3 | 2023_24_Q2 | Drinking Water
SOS504465 | 504465 | Water | SOS | Start on Site | 2023-06-02 | 2023-06-02 | 2023_24_P03 | 2023_24_P03 | 2023_24_Q1 | 2023_24_Q1 | Standards of service
SOS504995 | 504995 | Water | SOS | Start on Site | 2022-09-05 | 2022-08-22 | 2022_23_P06 | 2022_23_P05 | 2022_23_Q2 | 2022_23_Q2 | Standards of service
SOS505053 | 505053 | Wastewater | SOS | Start on Site | 2022-05-23 | 2022-05-23 | 2022_23_P02 | 2022_23_P02 | 2022_23_Q1 | 2022_23_Q1 | Standards of service
SOS505339 | 505339 | Wastewater | SOS | Start on Site | 2024-04-09 | 2024-01-15 | 2024_25_P01 | 2023_24_P10 | 2024_25_Q1 | 2023_24_Q4 | Standards of service
SOS505447 | 505447 | Water | SOS | Start on Site | 2021-12-01 | 2021-11-29 | 2021_22_P09 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
SOS505504 | 505504 | Water | SOS | Start on Site | 2021-11-29 | 2022-08-01 | 2021_22_P08 | 2022_23_P05 | 2021_22_Q3 | 2022_23_Q2 | Standards of service
SOS505687 | 505687 | Wastewater | SOS | Start on Site | 2023-02-15 | 2022-10-12 | 2022_23_P11 | 2022_23_P07 | 2022_23_Q4 | 2022_23_Q3 | Supporting Sustainable Economic Growth
SOS505693 | 505693 | Water | SOS | Start on Site | 2021-11-08 | 2021-11-22 | 2021_22_P08 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
SOS505641 | 505641 | Wastewater | SOS | Start on Site | 2022-01-06 | 2022-01-06 | 2021_22_P10 | 2021_22_P10 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
SOS505927 | 505927 | Water | SOS | Start on Site | 2022-12-19 | 2022-12-14 | 2022_23_P09 | 2022_23_P09 | 2022_23_Q3 | 2022_23_Q3 | Standards of service
SOS505949 | 505949 | Wastewater | SOS | Start on Site | 2023-02-15 | 2022-11-14 | 2022_23_P11 | 2022_23_P08 | 2022_23_Q4 | 2022_23_Q3 | Standards of service
SOS506029 | 506029 | Water | SOS | Start on Site | 2022-08-31 | 2022-08-22 | 2022_23_P05 | 2022_23_P05 | 2022_23_Q2 | 2022_23_Q2 | Standards of service
SOS506032 | 506032 | Water | SOS | Start on Site | 2022-09-30 | 2022-09-05 | 2022_23_P06 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2 | Standards of service
SOS506149 | 506149 | Water | SOS | Start on Site | 2022-05-23 | 2022-06-27 | 2022_23_P02 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1 | Standards of service
SOS506151 | 506151 | Water | SOS | Start on Site | 2023-03-06 | 2023-03-05 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4 | Standards of service
SOS506130 | 506130 | Water | SOS | Start on Site | 2023-09-11 | 2023-08-31 | 2023_24_P06 | 2023_24_P05 | 2023_24_Q2 | 2023_24_Q2 | Standards of service
SOS506234 | 506234 | Water | SOS | Start on Site | 2021-10-26 | 2021-10-26 | 2021_22_P07 | 2021_22_P07 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
SOS506186 | 506186 | Water | SOS | Start on Site | 2024-01-08 | 2024-01-08 | 2023_24_P10 | 2023_24_P10 | 2023_24_Q4 | 2023_24_Q4 | Standards of service
SOS506232 | 506232 | Water | SOS | Start on Site | 2021-10-11 | 2021-10-11 | 2021_22_P07 | 2021_22_P07 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
SOS506228 | 506228 | Water | SOS | Start on Site | 2021-10-11 | 2021-11-22 | 2021_22_P07 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
SOS506231 | 506231 | Water | SOS | Start on Site | 2023-01-16 | 2023-01-09 | 2022_23_P10 | 2022_23_P10 | 2022_23_Q4 | 2022_23_Q4 | Standards of service
SOS506275 | 506275 | Water | SOS | Start on Site | 2022-06-27 | 2022-06-27 | 2022_23_P03 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1 | Standards of service
SOS506271 | 506271 | Water | SOS | Start on Site | 2022-11-01 | 2022-11-28 | 2022_23_P08 | 2022_23_P08 | 2022_23_Q3 | 2022_23_Q3 | Standards of service
SOS506422 | 506422 | Support Services | SOS | Start on Site | 2022-09-26 | 2022-10-01 | 2022_23_P06 | 2022_23_P07 | 2022_23_Q2 | 2022_23_Q3 | Security & Resilience
SOS506586 | 506586 | Wastewater | SOS | Start on Site | 2024-02-05 | 2024-03-25 | 2023_24_P11 | 2023_24_P12 | 2023_24_Q4 | 2023_24_Q4 | Environment
SOS506608 | 506608 | Water | SOS | Start on Site | 2022-06-10 | 2022-06-20 | 2022_23_P03 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1 | Standards of service
SOS506618 | 506618 | Water | SOS | Start on Site | 2022-07-12 | 2022-07-26 | 2022_23_P04 | 2022_23_P04 | 2022_23_Q2 | 2022_23_Q2 | Standards of service
SOS506684 | 506684 | Water | SOS | Start on Site | 2021-04-05 | 2021-03-23 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4 | Standards of service
SOS506779 | 506779 | Water | SOS | Start on Site | 2021-10-11 | 2021-11-01 | 2021_22_P07 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
SOS507057 | 507057 | Water | SOS | Start on Site | 2022-05-30 | 2022-05-23 | 2022_23_P02 | 2022_23_P02 | 2022_23_Q1 | 2022_23_Q1 | Standards of service
SOS507186 | 507186 | Water | SOS | Start on Site |  | 2022-01-24 | 2021_22_P10 | 2021_22_P10 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
SOS507189 | 507189 | Water | SOS | Start on Site | 2022-03-30 | 2022-03-31 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
SOS507209 | 507209 | Wastewater | SOS | Start on Site | 2024-01-08 | 2023-10-23 | 2023_24_P10 | 2023_24_P07 | 2023_24_Q4 | 2023_24_Q3 | Standards of service
SOS507492 | 507492 | Water | SOS | Start on Site | 2023-08-14 | 2023-08-14 | 2023_24_P05 | 2023_24_P05 | 2023_24_Q2 | 2023_24_Q2 | Standards of service
SOS507493 | 507493 | Water | SOS | Start on Site | 2022-09-12 | 2022-09-26 | 2022_23_P06 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2 | Standards of service
SOS507808 | 507808 | Wastewater | SOS | Start on Site | 2023-11-06 | 2023-11-06 | 2023_24_P08 | 2023_24_P08 | 2023_24_Q3 | 2023_24_Q3 | Supporting Sustainable Economic Growth
SOS507933 | 507933 | Wastewater | SOS | Start on Site | 2021-10-22 | 2021-11-19 | 2021_22_P07 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
SOS508109 | 508109 | Support Services | SOS | Start on Site | 2021-04-19 | 2021-03-24 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4 | Standards of service
SOS508601 | 508601 | Wastewater | SOS | Start on Site | 2021-11-02 | 2022-01-10 | 2021_22_P08 | 2021_22_P10 | 2021_22_Q3 | 2021_22_Q4 | Standards of service
SOS508752 | 508752 | Wastewater | SOS | Start on Site | 2022-11-04 | 2022-08-31 | 2022_23_P08 | 2022_23_P05 | 2022_23_Q3 | 2022_23_Q2 | Supporting Sustainable Economic Growth
SOS508949 | 508949 | Water | SOS | Start on Site | 2024-06-18 | 2024-03-25 | 2024_25_P03 | 2023_24_P12 | 2024_25_Q1 | 2023_24_Q4 | Supporting Sustainable Economic Growth
SOS509283 | 509283 | Water | SOS | Start on Site | 2021-04-12 | 2021-02-15 | 2021_22_P01 | 2020_21_P11 | 2021_22_Q1 | 2020_21_Q4 | Standards of service
SOS510392 | 510392 | Wastewater | SOS | Start on Site | 2022-10-25 | 2022-10-24 | 2022_23_P07 | 2022_23_P07 | 2022_23_Q3 | 2022_23_Q3 | Standards of service
SOS510546 | 510546 | Wastewater | SOS | Start on Site | 2024-08-19 | 2024-09-09 | 2024_25_P05 | 2024_25_P06 | 2024_25_Q2 | 2024_25_Q2 | Standards of service
SOS510727 | 510727 | Support Services | SOS | Start on Site | 2021-12-13 | 2021-11-09 | 2021_22_P09 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
SOS510931 | 510931 | Water | SOS | Start on Site | 2022-09-12 | 2022-09-12 | 2022_23_P06 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2 | Standards of service
SOS511334 | 511334 | Water | SOS | Start on Site | 2022-10-10 | 2022-10-19 | 2022_23_P07 | 2022_23_P07 | 2022_23_Q3 | 2022_23_Q3 | Standards of service
SOS511344 | 511344 | Support Services | SOS | Start on Site | 2022-08-24 | 2021-04-30 | 2022_23_P05 | 2021_22_P01 | 2022_23_Q2 | 2021_22_Q1 | Standards of service
SOS511495 | 511495 | Water | SOS | Start on Site | 2023-02-20 | 2023-02-13 | 2022_23_P11 | 2022_23_P11 | 2022_23_Q4 | 2022_23_Q4 | Drinking Water
SOS511500 | 511500 | Water | SOS | Start on Site | 2023-01-11 | 2022-12-12 | 2022_23_P10 | 2022_23_P09 | 2022_23_Q4 | 2022_23_Q3 | Drinking Water
SOS511704 | 511704 | Water | SOS | Start on Site | 2022-11-28 | 2022-11-28 | 2022_23_P08 | 2022_23_P08 | 2022_23_Q3 | 2022_23_Q3 | Standards of service
SOS512469 | 512469 | Water | SOS | Start on Site | 2023-01-16 | 2023-01-19 | 2022_23_P10 | 2022_23_P10 | 2022_23_Q4 | 2022_23_Q4 | Drinking Water
SOS512555 | 512555 | Wastewater | SOS | Start on Site | 2023-07-03 | 2023-07-03 | 2023_24_P04 | 2023_24_P04 | 2023_24_Q2 | 2023_24_Q2 | Supporting Sustainable Economic Growth
SOS512600 | 512600 | Water | SOS | Start on Site | 2022-04-04 | 2022-04-04 | 2022_23_P01 | 2022_23_P01 | 2022_23_Q1 | 2022_23_Q1 | Supporting Sustainable Economic Growth
SOS512639 | 512639 | Support Services | SOS | Start on Site | 2022-08-08 | 2022-09-01 | 2022_23_P05 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2 | Standards of service
SOS512749 | 512749 | Water | SOS | Start on Site | 2022-05-25 | 2022-07-29 | 2022_23_P02 | 2022_23_P04 | 2022_23_Q1 | 2022_23_Q2 | Standards of service
SOS512711 | 512711 | Water | SOS | Start on Site | 2022-06-29 | 2022-03-31 | 2022_23_P03 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4 | Standards of service
SOS512815 | 512815 | Water | SOS | Start on Site | 2023-05-18 | 2023-04-01 | 2023_24_P02 | 2023_24_P01 | 2023_24_Q1 | 2023_24_Q1 | Standards of service
SOS512940 | 512940 | Water | SOS | Start on Site | 2023-01-09 | 2023-01-30 | 2022_23_P10 | 2022_23_P10 | 2022_23_Q4 | 2022_23_Q4 | Standards of service
SOS512997 | 512997 | Water | SOS | Start on Site | 2023-08-17 | 2023-06-19 | 2023_24_P05 | 2023_24_P03 | 2023_24_Q2 | 2023_24_Q1 | Supporting Sustainable Economic Growth
SOS513208 | 513208 | Water | SOS | Start on Site | 2023-03-21 | 2023-01-12 | 2022_23_P12 | 2022_23_P10 | 2022_23_Q4 | 2022_23_Q4 | Drinking Water
SOS513312 | 513312 | CE&FS | SOS | Start on Site | 2021-06-22 | 2021-06-21 | 2021_22_P03 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1 | Long Term Water Sector Vision
SOS513433 | 513433 | Water | SOS | Start on Site | 2023-05-18 | 2023-05-18 | 2023_24_P02 | 2023_24_P02 | 2023_24_Q1 | 2023_24_Q1 | Drinking Water
SOS513412 | 513412 | Wastewater | SOS | Start on Site | 2023-08-17 | 2023-07-21 | 2023_24_P05 | 2023_24_P04 | 2023_24_Q2 | 2023_24_Q2 | Standards of service
SOS513417 | 513417 | Wastewater | SOS | Start on Site | 2023-10-16 | 2023-10-24 | 2023_24_P07 | 2023_24_P07 | 2023_24_Q3 | 2023_24_Q3 | Standards of service
SOS513461 | 513461 | Support Services | SOS | Start on Site | 2022-03-21 | 2022-01-26 | 2021_22_P12 | 2021_22_P10 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
SOS513514 | 513514 | Wastewater | SOS | Start on Site | 2023-12-19 | 2023-12-19 | 2023_24_P09 | 2023_24_P09 | 2023_24_Q3 | 2023_24_Q3 | Standards of service
SOS513826 | 513826 | Water | SOS | Start on Site | 2022-11-07 | 2022-10-23 | 2022_23_P08 | 2022_23_P07 | 2022_23_Q3 | 2022_23_Q3 | Standards of service
SOS513827 | 513827 | Water | SOS | Start on Site | 2023-12-15 | 2023-11-27 | 2023_24_P09 | 2023_24_P08 | 2023_24_Q3 | 2023_24_Q3 | Standards of service
SOS513829 | 513829 | Water | SOS | Start on Site | 2023-11-27 | 2023-11-27 | 2023_24_P08 | 2023_24_P08 | 2023_24_Q3 | 2023_24_Q3 | Standards of service
SOS513832 | 513832 | Support Services | SOS | Start on Site | 2021-08-17 | 2021-08-23 | 2021_22_P05 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
SOS513880 | 513880 | Support Services | SOS | Start on Site | 2023-05-01 | 2023-05-16 | 2023_24_P02 | 2023_24_P02 | 2023_24_Q1 | 2023_24_Q1 | Security & Resilience
SOS513923 | 513923 | Water | SOS | Start on Site | 2021-11-15 | 2021-11-25 | 2021_22_P08 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
SOS513964 | 513964 | Water | SOS | Start on Site | 2023-08-03 | 2023-08-03 | 2023_24_P05 | 2023_24_P05 | 2023_24_Q2 | 2023_24_Q2 | Standards of service
SOS514041 | 514041 | Wastewater | SOS | Start on Site | 2023-04-10 | 2023-04-01 | 2023_24_P01 | 2023_24_P01 | 2023_24_Q1 | 2023_24_Q1 | Standards of service
SOS514045 | 514045 | Wastewater | SOS | Start on Site | 2023-07-18 | 2023-06-09 | 2023_24_P04 | 2023_24_P03 | 2023_24_Q2 | 2023_24_Q1 | Environment
SOS514047 | 514047 | Water | SOS | Start on Site | 2023-01-09 | 2022-11-30 | 2022_23_P10 | 2022_23_P08 | 2022_23_Q4 | 2022_23_Q3 | Standards of service
SOS514080 | 514080 | Water | SOS | Start on Site | 2023-04-24 | 2023-03-20 | 2023_24_P01 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4 | Standards of service
SOS514217 | 514217 | Wastewater | SOS | Start on Site | 2022-11-01 | 2022-11-07 | 2022_23_P08 | 2022_23_P08 | 2022_23_Q3 | 2022_23_Q3 | Standards of service
SOS514281 | 514281 | Water | SOS | Start on Site | 2024-02-29 | 2024-03-04 | 2023_24_P11 | 2023_24_P12 | 2023_24_Q4 | 2023_24_Q4 | Standards of service
SOS514282 | 514282 | Water | SOS | Start on Site | 2023-12-11 | 2023-12-05 | 2023_24_P09 | 2023_24_P09 | 2023_24_Q3 | 2023_24_Q3 | Standards of service
SOS514441 | 514441 | Support Services | SOS | Start on Site | 2023-02-02 | 2023-02-02 | 2022_23_P11 | 2022_23_P11 | 2022_23_Q4 | 2022_23_Q4 | Security & Resilience
SOS514448 | 514448 | Wastewater | SOS | Start on Site | 2023-11-22 | 2023-04-01 | 2023_24_P08 | 2023_24_P01 | 2023_24_Q3 | 2023_24_Q1 | Standards of service
SOS514460 | 514460 | Wastewater | SOS | Start on Site | 2024-08-23 | 2024-08-23 | 2024_25_P05 | 2024_25_P05 | 2024_25_Q2 | 2024_25_Q2 | Standards of service
SOS514551 | 514551 | Wastewater | SOS | Start on Site | 2023-11-06 | 2023-10-16 | 2023_24_P08 | 2023_24_P07 | 2023_24_Q3 | 2023_24_Q3 | Standards of service
SOS514598 | 514598 | Support Services | SOS | Start on Site | 2022-12-28 | 2023-01-01 | 2022_23_P09 | 2022_23_P10 | 2022_23_Q3 | 2022_23_Q4 | Standards of service
SOS514631 | 514631 | Wastewater | SOS | Start on Site | 2022-09-16 | 2022-09-16 | 2022_23_P06 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2 | Standards of service
SOS514765 | 514765 | Wastewater | SOS | Start on Site | 2024-06-18 | 2024-06-18 | 2024_25_P03 | 2024_25_P03 | 2024_25_Q1 | 2024_25_Q1 | Standards of service
SOS514783 | 514783 | Wastewater | SOS | Start on Site | 2024-01-24 | 2024-01-24 | 2023_24_P10 | 2023_24_P10 | 2023_24_Q4 | 2023_24_Q4 | Standards of service
SOS514831 | 514831 | Wastewater | SOS | Start on Site | 2024-04-15 | 2024-04-15 | 2024_25_P01 | 2024_25_P01 | 2024_25_Q1 | 2024_25_Q1 | Standards of service
SOS515139 | 515139 | Water | SOS | Start on Site | 2023-03-31 | 2023-03-29 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4 | Standards of service
SOS515268 | 515268 | Support Services | SOS | Start on Site | 2023-11-08 | 2023-12-01 | 2023_24_P08 | 2023_24_P09 | 2023_24_Q3 | 2023_24_Q3 | Security & Resilience
SOS515404 | 515404 | CE&FS | SOS | Start on Site | 2023-08-04 | 2023-08-08 | 2023_24_P05 | 2023_24_P05 | 2023_24_Q2 | 2023_24_Q2 | Climate Change, Adaptation and Mitigation
SOS515505 | 515505 | Water | SOS | Start on Site | 2022-04-11 | 2022-03-31 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4 | Drinking Water
SOS515607 | 515607 | Wastewater | SOS | Start on Site | 2023-06-05 | 2023-03-20 | 2023_24_P03 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4 | Standards of service
SOS515612 | 515612 | Wastewater | SOS | Start on Site | 2024-07-23 | 2024-06-03 | 2024_25_P04 | 2024_25_P03 | 2024_25_Q2 | 2024_25_Q1 | Standards of service
SOS515625 | 515625 | Support Services | SOS | Start on Site | 2022-12-19 | 2022-12-13 | 2022_23_P09 | 2022_23_P09 | 2022_23_Q3 | 2022_23_Q3 | Standards of service
SOS515827 | 515827 | Wastewater | SOS | Start on Site | 2024-02-05 | 2024-02-19 | 2023_24_P11 | 2023_24_P11 | 2023_24_Q4 | 2023_24_Q4 | Standards of service
SOS516045 | 516045 | Water | SOS | Start on Site | 2023-04-10 | 2023-03-31 | 2023_24_P01 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4 | Standards of service
SOS516085 | 516085 | Water | SOS | Start on Site | 2023-06-16 | 2023-06-16 | 2023_24_P03 | 2023_24_P03 | 2023_24_Q1 | 2023_24_Q1 | Standards of service
SOS516082 | 516082 | Water | SOS | Start on Site | 2024-04-15 | 2024-03-18 | 2024_25_P01 | 2023_24_P12 | 2024_25_Q1 | 2023_24_Q4 | Standards of service
SOS516517 | 516517 | Water | SOS | Start on Site | 2023-08-23 | 2023-07-24 | 2023_24_P05 | 2023_24_P04 | 2023_24_Q2 | 2023_24_Q2 | Standards of service
SOS516502 | 516502 | Water | SOS | Start on Site | 2022-06-23 | 2022-06-23 | 2022_23_P03 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1 | Drinking Water
SOS516563 | 516563 | Wastewater | SOS | Start on Site | 2024-01-08 | 2023-11-10 | 2023_24_P10 | 2023_24_P08 | 2023_24_Q4 | 2023_24_Q3 | Standards of service
SOS516659 | 516659 | Wastewater | SOS | Start on Site | 2023-01-31 | 2022-12-21 | 2022_23_P10 | 2022_23_P09 | 2022_23_Q4 | 2022_23_Q3 | Climate Change, Adaptation and Mitigation
SOS516857 | 516857 | Wastewater | SOS | Start on Site | 2023-07-26 | 2023-07-10 | 2023_24_P04 | 2023_24_P04 | 2023_24_Q2 | 2023_24_Q2 | Standards of service
SOS517345 | 517345 | CE&FS | SOS | Start on Site | 2024-02-21 | 2024-01-15 | 2023_24_P11 | 2023_24_P10 | 2023_24_Q4 | 2023_24_Q4 | Climate Change, Adaptation and Mitigation
SOS517325 | 517325 | Wastewater | SOS | Start on Site | 2024-08-19 | 2024-08-19 | 2024_25_P05 | 2024_25_P05 | 2024_25_Q2 | 2024_25_Q2 | Standards of service
SOS517533 | 517533 | Water | SOS | Start on Site | 2022-07-11 | 2022-07-11 | 2022_23_P04 | 2022_23_P04 | 2022_23_Q2 | 2022_23_Q2 | Drinking Water
SOS517567 | 517567 | Support Services | SOS | Start on Site | 2023-10-02 | 2023-10-02 | 2023_24_P07 | 2023_24_P07 | 2023_24_Q3 | 2023_24_Q3 | Standards of service
SOS517996 | 517996 | Water | SOS | Start on Site | 2023-08-07 | 2023-06-12 | 2023_24_P05 | 2023_24_P03 | 2023_24_Q2 | 2023_24_Q1 | Standards of service
SOS518147 | 518147 | Water | SOS | Start on Site | 2024-01-08 | 2024-01-15 | 2023_24_P10 | 2023_24_P10 | 2023_24_Q4 | 2023_24_Q4 | Supporting Sustainable Economic Growth
SOS518244 | 518244 | Wastewater | SOS | Start on Site | 2023-02-06 | 2023-02-20 | 2022_23_P11 | 2022_23_P11 | 2022_23_Q4 | 2022_23_Q4 | Standards of service
SOS518444 | 518444 | Water | SOS | Start on Site | 2023-01-19 | 2023-01-19 | 2022_23_P10 | 2022_23_P10 | 2022_23_Q4 | 2022_23_Q4 | Environment
SOS518591 | 518591 | Water | SOS | Start on Site | 2023-10-06 | 2023-08-14 | 2023_24_P07 | 2023_24_P05 | 2023_24_Q3 | 2023_24_Q2 | Standards of service
SOS518579 | 518579 | Wastewater | SOS | Start on Site | 2022-11-01 | 2022-09-26 | 2022_23_P08 | 2022_23_P06 | 2022_23_Q3 | 2022_23_Q2 | Standards of service
SOS518658 | 518658 | Support Services | SOS | Start on Site | 2023-10-02 | 2023-09-29 | 2023_24_P07 | 2023_24_P06 | 2023_24_Q3 | 2023_24_Q2 | Standards of service
SOS518660 | 518660 | Support Services | SOS | Start on Site | 2023-10-02 | 2023-09-29 | 2023_24_P07 | 2023_24_P06 | 2023_24_Q3 | 2023_24_Q2 | Standards of service
SOS518731 | 518731 | Wastewater | SOS | Start on Site | 2023-11-20 | 2023-12-05 | 2023_24_P08 | 2023_24_P09 | 2023_24_Q3 | 2023_24_Q3 | Standards of service
SOS519344 | 519344 | Support Services | SOS | Start on Site | 2024-03-11 | 2024-03-01 | 2023_24_P12 | 2023_24_P12 | 2023_24_Q4 | 2023_24_Q4 | Standards of service
SOS519703 | 519703 | Water | SOS | Start on Site | 2023-06-12 | 2023-06-15 | 2023_24_P03 | 2023_24_P03 | 2023_24_Q1 | 2023_24_Q1 | Drinking Water
SOS519709 | 519709 | Water | SOS | Start on Site | 2023-12-15 | 2023-11-20 | 2023_24_P09 | 2023_24_P08 | 2023_24_Q3 | 2023_24_Q3 | Standards of service
SOS520166 | 520166 | Water | SOS | Start on Site | 2023-07-06 | 2023-06-30 | 2023_24_P04 | 2023_24_P03 | 2023_24_Q2 | 2023_24_Q1 | Standards of service
SOS520228 | 520228 | Water | SOS | Start on Site | 2023-03-17 | 2023-03-14 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4 | Drinking Water
SOS520229 | 520229 | Support Services | SOS | Start on Site | 2022-06-10 | 2022-05-30 | 2022_23_P03 | 2022_23_P02 | 2022_23_Q1 | 2022_23_Q1 | Standards of service
SOS520427 | 520427 | Water | SOS | Start on Site | 2024-04-29 | 2024-04-29 | 2024_25_P01 | 2024_25_P01 | 2024_25_Q1 | 2024_25_Q1 | Standards of service
SOS520459 | 520459 | Support Services | SOS | Start on Site | 2023-03-13 | 2023-03-01 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4 | Security & Resilience
SOS520500 | 520500 | Wastewater | SOS | Start on Site | 2023-07-10 | 2023-07-10 | 2023_24_P04 | 2023_24_P04 | 2023_24_Q2 | 2023_24_Q2 | Supporting Sustainable Economic Growth
SOS520606 | 520606 | Water | SOS | Start on Site | 2023-01-09 | 2023-01-25 | 2022_23_P10 | 2022_23_P10 | 2022_23_Q4 | 2022_23_Q4 | Standards of service
SOS520675 | 520675 | Water | SOS | Start on Site | 2024-01-29 | 2024-01-24 | 2023_24_P10 | 2023_24_P10 | 2023_24_Q4 | 2023_24_Q4 | Drinking Water
SOS519934 | 519934 | CE&FS | SOS | Start on Site | 2023-08-18 | 2023-08-14 | 2023_24_P05 | 2023_24_P05 | 2023_24_Q2 | 2023_24_Q2 | Long Term Water Sector Vision
SOS520761 | 520761 | Support Services | SOS | Start on Site | 2023-01-23 | 2023-01-01 | 2022_23_P10 | 2022_23_P10 | 2022_23_Q4 | 2022_23_Q4 | Standards of service
SOS522707 | 522707 | Water | SOS | Start on Site | 2023-06-05 | 2023-06-06 | 2023_24_P03 | 2023_24_P03 | 2023_24_Q1 | 2023_24_Q1 | Standards of service
SOS522742 | 522742 | Wastewater | SOS | Start on Site | 2023-04-25 | 2023-04-27 | 2023_24_P01 | 2023_24_P01 | 2023_24_Q1 | 2023_24_Q1 | Standards of service
SOS523226 | 523226 | Support Services | SOS | Start on Site | 2024-02-26 | 2024-03-01 | 2023_24_P11 | 2023_24_P12 | 2023_24_Q4 | 2023_24_Q4 | Standards of service
SOS523234 | 523234 | Support Services | SOS | Start on Site | 2023-10-23 | 2023-10-06 | 2023_24_P07 | 2023_24_P07 | 2023_24_Q3 | 2023_24_Q3 | Security & Resilience
SOS523508 | 523508 | Wastewater | SOS | Start on Site | 2023-02-13 | 2023-02-06 | 2022_23_P11 | 2022_23_P11 | 2022_23_Q4 | 2022_23_Q4 | Standards of service
SOS524093 | 524093 | CE&FS | SOS | Start on Site | 2024-06-18 | 2024-06-18 | 2024_25_P03 | 2024_25_P03 | 2024_25_Q1 | 2024_25_Q1 | Climate Change, Adaptation and Mitigation
SOS524269 | 524269 | CE&FS | SOS | Start on Site | 2024-08-20 | 2024-08-20 | 2024_25_P05 | 2024_25_P05 | 2024_25_Q2 | 2024_25_Q2 | Climate Change, Adaptation and Mitigation
SOS524492 | 524492 | CE&FS | SOS | Start on Site | 2024-02-05 | 2024-02-19 | 2023_24_P11 | 2023_24_P11 | 2023_24_Q4 | 2023_24_Q4 | Climate Change, Adaptation and Mitigation
SOS524913 | 524913 | Support Services | SOS | Start on Site | 2023-03-13 | 2023-03-01 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4 | Standards of service
SOS524914 | 524914 | Support Services | SOS | Start on Site | 2023-03-13 | 2023-03-22 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4 | Standards of service
SOS524939 | 524939 | Support Services | SOS | Start on Site | 2023-06-02 | 2023-04-18 | 2023_24_P03 | 2023_24_P01 | 2023_24_Q1 | 2023_24_Q1 | Standards of service
SOS525189 | 525189 | Wastewater | SOS | Start on Site | 2023-03-31 | 2023-03-31 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4 | Standards of service
SOS525206 | 525206 | Water | SOS | Start on Site | 2024-04-24 | 2024-04-24 | 2024_25_P01 | 2024_25_P01 | 2024_25_Q1 | 2024_25_Q1 | Standards of service
SOS525281 | 525281 | CE&FS | SOS | Start on Site | 2023-11-27 | 2023-11-27 | 2023_24_P08 | 2023_24_P08 | 2023_24_Q3 | 2023_24_Q3 | Climate Change, Adaptation and Mitigation
SOS526537 | 526537 | Wastewater | SOS | Start on Site | 2023-07-03 | 2023-07-03 | 2023_24_P04 | 2023_24_P04 | 2023_24_Q2 | 2023_24_Q2 | Standards of service
SOS526670 | 526670 | Water | SOS | Start on Site | 2023-08-01 | 2023-08-14 | 2023_24_P05 | 2023_24_P05 | 2023_24_Q2 | 2023_24_Q2 | Standards of service
SOS526838 | 526838 | Support Services | SOS | Start on Site | 2023-10-31 | 2023-09-18 | 2023_24_P07 | 2023_24_P06 | 2023_24_Q3 | 2023_24_Q2 | Standards of service
SOS526984 | 526984 | Wastewater | SOS | Start on Site | 2024-06-03 | 2023-12-12 | 2024_25_P03 | 2023_24_P09 | 2024_25_Q1 | 2023_24_Q3 | Standards of service
SOS527220 | 527220 | Support Services | SOS | Start on Site | 2023-01-23 | 2023-01-31 | 2022_23_P10 | 2022_23_P10 | 2022_23_Q4 | 2022_23_Q4 | Standards of service
SOS527305 | 527305 | Wastewater | SOS | Start on Site | 2023-10-13 | 2023-09-25 | 2023_24_P07 | 2023_24_P06 | 2023_24_Q3 | 2023_24_Q2 | Standards of service
SOS527413 | 527413 | Water | SOS | Start on Site | 2023-07-21 | 2023-07-21 | 2023_24_P04 | 2023_24_P04 | 2023_24_Q2 | 2023_24_Q2 | Drinking Water
SOS528014 | 528014 | Water | SOS | Start on Site | 2023-08-07 | 2023-08-30 | 2023_24_P05 | 2023_24_P05 | 2023_24_Q2 | 2023_24_Q2 | Standards of service
SOS528068 | 528068 | Water | SOS | Start on Site | 2023-07-20 | 2023-07-24 | 2023_24_P04 | 2023_24_P04 | 2023_24_Q2 | 2023_24_Q2 | Standards of service
SOS528241 | 528241 | Support Services | SOS | Start on Site | 2023-06-02 | 2023-04-11 | 2023_24_P03 | 2023_24_P01 | 2023_24_Q1 | 2023_24_Q1 | Standards of service
SOS528868 | 528868 | Water | SOS | Start on Site | 2023-06-12 | 2023-05-31 | 2023_24_P03 | 2023_24_P02 | 2023_24_Q1 | 2023_24_Q1 | Standards of service
SOS529261 | 529261 | Water | SOS | Start on Site | 2023-06-01 | 2023-05-29 | 2023_24_P03 | 2023_24_P02 | 2023_24_Q1 | 2023_24_Q1 | Standards of service
SOS530690 | 530690 | Wastewater | SOS | Start on Site | 2024-02-22 | 2024-03-18 | 2023_24_P11 | 2023_24_P12 | 2023_24_Q4 | 2023_24_Q4 | Standards of service
SOS532423 | 532423 | Wastewater | SOS | Start on Site | 2024-04-29 | 2024-01-22 | 2024_25_P01 | 2023_24_P10 | 2024_25_Q1 | 2023_24_Q4 | Standards of service
SOS532714 | 532714 | Water | SOS | Start on Site | 2023-10-09 | 2023-10-09 | 2023_24_P07 | 2023_24_P07 | 2023_24_Q3 | 2023_24_Q3 | Standards of service
SOS532730 | 532730 | Water | SOS | Start on Site | 2023-09-12 | 2023-09-12 | 2023_24_P06 | 2023_24_P06 | 2023_24_Q2 | 2023_24_Q2 | Standards of service
SOS533107 | 533107 | Water | SOS | Start on Site | 2023-10-09 | 2023-10-09 | 2023_24_P07 | 2023_24_P07 | 2023_24_Q3 | 2023_24_Q3 | Standards of service
SOS533223 | 533223 | Water | SOS | Start on Site | 2023-10-09 | 2023-10-09 | 2023_24_P07 | 2023_24_P07 | 2023_24_Q3 | 2023_24_Q3 | Standards of service
SOS534910 | 534910 | Water | SOS | Start on Site | 2024-01-03 | 2024-01-01 | 2023_24_P10 | 2023_24_P10 | 2023_24_Q4 | 2023_24_Q4 | Standards of service
SOS534911 | 534911 | Water | SOS | Start on Site | 2023-12-11 | 2024-01-01 | 2023_24_P09 | 2023_24_P10 | 2023_24_Q3 | 2023_24_Q4 | Standards of service
SOS535840 | 535840 | Support Services | SOS | Start on Site | 2023-11-08 | 2023-11-07 | 2023_24_P08 | 2023_24_P08 | 2023_24_Q3 | 2023_24_Q3 | Standards of service
SOS536455 | 536455 | Water | SOS | Start on Site | 2024-06-24 | 2024-09-02 | 2024_25_P03 | 2024_25_P06 | 2024_25_Q1 | 2024_25_Q2 | Standards of service
SOS537270 | 537270 | Support Services | SOS | Start on Site | 2024-04-18 | 2024-04-18 | 2024_25_P01 | 2024_25_P01 | 2024_25_Q1 | 2024_25_Q1 | Security & Resilience
G100046172 | 046172 | Water | G100 | Gate 100 | 2021-09-01 | 2021-10-05 | 2021_22_P06 | 2021_22_P07 | 2021_22_Q2 | 2021_22_Q3 | Standards of service
G100400324 | 400324 | Water | G100 | Gate 100 | 2023-04-14 | 2023-02-01 | 2023_24_P01 | 2022_23_P11 | 2023_24_Q1 | 2022_23_Q4 | Standards of service
G100401705 | 401705 | Wastewater | G100 | Gate 100 | 2021-10-24 | 2024-09-18 | 2021_22_P07 | 2024_25_P06 | 2021_22_Q3 | 2024_25_Q2 | Standards of service
G100402197 | 402197 | Wastewater | G100 | Gate 100 | 2021-05-11 | 2021-04-30 | 2021_22_P02 | 2021_22_P01 | 2021_22_Q1 | 2021_22_Q1 | Standards of service
G100401685 | 401685 | Wastewater | G100 | Gate 100 | 2021-09-20 | 2021-09-21 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
G100401795 | 401795 | Wastewater | G100 | Gate 100 | 2021-07-06 | 2021-06-28 | 2021_22_P04 | 2021_22_P03 | 2021_22_Q2 | 2021_22_Q1 | Standards of service
G100401687 | 401687 | Wastewater | G100 | Gate 100 | 2021-09-21 | 2021-09-21 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
G100401668 | 401668 | Wastewater | G100 | Gate 100 | 2021-09-20 | 2024-07-25 | 2021_22_P06 | 2024_25_P04 | 2021_22_Q2 | 2024_25_Q2 | Standards of service
G100403238 | 403238 | Wastewater | G100 | Gate 100 | 2021-08-16 | 2021-09-21 | 2021_22_P05 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
G100403098 | 403098 | Wastewater | G100 | Gate 100 | 2021-12-01 | 2022-03-24 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4 | Standards of service
G100403103 | 403103 | Wastewater | G100 | Gate 100 | 2021-09-26 | 2021-03-31 | 2021_22_P06 | 2020_21_P12 | 2021_22_Q2 | 2020_21_Q4 | Standards of service
G100403102 | 403102 | Wastewater | G100 | Gate 100 | 2021-08-24 | 2021-09-21 | 2021_22_P05 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
G100403090 | 403090 | Water | G100 | Gate 100 | 2021-06-30 | 2021-05-31 | 2021_22_P03 | 2021_22_P02 | 2021_22_Q1 | 2021_22_Q1 | Standards of service
G100403100 | 403100 | Wastewater | G100 | Gate 100 | 2021-08-21 | 2021-09-24 | 2021_22_P05 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
G100403101 | 403101 | Wastewater | G100 | Gate 100 | 2021-08-24 | 2021-09-21 | 2021_22_P05 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
G100403104 | 403104 | Wastewater | G100 | Gate 100 | 2021-09-01 | 2022-03-30 | 2021_22_P06 | 2021_22_P12 | 2021_22_Q2 | 2021_22_Q4 | Standards of service
G100403658 | 403658 | Water | G100 | Gate 100 | 2022-09-30 | 2023-02-23 | 2022_23_P06 | 2022_23_P11 | 2022_23_Q2 | 2022_23_Q4 | Standards of service
G100403106 | 403106 | Wastewater | G100 | Gate 100 | 2023-01-31 | 2025-08-04 | 2022_23_P10 | 2025_26_P05 | 2022_23_Q4 | 2025_26_Q2 | Standards of service
G100402949 | 402949 | Wastewater | G100 | Gate 100 | 2022-10-21 | 2022-07-29 | 2022_23_P07 | 2022_23_P04 | 2022_23_Q3 | 2022_23_Q2 | Standards of service
G100403321 | 403321 | Wastewater | G100 | Gate 100 | 2022-08-27 | 2023-01-31 | 2022_23_P05 | 2022_23_P10 | 2022_23_Q2 | 2022_23_Q4 | Standards of service
G100403716 | 403716 | Wastewater | G100 | Gate 100 | 2023-02-22 | 2022-11-23 | 2022_23_P11 | 2022_23_P08 | 2022_23_Q4 | 2022_23_Q3 | Standards of service
G100404026 | 404026 | Wastewater | G100 | Gate 100 | 2022-06-20 | 2024-10-14 | 2022_23_P03 | 2024_25_P07 | 2022_23_Q1 | 2024_25_Q3 | Standards of service
G100500046 | 500046 | Water | G100 | Gate 100 | 2024-08-18 | 2022-03-10 | 2024_25_P05 | 2021_22_P12 | 2024_25_Q2 | 2021_22_Q4 | Standards of service
G100403995 | 403995 | Water | G100 | Gate 100 | 2024-10-17 | 2026-02-12 | 2024_25_P07 | 2025_26_P11 | 2024_25_Q3 | 2025_26_Q4 | Standards of service
G100403127 | 403127 | Water | G100 | Gate 100 | 2022-01-31 | 2023-03-30 | 2021_22_P10 | 2022_23_P12 | 2021_22_Q4 | 2022_23_Q4 | Standards of service
G100403532 | 403532 | Water | G100 | Gate 100 | 2021-10-01 | 2022-01-21 | 2021_22_P07 | 2021_22_P10 | 2021_22_Q3 | 2021_22_Q4 | Standards of service
G100403994 | 403994 | Water | G100 | Gate 100 | 2022-02-25 | 2023-11-30 | 2021_22_P11 | 2023_24_P08 | 2021_22_Q4 | 2023_24_Q3 | Standards of service
G100404003 | 404003 | Water | G100 | Gate 100 | 2021-04-01 | 2021-11-19 | 2021_22_P01 | 2021_22_P08 | 2021_22_Q1 | 2021_22_Q3 | Standards of service
G100500017 | 500017 | Wastewater | G100 | Gate 100 | 2022-02-21 | 2022-03-30 | 2021_22_P11 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
G100403967 | 403967 | Wastewater | G100 | Gate 100 | 2024-09-09 | 2024-07-30 | 2024_25_P06 | 2024_25_P04 | 2024_25_Q2 | 2024_25_Q2 | Supporting Sustainable Economic Growth
G100403939 | 403939 | Wastewater | G100 | Gate 100 | 2022-05-05 | 2023-05-19 | 2022_23_P02 | 2023_24_P02 | 2022_23_Q1 | 2023_24_Q1 | Supporting Sustainable Economic Growth
G100403781 | 403781 | Wastewater | G100 | Gate 100 | 2021-09-16 | 2021-07-20 | 2021_22_P06 | 2021_22_P04 | 2021_22_Q2 | 2021_22_Q2 | Supporting Sustainable Economic Growth
G100403782 | 403782 | Wastewater | G100 | Gate 100 | 2023-05-01 | 2024-01-23 | 2023_24_P02 | 2023_24_P10 | 2023_24_Q1 | 2023_24_Q4 | Supporting Sustainable Economic Growth
G100403991 | 403991 | Water | G100 | Gate 100 | 2023-01-30 | 2024-02-23 | 2022_23_P10 | 2023_24_P11 | 2022_23_Q4 | 2023_24_Q4 | Standards of service
G100500047 | 500047 | Water | G100 | Gate 100 | 2022-10-07 | 2022-11-25 | 2022_23_P07 | 2022_23_P08 | 2022_23_Q3 | 2022_23_Q3 | Standards of service
G100403923 | 403923 | Wastewater | G100 | Gate 100 | 2022-06-30 | 2023-02-22 | 2022_23_P03 | 2022_23_P11 | 2022_23_Q1 | 2022_23_Q4 | Standards of service
G100403934 | 403934 | Wastewater | G100 | Gate 100 | 2022-07-04 | 2023-01-18 | 2022_23_P04 | 2022_23_P10 | 2022_23_Q2 | 2022_23_Q4 | Supporting Sustainable Economic Growth
G100404134 | 404134 | Water | G100 | Gate 100 | 2021-06-17 | 2021-10-01 | 2021_22_P03 | 2021_22_P07 | 2021_22_Q1 | 2021_22_Q3 | Standards of service
G100403902 | 403902 | Wastewater | G100 | Gate 100 | 2021-11-22 | 2022-08-29 | 2021_22_P08 | 2022_23_P05 | 2021_22_Q3 | 2022_23_Q2 | Supporting Sustainable Economic Growth
G100500068 | 500068 | Wastewater | G100 | Gate 100 | 2021-06-23 | 2021-06-29 | 2021_22_P03 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1 | Supporting Sustainable Economic Growth
G100500218 | 500218 | Water | G100 | Gate 100 | 2022-02-15 | 2021-12-21 | 2021_22_P11 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3 | Standards of service
G100500040 | 500040 | Water | G100 | Gate 100 | 2021-04-30 | 2021-07-30 | 2021_22_P01 | 2021_22_P04 | 2021_22_Q1 | 2021_22_Q2 | Standards of service
G100403986 | 403986 | Water | G100 | Gate 100 | 2023-04-14 | 2023-03-28 | 2023_24_P01 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4 | Standards of service
G100500060 | 500060 | Water | G100 | Gate 100 | 2021-05-12 | 2021-04-01 | 2021_22_P02 | 2021_22_P01 | 2021_22_Q1 | 2021_22_Q1 | Standards of service
G100500235 | 500235 | Wastewater | G100 | Gate 100 | 2022-06-03 | 2022-11-28 | 2022_23_P03 | 2022_23_P08 | 2022_23_Q1 | 2022_23_Q3 | Supporting Sustainable Economic Growth
G100404069 | 404069 | Wastewater | G100 | Gate 100 | 2021-04-30 | 2021-03-24 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4 | Supporting Sustainable Economic Growth
G100404093 | 404093 | Water | G100 | Gate 100 | 2023-08-23 | 2024-08-01 | 2023_24_P05 | 2024_25_P05 | 2023_24_Q2 | 2024_25_Q2 | Standards of service
G100403943 | 403943 | Wastewater | G100 | Gate 100 | 2021-11-18 | 2023-03-29 | 2021_22_P08 | 2022_23_P12 | 2021_22_Q3 | 2022_23_Q4 | Supporting Sustainable Economic Growth
G100500207 | 500207 | Water | G100 | Gate 100 | 2021-06-01 | 2021-10-21 | 2021_22_P03 | 2021_22_P07 | 2021_22_Q1 | 2021_22_Q3 | Standards of service
G100404135 | 404135 | Water | G100 | Gate 100 | 2023-01-27 | 2024-06-07 | 2022_23_P10 | 2024_25_P03 | 2022_23_Q4 | 2024_25_Q1 | Standards of service
G100500246 | 500246 | Water | G100 | Gate 100 | 2021-10-22 | 2023-09-21 | 2021_22_P07 | 2023_24_P06 | 2021_22_Q3 | 2023_24_Q2 | Standards of service
G100500052 | 500052 | Wastewater | G100 | Gate 100 | 2022-07-30 | 2024-04-11 | 2022_23_P04 | 2024_25_P01 | 2022_23_Q2 | 2024_25_Q1 | Supporting Sustainable Economic Growth
G100500302 | 500302 | Wastewater | G100 | Gate 100 | 2022-06-30 | 2023-04-28 | 2022_23_P03 | 2023_24_P01 | 2022_23_Q1 | 2023_24_Q1 | Standards of service
G100404007 | 404007 | Wastewater | G100 | Gate 100 | 2022-02-18 | 2021-09-30 | 2021_22_P11 | 2021_22_P06 | 2021_22_Q4 | 2021_22_Q2 | Standards of service
G100500523 | 500523 | Water | G100 | Gate 100 | 2023-09-20 | 2025-02-14 | 2023_24_P06 | 2024_25_P11 | 2023_24_Q2 | 2024_25_Q4 | Standards of service
G100500573 | 500573 | Water | G100 | Gate 100 | 2022-06-28 | 2022-08-30 | 2022_23_P03 | 2022_23_P05 | 2022_23_Q1 | 2022_23_Q2 | Standards of service
G100500299 | 500299 | Wastewater | G100 | Gate 100 | 2021-10-20 | 2021-08-31 | 2021_22_P07 | 2021_22_P05 | 2021_22_Q3 | 2021_22_Q2 | Standards of service
G100404132 | 404132 | Water | G100 | Gate 100 | 2026-02-15 | 2025-03-18 | 2025_26_P11 | 2024_25_P12 | 2025_26_Q4 | 2024_25_Q4 | Standards of service
G100500233 | 500233 | Wastewater | G100 | Gate 100 | 2022-01-14 | 2024-04-26 | 2021_22_P10 | 2024_25_P01 | 2021_22_Q4 | 2024_25_Q1 | Supporting Sustainable Economic Growth
G100500681 | 500681 | Wastewater | G100 | Gate 100 | 2022-09-14 | 2023-09-27 | 2022_23_P06 | 2023_24_P06 | 2022_23_Q2 | 2023_24_Q2 | Standards of service
G100500742 | 500742 | Water | G100 | Gate 100 | 2021-04-30 | 2021-07-14 | 2021_22_P01 | 2021_22_P04 | 2021_22_Q1 | 2021_22_Q2 | Standards of service
G100500784 | 500784 | Wastewater | G100 | Gate 100 | 2021-04-23 | 2021-06-15 | 2021_22_P01 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1 | Standards of service
G100500687 | 500687 | Wastewater | G100 | Gate 100 | 2021-09-24 | 2021-07-29 | 2021_22_P06 | 2021_22_P04 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
G100500245 | 500245 | Water | G100 | Gate 100 | 2022-08-17 | 2024-10-04 | 2022_23_P05 | 2024_25_P07 | 2022_23_Q2 | 2024_25_Q3 | Standards of service
G100500229 | 500229 | Wastewater | G100 | Gate 100 | 2023-07-28 | 2025-04-03 | 2023_24_P04 | 2025_26_P01 | 2023_24_Q2 | 2025_26_Q1 | Supporting Sustainable Economic Growth
G100500576 | 500576 | Wastewater | G100 | Gate 100 | 2024-06-17 | 2024-02-02 | 2024_25_P03 | 2023_24_P11 | 2024_25_Q1 | 2023_24_Q4 | Standards of service
G100500579 | 500579 | Wastewater | G100 | Gate 100 | 2022-03-31 | 2023-03-17 | 2021_22_P12 | 2022_23_P12 | 2021_22_Q4 | 2022_23_Q4 | Standards of service
G100500707 | 500707 | Wastewater | G100 | Gate 100 | 2021-07-14 | 2021-06-14 | 2021_22_P04 | 2021_22_P03 | 2021_22_Q2 | 2021_22_Q1 | Standards of service
G100500509 | 500509 | Water | G100 | Gate 100 | 2021-08-24 | 2025-01-21 | 2021_22_P05 | 2024_25_P10 | 2021_22_Q2 | 2024_25_Q4 | Standards of service
G100501001 | 501001 | Water | G100 | Gate 100 | 2023-02-16 | 2026-02-23 | 2022_23_P11 | 2025_26_P11 | 2022_23_Q4 | 2025_26_Q4 | Standards of service
G100500665 | 500665 | Wastewater | G100 | Gate 100 | 2022-01-16 | 2021-11-24 | 2021_22_P10 | 2021_22_P08 | 2021_22_Q4 | 2021_22_Q3 | Standards of service
G100500575 | 500575 | Water | G100 | Gate 100 | 2022-08-22 | 2022-12-01 | 2022_23_P05 | 2022_23_P09 | 2022_23_Q2 | 2022_23_Q3 | Standards of service
G100500709 | 500709 | Water | G100 | Gate 100 | 2021-10-11 | 2022-12-23 | 2021_22_P07 | 2022_23_P09 | 2021_22_Q3 | 2022_23_Q3 | Standards of service
G100500496 | 500496 | Wastewater | G100 | Gate 100 | 2021-05-30 | 2021-03-26 | 2021_22_P02 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4 | Standards of service
G100500694 | 500694 | Wastewater | G100 | Gate 100 | 2021-11-22 | 2022-09-30 | 2021_22_P08 | 2022_23_P06 | 2021_22_Q3 | 2022_23_Q2 | Standards of service
G100500892 | 500892 | Water | G100 | Gate 100 | 2022-06-27 | 2024-03-28 | 2022_23_P03 | 2023_24_P12 | 2022_23_Q1 | 2023_24_Q4 | Supporting Sustainable Economic Growth
G100500580 | 500580 | Wastewater | G100 | Gate 100 | 2022-10-30 | 2023-09-29 | 2022_23_P07 | 2023_24_P06 | 2022_23_Q3 | 2023_24_Q2 | Standards of service
G100501019 | 501019 | Wastewater | G100 | Gate 100 | 2021-05-29 | 2021-03-12 | 2021_22_P02 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4 | Standards of service
G100404082 | 404082 | Water | G100 | Gate 100 | 2021-09-10 | 2021-04-26 | 2021_22_P06 | 2021_22_P01 | 2021_22_Q2 | 2021_22_Q1 | Standards of service
G100501216 | 501216 | Water | G100 | Gate 100 | 2021-11-18 | 2022-03-22 | 2021_22_P08 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4 | Standards of service
G100500771 | 500771 | Water | G100 | Gate 100 | 2021-06-14 | 2021-12-21 | 2021_22_P03 | 2021_22_P09 | 2021_22_Q1 | 2021_22_Q3 | Supporting Sustainable Economic Growth
G100500662 | 500662 | Wastewater | G100 | Gate 100 | 2021-11-24 | 2022-01-26 | 2021_22_P08 | 2021_22_P10 | 2021_22_Q3 | 2021_22_Q4 | Standards of service
G100500682 | 500682 | Wastewater | G100 | Gate 100 | 2022-09-07 | 2023-02-28 | 2022_23_P06 | 2022_23_P11 | 2022_23_Q2 | 2022_23_Q4 | Standards of service
G100500655 | 500655 | Wastewater | G100 | Gate 100 | 2022-03-28 | 2021-10-29 | 2021_22_P12 | 2021_22_P07 | 2021_22_Q4 | 2021_22_Q3 | Standards of service
G100500755 | 500755 | Water | G100 | Gate 100 | 2023-11-13 | 2025-04-04 | 2023_24_P08 | 2025_26_P01 | 2023_24_Q3 | 2025_26_Q1 | Standards of service
G100500947 | 500947 | Support Services | G100 | Gate 100 | 2021-06-16 | 2022-03-03 | 2021_22_P03 | 2021_22_P12 | 2021_22_Q1 | 2021_22_Q4 | Standards of service
G100500723 | 500723 | Wastewater | G100 | Gate 100 | 2022-01-14 | 2022-01-26 | 2021_22_P10 | 2021_22_P10 | 2021_22_Q4 | 2021_22_Q4 | Supporting Sustainable Economic Growth
G100500652 | 500652 | Wastewater | G100 | Gate 100 | 2021-11-09 | 2022-03-17 | 2021_22_P08 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4 | Standards of service
G100500661 | 500661 | Wastewater | G100 | Gate 100 | 2022-09-22 | 2023-01-31 | 2022_23_P06 | 2022_23_P10 | 2022_23_Q2 | 2022_23_Q4 | Standards of service
G100501211 | 501211 | Water | G100 | Gate 100 | 2025-02-16 | 2025-04-16 | 2024_25_P11 | 2025_26_P01 | 2024_25_Q4 | 2025_26_Q1 | Standards of service
G100500654 | 500654 | Wastewater | G100 | Gate 100 | 2022-01-29 | 2023-01-31 | 2021_22_P10 | 2022_23_P10 | 2021_22_Q4 | 2022_23_Q4 | Standards of service
G100500958 | 500958 | Water | G100 | Gate 100 | 2021-07-08 | 2022-01-13 | 2021_22_P04 | 2021_22_P10 | 2021_22_Q2 | 2021_22_Q4 | Standards of service
G100500695 | 500695 | Wastewater | G100 | Gate 100 | 2021-04-02 | 2021-03-22 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4 | Standards of service
G100500729 | 500729 | Wastewater | G100 | Gate 100 | 2024-11-10 | 2024-02-22 | 2024_25_P08 | 2023_24_P11 | 2024_25_Q3 | 2023_24_Q4 | Standards of service
G100500724 | 500724 | Wastewater | G100 | Gate 100 | 2025-01-07 | 2024-10-24 | 2024_25_P10 | 2024_25_P07 | 2024_25_Q4 | 2024_25_Q3 | Supporting Sustainable Economic Growth
G100501151 | 501151 | Wastewater | G100 | Gate 100 | 2021-05-25 | 2021-06-28 | 2021_22_P02 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1 | Standards of service
G100501390 | 501390 | Water | G100 | Gate 100 | 2022-11-10 | 2025-04-11 | 2022_23_P08 | 2025_26_P01 | 2022_23_Q3 | 2025_26_Q1 | Standards of service
G100501200 | 501200 | Water | G100 | Gate 100 | 2022-04-25 | 2022-08-31 | 2022_23_P01 | 2022_23_P05 | 2022_23_Q1 | 2022_23_Q2 | Standards of service
G100501021 | 501021 | Wastewater | G100 | Gate 100 | 2022-03-31 | 2023-09-28 | 2021_22_P12 | 2023_24_P06 | 2021_22_Q4 | 2023_24_Q2 | Supporting Sustainable Economic Growth
G100501158 | 501158 | Wastewater | G100 | Gate 100 | 2021-06-03 | 2022-03-01 | 2021_22_P03 | 2021_22_P12 | 2021_22_Q1 | 2021_22_Q4 | Standards of service
G100501040 | 501040 | Water | G100 | Gate 100 | 2021-05-31 | 2021-06-30 | 2021_22_P02 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1 | Standards of service
G100501352 | 501352 | Wastewater | G100 | Gate 100 | 2021-12-09 | 2022-03-29 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4 | Standards of service
G100500731 | 500731 | Wastewater | G100 | Gate 100 | 2024-09-10 | 2025-08-14 | 2024_25_P06 | 2025_26_P05 | 2024_25_Q2 | 2025_26_Q2 | Supporting Sustainable Economic Growth
G100501070 | 501070 | Water | G100 | Gate 100 | 2021-10-22 | 2023-07-19 | 2021_22_P07 | 2023_24_P04 | 2021_22_Q3 | 2023_24_Q2 | Drinking Water
G100501017 | 501017 | Wastewater | G100 | Gate 100 | 2023-11-02 | 2024-03-26 | 2023_24_P08 | 2023_24_P12 | 2023_24_Q3 | 2023_24_Q4 | Standards of service
G100501219 | 501219 | Water | G100 | Gate 100 | 2021-07-01 | 2021-07-29 | 2021_22_P04 | 2021_22_P04 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
G100500918 | 500918 | Water | G100 | Gate 100 | 2022-05-31 | 2022-07-22 | 2022_23_P02 | 2022_23_P04 | 2022_23_Q1 | 2022_23_Q2 | Standards of service
G100501720 | 501720 | Wastewater | G100 | Gate 100 | 2021-08-30 | 2021-06-28 | 2021_22_P05 | 2021_22_P03 | 2021_22_Q2 | 2021_22_Q1 | Standards of service
G100501153 | 501153 | Wastewater | G100 | Gate 100 | 2021-09-28 | 2022-10-31 | 2021_22_P06 | 2022_23_P07 | 2021_22_Q2 | 2022_23_Q3 | Standards of service
G100501217 | 501217 | Water | G100 | Gate 100 | 2021-08-31 | 2023-06-29 | 2021_22_P05 | 2023_24_P03 | 2021_22_Q2 | 2023_24_Q1 | Standards of service
G100501233 | 501233 | Water | G100 | Gate 100 | 2021-07-30 | 2021-05-17 | 2021_22_P04 | 2021_22_P02 | 2021_22_Q2 | 2021_22_Q1 | Standards of service
G100501146 | 501146 | Water | G100 | Gate 100 | 2021-04-30 | 2021-06-11 | 2021_22_P01 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1 | Standards of service
G100501159 | 501159 | Wastewater | G100 | Gate 100 | 2023-06-20 | 2025-10-09 | 2023_24_P03 | 2025_26_P07 | 2023_24_Q1 | 2025_26_Q3 | Standards of service
G100501169 | 501169 | Wastewater | G100 | Gate 100 | 2021-04-01 | 2021-05-10 | 2021_22_P01 | 2021_22_P02 | 2021_22_Q1 | 2021_22_Q1 | Standards of service
G100501144 | 501144 | Water | G100 | Gate 100 | 2022-01-21 | 2022-02-21 | 2021_22_P10 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
G100500896 | 500896 | Water | G100 | Gate 100 | 2022-11-07 | 2024-05-17 | 2022_23_P08 | 2024_25_P02 | 2022_23_Q3 | 2024_25_Q1 | Standards of service
G100501290 | 501290 | Wastewater | G100 | Gate 100 | 2022-07-30 | 2022-10-31 | 2022_23_P04 | 2022_23_P07 | 2022_23_Q2 | 2022_23_Q3 | Supporting Sustainable Economic Growth
G100501091 | 501091 | Water | G100 | Gate 100 | 2022-01-12 | 2021-08-23 | 2021_22_P10 | 2021_22_P05 | 2021_22_Q4 | 2021_22_Q2 | Standards of service
G100501599 | 501599 | Wastewater | G100 | Gate 100 | 2021-06-30 | 2023-03-09 | 2021_22_P03 | 2022_23_P12 | 2021_22_Q1 | 2022_23_Q4 | Standards of service
G100500893 | 500893 | Water | G100 | Gate 100 | 2023-12-21 | 2023-09-22 | 2023_24_P09 | 2023_24_P06 | 2023_24_Q3 | 2023_24_Q2 | Standards of service
G100501168 | 501168 | Wastewater | G100 | Gate 100 | 2022-05-30 | 2022-05-31 | 2022_23_P02 | 2022_23_P02 | 2022_23_Q1 | 2022_23_Q1 | Standards of service
G100501156 | 501156 | Wastewater | G100 | Gate 100 | 2021-10-11 | 2022-03-31 | 2021_22_P07 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4 | Standards of service
G100501402 | 501402 | Water | G100 | Gate 100 | 2021-05-07 | 2021-03-31 | 2021_22_P02 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4 | Standards of service
G100501512 | 501512 | Wastewater | G100 | Gate 100 | 2024-04-25 | 2024-07-26 | 2024_25_P01 | 2024_25_P04 | 2024_25_Q1 | 2024_25_Q2 | Standards of service
G100501632 | 501632 | Support Services | G100 | Gate 100 | 2021-05-07 | 2021-06-02 | 2021_22_P02 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1 | Standards of service
G100501499 | 501499 | Wastewater | G100 | Gate 100 | 2022-02-21 | 2022-08-31 | 2021_22_P11 | 2022_23_P05 | 2021_22_Q4 | 2022_23_Q2 | Standards of service
G100501500 | 501500 | Wastewater | G100 | Gate 100 | 2021-05-30 | 2021-03-31 | 2021_22_P02 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4 | Supporting Sustainable Economic Growth
G100501635 | 501635 | Water | G100 | Gate 100 | 2021-06-30 | 2021-06-21 | 2021_22_P03 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1 | Standards of service
G100501243 | 501243 | Water | G100 | Gate 100 | 2023-02-01 | 2024-05-27 | 2022_23_P11 | 2024_25_P02 | 2022_23_Q4 | 2024_25_Q1 | Drinking Water
G100501518 | 501518 | Wastewater | G100 | Gate 100 | 2021-09-30 | 2021-12-20 | 2021_22_P06 | 2021_22_P09 | 2021_22_Q2 | 2021_22_Q3 | Standards of service
G100501232 | 501232 | Water | G100 | Gate 100 | 2022-02-02 | 2024-08-06 | 2021_22_P11 | 2024_25_P05 | 2021_22_Q4 | 2024_25_Q2 | Standards of service
G100501165 | 501165 | Wastewater | G100 | Gate 100 | 2021-06-16 | 2021-03-30 | 2021_22_P03 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4 | Standards of service
G100501218 | 501218 | Water | G100 | Gate 100 | 2021-08-27 | 2021-11-17 | 2021_22_P05 | 2021_22_P08 | 2021_22_Q2 | 2021_22_Q3 | Standards of service
G100501388 | 501388 | Water | G100 | Gate 100 | 2022-01-31 | 2024-03-12 | 2021_22_P10 | 2023_24_P12 | 2021_22_Q4 | 2023_24_Q4 | Standards of service
G100501600 | 501600 | Water | G100 | Gate 100 | 2021-07-12 | 2021-09-24 | 2021_22_P04 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
G100501639 | 501639 | Support Services | G100 | Gate 100 | 2021-06-15 | 2021-09-06 | 2021_22_P03 | 2021_22_P06 | 2021_22_Q1 | 2021_22_Q2 | Standards of service
G100501488 | 501488 | Wastewater | G100 | Gate 100 | 2022-03-30 | 2022-03-28 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
G100501592 | 501592 | Wastewater | G100 | Gate 100 | 2021-05-30 | 2021-05-20 | 2021_22_P02 | 2021_22_P02 | 2021_22_Q1 | 2021_22_Q1 | Standards of service
G100501593 | 501593 | Wastewater | G100 | Gate 100 | 2021-04-01 | 2021-04-01 | 2021_22_P01 | 2021_22_P01 | 2021_22_Q1 | 2021_22_Q1 | Standards of service
G100501554 | 501554 | Water | G100 | Gate 100 | 2022-11-10 | 2023-01-31 | 2022_23_P08 | 2022_23_P10 | 2022_23_Q3 | 2022_23_Q4 | Standards of service
G100501393 | 501393 | Water | G100 | Gate 100 | 2022-05-30 | 2024-06-17 | 2022_23_P02 | 2024_25_P03 | 2022_23_Q1 | 2024_25_Q1 | Standards of service
G100501579 | 501579 | Wastewater | G100 | Gate 100 | 2022-12-30 | 2023-12-15 | 2022_23_P09 | 2023_24_P09 | 2022_23_Q3 | 2023_24_Q3 | Standards of service
G100501379 | 501379 | Water | G100 | Gate 100 | 2022-09-29 | 2024-06-11 | 2022_23_P06 | 2024_25_P03 | 2022_23_Q2 | 2024_25_Q1 | Standards of service
G100501670 | 501670 | Water | G100 | Gate 100 | 2024-09-08 | 2024-06-10 | 2024_25_P06 | 2024_25_P03 | 2024_25_Q2 | 2024_25_Q1 | Standards of service
G100501666 | 501666 | Water | G100 | Gate 100 | 2021-06-25 | 2022-07-15 | 2021_22_P03 | 2022_23_P04 | 2021_22_Q1 | 2022_23_Q2 | Standards of service
G100501259 | 501259 | Water | G100 | Gate 100 | 2021-06-15 | 2021-07-19 | 2021_22_P03 | 2021_22_P04 | 2021_22_Q1 | 2021_22_Q2 | Standards of service
G100501683 | 501683 | Wastewater | G100 | Gate 100 | 2021-11-30 | 2023-11-29 | 2021_22_P08 | 2023_24_P08 | 2021_22_Q3 | 2023_24_Q3 | Standards of service
G100501731 | 501731 | Water | G100 | Gate 100 | 2024-08-01 | 2024-07-29 | 2024_25_P05 | 2024_25_P04 | 2024_25_Q2 | 2024_25_Q2 | Standards of service
G100501436 | 501436 | Water | G100 | Gate 100 | 2021-04-28 | 2021-06-18 | 2021_22_P01 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1 | Standards of service
G100501418 | 501418 | Water | G100 | Gate 100 | 2021-12-03 | 2023-05-31 | 2021_22_P09 | 2023_24_P02 | 2021_22_Q3 | 2023_24_Q1 | Standards of service
G100501421 | 501421 | Water | G100 | Gate 100 | 2021-04-01 | 2021-06-11 | 2021_22_P01 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1 | Standards of service
G100501829 | 501829 | Wastewater | G100 | Gate 100 | 2021-12-11 | 2022-05-31 | 2021_22_P09 | 2022_23_P02 | 2021_22_Q3 | 2022_23_Q1 | Standards of service
G100501739 | 501739 | Wastewater | G100 | Gate 100 | 2021-07-22 | 2022-11-25 | 2021_22_P04 | 2022_23_P08 | 2021_22_Q2 | 2022_23_Q3 | Standards of service
G100501703 | 501703 | Wastewater | G100 | Gate 100 | 2024-04-25 | 2024-01-18 | 2024_25_P01 | 2023_24_P10 | 2024_25_Q1 | 2023_24_Q4 | Standards of service
G100501898 | 501898 | Support Services | G100 | Gate 100 | 2021-09-29 | 2022-05-31 | 2021_22_P06 | 2022_23_P02 | 2021_22_Q2 | 2022_23_Q1 | Standards of service
G100502246 | 502246 | Water | G100 | Gate 100 | 2021-07-12 | 2021-12-20 | 2021_22_P04 | 2021_22_P09 | 2021_22_Q2 | 2021_22_Q3 | Standards of service
G100502267 | 502267 | Wastewater | G100 | Gate 100 | 2021-04-22 | 2021-03-22 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4 | Standards of service
G100502268 | 502268 | Wastewater | G100 | Gate 100 | 2022-04-14 | 2023-03-23 | 2022_23_P01 | 2022_23_P12 | 2022_23_Q1 | 2022_23_Q4 | Standards of service
G100501818 | 501818 | Support Services | G100 | Gate 100 | 2021-07-28 | 2021-11-30 | 2021_22_P04 | 2021_22_P08 | 2021_22_Q2 | 2021_22_Q3 | Standards of service
G100502132 | 502132 | Water | G100 | Gate 100 | 2023-01-20 | 2024-11-27 | 2022_23_P10 | 2024_25_P08 | 2022_23_Q4 | 2024_25_Q3 | Standards of service
G100502269 | 502269 | Wastewater | G100 | Gate 100 | 2021-04-12 | 2021-03-22 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4 | Standards of service
G100502243 | 502243 | Water | G100 | Gate 100 | 2024-12-01 | 2025-12-09 | 2024_25_P09 | 2025_26_P09 | 2024_25_Q3 | 2025_26_Q3 | Standards of service
G100502332 | 502332 | Wastewater | G100 | Gate 100 | 2023-10-23 | 2024-02-01 | 2023_24_P07 | 2023_24_P11 | 2023_24_Q3 | 2023_24_Q4 | Supporting Sustainable Economic Growth
G100502231 | 502231 | Wastewater | G100 | Gate 100 | 2021-04-02 | 2021-03-22 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4 | Standards of service
G100502281 | 502281 | Wastewater | G100 | Gate 100 | 2021-11-19 | 2022-04-25 | 2021_22_P08 | 2022_23_P01 | 2021_22_Q3 | 2022_23_Q1 | Standards of service
G100502280 | 502280 | Wastewater | G100 | Gate 100 | 2022-03-07 | 2023-03-28 | 2021_22_P12 | 2022_23_P12 | 2021_22_Q4 | 2022_23_Q4 | Standards of service
G100502212 | 502212 | Wastewater | G100 | Gate 100 | 2023-10-24 | 2023-03-30 | 2023_24_P07 | 2022_23_P12 | 2023_24_Q3 | 2022_23_Q4 | Standards of service
G100502220 | 502220 | Wastewater | G100 | Gate 100 | 2025-08-17 | 2025-04-25 | 2025_26_P05 | 2025_26_P01 | 2025_26_Q2 | 2025_26_Q1 | Standards of service
G100502584 | 502584 | Wastewater | G100 | Gate 100 | 2021-04-01 | 2021-03-24 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4 | Standards of service
G100502282 | 502282 | Water | G100 | Gate 100 | 2023-09-14 | 2023-05-31 | 2023_24_P06 | 2023_24_P02 | 2023_24_Q2 | 2023_24_Q1 | Standards of service
G100502425 | 502425 | Wastewater | G100 | Gate 100 | 2024-08-14 | 2024-03-22 | 2024_25_P05 | 2023_24_P12 | 2024_25_Q2 | 2023_24_Q4 | Standards of service
G100502375 | 502375 | Wastewater | G100 | Gate 100 | 2023-07-18 | 2022-12-06 | 2023_24_P04 | 2022_23_P09 | 2023_24_Q2 | 2022_23_Q3 | Standards of service
G100502342 | 502342 | Wastewater | G100 | Gate 100 | 2022-07-07 | 2022-11-25 | 2022_23_P04 | 2022_23_P08 | 2022_23_Q2 | 2022_23_Q3 | Standards of service
G100502895 | 502895 | Wastewater | G100 | Gate 100 | 2022-09-18 | 2022-11-29 | 2022_23_P06 | 2022_23_P08 | 2022_23_Q2 | 2022_23_Q3 | Standards of service
G100502896 | 502896 | Water | G100 | Gate 100 | 2021-10-12 | 2021-11-29 | 2021_22_P07 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
G100502329 | 502329 | Water | G100 | Gate 100 | 2021-08-09 | 2021-08-24 | 2021_22_P05 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
G100502868 | 502868 | Wastewater | G100 | Gate 100 | 2025-05-08 | 2025-02-07 | 2025_26_P02 | 2024_25_P11 | 2025_26_Q1 | 2024_25_Q4 | Standards of service
G100502578 | 502578 | Wastewater | G100 | Gate 100 | 2022-04-27 | 2022-03-31 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4 | Standards of service
G100502648 | 502648 | Water | G100 | Gate 100 | 2022-06-01 | 2024-03-29 | 2022_23_P03 | 2023_24_P12 | 2022_23_Q1 | 2023_24_Q4 | Drinking Water
G100502355 | 502355 | Wastewater | G100 | Gate 100 | 2027-11-02 | 2027-08-04 | 2027_28_P08 | 2027_28_P05 | 2027_28_Q3 | 2027_28_Q2 | Standards of service
G100502382 | 502382 | Water | G100 | Gate 100 | 2021-10-29 | 2022-03-24 | 2021_22_P07 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4 | Standards of service
G100502780 | 502780 | Wastewater | G100 | Gate 100 | 2021-06-11 | 2021-06-28 | 2021_22_P03 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1 | Standards of service
G100502651 | 502651 | Water | G100 | Gate 100 | 2022-07-19 | 2024-10-23 | 2022_23_P04 | 2024_25_P07 | 2022_23_Q2 | 2024_25_Q3 | Drinking Water
G100502652 | 502652 | Water | G100 | Gate 100 | 2023-01-19 | 2023-03-28 | 2022_23_P10 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4 | Standards of service
G100502741 | 502741 | Wastewater | G100 | Gate 100 | 2021-07-22 | 2021-06-02 | 2021_22_P04 | 2021_22_P03 | 2021_22_Q2 | 2021_22_Q1 | Standards of service
G100502742 | 502742 | Wastewater | G100 | Gate 100 | 2021-10-14 | 2021-08-24 | 2021_22_P07 | 2021_22_P05 | 2021_22_Q3 | 2021_22_Q2 | Standards of service
G100502747 | 502747 | Wastewater | G100 | Gate 100 | 2021-09-30 | 2021-09-21 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
G100502369 | 502369 | Water | G100 | Gate 100 | 2024-08-15 | 2024-09-12 | 2024_25_P05 | 2024_25_P06 | 2024_25_Q2 | 2024_25_Q2 | Drinking Water
G100502412 | 502412 | Water | G100 | Gate 100 | 2021-06-25 | 2021-08-03 | 2021_22_P03 | 2021_22_P05 | 2021_22_Q1 | 2021_22_Q2 | Standards of service
G100502827 | 502827 | Wastewater | G100 | Gate 100 | 2022-01-13 | 2022-03-30 | 2021_22_P10 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4 | Supporting Sustainable Economic Growth
G100502765 | 502765 | Wastewater | G100 | Gate 100 | 2021-10-26 | 2021-09-21 | 2021_22_P07 | 2021_22_P06 | 2021_22_Q3 | 2021_22_Q2 | Standards of service
G100502766 | 502766 | Wastewater | G100 | Gate 100 | 2026-04-30 | 2026-07-22 | 2026_27_P01 | 2026_27_P04 | 2026_27_Q1 | 2026_27_Q2 | Supporting Sustainable Economic Growth
G100502743 | 502743 | Wastewater | G100 | Gate 100 | 2022-06-13 | 2022-11-04 | 2022_23_P03 | 2022_23_P08 | 2022_23_Q1 | 2022_23_Q3 | Environment
G100502383 | 502383 | Water | G100 | Gate 100 | 2021-12-20 | 2022-01-31 | 2021_22_P09 | 2021_22_P10 | 2021_22_Q3 | 2021_22_Q4 | Standards of service
G100502934 | 502934 | Wastewater | G100 | Gate 100 | 2021-10-03 | 2021-11-22 | 2021_22_P07 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
G100502958 | 502958 | Wastewater | G100 | Gate 100 | 2023-01-03 | 2023-03-03 | 2022_23_P10 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4 | Standards of service
G100502748 | 502748 | Wastewater | G100 | Gate 100 | 2022-07-24 | 2022-01-27 | 2022_23_P04 | 2021_22_P10 | 2022_23_Q2 | 2021_22_Q4 | Standards of service
G100502791 | 502791 | Water | G100 | Gate 100 | 2025-02-25 | 2024-11-20 | 2024_25_P11 | 2024_25_P08 | 2024_25_Q4 | 2024_25_Q3 | Standards of service
G100502605 | 502605 | Water | G100 | Gate 100 | 2021-09-30 | 2021-09-30 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
G100502563 | 502563 | Water | G100 | Gate 100 | 2022-01-18 | 2021-12-16 | 2021_22_P10 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3 | Standards of service
G100503119 | 503119 | Support Services | G100 | Gate 100 | 2021-07-28 | 2021-11-25 | 2021_22_P04 | 2021_22_P08 | 2021_22_Q2 | 2021_22_Q3 | Security & Resilience
G100503072 | 503072 | Water | G100 | Gate 100 | 2022-09-30 | 2022-09-29 | 2022_23_P06 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2 | Standards of service
G100502944 | 502944 | Wastewater | G100 | Gate 100 | 2021-09-06 | 2024-07-11 | 2021_22_P06 | 2024_25_P04 | 2021_22_Q2 | 2024_25_Q2 | Environment
G100502859 | 502859 | Water | G100 | Gate 100 | 2026-02-16 | 2025-11-18 | 2025_26_P11 | 2025_26_P08 | 2025_26_Q4 | 2025_26_Q3 | Standards of service
G100502866 | 502866 | Wastewater | G100 | Gate 100 | 2022-01-14 | 2022-02-17 | 2021_22_P10 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4 | Supporting Sustainable Economic Growth
G100502867 | 502867 | Water | G100 | Gate 100 | 2022-01-14 | 2021-12-08 | 2021_22_P10 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3 | Standards of service
G100502358 | 502358 | Water | G100 | Gate 100 | 2024-06-06 | 2025-01-10 | 2024_25_P03 | 2024_25_P10 | 2024_25_Q1 | 2024_25_Q4 | Supporting Sustainable Economic Growth
G100502772 | 502772 | Water | G100 | Gate 100 | 2021-05-11 | 2021-03-31 | 2021_22_P02 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4 | Standards of service
G100502945 | 502945 | Wastewater | G100 | Gate 100 | 2021-09-29 | 2022-12-21 | 2021_22_P06 | 2022_23_P09 | 2021_22_Q2 | 2022_23_Q3 | Standards of service
G100502380 | 502380 | Water | G100 | Gate 100 | 2021-04-01 | 2021-08-17 | 2021_22_P01 | 2021_22_P05 | 2021_22_Q1 | 2021_22_Q2 | Standards of service
G100502883 | 502883 | Wastewater | G100 | Gate 100 | 2025-06-30 | 2025-04-01 | 2025_26_P03 | 2025_26_P01 | 2025_26_Q1 | 2025_26_Q1 | Standards of service
G100502689 | 502689 | Wastewater | G100 | Gate 100 | 2026-01-18 | 2025-10-20 | 2025_26_P10 | 2025_26_P07 | 2025_26_Q4 | 2025_26_Q3 | Standards of service
G100502783 | 502783 | Water | G100 | Gate 100 | 2022-06-23 | 2025-06-16 | 2022_23_P03 | 2025_26_P03 | 2022_23_Q1 | 2025_26_Q1 | Standards of service
G100502955 | 502955 | Wastewater | G100 | Gate 100 | 2025-01-12 | 2024-03-12 | 2024_25_P10 | 2023_24_P12 | 2024_25_Q4 | 2023_24_Q4 | Standards of service
G100502853 | 502853 | Water | G100 | Gate 100 | 2022-10-26 | 2022-08-24 | 2022_23_P07 | 2022_23_P05 | 2022_23_Q3 | 2022_23_Q2 | Standards of service
G100502649 | 502649 | Water | G100 | Gate 100 | 2023-01-30 | 2024-05-03 | 2022_23_P10 | 2024_25_P02 | 2022_23_Q4 | 2024_25_Q1 | Drinking Water
G100502650 | 502650 | Water | G100 | Gate 100 | 2022-06-16 | 2023-06-30 | 2022_23_P03 | 2023_24_P03 | 2022_23_Q1 | 2023_24_Q1 | Drinking Water
G100503050 | 503050 | Water | G100 | Gate 100 | 2022-08-25 | 2023-03-29 | 2022_23_P05 | 2022_23_P12 | 2022_23_Q2 | 2022_23_Q4 | Standards of service
G100502946 | 502946 | Wastewater | G100 | Gate 100 | 2021-12-03 | 2022-12-21 | 2021_22_P09 | 2022_23_P09 | 2021_22_Q3 | 2022_23_Q3 | Environment
G100502949 | 502949 | Wastewater | G100 | Gate 100 | 2022-03-01 | 2024-01-22 | 2021_22_P12 | 2023_24_P10 | 2021_22_Q4 | 2023_24_Q4 | Supporting Sustainable Economic Growth
G100502947 | 502947 | Wastewater | G100 | Gate 100 | 2021-07-26 | 2021-09-29 | 2021_22_P04 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2 | Environment
G100502740 | 502740 | Wastewater | G100 | Gate 100 | 2021-08-27 | 2021-06-02 | 2021_22_P05 | 2021_22_P03 | 2021_22_Q2 | 2021_22_Q1 | Standards of service
G100502392 | 502392 | Water | G100 | Gate 100 | 2022-03-01 | 2022-03-22 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4 | Supporting Sustainable Economic Growth
G100502746 | 502746 | Wastewater | G100 | Gate 100 | 2025-04-22 | 2024-10-09 | 2025_26_P01 | 2024_25_P07 | 2025_26_Q1 | 2024_25_Q3 | Standards of service
G100502749 | 502749 | Wastewater | G100 | Gate 100 | 2022-05-10 | 2022-11-29 | 2022_23_P02 | 2022_23_P08 | 2022_23_Q1 | 2022_23_Q3 | Standards of service
G100503120 | 503120 | Support Services | G100 | Gate 100 | 2021-07-28 | 2021-12-22 | 2021_22_P04 | 2021_22_P09 | 2021_22_Q2 | 2021_22_Q3 | Security & Resilience
G100502877 | 502877 | Wastewater | G100 | Gate 100 | 2025-02-24 | 2024-11-26 | 2024_25_P11 | 2024_25_P08 | 2024_25_Q4 | 2024_25_Q3 | Standards of service
G100502857 | 502857 | Water | G100 | Gate 100 | 2023-06-20 | 2023-09-26 | 2023_24_P03 | 2023_24_P06 | 2023_24_Q1 | 2023_24_Q2 | Standards of service
G100502808 | 502808 | Water | G100 | Gate 100 | 2021-11-02 | 2021-12-01 | 2021_22_P08 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
G100503199 | 503199 | Water | G100 | Gate 100 | 2021-09-30 | 2021-09-30 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
G100503200 | 503200 | Water | G100 | Gate 100 | 2021-06-17 | 2021-09-03 | 2021_22_P03 | 2021_22_P06 | 2021_22_Q1 | 2021_22_Q2 | Standards of service
G100503194 | 503194 | Water | G100 | Gate 100 | 2021-04-27 | 2021-06-30 | 2021_22_P01 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1 | Standards of service
G100503256 | 503256 | Water | G100 | Gate 100 | 2021-06-29 | 2021-07-29 | 2021_22_P03 | 2021_22_P04 | 2021_22_Q1 | 2021_22_Q2 | Standards of service
G100503257 | 503257 | Water | G100 | Gate 100 | 2021-04-30 | 2021-03-31 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4 | Standards of service
G100503132 | 503132 | Wastewater | G100 | Gate 100 | 2026-04-07 | 2026-02-11 | 2026_27_P01 | 2025_26_P11 | 2026_27_Q1 | 2025_26_Q4 | Standards of service
G100503177 | 503177 | Wastewater | G100 | Gate 100 | 2021-11-17 | 2021-10-26 | 2021_22_P08 | 2021_22_P07 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
G100503234 | 503234 | Water | G100 | Gate 100 | 2021-12-20 | 2021-12-06 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
G100503235 | 503235 | Water | G100 | Gate 100 | 2022-11-30 | 2024-11-19 | 2022_23_P08 | 2024_25_P08 | 2022_23_Q3 | 2024_25_Q3 | Standards of service
G100503249 | 503249 | Water | G100 | Gate 100 | 2021-04-21 | 2022-03-10 | 2021_22_P01 | 2021_22_P12 | 2021_22_Q1 | 2021_22_Q4 | Standards of service
G100503162 | 503162 | Water | G100 | Gate 100 | 2022-08-09 | 2024-04-01 | 2022_23_P05 | 2024_25_P01 | 2022_23_Q2 | 2024_25_Q1 | Standards of service
G100503195 | 503195 | Water | G100 | Gate 100 | 2022-08-30 | 2021-09-30 | 2022_23_P05 | 2021_22_P06 | 2022_23_Q2 | 2021_22_Q2 | Standards of service
G100503197 | 503197 | Water | G100 | Gate 100 | 2021-09-30 | 2021-09-30 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
G100502600 | 502600 | Water | G100 | Gate 100 | 2022-01-10 | 2022-10-21 | 2021_22_P10 | 2022_23_P07 | 2021_22_Q4 | 2022_23_Q3 | Standards of service
G100502943 | 502943 | Wastewater | G100 | Gate 100 | 2021-09-06 | 2022-05-31 | 2021_22_P06 | 2022_23_P02 | 2021_22_Q2 | 2022_23_Q1 | Environment
G100503056 | 503056 | Water | G100 | Gate 100 | 2025-03-13 | 2024-12-13 | 2024_25_P12 | 2024_25_P09 | 2024_25_Q4 | 2024_25_Q3 | Standards of service
G100503092 | 503092 | Water | G100 | Gate 100 | 2024-03-14 | 2024-03-27 | 2023_24_P12 | 2023_24_P12 | 2023_24_Q4 | 2023_24_Q4 | Standards of service
G100503045 | 503045 | Wastewater | G100 | Gate 100 | 2021-07-02 | 2021-08-26 | 2021_22_P04 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2 | Supporting Sustainable Economic Growth
G100503480 | 503480 | Water | G100 | Gate 100 | 2024-08-14 | 2024-09-13 | 2024_25_P05 | 2024_25_P06 | 2024_25_Q2 | 2024_25_Q2 | Standards of service
G100503110 | 503110 | Water | G100 | Gate 100 | 2023-05-27 | 2023-03-30 | 2023_24_P02 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4 | Drinking Water
G100503121 | 503121 | Support Services | G100 | Gate 100 | 2021-07-28 | 2022-01-20 | 2021_22_P04 | 2021_22_P10 | 2021_22_Q2 | 2021_22_Q4 | Security & Resilience
G100503291 | 503291 | Support Services | G100 | Gate 100 | 2021-07-28 | 2022-04-05 | 2021_22_P04 | 2022_23_P01 | 2021_22_Q2 | 2022_23_Q1 | Security & Resilience
G100503230 | 503230 | Wastewater | G100 | Gate 100 | 2023-06-20 | 2023-03-30 | 2023_24_P03 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4 | Standards of service
G100503094 | 503094 | Water | G100 | Gate 100 | 2021-04-01 | 2021-03-31 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4 | Environment
G100503229 | 503229 | Wastewater | G100 | Gate 100 | 2021-12-10 | 2021-12-20 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
G100503336 | 503336 | Water | G100 | Gate 100 | 2022-11-01 | 2024-03-22 | 2022_23_P08 | 2023_24_P12 | 2022_23_Q3 | 2023_24_Q4 | Standards of service
G100502940 | 502940 | Water | G100 | Gate 100 | 2021-10-04 | 2023-03-22 | 2021_22_P07 | 2022_23_P12 | 2021_22_Q3 | 2022_23_Q4 | Standards of service
G100503393 | 503393 | Wastewater | G100 | Gate 100 | 2021-11-03 | 2022-01-17 | 2021_22_P08 | 2021_22_P10 | 2021_22_Q3 | 2021_22_Q4 | Standards of service
G100503198 | 503198 | Water | G100 | Gate 100 | 2021-09-30 | 2021-09-30 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
G100503362 | 503362 | Wastewater | G100 | Gate 100 | 2021-09-01 | 2024-08-27 | 2021_22_P06 | 2024_25_P05 | 2021_22_Q2 | 2024_25_Q2 | Supporting Sustainable Economic Growth
G100503525 | 503525 | CE&FS | G100 | Gate 100 | 2025-09-29 | 2025-07-01 | 2025_26_P06 | 2025_26_P04 | 2025_26_Q2 | 2025_26_Q2 | Standards of service
G100503441 | 503441 | Wastewater | G100 | Gate 100 | 2023-08-20 | 2023-05-30 | 2023_24_P05 | 2023_24_P02 | 2023_24_Q2 | 2023_24_Q1 | Supporting Sustainable Economic Growth
G100503408 | 503408 | Water | G100 | Gate 100 | 2022-11-30 | 2022-08-26 | 2022_23_P08 | 2022_23_P05 | 2022_23_Q3 | 2022_23_Q2 | Standards of service
G100503238 | 503238 | Water | G100 | Gate 100 | 2025-09-24 | 2025-06-26 | 2025_26_P06 | 2025_26_P03 | 2025_26_Q2 | 2025_26_Q1 | Standards of service
G100503250 | 503250 | Water | G100 | Gate 100 | 2021-07-30 | 2021-07-29 | 2021_22_P04 | 2021_22_P04 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
G100503239 | 503239 | Water | G100 | Gate 100 | 2021-09-01 | 2022-03-25 | 2021_22_P06 | 2021_22_P12 | 2021_22_Q2 | 2021_22_Q4 | Supporting Sustainable Economic Growth
G100503236 | 503236 | Water | G100 | Gate 100 | 2021-04-06 | 2021-03-31 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4 | Standards of service
G100503269 | 503269 | Wastewater | G100 | Gate 100 | 2022-05-18 | 2022-08-29 | 2022_23_P02 | 2022_23_P05 | 2022_23_Q1 | 2022_23_Q2 | Standards of service
G100503412 | 503412 | Water | G100 | Gate 100 | 2021-09-30 | 2021-09-30 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
G100503413 | 503413 | Water | G100 | Gate 100 | 2021-09-30 | 2021-09-21 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
G100503434 | 503434 | Water | G100 | Gate 100 | 2022-03-31 | 2022-10-31 | 2021_22_P12 | 2022_23_P07 | 2021_22_Q4 | 2022_23_Q3 | Standards of service
G100503562 | 503562 | Water | G100 | Gate 100 | 2021-09-10 | 2022-01-31 | 2021_22_P06 | 2021_22_P10 | 2021_22_Q2 | 2021_22_Q4 | Drinking Water
G100503571 | 503571 | Wastewater | G100 | Gate 100 | 2022-03-31 | 2022-11-25 | 2021_22_P12 | 2022_23_P08 | 2021_22_Q4 | 2022_23_Q3 | Standards of service
G100503564 | 503564 | Wastewater | G100 | Gate 100 | 2022-02-03 | 2022-06-30 | 2021_22_P11 | 2022_23_P03 | 2021_22_Q4 | 2022_23_Q1 | Supporting Sustainable Economic Growth
G100503415 | 503415 | Wastewater | G100 | Gate 100 | 2022-04-22 | 2023-01-18 | 2022_23_P01 | 2022_23_P10 | 2022_23_Q1 | 2022_23_Q4 | Standards of service
G100503418 | 503418 | Wastewater | G100 | Gate 100 | 2021-09-30 | 2021-10-12 | 2021_22_P06 | 2021_22_P07 | 2021_22_Q2 | 2021_22_Q3 | Standards of service
G100503421 | 503421 | Water | G100 | Gate 100 | 2023-04-05 | 2023-08-30 | 2023_24_P01 | 2023_24_P05 | 2023_24_Q1 | 2023_24_Q2 | Drinking Water
G100503587 | 503587 | Water | G100 | Gate 100 | 2021-10-30 | 2022-06-30 | 2021_22_P07 | 2022_23_P03 | 2021_22_Q3 | 2022_23_Q1 | Standards of service
G100503594 | 503594 | Wastewater | G100 | Gate 100 | 2024-10-06 | 2024-12-20 | 2024_25_P07 | 2024_25_P09 | 2024_25_Q3 | 2024_25_Q3 | Standards of service
G100503595 | 503595 | Water | G100 | Gate 100 | 2022-03-29 | 2024-07-01 | 2021_22_P12 | 2024_25_P04 | 2021_22_Q4 | 2024_25_Q2 | Standards of service
G100503628 | 503628 | Water | G100 | Gate 100 | 2026-02-19 | 2025-11-21 | 2025_26_P11 | 2025_26_P08 | 2025_26_Q4 | 2025_26_Q3 | Drinking Water
G100503630 | 503630 | Water | G100 | Gate 100 | 2021-09-30 | 2021-09-30 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2 | Standards of service
G100503631 | 503631 | Water | G100 | Gate 100 | 2022-01-27 | 2022-03-24 | 2021_22_P10 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
G100503638 | 503638 | Wastewater | G100 | Gate 100 | 2024-03-21 | 2025-06-20 | 2023_24_P12 | 2025_26_P03 | 2023_24_Q4 | 2025_26_Q1 | Standards of service
G100503632 | 503632 | Water | G100 | Gate 100 | 2022-07-05 | 2022-08-31 | 2022_23_P04 | 2022_23_P05 | 2022_23_Q2 | 2022_23_Q2 | Standards of service
G100503613 | 503613 | Water | G100 | Gate 100 | 2026-04-09 | 2024-12-02 | 2026_27_P01 | 2024_25_P09 | 2026_27_Q1 | 2024_25_Q3 | Standards of service
G100503617 | 503617 | Water | G100 | Gate 100 | 2022-03-17 | 2022-03-28 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
G100503543 | 503543 | Wastewater | G100 | Gate 100 | 2021-09-21 | 2022-03-30 | 2021_22_P06 | 2021_22_P12 | 2021_22_Q2 | 2021_22_Q4 | Environment
G100503545 | 503545 | Wastewater | G100 | Gate 100 | 2021-09-21 | 2022-02-16 | 2021_22_P06 | 2021_22_P11 | 2021_22_Q2 | 2021_22_Q4 | Environment
G100503546 | 503546 | Wastewater | G100 | Gate 100 | 2021-09-21 | 2021-08-24 | 2021_22_P06 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2 | Environment
G100503656 | 503656 | Wastewater | G100 | Gate 100 | 2026-08-17 | 2023-12-07 | 2026_27_P05 | 2023_24_P09 | 2026_27_Q2 | 2023_24_Q3 | Standards of service
G100503678 | 503678 | Water | G100 | Gate 100 | 2024-01-16 | 2026-09-11 | 2023_24_P10 | 2026_27_P06 | 2023_24_Q4 | 2026_27_Q2 | Standards of service
G100503680 | 503680 | Water | G100 | Gate 100 | 2026-03-19 | 2025-12-19 | 2025_26_P12 | 2025_26_P09 | 2025_26_Q4 | 2025_26_Q3 | Standards of service
G100503681 | 503681 | Water | G100 | Gate 100 | 2025-08-27 | 2025-05-29 | 2025_26_P05 | 2025_26_P02 | 2025_26_Q2 | 2025_26_Q1 | Standards of service
G100503733 | 503733 | Water | G100 | Gate 100 | 2022-05-31 | 2022-03-14 | 2022_23_P02 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4 | Standards of service
G100503686 | 503686 | Water | G100 | Gate 100 | 2023-08-31 | 2022-12-19 | 2023_24_P05 | 2022_23_P09 | 2023_24_Q2 | 2022_23_Q3 | Standards of service
G100503714 | 503714 | Water | G100 | Gate 100 | 2024-03-17 | 2023-12-12 | 2023_24_P12 | 2023_24_P09 | 2023_24_Q4 | 2023_24_Q3 | Standards of service
G100503716 | 503716 | Water | G100 | Gate 100 | 2022-04-30 | 2021-12-02 | 2022_23_P01 | 2021_22_P09 | 2022_23_Q1 | 2021_22_Q3 | Standards of service
G100503730 | 503730 | Water | G100 | Gate 100 | 2023-10-26 | 2022-12-20 | 2023_24_P07 | 2022_23_P09 | 2023_24_Q3 | 2022_23_Q3 | Standards of service
G100503731 | 503731 | Water | G100 | Gate 100 | 2022-08-23 | 2022-09-22 | 2022_23_P05 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2 | Standards of service
G100503732 | 503732 | Water | G100 | Gate 100 | 2024-06-20 | 2024-05-21 | 2024_25_P03 | 2024_25_P02 | 2024_25_Q1 | 2024_25_Q1 | Standards of service
G100503726 | 503726 | Water | G100 | Gate 100 | 2021-10-06 | 2021-11-29 | 2021_22_P07 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
G100503753 | 503753 | Wastewater | G100 | Gate 100 | 2025-04-27 | 2025-01-27 | 2025_26_P01 | 2024_25_P10 | 2025_26_Q1 | 2024_25_Q4 | Standards of service
G100503727 | 503727 | Water | G100 | Gate 100 | 2022-02-15 | 2022-01-31 | 2021_22_P11 | 2021_22_P10 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
G100503728 | 503728 | Water | G100 | Gate 100 | 2021-06-30 | 2021-06-09 | 2021_22_P03 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1 | Standards of service
G100503701 | 503701 | Wastewater | G100 | Gate 100 | 2021-05-14 | 2021-05-28 | 2021_22_P02 | 2021_22_P02 | 2021_22_Q1 | 2021_22_Q1 | Standards of service
G100503761 | 503761 | Water | G100 | Gate 100 | 2023-06-19 | 2023-03-27 | 2023_24_P03 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4 | Drinking Water
G100503699 | 503699 | Water | G100 | Gate 100 | 2025-07-21 | 2025-04-15 | 2025_26_P04 | 2025_26_P01 | 2025_26_Q2 | 2025_26_Q1 | Standards of service
G100503860 | 503860 | Wastewater | G100 | Gate 100 | 2022-07-28 | 2022-09-01 | 2022_23_P04 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2 | Standards of service
G100504068 | 504068 | Water | G100 | Gate 100 | 2026-01-13 | 2025-10-15 | 2025_26_P10 | 2025_26_P07 | 2025_26_Q4 | 2025_26_Q3 | Standards of service
G100504203 | 504203 | Water | G100 | Gate 100 | 2027-01-12 | 2026-10-14 | 2026_27_P10 | 2026_27_P07 | 2026_27_Q4 | 2026_27_Q3 | Standards of service
G100504391 | 504391 | Water | G100 | Gate 100 | 2028-02-13 | 2027-07-20 | 2027_28_P11 | 2027_28_P04 | 2027_28_Q4 | 2027_28_Q2 | Drinking Water
G100504434 | 504434 | Water | G100 | Gate 100 | 2021-11-18 | 2021-11-29 | 2021_22_P08 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
G100504465 | 504465 | Water | G100 | Gate 100 | 2024-04-17 | 2024-09-06 | 2024_25_P01 | 2024_25_P06 | 2024_25_Q1 | 2024_25_Q2 | Standards of service
G100505032 | 505032 | Water | G100 | Gate 100 | 2021-12-10 | 2022-03-18 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4 | Supporting Sustainable Economic Growth
G100504995 | 504995 | Water | G100 | Gate 100 | 2024-10-24 | 2024-07-26 | 2024_25_P07 | 2024_25_P04 | 2024_25_Q3 | 2024_25_Q2 | Standards of service
G100505053 | 505053 | Wastewater | G100 | Gate 100 | 2023-08-02 | 2023-05-29 | 2023_24_P05 | 2023_24_P02 | 2023_24_Q2 | 2023_24_Q1 | Standards of service
G100505339 | 505339 | Wastewater | G100 | Gate 100 | 2025-10-02 | 2025-07-04 | 2025_26_P07 | 2025_26_P04 | 2025_26_Q3 | 2025_26_Q2 | Standards of service
G100505384 | 505384 | Water | G100 | Gate 100 | 2024-01-19 | 2023-12-01 | 2023_24_P10 | 2023_24_P09 | 2023_24_Q4 | 2023_24_Q3 | Standards of service
G100505447 | 505447 | Water | G100 | Gate 100 | 2023-06-11 | 2023-02-28 | 2023_24_P03 | 2022_23_P11 | 2023_24_Q1 | 2022_23_Q4 | Standards of service
G100505504 | 505504 | Water | G100 | Gate 100 | 2022-12-05 | 2023-03-31 | 2022_23_P09 | 2022_23_P12 | 2022_23_Q3 | 2022_23_Q4 | Standards of service
G100505687 | 505687 | Wastewater | G100 | Gate 100 | 2024-02-28 | 2023-12-12 | 2023_24_P11 | 2023_24_P09 | 2023_24_Q4 | 2023_24_Q3 | Supporting Sustainable Economic Growth
G100505693 | 505693 | Water | G100 | Gate 100 | 2024-02-26 | 2023-06-29 | 2023_24_P11 | 2023_24_P03 | 2023_24_Q4 | 2023_24_Q1 | Standards of service
G100505641 | 505641 | Wastewater | G100 | Gate 100 | 2022-12-14 | 2023-03-17 | 2022_23_P09 | 2022_23_P12 | 2022_23_Q3 | 2022_23_Q4 | Standards of service
G100505927 | 505927 | Water | G100 | Gate 100 | 2024-04-08 | 2023-12-13 | 2024_25_P01 | 2023_24_P09 | 2024_25_Q1 | 2023_24_Q3 | Standards of service
G100505949 | 505949 | Wastewater | G100 | Gate 100 | 2025-03-20 | 2024-12-20 | 2024_25_P12 | 2024_25_P09 | 2024_25_Q4 | 2024_25_Q3 | Standards of service
G100506029 | 506029 | Water | G100 | Gate 100 | 2024-06-19 | 2024-05-24 | 2024_25_P03 | 2024_25_P02 | 2024_25_Q1 | 2024_25_Q1 | Standards of service
G100506032 | 506032 | Water | G100 | Gate 100 | 2024-07-29 | 2024-12-20 | 2024_25_P04 | 2024_25_P09 | 2024_25_Q2 | 2024_25_Q3 | Standards of service
G100506149 | 506149 | Water | G100 | Gate 100 | 2024-03-17 | 2024-12-17 | 2023_24_P12 | 2024_25_P09 | 2023_24_Q4 | 2024_25_Q3 | Standards of service
G100506151 | 506151 | Water | G100 | Gate 100 | 2024-11-24 | 2024-10-10 | 2024_25_P08 | 2024_25_P07 | 2024_25_Q3 | 2024_25_Q3 | Standards of service
G100506130 | 506130 | Water | G100 | Gate 100 | 2027-05-16 | 2027-02-15 | 2027_28_P02 | 2026_27_P11 | 2027_28_Q1 | 2026_27_Q4 | Standards of service
G100506234 | 506234 | Water | G100 | Gate 100 | 2023-07-02 | 2022-09-29 | 2023_24_P04 | 2022_23_P06 | 2023_24_Q2 | 2022_23_Q2 | Standards of service
G100506186 | 506186 | Water | G100 | Gate 100 | 2025-05-27 | 2025-06-13 | 2025_26_P02 | 2025_26_P03 | 2025_26_Q1 | 2025_26_Q1 | Standards of service
G100506232 | 506232 | Water | G100 | Gate 100 | 2023-07-02 | 2023-03-28 | 2023_24_P04 | 2022_23_P12 | 2023_24_Q2 | 2022_23_Q4 | Standards of service
G100506228 | 506228 | Water | G100 | Gate 100 | 2023-07-02 | 2023-05-31 | 2023_24_P04 | 2023_24_P02 | 2023_24_Q2 | 2023_24_Q1 | Standards of service
G100506231 | 506231 | Water | G100 | Gate 100 | 2024-09-15 | 2024-03-21 | 2024_25_P06 | 2023_24_P12 | 2024_25_Q2 | 2023_24_Q4 | Standards of service
G100506275 | 506275 | Water | G100 | Gate 100 | 2024-01-21 | 2023-10-31 | 2023_24_P10 | 2023_24_P07 | 2023_24_Q4 | 2023_24_Q3 | Standards of service
G100506271 | 506271 | Water | G100 | Gate 100 | 2024-09-04 | 2025-02-06 | 2024_25_P06 | 2024_25_P11 | 2024_25_Q2 | 2024_25_Q4 | Standards of service
G100506422 | 506422 | Support Services | G100 | Gate 100 | 2023-10-19 | 2023-08-17 | 2023_24_P07 | 2023_24_P05 | 2023_24_Q3 | 2023_24_Q2 | Security & Resilience
G100506586 | 506586 | Wastewater | G100 | Gate 100 | 2025-07-27 | 2025-01-16 | 2025_26_P04 | 2024_25_P10 | 2025_26_Q2 | 2024_25_Q4 | Environment
G100506608 | 506608 | Water | G100 | Gate 100 | 2023-04-26 | 2023-02-27 | 2023_24_P01 | 2022_23_P11 | 2023_24_Q1 | 2022_23_Q4 | Standards of service
G100506618 | 506618 | Water | G100 | Gate 100 | 2024-02-21 | 2023-12-22 | 2023_24_P11 | 2023_24_P09 | 2023_24_Q4 | 2023_24_Q3 | Standards of service
G100506684 | 506684 | Water | G100 | Gate 100 | 2023-03-24 | 2022-11-04 | 2022_23_P12 | 2022_23_P08 | 2022_23_Q4 | 2022_23_Q3 | Standards of service
G100506779 | 506779 | Water | G100 | Gate 100 | 2024-01-18 | 2024-05-14 | 2023_24_P10 | 2024_25_P02 | 2023_24_Q4 | 2024_25_Q1 | Standards of service
G100506864 | 506864 | Water | G100 | Gate 100 | 2023-03-01 | 2023-09-28 | 2022_23_P12 | 2023_24_P06 | 2022_23_Q4 | 2023_24_Q2 | Supporting Sustainable Economic Growth
G100506865 | 506865 | Wastewater | G100 | Gate 100 | 2023-03-01 | 2023-09-28 | 2022_23_P12 | 2023_24_P06 | 2022_23_Q4 | 2023_24_Q2 | Supporting Sustainable Economic Growth
G100506896 | 506896 | Support Services | G100 | Gate 100 | 2021-09-30 | 2022-01-18 | 2021_22_P06 | 2021_22_P10 | 2021_22_Q2 | 2021_22_Q4 | Standards of service
G100507057 | 507057 | Water | G100 | Gate 100 | 2023-12-17 | 2023-09-22 | 2023_24_P09 | 2023_24_P06 | 2023_24_Q3 | 2023_24_Q2 | Standards of service
G100507186 | 507186 | Water | G100 | Gate 100 | 2023-07-16 | 2023-02-28 | 2023_24_P04 | 2022_23_P11 | 2023_24_Q2 | 2022_23_Q4 | Standards of service
G100507189 | 507189 | Water | G100 | Gate 100 | 2023-12-18 | 2023-06-28 | 2023_24_P09 | 2023_24_P03 | 2023_24_Q3 | 2023_24_Q1 | Standards of service
G100507173 | 507173 | Support Services | G100 | Gate 100 | 2021-08-02 | 2021-12-21 | 2021_22_P05 | 2021_22_P09 | 2021_22_Q2 | 2021_22_Q3 | Security & Resilience
G100507209 | 507209 | Wastewater | G100 | Gate 100 | 2025-01-30 | 2024-09-03 | 2024_25_P10 | 2024_25_P06 | 2024_25_Q4 | 2024_25_Q2 | Standards of service
G100507455 | 507455 | Water | G100 | Gate 100 | 2024-04-30 | 2024-03-13 | 2024_25_P01 | 2023_24_P12 | 2024_25_Q1 | 2023_24_Q4 | Supporting Sustainable Economic Growth
G100507492 | 507492 | Water | G100 | Gate 100 | 2025-05-29 | 2025-06-06 | 2025_26_P02 | 2025_26_P03 | 2025_26_Q1 | 2025_26_Q1 | Standards of service
G100507493 | 507493 | Water | G100 | Gate 100 | 2024-04-16 | 2023-08-08 | 2024_25_P01 | 2023_24_P05 | 2024_25_Q1 | 2023_24_Q2 | Standards of service
G100507813 | 507813 | Water | G100 | Gate 100 | 2022-04-25 | 2022-03-31 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4 | Standards of service
G100507860 | 507860 | Water | G100 | Gate 100 | 2022-05-15 | 2021-12-15 | 2022_23_P02 | 2021_22_P09 | 2022_23_Q1 | 2021_22_Q3 | Standards of service
G100507808 | 507808 | Wastewater | G100 | Gate 100 | 2024-12-05 | 2024-12-12 | 2024_25_P09 | 2024_25_P09 | 2024_25_Q3 | 2024_25_Q3 | Supporting Sustainable Economic Growth
G100507933 | 507933 | Wastewater | G100 | Gate 100 | 2022-11-16 | 2022-12-22 | 2022_23_P08 | 2022_23_P09 | 2022_23_Q3 | 2022_23_Q3 | Standards of service
G100508109 | 508109 | Support Services | G100 | Gate 100 | 2021-05-14 | 2021-12-07 | 2021_22_P02 | 2021_22_P09 | 2021_22_Q1 | 2021_22_Q3 | Standards of service
G100508601 | 508601 | Wastewater | G100 | Gate 100 | 2022-06-12 | 2022-06-01 | 2022_23_P03 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1 | Standards of service
G100508752 | 508752 | Wastewater | G100 | Gate 100 | 2024-05-08 | 2024-10-04 | 2024_25_P02 | 2024_25_P07 | 2024_25_Q1 | 2024_25_Q3 | Supporting Sustainable Economic Growth
G100508949 | 508949 | Water | G100 | Gate 100 | 2026-10-04 | 2026-07-06 | 2026_27_P07 | 2026_27_P04 | 2026_27_Q3 | 2026_27_Q2 | Supporting Sustainable Economic Growth
G100509283 | 509283 | Water | G100 | Gate 100 | 2022-06-04 | 2022-06-29 | 2022_23_P03 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1 | Standards of service
G100510392 | 510392 | Wastewater | G100 | Gate 100 | 2023-09-01 | 2023-06-13 | 2023_24_P06 | 2023_24_P03 | 2023_24_Q2 | 2023_24_Q1 | Standards of service
G100510546 | 510546 | Wastewater | G100 | Gate 100 | 2025-06-26 | 2025-04-22 | 2025_26_P03 | 2025_26_P01 | 2025_26_Q1 | 2025_26_Q1 | Standards of service
G100510727 | 510727 | Support Services | G100 | Gate 100 | 2022-11-04 | 2024-05-07 | 2022_23_P08 | 2024_25_P02 | 2022_23_Q3 | 2024_25_Q1 | Standards of service
G100510931 | 510931 | Water | G100 | Gate 100 | 2023-11-16 | 2023-04-27 | 2023_24_P08 | 2023_24_P01 | 2023_24_Q3 | 2023_24_Q1 | Standards of service
G100511334 | 511334 | Water | G100 | Gate 100 | 2024-01-15 | 2023-07-14 | 2023_24_P10 | 2023_24_P04 | 2023_24_Q4 | 2023_24_Q2 | Standards of service
G100511344 | 511344 | Support Services | G100 | Gate 100 | 2024-04-17 | 2022-10-25 | 2024_25_P01 | 2022_23_P07 | 2024_25_Q1 | 2022_23_Q3 | Standards of service
G100511495 | 511495 | Water | G100 | Gate 100 | 2024-07-21 | 2024-07-31 | 2024_25_P04 | 2024_25_P04 | 2024_25_Q2 | 2024_25_Q2 | Drinking Water
G100511500 | 511500 | Water | G100 | Gate 100 | 2023-12-26 | 2024-03-28 | 2023_24_P09 | 2023_24_P12 | 2023_24_Q3 | 2023_24_Q4 | Drinking Water
G100511704 | 511704 | Water | G100 | Gate 100 | 2024-01-04 | 2023-07-31 | 2023_24_P10 | 2023_24_P04 | 2023_24_Q4 | 2023_24_Q2 | Standards of service
G100512469 | 512469 | Water | G100 | Gate 100 | 2023-10-26 | 2023-09-07 | 2023_24_P07 | 2023_24_P06 | 2023_24_Q3 | 2023_24_Q2 | Drinking Water
G100512555 | 512555 | Wastewater | G100 | Gate 100 | 2025-10-09 | 2025-12-22 | 2025_26_P07 | 2025_26_P09 | 2025_26_Q3 | 2025_26_Q3 | Supporting Sustainable Economic Growth
G100512600 | 512600 | Water | G100 | Gate 100 | 2023-08-24 | 2023-03-24 | 2023_24_P05 | 2022_23_P12 | 2023_24_Q2 | 2022_23_Q4 | Supporting Sustainable Economic Growth
G100512639 | 512639 | Support Services | G100 | Gate 100 | 2024-01-28 | 2024-07-01 | 2023_24_P10 | 2024_25_P04 | 2023_24_Q4 | 2024_25_Q2 | Standards of service
G100512749 | 512749 | Water | G100 | Gate 100 | 2023-11-30 | 2023-03-23 | 2023_24_P08 | 2022_23_P12 | 2023_24_Q3 | 2022_23_Q4 | Standards of service
G100512711 | 512711 | Water | G100 | Gate 100 | 2023-09-10 | 2023-03-31 | 2023_24_P06 | 2022_23_P12 | 2023_24_Q2 | 2022_23_Q4 | Standards of service
G100512815 | 512815 | Water | G100 | Gate 100 | 2024-10-13 | 2024-11-25 | 2024_25_P07 | 2024_25_P08 | 2024_25_Q3 | 2024_25_Q3 | Standards of service
G100512940 | 512940 | Water | G100 | Gate 100 | 2024-06-23 | 2023-07-31 | 2024_25_P03 | 2023_24_P04 | 2024_25_Q1 | 2023_24_Q2 | Standards of service
G100512997 | 512997 | Water | G100 | Gate 100 | 2024-08-04 | 2024-03-05 | 2024_25_P05 | 2023_24_P12 | 2024_25_Q2 | 2023_24_Q4 | Supporting Sustainable Economic Growth
G100513208 | 513208 | Water | G100 | Gate 100 | 2024-04-04 | 2023-11-10 | 2024_25_P01 | 2023_24_P08 | 2024_25_Q1 | 2023_24_Q3 | Drinking Water
G100513312 | 513312 | CE&FS | G100 | Gate 100 | 2027-09-16 | 2027-06-18 | 2027_28_P06 | 2027_28_P03 | 2027_28_Q2 | 2027_28_Q1 | Long Term Water Sector Vision
G100513433 | 513433 | Water | G100 | Gate 100 | 2024-02-28 | 2024-12-03 | 2023_24_P11 | 2024_25_P09 | 2023_24_Q4 | 2024_25_Q3 | Drinking Water
G100513412 | 513412 | Wastewater | G100 | Gate 100 | 2025-05-12 | 2025-04-10 | 2025_26_P02 | 2025_26_P01 | 2025_26_Q1 | 2025_26_Q1 | Standards of service
G100513417 | 513417 | Wastewater | G100 | Gate 100 | 2025-06-05 | 2025-03-07 | 2025_26_P03 | 2024_25_P12 | 2025_26_Q1 | 2024_25_Q4 | Standards of service
G100513461 | 513461 | Support Services | G100 | Gate 100 | 2022-08-21 | 2023-03-08 | 2022_23_P05 | 2022_23_P12 | 2022_23_Q2 | 2022_23_Q4 | Standards of service
G100513514 | 513514 | Wastewater | G100 | Gate 100 | 2025-01-20 | 2024-10-22 | 2024_25_P10 | 2024_25_P07 | 2024_25_Q4 | 2024_25_Q3 | Standards of service
G100513826 | 513826 | Water | G100 | Gate 100 | 2024-05-15 | 2024-09-13 | 2024_25_P02 | 2024_25_P06 | 2024_25_Q1 | 2024_25_Q2 | Standards of service
G100513827 | 513827 | Water | G100 | Gate 100 | 2025-10-12 | 2025-07-14 | 2025_26_P07 | 2025_26_P04 | 2025_26_Q3 | 2025_26_Q2 | Standards of service
G100513829 | 513829 | Water | G100 | Gate 100 | 2025-08-31 | 2025-06-30 | 2025_26_P05 | 2025_26_P03 | 2025_26_Q2 | 2025_26_Q1 | Standards of service
G100513832 | 513832 | Support Services | G100 | Gate 100 | 2022-03-31 | 2022-03-28 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
G100513880 | 513880 | Support Services | G100 | Gate 100 | 2025-11-07 | 2025-06-26 | 2025_26_P08 | 2025_26_P03 | 2025_26_Q3 | 2025_26_Q1 | Security & Resilience
G100513923 | 513923 | Water | G100 | Gate 100 | 2023-07-02 | 2025-01-10 | 2023_24_P04 | 2024_25_P10 | 2023_24_Q2 | 2024_25_Q4 | Standards of service
G100513964 | 513964 | Water | G100 | Gate 100 | 2024-05-05 | 2024-03-15 | 2024_25_P02 | 2023_24_P12 | 2024_25_Q1 | 2023_24_Q4 | Standards of service
G100514041 | 514041 | Wastewater | G100 | Gate 100 | 2024-12-12 | 2024-10-04 | 2024_25_P09 | 2024_25_P07 | 2024_25_Q3 | 2024_25_Q3 | Standards of service
G100514045 | 514045 | Wastewater | G100 | Gate 100 | 2024-08-05 | 2024-02-26 | 2024_25_P05 | 2023_24_P11 | 2024_25_Q2 | 2023_24_Q4 | Environment
G100514047 | 514047 | Water | G100 | Gate 100 | 2025-01-12 | 2024-08-23 | 2024_25_P10 | 2024_25_P05 | 2024_25_Q4 | 2024_25_Q2 | Standards of service
G100514080 | 514080 | Water | G100 | Gate 100 | 2024-11-27 | 2025-01-07 | 2024_25_P08 | 2024_25_P10 | 2024_25_Q3 | 2024_25_Q4 | Standards of service
G100514217 | 514217 | Wastewater | G100 | Gate 100 | 2023-07-18 | 2023-03-31 | 2023_24_P04 | 2022_23_P12 | 2023_24_Q2 | 2022_23_Q4 | Standards of service
G100514281 | 514281 | Water | G100 | Gate 100 | 2024-12-26 | 2024-09-27 | 2024_25_P09 | 2024_25_P06 | 2024_25_Q3 | 2024_25_Q2 | Standards of service
G100514282 | 514282 | Water | G100 | Gate 100 | 2025-03-20 | 2024-12-20 | 2024_25_P12 | 2024_25_P09 | 2024_25_Q4 | 2024_25_Q3 | Standards of service
G100514441 | 514441 | Support Services | G100 | Gate 100 | 2024-05-09 | 2023-11-13 | 2024_25_P02 | 2023_24_P08 | 2024_25_Q1 | 2023_24_Q3 | Security & Resilience
G100514448 | 514448 | Wastewater | G100 | Gate 100 | 2024-11-04 | 2024-03-11 | 2024_25_P08 | 2023_24_P12 | 2024_25_Q3 | 2023_24_Q4 | Standards of service
G100514460 | 514460 | Wastewater | G100 | Gate 100 | 2025-07-27 | 2025-04-28 | 2025_26_P04 | 2025_26_P01 | 2025_26_Q2 | 2025_26_Q1 | Standards of service
G100514551 | 514551 | Wastewater | G100 | Gate 100 | 2024-07-02 | 2024-01-23 | 2024_25_P04 | 2023_24_P10 | 2024_25_Q2 | 2023_24_Q4 | Standards of service
G100514598 | 514598 | Support Services | G100 | Gate 100 | 2024-01-22 | 2024-08-08 | 2023_24_P10 | 2024_25_P05 | 2023_24_Q4 | 2024_25_Q2 | Standards of service
G100514631 | 514631 | Wastewater | G100 | Gate 100 | 2023-11-08 | 2023-10-26 | 2023_24_P08 | 2023_24_P07 | 2023_24_Q3 | 2023_24_Q3 | Standards of service
G100514765 | 514765 | Wastewater | G100 | Gate 100 | 2025-03-17 | 2024-12-27 | 2024_25_P12 | 2024_25_P09 | 2024_25_Q4 | 2024_25_Q3 | Standards of service
G100514783 | 514783 | Wastewater | G100 | Gate 100 | 2025-04-06 | 2025-01-06 | 2025_26_P01 | 2024_25_P10 | 2025_26_Q1 | 2024_25_Q4 | Standards of service
G100514831 | 514831 | Wastewater | G100 | Gate 100 | 2025-06-12 | 2025-03-14 | 2025_26_P03 | 2024_25_P12 | 2025_26_Q1 | 2024_25_Q4 | Standards of service
G100515139 | 515139 | Water | G100 | Gate 100 | 2024-03-07 | 2023-10-13 | 2023_24_P12 | 2023_24_P07 | 2023_24_Q4 | 2023_24_Q3 | Standards of service
G100515268 | 515268 | Support Services | G100 | Gate 100 | 2024-08-23 | 2024-09-02 | 2024_25_P05 | 2024_25_P06 | 2024_25_Q2 | 2024_25_Q2 | Security & Resilience
G100515404 | 515404 | CE&FS | G100 | Gate 100 | 2024-12-01 | 2024-09-02 | 2024_25_P09 | 2024_25_P06 | 2024_25_Q3 | 2024_25_Q2 | Climate Change, Adaptation and Mitigation
G100515505 | 515505 | Water | G100 | Gate 100 | 2022-10-19 | 2023-12-22 | 2022_23_P07 | 2023_24_P09 | 2022_23_Q3 | 2023_24_Q3 | Drinking Water
G100515607 | 515607 | Wastewater | G100 | Gate 100 | 2024-10-06 | 2024-07-19 | 2024_25_P07 | 2024_25_P04 | 2024_25_Q3 | 2024_25_Q2 | Standards of service
G100515612 | 515612 | Wastewater | G100 | Gate 100 | 2025-06-02 | 2025-01-13 | 2025_26_P03 | 2024_25_P10 | 2025_26_Q1 | 2024_25_Q4 | Standards of service
G100515625 | 515625 | Support Services | G100 | Gate 100 | 2023-05-03 | 2023-02-28 | 2023_24_P02 | 2022_23_P11 | 2023_24_Q1 | 2022_23_Q4 | Standards of service
G100515827 | 515827 | Wastewater | G100 | Gate 100 | 2024-12-01 | 2025-12-31 | 2024_25_P09 | 2025_26_P09 | 2024_25_Q3 | 2025_26_Q3 | Standards of service
G100516045 | 516045 | Water | G100 | Gate 100 | 2024-10-17 | 2023-12-22 | 2024_25_P07 | 2023_24_P09 | 2024_25_Q3 | 2023_24_Q3 | Standards of service
G100516085 | 516085 | Water | G100 | Gate 100 | 2025-03-12 | 2024-09-13 | 2024_25_P12 | 2024_25_P06 | 2024_25_Q4 | 2024_25_Q2 | Standards of service
G100516082 | 516082 | Water | G100 | Gate 100 | 2025-09-18 | 2025-06-20 | 2025_26_P06 | 2025_26_P03 | 2025_26_Q2 | 2025_26_Q1 | Standards of service
G100516517 | 516517 | Water | G100 | Gate 100 | 2025-05-28 | 2024-11-20 | 2025_26_P02 | 2024_25_P08 | 2025_26_Q1 | 2024_25_Q3 | Standards of service
G100516502 | 516502 | Water | G100 | Gate 100 | 2022-12-28 | 2023-02-27 | 2022_23_P09 | 2022_23_P11 | 2022_23_Q3 | 2022_23_Q4 | Drinking Water
G100516563 | 516563 | Wastewater | G100 | Gate 100 | 2026-02-12 | 2025-11-14 | 2025_26_P11 | 2025_26_P08 | 2025_26_Q4 | 2025_26_Q3 | Standards of service
G100516659 | 516659 | Wastewater | G100 | Gate 100 | 2023-10-10 | 2024-03-08 | 2023_24_P07 | 2023_24_P12 | 2023_24_Q3 | 2023_24_Q4 | Climate Change, Adaptation and Mitigation
G100516857 | 516857 | Wastewater | G100 | Gate 100 | 2024-07-17 | 2024-04-18 | 2024_25_P04 | 2024_25_P01 | 2024_25_Q2 | 2024_25_Q1 | Standards of service
G100517345 | 517345 | CE&FS | G100 | Gate 100 | 2026-03-19 | 2025-12-19 | 2025_26_P12 | 2025_26_P09 | 2025_26_Q4 | 2025_26_Q3 | Climate Change, Adaptation and Mitigation
G100517325 | 517325 | Wastewater | G100 | Gate 100 | 2025-07-17 | 2025-04-18 | 2025_26_P04 | 2025_26_P01 | 2025_26_Q2 | 2025_26_Q1 | Standards of service
G100517533 | 517533 | Water | G100 | Gate 100 | 2025-09-16 | 2025-06-18 | 2025_26_P06 | 2025_26_P03 | 2025_26_Q2 | 2025_26_Q1 | Drinking Water
G100517567 | 517567 | Support Services | G100 | Gate 100 | 2024-11-04 | 2024-06-03 | 2024_25_P08 | 2024_25_P03 | 2024_25_Q3 | 2024_25_Q1 | Standards of service
G100517996 | 517996 | Water | G100 | Gate 100 | 2025-04-28 | 2023-12-22 | 2025_26_P01 | 2023_24_P09 | 2025_26_Q1 | 2023_24_Q3 | Standards of service
G100518147 | 518147 | Water | G100 | Gate 100 | 2025-09-21 | 2025-05-23 | 2025_26_P06 | 2025_26_P02 | 2025_26_Q2 | 2025_26_Q1 | Supporting Sustainable Economic Growth
G100518244 | 518244 | Wastewater | G100 | Gate 100 | 2024-12-30 | 2024-03-21 | 2024_25_P09 | 2023_24_P12 | 2024_25_Q3 | 2023_24_Q4 | Standards of service
G100518444 | 518444 | Water | G100 | Gate 100 | 2023-10-18 | 2023-12-06 | 2023_24_P07 | 2023_24_P09 | 2023_24_Q3 | 2023_24_Q3 | Environment
G100518591 | 518591 | Water | G100 | Gate 100 | 2025-07-10 | 2025-04-11 | 2025_26_P04 | 2025_26_P01 | 2025_26_Q2 | 2025_26_Q1 | Standards of service
G100518579 | 518579 | Wastewater | G100 | Gate 100 | 2024-01-26 | 2023-10-11 | 2023_24_P10 | 2023_24_P07 | 2023_24_Q4 | 2023_24_Q3 | Standards of service
G100518658 | 518658 | Support Services | G100 | Gate 100 | 2025-09-28 | 2026-08-21 | 2025_26_P06 | 2026_27_P05 | 2025_26_Q2 | 2026_27_Q2 | Standards of service
G100518660 | 518660 | Support Services | G100 | Gate 100 | 2025-09-28 | 2026-09-25 | 2025_26_P06 | 2026_27_P06 | 2025_26_Q2 | 2026_27_Q2 | Standards of service
G100518731 | 518731 | Wastewater | G100 | Gate 100 | 2025-02-05 | 2025-01-21 | 2024_25_P11 | 2024_25_P10 | 2024_25_Q4 | 2024_25_Q4 | Standards of service
G100519344 | 519344 | Support Services | G100 | Gate 100 | 2026-04-04 | 2025-11-05 | 2026_27_P01 | 2025_26_P08 | 2026_27_Q1 | 2025_26_Q3 | Standards of service
G100519703 | 519703 | Water | G100 | Gate 100 | 2024-04-11 | 2024-04-01 | 2024_25_P01 | 2024_25_P01 | 2024_25_Q1 | 2024_25_Q1 | Drinking Water
G100519709 | 519709 | Water | G100 | Gate 100 | 2025-10-12 | 2025-10-28 | 2025_26_P07 | 2025_26_P07 | 2025_26_Q3 | 2025_26_Q3 | Standards of service
G100520166 | 520166 | Water | G100 | Gate 100 | 2024-11-28 | 2024-08-30 | 2024_25_P08 | 2024_25_P05 | 2024_25_Q3 | 2024_25_Q2 | Standards of service
G100520228 | 520228 | Water | G100 | Gate 100 | 2024-07-31 | 2024-03-08 | 2024_25_P04 | 2023_24_P12 | 2024_25_Q2 | 2023_24_Q4 | Drinking Water
G100520229 | 520229 | Support Services | G100 | Gate 100 | 2023-08-24 | 2024-03-25 | 2023_24_P05 | 2023_24_P12 | 2023_24_Q2 | 2023_24_Q4 | Standards of service
G100520427 | 520427 | Water | G100 | Gate 100 | 2025-11-06 | 2025-08-08 | 2025_26_P08 | 2025_26_P05 | 2025_26_Q3 | 2025_26_Q2 | Standards of service
G100520459 | 520459 | Support Services | G100 | Gate 100 | 2023-12-28 | 2023-08-29 | 2023_24_P09 | 2023_24_P05 | 2023_24_Q3 | 2023_24_Q2 | Security & Resilience
G100520500 | 520500 | Wastewater | G100 | Gate 100 | 2024-09-19 | 2024-06-21 | 2024_25_P06 | 2024_25_P03 | 2024_25_Q2 | 2024_25_Q1 | Supporting Sustainable Economic Growth
G100520606 | 520606 | Water | G100 | Gate 100 | 2024-06-26 | 2023-09-27 | 2024_25_P03 | 2023_24_P06 | 2024_25_Q1 | 2023_24_Q2 | Standards of service
G100520675 | 520675 | Water | G100 | Gate 100 | 2024-10-13 | 2024-09-13 | 2024_25_P07 | 2024_25_P06 | 2024_25_Q3 | 2024_25_Q2 | Drinking Water
G100519934 | 519934 | CE&FS | G100 | Gate 100 | 2024-10-10 | 2024-07-10 | 2024_25_P07 | 2024_25_P04 | 2024_25_Q3 | 2024_25_Q2 | Long Term Water Sector Vision
G100520761 | 520761 | Support Services | G100 | Gate 100 | 2024-03-25 | 2023-12-21 | 2023_24_P12 | 2023_24_P09 | 2023_24_Q4 | 2023_24_Q3 | Standards of service
G100522707 | 522707 | Water | G100 | Gate 100 | 2024-02-04 | 2024-03-26 | 2023_24_P11 | 2023_24_P12 | 2023_24_Q4 | 2023_24_Q4 | Standards of service
G100522742 | 522742 | Wastewater | G100 | Gate 100 | 2024-01-22 | 2024-02-22 | 2023_24_P10 | 2023_24_P11 | 2023_24_Q4 | 2023_24_Q4 | Standards of service
G100523226 | 523226 | Support Services | G100 | Gate 100 | 2025-09-04 | 2025-04-07 | 2025_26_P06 | 2025_26_P01 | 2025_26_Q2 | 2025_26_Q1 | Standards of service
G100523234 | 523234 | Support Services | G100 | Gate 100 | 2027-01-28 | 2026-08-31 | 2026_27_P10 | 2026_27_P05 | 2026_27_Q4 | 2026_27_Q2 | Security & Resilience
G100523508 | 523508 | Wastewater | G100 | Gate 100 | 2024-04-25 | 2024-01-31 | 2024_25_P01 | 2023_24_P10 | 2024_25_Q1 | 2023_24_Q4 | Standards of service
G100524093 | 524093 | CE&FS | G100 | Gate 100 | 2025-05-01 | 2025-01-31 | 2025_26_P02 | 2024_25_P10 | 2025_26_Q1 | 2024_25_Q4 | Climate Change, Adaptation and Mitigation
G100524269 | 524269 | CE&FS | G100 | Gate 100 | 2025-10-01 | 2025-07-03 | 2025_26_P07 | 2025_26_P04 | 2025_26_Q3 | 2025_26_Q2 | Climate Change, Adaptation and Mitigation
G100524492 | 524492 | CE&FS | G100 | Gate 100 | 2025-07-06 | 2025-04-07 | 2025_26_P04 | 2025_26_P01 | 2025_26_Q2 | 2025_26_Q1 | Climate Change, Adaptation and Mitigation
G100524913 | 524913 | Support Services | G100 | Gate 100 | 2023-10-29 | 2023-09-29 | 2023_24_P07 | 2023_24_P06 | 2023_24_Q3 | 2023_24_Q2 | Standards of service
G100524914 | 524914 | Support Services | G100 | Gate 100 | 2023-10-29 | 2023-09-29 | 2023_24_P07 | 2023_24_P06 | 2023_24_Q3 | 2023_24_Q2 | Standards of service
G100524939 | 524939 | Support Services | G100 | Gate 100 | 2023-10-29 | 2023-09-29 | 2023_24_P07 | 2023_24_P06 | 2023_24_Q3 | 2023_24_Q2 | Standards of service
G100525189 | 525189 | Wastewater | G100 | Gate 100 | 2024-05-06 | 2024-02-29 | 2024_25_P02 | 2023_24_P11 | 2024_25_Q1 | 2023_24_Q4 | Standards of service
G100525206 | 525206 | Water | G100 | Gate 100 | 2026-01-04 | 2025-10-06 | 2025_26_P10 | 2025_26_P07 | 2025_26_Q4 | 2025_26_Q3 | Standards of service
G100525281 | 525281 | CE&FS | G100 | Gate 100 | 2024-09-05 | 2024-06-07 | 2024_25_P06 | 2024_25_P03 | 2024_25_Q2 | 2024_25_Q1 | Climate Change, Adaptation and Mitigation
G100526537 | 526537 | Wastewater | G100 | Gate 100 | 2024-12-26 | 2024-12-04 | 2024_25_P09 | 2024_25_P09 | 2024_25_Q3 | 2024_25_Q3 | Standards of service
G100526670 | 526670 | Water | G100 | Gate 100 | 2024-12-23 | 2024-09-24 | 2024_25_P09 | 2024_25_P06 | 2024_25_Q3 | 2024_25_Q2 | Standards of service
G100526838 | 526838 | Support Services | G100 | Gate 100 | 2024-07-28 | 2024-04-29 | 2024_25_P04 | 2024_25_P01 | 2024_25_Q2 | 2024_25_Q1 | Standards of service
G100526984 | 526984 | Wastewater | G100 | Gate 100 | 2025-03-20 | 2025-05-05 | 2024_25_P12 | 2025_26_P02 | 2024_25_Q4 | 2025_26_Q1 | Standards of service
G100527220 | 527220 | Support Services | G100 | Gate 100 | 2023-07-27 | 2023-08-31 | 2023_24_P04 | 2023_24_P05 | 2023_24_Q2 | 2023_24_Q2 | Standards of service
G100527305 | 527305 | Wastewater | G100 | Gate 100 | 2025-01-02 | 2024-08-30 | 2024_25_P10 | 2024_25_P05 | 2024_25_Q4 | 2024_25_Q2 | Standards of service
G100527413 | 527413 | Water | G100 | Gate 100 | 2025-01-06 | 2024-10-08 | 2024_25_P10 | 2024_25_P07 | 2024_25_Q4 | 2024_25_Q3 | Drinking Water
G100528014 | 528014 | Water | G100 | Gate 100 | 2024-08-29 | 2024-10-17 | 2024_25_P05 | 2024_25_P07 | 2024_25_Q2 | 2024_25_Q3 | Standards of service
G100528068 | 528068 | Water | G100 | Gate 100 | 2024-05-30 | 2024-04-02 | 2024_25_P02 | 2024_25_P01 | 2024_25_Q1 | 2024_25_Q1 | Standards of service
G100528241 | 528241 | Support Services | G100 | Gate 100 | 2024-03-28 | 2023-12-19 | 2023_24_P12 | 2023_24_P09 | 2023_24_Q4 | 2023_24_Q3 | Standards of service
G100528868 | 528868 | Water | G100 | Gate 100 | 2026-03-12 | 2025-12-03 | 2025_26_P12 | 2025_26_P09 | 2025_26_Q4 | 2025_26_Q3 | Standards of service
G100529261 | 529261 | Water | G100 | Gate 100 | 2024-08-15 | 2024-10-18 | 2024_25_P05 | 2024_25_P07 | 2024_25_Q2 | 2024_25_Q3 | Standards of service
G100530690 | 530690 | Wastewater | G100 | Gate 100 | 2024-12-18 | 2025-04-09 | 2024_25_P09 | 2025_26_P01 | 2024_25_Q3 | 2025_26_Q1 | Standards of service
G100532423 | 532423 | Wastewater | G100 | Gate 100 | 2025-07-27 | 2024-12-20 | 2025_26_P04 | 2024_25_P09 | 2025_26_Q2 | 2024_25_Q3 | Standards of service
G100532714 | 532714 | Water | G100 | Gate 100 | 2024-07-04 | 2024-06-05 | 2024_25_P04 | 2024_25_P03 | 2024_25_Q2 | 2024_25_Q1 | Standards of service
G100532730 | 532730 | Water | G100 | Gate 100 | 2024-05-22 | 2024-02-22 | 2024_25_P02 | 2023_24_P11 | 2024_25_Q1 | 2023_24_Q4 | Standards of service
G100533107 | 533107 | Water | G100 | Gate 100 | 2024-07-04 | 2024-02-28 | 2024_25_P04 | 2023_24_P11 | 2024_25_Q2 | 2023_24_Q4 | Standards of service
G100533223 | 533223 | Water | G100 | Gate 100 | 2024-07-04 | 2023-12-20 | 2024_25_P04 | 2023_24_P09 | 2024_25_Q2 | 2023_24_Q3 | Standards of service
G100534910 | 534910 | Water | G100 | Gate 100 | 2024-08-19 | 2024-07-10 | 2024_25_P05 | 2024_25_P04 | 2024_25_Q2 | 2024_25_Q2 | Standards of service
G100534911 | 534911 | Water | G100 | Gate 100 | 2025-01-19 | 2024-10-21 | 2024_25_P10 | 2024_25_P07 | 2024_25_Q4 | 2024_25_Q3 | Standards of service
G100535840 | 535840 | Support Services | G100 | Gate 100 | 2027-02-21 | 2025-10-02 | 2026_27_P11 | 2025_26_P07 | 2026_27_Q4 | 2025_26_Q3 | Standards of service
G100536455 | 536455 | Water | G100 | Gate 100 | 2025-08-14 | 2025-07-25 | 2025_26_P05 | 2025_26_P04 | 2025_26_Q2 | 2025_26_Q2 | Standards of service
G100537270 | 537270 | Support Services | G100 | Gate 100 | 2025-01-12 | 2024-05-29 | 2024_25_P10 | 2024_25_P02 | 2024_25_Q4 | 2024_25_Q1 | Security & Resilience
G110046172 | 046172 | Water | G110 | Gate 110 | 2022-06-02 | 2022-10-26 | 2022_23_P03 | 2022_23_P07 | 2022_23_Q1 | 2022_23_Q3 | Standards of service
G110400324 | 400324 | Water | G110 | Gate 110 | 2024-01-13 | 2023-08-11 | 2023_24_P10 | 2023_24_P05 | 2023_24_Q4 | 2023_24_Q2 | Standards of service
G110401705 | 401705 | Wastewater | G110 | Gate 110 | 2022-07-25 | 2025-01-22 | 2022_23_P04 | 2024_25_P10 | 2022_23_Q2 | 2024_25_Q4 | Standards of service
G110402197 | 402197 | Wastewater | G110 | Gate 110 | 2022-02-09 | 2022-02-01 | 2021_22_P11 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
G110401685 | 401685 | Wastewater | G110 | Gate 110 | 2022-06-21 | 2023-02-24 | 2022_23_P03 | 2022_23_P11 | 2022_23_Q1 | 2022_23_Q4 | Standards of service
G110401795 | 401795 | Wastewater | G110 | Gate 110 | 2022-04-06 | 2022-02-15 | 2022_23_P01 | 2021_22_P11 | 2022_23_Q1 | 2021_22_Q4 | Standards of service
G110401687 | 401687 | Wastewater | G110 | Gate 110 | 2022-06-22 | 2023-02-24 | 2022_23_P03 | 2022_23_P11 | 2022_23_Q1 | 2022_23_Q4 | Standards of service
G110401668 | 401668 | Wastewater | G110 | Gate 110 | 2022-06-21 | 2024-11-27 | 2022_23_P03 | 2024_25_P08 | 2022_23_Q1 | 2024_25_Q3 | Standards of service
G110403238 | 403238 | Wastewater | G110 | Gate 110 | 2022-05-17 | 2023-02-27 | 2022_23_P02 | 2022_23_P11 | 2022_23_Q1 | 2022_23_Q4 | Standards of service
G110403097 | 403097 | Wastewater | G110 | Gate 110 | 2021-11-26 | 2021-12-09 | 2021_22_P08 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
G110403098 | 403098 | Wastewater | G110 | Gate 110 | 2022-09-01 | 2023-01-31 | 2022_23_P06 | 2022_23_P10 | 2022_23_Q2 | 2022_23_Q4 | Standards of service
G110403103 | 403103 | Wastewater | G110 | Gate 110 | 2022-06-27 | 2021-08-25 | 2022_23_P03 | 2021_22_P05 | 2022_23_Q1 | 2021_22_Q2 | Standards of service
G110403102 | 403102 | Wastewater | G110 | Gate 110 | 2022-05-25 | 2024-03-26 | 2022_23_P02 | 2023_24_P12 | 2022_23_Q1 | 2023_24_Q4 | Standards of service
G110403090 | 403090 | Water | G110 | Gate 110 | 2022-03-31 | 2022-10-24 | 2021_22_P12 | 2022_23_P07 | 2021_22_Q4 | 2022_23_Q3 | Standards of service
G110403100 | 403100 | Wastewater | G110 | Gate 110 | 2022-05-22 | 2022-03-30 | 2022_23_P02 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4 | Standards of service
G110403101 | 403101 | Wastewater | G110 | Gate 110 | 2022-05-25 | 2023-02-27 | 2022_23_P02 | 2022_23_P11 | 2022_23_Q1 | 2022_23_Q4 | Standards of service
G110403104 | 403104 | Wastewater | G110 | Gate 110 | 2022-06-02 | 2022-06-23 | 2022_23_P03 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1 | Standards of service
G110403146 | 403146 | Water | G110 | Gate 110 | 2021-06-16 | 2021-07-01 | 2021_22_P03 | 2021_22_P04 | 2021_22_Q1 | 2021_22_Q2 | Standards of service
G110403658 | 403658 | Water | G110 | Gate 110 | 2023-07-01 | 2023-05-31 | 2023_24_P04 | 2023_24_P02 | 2023_24_Q2 | 2023_24_Q1 | Standards of service
G110403106 | 403106 | Wastewater | G110 | Gate 110 | 2023-11-01 | 2025-12-10 | 2023_24_P08 | 2025_26_P09 | 2023_24_Q3 | 2025_26_Q3 | Standards of service
G110402949 | 402949 | Wastewater | G110 | Gate 110 | 2023-07-22 | 2023-03-30 | 2023_24_P04 | 2022_23_P12 | 2023_24_Q2 | 2022_23_Q4 | Standards of service
G110403321 | 403321 | Wastewater | G110 | Gate 110 | 2023-05-28 | 2023-03-24 | 2023_24_P02 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4 | Standards of service
G110403917 | 403917 | Water | G110 | Gate 110 | 2022-06-29 | 2022-03-31 | 2022_23_P03 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4 | Standards of service
G110403716 | 403716 | Wastewater | G110 | Gate 110 | 2023-11-19 | 2023-07-31 | 2023_24_P08 | 2023_24_P04 | 2023_24_Q3 | 2023_24_Q2 | Standards of service
G110403605 | 403605 | Water | G110 | Gate 110 | 2021-11-29 | 2022-01-27 | 2021_22_P08 | 2021_22_P10 | 2021_22_Q3 | 2021_22_Q4 | Environment
G110404026 | 404026 | Wastewater | G110 | Gate 110 | 2023-04-22 | 2025-02-05 | 2023_24_P01 | 2024_25_P11 | 2023_24_Q1 | 2024_25_Q4 | Standards of service
G110500046 | 500046 | Water | G110 | Gate 110 | 2025-05-15 | 2023-03-30 | 2025_26_P02 | 2022_23_P12 | 2025_26_Q1 | 2022_23_Q4 | Standards of service
G110403995 | 403995 | Water | G110 | Gate 110 | 2025-07-14 | 2026-06-24 | 2025_26_P04 | 2026_27_P03 | 2025_26_Q2 | 2026_27_Q1 | Standards of service
G110403127 | 403127 | Water | G110 | Gate 110 | 2023-05-17 | 2024-02-29 | 2023_24_P02 | 2023_24_P11 | 2023_24_Q1 | 2023_24_Q4 | Standards of service
G110403532 | 403532 | Water | G110 | Gate 110 | 2022-07-02 | 2022-03-30 | 2022_23_P04 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4 | Standards of service
G110403994 | 403994 | Water | G110 | Gate 110 | 2022-11-26 | 2024-02-29 | 2022_23_P08 | 2023_24_P11 | 2022_23_Q3 | 2023_24_Q4 | Standards of service
G110404003 | 404003 | Water | G110 | Gate 110 | 2021-12-31 | 2022-04-29 | 2021_22_P09 | 2022_23_P01 | 2021_22_Q3 | 2022_23_Q1 | Standards of service
G110500017 | 500017 | Wastewater | G110 | Gate 110 | 2022-11-22 | 2022-08-30 | 2022_23_P08 | 2022_23_P05 | 2022_23_Q3 | 2022_23_Q2 | Standards of service
G110403967 | 403967 | Wastewater | G110 | Gate 110 | 2025-06-06 | 2024-12-16 | 2025_26_P03 | 2024_25_P09 | 2025_26_Q1 | 2024_25_Q3 | Supporting Sustainable Economic Growth
G110403939 | 403939 | Wastewater | G110 | Gate 110 | 2023-02-03 | 2023-11-23 | 2022_23_P11 | 2023_24_P08 | 2022_23_Q4 | 2023_24_Q3 | Supporting Sustainable Economic Growth
G110403781 | 403781 | Wastewater | G110 | Gate 110 | 2022-06-17 | 2022-01-18 | 2022_23_P03 | 2021_22_P10 | 2022_23_Q1 | 2021_22_Q4 | Supporting Sustainable Economic Growth
G110403782 | 403782 | Wastewater | G110 | Gate 110 | 2024-01-26 | 2024-07-10 | 2023_24_P10 | 2024_25_P04 | 2023_24_Q4 | 2024_25_Q2 | Supporting Sustainable Economic Growth
G110403991 | 403991 | Water | G110 | Gate 110 | 2023-10-31 | 2024-02-28 | 2023_24_P07 | 2023_24_P11 | 2023_24_Q3 | 2023_24_Q4 | Standards of service
G110500047 | 500047 | Water | G110 | Gate 110 | 2023-07-08 | 2023-03-30 | 2023_24_P04 | 2022_23_P12 | 2023_24_Q2 | 2022_23_Q4 | Standards of service
G110403923 | 403923 | Wastewater | G110 | Gate 110 | 2023-03-31 | 2023-03-27 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4 | Standards of service
G110403934 | 403934 | Wastewater | G110 | Gate 110 | 2023-04-04 | 2023-03-24 | 2023_24_P01 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4 | Supporting Sustainable Economic Growth
G110404134 | 404134 | Water | G110 | Gate 110 | 2022-03-18 | 2022-03-31 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
G110403902 | 403902 | Wastewater | G110 | Gate 110 | 2022-08-23 | 2023-03-30 | 2022_23_P05 | 2022_23_P12 | 2022_23_Q2 | 2022_23_Q4 | Supporting Sustainable Economic Growth
G110403968 | 403968 | Wastewater | G110 | Gate 110 | 2021-12-30 | 2022-03-28 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4 | Supporting Sustainable Economic Growth
G110500068 | 500068 | Wastewater | G110 | Gate 110 | 2022-03-24 | 2021-12-21 | 2021_22_P12 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3 | Supporting Sustainable Economic Growth
G110500218 | 500218 | Water | G110 | Gate 110 | 2022-11-16 | 2022-04-01 | 2022_23_P08 | 2022_23_P01 | 2022_23_Q3 | 2022_23_Q1 | Standards of service
G110500040 | 500040 | Water | G110 | Gate 110 | 2022-01-29 | 2021-12-16 | 2021_22_P10 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3 | Standards of service
G110403986 | 403986 | Water | G110 | Gate 110 | 2024-01-13 | 2023-08-29 | 2023_24_P10 | 2023_24_P05 | 2023_24_Q4 | 2023_24_Q2 | Standards of service
G110500060 | 500060 | Water | G110 | Gate 110 | 2022-02-23 | 2021-11-26 | 2021_22_P11 | 2021_22_P08 | 2021_22_Q4 | 2021_22_Q3 | Standards of service
G110500235 | 500235 | Wastewater | G110 | Gate 110 | 2023-03-04 | 2023-03-24 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4 | Supporting Sustainable Economic Growth
G110404069 | 404069 | Wastewater | G110 | Gate 110 | 2022-01-29 | 2021-11-09 | 2021_22_P10 | 2021_22_P08 | 2021_22_Q4 | 2021_22_Q3 | Supporting Sustainable Economic Growth
G110404093 | 404093 | Water | G110 | Gate 110 | 2024-05-23 | 2025-01-08 | 2024_25_P02 | 2024_25_P10 | 2024_25_Q1 | 2024_25_Q4 | Standards of service
G110403943 | 403943 | Wastewater | G110 | Gate 110 | 2022-08-19 | 2023-07-18 | 2022_23_P05 | 2023_24_P04 | 2022_23_Q2 | 2023_24_Q2 | Supporting Sustainable Economic Growth
G110500206 | 500206 | Water | G110 | Gate 110 | 2021-05-05 | 2021-12-16 | 2021_22_P02 | 2021_22_P09 | 2021_22_Q1 | 2021_22_Q3 | Standards of service
G110500207 | 500207 | Water | G110 | Gate 110 | 2022-09-21 | 2023-03-31 | 2022_23_P06 | 2022_23_P12 | 2022_23_Q2 | 2022_23_Q4 | Standards of service
G110404135 | 404135 | Water | G110 | Gate 110 | 2023-10-28 | 2024-10-02 | 2023_24_P07 | 2024_25_P07 | 2023_24_Q3 | 2024_25_Q3 | Standards of service
G110500246 | 500246 | Water | G110 | Gate 110 | 2022-07-23 | 2024-03-18 | 2022_23_P04 | 2023_24_P12 | 2022_23_Q2 | 2023_24_Q4 | Standards of service
G110500030 | 500030 | Water | G110 | Gate 110 | 2021-12-30 | 2022-03-10 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4 | Standards of service
G110500190 | 500190 | Water | G110 | Gate 110 | 2021-12-07 | 2022-03-24 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4 | Standards of service
G110500052 | 500052 | Wastewater | G110 | Gate 110 | 2023-04-30 | 2024-09-04 | 2023_24_P01 | 2024_25_P06 | 2023_24_Q1 | 2024_25_Q2 | Supporting Sustainable Economic Growth
G110500154 | 500154 | Wastewater | G110 | Gate 110 | 2021-10-29 | 2021-09-24 | 2021_22_P07 | 2021_22_P06 | 2021_22_Q3 | 2021_22_Q2 | Standards of service
G110500211 | 500211 | Water | G110 | Gate 110 | 2021-10-20 | 2022-03-31 | 2021_22_P07 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4 | Standards of service
G110500302 | 500302 | Wastewater | G110 | Gate 110 | 2023-03-31 | 2023-11-22 | 2022_23_P12 | 2023_24_P08 | 2022_23_Q4 | 2023_24_Q3 | Standards of service
G110404007 | 404007 | Wastewater | G110 | Gate 110 | 2022-11-19 | 2022-02-08 | 2022_23_P08 | 2021_22_P11 | 2022_23_Q3 | 2021_22_Q4 | Standards of service
G110500523 | 500523 | Water | G110 | Gate 110 | 2024-06-20 | 2025-07-09 | 2024_25_P03 | 2025_26_P04 | 2024_25_Q1 | 2025_26_Q2 | Standards of service
G110500573 | 500573 | Water | G110 | Gate 110 | 2023-03-29 | 2023-03-21 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4 | Standards of service
G110500299 | 500299 | Wastewater | G110 | Gate 110 | 2022-07-21 | 2022-02-11 | 2022_23_P04 | 2021_22_P11 | 2022_23_Q2 | 2021_22_Q4 | Standards of service
G110404132 | 404132 | Water | G110 | Gate 110 | 2026-11-12 | 2025-08-20 | 2026_27_P08 | 2025_26_P05 | 2026_27_Q3 | 2025_26_Q2 | Standards of service
G110500244 | 500244 | Water | G110 | Gate 110 | 2021-11-19 | 2021-07-30 | 2021_22_P08 | 2021_22_P04 | 2021_22_Q3 | 2021_22_Q2 | Standards of service
G110500233 | 500233 | Wastewater | G110 | Gate 110 | 2022-10-15 | 2024-07-10 | 2022_23_P07 | 2024_25_P04 | 2022_23_Q3 | 2024_25_Q2 | Supporting Sustainable Economic Growth
G110500681 | 500681 | Wastewater | G110 | Gate 110 | 2023-06-14 | 2024-03-11 | 2023_24_P03 | 2023_24_P12 | 2023_24_Q1 | 2023_24_Q4 | Standards of service
G110500742 | 500742 | Water | G110 | Gate 110 | 2022-01-29 | 2022-11-18 | 2021_22_P10 | 2022_23_P08 | 2021_22_Q4 | 2022_23_Q3 | Standards of service
G110500241 | 500241 | Water | G110 | Gate 110 | 2021-10-26 | 2021-12-21 | 2021_22_P07 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
G110500784 | 500784 | Wastewater | G110 | Gate 110 | 2022-01-22 | 2021-11-24 | 2021_22_P10 | 2021_22_P08 | 2021_22_Q4 | 2021_22_Q3 | Standards of service
G110500687 | 500687 | Wastewater | G110 | Gate 110 | 2022-06-25 | 2022-03-30 | 2022_23_P03 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4 | Standards of service
G110500245 | 500245 | Water | G110 | Gate 110 | 2023-05-18 | 2025-04-10 | 2023_24_P02 | 2025_26_P01 | 2023_24_Q1 | 2025_26_Q1 | Standards of service
G110500229 | 500229 | Wastewater | G110 | Gate 110 | 2024-04-27 | 2027-03-01 | 2024_25_P01 | 2026_27_P12 | 2024_25_Q1 | 2026_27_Q4 | Supporting Sustainable Economic Growth
G110500576 | 500576 | Wastewater | G110 | Gate 110 | 2025-03-14 | 2024-08-02 | 2024_25_P12 | 2024_25_P05 | 2024_25_Q4 | 2024_25_Q2 | Standards of service
G110500579 | 500579 | Wastewater | G110 | Gate 110 | 2022-12-30 | 2024-02-29 | 2022_23_P09 | 2023_24_P11 | 2022_23_Q3 | 2023_24_Q4 | Standards of service
G110500707 | 500707 | Wastewater | G110 | Gate 110 | 2022-04-14 | 2021-12-22 | 2022_23_P01 | 2021_22_P09 | 2022_23_Q1 | 2021_22_Q3 | Standards of service
G110500843 | 500843 | Water | G110 | Gate 110 | 2021-12-30 | 2021-11-19 | 2021_22_P09 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
G110500509 | 500509 | Water | G110 | Gate 110 | 2022-05-25 | 2025-07-09 | 2022_23_P02 | 2025_26_P04 | 2022_23_Q1 | 2025_26_Q2 | Standards of service
G110501001 | 501001 | Water | G110 | Gate 110 | 2023-11-17 | 2026-05-27 | 2023_24_P08 | 2026_27_P02 | 2023_24_Q3 | 2026_27_Q1 | Standards of service
G110500665 | 500665 | Wastewater | G110 | Gate 110 | 2022-10-17 | 2022-03-30 | 2022_23_P07 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4 | Standards of service
G110500575 | 500575 | Water | G110 | Gate 110 | 2023-05-23 | 2023-03-22 | 2023_24_P02 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4 | Standards of service
G110500709 | 500709 | Water | G110 | Gate 110 | 2022-07-12 | 2023-03-23 | 2022_23_P04 | 2022_23_P12 | 2022_23_Q2 | 2022_23_Q4 | Standards of service
G110500496 | 500496 | Wastewater | G110 | Gate 110 | 2022-02-28 | 2022-03-30 | 2021_22_P11 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
G110500694 | 500694 | Wastewater | G110 | Gate 110 | 2022-08-23 | 2023-03-15 | 2022_23_P05 | 2022_23_P12 | 2022_23_Q2 | 2022_23_Q4 | Standards of service
G110500892 | 500892 | Water | G110 | Gate 110 | 2023-03-28 | 2024-08-21 | 2022_23_P12 | 2024_25_P05 | 2022_23_Q4 | 2024_25_Q2 | Supporting Sustainable Economic Growth
G110500580 | 500580 | Wastewater | G110 | Gate 110 | 2023-07-31 | 2024-01-30 | 2023_24_P04 | 2023_24_P10 | 2023_24_Q2 | 2023_24_Q4 | Standards of service
G110501019 | 501019 | Wastewater | G110 | Gate 110 | 2022-02-27 | 2021-12-22 | 2021_22_P11 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3 | Standards of service
G110404082 | 404082 | Water | G110 | Gate 110 | 2022-06-11 | 2021-11-10 | 2022_23_P03 | 2021_22_P08 | 2022_23_Q1 | 2021_22_Q3 | Standards of service
G110501216 | 501216 | Water | G110 | Gate 110 | 2022-08-19 | 2022-10-26 | 2022_23_P05 | 2022_23_P07 | 2022_23_Q2 | 2022_23_Q3 | Standards of service
G110500771 | 500771 | Water | G110 | Gate 110 | 2022-03-15 | 2022-03-24 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4 | Supporting Sustainable Economic Growth
G110500662 | 500662 | Wastewater | G110 | Gate 110 | 2022-08-25 | 2022-05-30 | 2022_23_P05 | 2022_23_P02 | 2022_23_Q2 | 2022_23_Q1 | Standards of service
G110500682 | 500682 | Wastewater | G110 | Gate 110 | 2023-06-04 | 2023-03-29 | 2023_24_P03 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4 | Standards of service
G110500655 | 500655 | Wastewater | G110 | Gate 110 | 2022-12-27 | 2022-03-30 | 2022_23_P09 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4 | Standards of service
G110500755 | 500755 | Water | G110 | Gate 110 | 2024-08-23 | 2025-07-09 | 2024_25_P05 | 2025_26_P04 | 2024_25_Q2 | 2025_26_Q2 | Standards of service
G110500947 | 500947 | Support Services | G110 | Gate 110 | 2022-03-17 | 2022-07-27 | 2021_22_P12 | 2022_23_P04 | 2021_22_Q4 | 2022_23_Q2 | Standards of service
G110500723 | 500723 | Wastewater | G110 | Gate 110 | 2022-10-15 | 2022-08-31 | 2022_23_P07 | 2022_23_P05 | 2022_23_Q3 | 2022_23_Q2 | Supporting Sustainable Economic Growth
G110500652 | 500652 | Wastewater | G110 | Gate 110 | 2022-08-10 | 2022-12-16 | 2022_23_P05 | 2022_23_P09 | 2022_23_Q2 | 2022_23_Q3 | Standards of service
G110500661 | 500661 | Wastewater | G110 | Gate 110 | 2023-06-19 | 2023-03-27 | 2023_24_P03 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4 | Standards of service
G110501211 | 501211 | Water | G110 | Gate 110 | 2025-11-13 | 2025-07-24 | 2025_26_P08 | 2025_26_P04 | 2025_26_Q3 | 2025_26_Q2 | Standards of service
G110500654 | 500654 | Wastewater | G110 | Gate 110 | 2022-10-30 | 2023-03-26 | 2022_23_P07 | 2022_23_P12 | 2022_23_Q3 | 2022_23_Q4 | Standards of service
G110500958 | 500958 | Water | G110 | Gate 110 | 2022-04-08 | 2022-03-29 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4 | Standards of service
G110500695 | 500695 | Wastewater | G110 | Gate 110 | 2022-01-01 | 2021-10-22 | 2021_22_P10 | 2021_22_P07 | 2021_22_Q4 | 2021_22_Q3 | Standards of service
G110500729 | 500729 | Wastewater | G110 | Gate 110 | 2025-08-07 | 2024-03-22 | 2025_26_P05 | 2023_24_P12 | 2025_26_Q2 | 2023_24_Q4 | Standards of service
G110500724 | 500724 | Wastewater | G110 | Gate 110 | 2025-10-04 | 2025-04-16 | 2025_26_P07 | 2025_26_P01 | 2025_26_Q3 | 2025_26_Q1 | Supporting Sustainable Economic Growth
G110501151 | 501151 | Wastewater | G110 | Gate 110 | 2022-02-23 | 2021-12-22 | 2021_22_P11 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3 | Standards of service
G110501390 | 501390 | Water | G110 | Gate 110 | 2023-08-11 | 2025-09-10 | 2023_24_P05 | 2025_26_P06 | 2023_24_Q2 | 2025_26_Q2 | Standards of service
G110501200 | 501200 | Water | G110 | Gate 110 | 2023-01-24 | 2022-11-30 | 2022_23_P10 | 2022_23_P08 | 2022_23_Q4 | 2022_23_Q3 | Standards of service
G110501021 | 501021 | Wastewater | G110 | Gate 110 | 2022-12-30 | 2024-02-29 | 2022_23_P09 | 2023_24_P11 | 2022_23_Q3 | 2023_24_Q4 | Supporting Sustainable Economic Growth
G110501158 | 501158 | Wastewater | G110 | Gate 110 | 2022-03-04 | 2022-09-28 | 2021_22_P12 | 2022_23_P06 | 2021_22_Q4 | 2022_23_Q2 | Standards of service
G110501040 | 501040 | Water | G110 | Gate 110 | 2022-03-01 | 2022-02-28 | 2021_22_P12 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
G110501352 | 501352 | Wastewater | G110 | Gate 110 | 2022-09-09 | 2022-12-21 | 2022_23_P06 | 2022_23_P09 | 2022_23_Q2 | 2022_23_Q3 | Standards of service
G110500731 | 500731 | Wastewater | G110 | Gate 110 | 2025-06-07 | 2026-01-08 | 2025_26_P03 | 2025_26_P10 | 2025_26_Q1 | 2025_26_Q4 | Supporting Sustainable Economic Growth
G110501070 | 501070 | Water | G110 | Gate 110 | 2022-07-23 | 2023-10-04 | 2022_23_P04 | 2023_24_P07 | 2022_23_Q2 | 2023_24_Q3 | Drinking Water
G110501017 | 501017 | Wastewater | G110 | Gate 110 | 2024-07-29 | 2024-06-12 | 2024_25_P04 | 2024_25_P03 | 2024_25_Q2 | 2024_25_Q1 | Standards of service
G110501219 | 501219 | Water | G110 | Gate 110 | 2022-04-01 | 2022-01-20 | 2022_23_P01 | 2021_22_P10 | 2022_23_Q1 | 2021_22_Q4 | Standards of service
G110500918 | 500918 | Water | G110 | Gate 110 | 2023-03-01 | 2022-11-08 | 2022_23_P12 | 2022_23_P08 | 2022_23_Q4 | 2022_23_Q3 | Standards of service
G110501720 | 501720 | Wastewater | G110 | Gate 110 | 2022-05-31 | 2022-02-28 | 2022_23_P02 | 2021_22_P11 | 2022_23_Q1 | 2021_22_Q4 | Standards of service
G110501153 | 501153 | Wastewater | G110 | Gate 110 | 2022-06-29 | 2023-03-29 | 2022_23_P03 | 2022_23_P12 | 2022_23_Q1 | 2022_23_Q4 | Standards of service
G110501217 | 501217 | Water | G110 | Gate 110 | 2022-06-01 | 2024-02-29 | 2022_23_P03 | 2023_24_P11 | 2022_23_Q1 | 2023_24_Q4 | Standards of service
G110501233 | 501233 | Water | G110 | Gate 110 | 2022-04-30 | 2021-10-29 | 2022_23_P01 | 2021_22_P07 | 2022_23_Q1 | 2021_22_Q3 | Standards of service
G110500899 | 500899 | Water | G110 | Gate 110 | 2021-12-17 | 2022-03-29 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4 | Standards of service
G110501146 | 501146 | Water | G110 | Gate 110 | 2022-01-29 | 2021-07-30 | 2021_22_P10 | 2021_22_P04 | 2021_22_Q4 | 2021_22_Q2 | Standards of service
G110501159 | 501159 | Wastewater | G110 | Gate 110 | 2024-03-20 | 2026-03-18 | 2023_24_P12 | 2025_26_P12 | 2023_24_Q4 | 2025_26_Q4 | Standards of service
G110501169 | 501169 | Wastewater | G110 | Gate 110 | 2021-12-31 | 2021-11-15 | 2021_22_P09 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
G110501144 | 501144 | Water | G110 | Gate 110 | 2022-10-22 | 2022-04-28 | 2022_23_P07 | 2022_23_P01 | 2022_23_Q3 | 2022_23_Q1 | Standards of service
G110500896 | 500896 | Water | G110 | Gate 110 | 2023-08-08 | 2024-08-16 | 2023_24_P05 | 2024_25_P05 | 2023_24_Q2 | 2024_25_Q2 | Standards of service
G110501227 | 501227 | Water | G110 | Gate 110 | 2022-05-18 | 2021-06-29 | 2022_23_P02 | 2021_22_P03 | 2022_23_Q1 | 2021_22_Q1 | Standards of service
G110501574 | 501574 | Water | G110 | Gate 110 | 2021-06-16 | 2022-03-24 | 2021_22_P03 | 2021_22_P12 | 2021_22_Q1 | 2021_22_Q4 | Standards of service
G110501290 | 501290 | Wastewater | G110 | Gate 110 | 2023-04-30 | 2023-03-31 | 2023_24_P01 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4 | Supporting Sustainable Economic Growth
G110501091 | 501091 | Water | G110 | Gate 110 | 2022-10-13 | 2022-03-31 | 2022_23_P07 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4 | Standards of service
G110501092 | 501092 | Water | G110 | Gate 110 | 2021-11-18 | 2022-03-31 | 2021_22_P08 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4 | Standards of service
G110501599 | 501599 | Wastewater | G110 | Gate 110 | 2022-03-31 | 2023-03-26 | 2021_22_P12 | 2022_23_P12 | 2021_22_Q4 | 2022_23_Q4 | Standards of service
G110501152 | 501152 | Wastewater | G110 | Gate 110 | 2021-12-30 | 2022-03-16 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4 | Standards of service
G110500893 | 500893 | Water | G110 | Gate 110 | 2024-09-16 | 2024-02-19 | 2024_25_P06 | 2023_24_P11 | 2024_25_Q2 | 2023_24_Q4 | Standards of service
G110501203 | 501203 | Water | G110 | Gate 110 | 2021-12-11 | 2021-07-30 | 2021_22_P09 | 2021_22_P04 | 2021_22_Q3 | 2021_22_Q2 | Standards of service
G110501168 | 501168 | Wastewater | G110 | Gate 110 | 2023-02-28 | 2023-03-29 | 2022_23_P11 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4 | Standards of service
G110501156 | 501156 | Wastewater | G110 | Gate 110 | 2022-07-12 | 2023-02-27 | 2022_23_P04 | 2022_23_P11 | 2022_23_Q2 | 2022_23_Q4 | Standards of service
G110501402 | 501402 | Water | G110 | Gate 110 | 2022-02-05 | 2021-11-12 | 2021_22_P11 | 2021_22_P08 | 2021_22_Q4 | 2021_22_Q3 | Standards of service
G110501512 | 501512 | Wastewater | G110 | Gate 110 | 2025-01-20 | 2024-10-16 | 2024_25_P10 | 2024_25_P07 | 2024_25_Q4 | 2024_25_Q3 | Standards of service
G110501632 | 501632 | Support Services | G110 | Gate 110 | 2022-02-05 | 2021-06-30 | 2021_22_P11 | 2021_22_P03 | 2021_22_Q4 | 2021_22_Q1 | Standards of service
G110501499 | 501499 | Wastewater | G110 | Gate 110 | 2022-11-22 | 2023-01-31 | 2022_23_P08 | 2022_23_P10 | 2022_23_Q3 | 2022_23_Q4 | Standards of service
G110501500 | 501500 | Wastewater | G110 | Gate 110 | 2022-02-28 | 2022-02-28 | 2021_22_P11 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4 | Supporting Sustainable Economic Growth
G110501635 | 501635 | Water | G110 | Gate 110 | 2022-03-31 | 2021-08-31 | 2021_22_P12 | 2021_22_P05 | 2021_22_Q4 | 2021_22_Q2 | Standards of service
G110501243 | 501243 | Water | G110 | Gate 110 | 2023-11-02 | 2024-11-13 | 2023_24_P08 | 2024_25_P08 | 2023_24_Q3 | 2024_25_Q3 | Drinking Water
G110501518 | 501518 | Wastewater | G110 | Gate 110 | 2022-07-01 | 2022-03-31 | 2022_23_P04 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4 | Standards of service
G110501642 | 501642 | Water | G110 | Gate 110 | 2021-12-30 | 2021-10-28 | 2021_22_P09 | 2021_22_P07 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
G110501232 | 501232 | Water | G110 | Gate 110 | 2022-11-03 | 2025-02-05 | 2022_23_P08 | 2024_25_P11 | 2022_23_Q3 | 2024_25_Q4 | Standards of service
G110501165 | 501165 | Wastewater | G110 | Gate 110 | 2022-03-17 | 2022-02-28 | 2021_22_P12 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
G110501218 | 501218 | Water | G110 | Gate 110 | 2022-05-28 | 2022-10-31 | 2022_23_P02 | 2022_23_P07 | 2022_23_Q1 | 2022_23_Q3 | Standards of service
G110501388 | 501388 | Water | G110 | Gate 110 | 2022-11-01 | 2024-06-12 | 2022_23_P08 | 2024_25_P03 | 2022_23_Q3 | 2024_25_Q1 | Standards of service
G110501600 | 501600 | Water | G110 | Gate 110 | 2022-04-12 | 2022-02-24 | 2022_23_P01 | 2021_22_P11 | 2022_23_Q1 | 2021_22_Q4 | Standards of service
G110501639 | 501639 | Support Services | G110 | Gate 110 | 2022-03-16 | 2021-11-29 | 2021_22_P12 | 2021_22_P08 | 2021_22_Q4 | 2021_22_Q3 | Standards of service
G110501488 | 501488 | Wastewater | G110 | Gate 110 | 2022-12-29 | 2022-08-31 | 2022_23_P09 | 2022_23_P05 | 2022_23_Q3 | 2022_23_Q2 | Standards of service
G110501573 | 501573 | Water | G110 | Gate 110 | 2021-12-25 | 2021-06-10 | 2021_22_P09 | 2021_22_P03 | 2021_22_Q3 | 2021_22_Q1 | Standards of service
G110501592 | 501592 | Wastewater | G110 | Gate 110 | 2022-02-28 | 2022-03-16 | 2021_22_P11 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
G110501593 | 501593 | Wastewater | G110 | Gate 110 | 2021-12-31 | 2021-12-22 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
G110501554 | 501554 | Water | G110 | Gate 110 | 2023-08-11 | 2023-10-12 | 2023_24_P05 | 2023_24_P07 | 2023_24_Q2 | 2023_24_Q3 | Standards of service
G110501393 | 501393 | Water | G110 | Gate 110 | 2023-02-28 | 2024-11-27 | 2022_23_P11 | 2024_25_P08 | 2022_23_Q4 | 2024_25_Q3 | Standards of service
G110501579 | 501579 | Wastewater | G110 | Gate 110 | 2023-09-30 | 2024-03-20 | 2023_24_P06 | 2023_24_P12 | 2023_24_Q2 | 2023_24_Q4 | Standards of service
G110501379 | 501379 | Water | G110 | Gate 110 | 2023-06-30 | 2024-09-18 | 2023_24_P03 | 2024_25_P06 | 2023_24_Q1 | 2024_25_Q2 | Standards of service
G110501670 | 501670 | Water | G110 | Gate 110 | 2025-06-05 | 2024-11-27 | 2025_26_P03 | 2024_25_P08 | 2025_26_Q1 | 2024_25_Q3 | Standards of service
G110501666 | 501666 | Water | G110 | Gate 110 | 2022-03-26 | 2023-02-27 | 2021_22_P12 | 2022_23_P11 | 2021_22_Q4 | 2022_23_Q4 | Standards of service
G110501258 | 501258 | Water | G110 | Gate 110 | 2021-12-24 | 2021-11-12 | 2021_22_P09 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
G110501259 | 501259 | Water | G110 | Gate 110 | 2022-04-06 | 2022-03-30 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4 | Standards of service
G110501683 | 501683 | Wastewater | G110 | Gate 110 | 2022-08-31 | 2024-03-22 | 2022_23_P05 | 2023_24_P12 | 2022_23_Q2 | 2023_24_Q4 | Standards of service
G110501731 | 501731 | Water | G110 | Gate 110 | 2025-05-01 | 2025-01-22 | 2025_26_P02 | 2024_25_P10 | 2025_26_Q1 | 2024_25_Q4 | Standards of service
G110501436 | 501436 | Water | G110 | Gate 110 | 2022-01-27 | 2022-03-23 | 2021_22_P10 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
G110501418 | 501418 | Water | G110 | Gate 110 | 2022-09-03 | 2024-02-28 | 2022_23_P06 | 2023_24_P11 | 2022_23_Q2 | 2023_24_Q4 | Standards of service
G110501421 | 501421 | Water | G110 | Gate 110 | 2021-12-31 | 2021-12-21 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
G110501829 | 501829 | Wastewater | G110 | Gate 110 | 2022-09-11 | 2022-10-14 | 2022_23_P06 | 2022_23_P07 | 2022_23_Q2 | 2022_23_Q3 | Standards of service
G110501739 | 501739 | Wastewater | G110 | Gate 110 | 2022-04-22 | 2023-03-26 | 2022_23_P01 | 2022_23_P12 | 2022_23_Q1 | 2022_23_Q4 | Standards of service
G110501703 | 501703 | Wastewater | G110 | Gate 110 | 2025-01-20 | 2024-07-24 | 2024_25_P10 | 2024_25_P04 | 2024_25_Q4 | 2024_25_Q2 | Standards of service
G110501898 | 501898 | Support Services | G110 | Gate 110 | 2022-06-30 | 2022-07-27 | 2022_23_P03 | 2022_23_P04 | 2022_23_Q1 | 2022_23_Q2 | Standards of service
G110502246 | 502246 | Water | G110 | Gate 110 | 2022-04-12 | 2022-08-22 | 2022_23_P01 | 2022_23_P05 | 2022_23_Q1 | 2022_23_Q2 | Standards of service
G110502267 | 502267 | Wastewater | G110 | Gate 110 | 2022-01-21 | 2022-01-27 | 2021_22_P10 | 2021_22_P10 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
G110502268 | 502268 | Wastewater | G110 | Gate 110 | 2023-01-13 | 2023-12-19 | 2022_23_P10 | 2023_24_P09 | 2022_23_Q4 | 2023_24_Q3 | Standards of service
G110501818 | 501818 | Support Services | G110 | Gate 110 | 2022-04-28 | 2021-12-21 | 2022_23_P01 | 2021_22_P09 | 2022_23_Q1 | 2021_22_Q3 | Standards of service
G110502132 | 502132 | Water | G110 | Gate 110 | 2023-10-21 | 2025-05-28 | 2023_24_P07 | 2025_26_P02 | 2023_24_Q3 | 2025_26_Q1 | Standards of service
G110502269 | 502269 | Wastewater | G110 | Gate 110 | 2022-01-11 | 2022-01-27 | 2021_22_P10 | 2021_22_P10 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
G110502243 | 502243 | Water | G110 | Gate 110 | 2025-08-01 | 2026-03-18 | 2025_26_P05 | 2025_26_P12 | 2025_26_Q2 | 2025_26_Q4 | Standards of service
G110502332 | 502332 | Wastewater | G110 | Gate 110 | 2024-07-19 | 2024-03-22 | 2024_25_P04 | 2023_24_P12 | 2024_25_Q2 | 2023_24_Q4 | Supporting Sustainable Economic Growth
G110502231 | 502231 | Wastewater | G110 | Gate 110 | 2022-01-01 | 2021-12-21 | 2021_22_P10 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3 | Standards of service
G110502281 | 502281 | Wastewater | G110 | Gate 110 | 2022-08-20 | 2022-08-26 | 2022_23_P05 | 2022_23_P05 | 2022_23_Q2 | 2022_23_Q2 | Standards of service
G110502280 | 502280 | Wastewater | G110 | Gate 110 | 2022-12-06 | 2023-08-29 | 2022_23_P09 | 2023_24_P05 | 2022_23_Q3 | 2023_24_Q2 | Standards of service
G110502212 | 502212 | Wastewater | G110 | Gate 110 | 2024-07-20 | 2023-10-18 | 2024_25_P04 | 2023_24_P07 | 2024_25_Q2 | 2023_24_Q3 | Standards of service
G110502220 | 502220 | Wastewater | G110 | Gate 110 | 2026-05-14 | 2025-08-06 | 2026_27_P02 | 2025_26_P05 | 2026_27_Q1 | 2025_26_Q2 | Standards of service
G110502584 | 502584 | Wastewater | G110 | Gate 110 | 2021-12-31 | 2021-12-16 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
G110502282 | 502282 | Water | G110 | Gate 110 | 2024-06-10 | 2023-08-28 | 2024_25_P03 | 2023_24_P05 | 2024_25_Q1 | 2023_24_Q2 | Standards of service
G110502425 | 502425 | Wastewater | G110 | Gate 110 | 2025-05-11 | 2024-06-12 | 2025_26_P02 | 2024_25_P03 | 2025_26_Q1 | 2024_25_Q1 | Standards of service
G110502375 | 502375 | Wastewater | G110 | Gate 110 | 2024-04-13 | 2023-06-19 | 2024_25_P01 | 2023_24_P03 | 2024_25_Q1 | 2023_24_Q1 | Standards of service
G110502342 | 502342 | Wastewater | G110 | Gate 110 | 2022-11-22 | 2023-02-20 | 2022_23_P08 | 2022_23_P11 | 2022_23_Q3 | 2022_23_Q4 | Standards of service
G110502895 | 502895 | Wastewater | G110 | Gate 110 | 2023-06-15 | 2023-03-29 | 2023_24_P03 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4 | Standards of service
G110502896 | 502896 | Water | G110 | Gate 110 | 2022-07-13 | 2022-03-30 | 2022_23_P04 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4 | Standards of service
G110502329 | 502329 | Water | G110 | Gate 110 | 2022-05-10 | 2022-02-25 | 2022_23_P02 | 2021_22_P11 | 2022_23_Q1 | 2021_22_Q4 | Standards of service
G110502868 | 502868 | Wastewater | G110 | Gate 110 | 2026-02-02 | 2025-07-14 | 2025_26_P11 | 2025_26_P04 | 2025_26_Q4 | 2025_26_Q2 | Standards of service
G110502578 | 502578 | Wastewater | G110 | Gate 110 | 2023-01-26 | 2022-06-30 | 2022_23_P10 | 2022_23_P03 | 2022_23_Q4 | 2022_23_Q1 | Standards of service
G110502648 | 502648 | Water | G110 | Gate 110 | 2023-08-23 | 2024-07-24 | 2023_24_P05 | 2024_25_P04 | 2023_24_Q2 | 2024_25_Q2 | Drinking Water
G110502355 | 502355 | Wastewater | G110 | Gate 110 | 2028-07-29 | 2028-05-25 | 2028_29_P04 | 2028_29_P02 | 2028_29_Q2 | 2028_29_Q1 | Standards of service
G110502382 | 502382 | Water | G110 | Gate 110 | 2022-07-30 | 2022-10-19 | 2022_23_P04 | 2022_23_P07 | 2022_23_Q2 | 2022_23_Q3 | Standards of service
G110502780 | 502780 | Wastewater | G110 | Gate 110 | 2022-03-12 | 2022-03-24 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
G110502651 | 502651 | Water | G110 | Gate 110 | 2023-04-19 | 2025-01-22 | 2023_24_P01 | 2024_25_P10 | 2023_24_Q1 | 2024_25_Q4 | Drinking Water
G110502652 | 502652 | Water | G110 | Gate 110 | 2023-10-16 | 2023-05-17 | 2023_24_P07 | 2023_24_P02 | 2023_24_Q3 | 2023_24_Q1 | Standards of service
G110502741 | 502741 | Wastewater | G110 | Gate 110 | 2022-04-22 | 2022-03-24 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4 | Standards of service
G110502742 | 502742 | Wastewater | G110 | Gate 110 | 2022-07-15 | 2022-03-29 | 2022_23_P04 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4 | Standards of service
G110502747 | 502747 | Wastewater | G110 | Gate 110 | 2022-07-01 | 2022-05-30 | 2022_23_P04 | 2022_23_P02 | 2022_23_Q2 | 2022_23_Q1 | Standards of service
G110502606 | 502606 | Water | G110 | Gate 110 | 2021-05-19 | 2021-10-28 | 2021_22_P02 | 2021_22_P07 | 2021_22_Q1 | 2021_22_Q3 | Supporting Sustainable Economic Growth
G110502369 | 502369 | Water | G110 | Gate 110 | 2025-05-12 | 2024-11-13 | 2025_26_P02 | 2024_25_P08 | 2025_26_Q1 | 2024_25_Q3 | Drinking Water
G110502412 | 502412 | Water | G110 | Gate 110 | 2022-03-26 | 2023-03-31 | 2021_22_P12 | 2022_23_P12 | 2021_22_Q4 | 2022_23_Q4 | Standards of service
G110502827 | 502827 | Wastewater | G110 | Gate 110 | 2022-10-14 | 2022-09-26 | 2022_23_P07 | 2022_23_P06 | 2022_23_Q3 | 2022_23_Q2 | Supporting Sustainable Economic Growth
G110502765 | 502765 | Wastewater | G110 | Gate 110 | 2022-07-27 | 2022-09-16 | 2022_23_P04 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2 | Standards of service
G110502766 | 502766 | Wastewater | G110 | Gate 110 | 2027-01-25 | 2026-09-30 | 2026_27_P10 | 2026_27_P06 | 2026_27_Q4 | 2026_27_Q2 | Supporting Sustainable Economic Growth
G110502743 | 502743 | Wastewater | G110 | Gate 110 | 2023-03-14 | 2023-03-23 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4 | Environment
G110502383 | 502383 | Water | G110 | Gate 110 | 2022-09-20 | 2022-07-27 | 2022_23_P06 | 2022_23_P04 | 2022_23_Q2 | 2022_23_Q2 | Standards of service
G110502934 | 502934 | Wastewater | G110 | Gate 110 | 2022-07-04 | 2022-03-24 | 2022_23_P04 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4 | Standards of service
G110502958 | 502958 | Wastewater | G110 | Gate 110 | 2023-09-30 | 2023-07-24 | 2023_24_P06 | 2023_24_P04 | 2023_24_Q2 | 2023_24_Q2 | Standards of service
G110502748 | 502748 | Wastewater | G110 | Gate 110 | 2023-04-24 | 2022-09-16 | 2023_24_P01 | 2022_23_P06 | 2023_24_Q1 | 2022_23_Q2 | Standards of service
G110502791 | 502791 | Water | G110 | Gate 110 | 2025-11-22 | 2025-05-14 | 2025_26_P08 | 2025_26_P02 | 2025_26_Q3 | 2025_26_Q1 | Standards of service
G110502792 | 502792 | Support Services | G110 | Gate 110 | 2021-12-01 | 2021-04-13 | 2021_22_P09 | 2021_22_P01 | 2021_22_Q3 | 2021_22_Q1 | Standards of service
G110502605 | 502605 | Water | G110 | Gate 110 | 2022-07-01 | 2022-06-30 | 2022_23_P04 | 2022_23_P03 | 2022_23_Q2 | 2022_23_Q1 | Standards of service
G110502563 | 502563 | Water | G110 | Gate 110 | 2022-10-19 | 2022-04-08 | 2022_23_P07 | 2022_23_P01 | 2022_23_Q3 | 2022_23_Q1 | Standards of service
G110503119 | 503119 | Support Services | G110 | Gate 110 | 2022-04-28 | 2022-03-11 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4 | Security & Resilience
G110503037 | 503037 | Water | G110 | Gate 110 | 2021-12-30 | 2021-09-13 | 2021_22_P09 | 2021_22_P06 | 2021_22_Q3 | 2021_22_Q2 | Standards of service
G110503072 | 503072 | Water | G110 | Gate 110 | 2023-07-01 | 2023-03-30 | 2023_24_P04 | 2022_23_P12 | 2023_24_Q2 | 2022_23_Q4 | Standards of service
G110502944 | 502944 | Wastewater | G110 | Gate 110 | 2022-06-07 | 2024-10-16 | 2022_23_P03 | 2024_25_P07 | 2022_23_Q1 | 2024_25_Q3 | Environment
G110502859 | 502859 | Water | G110 | Gate 110 | 2026-11-13 | 2026-05-13 | 2026_27_P08 | 2026_27_P02 | 2026_27_Q3 | 2026_27_Q1 | Standards of service
G110502866 | 502866 | Wastewater | G110 | Gate 110 | 2022-10-15 | 2024-04-03 | 2022_23_P07 | 2024_25_P01 | 2022_23_Q3 | 2024_25_Q1 | Supporting Sustainable Economic Growth
G110502867 | 502867 | Water | G110 | Gate 110 | 2022-10-15 | 2022-03-31 | 2022_23_P07 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4 | Standards of service
G110502358 | 502358 | Water | G110 | Gate 110 | 2025-03-03 | 2025-05-30 | 2024_25_P12 | 2025_26_P02 | 2024_25_Q4 | 2025_26_Q1 | Supporting Sustainable Economic Growth
G110502772 | 502772 | Water | G110 | Gate 110 | 2022-02-09 | 2021-12-03 | 2021_22_P11 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3 | Standards of service
G110502945 | 502945 | Wastewater | G110 | Gate 110 | 2022-06-30 | 2023-03-10 | 2022_23_P03 | 2022_23_P12 | 2022_23_Q1 | 2022_23_Q4 | Standards of service
G110502380 | 502380 | Water | G110 | Gate 110 | 2021-12-31 | 2022-10-19 | 2021_22_P09 | 2022_23_P07 | 2021_22_Q3 | 2022_23_Q3 | Standards of service
G110502883 | 502883 | Wastewater | G110 | Gate 110 | 2026-03-27 | 2025-10-29 | 2025_26_P12 | 2025_26_P07 | 2025_26_Q4 | 2025_26_Q3 | Standards of service
G110502689 | 502689 | Wastewater | G110 | Gate 110 | 2026-10-15 | 2026-11-11 | 2026_27_P07 | 2026_27_P08 | 2026_27_Q3 | 2026_27_Q3 | Standards of service
G110502783 | 502783 | Water | G110 | Gate 110 | 2023-03-24 | 2025-11-12 | 2022_23_P12 | 2025_26_P08 | 2022_23_Q4 | 2025_26_Q3 | Standards of service
G110502955 | 502955 | Wastewater | G110 | Gate 110 | 2025-10-09 | 2024-07-24 | 2025_26_P07 | 2024_25_P04 | 2025_26_Q3 | 2024_25_Q2 | Standards of service
G110502853 | 502853 | Water | G110 | Gate 110 | 2023-07-23 | 2023-01-25 | 2023_24_P04 | 2022_23_P10 | 2023_24_Q2 | 2022_23_Q4 | Standards of service
G110502649 | 502649 | Water | G110 | Gate 110 | 2023-10-31 | 2024-09-04 | 2023_24_P07 | 2024_25_P06 | 2023_24_Q3 | 2024_25_Q2 | Drinking Water
G110502650 | 502650 | Water | G110 | Gate 110 | 2023-09-20 | 2024-01-31 | 2023_24_P06 | 2023_24_P10 | 2023_24_Q2 | 2023_24_Q4 | Drinking Water
G110503050 | 503050 | Water | G110 | Gate 110 | 2023-05-22 | 2024-02-19 | 2023_24_P02 | 2023_24_P11 | 2023_24_Q1 | 2023_24_Q4 | Standards of service
G110502946 | 502946 | Wastewater | G110 | Gate 110 | 2022-09-03 | 2023-03-10 | 2022_23_P06 | 2022_23_P12 | 2022_23_Q2 | 2022_23_Q4 | Environment
G110502949 | 502949 | Wastewater | G110 | Gate 110 | 2023-03-08 | 2024-02-08 | 2022_23_P12 | 2023_24_P11 | 2022_23_Q4 | 2023_24_Q4 | Supporting Sustainable Economic Growth
G110503106 | 503106 | Water | G110 | Gate 110 | 2021-12-23 | 2021-09-28 | 2021_22_P09 | 2021_22_P06 | 2021_22_Q3 | 2021_22_Q2 | Standards of service
G110502947 | 502947 | Wastewater | G110 | Gate 110 | 2022-04-26 | 2022-03-23 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4 | Environment
G110502740 | 502740 | Wastewater | G110 | Gate 110 | 2022-05-28 | 2021-12-21 | 2022_23_P02 | 2021_22_P09 | 2022_23_Q1 | 2021_22_Q3 | Standards of service
G110502392 | 502392 | Water | G110 | Gate 110 | 2023-06-14 | 2023-05-31 | 2023_24_P03 | 2023_24_P02 | 2023_24_Q1 | 2023_24_Q1 | Supporting Sustainable Economic Growth
G110502746 | 502746 | Wastewater | G110 | Gate 110 | 2026-01-17 | 2025-01-22 | 2025_26_P10 | 2024_25_P10 | 2025_26_Q4 | 2024_25_Q4 | Standards of service
G110502749 | 502749 | Wastewater | G110 | Gate 110 | 2023-02-08 | 2023-03-23 | 2022_23_P11 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4 | Standards of service
G110503120 | 503120 | Support Services | G110 | Gate 110 | 2022-04-28 | 2022-03-31 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4 | Security & Resilience
G110502877 | 502877 | Wastewater | G110 | Gate 110 | 2025-11-21 | 2025-04-16 | 2025_26_P08 | 2025_26_P01 | 2025_26_Q3 | 2025_26_Q1 | Standards of service
G110502857 | 502857 | Water | G110 | Gate 110 | 2024-03-16 | 2024-01-29 | 2023_24_P12 | 2023_24_P10 | 2023_24_Q4 | 2023_24_Q4 | Standards of service
G110502808 | 502808 | Water | G110 | Gate 110 | 2022-08-03 | 2022-02-10 | 2022_23_P05 | 2021_22_P11 | 2022_23_Q2 | 2021_22_Q4 | Standards of service
G110503199 | 503199 | Water | G110 | Gate 110 | 2022-10-19 | 2022-03-30 | 2022_23_P07 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4 | Standards of service
G110503200 | 503200 | Water | G110 | Gate 110 | 2022-04-20 | 2021-12-23 | 2022_23_P01 | 2021_22_P09 | 2022_23_Q1 | 2021_22_Q3 | Standards of service
G110503193 | 503193 | Water | G110 | Gate 110 | 2021-12-01 | 2021-12-15 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
G110503194 | 503194 | Water | G110 | Gate 110 | 2022-01-26 | 2022-02-28 | 2021_22_P10 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
G110503256 | 503256 | Water | G110 | Gate 110 | 2022-04-06 | 2022-03-30 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4 | Standards of service
G110503257 | 503257 | Water | G110 | Gate 110 | 2022-10-19 | 2022-03-31 | 2022_23_P07 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4 | Standards of service
G110503132 | 503132 | Wastewater | G110 | Gate 110 | 2027-01-02 | 2026-07-30 | 2026_27_P10 | 2026_27_P04 | 2026_27_Q4 | 2026_27_Q2 | Standards of service
G110503177 | 503177 | Wastewater | G110 | Gate 110 | 2022-08-18 | 2022-03-29 | 2022_23_P05 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4 | Standards of service
G110503234 | 503234 | Water | G110 | Gate 110 | 2022-09-20 | 2022-03-18 | 2022_23_P06 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4 | Standards of service
G110503235 | 503235 | Water | G110 | Gate 110 | 2023-08-31 | 2025-05-14 | 2023_24_P05 | 2025_26_P02 | 2023_24_Q2 | 2025_26_Q1 | Standards of service
G110503249 | 503249 | Water | G110 | Gate 110 | 2022-01-20 | 2023-01-25 | 2021_22_P10 | 2022_23_P10 | 2021_22_Q4 | 2022_23_Q4 | Standards of service
G110503162 | 503162 | Water | G110 | Gate 110 | 2023-05-10 | 2024-09-18 | 2023_24_P02 | 2024_25_P06 | 2023_24_Q1 | 2024_25_Q2 | Standards of service
G110503248 | 503248 | Water | G110 | Gate 110 | 2021-12-29 | 2023-03-29 | 2021_22_P09 | 2022_23_P12 | 2021_22_Q3 | 2022_23_Q4 | Standards of service
G110503195 | 503195 | Water | G110 | Gate 110 | 2023-05-31 | 2022-03-30 | 2023_24_P02 | 2021_22_P12 | 2023_24_Q1 | 2021_22_Q4 | Standards of service
G110503197 | 503197 | Water | G110 | Gate 110 | 2022-10-19 | 2022-03-31 | 2022_23_P07 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4 | Standards of service
G110503083 | 503083 | Wastewater | G110 | Gate 110 | 2022-03-15 | 2022-03-24 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4 | Environment
G110502600 | 502600 | Water | G110 | Gate 110 | 2022-10-11 | 2023-03-30 | 2022_23_P07 | 2022_23_P12 | 2022_23_Q3 | 2022_23_Q4 | Standards of service
G110502943 | 502943 | Wastewater | G110 | Gate 110 | 2022-06-07 | 2022-10-12 | 2022_23_P03 | 2022_23_P07 | 2022_23_Q1 | 2022_23_Q3 | Environment
G110503056 | 503056 | Water | G110 | Gate 110 | 2025-12-08 | 2025-04-02 | 2025_26_P09 | 2025_26_P01 | 2025_26_Q3 | 2025_26_Q1 | Standards of service
G110503092 | 503092 | Water | G110 | Gate 110 | 2024-12-09 | 2024-09-04 | 2024_25_P09 | 2024_25_P06 | 2024_25_Q3 | 2024_25_Q2 | Standards of service
G110503045 | 503045 | Wastewater | G110 | Gate 110 | 2022-04-02 | 2022-02-01 | 2022_23_P01 | 2021_22_P11 | 2022_23_Q1 | 2021_22_Q4 | Supporting Sustainable Economic Growth
G110503266 | 503266 | Water | G110 | Gate 110 | 2022-02-28 | 2021-09-21 | 2021_22_P11 | 2021_22_P06 | 2021_22_Q4 | 2021_22_Q2 | Drinking Water
G110503480 | 503480 | Water | G110 | Gate 110 | 2025-05-11 | 2025-03-05 | 2025_26_P02 | 2024_25_P12 | 2025_26_Q1 | 2024_25_Q4 | Standards of service
G110503110 | 503110 | Water | G110 | Gate 110 | 2024-02-25 | 2023-12-20 | 2023_24_P11 | 2023_24_P09 | 2023_24_Q4 | 2023_24_Q3 | Drinking Water
G110503121 | 503121 | Support Services | G110 | Gate 110 | 2022-04-28 | 2022-03-11 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4 | Security & Resilience
G110503291 | 503291 | Support Services | G110 | Gate 110 | 2022-04-28 | 2022-05-06 | 2022_23_P01 | 2022_23_P02 | 2022_23_Q1 | 2022_23_Q1 | Security & Resilience
G110503230 | 503230 | Wastewater | G110 | Gate 110 | 2024-03-16 | 2023-10-18 | 2023_24_P12 | 2023_24_P07 | 2023_24_Q4 | 2023_24_Q3 | Standards of service
G110503094 | 503094 | Water | G110 | Gate 110 | 2021-12-31 | 2022-01-20 | 2021_22_P09 | 2021_22_P10 | 2021_22_Q3 | 2021_22_Q4 | Environment
G110503229 | 503229 | Wastewater | G110 | Gate 110 | 2022-09-10 | 2022-09-13 | 2022_23_P06 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2 | Standards of service
G110503170 | 503170 | Water | G110 | Gate 110 | 2021-06-30 | 2022-03-31 | 2021_22_P03 | 2021_22_P12 | 2021_22_Q1 | 2021_22_Q4 | Standards of service
G110503336 | 503336 | Water | G110 | Gate 110 | 2023-06-14 | 2024-12-11 | 2023_24_P03 | 2024_25_P09 | 2023_24_Q1 | 2024_25_Q3 | Standards of service
G110502940 | 502940 | Water | G110 | Gate 110 | 2023-01-11 | 2023-11-30 | 2022_23_P10 | 2023_24_P08 | 2022_23_Q4 | 2023_24_Q3 | Standards of service
G110503393 | 503393 | Wastewater | G110 | Gate 110 | 2022-08-04 | 2024-02-12 | 2022_23_P05 | 2023_24_P11 | 2022_23_Q2 | 2023_24_Q4 | Standards of service
G110503198 | 503198 | Water | G110 | Gate 110 | 2022-10-19 | 2022-03-30 | 2022_23_P07 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4 | Standards of service
G110503362 | 503362 | Wastewater | G110 | Gate 110 | 2024-06-12 | 2024-11-13 | 2024_25_P03 | 2024_25_P08 | 2024_25_Q1 | 2024_25_Q3 | Supporting Sustainable Economic Growth
G110503525 | 503525 | CE&FS | G110 | Gate 110 | 2026-06-26 | 2025-12-24 | 2026_27_P03 | 2025_26_P09 | 2026_27_Q1 | 2025_26_Q3 | Standards of service
G110503441 | 503441 | Wastewater | G110 | Gate 110 | 2024-05-16 | 2025-02-19 | 2024_25_P02 | 2024_25_P11 | 2024_25_Q1 | 2024_25_Q4 | Supporting Sustainable Economic Growth
G110503408 | 503408 | Water | G110 | Gate 110 | 2023-08-27 | 2022-12-21 | 2023_24_P05 | 2022_23_P09 | 2023_24_Q2 | 2022_23_Q3 | Standards of service
G110503238 | 503238 | Water | G110 | Gate 110 | 2026-06-21 | 2025-12-10 | 2026_27_P03 | 2025_26_P09 | 2026_27_Q1 | 2025_26_Q3 | Standards of service
G110503243 | 503243 | Water | G110 | Gate 110 | 2021-12-16 | 2021-09-13 | 2021_22_P09 | 2021_22_P06 | 2021_22_Q3 | 2021_22_Q2 | Standards of service
G110503250 | 503250 | Water | G110 | Gate 110 | 2023-01-25 | 2022-11-14 | 2022_23_P10 | 2022_23_P08 | 2022_23_Q4 | 2022_23_Q3 | Standards of service
G110503239 | 503239 | Water | G110 | Gate 110 | 2024-07-10 | 2022-11-02 | 2024_25_P04 | 2022_23_P08 | 2024_25_Q2 | 2022_23_Q3 | Supporting Sustainable Economic Growth
G110503236 | 503236 | Water | G110 | Gate 110 | 2022-01-05 | 2021-08-30 | 2021_22_P10 | 2021_22_P05 | 2021_22_Q4 | 2021_22_Q2 | Standards of service
G110503237 | 503237 | Water | G110 | Gate 110 | 2021-12-29 | 2021-12-17 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
G110503269 | 503269 | Wastewater | G110 | Gate 110 | 2023-02-16 | 2025-04-02 | 2022_23_P11 | 2025_26_P01 | 2022_23_Q4 | 2025_26_Q1 | Standards of service
G110503412 | 503412 | Water | G110 | Gate 110 | 2022-12-28 | 2022-03-30 | 2022_23_P09 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4 | Standards of service
G110503413 | 503413 | Water | G110 | Gate 110 | 2022-12-28 | 2022-03-30 | 2022_23_P09 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4 | Standards of service
G110503434 | 503434 | Water | G110 | Gate 110 | 2022-12-30 | 2023-03-28 | 2022_23_P09 | 2022_23_P12 | 2022_23_Q3 | 2022_23_Q4 | Standards of service
G110503562 | 503562 | Water | G110 | Gate 110 | 2022-06-11 | 2022-03-24 | 2022_23_P03 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4 | Drinking Water
G110503571 | 503571 | Wastewater | G110 | Gate 110 | 2022-12-30 | 2023-03-24 | 2022_23_P09 | 2022_23_P12 | 2022_23_Q3 | 2022_23_Q4 | Standards of service
G110503564 | 503564 | Wastewater | G110 | Gate 110 | 2022-11-04 | 2022-11-29 | 2022_23_P08 | 2022_23_P08 | 2022_23_Q3 | 2022_23_Q3 | Supporting Sustainable Economic Growth
G110503415 | 503415 | Wastewater | G110 | Gate 110 | 2023-01-21 | 2024-07-24 | 2022_23_P10 | 2024_25_P04 | 2022_23_Q4 | 2024_25_Q2 | Standards of service
G110503418 | 503418 | Wastewater | G110 | Gate 110 | 2022-07-01 | 2022-06-07 | 2022_23_P04 | 2022_23_P03 | 2022_23_Q2 | 2022_23_Q1 | Standards of service
G110503421 | 503421 | Water | G110 | Gate 110 | 2023-12-31 | 2023-11-29 | 2023_24_P09 | 2023_24_P08 | 2023_24_Q3 | 2023_24_Q3 | Drinking Water
G110503424 | 503424 | Wastewater | G110 | Gate 110 | 2021-12-18 | 2021-11-26 | 2021_22_P09 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3 | Standards of service
G110503587 | 503587 | Water | G110 | Gate 110 | 2022-07-31 | 2022-08-30 | 2022_23_P04 | 2022_23_P05 | 2022_23_Q2 | 2022_23_Q2 | Standards of service
G110503594 | 503594 | Wastewater | G110 | Gate 110 | 2025-04-06 | 2025-03-19 | 2025_26_P01 | 2024_25_P12 | 2025_26_Q1 | 2024_25_Q4 | Standards of service
G110503595 | 503595 | Water | G110 | Gate 110 | 2022-12-28 | 2024-11-27 | 2022_23_P09 | 2024_25_P08 | 2022_23_Q3 | 2024_25_Q3 | Standards of service
G110503628 | 503628 | Water | G110 | Gate 110 | 2026-11-16 | 2026-04-15 | 2026_27_P08 | 2026_27_P01 | 2026_27_Q3 | 2026_27_Q1 | Drinking Water
G110503630 | 503630 | Water | G110 | Gate 110 | 2022-10-19 | 2022-11-08 | 2022_23_P07 | 2022_23_P08 | 2022_23_Q3 | 2022_23_Q3 | Standards of service
G110503631 | 503631 | Water | G110 | Gate 110 | 2022-10-28 | 2022-12-23 | 2022_23_P07 | 2022_23_P09 | 2022_23_Q3 | 2022_23_Q3 | Standards of service
G110503638 | 503638 | Wastewater | G110 | Gate 110 | 2024-12-16 | 2025-10-15 | 2024_25_P09 | 2025_26_P07 | 2024_25_Q3 | 2025_26_Q3 | Standards of service
G110503632 | 503632 | Water | G110 | Gate 110 | 2023-04-05 | 2023-02-28 | 2023_24_P01 | 2022_23_P11 | 2023_24_Q1 | 2022_23_Q4 | Standards of service
G110503613 | 503613 | Water | G110 | Gate 110 | 2027-01-04 | 2025-06-11 | 2026_27_P10 | 2025_26_P03 | 2026_27_Q4 | 2025_26_Q1 | Standards of service
G110503617 | 503617 | Water | G110 | Gate 110 | 2022-12-16 | 2022-12-23 | 2022_23_P09 | 2022_23_P09 | 2022_23_Q3 | 2022_23_Q3 | Standards of service
G110503543 | 503543 | Wastewater | G110 | Gate 110 | 2022-06-22 | 2022-05-30 | 2022_23_P03 | 2022_23_P02 | 2022_23_Q1 | 2022_23_Q1 | Environment
G110503545 | 503545 | Wastewater | G110 | Gate 110 | 2022-06-22 | 2022-03-29 | 2022_23_P03 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4 | Environment
G110503546 | 503546 | Wastewater | G110 | Gate 110 | 2022-06-22 | 2021-12-22 | 2022_23_P03 | 2021_22_P09 | 2022_23_Q1 | 2021_22_Q3 | Environment
G110503656 | 503656 | Wastewater | G110 | Gate 110 | 2027-05-14 | 2024-02-29 | 2027_28_P02 | 2023_24_P11 | 2027_28_Q1 | 2023_24_Q4 | Standards of service
G110503678 | 503678 | Water | G110 | Gate 110 | 2024-10-12 | 2027-03-03 | 2024_25_P07 | 2026_27_P12 | 2024_25_Q3 | 2026_27_Q4 | Standards of service
G110503680 | 503680 | Water | G110 | Gate 110 | 2026-12-14 | 2026-03-18 | 2026_27_P09 | 2025_26_P12 | 2026_27_Q3 | 2025_26_Q4 | Standards of service
G110503681 | 503681 | Water | G110 | Gate 110 | 2026-05-24 | 2025-10-15 | 2026_27_P02 | 2025_26_P07 | 2026_27_Q1 | 2025_26_Q3 | Standards of service
G110503733 | 503733 | Water | G110 | Gate 110 | 2023-03-01 | 2022-03-31 | 2022_23_P12 | 2021_22_P12 | 2022_23_Q4 | 2021_22_Q4 | Standards of service
G110503686 | 503686 | Water | G110 | Gate 110 | 2024-05-27 | 2023-03-23 | 2024_25_P02 | 2022_23_P12 | 2024_25_Q1 | 2022_23_Q4 | Standards of service
G110503714 | 503714 | Water | G110 | Gate 110 | 2024-12-12 | 2024-10-16 | 2024_25_P09 | 2024_25_P07 | 2024_25_Q3 | 2024_25_Q3 | Standards of service
G110503716 | 503716 | Water | G110 | Gate 110 | 2023-01-29 | 2022-06-30 | 2022_23_P10 | 2022_23_P03 | 2022_23_Q4 | 2022_23_Q1 | Standards of service
G110503730 | 503730 | Water | G110 | Gate 110 | 2024-07-22 | 2023-03-13 | 2024_25_P04 | 2022_23_P12 | 2024_25_Q2 | 2022_23_Q4 | Standards of service
G110503731 | 503731 | Water | G110 | Gate 110 | 2023-05-24 | 2023-02-28 | 2023_24_P02 | 2022_23_P11 | 2023_24_Q1 | 2022_23_Q4 | Standards of service
G110503732 | 503732 | Water | G110 | Gate 110 | 2025-03-17 | 2024-07-24 | 2024_25_P12 | 2024_25_P04 | 2024_25_Q4 | 2024_25_Q2 | Standards of service
G110503726 | 503726 | Water | G110 | Gate 110 | 2022-07-07 | 2022-03-30 | 2022_23_P04 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4 | Standards of service
G110503753 | 503753 | Wastewater | G110 | Gate 110 | 2026-01-22 | 2025-03-19 | 2025_26_P10 | 2024_25_P12 | 2025_26_Q4 | 2024_25_Q4 | Standards of service
G110503727 | 503727 | Water | G110 | Gate 110 | 2022-11-16 | 2022-03-31 | 2022_23_P08 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4 | Standards of service
G110503728 | 503728 | Water | G110 | Gate 110 | 2022-03-31 | 2021-12-23 | 2021_22_P12 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3 | Standards of service
G110503701 | 503701 | Wastewater | G110 | Gate 110 | 2022-02-12 | 2021-08-27 | 2021_22_P11 | 2021_22_P05 | 2021_22_Q4 | 2021_22_Q2 | Standards of service
G110503761 | 503761 | Water | G110 | Gate 110 | 2024-03-20 | 2023-11-29 | 2023_24_P12 | 2023_24_P08 | 2023_24_Q4 | 2023_24_Q3 | Drinking Water
G110503699 | 503699 | Water | G110 | Gate 110 | 2026-04-17 | 2025-10-01 | 2026_27_P01 | 2025_26_P07 | 2026_27_Q1 | 2025_26_Q3 | Standards of service
G110503860 | 503860 | Wastewater | G110 | Gate 110 | 2023-04-28 | 2023-01-31 | 2023_24_P01 | 2022_23_P10 | 2023_24_Q1 | 2022_23_Q4 | Standards of service
G110504068 | 504068 | Water | G110 | Gate 110 | 2026-10-10 | 2026-04-01 | 2026_27_P07 | 2026_27_P01 | 2026_27_Q3 | 2026_27_Q1 | Standards of service
G110504203 | 504203 | Water | G110 | Gate 110 | 2027-10-09 | 2026-10-21 | 2027_28_P07 | 2026_27_P07 | 2027_28_Q3 | 2026_27_Q3 | Standards of service
G110504391 | 504391 | Water | G110 | Gate 110 | 2028-11-09 | 2027-12-08 | 2028_29_P08 | 2027_28_P09 | 2028_29_Q3 | 2027_28_Q3 | Drinking Water
G110504434 | 504434 | Water | G110 | Gate 110 | 2022-08-19 | 2022-03-29 | 2022_23_P05 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4 | Standards of service
G110504465 | 504465 | Water | G110 | Gate 110 | 2025-01-12 | 2025-03-05 | 2024_25_P10 | 2024_25_P12 | 2024_25_Q4 | 2024_25_Q4 | Standards of service
G110505032 | 505032 | Water | G110 | Gate 110 | 2022-09-10 | 2022-10-31 | 2022_23_P06 | 2022_23_P07 | 2022_23_Q2 | 2022_23_Q3 | Supporting Sustainable Economic Growth
G110504995 | 504995 | Water | G110 | Gate 110 | 2025-07-21 | 2024-11-27 | 2025_26_P04 | 2024_25_P08 | 2025_26_Q2 | 2024_25_Q3 | Standards of service
G110505053 | 505053 | Wastewater | G110 | Gate 110 | 2024-04-28 | 2024-03-22 | 2024_25_P01 | 2023_24_P12 | 2024_25_Q1 | 2023_24_Q4 | Standards of service
G110505339 | 505339 | Wastewater | G110 | Gate 110 | 2026-06-29 | 2026-01-21 | 2026_27_P03 | 2025_26_P10 | 2026_27_Q1 | 2025_26_Q4 | Standards of service
G110505384 | 505384 | Water | G110 | Gate 110 | 2024-10-19 | 2024-05-15 | 2024_25_P07 | 2024_25_P02 | 2024_25_Q3 | 2024_25_Q1 | Standards of service
G110505447 | 505447 | Water | G110 | Gate 110 | 2024-03-07 | 2023-03-31 | 2023_24_P12 | 2022_23_P12 | 2023_24_Q4 | 2022_23_Q4 | Standards of service
G110505504 | 505504 | Water | G110 | Gate 110 | 2023-09-01 | 2023-08-11 | 2023_24_P06 | 2023_24_P05 | 2023_24_Q2 | 2023_24_Q2 | Standards of service
G110505687 | 505687 | Wastewater | G110 | Gate 110 | 2024-11-24 | 2024-09-18 | 2024_25_P08 | 2024_25_P06 | 2024_25_Q3 | 2024_25_Q2 | Supporting Sustainable Economic Growth
G110505693 | 505693 | Water | G110 | Gate 110 | 2024-11-22 | 2023-09-29 | 2024_25_P08 | 2023_24_P06 | 2024_25_Q3 | 2023_24_Q2 | Standards of service
G110505641 | 505641 | Wastewater | G110 | Gate 110 | 2023-09-10 | 2023-12-18 | 2023_24_P06 | 2023_24_P09 | 2023_24_Q2 | 2023_24_Q3 | Standards of service
G110505927 | 505927 | Water | G110 | Gate 110 | 2025-01-03 | 2024-03-28 | 2024_25_P10 | 2023_24_P12 | 2024_25_Q4 | 2023_24_Q4 | Standards of service
G110505949 | 505949 | Wastewater | G110 | Gate 110 | 2025-12-15 | 2025-10-29 | 2025_26_P09 | 2025_26_P07 | 2025_26_Q3 | 2025_26_Q3 | Standards of service
G110506029 | 506029 | Water | G110 | Gate 110 | 2025-03-16 | 2025-10-15 | 2024_25_P12 | 2025_26_P07 | 2024_25_Q4 | 2025_26_Q3 | Standards of service
G110506032 | 506032 | Water | G110 | Gate 110 | 2025-04-25 | 2025-04-16 | 2025_26_P01 | 2025_26_P01 | 2025_26_Q1 | 2025_26_Q1 | Standards of service
G110506149 | 506149 | Water | G110 | Gate 110 | 2024-12-12 | 2026-05-13 | 2024_25_P09 | 2026_27_P02 | 2024_25_Q3 | 2026_27_Q1 | Standards of service
G110506151 | 506151 | Water | G110 | Gate 110 | 2025-08-21 | 2025-02-05 | 2025_26_P05 | 2024_25_P11 | 2025_26_Q2 | 2024_25_Q4 | Standards of service
G110506130 | 506130 | Water | G110 | Gate 110 | 2028-02-10 | 2027-07-07 | 2027_28_P11 | 2027_28_P04 | 2027_28_Q4 | 2027_28_Q2 | Standards of service
G110506234 | 506234 | Water | G110 | Gate 110 | 2024-03-28 | 2023-02-24 | 2023_24_P12 | 2022_23_P11 | 2023_24_Q4 | 2022_23_Q4 | Standards of service
G110506186 | 506186 | Water | G110 | Gate 110 | 2026-02-21 | 2025-08-20 | 2025_26_P11 | 2025_26_P05 | 2025_26_Q4 | 2025_26_Q2 | Standards of service
G110506232 | 506232 | Water | G110 | Gate 110 | 2024-03-28 | 2023-06-21 | 2023_24_P12 | 2023_24_P03 | 2023_24_Q4 | 2023_24_Q1 | Standards of service
G110506228 | 506228 | Water | G110 | Gate 110 | 2024-03-28 | 2023-09-28 | 2023_24_P12 | 2023_24_P06 | 2023_24_Q4 | 2023_24_Q2 | Standards of service
G110506231 | 506231 | Water | G110 | Gate 110 | 2025-06-12 | 2024-09-18 | 2025_26_P03 | 2024_25_P06 | 2025_26_Q1 | 2024_25_Q2 | Standards of service
G110506275 | 506275 | Water | G110 | Gate 110 | 2024-10-17 | 2024-03-26 | 2024_25_P07 | 2023_24_P12 | 2024_25_Q3 | 2023_24_Q4 | Standards of service
G110506271 | 506271 | Water | G110 | Gate 110 | 2025-06-01 | 2025-03-19 | 2025_26_P03 | 2024_25_P12 | 2025_26_Q1 | 2024_25_Q4 | Standards of service
G110506422 | 506422 | Support Services | G110 | Gate 110 | 2024-03-17 | 2023-09-11 | 2023_24_P12 | 2023_24_P06 | 2023_24_Q4 | 2023_24_Q2 | Security & Resilience
G110506586 | 506586 | Wastewater | G110 | Gate 110 | 2026-04-23 | 2025-04-30 | 2026_27_P01 | 2025_26_P01 | 2026_27_Q1 | 2025_26_Q1 | Environment
G110506608 | 506608 | Water | G110 | Gate 110 | 2024-01-21 | 2023-09-04 | 2023_24_P10 | 2023_24_P06 | 2023_24_Q4 | 2023_24_Q2 | Standards of service
G110506618 | 506618 | Water | G110 | Gate 110 | 2024-11-17 | 2024-03-28 | 2024_25_P08 | 2023_24_P12 | 2024_25_Q3 | 2023_24_Q4 | Standards of service
G110506684 | 506684 | Water | G110 | Gate 110 | 2023-12-23 | 2023-08-29 | 2023_24_P09 | 2023_24_P05 | 2023_24_Q3 | 2023_24_Q2 | Standards of service
G110506779 | 506779 | Water | G110 | Gate 110 | 2024-10-14 | 2024-07-24 | 2024_25_P07 | 2024_25_P04 | 2024_25_Q3 | 2024_25_Q2 | Standards of service
G110506864 | 506864 | Water | G110 | Gate 110 | 2023-11-30 | 2023-10-31 | 2023_24_P08 | 2023_24_P07 | 2023_24_Q3 | 2023_24_Q3 | Supporting Sustainable Economic Growth
G110506865 | 506865 | Wastewater | G110 | Gate 110 | 2023-11-30 | 2023-10-31 | 2023_24_P08 | 2023_24_P07 | 2023_24_Q3 | 2023_24_Q3 | Supporting Sustainable Economic Growth
G110506896 | 506896 | Support Services | G110 | Gate 110 | 2022-07-01 | 2022-03-10 | 2022_23_P04 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4 | Standards of service
G110507057 | 507057 | Water | G110 | Gate 110 | 2024-09-12 | 2023-11-22 | 2024_25_P06 | 2023_24_P08 | 2024_25_Q2 | 2023_24_Q3 | Standards of service
G110507186 | 507186 | Water | G110 | Gate 110 | 2024-04-11 | 2023-03-28 | 2024_25_P01 | 2022_23_P12 | 2024_25_Q1 | 2022_23_Q4 | Standards of service
G110507189 | 507189 | Water | G110 | Gate 110 | 2024-09-13 | 2023-09-29 | 2024_25_P06 | 2023_24_P06 | 2024_25_Q2 | 2023_24_Q2 | Standards of service
G110507173 | 507173 | Support Services | G110 | Gate 110 | 2022-05-03 | 2022-02-01 | 2022_23_P02 | 2021_22_P11 | 2022_23_Q1 | 2021_22_Q4 | Security & Resilience
G110507209 | 507209 | Wastewater | G110 | Gate 110 | 2025-10-27 | 2025-04-16 | 2025_26_P07 | 2025_26_P01 | 2025_26_Q3 | 2025_26_Q1 | Standards of service
G110507455 | 507455 | Water | G110 | Gate 110 | 2025-01-29 | 2024-03-28 | 2024_25_P10 | 2023_24_P12 | 2024_25_Q4 | 2023_24_Q4 | Supporting Sustainable Economic Growth
G110507492 | 507492 | Water | G110 | Gate 110 | 2026-02-23 | 2025-11-26 | 2025_26_P11 | 2025_26_P08 | 2025_26_Q4 | 2025_26_Q3 | Standards of service
G110507493 | 507493 | Water | G110 | Gate 110 | 2025-01-11 | 2024-03-20 | 2024_25_P10 | 2023_24_P12 | 2024_25_Q4 | 2023_24_Q4 | Standards of service
G110507813 | 507813 | Water | G110 | Gate 110 | 2023-01-24 | 2022-08-15 | 2022_23_P10 | 2022_23_P05 | 2022_23_Q4 | 2022_23_Q2 | Standards of service
G110507860 | 507860 | Water | G110 | Gate 110 | 2023-02-13 | 2022-06-29 | 2022_23_P11 | 2022_23_P03 | 2022_23_Q4 | 2022_23_Q1 | Standards of service
G110507808 | 507808 | Wastewater | G110 | Gate 110 | 2025-09-01 | 2025-02-25 | 2025_26_P06 | 2024_25_P11 | 2025_26_Q2 | 2024_25_Q4 | Supporting Sustainable Economic Growth
G110507933 | 507933 | Wastewater | G110 | Gate 110 | 2023-08-13 | 2023-12-19 | 2023_24_P05 | 2023_24_P09 | 2023_24_Q2 | 2023_24_Q3 | Standards of service
G110508109 | 508109 | Support Services | G110 | Gate 110 | 2022-02-12 | 2022-02-10 | 2021_22_P11 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4 | Standards of service
G110508601 | 508601 | Wastewater | G110 | Gate 110 | 2023-03-09 | 2022-11-29 | 2022_23_P12 | 2022_23_P08 | 2022_23_Q4 | 2022_23_Q3 | Standards of service
G110508752 | 508752 | Wastewater | G110 | Gate 110 | 2025-02-02 | 2025-04-02 | 2024_25_P11 | 2025_26_P01 | 2024_25_Q4 | 2025_26_Q1 | Supporting Sustainable Economic Growth
G110508949 | 508949 | Water | G110 | Gate 110 | 2027-07-01 | 2027-04-14 | 2027_28_P04 | 2027_28_P01 | 2027_28_Q2 | 2027_28_Q1 | Supporting Sustainable Economic Growth
G110509283 | 509283 | Water | G110 | Gate 110 | 2023-03-05 | 2022-09-29 | 2022_23_P12 | 2022_23_P06 | 2022_23_Q4 | 2022_23_Q2 | Standards of service
G110510392 | 510392 | Wastewater | G110 | Gate 110 | 2024-05-28 | 2023-09-13 | 2024_25_P02 | 2023_24_P06 | 2024_25_Q1 | 2023_24_Q2 | Standards of service
G110510546 | 510546 | Wastewater | G110 | Gate 110 | 2026-03-23 | 2025-11-12 | 2025_26_P12 | 2025_26_P08 | 2025_26_Q4 | 2025_26_Q3 | Standards of service
G110510727 | 510727 | Support Services | G110 | Gate 110 | 2023-04-03 | 2024-08-06 | 2023_24_P01 | 2024_25_P05 | 2023_24_Q1 | 2024_25_Q2 | Standards of service
G110510931 | 510931 | Water | G110 | Gate 110 | 2024-08-12 | 2023-08-29 | 2024_25_P05 | 2023_24_P05 | 2024_25_Q2 | 2023_24_Q2 | Standards of service
G110511334 | 511334 | Water | G110 | Gate 110 | 2024-10-11 | 2023-10-27 | 2024_25_P07 | 2023_24_P07 | 2024_25_Q3 | 2023_24_Q3 | Standards of service
G110511344 | 511344 | Support Services | G110 | Gate 110 | 2025-01-16 | 2023-03-24 | 2024_25_P10 | 2022_23_P12 | 2024_25_Q4 | 2022_23_Q4 | Standards of service
G110511495 | 511495 | Water | G110 | Gate 110 | 2025-04-17 | 2024-11-13 | 2025_26_P01 | 2024_25_P08 | 2025_26_Q1 | 2024_25_Q3 | Drinking Water
G110511500 | 511500 | Water | G110 | Gate 110 | 2024-09-21 | 2024-06-26 | 2024_25_P06 | 2024_25_P03 | 2024_25_Q2 | 2024_25_Q1 | Drinking Water
G110511704 | 511704 | Water | G110 | Gate 110 | 2024-09-30 | 2023-12-20 | 2024_25_P06 | 2023_24_P09 | 2024_25_Q2 | 2023_24_Q3 | Standards of service
G110512469 | 512469 | Water | G110 | Gate 110 | 2024-07-22 | 2023-11-14 | 2024_25_P04 | 2023_24_P08 | 2024_25_Q2 | 2023_24_Q3 | Drinking Water
G110512555 | 512555 | Wastewater | G110 | Gate 110 | 2026-07-06 | 2026-04-01 | 2026_27_P04 | 2026_27_P01 | 2026_27_Q2 | 2026_27_Q1 | Supporting Sustainable Economic Growth
G110512600 | 512600 | Water | G110 | Gate 110 | 2024-05-20 | 2023-07-14 | 2024_25_P02 | 2023_24_P04 | 2024_25_Q1 | 2023_24_Q2 | Supporting Sustainable Economic Growth
G110512639 | 512639 | Support Services | G110 | Gate 110 | 2024-06-26 | 2024-10-01 | 2024_25_P03 | 2024_25_P07 | 2024_25_Q1 | 2024_25_Q3 | Standards of service
G110512749 | 512749 | Water | G110 | Gate 110 | 2024-08-26 | 2023-03-29 | 2024_25_P05 | 2022_23_P12 | 2024_25_Q2 | 2022_23_Q4 | Standards of service
G110512711 | 512711 | Water | G110 | Gate 110 | 2024-06-06 | 2023-06-30 | 2024_25_P03 | 2023_24_P03 | 2024_25_Q1 | 2023_24_Q1 | Standards of service
G110512815 | 512815 | Water | G110 | Gate 110 | 2025-07-10 | 2025-05-28 | 2025_26_P04 | 2025_26_P02 | 2025_26_Q2 | 2025_26_Q1 | Standards of service
G110512940 | 512940 | Water | G110 | Gate 110 | 2025-03-20 | 2024-03-28 | 2024_25_P12 | 2023_24_P12 | 2024_25_Q4 | 2023_24_Q4 | Standards of service
G110512997 | 512997 | Water | G110 | Gate 110 | 2025-05-01 | 2024-06-18 | 2025_26_P02 | 2024_25_P03 | 2025_26_Q1 | 2024_25_Q1 | Supporting Sustainable Economic Growth
G110513208 | 513208 | Water | G110 | Gate 110 | 2024-12-30 | 2024-11-27 | 2024_25_P09 | 2024_25_P08 | 2024_25_Q3 | 2024_25_Q3 | Drinking Water
G110513312 | 513312 | CE&FS | G110 | Gate 110 | 2028-06-12 | 2027-09-15 | 2028_29_P03 | 2027_28_P06 | 2028_29_Q1 | 2027_28_Q2 | Long Term Water Sector Vision
G110513433 | 513433 | Water | G110 | Gate 110 | 2024-11-24 | 2025-04-30 | 2024_25_P08 | 2025_26_P01 | 2024_25_Q3 | 2025_26_Q1 | Drinking Water
G110513412 | 513412 | Wastewater | G110 | Gate 110 | 2026-02-06 | 2025-10-15 | 2025_26_P11 | 2025_26_P07 | 2025_26_Q4 | 2025_26_Q3 | Standards of service
G110513417 | 513417 | Wastewater | G110 | Gate 110 | 2026-03-02 | 2025-09-19 | 2025_26_P12 | 2025_26_P06 | 2025_26_Q4 | 2025_26_Q2 | Standards of service
G110513461 | 513461 | Support Services | G110 | Gate 110 | 2023-05-18 | 2024-03-06 | 2023_24_P02 | 2023_24_P12 | 2023_24_Q1 | 2023_24_Q4 | Standards of service
G110513514 | 513514 | Wastewater | G110 | Gate 110 | 2025-10-17 | 2025-03-05 | 2025_26_P07 | 2024_25_P12 | 2025_26_Q3 | 2024_25_Q4 | Standards of service
G110513826 | 513826 | Water | G110 | Gate 110 | 2025-02-09 | 2025-03-19 | 2024_25_P11 | 2024_25_P12 | 2024_25_Q4 | 2024_25_Q4 | Standards of service
G110513827 | 513827 | Water | G110 | Gate 110 | 2026-07-09 | 2025-10-01 | 2026_27_P04 | 2025_26_P07 | 2026_27_Q2 | 2025_26_Q3 | Standards of service
G110513829 | 513829 | Water | G110 | Gate 110 | 2026-05-28 | 2026-01-21 | 2026_27_P02 | 2025_26_P10 | 2026_27_Q1 | 2025_26_Q4 | Standards of service
G110513832 | 513832 | Support Services | G110 | Gate 110 | 2022-12-26 | 2022-06-30 | 2022_23_P09 | 2022_23_P03 | 2022_23_Q3 | 2022_23_Q1 | Standards of service
G110513880 | 513880 | Support Services | G110 | Gate 110 | 2026-04-06 | 2025-12-03 | 2026_27_P01 | 2025_26_P09 | 2026_27_Q1 | 2025_26_Q3 | Security & Resilience
G110513923 | 513923 | Water | G110 | Gate 110 | 2024-03-28 | 2025-04-02 | 2023_24_P12 | 2025_26_P01 | 2023_24_Q4 | 2025_26_Q1 | Standards of service
G110513964 | 513964 | Water | G110 | Gate 110 | 2025-01-30 | 2024-08-05 | 2024_25_P10 | 2024_25_P05 | 2024_25_Q4 | 2024_25_Q2 | Standards of service
G110514041 | 514041 | Wastewater | G110 | Gate 110 | 2025-09-08 | 2025-04-02 | 2025_26_P06 | 2025_26_P01 | 2025_26_Q2 | 2025_26_Q1 | Standards of service
G110514045 | 514045 | Wastewater | G110 | Gate 110 | 2025-05-02 | 2024-03-21 | 2025_26_P02 | 2023_24_P12 | 2025_26_Q1 | 2023_24_Q4 | Environment
G110514047 | 514047 | Water | G110 | Gate 110 | 2025-10-09 | 2025-03-05 | 2025_26_P07 | 2024_25_P12 | 2025_26_Q3 | 2024_25_Q4 | Standards of service
G110514080 | 514080 | Water | G110 | Gate 110 | 2025-08-24 | 2025-03-05 | 2025_26_P05 | 2024_25_P12 | 2025_26_Q2 | 2024_25_Q4 | Standards of service
G110514217 | 514217 | Wastewater | G110 | Gate 110 | 2024-04-13 | 2023-09-07 | 2024_25_P01 | 2023_24_P06 | 2024_25_Q1 | 2023_24_Q2 | Standards of service
G110514281 | 514281 | Water | G110 | Gate 110 | 2025-09-22 | 2024-11-27 | 2025_26_P06 | 2024_25_P08 | 2025_26_Q2 | 2024_25_Q3 | Standards of service
G110514282 | 514282 | Water | G110 | Gate 110 | 2025-12-15 | 2025-03-19 | 2025_26_P09 | 2024_25_P12 | 2025_26_Q3 | 2024_25_Q4 | Standards of service
G110514441 | 514441 | Support Services | G110 | Gate 110 | 2024-10-06 | 2024-02-29 | 2024_25_P07 | 2023_24_P11 | 2024_25_Q3 | 2023_24_Q4 | Security & Resilience
G110514448 | 514448 | Wastewater | G110 | Gate 110 | 2025-08-01 | 2024-05-29 | 2025_26_P05 | 2024_25_P02 | 2025_26_Q2 | 2024_25_Q1 | Standards of service
G110514460 | 514460 | Wastewater | G110 | Gate 110 | 2026-04-23 | 2025-07-15 | 2026_27_P01 | 2025_26_P04 | 2026_27_Q1 | 2025_26_Q2 | Standards of service
G110514551 | 514551 | Wastewater | G110 | Gate 110 | 2025-03-29 | 2024-07-10 | 2024_25_P12 | 2024_25_P04 | 2024_25_Q4 | 2024_25_Q2 | Standards of service
G110514598 | 514598 | Support Services | G110 | Gate 110 | 2024-06-20 | 2024-10-08 | 2024_25_P03 | 2024_25_P07 | 2024_25_Q1 | 2024_25_Q3 | Standards of service
G110514631 | 514631 | Wastewater | G110 | Gate 110 | 2024-08-04 | 2024-02-29 | 2024_25_P05 | 2023_24_P11 | 2024_25_Q2 | 2023_24_Q4 | Standards of service
G110514765 | 514765 | Wastewater | G110 | Gate 110 | 2025-12-12 | 2025-05-28 | 2025_26_P09 | 2025_26_P02 | 2025_26_Q3 | 2025_26_Q1 | Standards of service
G110514783 | 514783 | Wastewater | G110 | Gate 110 | 2026-01-01 | 2025-04-30 | 2025_26_P10 | 2025_26_P01 | 2025_26_Q4 | 2025_26_Q1 | Standards of service
G110514831 | 514831 | Wastewater | G110 | Gate 110 | 2026-03-09 | 2025-09-17 | 2025_26_P12 | 2025_26_P06 | 2025_26_Q4 | 2025_26_Q2 | Standards of service
G110515139 | 515139 | Water | G110 | Gate 110 | 2024-12-02 | 2024-03-26 | 2024_25_P09 | 2023_24_P12 | 2024_25_Q3 | 2023_24_Q4 | Standards of service
G110515268 | 515268 | Support Services | G110 | Gate 110 | 2025-01-20 | 2024-11-12 | 2024_25_P10 | 2024_25_P08 | 2024_25_Q4 | 2024_25_Q3 | Security & Resilience
G110515404 | 515404 | CE&FS | G110 | Gate 110 | 2025-08-28 | 2024-12-11 | 2025_26_P05 | 2024_25_P09 | 2025_26_Q2 | 2024_25_Q3 | Climate Change, Adaptation and Mitigation
G110515505 | 515505 | Water | G110 | Gate 110 | 2023-07-16 | 2024-02-29 | 2023_24_P04 | 2023_24_P11 | 2023_24_Q2 | 2023_24_Q4 | Drinking Water
G110515607 | 515607 | Wastewater | G110 | Gate 110 | 2025-07-03 | 2025-01-22 | 2025_26_P04 | 2024_25_P10 | 2025_26_Q2 | 2024_25_Q4 | Standards of service
G110515612 | 515612 | Wastewater | G110 | Gate 110 | 2026-02-27 | 2025-07-09 | 2025_26_P11 | 2025_26_P04 | 2025_26_Q4 | 2025_26_Q2 | Standards of service
G110515625 | 515625 | Support Services | G110 | Gate 110 | 2024-01-28 | 2023-03-08 | 2023_24_P10 | 2022_23_P12 | 2023_24_Q4 | 2022_23_Q4 | Standards of service
G110515827 | 515827 | Wastewater | G110 | Gate 110 | 2025-08-28 | 2026-04-29 | 2025_26_P05 | 2026_27_P01 | 2025_26_Q2 | 2026_27_Q1 | Standards of service
G110516045 | 516045 | Water | G110 | Gate 110 | 2025-07-14 | 2024-02-29 | 2025_26_P04 | 2023_24_P11 | 2025_26_Q2 | 2023_24_Q4 | Standards of service
G110516085 | 516085 | Water | G110 | Gate 110 | 2025-12-07 | 2025-04-02 | 2025_26_P09 | 2025_26_P01 | 2025_26_Q3 | 2025_26_Q1 | Standards of service
G110516082 | 516082 | Water | G110 | Gate 110 | 2026-06-15 | 2025-09-22 | 2026_27_P03 | 2025_26_P06 | 2026_27_Q1 | 2025_26_Q2 | Standards of service
G110516517 | 516517 | Water | G110 | Gate 110 | 2026-02-22 | 2025-05-14 | 2025_26_P11 | 2025_26_P02 | 2025_26_Q4 | 2025_26_Q1 | Standards of service
G110516502 | 516502 | Water | G110 | Gate 110 | 2023-09-24 | 2023-08-28 | 2023_24_P06 | 2023_24_P05 | 2023_24_Q2 | 2023_24_Q2 | Drinking Water
G110516563 | 516563 | Wastewater | G110 | Gate 110 | 2026-11-09 | 2026-05-13 | 2026_27_P08 | 2026_27_P02 | 2026_27_Q3 | 2026_27_Q1 | Standards of service
G110516659 | 516659 | Wastewater | G110 | Gate 110 | 2024-07-06 | 2024-03-26 | 2024_25_P04 | 2023_24_P12 | 2024_25_Q2 | 2023_24_Q4 | Climate Change, Adaptation and Mitigation
G110516857 | 516857 | Wastewater | G110 | Gate 110 | 2025-04-13 | 2024-08-21 | 2025_26_P01 | 2024_25_P05 | 2025_26_Q1 | 2024_25_Q2 | Standards of service
G110517345 | 517345 | CE&FS | G110 | Gate 110 | 2026-12-14 | 2026-06-24 | 2026_27_P09 | 2026_27_P03 | 2026_27_Q3 | 2026_27_Q1 | Climate Change, Adaptation and Mitigation
G110517325 | 517325 | Wastewater | G110 | Gate 110 | 2026-04-13 | 2025-08-20 | 2026_27_P01 | 2025_26_P05 | 2026_27_Q1 | 2025_26_Q2 | Standards of service
G110517533 | 517533 | Water | G110 | Gate 110 | 2026-06-13 | 2025-10-15 | 2026_27_P03 | 2025_26_P07 | 2026_27_Q1 | 2025_26_Q3 | Drinking Water
G110517567 | 517567 | Support Services | G110 | Gate 110 | 2025-04-03 | 2024-10-02 | 2025_26_P01 | 2024_25_P07 | 2025_26_Q1 | 2024_25_Q3 | Standards of service
G110517996 | 517996 | Water | G110 | Gate 110 | 2026-01-23 | 2024-03-28 | 2025_26_P10 | 2023_24_P12 | 2025_26_Q4 | 2023_24_Q4 | Standards of service
G110518147 | 518147 | Water | G110 | Gate 110 | 2026-06-18 | 2025-11-17 | 2026_27_P03 | 2025_26_P08 | 2026_27_Q1 | 2025_26_Q3 | Supporting Sustainable Economic Growth
G110518244 | 518244 | Wastewater | G110 | Gate 110 | 2025-09-26 | 2025-01-08 | 2025_26_P06 | 2024_25_P10 | 2025_26_Q2 | 2024_25_Q4 | Standards of service
G110518444 | 518444 | Water | G110 | Gate 110 | 2024-07-14 | 2024-02-26 | 2024_25_P04 | 2023_24_P11 | 2024_25_Q2 | 2023_24_Q4 | Environment
G110518591 | 518591 | Water | G110 | Gate 110 | 2026-04-06 | 2025-08-06 | 2026_27_P01 | 2025_26_P05 | 2026_27_Q1 | 2025_26_Q2 | Standards of service
G110518579 | 518579 | Wastewater | G110 | Gate 110 | 2024-10-22 | 2024-05-01 | 2024_25_P07 | 2024_25_P02 | 2024_25_Q3 | 2024_25_Q1 | Standards of service
G110518658 | 518658 | Support Services | G110 | Gate 110 | 2026-06-25 | 2026-12-09 | 2026_27_P03 | 2026_27_P09 | 2026_27_Q1 | 2026_27_Q3 | Standards of service
G110518660 | 518660 | Support Services | G110 | Gate 110 | 2026-06-25 | 2027-01-20 | 2026_27_P03 | 2026_27_P10 | 2026_27_Q1 | 2026_27_Q4 | Standards of service
G110518731 | 518731 | Wastewater | G110 | Gate 110 | 2025-11-02 | 2025-06-25 | 2025_26_P08 | 2025_26_P03 | 2025_26_Q3 | 2025_26_Q1 | Standards of service
G110519344 | 519344 | Support Services | G110 | Gate 110 | 2026-09-01 | 2026-02-18 | 2026_27_P06 | 2025_26_P11 | 2026_27_Q2 | 2025_26_Q4 | Standards of service
G110519703 | 519703 | Water | G110 | Gate 110 | 2025-01-06 | 2024-11-13 | 2024_25_P10 | 2024_25_P08 | 2024_25_Q4 | 2024_25_Q3 | Drinking Water
G110519709 | 519709 | Water | G110 | Gate 110 | 2026-07-09 | 2025-11-12 | 2026_27_P04 | 2025_26_P08 | 2026_27_Q2 | 2025_26_Q3 | Standards of service
G110520166 | 520166 | Water | G110 | Gate 110 | 2025-08-25 | 2025-02-19 | 2025_26_P05 | 2024_25_P11 | 2025_26_Q2 | 2024_25_Q4 | Standards of service
G110520228 | 520228 | Water | G110 | Gate 110 | 2025-04-27 | 2024-08-21 | 2025_26_P01 | 2024_25_P05 | 2025_26_Q1 | 2024_25_Q2 | Drinking Water
G110520229 | 520229 | Support Services | G110 | Gate 110 | 2024-05-20 | 2024-04-03 | 2024_25_P02 | 2024_25_P01 | 2024_25_Q1 | 2024_25_Q1 | Standards of service
G110520427 | 520427 | Water | G110 | Gate 110 | 2026-08-03 | 2026-01-21 | 2026_27_P05 | 2025_26_P10 | 2026_27_Q2 | 2025_26_Q4 | Standards of service
G110520459 | 520459 | Support Services | G110 | Gate 110 | 2024-05-26 | 2023-09-18 | 2024_25_P02 | 2023_24_P06 | 2024_25_Q1 | 2023_24_Q2 | Security & Resilience
G110520500 | 520500 | Wastewater | G110 | Gate 110 | 2025-06-16 | 2024-10-02 | 2025_26_P03 | 2024_25_P07 | 2025_26_Q1 | 2024_25_Q3 | Supporting Sustainable Economic Growth
G110520606 | 520606 | Water | G110 | Gate 110 | 2025-03-23 | 2024-03-28 | 2024_25_P12 | 2023_24_P12 | 2024_25_Q4 | 2023_24_Q4 | Standards of service
G110520675 | 520675 | Water | G110 | Gate 110 | 2025-07-10 | 2025-01-22 | 2025_26_P04 | 2024_25_P10 | 2025_26_Q2 | 2024_25_Q4 | Drinking Water
G110519934 | 519934 | CE&FS | G110 | Gate 110 | 2025-07-07 | 2025-01-22 | 2025_26_P04 | 2024_25_P10 | 2025_26_Q2 | 2024_25_Q4 | Long Term Water Sector Vision
G110520761 | 520761 | Support Services | G110 | Gate 110 | 2024-08-22 | 2024-03-21 | 2024_25_P05 | 2023_24_P12 | 2024_25_Q2 | 2023_24_Q4 | Standards of service
G110522707 | 522707 | Water | G110 | Gate 110 | 2024-10-31 | 2024-08-08 | 2024_25_P07 | 2024_25_P05 | 2024_25_Q3 | 2024_25_Q2 | Standards of service
G110522742 | 522742 | Wastewater | G110 | Gate 110 | 2024-10-18 | 2024-07-24 | 2024_25_P07 | 2024_25_P04 | 2024_25_Q3 | 2024_25_Q2 | Standards of service
G110523226 | 523226 | Support Services | G110 | Gate 110 | 2026-02-01 | 2025-06-25 | 2025_26_P11 | 2025_26_P03 | 2025_26_Q4 | 2025_26_Q1 | Standards of service
G110523234 | 523234 | Support Services | G110 | Gate 110 | 2027-06-27 | 2026-12-09 | 2027_28_P03 | 2026_27_P09 | 2027_28_Q1 | 2026_27_Q3 | Security & Resilience
G110523508 | 523508 | Wastewater | G110 | Gate 110 | 2025-01-20 | 2024-07-24 | 2024_25_P10 | 2024_25_P04 | 2024_25_Q4 | 2024_25_Q2 | Standards of service
G110524093 | 524093 | CE&FS | G110 | Gate 110 | 2026-01-26 | 2025-05-14 | 2025_26_P10 | 2025_26_P02 | 2025_26_Q4 | 2025_26_Q1 | Climate Change, Adaptation and Mitigation
G110524269 | 524269 | CE&FS | G110 | Gate 110 | 2026-06-28 | 2025-10-01 | 2026_27_P03 | 2025_26_P07 | 2026_27_Q1 | 2025_26_Q3 | Climate Change, Adaptation and Mitigation
G110524492 | 524492 | CE&FS | G110 | Gate 110 | 2026-04-02 | 2025-08-06 | 2026_27_P01 | 2025_26_P05 | 2026_27_Q1 | 2025_26_Q2 | Climate Change, Adaptation and Mitigation
G110524913 | 524913 | Support Services | G110 | Gate 110 | 2024-07-25 | 2024-02-21 | 2024_25_P04 | 2023_24_P11 | 2024_25_Q2 | 2023_24_Q4 | Standards of service
G110524914 | 524914 | Support Services | G110 | Gate 110 | 2024-07-25 | 2024-03-14 | 2024_25_P04 | 2023_24_P12 | 2024_25_Q2 | 2023_24_Q4 | Standards of service
G110524939 | 524939 | Support Services | G110 | Gate 110 | 2024-07-25 | 2024-03-14 | 2024_25_P04 | 2023_24_P12 | 2024_25_Q2 | 2023_24_Q4 | Standards of service
G110525189 | 525189 | Wastewater | G110 | Gate 110 | 2025-01-31 | 2024-03-28 | 2024_25_P10 | 2023_24_P12 | 2024_25_Q4 | 2023_24_Q4 | Standards of service
G110525206 | 525206 | Water | G110 | Gate 110 | 2026-10-01 | 2026-01-19 | 2026_27_P07 | 2025_26_P10 | 2026_27_Q3 | 2025_26_Q4 | Standards of service
G110525281 | 525281 | CE&FS | G110 | Gate 110 | 2025-06-02 | 2024-09-18 | 2025_26_P03 | 2024_25_P06 | 2025_26_Q1 | 2024_25_Q2 | Climate Change, Adaptation and Mitigation
G110526537 | 526537 | Wastewater | G110 | Gate 110 | 2025-09-22 | 2025-05-14 | 2025_26_P06 | 2025_26_P02 | 2025_26_Q2 | 2025_26_Q1 | Standards of service
G110526670 | 526670 | Water | G110 | Gate 110 | 2025-09-19 | 2025-01-22 | 2025_26_P06 | 2024_25_P10 | 2025_26_Q2 | 2024_25_Q4 | Standards of service
G110526838 | 526838 | Support Services | G110 | Gate 110 | 2025-04-24 | 2024-08-12 | 2025_26_P01 | 2024_25_P05 | 2025_26_Q1 | 2024_25_Q2 | Standards of service
G110526984 | 526984 | Wastewater | G110 | Gate 110 | 2025-12-15 | 2026-05-04 | 2025_26_P09 | 2026_27_P02 | 2025_26_Q3 | 2026_27_Q1 | Standards of service
G110527220 | 527220 | Support Services | G110 | Gate 110 | 2024-04-22 | 2023-10-19 | 2024_25_P01 | 2023_24_P07 | 2024_25_Q1 | 2023_24_Q3 | Standards of service
G110527305 | 527305 | Wastewater | G110 | Gate 110 | 2025-09-29 | 2025-02-19 | 2025_26_P06 | 2024_25_P11 | 2025_26_Q2 | 2024_25_Q4 | Standards of service
G110527413 | 527413 | Water | G110 | Gate 110 | 2025-10-03 | 2025-04-02 | 2025_26_P07 | 2025_26_P01 | 2025_26_Q3 | 2025_26_Q1 | Drinking Water
G110528014 | 528014 | Water | G110 | Gate 110 | 2025-05-26 | 2025-03-19 | 2025_26_P02 | 2024_25_P12 | 2025_26_Q1 | 2024_25_Q4 | Standards of service
G110528068 | 528068 | Water | G110 | Gate 110 | 2025-02-24 | 2024-10-16 | 2024_25_P11 | 2024_25_P07 | 2024_25_Q4 | 2024_25_Q3 | Standards of service
G110528241 | 528241 | Support Services | G110 | Gate 110 | 2024-12-23 | 2024-03-28 | 2024_25_P09 | 2023_24_P12 | 2024_25_Q3 | 2023_24_Q4 | Standards of service
G110528868 | 528868 | Water | G110 | Gate 110 | 2026-12-07 | 2026-06-10 | 2026_27_P09 | 2026_27_P03 | 2026_27_Q3 | 2026_27_Q1 | Standards of service
G110529261 | 529261 | Water | G110 | Gate 110 | 2025-05-12 | 2025-04-16 | 2025_26_P02 | 2025_26_P01 | 2025_26_Q1 | 2025_26_Q1 | Standards of service
G110530690 | 530690 | Wastewater | G110 | Gate 110 | 2025-09-14 | 2025-08-06 | 2025_26_P06 | 2025_26_P05 | 2025_26_Q2 | 2025_26_Q2 | Standards of service
G110532423 | 532423 | Wastewater | G110 | Gate 110 | 2026-04-23 | 2025-04-30 | 2026_27_P01 | 2025_26_P01 | 2026_27_Q1 | 2025_26_Q1 | Standards of service
G110532714 | 532714 | Water | G110 | Gate 110 | 2025-03-31 | 2024-09-18 | 2024_25_P12 | 2024_25_P06 | 2024_25_Q4 | 2024_25_Q2 | Standards of service
G110532730 | 532730 | Water | G110 | Gate 110 | 2025-02-16 | 2024-05-15 | 2024_25_P11 | 2024_25_P02 | 2024_25_Q4 | 2024_25_Q1 | Standards of service
G110533107 | 533107 | Water | G110 | Gate 110 | 2025-03-31 | 2024-07-24 | 2024_25_P12 | 2024_25_P04 | 2024_25_Q4 | 2024_25_Q2 | Standards of service
G110533223 | 533223 | Water | G110 | Gate 110 | 2025-03-31 | 2024-03-28 | 2024_25_P12 | 2023_24_P12 | 2024_25_Q4 | 2023_24_Q4 | Standards of service
G110534910 | 534910 | Water | G110 | Gate 110 | 2025-05-16 | 2024-10-02 | 2025_26_P02 | 2024_25_P07 | 2025_26_Q1 | 2024_25_Q3 | Standards of service
G110534911 | 534911 | Water | G110 | Gate 110 | 2025-10-16 | 2025-02-10 | 2025_26_P07 | 2024_25_P11 | 2025_26_Q3 | 2024_25_Q4 | Standards of service
G110535840 | 535840 | Support Services | G110 | Gate 110 | 2027-11-18 | 2026-01-21 | 2027_28_P08 | 2025_26_P10 | 2027_28_Q3 | 2025_26_Q4 | Standards of service
G110536455 | 536455 | Water | G110 | Gate 110 | 2026-05-11 | 2025-11-26 | 2026_27_P02 | 2025_26_P08 | 2026_27_Q1 | 2025_26_Q3 | Standards of service
G110537270 | 537270 | Support Services | G110 | Gate 110 | 2025-06-11 | 2024-09-26 | 2025_26_P03 | 2024_25_P06 | 2025_26_Q1 | 2024_25_Q2 | Security & Resilience

## G9 - Growth
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2024
SECTION G: INVESTMENT MONITORING
Table G9: Growth
|  |  |  | Actual and Forecast | [5 empty] | Confidence Grades
Line | Description | Units | Field | Actual Year | Actual Year | Report Year | Forecast Year | Forecast Year | Forecast Year | Actual Year | Actual Year | Report Year | Forecast Year | Forecast Year | Forecast Year
Ref. |  |  | Type
|  |  |  | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27
1 | Growth expenditure (gross)
G9.1 | Expenditure for Reasonable Cost Contributions - household - water | £m | I | 10.1453 | 10.3907 | 8.0763 | 12.7397 | 11.3297 | 11.6242 | A1 | A1 | A1 | A1 | A1 | A1
G9.2 | Expenditure for Reasonable Cost Contributions - non-household - water | £m | I | -0.047478 | -0.12103 | -0.0050961 | 0.050174 | 0.050174 | 0.045993 | A1 | A1 | A1 | A1 | A1 | A1
G9.3 | Total expenditure on Reasonable Cost Contributions - water | £m | C | 10.0979 | 10.2697 | 8.0712 | 12.7899 | 11.3799 | 11.6702
G9.4 | Expenditure for Reasonable Cost Contributions - household - wastewater | £m | I | 14.795 | 22.896 | 25.0389 | 28.5929 | 21.4155 | 26.7017 | A1 | A1 | A1 | A1 | A1 | A1
G9.5 | Expenditure for Reasonable Cost Contributions - non-household - wastewater | £m | I | -0.0018045 | -0.0018652 | -0.0040218 | 0.018258 | 0.018258 | 0.016736 | A1 | A1 | A1 | A1 | A1 | A1
G9.6 | Total expenditure on Reasonable Cost Contributions - wastewater | £m | C | 14.7932 | 22.8942 | 25.0349 | 28.6111 | 21.4337 | 26.7185
G9.7 | Total expenditure on Reasonable Cost Contributions - water and wastewater | £m | C | 24.8911 | 33.1639 | 33.1061 | 41.401 | 32.8137 | 38.3887
G9.8 | Expenditure on Part 3 Strategic Capacity - water | £m | I | 10.1519 | 16.0706 | 13.1753 | 8.5799 | 4.3372 | 3.7288 | A1 | A1 | A1 | A1 | A1 | A1
G9.9 | Expenditure on Part 3 Strategic Capacity - wastewater | £m | I | 1.9824 | 3.7966 | 9.9095 | 16.4788 | 26.5409 | 22.1249 | A1 | A1 | A1 | A1 | A1 | A1
G9.10 | Expenditure on Part 3 Strategic Capacity - foul sewage | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1
G9.11 | Expenditure on Part 3 Strategic Capacity - surface water | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1
G9.12 | Total expenditure on Part 3 Strategic Capacity - water, wastewater and surface water | £m | C | 12.1343 | 19.8672 | 23.0848 | 25.0587 | 30.8781 | 25.8537
G9.13 | Expenditure on Part 4 assets - water | £m | I | 0.96259 | 0.62125 | 1.2888 | 9.7487 | 9.8694 | 5.8744 | A1 | A1 | A1 | A1 | A1 | A1
G9.14 | Expenditure on Part 4 assets - wastewater | £m | I | 35.0858 | 45.9955 | 43.4599 | 16.7687 | 46.0758 | 40.8236 | A1 | A1 | A1 | A1 | A1 | A1
G9.15 | Total expenditure on Part 4 assets - water and wastewater | £m | C | 36.0484 | 46.6168 | 44.7487 | 26.5173 | 55.9452 | 46.698
G9.16 | Total gross expenditure on growth - (RCC + Part 3 strategic capacity + Part 4) | £m | C | 73.0737 | 99.6479 | 100.9396 | 92.977 | 119.637 | 110.9404
2 | Service relocations
G9.17 | Service relocations water | £m | I | 3.5084 | 3.3781 | 3.9237 | 19.8075 | 14.826 | 10.0515 | A1 | A1 | A1 | A1 | A1 | A1
G9.18 | Service relocations wastewater | £m | I | 0.77394 | 0.33686 | 0.2878 | 3.3041 | 0.76499 | 0.70535 | A1 | A1 | A1 | A1 | A1 | A1
G9.19 | Service relocations foul sewage | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1
G9.20 | Service relocations surface water | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1
G9.21 | Service relocations water contributions | £m | I | -6.745 | -3.0716 | -2.7845 | -6.2441 | -6.2441 | -6.2441 | A1 | A1 | A1 | B1 | B1 | B1
G9.22 | Service relocations wastewater contributions | £m | I | -3.4747 | -0.30379 | -0.20821 | -0.46691 | -0.46691 | -0.46691 | A1 | A1 | A1 | B1 | B1 | B1
G9.23 | Service relocations foul sewage contributions | £m | I
G9.24 | Service relocations surface water contributions | £m | I
G9.25 | Net service relocations | £m | C | -5.9373 | 0.3395 | 1.2188 | 16.4006 | 8.88 | 4.0458
3 | Gross growth expenditure
G9.26 | Total gross expenditure on growth and service relocations | £m | C | 67.1364 | 99.9874 | 102.1584 | 109.3777 | 128.517 | 114.9862
G9.27 | Total gross expenditure on growth and service relocations (excluding reasonable cost contributions) | £m | C | 42.2453 | 66.8235 | 69.0523 | 67.9767 | 95.7033 | 76.5975
4 | Growth income (Infrastructure charge)
G9.28 | Water household infrastructure charge income | £m | I | 9.7321 | 9.6722 | 6.939 | 10.988 | 11.087 | 11.186 | A1 | A1 | A1 | A1 | A1 | A1
G9.29 | Water non-household infrastructure charge income | £m | I | 0.23477 | 0.23807 | 0.22 | 0.206 | 0.208 | 0.209 | A1 | A1 | A1 | A1 | A1 | A1
G9.30 | Wastewater household infrastructure charge income | £m | I | 9.0469 | 9.488 | 6.245 | 10.438 | 10.532 | 10.627 | A1 | A1 | A1 | A1 | A1 | A1
G9.31 | Wastewater non-household infrastructure charge income | £m | I | 0.017365 | 0.011622 | 0.165 | 0.058 | 0.059 | 0.059 | A1 | A1 | A1 | A1 | A1 | A1
G9.32 | Total infrastructure charge income | £m | C | 19.0311 | 19.4098 | 13.569 | 21.69 | 21.886 | 22.081
5 | Growth expenditure (net of income)
G9.33 | Total net growth expenditure | £m | C | 48.1052 | 80.5775 | 88.5894 | 87.6877 | 106.631 | 92.9052
G9.34 | Total net growth expenditure (excluding reasonable cost contributions) | £m | C | 23.2142 | 47.4137 | 55.4833 | 46.2867 | 73.8173 | 54.5165
6 | Growth - properties and populations
G9.35 | Number of new household properties connected to the water network | Nr | I | 23172 | 22620 | 14272 | 22599 | 22803 | 23008 | A1 | A1 | A1 | A1 | A1 | A1
G9.36 | Number of new non-household properties connected to the water network | Nr | I | 559 | 27 | 452 | 423 | 427 | 431 | A1 | A1 | A1 | A1 | A1 | A1
G9.37 | Total number of new properties connected to the water network | Nr | C | 23731 | 22647 | 14724 | 23022 | 23230 | 23439
G9.38 | Number of new household properties connected to the foul sewage network | Nr | I | 21540 | 21164 | 12845 | 21469 | 21663 | 21858 | A1 | A1 | A1 | A1 | A1 | A1
G9.39 | Number of new non-household properties connected to the foul sewage network | Nr | I | 41 | 544 | 339 | 120 | 121 | 122 | A1 | A1 | A1 | A1 | A1 | A1
G9.40 | Total number of new properties connected to the foul sewage network | Nr | C | 21581 | 21708 | 13184 | 21589 | 21784 | 21980
G9.41 | Number of new household properties connected to the surface water network | Nr | I | 0 | 0 | - | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1
G9.42 | Number of new non-household properties connected to the surface water network | Nr | I | 0 | 0 | - | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1
G9.43 | Total number of new properties connected to the surface water network | Nr | C | 0 | 0 | 0 | 0 | 0 | 0
G9.44 | Number of new household properties receiving reasonable cost contributions - water | Nr | I | 28296 | 28675 | 18965 | 29916 | 26605 | 27297 | A1 | A1 | A1 | A1 | A1 | A1
G9.45 | Number of new non-household properties receiving reasonable cost contributions - water | Nr | I | 12 | -343 | -12 | 118 | 118 | 108 | A1 | A1 | A1 | A1 | A1 | A1
G9.46 | Total number of properties receiving reasonable cost contributions - water Part 2 | Nr | C | 28308 | 28332 | 18953 | 30034 | 26723 | 27405
G9.47 | Number of new household properties receiving reasonable cost contributions - wastewater | Nr | I | 14580 | 28418 | 31681 | 36178 | 27097 | 33785 | A1 | A1 | A1 | A1 | A1 | A1
G9.48 | Number of new non-household properties receiving reasonable cost contributions - wastewater | Nr | I | 95 | -2 | -5 | 23 | 23 | 21 | A1 | A1 | A1 | A1 | A1 | A1
G9.49 | Total number of properties receiving reasonable cost contributions - wastewater Part 2 | Nr | C | 14675 | 28416 | 31676 | 36201 | 27120 | 33806
G9.50 | Number of household property infrastructure charge payments - water | Nr | I | 23172 | 22620 | 14272 | 22599 | 22803 | 23008 | A1 | A1 | A1 | A1 | A1 | A1
G9.51 | Number of non-household property infrastructure charge payments - water | Nr | I | 559 | 27 | 452 | 423 | 427 | 431 | A1 | A1 | A1 | A1 | A1 | A1
G9.52 | Total number of infrastructure charge payments - water | Nr | C | 23731 | 22647 | 14724 | 23022 | 23230 | 23439
G9.53 | Number of household property infrastructure charge payments - wastewater | Nr | I | 21540 | 21164 | 12845 | 21469 | 21663 | 21858 | A1 | A1 | A1 | A1 | A1 | A1
G9.54 | Number of non-household property infrastructure charge payments - wastewater | Nr | I | 41 | 544 | 339 | 120 | 121 | 122 | A1 | A1 | A1 | A1 | A1 | A1
G9.55 | Total number of infrastructure charge payments - wastewater | Nr | C | 21581 | 21708 | 13184 | 21589 | 21784 | 21980
G9.56 | Additional population equivalent served from new Part 4 investment - water | Pe | I | 400 | 10 | 0 | 0 | 0 | 0 | B1 | B1 | B1 | B1 | B1 | B1
G9.57 | Additional population equivalent served from new Part 4 investment - wastewater | Pe | I | 1391 | 15673 | 4171 | 18000 | 12698 | 32912 | B1 | B1 | B1 | B1 | B1 | B1
Prepared by: …………………………………….……………………………….. |  |  | Date: 07/10/2024
Checked by: …………………………….………………………………………….. |  |  | Date: 07/10/2024
Authorised by: …...........……………………...……............ |  |  | Date: 07/10/2024

## G10 - Inflation
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2024
SECTION G: INVESTMENT MONITORING
Table G10: Inflation assumptions
Line Ref. | Description | Units | Field Type | Actual Year 2017-18 | Actual Year 2018-19 | Actual Year 2019-20 | Actual Year 2020-21 | Actual Year 2021-22 | Actual Year 2022-23 | Actual Year 2023-24 | Forecast Year 2024-25 | Forecast Year 2025-26 | Forecast Year 2026-27 | Forecast annual average 2027-28 to 2032-33 | Forecast annual average 2033-34 to 2038-39 | Forecast annual average 2039-40 to 2044-45 | Forecast annual average 2045-46 to 2050-51
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Cost Inflation
G10.1 | Cost inflation (RPI until 2021 and CPI from 2021-22; financial year average) | % | I |  | 3.06% | 2.588% | 1.213% | 3.98% | 10.06% | 5.67% | 2.4% | 2.6% | 2% | 2% | 2% | 2% | 2%
G10.2 | Inflation index (2017-18 base year) | Nr. | I/C | 1 | 1.0306 | 1.0573 | 1.0701 | 1.1127 | 1.2246 | 1.2941 | 1.3251 | 1.3596 | 1.3868 | 1.4871 | 1.6748 | 1.8861 | 2.124
2 | Capital Price Inflation
G10.3 | Capital price inflation | % | I |  | 3.06% | 2.588% | 1.213% | 5.98% | 11.26% | 6.47% | 3.3% | 3% | 2% | 2% | 2% | 2% | 2%
G10.4 | Capital price inflation factor | Nr. | I/C | 1 | 1.0306 | 1.0573 | 1.0701 | 1.1341 | 1.2618 | 1.3434 | 1.3878 | 1.4294 | 1.458 | 1.5635 | 1.7608 | 1.9829 | 2.2331
Prepared by: ……………………………………………...….. |  | Date: 07/10/2024
Checked by: ……………………………………………...….. |  | Date: 07/10/2024
Authorised by: …...........……………………...……............ |  | Date: 07/10/2024